## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-766
Joint Standoff Weapon - Baseline Variant and Unitary Warhead Variant (JSOW)
As of FY 2016 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 13
Track to Budget 16
Cost and Funding 17
Low Rate Initial Production 35
Foreign Military Sales 36
Nuclear Costs 37
Unit Cost 38
Cost Variance 46
Contracts 52
Deliveries and Expenditures 54
Operating and Support Cost 55

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Joint Standoff Weapon - Baseline Variant and Unitary Warhead Variant (JSOW)
DoD Component
Navy
Responsible Office
CAPT Jaime Engdahl, USN Precision Strike Weapons, PMA 201 Bldg 2272
47123 Buse Road, Room 448 Patuxent River, MD 20670-1547
jaime.engdahl@navy.mil
Phone: | 301-757-7477
Fax: | 301-757-7435
DSN Phone: | 757-7477
DSN Fax:
Date Assigned: | January 16, 2014
References
BASELINE/BLU-108
SAR Baseline (Production Estimate)
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated July 10, 1999
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated December 20, 2004
UNITARY
SAR Baseline (Production Estimate)
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated December 20, 2004
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated August 5, 2009

## Table 6
Mission and Description
The Joint Standoff Weapon (JSOW) is an air-to-ground weapon designed to attack a variety of targets during day, night, and adverse weather conditions. JSOW enhances aircraft survivability by providing the capability for launch aircraft to standoff outside the range of most target area surface-to-air threat systems. The JSOW launch-and-leave capability allows several target kills per aircraft sortie. The common JSOW variant nomenclature is JSOW-A (Baseline), JSOW-A-1, JSOW-B (BLU
-108), JSOW-C (Unitary), and JSOW-C-1 (Network Enabled Weapon Moving Maritime Target Capability).
The JSOW program developed a Baseline weapon for use against fixed, area targets. The JSOW Baseline variant includes a kinematically efficient airframe and integrated Global Positioning System/Inertial Navigation System capability, and a BLU- 97/B submunition payload. The JSOW-A-1 configuration carries a BLU-111 warhead and is being marketed by Raytheon to FMS customers. The JSOW-B variant incorporates the Sensor Fuzed Weapon submunition (BLU-108) into the baseline vehicle. The JSOW-B variant provides a standoff delivery capability against massed armor and land combat vehicles.
JSOW-C and C-1 variants both use the Unitary lethal package, termed Bomb Royal Ordnance Augmented Charge (BROACH), which is produced by BAE Systems. The BROACH incorporates an advanced multi-stage warhead, which allows the warfighter to attack blast/frag sensitive and hardened point targets. JSOW-C uses an Imaging Infrared (IIR) seeker with embedded Autonomous Targeting Acquisition software, increasing accuracy and lethality. The IIR affords the mission planner precise aimpoint selection and target discrimination. An anti-tamper/anti-spoofing capability was inserted in the guidance electronics unit with FY 2006 production. The JSOW-C-1 adds a weapon data link and seeker upgrade to attack moving maritime targets in addition to the JSOW-C stationary land target mission set.
Through adherence to international standards for weapons interfaces and minimized weight and dimension considerations, JSOW is compatible with Navy, Air Force and North Atlantic Treaty Organization aircraft. JSOW is a Navy-led, joint program.

## Table 7
Executive Summary
This is the final SAR submission for the JSOW program because future procurement has been terminated after FY 2015.
Based on the FY 2016 PB decision of the DoD that JSOW-C-1 procurement is terminated after FY 2015, the program will develop a transition plan to begin a smooth and orderly shutdown of JSOW production and transition of the program to operations and sustainment. This plan will focus on the following main areas: completion of JSOW-C-1 Operational Test, use of RDT&E and procurement dollars in FY 2016 through FY 2019 to support Captive Air Training Missiles, Telemetry Instrumentation Kits, testing and training activities, and ongoing sustainment activities to support all JSOW inventory through 2036, all of which fulfill current U.S. Navy Munitions Requirements and represent a significant value to the Government.
JSOW is in the post Milestone III production phase transitioning to sustainment, with final JSOW-A dispenser variant deliveries completed in July 2007; JSOW-C Unitary variant production completed deliveries in June 2010. JSOW-C-1 deliveries commenced October 2010 with 1,067 weapons delivered through FY 2012 (FRP-8). FY 2013 (FRP-9) and FY 2014 (FRP-10) production lots are currently on contract with an anticipated third quarter FY 2015 contract award for FY 2015 (FRP-11). The JSOW program continues to meet all CPD, KPP, Key System Attributes, and APB schedule and performance thresholds.
JSOW-C-1 is an Engineering Change Proposal modification to the JSOW-C Unitary variant. JSOW-C-1 will provide the U.S. Navy with an Anti-Surface Warfare stand-off weapon that can precisely strike Moving Maritime Targets. The JSOW-C-1 program has successfully executed Developmental Test and Integrated Test phases, scoring all direct hits, and demonstrating aimpoint accuracy for Moving Maritime Targets and retention of the Stationary Land Target capability. JSOW
-C-1 will complete Operational Test in 2015 and is expected to achieve IOC in 2016 with threshold platform F/A-18E/F H10E System Configuration Set.
Due to procurement termination, the FY 2016 PB weapon production quantities were zeroed for both the JSOW Baseline/BLU-108 and JSOW-C-1 Unitary variants. This has resulted in significant and critical Nunn-McCurdy unit cost breaches. Specifically, the Baseline variant PAUC increased 20% above the current APB; the Unitary variant PAUC increased 46% and the Unitary variant APUC increased 28% above the current APB. The quantity reductions were the result of a DoD weapons/target pairing assessment that deemed that with the delivery of weapons from the FY 2015 procurement contract sufficient JSOW-C-1 assets would be in inventory to address the target set requirements allocated to the Department of the Navy rather than any program execution or cost concerns. The information required by 10 USC 2433(g)
(1) (A) - (F) is included in this report. In accordance with 10 USC 2433(g)(2), the Secretary of Defense certification is not required to be submitted for termination or cancellation of a program.
A Program Deviation Report (PDR) was signed by the Program Manager on February 23, 2015. The Program Executive Officer for Strike Weapons and Unmanned Aviation endorsed and forwarded the PDR to the Milestone Decision Authority, the Assistant Secretary of the Navy for Research, Development and Acquisition, on March 3, 2015.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
BASELINE/BLU-108
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
JSOW Baseline/BLU-108 unit cost breaches are the result
of termination of JSOW procurement, which reduces the overall quantity by 817 weapons in comparison to the APB.
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC Significant APUC None
Original UCR Baseline
PAUC None
APUC None
UNITARY
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
JSOW Unitary unit cost breaches are the result of termination of JSOW procurement, which reduces the overall quantity by 3,815 weapons in comparison to the APB.
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC Critical APUC Critical
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule

## Table 10
BASELINE/BLU-108
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone I | Jun 1989 | Jun 1989 | Dec 1989 | Jun 1989
DEMVAL Contract Award | Jun 1989 | Jun 1989 | Dec 1989 | Jun 1989
Early Operational Assessment (OT-I)
Start | Mar 1991 | Mar 1991 | Sep 1991 | Mar 1991
Complete (Report) | Oct 1991 | Oct 1991 | Apr 1992 | Oct 1991
Milestone II | Apr 1992 | Apr 1992 | Oct 1992 | Jun 1992
E&MD Contract Award | May 1992 | May 1992 | Nov 1992 | Jun 1992
BLU-108 SYSTEM
Milestone II | Apr 1995 | Apr 1995 | Oct 1995 | Jun 1992
Pre-E&MD Contract Award | May 1993 | May 1993 | Nov 1993 | May 1993
Preliminary Fit Checks | Jun 1993 | Jun 1993 | Dec 1993 | Jun 1993
Eng Dev Test Vehicle Delivery | Feb 1994 | Feb 1994 | Aug 1994 | Feb 1994
F-16 Flight Tests | Mar 1994 | Mar 1994 | Sep 1994 | Mar 1994
F-15E Flight Tests | May 1994 | May 1994 | Nov 1994 | May 1994
Systems Design Review | Apr 1995 | Apr 1995 | Oct 1995 | Jun 1994
E&MD Contract Modification | Jun 1995 | Jun 1995 | Dec 1995 | Jun 1995
Preliminary Design Review | Oct 1995 | Oct 1995 | Apr 1996 | Oct 1995
DT&E
Start | Dec 1995 | Dec 1995 | Jun 1996 | Feb 1996
Complete (Report) | Jun 1998 | Jun 1998 | Dec 1998 | Sep 1998
Operational Assessment
Start | Dec 1995 | Dec 1995 | Jun 1996 | Apr 1996
Complete (Report) | Sep 1996 | Sep 1996 | Mar 1997 | Feb 1997
Critical Design Review | Oct 1996 | Oct 1996 | Apr 1997 | Apr 1997
LRIP Contract Option Exercised | Jan 2000 | Jan 2000 | Jul 2000 | Dec 1998
LRIP First Delivery | Jul 2001 | Jul 2001 | Jan 2002 | Jul 2000
Milestone III | Oct 2001 | N/A | N/A | N/A
Initial Operational Capability | Sep 2002 | N/A | N/A | N/A
Preliminary Design Review | Nov 1992 | Nov 1992 | May 1993 | Jan 1993
Critical Design Review | Dec 1994 | Dec 1994 | Jun 1995 | Apr 1995
Functional Configuration Audit | Oct 1995 | Oct 1995 | Apr 1996 | Dec 1995
Production Verification Review | Apr 1996 | Apr 1996 | Oct 1996 | Jan 1996
IOT&E (OT-IIA)

## Table 11
Start | Dec 1995 | Dec 1995 | Jun 1996 | Feb 1996
Complete (Report) | Jul 1996 | Jul 1996 | Jan 1997 | Dec 1996
TECHEVAL (DT-IIC)
Start | Nov 1995 | Nov 1995 | May 1996 | Feb 1996
Complete (Report) | Jul 1996 | Jul 1996 | Jan 1997 | Dec 1996
Production Readiness Review | Jun 1996 | Jun 1996 | Dec 1996 | Oct 1996
LRIP Contract Option Exercised | Oct 1996 | Oct 1996 | Apr 1997 | Feb 1997
OPEVAL (OT-IIB)
Start | Aug 1996 | Aug 1996 | Feb 1997 | Feb 1997
Complete (Report) | Jul 1997 | Jul 1997 | Jan 1998 | Sep 1997
LRIP First Delivery | May 1998 | May 1998 | Nov 1998 | May 1998
Milestone III | Jul 1998 | Jul 1998 | Jan 1999 | Oct 1998
IOC | Jul 1998 | Jul 1998 | Jan 1999 | Jan 1999
Organizational Level Support | Apr 2000 | Apr 2000 | Oct 2000 | Jun 2000
Intermediate Level Support | Jul 2000 | Jul 2000 | Jan 2001 | Sep 2000
Change Explanations
None
Acronyms and Abbreviations
DEMVAL - Demonstration and Validation DEV - Development
DT - Developmental Test
DT&E - Developmental Test and Evaluation
E&MD - Engineering and Manufacturing Development IOT&E - Initial Operational Test and Evaluation OPEVAL - Operational Evaluation
OT - Operational Test
TECHEVAL - Technical Evaluation

## Table 12
UNITARY
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone II | Apr 1995 | Apr 1995 | Oct 1995 | Apr 1995
E&MD Contract Award | Jul 1995 | Jul 1995 | Jan 1996 | Aug 1995
Critical Process Review #1 | Feb 1996 | Feb 1996 | Aug 1996 | Jun 1996
OPEVAL (OT-IIB)
Start | Dec 2003 | Dec 2003 | Jun 2004 | Dec 2003
Milestone III | Dec 2004 | Dec 2004 | Jun 2005 | Dec 2004
IOC | Aug 2004 | Aug 2004 | Feb 2005 | Feb 2005
Change Explanations
None
Acronyms and Abbreviations
E&MD - Engineering and Manufacturing Development OPEVAL - Operational Evaluation
OT - Operational Test

## Table 13
Performance
BASELINE/BLU-108
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Survivability
IAW Sys Spec (SD - 901-1) | IAW Sys Spec (SD- 901-1) | IAW Sys Spec (SD- 901-1) | IAW Sys Spec (SD - 901-1) | IAW Sys Spec (SD - 901-1)
Range (nm from launch at specified conditions)
Low Altitude (nm)
>or=15 (200 ft MSL, .8 IMN) | >or=15 (200 ft MSL, .8 IMN) | >or=12 (500 ft MSL, .8 IMN) | 12 (500 ft MSL, .8 IMN) | >or=15 (200 ft MSL, .8 IMN)
High (nm @ 30K ft MSL, .8 IMN)
>50 | >50 | >40 | 50 | >50
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Operational Requirements Document (ORD) dated December 10, 2002
Change Explanations
None
Acronyms and Abbreviations
ft - feet
IAW - In Accordance With IMN - Indicated Mach Number K - Thousand
MSL - Mean Sea Level nm - Nautical Miles Spec - Specification Sys - System

## Table 14
UNITARY
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Survivability
IAW Sys spec SD-901 -1 | IAW Sys spec SD-901 -1 | IAW Sys spec SD- 901-1 | IAW Sys spec SD-901-1 | IAW Sys spec SD-901-1
Accuracy (CEP)
Weapon (ft)
10 | 10 | 10 | 4.49 | 4.49
Weapon (Air Vehicle) (ft)
70 | 70 | 91 | 35.4 | 35.4
Range (nm from launch at specified conditions)
Low Altitude (nm)
>or=15 (200 ft MSL, .8 IMN) | >or=15 (200 ft MSL, .8 IMN) | >or=12 (500 ft MSL, .8 IMN) | 12 nm (500 ft MSL, 0.8 IMN) | 12 nm (500 ft MSL, 0.8 IMN)
High (nm @ 30K ft MSL, .8 IMN)
>50 | >50 | >40 | 50 nm (25K ft MSL, 0.8 IMN) | 50 nm (25K ft MSL, 0.8 IMN)
Accuracy, (SEP) Weapon (ft)
N/A | 10 | 20 | 2.2 ft (DT1) 3.6 ft (DT2) 2.2 ft (IT1) 15.5 ft (IT2) | 13 ft SEP (Based on Simulation Data)
Weapon Data Link
N/A | 3rd Party compatible waveform | IFTU from F/A-18 E/F | Demonstrated IFTU capability with F/A-18E/F during developmental and integration testing. 3rd Party compatible waveform demonstrated with the LSRS platform during the Joint Capability Test Demonstration. Confirmed during Trident Warrior 2013 testing with E2D. | Demonstrated IFTU capability with F/A-18E/F during developmental and integration testing. 3rd Party compatible waveform demonstrated with the LSRS platform during the Joint Capability Test Demonstration. Confirmed during Trident Warrior 2013 testing with E2D.
Material Availability (Sustainment)
N/A | >or=.95 | >or=.95 | 99.5 | 99.5
Net-Ready KPP
N/A | Std Definition | Std Definition | Compliant by design. Received NMSC Stage 4. Received Navy SPAWAR certification for use with F/A-18E/F H10E SCS. | Compliant by design. Received NMSC Stage 4. Navy SPAWAR and Joint Interoperability Certification testing is scheduled to complete with F/A-18E/F H10E SCS.

## Table 15
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Capability Production Document (CPD) dated February 2, 2009
Change Explanations
None
Acronyms and Abbreviations
CEP - Circular Error Probable DT - Developmental Test
ft - Feet
IAW - In Accordance With IFTU - In-Flight Target Update IMN - Indicated Mach Number IT - Integration Test
K - Thousand
KPP - Key Performance Parameter
LSRS - Littoral Surveillance Radar System MSL - Mean Sea Level
nm - nautical mile
NMSC - Navy-Marine Corps Spectrum Center SCS - System Configuration Set
SEP - Spherical Error Probable
SPAWAR - Space & Naval Warfare Systems Command Spec - Specification
Std - Standard Sys - System

## Table 16
Track to Budget
BASELINE/BLU-108
RDT&E
Appn |  |  | BA | PE
Navy |  | 1319 05 |  | 0604727N
|  | Project |  | Name
|  | 2068 |  | Joint Standoff Weapon (Navy) |  | (Sunk)
Air Force |  | 3600 05 |  | 0604727F
|  | Project |  | Name
|  | 1000 |  | Joint Standoff Weapon (Air Force) |  | (Sunk)
Procurement
Appn |  |  | BA | PE
Navy |  | 1507 02 |  | 0204162N
|  | Line Item |  |  | Name
|  | 2230 |  | JSOW |  | (Sunk)
Navy |  | 1507 06 |  | 0204162N
|  | Line Item |  |  | Name
|  | 6120 |  | Spares and Repair Parts (Shared) (Sunk)
Air Force |  | 3020 | 2 | 0207324F
Line Item |  |  |  | Name
JSOW |  |  |  | JSOW Missile Procurement Air Force |  | (Shared) (Sunk)
UNITARY
RDT&E
Appn |  |  | BA | PE
Navy 1319 05 0604727N
Project | Name
2068 Joint Standoff Weapon (Navy)
Procurement
Appn |  |  | BA | PE
Navy 1507 02 0204162N
Line Item Name
2230 JSOW
Navy 1507 06 0204162N
Line Item Name
6120 Spares and Repair Parts (Shared)

## Table 17
Cost and Funding
Cost Summary - Total Program
Total Acquisition Cost - Total Program
Appropriation | BY 1990 $M |  |  |  | BY 1990 $M |  | TY $M
| SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E | 836.8 |  | 887.8 | -- |  | 915.7 |  | 992.5 |  | 1052.9 |  | 1097.6
Procurement | 4685.5 |  | 2636.7 | -- |  | 1784.8 |  | 6852.4 |  | 3862.5 |  | 2502.1
Flyaway | -- |  | -- | -- |  | 1750.6 |  | -- |  | -- |  | 2454.9
Recurring | -- |  | -- | -- |  | 1445.4 |  | -- |  | -- |  | 2034.2
Non Recurring | -- |  | -- | -- |  | 305.2 |  | -- |  | -- |  | 420.7
Support | -- |  | -- | -- |  | 34.2 |  | -- |  | -- |  | 47.2
Other Support | -- |  | -- | -- |  | 31.1 |  | -- |  | -- |  | 42.5
Initial Spares | -- |  | -- | -- |  | 3.1 |  | -- |  | -- |  | 4.7
MILCON | 21.8 |  | 0 | -- |  | 0 |  | 28.6 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Total | 5544.1 |  | 3524.5 | N/A |  | 2700.5 |  | 7873.5 |  | 4915.4 |  | 3599.7

## Table 18
Cost and Funding
Cost Summary - BASELINE/BLU-108
Total Acquisition Cost - BASELINE/BLU-108
Appropriation | BY 1990 $M | [5 empty] | BY 1990 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E | 554 |  |  | 564.1 | 620.5 |  |  | 563.6 | 645 |  |  |  | 643.6 |  | 643.6
Procurement | 2990.5 |  |  | 941.7 | 1035.9 |  |  | 799.3 | 4225.1 |  |  |  | 1235.2 |  | 1016.3
Flyaway | -- |  |  | -- | -- |  |  | 778.2 | -- |  |  |  | -- |  | 989.8
Recurring | -- |  |  | -- | -- |  |  | 614.7 | -- |  |  |  | -- |  | 784.4
Non Recurring | -- |  |  | -- | -- |  |  | 163.5 | -- |  |  |  | -- |  | 205.4
Support | -- |  |  | -- | -- |  |  | 21.1 | -- |  |  |  | -- |  | 26.5
Other Support | -- |  |  | -- | -- |  |  | 20.3 | -- |  |  |  | -- |  | 25.4
Initial Spares | -- |  |  | -- | -- |  |  | 0.8 | -- |  |  |  | -- |  | 1.1
MILCON | 21.8 |  |  | 0 | -- |  |  | 0 | 28.6 |  |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | -- |  |  | 0 | 0 |  |  |  | 0 |  | 0
Total | 3566.3 |  |  | 1505.8 | N/A |  |  | 1362.9 | 4898.7 |  |  |  | 1878.8 |  | 1659.9
RDT&E | 0 | [6 empty] | 0 |  |  | 0
Procurement | 16124 | [6 empty] | 3334 |  |  | 2517
Total | 16124 | [6 empty] | 3334 |  |  | 2517
Total Quantity - BASELINE/BLU-108
Quantity |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  | Current Estimate
Quantity Notes
Current APB: 3,334 procurement missiles include 2,800 Navy Baselines, 523 Air Force Baselines, and 11 Air Force BLU- 108s.
Current Estimate: 2,517 procurement missiles include 1,983 Navy Baselines, 523 Air Force Baselines, and 11 Air Force BLU-108s.

## Table 19
Cost Summary - UNITARY
Total Acquisition Cost - UNITARY
Appropriation | BY 1990 $M | [6 empty] | BY 1990 $M |  | TY $M
| SAR Baseline Production Estimate |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 282.8 |  |  | 323.7 | 356.1 |  |  | 352.1 |  | 347.5 |  |  | 409.3 |  | 454
Procurement |  | 1695 |  |  | 1695 | 1864.5 |  |  | 985.5 |  | 2627.3 |  |  | 2627.3 |  | 1485.8
Flyaway |  | -- |  |  | -- | -- |  |  | 972.4 |  | -- |  |  | -- |  | 1465.1
Recurring |  | -- |  |  | -- | -- |  |  | 830.7 |  | -- |  |  | -- |  | 1249.8
Non Recurring |  | -- |  |  | -- | -- |  |  | 141.7 |  | -- |  |  | -- |  | 215.3
Support |  | -- |  |  | -- | -- |  |  | 13.1 |  | -- |  |  | -- |  | 20.7
Other Support |  | -- |  |  | -- | -- |  |  | 10.8 |  | -- |  |  | -- |  | 17.1
Initial Spares |  | -- |  |  | -- | -- |  |  | 2.3 |  | -- |  |  | -- |  | 3.6
MILCON |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 1977.8 |  |  | 2018.7 | N/A |  |  | 1337.6 |  | 2974.8 |  |  | 3036.6 |  | 1939.8
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The current estimate seeks to provide sufficient resources to execute the program under normal conditions, encountering average levels of technical, schedule and programmatic risk, and external interference. It is consistent with average resource expenditures on historical efforts.
Total Quantity - UNITARY
Quantity |  |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  |  | 7000 |  |  |  | 7000 |  |  |  |  | 3185
Total |  |  | 7000 |  |  |  | 7000 |  |  |  |  | 3185

## Table 20
Cost and Funding
Funding Summary - Total Program
Appropriation Summary
FY 2016 President's Budget / December 2014 SAR (TY$ M)
Appropriation | Prior | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | To Complete | Total
RDT&E | 1087.2 | 4.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.5 | 3.9 | 1097.6
Procurement | 2361.6 | 108.7 | 21.4 | 2.8 | 6.4 | 1.2 | 0 | 0 | 2502.1
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2016 Total | 3448.8 | 113.1 | 21.8 | 3.2 | 6.8 | 1.6 | 0.5 | 3.9 | 3599.7
PB 2015 Total | 3449.3 | 135.4 | 160.6 | 0.6 | 0.6 | 0.6 | 209.5 | 1493.1 | 5449.7
Delta | -0.5 | -22.3 | -138.8 | 2.6 | 6.2 | 1 | -209 | -1489.2 | -1850

## Table 21
Cost and Funding
Funding Summary - BASELINE/BLU-108
Appropriation Summary
FY 2016 President's Budget / December 2014 SA | [9 empty] | R (TY$ M)
Appropriation | Prior | FY | 2015 | FY 2016 |  | FY 2017 | FY 2018 |  | FY 2 | 19 | FY | 2020 | To Complete |  |  | Total
RDT&E | 643.6 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 643.6
Procurement | 1016.3 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 1016.3
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0
PB 2016 Total | 1659.9 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 1659.9
PB 2015 Total | 1659.9 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 213.7 |  |  | 1873.6
Delta | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | -213.7 |  |  | -213.7
Quantity Summary
FY 2016 President's Budget / December 2014 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2015 | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Production | 0 |  | 2517 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 2517
PB 2016 Total | 0 |  | 2517 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 2517
PB 2015 Total | 0 |  | 2517 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 817 |  | 3334
Delta | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | -817 |  | -817

## Table 22
Funding Summary - UNITARY
Appropriation Summary
FY 2016 President's Budget / December 2014 SAR (TY$ M)
Appropriation | Prior | FY 2015 |  | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | To Complete |  | Total
RDT&E | 443.6 | 4.4 |  | 0.4 |  | 0.4 |  | 0.4 |  | 0.4 |  | 0.5 |  | 3.9 |  | 454
Procurement | 1345.3 | 108.7 |  | 21.4 |  | 2.8 |  | 6.4 |  | 1.2 |  | 0 |  | 0 |  | 1485.8
MILCON | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2016 Total | 1788.9 | 113.1 |  | 21.8 |  | 3.2 |  | 6.8 |  | 1.6 |  | 0.5 |  | 3.9 |  | 1939.8
PB 2015 Total | 1789.4 | 135.4 |  | 160.6 |  | 0.6 |  | 0.6 |  | 0.6 |  | 209.5 |  | 1279.4 |  | 3576.1
Delta | -0.5 | -22.3 |  | -138.8 |  | 2.6 |  | 6.2 |  | 1 |  | -209 |  | -1275.5 |  | -1636.3
Funding Notes
JSOW FY 2016 PB profile reflects JSOW production termination after FY 2015.
Quantity Summary
FY 2016 President's Budget / December 2014 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2015 | FY 2016 | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | To Complete |  | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Production | 0 |  | 2985 |  | 200 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3185
PB 2016 Total | 0 |  | 2985 |  | 200 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3185
PB 2015 Total | 0 |  | 2985 |  | 200 | 200 | 0 |  | 0 |  | 0 |  | 517 |  | 3098 |  | 7000
Delta | 0 |  | 0 |  | 0 | -200 | 0 |  | 0 |  | 0 |  | -517 |  | -3098 |  | -3815

## Table 23
Cost and Funding
Annual Funding By Appropriation - BASELINE/BLU-108
Annual Funding - BASELINE/BLU-108 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1987 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1
1988 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.2
1989 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.5
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.5
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.5
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 45.8
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 58.8
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 80.9
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 104.3
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 46.9
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.2
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.2
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.4
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.1
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.9
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 449.2

## Table 24
Annual Funding - BASELINE/BLU-108 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 1990 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1987 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.1
1988 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.3
1989 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.7
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.3
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.6
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 52.7
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 71.1
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 89.9
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.8
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.5
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.8
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.4
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.1
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.7
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 399

## Table 25
Annual Funding - BASELINE/BLU-108 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.4
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.1
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 51.7
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.8
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.5
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.2
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.2
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 194.4

## Table 26
Annual Funding - BASELINE/BLU-108 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 1990 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.8
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.3
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44.5
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.3
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.4
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.8
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.1
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.2
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.2
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 164.6

## Table 27
Annual Funding - BASELINE/BLU-108 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1996 |  | -- | -- |  | -- |  | 24.3 |  | 24.3 |  | -- |  | 24.3
1997 |  | 100 | 46.2 |  | -- |  | 12.8 |  | 59 |  | 1.8 |  | 60.8
1998 |  | 135 | 58.1 |  | -- |  | 10.7 |  | 68.8 |  | 3.6 |  | 72.4
1999 |  | 328 | 83.2 |  | -- |  | 33.9 |  | 117.1 |  | 2.5 |  | 119.6
2000 |  | 454 | 103.4 |  | -- |  | 10.5 |  | 113.9 |  | 0.9 |  | 114.8
2001 |  | 29 | 120 |  | -- |  | 33.4 |  | 153.4 |  | 2.2 |  | 155.6
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | 490 | 104 |  | -- |  | 19.9 |  | 123.9 |  | 0.6 |  | 124.5
2004 |  | 231 | 65.7 |  | -- |  | 3.9 |  | 69.6 |  | 0.7 |  | 70.3
2005 |  | 216 | 52.2 |  | -- |  | 10.3 |  | 62.5 |  | 0.6 |  | 63.1
Subtotal |  | 1983 | 632.8 |  | -- |  | 159.7 |  | 792.5 |  | 12.9 |  | 805.4

## Table 28
Annual Funding - BASELINE/BLU-108 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | BY 1990 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1996 |  | -- | -- |  | -- |  | 20.4 |  | 20.4 |  | -- |  | 20.4
1997 |  | 100 | 38.3 |  | -- |  | 10.6 |  | 48.9 |  | 1.5 |  | 50.4
1998 |  | 135 | 47.6 |  | -- |  | 8.8 |  | 56.4 |  | 3 |  | 59.4
1999 |  | 328 | 67.4 |  | -- |  | 27.5 |  | 94.9 |  | 2 |  | 96.9
2000 |  | 454 | 82.6 |  | -- |  | 8.4 |  | 91 |  | 0.7 |  | 91.7
2001 |  | 29 | 94.7 |  | -- |  | 26.4 |  | 121.1 |  | 1.7 |  | 122.8
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | 490 | 79.6 |  | -- |  | 15.1 |  | 94.7 |  | 0.5 |  | 95.2
2004 |  | 231 | 48.8 |  | -- |  | 2.9 |  | 51.7 |  | 0.5 |  | 52.2
2005 |  | 216 | 37.7 |  | -- |  | 7.5 |  | 45.2 |  | 0.4 |  | 45.6
Subtotal |  | 1983 | 496.7 |  | -- |  | 127.6 |  | 624.3 |  | 10.3 |  | 634.6

## Table 29
Annual Funding - BASELINE/BLU-108 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1998 |  | 45 | 21.3 |  | -- |  | -- |  | 21.3 |  | -- |  | 21.3
1999 |  | 86 | 27.1 |  | -- |  | 4.2 |  | 31.3 |  | 2 |  | 33.3
2000 |  | 74 | 19.9 |  | -- |  | 3.1 |  | 23 |  | 4.3 |  | 27.3
2001 |  | -- | -- |  | -- |  | 21.7 |  | 21.7 |  | 6.4 |  | 28.1
2002 |  | -- | -- |  | -- |  | 9.7 |  | 9.7 |  | 0.5 |  | 10.2
2003 |  | 22 | 9.4 |  | -- |  | 2.7 |  | 12.1 |  | 0.1 |  | 12.2
2004 |  | 307 | 73.9 |  | -- |  | 4.3 |  | 78.2 |  | 0.3 |  | 78.5
Subtotal |  | 534 | 151.6 |  | -- |  | 45.7 |  | 197.3 |  | 13.6 |  | 210.9

## Table 30
Annual Funding - BASELINE/BLU-108 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | BY 1990 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1998 |  | 45 | 17.4 |  | -- |  | -- |  | 17.4 |  | -- |  | 17.4
1999 |  | 86 | 21.9 |  | -- |  | 3.4 |  | 25.3 |  | 1.6 |  | 26.9
2000 |  | 74 | 15.9 |  | -- |  | 2.5 |  | 18.4 |  | 3.4 |  | 21.8
2001 |  | -- | -- |  | -- |  | 17.1 |  | 17.1 |  | 5.1 |  | 22.2
2002 |  | -- | -- |  | -- |  | 7.5 |  | 7.5 |  | 0.4 |  | 7.9
2003 |  | 22 | 7.2 |  | -- |  | 2.1 |  | 9.3 |  | 0.1 |  | 9.4
2004 |  | 307 | 55.6 |  | -- |  | 3.3 |  | 58.9 |  | 0.2 |  | 59.1
Subtotal |  | 534 | 118 |  | -- |  | 35.9 |  | 153.9 |  | 10.8 |  | 164.7

## Table 31
Annual Funding By Appropriation - UNITARY
Annual Funding - UNITARY 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.6
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.4
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.3
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.9
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.9
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.5
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.2
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.7
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.4
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.8
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.6
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.2
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.8
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.8
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.6
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.4
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.4
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 454

## Table 32
Annual Funding - UNITARY 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 1990 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.1
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.1
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.9
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.2
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.4
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.8
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.4
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.8
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.3
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.1
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.2
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.7
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.1
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.7
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.4
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.8
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 352.1

## Table 33
Annual Funding - UNITARY 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | 4.5 |  | 4.5 |  | -- |  | 4.5
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | 42 | 29.1 |  | -- |  | 5.8 |  | 34.9 |  | -- |  | 34.9
2004 |  | 97 | 39.4 |  | -- |  | 7.7 |  | 47.1 |  | -- |  | 47.1
2005 |  | 189 | 66.4 |  | -- |  | 11.9 |  | 78.3 |  | 0.3 |  | 78.6
2006 |  | 420 | 119.6 |  | -- |  | 22.4 |  | 142 |  | 2.4 |  | 144.4
2007 |  | 388 | 112 |  | -- |  | 11.3 |  | 123.3 |  | 1 |  | 124.3
2008 |  | 370 | 117.2 |  | -- |  | 11.2 |  | 128.4 |  | 0.9 |  | 129.3
2009 |  | 281 | 124.1 |  | -- |  | 19.2 |  | 143.3 |  | 0.6 |  | 143.9
2010 |  | 313 | 125.9 |  | -- |  | 15.4 |  | 141.3 |  | 0.7 |  | 142
2011 |  | 225 | 117.1 |  | -- |  | 10.3 |  | 127.4 |  | 0.8 |  | 128.2
2012 |  | 246 | 118.6 |  | -- |  | 9.9 |  | 128.5 |  | 0.7 |  | 129.2
2013 |  | 202 | 94.3 |  | -- |  | 25 |  | 119.3 |  | 0.7 |  | 120
2014 |  | 212 | 97.5 |  | -- |  | 13.6 |  | 111.1 |  | 7.8 |  | 118.9
2015 |  | 200 | 88.6 |  | -- |  | 17.1 |  | 105.7 |  | 3 |  | 108.7
2016 |  | -- | -- |  | -- |  | 19.6 |  | 19.6 |  | 1.8 |  | 21.4
2017 |  | -- | -- |  | -- |  | 2.8 |  | 2.8 |  | -- |  | 2.8
2018 |  | -- | -- |  | -- |  | 6.4 |  | 6.4 |  | -- |  | 6.4
2019 |  | -- | -- |  | -- |  | 1.2 |  | 1.2 |  | -- |  | 1.2
Subtotal |  | 3185 | 1249.8 |  | -- |  | 215.3 |  | 1465.1 |  | 20.7 |  | 1485.8

## Table 34
Annual Funding - UNITARY 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | BY 1990 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | 3.6 |  | 3.6 |  | -- |  | 3.6
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | 42 | 22.3 |  | -- |  | 4.4 |  | 26.7 |  | -- |  | 26.7
2004 |  | 97 | 29.3 |  | -- |  | 5.7 |  | 35 |  | -- |  | 35
2005 |  | 189 | 48 |  | -- |  | 8.6 |  | 56.6 |  | 0.2 |  | 56.8
2006 |  | 420 | 84.4 |  | -- |  | 15.7 |  | 100.1 |  | 1.7 |  | 101.8
2007 |  | 388 | 77.3 |  | -- |  | 7.8 |  | 85.1 |  | 0.7 |  | 85.8
2008 |  | 370 | 79.6 |  | -- |  | 7.7 |  | 87.3 |  | 0.6 |  | 87.9
2009 |  | 281 | 83.1 |  | -- |  | 12.9 |  | 96 |  | 0.4 |  | 96.4
2010 |  | 313 | 82.9 |  | -- |  | 10.1 |  | 93 |  | 0.5 |  | 93.5
2011 |  | 225 | 75.6 |  | -- |  | 6.7 |  | 82.3 |  | 0.5 |  | 82.8
2012 |  | 246 | 75.4 |  | -- |  | 6.4 |  | 81.8 |  | 0.4 |  | 82.2
2013 |  | 202 | 59 |  | -- |  | 15.7 |  | 74.7 |  | 0.4 |  | 75.1
2014 |  | 212 | 60.1 |  | -- |  | 8.4 |  | 68.5 |  | 4.8 |  | 73.3
2015 |  | 200 | 53.7 |  | -- |  | 10.4 |  | 64.1 |  | 1.8 |  | 65.9
2016 |  | -- | -- |  | -- |  | 11.6 |  | 11.6 |  | 1.1 |  | 12.7
2017 |  | -- | -- |  | -- |  | 1.6 |  | 1.6 |  | -- |  | 1.6
2018 |  | -- | -- |  | -- |  | 3.7 |  | 3.7 |  | -- |  | 3.7
2019 |  | -- | -- |  | -- |  | 0.7 |  | 0.7 |  | -- |  | 0.7
Subtotal |  | 3185 | 830.7 |  | -- |  | 141.7 |  | 972.4 |  | 13.1 |  | 985.5

## Table 35
Low Rate Initial Production
BASELINE/BLU-108
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 1992-06-23 | 1992-06-23
Approved Quantity | 291 | 291
Reference | Milestone II ADM | Milestone II ADM
Start Year | 1997 | 1997
End Year | 1999 | 1999
LRIP quantity of 291 (includes 280 for JSOW-A and 11 for JSOW-B) was approved at Milestone II in June 1992.
UNITARY
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 1995-04-26 | 1995-04-26
Approved Quantity | 139 | 139
Reference | Milestone II ADM | Milestone II ADM
Start Year | 2003 | 2003
End Year | 2006 | 2006
LRIP quantities of 139 approved at Milestone II in April 1995.

## Table 36
Foreign Military Sales
BASELINE/BLU-108
Country | Date of Sale | Quantity | Total Cost $M | Description
Turkey 11/15/2005 50 26.4 U.S. Navy Case - Turkey; 50 AGM-154A-1; 54 AGM-
154C
Total Case Value: $26,422,774.00
Turkey 11/15/2005 0 4.9 U.S. Navy Case - Turkey; JSOW integration on the
Turkish Air Force General Avionics Computer based Block-40 F-16 aircraft; Total Case Value:
4955940
Notes
UNITARY
Country | Date of Sale | Quantity | Total Cost $M | Description
Australia | 2009-06-25 |  | 29.9 | U.S. Navy Case - Australia; Total Case Value: $29,853,224.00
Finland | 2009-06-05 | 11 | 8.9 | U.S. Navy Case - Finland; 11 AGM-154C; Total Case Value $8,897,122.95
Australia | 2008-03-31 |  | 15.7 | U.S. Navy Case - Australia; Total Case Value: $15,687,401.00
Greece | 2007-01-31 | 40 | 13.3 | U.S. Navy Case - Greece; 40 AGM-154C; Total Case Value $13,294,755.14
Greece | 2005-12-13 | 0 | 3.2 | U.S. Air Force Case - Greece; Greece integration case; Total Case Value $1,932,022,845.00; JSOW Case Value portion $3,178,646.59
Turkey | 2005-11-15 | 54 | 26.4 | U.S. Navy Case - Turkey; 50 AGM-154A-1; 54 AGM- 154C Total Case Value: $26,442,774.00
Poland | 2003-04-18 | 80 | 27.4 | U.S. Air Force Case - Poland; 80 AGM-154C; Total Case Value $27,428,861.80
Notes
Total cost dollars may increase or decrease based on scope changes in follow-on support work.

## Table 37
Nuclear Costs
BASELINE/BLU-108
None
UNITARY
None

## Table 38
Unit Cost
BASELINE/BLU-108
Unit Cost Report
Item |  |  |  | BY 1990 $M |  |  | BY 1990 $M |  |  | % Change
|  |  |  | Current UCR Baseline (Dec 2004 APB) |  |  | Current Estimate (Dec 2014 SAR)
Program Acquisition Unit Cost
Cost |  |  | 1505.8 |  |  |  |  | 1362.9
Quantity |  |  | 3334 |  |  |  |  | 2517
Item |  |  | 0.452 |  |  |  |  | 0.541 |  |  |  | +19.691
Average Procurement Unit Cost
Cost |  |  | 941.7 |  |  |  |  | 799.3
Quantity |  |  | 3334 |  |  |  |  | 2517
Unit Cost |  |  | 0.282 |  |  |  |  | 0.318 |  |  |  | 12.77
Item |  |  |  | BY 1990 $M |  |  | BY 1990 $M |  |  | % Change
Revised
|  |  |  | Original UCR |  |  | Current Estimate
|  |  |  | Baseline |  |  | (Dec 2014 SAR)
(Dec 2004 APB)
Program Acquisition Unit Cost
Cost |  |  | 1505.8 |  |  |  |  | 1362.9
Quantity |  |  | 3334 |  |  |  |  | 2517
Unit Cost |  |  | 0.452 |  |  |  |  | 0.541 |  |  |  | 19.69
Average Procurement Unit Cost
Cost |  |  | 941.7 |  |  |  |  | 799.3
Quantity |  |  | 3334 |  |  |  |  | 2517
Unit Cost |  |  | 0.282 |  |  |  |  | 0.318 |  |  |  | 12.77
Unit Cost | TY $M | [7 empty] | TY % Change
| Current UCR Baseline (Dec 2004 APB) |  |  |  | Current Estimate (Dec 2014 SAR)
Program Acquisition Unit Cost (PAUC)
Cost |  | 1878.8 |  |  |  | 1659.9
Unit Cost |  | 0.564 |  |  |  | 0.659 |  |  |  |  | 16.84
Average Procurement Unit Cost (APUC)
Cost |  | 1235.2 |  |  |  | 1016.3
Unit Cost |  | 0.37 |  |  |  | 0.404 |  |  |  |  | 9.19

## Table 39
Unit Cost | TY $M | [6 empty] | TY % Change
| Revised Original UCR Baseline (Dec 2004 APB) |  | Current Estimate (Dec 2014 SAR)
Program Acquisition Unit Cost (PAUC)
Cost |  | 1878.8 |  |  | 1659.9
Unit Cost |  | 0.564 |  |  | 0.659 |  |  |  | 16.84
Average Procurement Unit Cost (APUC)
Cost |  | 1235.2 |  |  | 1016.3
Unit Cost |  | 0.37 |  |  | 0.404 |  |  |  | 9.19
1
Nunn-McCurdy Breach
JSOW Baseline/BLU-108 unit cost breaches are the result of the termination of JSOW procurement, which reduces the overall quantity by 817 weapons in comparison to the APB.
Unit Cost Breach Data
Changes From Previous SAR |  |  |  | $M/Qty. |  | Percent
PAUC (BY $M) |  |  |  |  | 0.1 |  | 22.68
APUC (BY $M) |  |  |  |  | 0.046 |  | 16.91
PAUC Quantity |  |  |  |  | -817 |  | 0
PAUC (TY $M) |  |  |  |  | 0.097 |  | 17.26
APUC (TY $M) |  |  |  |  | 0.035 |  | 9.49
Initial SAR Information - Dec 1997 |  |  |  | BY1990 $M |  | TY $M
Program Acquisition Cost |  |  |  | 0.5 |  | 0.7
Unit Cost PAUC Changes
JSOW Baseline/BLU-108 unit cost breaches are the result of the termination of JSOW procurement, which reduces the overall quantity by 817 weapons in comparison to the APB.
Unit Cost APUC Changes
JSOW Baseline/BLU-108 unit cost breaches are the result of the termination of JSOW procurement, which reduces the overall quantity by 817 weapons in comparison to the APB.

## Table 40
BASELINE/BLU-108
Unit Cost History
Item | [7 empty] | Date |  |  |  | BY 1990 $M | [6 empty] | TY $M
[12 empty] | PAUC |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Jun 1992 | [6 empty] | 0.214 |  |  |  | 0.175 |  |  |  | 0.337 |  |  |  | 0.292
APB as of January 2006 |  |  |  |  | Aug 2009 | [6 empty] | 0.452 |  |  |  | 0.282 |  |  |  | 0.564 |  |  |  | 0.37
Revised Original APB |  |  |  |  | Dec 2004 | [6 empty] | 0.452 |  |  |  | 0.282 |  |  |  | 0.564 |  |  |  | 0.37
Prior APB |  |  |  |  | May 2004 | [6 empty] | 0.231 |  |  |  | 0.184 |  |  |  | 0.316 |  |  |  | 0.261
Current APB |  |  |  |  | Aug 2009 | [6 empty] | 0.452 |  |  |  | 0.282 |  |  |  | 0.564 |  |  |  | 0.37
Prior Annual SAR |  |  |  |  | Dec 2013 | [6 empty] | 0.441 |  |  |  | 0.272 |  |  |  | 0.562 |  |  |  | 0.369
Current Estimate |  |  |  |  | Dec 2014 | [6 empty] | 0.541 |  |  |  | 0.318 |  |  |  | 0.659 |  |  |  | 0.404
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [20 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth |  | Spt |  |  | Total
0.340 -0.030 -0.060 0.000 0.000 0.064 0.000 -0.010 -0.036 0.304
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [18 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  | Eng | Est |  |  | Oth | Spt |  |  | Total
0.304 -0.013 0.255 0.166 0.041 -0.085 0.000 -0.009 0.355 0.659

## Table 41
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [14 empty] | APUC Production Estimate
| Econ | Qty |  |  | Sch |  | Eng |  |  | Est | Oth | Spt |  | Total
0.290 -0.030 -0.040 0.000 0.000 0.052 0.000 -0.010 -0.028 0.262
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [14 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng |  |  | Est |  | Oth | Spt |  |  | Total
0.262 -0.014 0.030 0.166 0.024 -0.055 0.000 -0.009 0.142 0.404
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  |  |  | SAR Development Estimate |  |  |  |  | SAR Production Estimate |  |  |  | Current Estimate
Milestone I |  |  | Jun 1989 |  |  |  |  | Jun 1989 |  |  |  |  | Jun 1989 |  |  |  | Jun 1989
Milestone II |  |  | Mar 1991 |  |  |  |  | Apr 1992 |  |  |  |  | Apr 1995 |  |  |  | Jun 1992
Milestone III |  |  | Jun 1994 |  |  |  |  | Jul 1998 |  |  |  |  | Oct 2001 |  |  |  | Oct 1998
IOC |  |  | Sep 1995 |  |  |  |  | Jul 1998 |  |  |  |  | Sep 2002 |  |  |  | Jan 1999
Total Cost (TY $M) |  |  | 260 |  |  |  |  | 2969.2 |  |  |  |  | 4898.7 |  |  |  | 1659.9
Total Quantity |  |  | N/A |  |  |  |  | 8800 |  |  |  |  | 16124 |  |  |  | 2517
PAUC |  |  | N/A |  |  |  |  | 0.337 |  |  |  |  | 0.304 |  |  |  | 0.659

## Table 42
UNITARY
Unit Cost Report
Item |  |  |  | BY 1990 $M |  |  | BY 1990 $M |  |  | % Change
|  |  |  | Current UCR Baseline (Aug 2009 APB) |  |  | Current Estimate (Dec 2014 SAR)
Program Acquisition Unit Cost
Cost |  |  | 2018.7 |  |  |  |  | 1337.6
Quantity |  |  | 7000 |  |  |  |  | 3185
Item |  |  | 0.288 |  |  |  |  | 0.42 |  |  |  | +45.831
Average Procurement Unit Cost
Cost |  |  | 1695 |  |  |  |  | 985.5
Quantity |  |  | 7000 |  |  |  |  | 3185
Unit Cost |  |  | 0.242 |  |  |  |  | 0.309 |  |  |  | +27.691
Item |  |  |  | BY 1990 $M |  | BY 1990 $M |  |  |  | % Change
|  |  |  | Original UCR Baseline (Apr 1995 APB) |  | Current Estimate (Dec 2014 SAR)
Program Acquisition Unit Cost
Cost |  |  | 3360.9 |  |  |  |  | 1337.6
Quantity |  |  | 7800 |  |  |  |  | 3185
Unit Cost |  |  | 0.431 |  |  |  |  | 0.42 |  |  |  | -2.55
Average Procurement Unit Cost
Cost |  |  | 3103.7 |  |  |  |  | 985.5
Quantity |  |  | 7800 |  |  |  |  | 3185
Unit Cost |  |  | 0.398 |  |  |  |  | 0.309 |  |  |  | -22.36
Unit Cost | TY $M | [7 empty] | TY % Change
| Current UCR Baseline (Aug 2009 APB) |  |  |  | Current Estimate (Dec 2014 SAR)
Program Acquisition Unit Cost (PAUC)
Cost |  | 3036.6 |  |  |  | 1939.8
Unit Cost |  | 0.434 |  |  |  | 0.609 |  |  |  |  | 40.32
Average Procurement Unit Cost (APUC)
Cost |  | 2627.3 |  |  |  | 1485.8
Unit Cost |  | 0.375 |  |  |  | 0.466 |  |  |  |  | 24.27

## Table 43
Unit Cost | TY $M | [6 empty] | TY % Change
| Original UCR Baseline (Apr 1995 APB) |  | Current Estimate (Dec 2014 SAR)
Program Acquisition Unit Cost (PAUC)
Cost |  | 6307.2 |  |  | 1939.8
Unit Cost |  | 0.809 |  |  | 0.609 |  |  |  | -24.72
Average Procurement Unit Cost (APUC)
Cost |  | 5970.9 |  |  | 1485.8
Unit Cost |  | 0.766 |  |  | 0.466 |  |  |  | -39.16
1
Nunn-McCurdy Breach
JSOW Unitary unit cost breaches are the result of the termination of JSOW procurement, which reduces the overall quantity by 3,815 weapons in comparison to the APB.
Unit Cost Breach Data
Changes From Previous SAR |  |  |  | $M/Qty. |  | Percent
PAUC (BY $M) |  |  |  |  | 0.107 |  | 34.19
APUC (BY $M) |  |  |  |  | 0.047 |  | 17.94
PAUC Quantity |  |  |  |  | -3815 |  | 0
PAUC (TY $M) |  |  |  |  | 0.098 |  | 19.18
APUC (TY $M) |  |  |  |  | 0.02 |  | 4.48
Initial SAR Information - Dec 1997 |  |  |  | BY1990 $M |  | TY $M
Program Acquisition Cost |  |  |  | 0.4 |  | 0.6
Unit Cost PAUC Changes
JSOW Unitary unit cost breaches are the result of the termination of JSOW procurement, which reduces the overall quantity by 3,815 weapons in comparison to the APB.
Unit Cost APUC Changes
JSOW Unitary unit cost breaches are the result of the termination of JSOW procurement, which reduces the overall quantity by 3,815 weapons in comparison to the APB.

## Table 44
UNITARY
Unit Cost History
Item | [7 empty] | Date |  |  | BY 1990 $M | [7 empty] | TY $M
[11 empty] | PAUC |  |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Apr 1995 | [5 empty] | 0.431 |  |  |  |  | 0.398 |  |  |  | 0.809 |  |  |  | 0.766
APB as of January 2006 |  |  |  |  | Dec 2004 | [5 empty] | 0.283 |  |  |  |  | 0.242 |  |  |  | 0.425 |  |  |  | 0.375
Revised Original APB |  |  |  |  | N/A | [5 empty] | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | Feb 2008 | [5 empty] | 0.288 |  |  |  |  | 0.242 |  |  |  | 0.434 |  |  |  | 0.375
Current APB |  |  |  |  | Aug 2009 | [5 empty] | 0.288 |  |  |  |  | 0.242 |  |  |  | 0.434 |  |  |  | 0.375
Prior Annual SAR |  |  |  |  | Dec 2013 | [5 empty] | 0.313 |  |  |  |  | 0.262 |  |  |  | 0.511 |  |  |  | 0.446
Current Estimate |  |  |  |  | Dec 2014 | [5 empty] | 0.42 |  |  |  |  | 0.309 |  |  |  | 0.609 |  |  |  | 0.466
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [20 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng | Est |  |  | Oth |  | Spt |  |  | Total
0.809 -0.054 0.041 -0.014 0.098 -0.414 0.000 -0.041 -0.384 0.425
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [18 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  | Eng | Est |  | Oth |  | Spt |  |  | Total
0.425 0.034 0.054 0.069 0.154 -0.125 0.000 -0.002 0.184 0.609

## Table 45
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [11 empty] | APUC Production Estimate
| Econ | Qty |  | Sch |  | Eng |  | Est | Oth | Spt |  | Total
0.766 -0.051 0.035 -0.014 0.092 -0.412 0.000 -0.041 -0.391 0.375
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [11 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch | Eng |  | Est | Oth | Spt |  | Total
0.375 0.034 -0.008 0.067 0.140 -0.140 0.000 -0.002 0.091 0.466
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone I |  |  | N/A |  |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone II |  |  | N/A |  |  |  | Apr 1995 |  |  |  | Apr 1995 |  |  | Apr 1995
Milestone III |  |  | N/A |  |  |  | Sep 2002 |  |  |  | Dec 2004 |  |  | Dec 2004
IOC |  |  | N/A |  |  |  | Sep 2002 |  |  |  | Aug 2004 |  |  | Feb 2005
Total Cost (TY $M) |  |  | N/A |  |  |  | 6307.2 |  |  |  | 2974.8 |  |  | 1939.8
Total Quantity |  |  | N/A |  |  |  | 7800 |  |  |  | 7000 |  |  | 3185
PAUC |  |  | N/A |  |  |  | 0.809 |  |  |  | 0.425 |  |  | 0.609

## Table 46
Cost Variance
BASELINE/BLU-108
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 645 | 4225.1 | 28.6 | 4898.7
Previous Changes
Economic | 1.5 | -33.4 | -- | -31.9
Quantity | -- | -3204.5 | -- | -3204.5
Schedule | -- | 417.2 | 0.4 | 417.6
Engineering | 44.1 | 59.9 | -- | 104
Estimating | -47 | -213 | -29 | -289
Other | -- | -- | -- | --
Support | -- | -21.3 | -- | -21.3
Subtotal | -1.4 | -2995.1 | -28.6 | -3025.1
Current Changes
Economic | -- | -1.8 | -- | -1.8
Quantity | -- | -285.7 | -- | -285.7
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | 74.6 | -- | 74.6
Other | -- | -- | -- | --
Support | -- | -0.8 | -- | -0.8
Subtotal | -- | -213.7 | -- | -213.7
Total Changes | -1.4 | -3208.8 | -28.6 | -3238.8
CE - Cost Variance | 643.6 | 1016.3 | -- | 1659.9
CE - Cost & Funding | 643.6 | 1016.3 | -- | 1659.9

## Table 47
Summary BY 1990 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 554 | 2990.5 | 21.8 | 3566.3
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -2059.3 | -- | -2059.3
Schedule | -- | 8.4 | -- | 8.4
Engineering | 33.1 | 43.5 | -- | 76.6
Estimating | -23.5 | -61.4 | -21.8 | -106.7
Other | -- | -- | -- | --
Support | -- | -13.6 | -- | -13.6
Subtotal | 9.6 | -2082.4 | -21.8 | -2094.6
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -146.7 | -- | -146.7
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | 38.3 | -- | 38.3
Other | -- | -- | -- | --
Support | -- | -0.4 | -- | -0.4
Subtotal | -- | -108.8 | -- | -108.8
Total Changes | 9.6 | -2191.2 | -21.8 | -2203.4
CE - Cost Variance | 563.6 | 799.3 | -- | 1362.9
CE - Cost & Funding | 563.6 | 799.3 | -- | 1362.9
Previous Estimate: December 2013

## Table 48
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -1.8
Quantity variance resulting from a decrease of 817 JSOW Baseline units from 2,800 to 1,983 (Navy). (Quantity)
Adjustment to zero out remaining JSOW Baseline units and cost as the result of JSOW production termination. (Estimating) (QR)
Adjustment to zero out remaining JSOW Integrated Logistic Support as the result of JSOW production termination. (Support) (QR)
-146.7 -285.7
+38.3 +74.6
-0.4 -0.8
Procurement Subtotal -108.8 -213.7
(QR) Quantity Related

## Table 49
Cost Variance
UNITARY
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
347.5 2627.3 -- 2974.8
Economic |  | 3.5 |  | 122.4 |  | -- |  | 125.9
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | 7.5 |  | 294.5 |  | -- |  | 302
Engineering |  | 46.7 |  | 616 |  | -- |  | 662.7
Estimating |  | 48.9 |  | -564.9 |  | -- |  | -516
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 26.7 |  | -- |  | 26.7
Subtotal |  | 106.6 |  | 494.7 |  | -- |  | 601.3
Current Changes Economic |  | -0.4 |  | -15.7 |  | -- |  | -16.1
Quantity |  | -- |  | -1453.2 |  | -- |  | -1453.2
Schedule |  | -- |  | -81.6 |  | -- |  | -81.6
Engineering |  | -- |  | -170.8 |  | -- |  | -170.8
Estimating |  | 0.3 |  | 117.5 |  | -- |  | 117.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -32.4 |  | -- |  | -32.4
Subtotal |  | -0.1 |  | -1636.2 |  | -- |  | -1636.3
Total Changes |  | 106.5 |  | -1141.5 |  | -- |  | -1035
CE - Cost Variance |  | 454 |  | 1485.8 |  | -- |  | 1939.8
CE - Cost & Funding |  | 454 |  | 1485.8 |  | -- |  | 1939.8

## Table 50
Summary BY 1990 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 282.8 | 1695 | -- | 1977.8
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | 4.9 | 61 | -- | 65.9
Engineering | 31.1 | 378 | -- | 409.1
Estimating | 33.3 | -311.6 | -- | -278.3
Other | -- | -- | -- | --
Support | -- | 14.4 | -- | 14.4
Subtotal | 69.3 | 141.8 | -- | 211.1
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -759.1 | -- | -759.1
Schedule | -- | -42.5 | -- | -42.5
Engineering | -- | -89.1 | -- | -89.1
Estimating | -- | 58.1 | -- | 58.1
Other | -- | -- | -- | --
Support | -- | -18.7 | -- | -18.7
Subtotal | -- | -851.3 | -- | -851.3
Total Changes | 69.3 | -709.5 | -- | -640.2
CE - Cost Variance | 352.1 | 985.5 | -- | 1337.6
CE - Cost & Funding | 352.1 | 985.5 | -- | 1337.6
Previous Estimate: December 2013

## Table 51
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -0.4
Adjustment for current and prior escalation. (Estimating) +0.1 +0.2
Revised estimate due to reprogramming of funds in FY 2013 to support other Department of the Navy activities. (Estimating)
Revised estimate to allow JSOW Unitary to increase future capabilities while entering program sustainment. (Estimating)
-0.6 -1.1
+0.5 +1.2
RDT&E Subtotal 0.0 -0.1
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -15.7
Adjustment for current and prior escalation. (Estimating) +1.1 +1.8
Quantity variance resulting from a decrease of 3,815 JSOW Unitary weapons from 7,000 to 3,185. (Subtotal)
Quantity variance resulting from a decrease of 3,815 JSOW Untiary weapons from 7,000 to 3,185. (Quantity)
-846.7 -1621.1
(-759.1) (-1453.2)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) (-42.5) (-81.6) Allocation to Engineering resulting from Quantity change. (Engineering) (QR) (-89.1) (-170.8) Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (+44.0) (+84.5)
Adjustment to account for zeroing out JSOW Unitary weapons after FY 2015 as a result of JSOW production termination. (Estimating) (QR)
Revised estimate due to identifying an organic solution for telemetry instrumentation kits. (Estimating)
Revised estimate to account for production shutdown costs as the result of JSOW production deferral. (Estimating)
Revised estimate to remove additional Operational Flight Program software work from Command & Launch. (Estimating)
+20.6 +43.1
-8.5 -13.8
+9.5 +16.0
-3.8 -6.2
Revised estimate to account for anticipated FMS synergies in FY 2015. (Estimating) -4.6 -7.6 Revised estimate to account for prior year actuals. (Estimating) -0.2 -0.3
Revised Captive AIR Training Missile estimate due to reduced quantity and supplying of Government Furnished Equipment. (Support)
-18.2 -31.1
Decrease in Initial Spares. (Support) | -0.5 |  |  | -1.3
Procurement Subtotal (QR) Quantity Related | -851.3 |  |  | -1636.2

## Table 52
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: AGM-154C-1 FY 2011/2012 Production
Contractor: Raytheon Company
Contractor Location: 1151 E Hermans Road
Tucson, AZ 85706
Contract Number: N00019-11-C-0032
Contract Type: Firm Fixed Price (FFP)
Award Date: July 28, 2011
Definitization Date: July 28, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
85.6 N/A 225 180.5 N/A 473 180.5 180.5
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the exercise of the FY 2012 production option.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 53
Contract Identification
Appropriation: Procurement
Contract Name: AGM-154C-1 FY 2013/2014 Production
Contractor: Raytheon Company
Contractor Location: 1151 E Hermans Road
Tucson, AZ 85706
Contract Number: N00019-13-C-0011
Contract Type: Firm Fixed Price (FFP)
Award Date: June 05, 2013
Definitization Date: June 05, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
80.5 N/A 200 164.3 N/A 412 164.3 164.3
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the exercise of the FY 2014 production option.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 54
Deliveries and Expenditures
BASELINE/BLU-108
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 2517 | 2517 | 2517 | 100%
Total Program Quantity Delivered | 2517 | 2517 | 2517 | 100%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
1659.9
1659.9
100%
19
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
19
100%
1659.9
100%
The above data is current as of February 28, 2015.
UNITARY
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 2615 | 2615 | 3185 | 82.1%
Total Program Quantity Delivered | 2615 | 2615 | 3185 | 82.1%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
1939.8
1584.5
81.68%
37
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
24
64.86%
1902
98.05%
The above data is current as of February 28, 2015.

## Table 55
Operating and Support Cost
BASELINE/BLU-108
Cost Estimate Details
Date of Estimate: January 29, 2015
Source of Estimate: POE
Quantity to Sustain: 2517
Unit of Measure: Total Quantity
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 1998 - FY 2018
• Estimate is based on JSOW production termination after FY 2015.
• No additional Unit Operations, Unit-Level Manpower, or Indirect Support were required with the release of the JSOW Baseline variant.
Sustainment Strategy
• Single-tier maintenance approach (Depot Level) at contractor facility.
• No warranty.
Antecedent Information
No Antecedent
Annual O&S Costs BY1990 $M
Cost Element | BASELINE/BLU-108 Average Annual Cost Per Total Quantity | No Antecedent (Antecedent)
Unit-Level Manpower | 0 | --
Unit Operations | 0 | --
Maintenance | 0.47 | --
Sustaining Support | 0.492 | --
Continuing System Improvements | 0 | --
Indirect Support | 0 | --
Other | 0 | --
Total | 0.962 | --

## Table 56
Item | Total O&S Cost $M
| BASELINE/BLU-108 | [5 empty] | No Antecedent (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | N/A |  | N/A |  |  | 20.2 | N/A
Then Year | N/A |  | N/A |  |  | 31.1 | N/A
Equation to Translate Annual Cost to Total Cost
21 Years * .962M Average Annual Cost = $20.2M
O&S Cost Variance
Category |  | BY 1990 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2013 SAR
146.9
Programmatic/Planning Factors -126.7 Revised estimate to account for termination of the JSOW
Baseline/BLU-108 production program.
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes -126.7
Current Estimate 20.2
Disposal Estimate Details
Date of Estimate: January 29, 2015
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 1990 $M): Total costs for disposal of all Total Quantity are 2.4
Demilitarization will occur for remaining JSOW Baseline/BLU-108 units in FY 2018.

## Table 57
UNITARY
Cost Estimate Details
Date of Estimate: January 29, 2015
Source of Estimate: POE
Quantity to Sustain: 3185
Unit of Measure: Total Quantity
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2006 - FY 2037
• Estimate based on JSOW production termination after FY 2015.
• No additional Unit Operations, Unit-Level Manpower, or Indirect Support were required with the release of the JSOW Unitary variant.
Sustainment Strategy
• Single-tier maintenance approach (Depot Level) at contractor facility.
• No warranty.
Antecedent Information
No Antecedent
Annual O&S Costs BY1990 $M
Cost Element | UNITARY Average Annual Cost Per Total Quantity | No Antecedent (Antecedent) No Antecedent
Unit-Level Manpower | 0 | --
Unit Operations | 0 | --
Maintenance | 0.267 | --
Sustaining Support | 1.691 | --
Continuing System Improvements | 1.013 | --
Indirect Support | 0 | --
Other | 0 | --
Total | 2.971 | --

## Table 58
Item | Total O&S Cost $M
| UNITARY | [5 empty] | No Antecedent (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | N/A |  | N/A |  |  | 95 | N/A
Then Year | N/A |  | N/A |  |  | 195.6 | N/A
Equation to Translate Annual Cost to Total Cost
32 Years * $2.971M Average Annual Cost = $95.0M
O&S Cost Variance
Category |  | BY 1990 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2013 SAR
152.7
Programmatic/Planning Factors -57.7 Revised estimate due to reduced quantity and sustainment
life of the JSOW Unitary variant as the result of production termination after FY 2015.
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes -57.7
Current Estimate 95.0
Disposal Estimate Details
Date of Estimate: January 29, 2015
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 1990 $M): Total costs for disposal of all Total Quantity are 3.5
Disposal assumed after 20 year shelf life is complete.