## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-537
National Airspace System (NAS)
As of FY 2015 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations |  | 3
Program Information |  | 4
Responsible Office |  | 4
References |  | 4
Mission and Description |  | 5
Executive Summary |  | 6
Threshold Breaches |  | 7
Schedule |  | 8
Performance |  | 11
Track to Budget |  | 13
Cost and Funding |  | 14
Low Rate Initial Production |  | 28
Foreign Military Sales |  | 29
Nuclear Costs |  | 29
Unit Cost |  | 30
Cost Variance |  | 33
Contracts |  | 36
Deliveries and Expenditures |  | 37
Operating and Support Cost |  | 38

## Table 3
Common Acronyms and Abbreviations
Acq O&M - Acquisition-Related Operations and Maintenance APB - Acquisition Program Baseline
APPN - Appropriation
APUC - Average Procurement Unit Cost BA - Budget Authority/Budget Activity
BY - Base Year
DAMIR - Defense Acquisition Management Information Retrieval Dev Est - Development Estimate
DoD - Department of Defense DSN - Defense Switched Network Econ - Economic
Eng - Engineering Est - Estimating
FMS - Foreign Military Sales FY - Fiscal Year
IOC - Initial Operational Capability
$K - Thousands of Dollars
LRIP - Low Rate Initial Production
$M - Millions of Dollars MILCON - Military Construction N/A - Not Applicable
O&S - Operating and Support Oth - Other
PAUC - Program Acquisition Unit Cost PB - President’s Budget
PE - Program Element Proc - Procurement
Prod Est - Production Estimate QR - Quantity Related
Qty - Quantity
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
Sch - Schedule Spt - Support
TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting

## Table 4
Program Information
Program Name
National Airspace System (NAS)
DoD Component
Air Force
Joint Participants
Army; Navy
Responsible Office
Responsible Office
Col Norman J Leonard, III | Phone | 781-225-5479
AFLCMC/HBA | Fax | 781-225-2433
75 Vandenberg Drive Bldg 1630 | DSN Phone | 845-5479
Hanscom AFB Bedford, MA 01731-2103 | DSN Fax | 845-2433
norman.leonard@us.af.mil | Date Assigned | July 16, 2012
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated June 7, 2005
Approved APB
Air Force Acquisition Executive (AFAE) Approved Acquisition Program Baseline (APB) dated July 12, 2006

## Table 5
Mission and Description
The DoD National Airspace System (NAS) is comprised of three systems: the Digital Airport Surveillance Radar (DASR), the DoD Advanced Automation System (DAAS), also known as the Standard Terminal Automation Replacement System (STARS) within the Federal Aviation Administration (FAA), and the Voice Communication Switching System (VCSS). The DoD NAS program is modernizing the DoD radar approach control facilities in parallel with the FAA. The DoD NAS program provides systems and facilities compatible/interoperable with the FAA modernization, prevents DoD flight delays and cancellations, continues DoD's access into Special Use Airspace, provides transparent services to military and civil aircraft, replaces aging DoD Air Traffic Control (ATC) systems, and increases flight safety. NAS is a Non-Developmental Item (NDI) acquisition. DoD will upgrade voice, data, and sensor systems as well as facility configurations and operations concepts to provide continued quantity and quality of ATC services to the aviation community. To supplement the DAAS, the DoD procured the Airfield Automation System (AFAS) to integrate weather, airport environmental data, and airfield equipment status at air traffic control positions. DoD military ATC and fighting/flying readiness will be maintained.

## Table 6
Executive Summary
NAS program continued production and delivery of Digital Airport Surveillance Radars (DASR) and DoD Advanced Automation Systems (DAAS) for the Air Force (AF), Army and Navy in Calendar Year 2013.
DASR Configuration 5 Federal Aviation Administration contract was awarded February 5, 2013.
DASR Site Acceptance Test (SAT) was completed at Shaw Air Force Base (AFB), South Carolina (AF Site) on April 23, 2013 and the DD250 was signed on June 11, 2013.
DASR DD250 was signed at Fort Rucker, Alabama (Army Site) on February 1, 2013 and the DAAS DD250 was signed on June 27, 2013.
IOC attained at Incirlik Air Base (AB), Turkey on August 2, 2013.
DAAS DD250 was signed at McGuire AFB, New Jersey (AF Site) on June 6, 2013 (1st Tech Refresh Site), with the System Cutover to operational use on August 10, 2013.
DAAS DD250 was signed at Ft. Hood, Texas (Army Site) on August 29, 2013.
DASR Installation and Check-Out (INCO) started at Dobbins AFB, Georgia (AF Site) on February 25, 2013, with SAT completed on July 17, 2013 and DD250 signed on September 17, 2013.
DASR INCO at Aviano AB, Italy started on September 9, 2013.
DAAS DD250 was signed at Osan AB, Korea on April 4, 2013 with DASR SAT completed on September 20, 2013 and DASR DD250 signed on September 30, 2013.
DAAS Equipment Delivery (ED) was accomplished at Thule AB, Greenland on August 16, 2013; DASR SAT was completed on August 29, 2013; DASR DD250 was signed September 30, 2013; and DAAS DD250 was signed October 11, 2013.
Small Business contract was awarded to JVN Communications, Inc on October 31, 2013 for an Automated Protocol Exchanger (APEX) at the two (2) German DAAS sites to interface with the host nation automation system.
DASR SAT was completed at Selfridge AFB, Michigan on May 7, 2013; DAAS ED was accomplished on Aug 27, 2013; DASR DD250 was signed on June 6, 2013; and DAAS DD250 was signed on November 7, 2013.
The Annual Configuration Steering Board was accomplished on December 11, 2013.
DASR DD250 was signed at NAS North Island (Navy site) on December 16, 2013.
DASR INCO at Lajes Field, Portugal started on June 12, 2013; DASR SAT was completed on January 30, 2014.
There are no significant software-related issues with this program at this time.

## Table 7
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 8
Schedule

## Table 9
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
DoD ATCALS in the NAS
Milestone 0 | NOV 1990 | NOV 1990 | MAY 1991 | NOV 1990
Milestone I | JUL 1992 | JUL 1992 | JAN 1993 | JUL 1992
Milestone II | JUL 1995 | JUL 1995 | JAN 1996 | JUL 1995
IOC (First DoD Site Activation) | JAN 2003 | JAN 2003 | JUL 2003 | JAN 2003
Milestone III | APR 2005 | APR 2005 | OCT 2005 | JUN 2005
MAMS
Development Contract | JUL 1995 | JUL 1995 | JAN 1996 | NOV 1995
Combined T&E
Start | MAR 1998 | MAR 1998 | SEP 1998 | MAR 1998
Complete | AUG 1998 | AUG 1998 | FEB 1999 | AUG 1998
Milestone III Review | DEC 1998 | DEC 1998 | JUN 1999 | DEC 1998
IOC (First Delivery) | JAN 1999 | JAN 1999 | JUL 1999 | JAN 1999
Full Rate Production Contract Award | MAR 1999 | MAR 1999 | SEP 1999 | MAR 1999
RADAR (DASR)
Contract Award | AUG 1996 | AUG 1996 | FEB 1997 | AUG 1996
DT&E
Start | JUL 1997 | JUL 1997 | JAN 1998 | JUL 1997
Complete | JUN 1999 | JUN 1999 | DEC 1999 | OCT 1999
IOT&E
Start | JUL 2000 | JUL 2000 | JAN 2001 | JUL 2000
Complete | OCT 2003 | OCT 2003 | OCT 2004 | OCT 2004
Full Rate Production Contract Award | APR 2005 | APR 2005 | OCT 2005 | JUN 2005
FOT&E Start | JUN 2006 | APR 2009 | OCT 2009 | MAY 2009
VOICE (VCSS)
Program Review | NOV 1999 | NOV 1999 | MAY 2000 | NOV 1999
AUTOMATION (DAAS)
Production Award Exercise | APR 2005 | APR 2005 | OCT 2005 | JUN 2005
Change Explanations
None

## Table 10
Acronyms and Abbreviations
ATCALS - Air Traffic Control and Landing Systems DAAS - DOD Advanced Automation System DASR - Digital Airport Surveillance Radar
DT&E - Developmental Test & Evaluation
FOT&E - Follow-on Operational Test & Evaluation IOT&E - Initial Operational Test and Evaluation MAMS - Military Airspace Management System T&E - Test and Evaluation
VCSS - Voice Communications Switching System

## Table 11
Performance
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
DoD ATCALS in the NAS
Inter/Intrafacility Data Transfer
Auto Transfer of Position Track Data | IAW ICD | IAW ICD | IAW ICD | IAW ICD | IAW ICD
Electronic Inter- facility Transfer of Flight Plans | IAW ICD | IAW ICD | IAW ICD | IAW ICD | IAW ICD
Aircraft Tracked Medium (LCF) | 900 | 900 | 250 | 422 | 422
Radar Subclutter Visibility (dB) | 55 | 55 | 42 | 47 | 47
Net-Ready | 100% of applicable, approved key inter- face profiles | 100% of applicable, approved key interface profiles | With FAA agreement, 100% of enterprise- level or critical applicable, approved key interface profiles | TBD | With FAA agreement, 100% of enterprise- level or critical applicable, approved key interface profiles
MAMS
Conflict Identification | 100% of conflicts identified; 85 % of conflicts identified <or = 10 (sec) | N/A | N/A | TBD | N/A
Interface with FAA | Transmittal Time for 85% of mess ages between Scheduler and FAA < or = 5 (min) | N/A | N/A | TBD | N/A

## Table 12
Reporting Processing Time of Utilization Data Requests
<or = 1 (min); Total Manual and Automatic Report Generation
<or = 10
N/A N/A TBD N/A
(min)
Requirements Source
Operational Requirements Document (ORD) for DoD Air Traffic Control and Landing Systems (ATCALS) dated March 16, 2005
Change Explanations
None
Acronyms and Abbreviations
ATCALS - Air Traffic Control and Landing Systems dB - decibels
FAA - Federal Aviation Administration IAW - In Accordance With
ICD - Interface Control Document LCF - Local Control Facility
MAMS - Military Airspace Management System min - minute
sec - second

## Table 13
Track to Budget
RDT&E
Appn |  |  | BA | PE
Navy 1319 05 0604504N
1657 Navy NAS Mod/Shore Air Traffic
(Shared) (Sunk)
Project |  |  | Name
Control Systems
Army | 2040 | 5 |  | 0604633A
| Project |  |  | Name
| D586 |  |  | Army Airfield Support Equipment | (Sunk)
Air Force | 3600 | 7 |  | 0305137F
| Project |  |  | Name
| 4090 |  |  | National Airspace System (NAS) | (Sunk)
Procurement
Appn |  |  | BA | PE
Navy | 1810 |  | 2 | 0204696N
| Line Item |  |  | Name
| 284000 |  |  | Navy NAS Mod | (Shared)
Navy | 1810 |  | 8 | 0204696N
| Line Item |  |  | Name
| 9020 |  |  | Navy NAS Mod | (Shared) | (Sunk)
Army | 2031 |  | 4 | 0210100A
| Line Item |  |  | Name
| AA0050 |  |  | Army Airfield Support Equipment | (Shared)
Air Force | 3080 |  | 3 | 0305137F
| Line Item |  |  | Name
| 833020 |  |  | NAS | (Shared)
Air Force | 3080 |  | 5 | 0305137F
| Line Item |  |  | Name
| 861900 |  |  | NAS | (Shared) | (Sunk)

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
|  | BY2005 $M | [6 empty] | BY2005 $M
Appropriation |  | SAR Baseline Prod Est |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate
TY $M
SAR Baseline Prod Est | Current APB Production Objective |  |  | Current Estimate
RDT&E |  | 134 |  |  |  | 134 |  | 147.4 |  | 135.1 |  | 115.8 | 115.8 | 115.8
Procurement |  | 1239.2 |  |  |  | 1239.2 |  | 1363.1 |  | 1270 |  | 1305.3 | 1305.3 | 1343.1
Flyaway |  | -- |  |  |  | -- |  | -- |  | 917.2 |  | -- | -- | 977.3
Recurring |  | -- |  |  |  | -- |  | -- |  | 917.2 |  | -- | -- | 977.3
Non Recurring |  | -- |  |  |  | -- |  | -- |  | 0 |  | -- | -- | 0
Support |  | -- |  |  |  | -- |  | -- |  | 352.8 |  | -- | -- | 365.8
Other Support |  | -- |  |  |  | -- |  | -- |  | 290.8 |  | -- | -- | 302.2
Initial Spares |  | -- |  |  |  | -- |  | -- |  | 62 |  | -- | -- | 63.6
MILCON |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Acq O&M |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Total |  | 1373.2 |  |  |  | 1373.2 |  | N/A |  | 1405.1 |  | 1421.1 | 1421.1 | 1458.9
Quantity |  |  | SAR Baseline Prod Est |  |  |  | Current APB Production |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  | 0
Procurement |  |  | 93 |  |  |  | 93 |  |  |  | 88
Total |  |  | 93 |  |  |  | 93 |  |  |  | 88
The unit of measure of this program represents NAS operational sites. A NAS site (unit) represents at least one paired DoD Advanced Automation Systems (DAAS) and Digital Airport Surveillance Radars (DASR). This definition of a unit is not representative of the typical equipment installed at a NAS site. It does not account for Voice Communication Switching System equipment, stand-alone DAAS equipment, or sites that have multiple DASR systems. Costs vary significantly from site to site due to particular site unique configuration requirements.

## Table 15
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2015 President's Budget / December 2013 SAR (TY$ M)
Appropriation |  | Prior | FY2014 |  |  | FY2015 |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  |  | FY2019 |  |  | To Complete |  | Total
RDT&E | 115.8 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 115.8
Procurement | 1284.3 |  |  | 24.3 |  |  | 17.1 |  |  | 11.9 |  | 2.7 |  |  | 2.8 |  |  | 0 |  |  | 0 |  | 1343.1
MILCON | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
PB 2015 Total | 1400.1 |  |  | 24.3 |  |  | 17.1 |  |  | 11.9 |  | 2.7 |  |  | 2.8 |  |  | 0 |  |  | 0 |  | 1458.9
PB 2014 Total | 1401.6 |  |  | 20.4 |  |  | 12.1 |  |  | 7.2 |  | 2.7 |  |  | 2.8 |  |  | 0 |  |  | 0 |  | 1446.8
Delta | -1.5 |  |  | 3.9 |  |  | 5 |  |  | 4.7 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 12.1
Quantity | Undistributed |  |  |  | Prior |  | FY2014 |  | FY2015 |  | FY2016 |  | FY2017 |  |  | FY2018 |  |  | FY2019 |  | To Complete |  |  | Total
Development | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
Production | 0 |  |  |  | 88 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 88
PB 2015 Total | 0 |  |  |  | 88 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 88
PB 2014 Total | 0 |  |  |  | 88 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 88
Delta | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1990 | -- | -- | -- | -- | -- | -- | 4
1991 | -- | -- | -- | -- | -- | -- | 9.9
1992 | -- | -- | -- | -- | -- | -- | 4.2
1993 | -- | -- | -- | -- | -- | -- | 6.7
1994 | -- | -- | -- | -- | -- | -- | 14.2
1995 | -- | -- | -- | -- | -- | -- | 29.5
1996 | -- | -- | -- | -- | -- | -- | 13.3
1997 | -- | -- | -- | -- | -- | -- | 11.8
1998 | -- | -- | -- | -- | -- | -- | 11.6
1999 | -- | -- | -- | -- | -- | -- | 1.8
2000 | -- | -- | -- | -- | -- | -- | 1.8
Subtotal | -- | -- | -- | -- | -- | -- | 108.8

## Table 17
Annual Funding BY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2005 $M | Non End Item Recurring Flyaway BY 2005 $M | Non Recurring Flyaway BY 2005 $M | Total Flyaway BY 2005 $M | Total Support BY 2005 $M | Total Program BY 2005 $M
1990 | -- | -- | -- | -- | -- | -- | 5.2
1991 | -- | -- | -- | -- | -- | -- | 12.4
1992 | -- | -- | -- | -- | -- | -- | 5.1
1993 | -- | -- | -- | -- | -- | -- | 8
1994 | -- | -- | -- | -- | -- | -- | 16.6
1995 | -- | -- | -- | -- | -- | -- | 33.9
1996 | -- | -- | -- | -- | -- | -- | 15
1997 | -- | -- | -- | -- | -- | -- | 13.1
1998 | -- | -- | -- | -- | -- | -- | 12.8
1999 | -- | -- | -- | -- | -- | -- | 2
2000 | -- | -- | -- | -- | -- | -- | 1.9
Subtotal | -- | -- | -- | -- | -- | -- | 126

## Table 18
Annual Funding TY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1990 -- -- -- -- -- -- 4.0
Subtotal | -- | -- | -- | -- | -- | -- | 4

## Table 19
Annual Funding BY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2005 $M | Non End Item Recurring Flyaway BY 2005 $M | Non Recurring Flyaway BY 2005 $M | Total Flyaway BY 2005 $M | Total Support BY 2005 $M | Total Program BY 2005 $M
1990 -- -- -- -- -- -- 5.2
Subtotal | -- | -- | -- | -- | -- | -- | 5.2

## Table 20
Annual Funding TY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1990 -- -- -- -- -- -- 3.0
Subtotal | -- | -- | -- | -- | -- | -- | 3

## Table 21
Annual Funding BY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2005 $M | Non End Item Recurring Flyaway BY 2005 $M | Non Recurring Flyaway BY 2005 $M | Total Flyaway BY 2005 $M | Total Support BY 2005 $M | Total Program BY 2005 $M
1990 -- -- -- -- -- -- 3.9
Subtotal | -- | -- | -- | -- | -- | -- | 3.9

## Table 22
Annual Funding TY$
2031 ¦ Procurement ¦ Aircraft Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1997 | -- | -- | 0.7 | -- | 0.7 | -- | 0.7
1998 | -- | -- | 0.1 | -- | 0.1 | 1 | 1.1
1999 | -- | -- | 1.6 | -- | 1.6 | 0.1 | 1.7
2000 | -- | -- | 2.4 | -- | 2.4 | -- | 2.4
2001 | -- | -- | 12 | -- | 12 | 1.2 | 13.2
2002 | -- | -- | 5.5 | -- | 5.5 | 2.9 | 8.4
2003 | 1 | 6.7 | 2.4 | -- | 9.1 | 4.6 | 13.7
2004 | 1 | 7.3 | 0.3 | -- | 7.6 | 5.2 | 12.8
2005 | 2 | 7.7 | 1 | -- | 8.7 | 4.8 | 13.5
2006 | 1 | 10.1 | 1.1 | -- | 11.2 | 4 | 15.2
2007 | 2 | 18.6 | 4.8 | -- | 23.4 | 4.8 | 28.2
2008 | 2 | 9 | 4.2 | -- | 13.2 | 6.2 | 19.4
2009 | 1 | 19.1 | 4.1 | -- | 23.2 | 5.1 | 28.3
2010 | 1 | 7.8 | 2.9 | -- | 10.7 | 2.2 | 12.9
2011 | -- | -- | 3.2 | -- | 3.2 | 1.3 | 4.5
2012 | -- | -- | 8.6 | -- | 8.6 | 1.8 | 10.4
2013 | -- | -- | 5.3 | -- | 5.3 | 0.2 | 5.5
2014 | -- | -- | 1.9 | -- | 1.9 | 0.6 | 2.5
2015 | -- | -- | 2.8 | -- | 2.8 | 0.9 | 3.7
2016 | -- | -- | 1.6 | -- | 1.6 | 0.9 | 2.5
Subtotal | 11 | 86.3 | 66.5 | -- | 152.8 | 47.8 | 200.6

## Table 23
Annual Funding BY$
2031 ¦ Procurement ¦ Aircraft Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2005 $M | Non End Item Recurring Flyaway BY 2005 $M | Non Recurring Flyaway BY 2005 $M | Total Flyaway BY 2005 $M | Total Support BY 2005 $M | Total Program BY 2005 $M
1997 | -- | -- | 0.8 | -- | 0.8 | -- | 0.8
1998 | -- | -- | 0.1 | -- | 0.1 | 1.1 | 1.2
1999 | -- | -- | 1.7 | -- | 1.7 | 0.1 | 1.8
2000 | -- | -- | 2.6 | -- | 2.6 | -- | 2.6
2001 | -- | -- | 12.6 | -- | 12.6 | 1.3 | 13.9
2002 | -- | -- | 5.6 | -- | 5.6 | 3.1 | 8.7
2003 | 1 | 6.8 | 2.4 | -- | 9.2 | 4.8 | 14
2004 | 1 | 7.2 | 0.3 | -- | 7.5 | 5.2 | 12.7
2005 | 2 | 7.4 | 1 | -- | 8.4 | 4.6 | 13
2006 | 1 | 9.5 | 1 | -- | 10.5 | 3.8 | 14.3
2007 | 2 | 17.1 | 4.5 | -- | 21.6 | 4.4 | 26
2008 | 2 | 8.2 | 3.8 | -- | 12 | 5.6 | 17.6
2009 | 1 | 17.1 | 3.7 | -- | 20.8 | 4.5 | 25.3
2010 | 1 | 6.8 | 2.6 | -- | 9.4 | 1.9 | 11.3
2011 | -- | -- | 2.8 | -- | 2.8 | 1.1 | 3.9
2012 | -- | -- | 7.3 | -- | 7.3 | 1.5 | 8.8
2013 | -- | -- | 4.4 | -- | 4.4 | 0.2 | 4.6
2014 | -- | -- | 1.5 | -- | 1.5 | 0.5 | 2
2015 | -- | -- | 2.2 | -- | 2.2 | 0.7 | 2.9
2016 | -- | -- | 1.3 | -- | 1.3 | 0.7 | 2
Subtotal | 11 | 80.1 | 62.2 | -- | 142.3 | 45.1 | 187.4

## Table 24
Annual Funding TY$
3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1998 | -- | -- | 4.5 | -- | 4.5 | 11.3 | 15.8
1999 | -- | -- | 5.9 | -- | 5.9 | 9.2 | 15.1
2000 | 3 | 28 | 7.9 | -- | 35.9 | 12.7 | 48.6
2001 | 2 | 33.7 | 12 | -- | 45.7 | 14.5 | 60.2
2002 | 4 | 32.4 | 0.3 | -- | 32.7 | 21.1 | 53.8
2003 | 1 | 13.3 | 2.9 | -- | 16.2 | 21.5 | 37.7
2004 | -- | -- | 13.2 | -- | 13.2 | 16.8 | 30
2005 | 1 | 28.3 | 2.5 | -- | 30.8 | 12.8 | 43.6
2006 | 3 | 34.3 | 5.5 | -- | 39.8 | 24.5 | 64.3
2007 | 6 | 40.6 | 2.2 | -- | 42.8 | 26.7 | 69.5
2008 | 4 | 50.3 | -- | -- | 50.3 | 15.1 | 65.4
2009 | 6 | 49.9 | -- | -- | 49.9 | 14.5 | 64.4
2010 | 4 | 42.2 | -- | -- | 42.2 | 14.5 | 56.7
2011 | 7 | 74.8 | -- | -- | 74.8 | 16.6 | 91.4
2012 | 3 | 34.5 | -- | -- | 34.5 | 10.8 | 45.3
2013 | -- | -- | 15.3 | -- | 15.3 | 7.4 | 22.7
2014 | -- | -- | 3.3 | -- | 3.3 | 4 | 7.3
2015 | -- | -- | 0.2 | -- | 0.2 | 2 | 2.2
2016 | -- | -- | 0.2 | -- | 0.2 | 2 | 2.2
2017 | -- | -- | 0.2 | -- | 0.2 | 2.5 | 2.7
2018 | -- | -- | 0.3 | -- | 0.3 | 2.5 | 2.8
Subtotal | 44 | 462.3 | 76.4 | -- | 538.7 | 263 | 801.7

## Table 25
Annual Funding BY$
3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2005 $M | Non End Item Recurring Flyaway BY 2005 $M | Non Recurring Flyaway BY 2005 $M | Total Flyaway BY 2005 $M | Total Support BY 2005 $M | Total Program BY 2005 $M
1998 | -- | -- | 4.9 | -- | 4.9 | 12.3 | 17.2
1999 | -- | -- | 6.3 | -- | 6.3 | 9.9 | 16.2
2000 | 3 | 29.7 | 8.4 | -- | 38.1 | 13.4 | 51.5
2001 | 2 | 35.1 | 12.6 | -- | 47.7 | 15.1 | 62.8
2002 | 4 | 33.2 | 0.3 | -- | 33.5 | 21.6 | 55.1
2003 | 1 | 13.8 | 3 | -- | 16.8 | 22.3 | 39.1
2004 | -- | -- | 13.4 | -- | 13.4 | 17.1 | 30.5
2005 | 1 | 27.9 | 2.5 | -- | 30.4 | 12.6 | 43
2006 | 3 | 32.9 | 5.3 | -- | 38.2 | 23.4 | 61.6
2007 | 6 | 37.9 | 2.1 | -- | 40 | 25 | 65
2008 | 4 | 46.1 | -- | -- | 46.1 | 13.8 | 59.9
2009 | 6 | 45.1 | -- | -- | 45.1 | 13.1 | 58.2
2010 | 4 | 37.6 | -- | -- | 37.6 | 12.9 | 50.5
2011 | 7 | 65.5 | -- | -- | 65.5 | 14.5 | 80
2012 | 3 | 29.6 | -- | -- | 29.6 | 9.3 | 38.9
2013 | -- | -- | 12.9 | -- | 12.9 | 6.3 | 19.2
2014 | -- | -- | 2.7 | -- | 2.7 | 3.4 | 6.1
2015 | -- | -- | 0.2 | -- | 0.2 | 1.6 | 1.8
2016 | -- | -- | 0.2 | -- | 0.2 | 1.6 | 1.8
2017 | -- | -- | 0.2 | -- | 0.2 | 1.9 | 2.1
2018 | -- | -- | 0.2 | -- | 0.2 | 2 | 2.2
Subtotal | 44 | 434.4 | 75.2 | -- | 509.6 | 253.1 | 762.7

## Table 26
Annual Funding TY$
1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1998 | -- | -- | 0.9 | -- | 0.9 | 1.3 | 2.2
1999 | 2 | 5.3 | -- | -- | 5.3 | 3.4 | 8.7
2000 | 5 | 27 | -- | -- | 27 | 6.4 | 33.4
2001 | -- | -- | 23.6 | -- | 23.6 | 7.8 | 31.4
2002 | 3 | 13.3 | -- | -- | 13.3 | 5.3 | 18.6
2003 | 2 | 5.1 | -- | -- | 5.1 | 1.9 | 7
2004 | 1 | 11.3 | -- | -- | 11.3 | 4.6 | 15.9
2005 | 1 | 8.4 | -- | -- | 8.4 | 4.7 | 13.1
2006 | 4 | 14.4 | -- | -- | 14.4 | 3.8 | 18.2
2007 | 4 | 22.8 | -- | -- | 22.8 | 4.5 | 27.3
2008 | 1 | 19.9 | -- | -- | 19.9 | 4.1 | 24
2009 | 3 | 21.5 | -- | -- | 21.5 | 1.5 | 23
2010 | 3 | 27.8 | -- | -- | 27.8 | 1.1 | 28.9
2011 | 1 | 16.6 | -- | -- | 16.6 | 0.8 | 17.4
2012 | 2 | 23.4 | -- | -- | 23.4 | 1.2 | 24.6
2013 | 1 | 13.2 | -- | -- | 13.2 | 1 | 14.2
2014 | -- | -- | 13.7 | -- | 13.7 | 0.8 | 14.5
2015 | -- | -- | 10.6 | -- | 10.6 | 0.6 | 11.2
2016 | -- | -- | 7 | -- | 7 | 0.2 | 7.2
Subtotal | 33 | 230 | 55.8 | -- | 285.8 | 55 | 340.8

## Table 27
Annual Funding BY$
1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2005 $M | Non End Item Recurring Flyaway BY 2005 $M | Non Recurring Flyaway BY 2005 $M | Total Flyaway BY 2005 $M | Total Support BY 2005 $M | Total Program BY 2005 $M
1998 | -- | -- | 1 | -- | 1 | 1.4 | 2.4
1999 | 2 | 5.7 | -- | -- | 5.7 | 3.7 | 9.4
2000 | 5 | 28.9 | -- | -- | 28.9 | 6.8 | 35.7
2001 | -- | -- | 25 | -- | 25 | 8.2 | 33.2
2002 | 3 | 13.9 | -- | -- | 13.9 | 5.5 | 19.4
2003 | 2 | 5.2 | -- | -- | 5.2 | 2 | 7.2
2004 | 1 | 11.3 | -- | -- | 11.3 | 4.6 | 15.9
2005 | 1 | 8.1 | -- | -- | 8.1 | 4.6 | 12.7
2006 | 4 | 13.5 | -- | -- | 13.5 | 3.6 | 17.1
2007 | 4 | 20.9 | -- | -- | 20.9 | 4.2 | 25.1
2008 | 1 | 18 | -- | -- | 18 | 3.7 | 21.7
2009 | 3 | 19.2 | -- | -- | 19.2 | 1.3 | 20.5
2010 | 3 | 24.3 | -- | -- | 24.3 | 1 | 25.3
2011 | 1 | 14.3 | -- | -- | 14.3 | 0.7 | 15
2012 | 2 | 19.8 | -- | -- | 19.8 | 1.1 | 20.9
2013 | 1 | 11 | -- | -- | 11 | 0.8 | 11.8
2014 | -- | -- | 11.2 | -- | 11.2 | 0.7 | 11.9
2015 | -- | -- | 8.5 | -- | 8.5 | 0.5 | 9
2016 | -- | -- | 5.5 | -- | 5.5 | 0.2 | 5.7
Subtotal | 33 | 214.1 | 51.2 | -- | 265.3 | 54.6 | 319.9

## Table 28
Low Rate Initial Production
The Current Total LRIP Quantity is more than 10% of the total production quantity due to Air Force approved amendment to the Acquisition Decision Memorandum (ADM) dated August 8, 2001, which authorized LRIP of up to 20 Digital Airport Surveillance Radars (DASRs) and 13 DoD Advanced Automation Systems (DAAS). This keeps DoD DASR production and deployment efforts on track avoiding shutdown, restart, and retraining impacts.
The LRIP quantity of eight DASR and zero DAAS approved at Milestone II during July 1995 was for the radar and automation portions of NAS.
| Initial LRIP Decision | Current Total LRIP
Approval Date | 7/1/1995 8/8/2001 8 20 Milestone II ADM ADM 1995 1995 2001 2001
Approved Quantity
Reference
Start Year
End Year

## Table 29
Foreign Military Sales
None
Nuclear Costs
None

## Table 30
Unit Cost
Unit Cost Report
|  | BY2005 $M | BY2005 $M
Unit Cost |  | Current UCR Baseline (JUL 2006 APB) | Current Estimate (DEC 2013 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 1373.2 |  |  | 1405.1
Quantity | 93 |  |  | 88
Unit Cost | 14.766 |  |  | 15.967 |  |  | 8.13
Average Procurement Unit Cost (APUC)
Cost | 1239.2 |  |  | 1270
Quantity | 93 |  |  | 88
Unit Cost | 13.325 |  |  | 14.432 |  |  | 8.31
|  | BY2005 $M | BY2005 $M
Unit Cost |  | Original UCR Baseline (JUL 1995 APB) | Current Estimate (DEC 2013 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 762.1 |  |  | 1405.1
Quantity | 53 |  |  | 88
Unit Cost | 14.379 |  |  | 15.967 |  | 11.04
Average Procurement Unit Cost (APUC)
Cost | 629.7 |  |  | 1270
Quantity | 53 |  |  | 88
Unit Cost | 11.881 |  |  | 14.432 |  | 21.47

## Table 31
Unit Cost History
[7 empty] | BY2005 $M |  |  |  | TY $M
|  |  | Date |  |  |  | PAUC |  | APUC |  | PAUC |  |  | APUC
Original APB |  |  | JUL 1995 |  |  |  | 14.27 |  | 11.789 |  | 14.926 |  |  | 12.711
APB as of January 2006 |  |  | JUN 2005 |  |  |  | 14.766 |  | 13.325 |  | 15.281 |  |  | 14.035
Revised Original APB |  |  | N/A |  |  |  | N/A |  | N/A |  | N/A |  |  | N/A
Prior APB |  |  | JUN 2005 |  |  |  | 14.766 |  | 13.325 |  | 15.281 |  |  | 14.035
Current APB |  |  | JUL 2006 |  |  |  | 14.766 |  | 13.325 |  | 15.281 |  |  | 14.035
Prior Annual SAR |  |  | DEC 2012 |  |  |  | 15.842 |  | 14.307 |  | 16.441 |  |  | 15.125
Current Estimate |  |  | DEC 2013 |  |  |  | 15.967 |  | 14.432 |  | 16.578 |  |  | 15.262
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Dev Est | Changes | [11 empty] | PAUC Prod Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt |  | Total
14.926 -0.815 -3.104 1.517 1.544 -0.791 0.000 2.004 0.355 15.281

## Table 32
Current SAR Baseline to Current Estimate (TY $M)
PAUC Prod Est | Changes | [15 empty] | PAUC Current Est
| Econ | Qty |  |  | Sch |  | Eng |  | Est |  | Oth |  | Spt |  |  | Total
15.281 0.011 0.327 0.091 0.000 1.383 0.000 -0.515 1.297 16.578
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Dev Est | Changes | [15 empty] | APUC Prod Est
| Econ |  | Qty |  |  | Sch |  | Eng |  | Est |  | Oth |  | Spt |  | Total
12.711 -0.747 -2.152 1.517 1.544 -0.842 0.000 2.004 1.324 14.035
Current SAR Baseline to Current Estimate (TY $M)
APUC Prod Est | Changes | [15 empty] | APUC Current Est
| Econ | Qty |  |  | Sch |  | Eng |  | Est |  | Oth |  | Spt |  |  | Total
14.035 0.023 0.256 0.091 0.000 1.372 0.000 -0.515 1.227 15.262
SAR Baseline History
Item/Event |  |  |  | SAR Planning Estimate (PE) | [5 empty] | SAR Development Estimate (DE) |  |  |  |  | SAR Production Estimate (PdE) |  |  | Current Estimate
Milestone I |  |  |  | JUL 1992 | [5 empty] | JUL 1992 |  |  |  |  | JUL 1992 |  |  | JUL 1992
Milestone II |  |  |  | JAN 1994 | [5 empty] | JUL 1995 |  |  |  |  | JUL 1995 |  |  | JUL 1995
Milestone III |  |  |  | MAR 1997 | [5 empty] | JUN 1998 |  |  |  |  | APR 2005 |  |  | JUN 2005
IOC |  |  |  | OCT 1999 | [5 empty] | APR 2000 |  |  |  |  | JAN 2003 |  |  | JAN 2003
Total Cost (TY $M) |  |  |  | 122.6 | [5 empty] | 791.1 |  |  |  |  | 1421.1 |  |  | 1458.9
Total Quantity |  |  |  | N/A | [5 empty] | 53 |  |  |  |  | 93 |  |  | 88
Prog. Acq. Unit Cost (PAUC) |  |  |  | N/A | [5 empty] | 14.926 |  |  |  |  | 15.281 |  |  | 16.578

## Table 33
Cost Variance
Summary Then Year $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 115.8 1305.3 -- 1421.1
Previous Changes
Economic |  | -1 |  | 3.5 |  | -- |  | 2.5
Quantity |  | -- |  | -47.6 |  | -- |  | -47.6
Schedule |  | -- |  | 8 |  | -- |  | 8
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 1 |  | 108.4 |  | -- |  | 109.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -46.6 |  | -- |  | -46.6
Subtotal |  | -- |  | 25.7 |  | -- |  | 25.7
Current Changes Economic |  | -- |  | -1.5 |  | -- |  | -1.5
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | 12.3 |  | -- |  | 12.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 1.3 |  | -- |  | 1.3
Subtotal |  | -- |  | 12.1 |  | -- |  | 12.1
Total Changes |  | -- |  | 37.8 |  | -- |  | 37.8
CE - Cost Variance |  | 115.8 |  | 1343.1 |  | -- |  | 1458.9
CE - Cost & Funding |  | 115.8 |  | 1343.1 |  | -- |  | 1458.9

## Table 34
Summary Base Year 2005 $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 134.0 1239.2 -- 1373.2
Previous Changes
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -38.5 |  | -- |  | -38.5
Schedule |  | -- |  | 10.9 |  | -- |  | 10.9
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 1.1 |  | 89.6 |  | -- |  | 90.7
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -42.2 |  | -- |  | -42.2
Subtotal |  | 1.1 |  | 19.8 |  | -- |  | 20.9
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | 9.5 |  | -- |  | 9.5
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 1.5 |  | -- |  | 1.5
Subtotal |  | -- |  | 11 |  | -- |  | 11
Total Changes |  | 1.1 |  | 30.8 |  | -- |  | 31.9
CE - Cost Variance |  | 135.1 |  | 1270 |  | -- |  | 1405.1
CE - Cost & Funding |  | 135.1 |  | 1270 |  | -- |  | 1405.1
Previous Estimate: December 2012

## Table 35
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -1.5
Army sites pulled forward to align with changes to Federal Aviation Administration fielding schedule. (Estimating)
Revised estimate reflects sequestration reduction in FY 2012 and FY 2013 (Air Force). (Estimating)
Congressional reduction early in FY 2013 resulted in a significant shift to many program efforts and a realignment of installations from FY 2013 to FY 2015 (Navy). (Estimating)
+4.0 +5.0
-3.2 -3.6
+8.0 +10.2
Adjustment for current and prior escalation. (Estimating) | 0.7 |  |  | 0.7
Adjustment for current and prior escalation. (Support) | 0.5 |  |  | 0.5
Increase in Other Support (Air Force). (Support) | 1 |  |  | 0.9
Decrease in Other Support (Navy). (Support) | 0 |  |  | -0.1
Procurement Subtotal | 11 |  |  | 12.1

## Table 36
Contracts
Appropriation: Procurement
Contract Name Digital Airport Surveillance Radar II
Contractor Raytheon Company
Contractor Location Marlborough, MA 01752
Contract Number, Type FA8730-08-D-0001/1, FFP/IDIQ
Award Date May 22, 2008
Definitization Date September 30, 2008
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price at Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
36.8 N/A 7 326.1 N/A 37 326.1 326.1
Target Price Change Explanation
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this FFP/IDIQ contract.
Contract Comments
The Initial Contract Price of $36.8M and the initial quantity of 7 represents the Delivery Orders (DOs) 0001-0009 awarded May 22, 2008, which encompass annual Program Management Operations, Technical Support Services and the initial 7 system orders.
The Current Contract Price of $326.1M and the current quantity of 37 represent contract funding and quantities ordered to date.
37 Quantities ordered to date:
• United States Air Force - 20
• United States Navy -13
• United States Army - 4
The maximum price and quantity and that could be contracted for under this Digital Airport Surveillance Radar Phase II FFP/IDIQ contract are $679M and 95 units respectively.

## Table 37
Deliveries and Expenditures
Delivered to Date | Plan to Date |  | Actual to Date | Total Quantity |  | Percent Delivered
Development | 0 |  | 0 |  | 0 | --
Production | 78 |  | 78 |  | 88 | 88.64%
Total Program Quantity Delivered | 78 |  | 78 |  | 88 | 88.64%
Expended and |  | Appropriated (TY $M)
Total Acquisition Cost | 1458.9 | Years Appropriated |  |  | 25
Expended to Date | 1275.5 | Percent Years Appropriated |  |  | 86.21%
Percent Expended | 87.43% | Appropriated to Date |  |  | 1424.4
Total Funding Years | 29 | Percent Appropriated |  |  | 97.64%
The above data is current as of 3/20/2014.

## Table 38
Operating and Support Cost
NAS
Assumptions and Ground Rules
Cost Estimate Reference:
The O&S cost estimate is based on analysis performed for the Milestone III decision, letter titled "Department of Defense (DOD) National Airspace System (NAS) Air Force Cost Analysis Improvement Group (AFCAIG) Service Cost Position (SCP)" from the Air Force Financial Management and Comptroller Cost and Economics office dated March 18, 2005.
Sustainment Strategy:
The estimate assumes a 34 year life from year FY 2000 to FY 2034 for the 88 sites.
Antecedent Information:
There is no antecedent system.
Unitized O&S Costs BY2005 $M
Cost Element |  | NAS Avg Annual Cost Per NAS Site |  | Avg Annual Cost Per (Antecedent) Antecedent
Unit-Level Manpower |  | 2.1 |  | 0
Unit Operations |  | 0.2 |  | 0
Maintenance |  | 0 |  | 0
Sustaining Support |  | 0.1 |  | 0
Continuing System Improvements |  | 0.4 |  | 0
Indirect Support |  | 0.3 |  | 0
Other |  | 0 |  | 0
Total |  | 3.1 |  | --
Unitized Cost Comments:
Total Cost = average annual cost per site* number of sites *planned service years = 3.1 * 88 * 34 = 9275.2
Total O&S Cost $M
| Current Production APB Objective/Threshold |  | Current Estimate
| NAS |  | NAS |  | Avg Annual Cost Per (Antecedent)
Base Year | N/A N/A 9275.2 N/A
Then Year | N/A N/A 11000.1 N/A
Total O&S Costs Comments: None

## Table 39
Disposal Costs:
None