## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-479
Combat Rescue Helicopter (CRH)
As of FY 2016 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 13
Cost and Funding 14
Low Rate Initial Production 22
Foreign Military Sales 23
Nuclear Costs 23
Unit Cost 24
Cost Variance 27
Contracts 30
Deliveries and Expenditures 32
Operating and Support Cost 33

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Combat Rescue Helicopter (CRH)
DoD Component
Air Force
Responsible Office
Mr. J. David Schairbaum 1895 5th Street
Area B, Bldg 46
Wright-Patterson Air Force Base, OH 45433-7200
james.schairbaum@us.af.mil
Phone: | 937-656-8278
Fax: | 937-656-7223
DSN Phone: | 986-8278
DSN Fax: | 986-7223
Date Assigned: | June 19, 2011
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated June 18, 2014
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated June 18, 2014

## Table 6
Mission and Description
The Combat Rescue Helicopter (CRH) system will provide Personnel Recovery (PR) forces with a vertical takeoff and landing aircraft that is quickly deployable and capable of main base and austere location operations for worldwide PR missions. CRH system activities may be required during any phase of a service/joint/coalition operation, across the full range of military operations, in any land or sea location, within the areas covered by the relevant defense planning scenarios.
The United States Air Force (USAF) has 12 Core Functions that address its unique capabilities in support of the Joint Functional Capabilities (JFC) across the full spectrum of political and military operations in all environments. The USAF has demonstrated its commitment to the Joint Force by making PR one of the 12 USAF Core Functions. The Air Force recognizes the inherent interdependence of PR, although established as an individual Core Function, with the other Core Functions as well as with the JFCs.
The CRH shall be capable of employment day or night, in adverse weather, and in a variety of threat spectrums from terrorist attacks to chemical, biological, radiological, and nuclear threats. A single pilot must be able to fly and operate all electronic/sensor weapons systems including countermeasures, leaving the second pilot to navigate, communicate, and manage mission execution. Onboard defensive capabilities will permit the CRH system to operate in an increased threat environment. An in-flight air refueling capability will provide an airborne alert capability and extend its combat mission range. The CRH system may conduct combat search and rescue airborne mission commander duties. The aircraft will be self-supporting to the maximum extent practical.
The CRH system may also conduct other collateral missions inherent in their capabilities to conduct PR, such as non- conventional assisted recovery, national emergency operations, civil search and rescue, international aid, emergency aero medical evacuation, disaster/humanitarian relief, counter drug activities, support for National Aeronautics and Space Administration flight operations, and insertion/extraction of combat forces.

## Table 7
Executive Summary
CRH is an ACAT ID program entering the acquisition process at the EMD phase.
The United States Air Force (USAF) CRH program addresses the need to replace the USAF's aging HH-60G Pave Hawk helicopters (air vehicles, training systems, and product support) with a new system. The CRH program will replace the aging fleet by leveraging in-production air vehicles and training systems and integrating existing technologies to acquire a new system.
The CRH contract was awarded to Sikorsky Aircraft Corporation (SAC) on June 26, 2014. Both SAC and the CRH program office have ramped up manning in the first six months of execution. In this timeframe, the program has also conducted a Program Startup Workshop, Program Management Review, and Integrated Baseline Review. The program is on track to conduct the air vehicle System Requirements Review (SRR) and System Functional Review (SFR) in April 2015 and the training system SRR/SFR in June 2015.
At Milestone B approval, four of the 2366b provisions were required to be waived by the USD(AT&L). Two of the four provisions were due to sequestration and reprogramming of funds in the FY 2015 budget process, thus (a)(1)(B) Cost/Schedule/Performance Tradeoff and (a)(1)(D) Full Funding were not able to be satisfied at the point of milestone approval. To meet these two certification provisions, the USAF realigned funding in the FY 2016 budget process to fund the program to the Milestone B SCP. Relative to the third waived provision, (a)(2), the program will satisfy the certification requirement upon completion of the Preliminary Design Review, which is scheduled to occur in April 2016. For the fourth and final waived provision, (a)(3)(D), the USD(AT&L) determined that a Technology Readiness Assessment (TRA) was not required for milestone approval based upon the maturity of the required technology. A TRA will be conducted in summer 2015 to satisfy this waived provision requirement. The USD(AT&L) will continue periodic reviews, in accordance with subsection (d)(2)(B), until a certification determination can be made for the waived provisions.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | Jun 2014 | Jun 2014 | Dec 2014 | Jun 2014
PDR | Apr 2016 | Apr 2016 | Oct 2016 | Apr 2016
CDR | Jul 2017 | Jul 2017 | Jan 2018 | Jul 2017
DT&E Start | Sep 2018 | Sep 2018 | Mar 2019 | Sep 2018
Milestone C | Oct 2019 | Oct 2019 | Apr 2020 | Oct 2019
RAA | Sep 2020 | Sep 2020 | Mar 2021 | Sep 2020
FRP Decision | Oct 2021 | Oct 2021 | Apr 2022 | Oct 2021
Change Explanations
Notes
RAA is defined as delivery of eight production configuration aircraft (four mission & four training) with all required training devices, spares, support equipment, technical manuals, and sustainment support in place to support IOC .
Acronyms and Abbreviations
CDR - Critical Design Review
DT&E - Development Test & Evaluation PDR - Preliminary Design Review
RAA - Required Assets Available

## Table 10
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Hover Performance
A combat configured HH-60 Recap with SCL shall have an OGE hover capability at mid- mission gross weights at 6,000' PA, 35°C. | A combat configured HH-60 Recap with SCL shall have an OGE hover capability at mid-mission gross weights at 6,000' PA, 35°C. | A combat configured HH -60 Recap with SCL shall have an OGE hover capability at mid- mission gross weights at 4,000' PA, 35°C. | TBD | A combat configured HH -60 Recap with SCL shall have an OGE hover capability at mid- mission gross weights at 4,000' PA, 35°C.
Survivability
(Objective= Threshold) HH-60 Recap aircraft shall provide vulnerability reduction at least equal to existing HH-60G vulnerability reduction features - protection for the pilot, copilot and all flight critical components or subsystems against ground-fired 7.62 mm armor piercing projectiles at 100 meters. | (Objective= Threshold) HH-60 Recap aircraft shall provide vulnerability reduction at least equal to existing HH- 60G vulnerability reduction features - protection for the pilot, copilot and all flight critical components or subsystems against ground-fired 7.62 mm armor piercing projectiles at 100 meters. | HH-60 Recap aircraft shall provide vulnerability reduction at least equal to existing HH-60G vulnerability reduction features - protection for the pilot, copilot and all flight critical components or subsystems against ground-fired 7.62 mm armor piercing projectiles at 100 meters. | TBD | HH-60 Recap aircraft shall provide vulnerability reduction at least equal to existing HH-60G vulnerability reduction features - protection for the pilot, copilot and all flight critical components or subsystems against ground-fired 7.62 mm armor piercing projectiles at 100 meters.
Force Protection
Pilot and copilot seating to 14.5 mm AP projectiles at 500 meters. Walls around the primary cabin crew member positions and the entire cabin floor to 14.5 mm AP at 500 meters. | Pilot and copilot seating to 14.5 mm AP projectiles at 500 meters. Walls around the primary cabin crew member positions and the entire cabin floor to 14.5 mm AP at 500 meters. | Pilot and copilot seating will incorporate ballistic hardening to defeat 7.62 mm AP projectiles at 100 meters. The cabin walls around the primary cabin crew member positions and the entire cabin floor will have the capability to defeat 7.62 mm AP projectiles at 100 meters. | TBD | Pilot and copilot seating will incorporate ballistic hardening to defeat 7.62 mm AP projectiles at 100 meters. The cabin walls around the primary cabin crew member positions and the entire cabin floor will have the capability to defeat 7.62 mm AP projectiles at 100 meters
Net Ready
Execution of all operational activities and information | Execution of all operational activities and information | The capability, system, and/or service shall fully support execution of | TBD | The capability, system, and/or service shall fully support execution of

## Table 11
exchanges identified and information assurance requirements including availability, integrity, authentic-ation, confident-iality, and non -repudiation, and issuance of an ATO by the DAA. | exchanges identified and information assurance requirements including availability, integrity, authentic- ation, confident-iality, and non-repudiation, and issuance of an ATO by the DAA. | joint critical operational activities and information exchanges identified in the DoD Enterprise Architecture and solution architectures based on integrated DoDAF content, and shall satisfy the technical requirements for transition to Net-Centric military operations. Issuance of an IATO or ATO by the DAA. |  | joint critical operational activities and information exchanges identified in the DoD Enterprise Architecture and solution architectures based on integrated DoDAF content, and shall satisfy the technical requirements for transition to Net-Centric military operations. Issuance of an IATO or ATO by the DAA.
Sustainment (Material Availability)
(Objective= Threshold) MC rate of 83 percent at IOC | (Objective= Threshold) MC rate of 83 percent at IOC | MC rate of 83 percent at IOC | TBD | MC rate of 83 percent at IOC
System Training Process
(Objective= Threshold) HH-60 Recap shall provide operations and maintenance training systems | (Objective= Threshold) HH-60 Recap shall provide operations and maintenance training systems | HH-60 Recap shall provide operations and maintenance training systems | TBD | HH-60 Recap shall provide operations and maintenance training systems
Requirements Reference
Capability Development Document (CDD) for HH-60 Recapitalization Aircraft dated July 6, 2010 CDD Supplement for HH-60 Recapitalization Aircraft dated July 20, 2012
Change Explanations
None
Notes
CRH referred to as HH-60 Recap in CDD.

## Table 12
Acronyms and Abbreviations
AP - Armor Piercing
ATO - Authorization to Operate C - Celsius
DAA - Designated Accrediting Authority DoDAF - Department of Defense Air Force IATO - Interim Authorization to Operate MC - Mission Capable
mm - Millimeter
OGE - Out of Ground Effect PA - Pressure Altitude
SCL - Standard Combat Load

## Table 13
Track to Budget
RDT&E
Appn |  | BA | PE
Air Force 3600 05 0605229F
Project | Name
654364 Combat Rescue Helicopter
Procurement
Appn |  | BA | PE
Air Force 3010 04 0207229F
Line Item | Name
10HHX0 Combat Rescue Helicopter
MILCON
Appn |  | BA | PE
Air Force 3300 01 0207229F
Project | Name
VARIOUS Combat Rescue Helicopter Simulator

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2014 $M | [5 empty] | BY 2014 $M |  | TY $M
| SAR Baseline Development Estimate |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E | 1958.8 |  |  | 1958.8 | 2154.7 |  |  | 1972.9 |  | 2118.6 |  |  | 2118.6 |  | 2105.9
Procurement | 6108.4 |  |  | 6108.4 | 6719.2 |  |  | 6181.9 |  | 7708.7 |  |  | 7708.7 |  | 7708.7
Flyaway | -- |  |  | -- | -- |  |  | 4516.4 |  | -- |  |  | -- |  | 5643.9
Recurring | -- |  |  | -- | -- |  |  | 4488.8 |  | -- |  |  | -- |  | 5611.7
Non Recurring | -- |  |  | -- | -- |  |  | 27.6 |  | -- |  |  | -- |  | 32.2
Support | -- |  |  | -- | -- |  |  | 1665.5 |  | -- |  |  | -- |  | 2064.8
Other Support | -- |  |  | -- | -- |  |  | 1266.8 |  | -- |  |  | -- |  | 1568.3
Initial Spares | -- |  |  | -- | -- |  |  | 398.7 |  | -- |  |  | -- |  | 496.5
MILCON | 23.7 |  |  | 23.7 | 26.1 |  |  | 23.8 |  | 28.9 |  |  | 28.9 |  | 28.9
Acq O&M | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 8090.9 |  |  | 8090.9 | N/A |  |  | 8178.6 |  | 9856.2 |  |  | 9856.2 |  | 9843.5
Current APB Cost Estimate Reference
Service Cost Position (SCP) dated June 18, 2014
Confidence Level
Confidence Level of cost estimate for current APB: 61%
The Service Cost Position represents the expected value for both the Research, Development, Test and Evaluation (RDT&E) and production estimates. This portion of the estimate takes into consideration relevant risks, including ordinary levels of external and unforeseen events. It aims to provide sufficient resources to execute the program under normal conditions encountering average levels of technical, schedule and programmatic risk.
Total Quantity
Quantity |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  | 9 |  |  |  | 9 |  |  |  |  | 9
Procurement |  | 103 |  |  |  | 103 |  |  |  |  | 103
Total |  | 112 |  |  |  | 112 |  |  |  |  | 112

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2016 President's Budget / December 2014 SAR (TY$ M)
Appropriation | Prior | FY 2015 |  | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | To Complete |  | Total
RDT&E | 377.4 | 100 |  | 156.1 |  | 422.5 |  | 457.9 |  | 415.4 |  | 135 |  | 41.6 |  | 2105.9
Procurement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 89.6 |  | 628 |  | 6991.1 |  | 7708.7
MILCON | 0 | 0 |  | 0 |  | 0 |  | 7.3 |  | 2.8 |  | 0 |  | 18.8 |  | 28.9
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2016 Total | 377.4 | 100 |  | 156.1 |  | 422.5 |  | 465.2 |  | 507.8 |  | 763 |  | 7051.5 |  | 9843.5
| -- | -- |  | -- |  | -- |  | -- |  | -- |  | -- |  | -- |  | --
Funding Notes
Program full funding is resolved in the FY 2016 PB.
Quantity Summary
FY 2016 President's Budget / December 2014 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2015 | FY 2016 | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | To Complete |  | Total
Development | 9 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 9
Production | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 8 |  | 95 |  | 103
PB 2016 Total | 9 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 8 |  | 95 |  | 112
| -- |  | -- |  | -- | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.1
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.8
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 333.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 100
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 156.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 422.5
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 457.9
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 415.4
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 135
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.4
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.2
Subtotal |  | 9 | -- |  | -- |  | -- |  | -- |  | -- |  | 2105.9

## Table 17
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2014 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.9
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 329.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 97.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 149.7
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 397.7
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 422.8
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 376
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 119.8
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.6
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.2
Subtotal |  | 9 | -- |  | -- |  | -- |  | -- |  | -- |  | 1972.9

## Table 18
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | 89.6 |  | 89.6
2020 |  | 8 | 475.5 |  | -- |  | 24.2 |  | 499.7 |  | 128.3 |  | 628
2021 |  | 10 | 568.1 |  | -- |  | 8 |  | 576.1 |  | 343.8 |  | 919.9
2022 |  | 14 | 735.6 |  | -- |  | -- |  | 735.6 |  | 234.8 |  | 970.4
2023 |  | 14 | 745.6 |  | -- |  | -- |  | 745.6 |  | 286.9 |  | 1032.5
2024 |  | 14 | 757.6 |  | -- |  | -- |  | 757.6 |  | 275.7 |  | 1033.3
2025 |  | 14 | 760 |  | -- |  | -- |  | 760 |  | 214.4 |  | 974.4
2026 |  | 14 | 768.3 |  | -- |  | -- |  | 768.3 |  | 219.6 |  | 987.9
2027 |  | 15 | 801 |  | -- |  | -- |  | 801 |  | 270.6 |  | 1071.6
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | 1.1 |  | 1.1
Subtotal |  | 103 | 5611.7 |  | -- |  | 32.2 |  | 5643.9 |  | 2064.8 |  | 7708.7

## Table 19
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | BY 2014 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | 78.7 |  | 78.7
2020 |  | 8 | 409.7 |  | -- |  | 20.8 |  | 430.5 |  | 110.6 |  | 541.1
2021 |  | 10 | 479.9 |  | -- |  | 6.8 |  | 486.7 |  | 290.3 |  | 777
2022 |  | 14 | 609.2 |  | -- |  | -- |  | 609.2 |  | 194.4 |  | 803.6
2023 |  | 14 | 605.3 |  | -- |  | -- |  | 605.3 |  | 233 |  | 838.3
2024 |  | 14 | 603 |  | -- |  | -- |  | 603 |  | 219.5 |  | 822.5
2025 |  | 14 | 593.1 |  | -- |  | -- |  | 593.1 |  | 167.3 |  | 760.4
2026 |  | 14 | 587.8 |  | -- |  | -- |  | 587.8 |  | 168 |  | 755.8
2027 |  | 15 | 600.8 |  | -- |  | -- |  | 600.8 |  | 202.9 |  | 803.7
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.8 |  | 0.8
Subtotal |  | 103 | 4488.8 |  | -- |  | 27.6 |  | 4516.4 |  | 1665.5 |  | 6181.9

## Table 20
Annual Funding 3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | TY $M
Total Program
2018 | 7.3
2019 | 2.8
2020 | --
2021 | 2.9
2022 | 4.5
2023 | 2.2
2024 | --
2025 | 6.5
2026 | 2.7
Subtotal | 28.9

## Table 21
Annual Funding 3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | BY 2014 $M
Total Program
2018 | 6.5
2019 | 2.4
2020 | --
2021 | 2.4
2022 | 3.7
2023 | 1.8
2024 | --
2025 | 5
2026 | 2
Subtotal | 23.8

## Table 22
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2014-06-18 | 2014-06-18
Approved Quantity | 18 | 18
Reference | Milestone B ADM | Milestone B ADM
Start Year | 2019 | 2019
End Year | 2021 | 2021
The Current Total LRIP Quantity is more than 10% of the total production quantity due to 18 aircraft being the minimum quantity necessary to establish an initial production base for the system as permitted by section 2400 of title 10, United States Code, subsection (b).
The APB was approved based on six full-rate production lots. The relatively small total quantity of aircraft produced will require an LRIP quantity of more than 10 percent. There is an approved LRIP quantity of 18 aircraft.

## Table 23
Foreign Military Sales
None
Nuclear Costs
None

## Table 24
Unit Cost
Unit Cost Report
Item |  | BY 2014 $M | BY 2014 $M |  | % Change
|  | Current UCR Baseline (Jun 2014 APB) | Current Estimate (Dec 2014 SAR)
Program Acquisition Unit Cost
Cost | 8090.9 |  |  | 8178.6
Quantity | 112 |  |  | 112
Item | 72.24 |  |  | 73.023 |  | 1.08
Average Procurement Unit Cost
Cost | 6108.4 |  |  | 6181.9
Quantity | 103 |  |  | 103
Unit Cost | 59.305 |  |  | 60.018 |  | 1.2
Item |  | BY 2014 $M | BY 2014 $M |  | % Change
|  | Original UCR Baseline (Jun 2014 APB) | Current Estimate (Dec 2014 SAR)
Program Acquisition Unit Cost
Cost | 8090.9 |  |  | 8178.6
Quantity | 112 |  |  | 112
Unit Cost | 72.24 |  |  | 73.023 |  | 1.08
Average Procurement Unit Cost
Cost | 6108.4 |  |  | 6181.9
Quantity | 103 |  |  | 103
Unit Cost | 59.305 |  |  | 60.018 |  | 1.2

## Table 25
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2014 $M | [6 empty] | TY $M
[8 empty] | PAUC |  | APUC |  |  |  |  | PAUC |  |  | APUC
Original APB |  |  | Jun 2014 |  |  |  |  | 72.24 |  |  |  | 59.305 |  |  |  | 88.002 |  |  | 74.842
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A |  |  | N/A
Prior APB |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A |  |  | N/A
Current APB |  |  | Jun 2014 |  |  |  |  | 72.24 |  |  |  | 59.305 |  |  |  | 88.002 |  |  | 74.842
Prior Annual SAR |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A |  |  | N/A
Current Estimate |  |  | Dec 2014 |  |  |  |  | 73.023 |  |  |  | 60.018 |  |  |  | 87.888 |  |  | 74.842
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [15 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  |  | Total
88.002 -1.016 0.000 0.000 0.000 0.683 0.000 0.219 -0.114 87.888
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [15 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth |  | Spt |  |  | Total
74.842 -0.890 0.000 0.000 0.000 0.652 0.000 0.238 0.000 74.842

## Table 26
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Jun 2014 | N/A | Jun 2014
Milestone C | N/A | Oct 2019 | N/A | Oct 2019
IOC | N/A | Sep 2020 | N/A | Sep 2020
Total Cost (TY $M) | N/A | 9856.2 | N/A | 9843.5
Total Quantity | N/A | 112 | N/A | 112
PAUC | N/A | 88.002 | N/A | 87.888
Required Assets Available is used in lieu of IOC and is defined as delivery of eight production configuration aircraft (four mission & four training) with all required training devices, spares, support equipment, technical manuals, and sustainment support in place to support IOC.

## Table 27
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 2118.6 | 7708.7 | 28.9 | 9856.2
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | -- | -- | --
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -- | -- | -- | --
Current Changes
Economic | -21.9 | -91.7 | -0.1 | -113.7
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 9.2 | 67.2 | 0.1 | 76.5
Other | -- | -- | -- | --
Support | -- | 24.5 | -- | 24.5
Subtotal | -12.7 | -- | -- | -12.7
Total Changes | -12.7 | -- | -- | -12.7
CE - Cost Variance | 2105.9 | 7708.7 | 28.9 | 9843.5
CE - Cost & Funding | 2105.9 | 7708.7 | 28.9 | 9843.5

## Table 28
Summary BY 2014 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
1958.8 6108.4 23.7 8090.9
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | -- |  | -- |  | --
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -- |  | -- |  | -- |  | --
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 14.1 |  | 53.8 |  | 0.1 |  | 68
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 19.7 |  | -- |  | 19.7
Subtotal |  | 14.1 |  | 73.5 |  | 0.1 |  | 87.7
Total Changes |  | 14.1 |  | 73.5 |  | 0.1 |  | 87.7
CE - Cost Variance |  | 1972.9 |  | 6181.9 |  | 23.8 |  | 8178.6
CE - Cost & Funding |  | 1972.9 |  | 6181.9 |  | 23.8 |  | 8178.6
Previous Estimate: June 2014

## Table 29
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -21.9
Revised estimate to reflect the application of new out-year escalation indices. (Estimating) | 12.4 | 7.5
Adjustment for current and prior escalation. (Estimating) | 1.7 | 1.7
RDT&E Subtotal | 14.1 | -12.7
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -91.7
Revised estimate to reflect the application of new out-year escalation indices. (Estimating) +53.8 +67.2
Revised Other Support estimate to reflect the application of new out-year escalation indices. (Support)
Revised Initial Spares estimate to reflect the application of new out-year escalation indices. (Support)
+15.0 +18.7
+4.7 +5.8
Procurement Subtotal +73.5 0.0
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.1
Revised estimate to reflect the application of new out-year escalation indices. (Estimating) | 0.1 | 0.1
MILCON Subtotal | 0.1 | 0

## Table 30
Contracts
General Notes
Estimated Price at Completion if all CLIN options over 15 years are executed is $7.9B (at target).
Contract Identification
Appropriation: RDT&E
Contract Name: Combat Rescue Helicopter
Contractor: Sikorsky Aircraft Corp.
Contractor Location: 6900 Main Street
Stratford, CT 06614
Contract Number: FA8629-14-C-2403
Contract Type: Fixed Price Incentive(Firm Target) (FPIF), Firm Fixed Price (FFP), Cost Plus Fixed Fee (CPFF)
Award Date: June 26, 2014
Definitization Date: June 26, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1277.6 1380.0 N/A 1277.6 1380.0 N/A 1277.6 1277.6
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2014) -1.4 -3.5
Previous Cumulative Variances 0.0 0.0
Net Change -1.4 -3.5
Cost and Schedule Variance Explanations
The unfavorable cumulative cost variance is due to greater effort being expended than anticipated in the baseline.
The unfavorable cumulative schedule variance is due to staffing, training and resource allocation.

## Table 31
Notes
At contract award:
- Initial Contract Price: $1,277,618,606 (Face Value of Contract)
- Target Price: CLINs 0001 and 0002: $1,261,176,821
- Ceiling Price: CLINs 0001 and 0002: $1,363,590,492
- FFP: CLIN 0006: $16,441,785
EMD: $1,501,556,957 LRIP: $1,155,870,141 FRP: $5,253,672,404

## Table 32
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 9 | 0%
Production | 0 | 0 | 103 | 0%
Total Program Quantity Delivered | 0 | 0 | 112 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
9843.5
22.6
0.23%
17
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
4
23.53%
477.4
4.85%
The above data is current as of January 31, 2015.

## Table 33
Operating and Support Cost
Cost Estimate Details
Date of Estimate: June 18, 2014
Source of Estimate: SCP
Quantity to Sustain: 112
Unit of Measure: Aircraft
Service Life per Unit: 27.00 Years
Fiscal Years in Service: FY 2020 - FY 2054
Sustainment Strategy
The Product Support Strategy for CRH is 2-level maintenance, organic at both Organizational and Depot levels. The prime contractor, Sikorsky Aircraft Corporation, will develop, implement and maintain an Integrated Logistic Support (ILS) Plan in conjunction with the Program Office.
- Primary Aerospace Vehicle Inventory (PAI): 91
- Mission Capability Goal: 83%
- Materiel Availability Goal: 67.4%
- Mean Time Between Critical Failure Goal: > 28.5 hours
- Mean Time Between Maintenance Goal: > 0.30 hours
- Mean Down Time Goal: > 20.8 hours
- Service Life: 8,000 hour life
Antecedent Information
(As of May 1, 2014)
- HH-60G
- Total Quantity: 97
- PAI: 87
-- Note: 21 Operational Loss Replacement (OLR) aircraft are not included, currently being acquired. Anticipate additional HH-60G aircraft retirements due to excessive flying hours.
-- The HH-60Us are not included
- Mission Capability Rate: 73.4%
- Materiel Availability Rate: 57.1%
- Mean Time Between Critical Failure Rate: 15.4 hrs
- Mean Time Between Maintenance Rate: 0.18 hrs
- Mean Down Time Rate: 21.4 hrs
CRH costs shown in comparison to the antecedent system, HH-60G, reflect estimated average annual cost per primary authorized aircraft (PAA). The HH-60G was normalized for comparison to the CRH to reflect programmatic differences and estimating methodologies. The cost per PAA of the HH-60G was projected using Air Force Total Ownership Cost (AFTOC) system historical data. Costs for the HH-60G were normalized to reflect the CRH assumption of 360 annual flying hours per aircraft. This cost comparison excludes Indirect Support costs for the HH-60G antecedent system because the costs captured in the AFTOC database are incomplete and do not provide a meaningful comparison to those estimated for CRH.

## Table 34
Annual O&S Costs BY2014 $M
Cost Element |  | CRH Average Annual Cost Per Aircraft | [5 empty] | HH-60G (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower |  | 3.1 | [5 empty] | 3.5
Unit Operations |  | 1.1 | [5 empty] | 1
Maintenance |  | 2.6 | [5 empty] | 2.6
Sustaining Support |  | 0.5 | [5 empty] | 0.3
Continuing System Improvements |  | 0.7 | [5 empty] | 0.6
Indirect Support |  | 1.5 | [5 empty] | --
Other |  | -- | [5 empty] | --
Total |  | 9.5 | [5 empty] | 8
CRH average annual cost per aircraft assumes full funding of program requirements (unconstrained), whereas the HH- 60G reflects projected actual costs reported in the AFTOC system (constrained). Also, the cost of extending the life of the HH-60G is not reflected. The comparison is not adjusted for any capability differences, costs savings or efficiencies that may exist between the two systems.
Item | Total O&S Cost $M
| CRH | [7 empty] | HH-60G (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 24529.5 |  |  | 26982.5 |  |  | 24529.5 |  | N/A
Then Year | 40982.5 |  |  | N/A |  |  | 40982.5 |  | N/A
Equation to Translate Annual Cost to Total Cost
The CRH O&S annual unitized cost of $9.5M is calculated based on a steady state PAA fleet of 91 aircraft beginning in FY30 and ending in FY43. It is not possible to extrapolate this cost to a total O&S cost as it does not capture ramp up (FY20-29) or ramp down (FY44-54) years.
O&S Cost Variance
Category |  |  | BY 2014 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Jun 2014 SAR
24529.5
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 24529.5

## Table 35
Disposal Estimate Details
Date of Estimate: June 18, 2014
Source of Estimate: SCP
Disposal/Demilitarization Total Cost (BY 2014 $M): Total costs for disposal of all Aircraft are 29.3
TY$M: 76.2 (Total Cost)