## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-284
Joint Tactical Networks (JTN)
As of FY 2016 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 10
Schedule 11
Performance 14
Track to Budget 17
Cost and Funding 18
Low Rate Initial Production 30
Foreign Military Sales 31
Nuclear Costs 31
Unit Cost 32
Cost Variance 35
Contracts 38
Deliveries and Expenditures 48
Operating and Support Cost 49

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Joint Tactical Networks (JTN)
DoD Component
Army
Joint Participants
Army; Navy; Air Force
Responsible Office
CAPT Kevin Peterson Program Manager
JTNC Joint Tactical Networks (JTN) 33000 Nixie Way, Building 50, Suite 330 San Diego, CA 92147
kevin.r.peterson1@navy.mil
Phone: 619-524-5799
Fax: 619-524-5857
DSN Phone: DSN Fax:
Date
Assigned: September 15, 2011
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated June 24, 2002
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated December 21, 2009

## Table 6
Mission and Description
Joint Tactical Networks (JTN) develops and sustains portable, interoperable, and mobile ad hoc networking software-defined waveforms for Joint operations, as well as the associated network manager for these waveforms. Networking software- defined waveforms include: the Soldier Radio Waveform (SRW), the Wideband Networking Waveform (WNW), the Mobile User Objective System (MUOS) waveform, and the Link-16 waveform. The Joint Enterprise Network Manager supports network management functions (planning, provisioning, monitoring, and controlling) of the SRW, WNW, and MUOS waveforms. These waveforms, as well as 14 other legacy waveforms, are coded as software-defined waveforms and capable of operating in a variety of hardware radio platforms for both Programs of Record and commercial, Non- Developmental Items. This model of common Government controlled waveforms and network manager capable of being instantiated upon multiple various hardware radios systems enables Joint interoperability for tactical networks across the military services and fosters a competitive marketplace for multiple vendors to provide competitively priced interoperable products. Project Manager JTN employs a competitive contracting strategy for software sustainment of the waveforms and the network manager to ensure warfighter access to the best technology and innovative capabilities while addressing emerging threats and future requirements via an affordable, operationally effective, and timely framework.

## Table 7
Executive Summary
In a July 2012 ADM, the USD(AT&L), as MDA, approved the transition of the Joint Program Executive Office for Joint Tactical Radio System (JTRS) to the Joint Tactical Networking Center (JTNC). With this transition, the program management and execution responsibility of the JTNC was assigned to the Army, the JTRS hardware programs were transitioned to the respective Military Department-managed programs, and JTRS Network Enterprise Domain was renamed the Joint Tactical Networks (JTN) program with the Army designated as lead Service. In October 2012, the Army assigned the JTNC and the JTN program as PM JTN to the PEO for Command, Control and Communications – Tactical. On January 20, 2014, the MDA signed a follow-on ADM outlining the responsibilities for the JTN and JTNC. The ADM delegated responsibility to the JTNC to manage a jointly funded common Waveform Information Repository (IR); to sustain and evolve the Software Communications Architecture, Application Program Interfaces, and wireless communications standards; and to conduct technical assessments. The ADM delegated responsibility to JTN for the development and sustainment of the Joint Enterprise Network Manager (JENM) as well as the identification and reporting of waveform interoperability issues.
Additionally, the ADM established a JTNC Board of Directors which will meet at least annually to address waveform issues within the DoD. PM JTN is on-track to transition JTN waveforms to the individual Military Departments for sponsorship by 4th Quarter FY 2015. Specifically, Soldier Radio Waveform (SRW), Single Channel Ground Air Radio System (SINCGARS), and Wideband Networking Waveform (WNW) will transition to the Army for maintenance, sustainment and upgrades while Mobile User Objective System (MUOS) and Link-16 will transition to the Navy for maintenance, sustainment and upgrades. The other JTRS developed, JTN managed, software-defined versions of legacy waveforms will be sponsored by the individual Services.
Currently, PM JTN actively manages and is funded only to develop, update and sustain SRW, WNW, MUOS, Link-16, and JENM through FY 2015. FY 2016 funding and beyond supports efforts for JENM, SRW, and WNW that relate to on-going software code changes and upgrades that support the fielding of Software Defined Radios which connect to the operational network. Networked radios allow for secure communications without the use of vulnerable commercial cellphones. PM JTN has the capability to enhance, update, and sustain the following waveforms via a reimbursable basis: the High Frequency waveform, the HAVE QUICK II waveform, the JTRS Bowman Waveform, the SINCGARS waveform, the Ultra High Frequency (UHF) Satellite Communications waveforms, and the Very High Frequency (VHF)/UHF Line of Sight waveforms. A description of product development and sustainment activities conducted in FY 2014 follows for products programmed and funded by PM JTN as well as products supported via reimbursable funds received in FY 2014.
Soldier Radio Waveform (SRW):
SRW successfully completed Formal Qualification Test (FQT) in January 2009, and was: 1) a key component of both the Handheld, Manpack and Small Form Fit (HMS) Rifleman Radio Initial Operational Test & Evaluation (IOT&E) conducted at Network Integration Evaluation (NIE) 12.1 in November 2011 and the HMS Manpack (MP) Multi-Service Operational Test & Evaluation (MOT&E) conducted at NIE 12.2 in May 2012; and 2) has been subsequently fielded on 19,327 HMS Rifleman Radios and 5,179 HMS MPs. Recent SRW enhancements include: 1) Release of SRW 1.2.1 in October 2014, which provides a Combat Net Radio voice pre-emption capability and additional enhancements such as Voice-only Mode, Receive
-only Mode, Neighbor Visualization Table update, and dynamic gateway improvements; and 2) the addition of an Over-The- Air Management (OTAM) capability, which will provide/include Over-The-Air Key Transfer, Over-The-Air Zeroize, and Over- The-Air Reconfiguration. An OTAM Critical Design Review was completed in July 2014, and a final software delivery will be provided in February 2015 to support Mid-Tier Networking Vehicular Radio (MNVR) Limited User Test (LUT).
Wideband Networking Waveform (WNW):
WNW successfully completed FQT in December 2009 and is scheduled for MNVR IOT&E during NIE 16.2, with fielding to the Brigade Combat Teams beginning in January 2017. WNW v4.1 was released in December 2014. It reduces network overhead and fixes defects that cause duplicate multicast packets to be transmitted. WNW 4.2 will be released in June 2015 and will incorporate critical Information Assurance (IA) fixes, eliminate 30 mode throughput test router failures, improve Protocol-Independent Multicast-Dense Mode pruning, and incorporate Enterprise OTAM capability.

## Table 8
Mobile User Objective System (MUOS) waveform:
MUOS Waveform v3.1 successfully completed FQT in November 2012. Baseline maintenance is on-going to address open Program Change Requests (PCRs) and correct deficiencies found by the National Security Agency (NSA) during IA assessments. JTN continues to work closely with Space and Naval Warfare Systems Command (SPAWAR) and PEO Space Systems’ PMW-146 supporting end-to-end testing in preparation for MUOS technical evaluation (TECHEVAL) and MOT&E, currently scheduled for October 2015. MUOS Waveform version 3.1.2 posted to the IR in February 2014, and since then two interim engineering releases have been posted that resolve PCRs found during MUOS end-to-end integration. The final MUOS waveform version, v3.1.3, which will be the same waveform tested in the TECHEVAL and MOT&E, will be posted to the JTNC IR in May 2015. MUOS is scheduled to transition to PMW-146 in June 2015, pursuant to the January 2014 JTN ADM.
Link-16 software-defined waveform:
Link-16 successfully completed FQT in April 2009 and has been fielded with the Multifunctional Information Distribution System (MIDS) JTRS radio in support of F/A-18E/F aircraft beginning in December 2009. The NSA adjudicated all architecture and software design IA findings on Link-16 v1.06.0.2 in August 2013 and considers the waveform to be an acceptable baseline. The formal NSA acceptance letter was received in November 2013. A MIDS on-ship upgrade, which will provide Navy surface ships with a cryptographic modernized Link-16 waveform capable of running on a MIDS-JTRS terminal, is being developed in parallel with the MIDS Block Cycle 2 upgrade, and was delivered in September 2014 via the BAE Software In-Service Support (SwISS) contract with JTN. A separate baseline waveform maintenance task order was issued to BAE to correct 34 baseline defects and was delivered in August 2014. A subsequent follow-on effort is planned to merge these two baseline branches by June 2015.
Joint Enterprise Network Manager (JENM):
JENM successfully completed FQT in December 2012, and is scheduled for MNVR IOT&E in May 2016. The JENM v1.2 software baseline, as integrated into the Army's Joint Tactical Networking Environment NetOps Toolkit (J-TNT) platform, was fielded on the J-TNT hardened laptop to Army Capability Set-15 units starting in the first quarter of FY 2015. JENM v3.0.x, providing a plug-in architecture for WNW and SRW planning and provisioning, was provided as a series of successful engineering drops to MNVR, demonstrating initial capabilities of planning, loading, and management of WNW and SRW on the AN/VRC-118 radio during the MNVR Government Integration Test risk reduction test activities. JENM v3.1 is planned as the threshold baseline software supporting MUOS Provisioning, and will support MUOS TECHEVAL and MOT&E. The JENM v3.1 software baseline will be utilized at the Army's NIE 15.2 in the Spring of 2015 to support the MNVR program LUT. A training package for this software is under development to support the test event. JENM v3.X will likely be first fielded to Army units beginning in FY 2017. The Naval Special Warfare Command Mobile Communications Team 1 used JENM 3.1E3 to plan and configure HMS Manpacks for the MUOS Scenario-Based Event #4 in San Diego citing its ease of use. The JENM Target Interface Control Document (ICD), 1st Working Draft, was released in August 2014 for review by stakeholders and industry. Comments were addressed in the 2nd Working Draft, released in January 2015. The Target ICD found future design changes would be needed to accommodate new managed radios to enhance usability with a single load approach. A JENM v3.1 ICD is planned for release in February 2015 to establish configuration control for JENM
-radio interfaces which are part of the JENM v3.1 including MNVR and HMS. The JENM Target Interfaces will be included in the JENM v3.1 ICD for information. The Target Interfaces will fall under configuration control as they are implemented in the JENM 3.2 - 3.4 software versions. A JENM ICD will be released corresponding to each future version of JENM software, and establish configuration control for the JENM-radio interfaces included in that version.
Single Channel Ground and Airborne Radio System (SINCGARS) software defined waveform:
As a reimbursable funded effort in support of Airborne, Maritime, and Fixed (AMF) Radio Program, PM JTN matured the Government owned SINCGARS v1.4.12 by incorporating Packet Mode (software release v1.6, December 2013) and further engineering Enhanced Operating Mode/Frequency Hopping 2 (FH2) feature (software release 2.0, September 2014). Both Packet Mode and FH2 features were engineered at government laboratory located at SPAWAR Systems Center, Atlantic (SSC LANT). Along with packet mode and FH2 features, the waveform requirements documents were updated to include specifications for Radio Based Situational Awareness, Universal Network Situational Awareness and Radio Based Combat Identification modes by Exelis Corporation under the SwISS contract. To enhance software code quality, PM JTN leveraged

## Table 9
findings from Design Objective 178C compliance (a parallel) effort between PM AMF and SSC LANT. The code quality enhancements are incorporated in release of SINCGARS v2.0.
JTRS Bowman Waveform (JBW) for U.S. - United Kingdom Coalition Operations:
NSA conducted Delta IA assessment testing of the JBW baseline waveform (v2.2.6) architecture and software design and determined the waveform to be an acceptable baseline. The JTN received the formal NSA acceptance letter in April 2013. The updated waveform was successfully demonstrated during field testing at Fort Dix, New Jersey in April 2013. There are currently no active taskorders on the JBW SwISS contract with Exelis.
Merged VHF, UHF Line of Sight and HAVE QUICK II waveforms (VULOS/HQII):
This is a reimbursable funded effort in support of the U.S. Air Force. A final engineering delivery was provided by SSC LANT that merged the combined VULOS and HAVE QUICK II baseline waveforms into a common baseline which also included VHF Air Traffic Control Capabilities in September 2013. This was an efficient merge of the VULOS (73 thousand source lines of code (ksloc)) and HAVE QUICK II (71 ksloc) resulting in a single waveform product VULOS/HQII with only 85 ksloc.
There are no significant software-related issues with this program at this time.
Pursuant to section 2432 of title 10, United States Code, this is the final SAR submission for JTN, because the program is 90% or more expended.

## Table 10
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
The HAVE QUICK II and Mobile User Objective System Formal Qualification Testing breaches were reported in the December 2006 SAR and September 2011 SAR, respectively.
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 11
Schedule

## Table 12
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
MS B | Jun 2002 | Jun 2002 | Dec 2002 | Jun 2002
JTeL IOC | Aug 2003 | Aug 2003 | Feb 2004 | Jul 2003
UHF DAMA SATCOM (181/182/183)* | Sep 2004 | N/A | N/A | N/A
Link 16 | Oct 2005 | N/A | N/A | N/A
WNW* | Oct 2005 | N/A | N/A | N/A
MS C (PDSS) | Oct 2006 | N/A | N/A | N/A
Legacy Waveform
UHF DAMA SATCOM (181/182/183/184)* | N/A | Mar 2007 | Mar 2008 | Mar 2007
Bowman (VHF) | N/A | Jul 2007 | Jan 2008 | Jul 2007
Link 16* | N/A | May 2009 | May 2010 | Apr 2009
HF SSB/ALE | N/A | Jun 2009 | Jun 2010 | Dec 2009
SINCGARS ESIP* | Aug 2004 | Aug 2004 | Feb 2006 | Dec 2005
HAVE QUICK II* | Aug 2004 | Aug 2004 | Feb 2006 | Aug 20061
EPLRS* | Mar 2005 | Nov 2007 | Nov 2008 | Dec 2007
Networking Waveforms
SRW* | N/A | Dec 2009 | Jun 2011 | Jan 2009
WNW* | N/A | Jul 2009 | Jan 2011 | Dec 2009
MUOS | N/A | Aug 2010 | Feb 2012 | Nov 20121
Network Enterprise Services
JWNM | N/A | Jun 2009 | Dec 2010 | Mar 2010
ENS (Phase 1) | N/A | Jun 2010 | Dec 2011 | Apr 2011
JENM | N/A | Apr 2012 | Oct 2013 | Dec 2012
JAN-TE* | N/A | TBD | TBD | N/A
1 APB Breach
Change Explanations
None
Notes
A star (*) denotes a KPP.

## Table 13
Acronyms and Abbreviations
ALE - Automatic Link Establishment
DAMA - Demand Assigned Multiple Access ENS - Enterprise Networking Services
EPLRS - Enhanced Position Location Reporting System ESIP - Enhanced System Improvement Program
HF - High Frequency
JAN-TE - Joint Airborne Network - Tactical Edge JENM - Joint Enterprise Network Manager
JTeL IOC - JTRS Technology Lab Initial Operational Capability JWNM - JTRS WNW Network Manager
MS - Milestone
MUOS - Mobile User Objective System
PDSS - Post Deployment Sustainment Support SATCOM - Satellite Communications
SINCGARS - Single Channel Ground and Airborne Radio System SRW - Soldier Radio Waveform
SSB - Single Side Band UHF - Ultra High Frequency VHF - Very High Frequency
WNW - Wideband Networking Waveform

## Table 14
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
UHF DAMA SATCOM (181/182/183)*
225-400 MHz 5 and 25KHz 64Kbps | N/A | N/A | N/A | N/A
WNW*
2M-2GHz Scalable BW,BPS | N/A | N/A | N/A | N/A
Link 16
(960-121 5MHz) 3 MHz 118/236 Kbps w/FEC | N/A | N/A | N/A | N/A
Legacy Waveforms
SINCGARS ESIP*
30-88MHz 25KHz 1 6Kbps | 30-88MHz 25KHz 16Kbps | 30-88MHz 25KHz 16Kbps | 30-88MHz 25KHz 16Kbps | 30-88MHz 25KHz 16Kbps
HAVE QUICK II*
225-400 MHz 25KHz 16Kbps | 225-400 MHz 25KHz 16Kbps | 225-400 MHz 25KHz 16Kbps | 225-400 MHz 25KHz 16Kbps | 225-400 MHz 25KHz 16Kbps
EPLRS*
420-450 MHz 3MHz (57Kbps VHSIC SIP 114Kbps VECP) | 420MHz - 450MHz; 3MHz; (57Kbps, VHSIC SIP 228Kbps VECP) | 420MHz - 450MHz; 3MHz; (57Kbps, VHSIC SIP 228Kbps VECP) | 420MHz-450MHz; 3MHz; (57Kbps, VHSIC SIP 228Kbps VECP) | 420MHz-450MHz; 3MHz; (57Kbps, VHSIC SIP 228Kbps VECP)
Bowman (VHF)
N/A | 30MHz - 80MHz; 25KHz; 156Kbps | 30MHz - 80MHz; 25KHz; 156Kbps | 30MHz- 80MHz; 25KHz; 156Kbps | 30MHz- 80MHz; 25KHz; 156Kbps
HF SSB/ALE
N/A | 1.5MHz - 30MHz; 3Khz; VOICE: (A&D) DATA: 75, 150, 300, 600, 1200, 2400, 3200, 4800, 6400, 8000, 9600 bps per SSB channel | 2.0MHz - 30MHz; 3KHz; VOICE: (A&D) DATA: 75, 150, 300, 600, 1200, 2400, 3200, 4800, 6400, 8000, 9600 bps per SSB channel | 2.0MHz- 30MHz; 3KHz; VOICE: (A&D) DATA: 75, 150, 300, 600, 1200, 2400, 3200, 4800, 6400, 8000, 9600 bps per SSB channel | 2.0MHz- 30MHz; 3KHz; VOICE: (A&D) DATA: 75, 150, 300, 600, 1200, 2400, 3200, 4800, 6400, 8000, 9600 bps per SSB channel
Link 16*
N/A | 960MHz - 1215MHz; | 960MHz - 1215MHz; | 960MHz- 1215MHz ; | 960MHz- 1215MHz ;

## Table 15
| 3MHz; 118/1137 Kbps, w/FEC | 3MHz; 118/1137 Kbps, w/FEC | 3MHz; 118/ 1137 Kbps, w/FEC | 3MHz; 118/ 1137 Kbps, w/FEC
UHF DAMA SATCOM (181/182/183/184)*
N/A | 225MHz - 400MHz; 5KHz & 25KHz; 75bps - 64Kbps | 225MHz - 400MHz; 5KHz & 25KHz; 75bps - 56Kbps | 225MHz- 400MHz; 5KHz & 25KHz; 75bps- 56Kbps | 225MHz- 400MHz; 5KHz & 25KHz; 75bps - 56Kbps
Networking Waveforms
WNW (Throughput) *
N/A | 5Mbps | 2Mbps | 7Mbps | 7Mbps
SRW (Network Throughput)*
N/A | 1200Kbps | 600Kbps | 600Kbps | 600Kbps
MUOS
N/A | 240MHz - 320MHz; 5KHz & 25KHz; 2.4, 9.6, 16, 32, 64 Kbps | 240MHz - 320MHz; 5KHz & 25KHz; 2.4, 9.6, 16, 32, 64 Kbps | 240MHz- 320MHz; 5KHz & 25KHz; 2.4, 9.6, 16, 32, 64 Kbps | 240MHz- 320MHz; 5KHz & 25KHz; 2.4, 9.6, 16, 32, 64 Kbps
Network Enterprise Services
JWNM
N/A | Reconfigure 150 sets operating WNW in 5 min | Reconfigure 35 sets operating WNW in 10 min | TBD | Reconfigure 35 sets operating WNW in 10 min
JENM
N/A | Provide network planning, management and control of WNW, SRW, and MUOS on all Increment 1 form factors | Provide network planning, management and control of WNW, SRW, and MUOS on all Increment 1 form factors | TBD | Provide network planning, management and control of WNW, SRW and MUOS on all Increment 1 form factors
ENS
N/A | SINCGARS R/R IP data w/WNW, SRW and EPLRS on all applicable Increment 1 form factors (HF and UHF) SATCOM DAMA R/R IP data w/all applicable Increment 1 waveforms and form factors | SINCGARS R/R IP data w/WNW, SRW and EPLRS on the GMR; SINCGARS R/R IP data with SRW and EPLRS on the HMS MANPACK; WNW R/R IP data with HF and UHF SATCOM DAMA on the GMR | TBD | SINCGARS R/R IP data w/WNW, SRW on the GMR; SINCGARS R/R IP data with SRW on the HMS MANPACK; WNW R/R IP data with HF and UHF SATCOM DAMA on the GMR
JAN-TE (Network Throughput)*
N/A | TBD | TBD | TBD | TBD
Requirements Reference
Operational Requirements Document (ORD) 3.2/3.2.1 (Increment 1) dated August 28, 2006

## Table 16
Change Explanations
None
Notes
Asterisk (*) Denotes KPP. Increment 1 focuses on initial near-term waveform software capability development of the KPP waveforms and network manager.
Per the December 21, 2009 ADM, the JAN-TE capability remains an unfunded requirement.
Acronyms and Abbreviations
A&D - Analog & Digital
ALE - Automatic Link Establishment Bps - Bits per second
BW - Bandwidth
DAMA - Demand Assigned Multiple Access ENS - Enterprise Networking Services
EPLRS - Enhanced Position Location Reporting System ESIP - Enhanced System Improvement Program
FEC - Forward Error Correction GHz - Gigahertz
GMR - Ground Mobile Radio HF - High Frequency
HMS - Handheld, Manpack and Small Form Fit IP - Internet Protocol
JAN-TE - Joint Airborne Network - Tactical Edge JENM - Joint Enterprise Network Manager JWNM - JTRS WNW Network Manager
Kbps - Kilobits per second KHz - Kilohertz
Mbps - Megabits Per Second MHz - Megahertz
min - Minutes
MUOS - Mobile User Objective System R/R - Routing/Retransmit
SATCOM - Satellite Communications
SINCGARS - Single Channel Ground and Airborne Radio System SIP - Software Integration Plan
SRW - Soldier Radio Waveform SSB - Single Side Band
UHF - Ultra High Frequency
VECP - Value Engineering Change Proposal VHF - Very High Frequency
VHSIC - Very High Speed Integrated Circuit w/ - with
WNW - Wideband Networking Waveform

## Table 17
Track to Budget
General Notes
During the year of execution, DoD transfers funding from RDT&E to O&M to support program requirements.
RDT&E
Appn |  |  | BA | PE
Navy 1319 05 0604280N
Project | Name
3076 Joint Tactical Radio System (JTRS) Network Enterprise Domain (NED)
Navy 1319 05 0605030N
(Sunk)
|  | Project |  | Name
|  | 3077 |  | Joint Tactical Networking Center (JTNC) | (Shared)
Army |  | 2040 05 |  | 0604280A
|  | Project |  | Name
|  | 162 |  | Joint Tactical Radio System (JTRS) Network Enterprise Domain (NED) | (Shared) (Sunk)
Army |  | 2040 05 |  | 0605030A
|  | Project |  | Name
|  | EA8 |  | Joint Tactical Networking Center (JTNC) | (Shared)
Army |  | 2040 05 |  | 0605031A
|  | Project |  | Name
|  | EF05 |  | Joint Tactical Networks (JTN)
Air Force |  | 3600 05 |  | 0605030F
|  | Project |  | Name
|  | 655068 |  | Joint Tactical Networking Center (JTNC) | (Shared)

## Table 18
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2002 $M | [6 empty] | BY 2002 $M |  | TY $M
| SAR Baseline Development Estimate |  |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E |  | 812.9 |  |  | 1743.2 | 1917.5 |  |  | 1789 |  | 914.4 |  |  | 1961.8 |  | 2079.5
Procurement |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Flyaway |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Recurring |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Non Recurring |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Other Support |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Initial Spares |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
MILCON |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 812.9 |  |  | 1743.2 | N/A |  |  | 1789 |  | 914.4 |  |  | 1961.8 |  | 2079.5
Cost Notes
Per the January 2014 ADM, the Joint Tactical Networking Center (JTNC) and PM JTN are split. The JTNC budget is no longer captured in this Current Estimate (CE) for FY 2014 - FY 2033. The CE presented reflects approved reprogramming actions, realignments, and Small Business Innovative Research transfer. FY 2017 - FY 2033 CE reflects the split of funding between RDT&E and O&M.
Total Quantity
Quantity |  |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
Total |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
Quantity Notes
The JTN products are not systems or end items. They are components of software-defined radios. Accordingly, the JTN Program has no unit quantities.
There is no production or deployment directly associated with the JTN Program. All production and deployment will be functions of military service purchases of software defined radios and their intended usage. Consequently, there will be no LRIP or Full Rate Production decisions associated with this program. (Para 3.4.2.1 of the Network Enterprise Domain Acquisition Strategy of February 2008).

## Table 19
Cost and Funding
Funding Summary
Appropriation Summary
FY 2016 President's Budget / December 2014 SAR (TY$ M)
Appropriation | Prior | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | To Complete | Total
RDT&E | 1905.2 | 18 | 18.1 | 13.1 | 13 | 12.8 | 11.1 | 88.2 | 2079.5
Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2016 Total | 1905.2 | 18 | 18.1 | 13.1 | 13 | 12.8 | 11.1 | 88.2 | 2079.5
PB 2015 Total | 1915.5 | 18 | 8.1 | 9.6 | 9 | 9 | 7.2 | 120.3 | 2096.7
Delta | -10.3 | 0 | 10 | 3.5 | 4 | 3.8 | 3.9 | -32.1 | -17.2
Funding Notes
Changes in FY 2016 RDT&E funding amounts as reflected in the FY 2016 PB. The allocation via the Resource Management Decision (RMD) between RDT&E and O&M resulted in higher RDT&E reflected for JTN in FY 2016, however, the overall funding for JTN efforts in FY 2016 is reduced to $27.048M ($18.055M RDT&E and $8.993M O&M) in the FY 2016 PB from the total allocated funding for PM JTN efforts on Joint Enterprise Network Manager, Soldier Radio Waveform, and Wideband Networking Waveform of $37.308M in FY 2015 PB. All future JTN funding is held as RDT&E in the FYDP. Funding is allocated to O&M, Army (OMA) in the year of execution via the annual RMD. This report only reflects RDT&E annual estimates. Army funds waveform efforts and contributes the JENM funding shared with the Navy and Air Force.
JTN FY 2016 PB funding profile estimates (FY 2016 - FY 2020):
FY 2016: Army $18.055M RDT&E + $8.993M O&M = $27.048M
FY 2017:
Army $8.679M RDT&E + $12.901M (to OMA in year of execution) = $21.580M; Air Force $4.405M RDT&E + $2.022M (to O&M in year of execution) = $6.427M /// Total Funding: $28.007M
FY 2018: Army $8.718M RDT&E + $13.036M (to OMA in year of execution) = $21,754M; Air Force $4.267M RDT&E +
$1.975M (to O&M in year of execution) = $6.242M /// Total Funding: $27.996M
FY 2019: Army $6.861M RDT&E + $15.346M (to OMA in year of execution) = $22.207M; Air Force $3.375M RDT&E +
$2.780M (to O&M in year of execution) = $6.155M; Navy $2.507M RDT&E + $3.044M (to O&M in year of execution) =
$5.551M /// Total Funding = $33.913M
FY 2020: Army $5.291M RDT&E + $17.197M (to OMA in year of execution) = $22.488M; Air Force $3.399M RDT&E +
$2.652M (to O&M in year of execution) = $6.051M; Navy $2.447M RDT&E + $3.136M (to O&M in year of execution) =
$5.583M /// Total Funding = $34.122M

## Table 20
Quantity Summary
FY 2016 President's Budget / December 2014 SAR (TY$ M)
Quantity | Undistributed | Prior | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | To Complete | Total
Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2016 Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2015 Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Table 21
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 221.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 241.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 207.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 200.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 115.4
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 168.5
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.5
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.4
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.5
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.6
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.6
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.7
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.1
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.2
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.2
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.3
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.6
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.2
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.8
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.6
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1248.8

## Table 22
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2002 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 194.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 208.1
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 176.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 168.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 94.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 135.6
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.4
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.9
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.7
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1046.3

## Table 23
FY 2016 changes reflect Resource Management Decision (RMD) movement of funding for the annual transfer of Navy RDT&E to the Army as executing agent. FY 2019 - FY 2033 RDT&E funding reflects the portion of funding estimated to be required for development efforts after the annual RMD. Funding is split between O&M and RDT&E during year of execution. Funding required for O&M is in accordance with the estimated cost to sustain the software code.

## Table 24
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.4
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.5
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.8
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 72.7
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.9
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 105.6
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 140.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 131.7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.7
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.7
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.9
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.3
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.5
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.6
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.6
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.7
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.1
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.2
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.2
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.3
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.6
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.2
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.8
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.6
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 785.8

## Table 25
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2002 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.4
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.8
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.8
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 71.9
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 61.1
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 100.2
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 129.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 118.1
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.6
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.4
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.3
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.9
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.7
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.3
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.9
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.7
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 713

## Table 26
FY 2016 changes as reported in the President's Budget reflect updated cost methodology based on actual costs to date resulting in less funding allocated to O&M via the Resource Management Decision.

## Table 27
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.4
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.3
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.4
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.4
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.5
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.6
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.6
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.7
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.1
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.2
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.2
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.3
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.6
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.2
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.8
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.6
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44.9

## Table 28
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2002 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.3
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.2
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.4
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.4
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.4
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.9
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.7
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.7

## Table 29
FY 2016 changes reflect Resource Management Decision (RMD) movement of funding for the annual transfer of Air
Force RDT&E to the Army as executing agent. FY 2019 - FY 2033 RDT&E funding reflects the portion of funding estimated to be required for development efforts after the annual RMD. Funding is split between O&M and RDT&E during year of execution. Funding required for O&M is in accordance with the estimated cost to sustain the software code.

## Table 30
Low Rate Initial Production
There is no LRIP for the JTN program.

## Table 31
Foreign Military Sales
None
Nuclear Costs
None

## Table 32
Unit Cost
Unit Cost Report
Item |  | BY 2002 $M | BY 2002 $M |  | % Change
|  | Current UCR Baseline (Dec 2009 APB) | Current Estimate (Dec 2014 SAR)
Program Acquisition Unit Cost
Cost | 1743.2 |  |  | 1789
Quantity | 0 |  |  | 0
Item | -- |  |  | -- |  | --
Average Procurement Unit Cost
Cost | 0 |  |  | 0
Quantity | 0 |  |  | 0
Unit Cost | -- |  |  | -- |  | --
Item |  | BY 2002 $M | BY 2002 $M |  | % Change
|  | Original UCR Baseline (Jun 2002 APB) | Current Estimate (Dec 2014 SAR)
Program Acquisition Unit Cost
Cost | 812.9 |  |  | 1789
Quantity Unit Cost | 0 -- |  |  | 0 -- |  | --
Average Procurement Unit Cost
Cost | -- |  |  | 0
Quantity Unit Cost | -- -- |  |  | 0 -- |  | --
The JTN products are not systems or end items but are components of software-defined radios; therefore, the JTN program has no unit quantities.

## Table 33
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2002 $M | [5 empty] | TY $M
[8 empty] | PAUC |  |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Jun 2002 |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
APB as of January 2006 |  |  | Jun 2002 |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | Jan 2008 |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Current APB |  |  | Dec 2009 |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Prior Annual SAR |  |  | Dec 2013 |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Current Estimate |  |  | Dec 2014 |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [14 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  |  | Total
0.000 -- -- -- -- -- -- -- -- 0.000
A PAUC Unit Cost History is not available, since no Initial PAUC Estimate had been calculated due to a lack of defined quantities.

## Table 34
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [9 empty] | APUC Current Estimate
| Econ | Qty | Sch | Eng |  | Est | Oth | Spt |  | Total
0.000 -- -- -- -- -- -- -- -- 0.000
An APUC Unit Cost History is not available, since no Initial APUC Estimate had been calculated due to a lack of defined quantities.
SAR Baseline History
Item |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone B |  | N/A |  |  | Jun 2002 |  |  |  | N/A |  |  | Jun 2002
Milestone C |  | N/A |  |  | Oct 2006 |  |  |  | N/A |  |  | N/A
IOC |  | N/A |  |  | N/A |  |  |  | N/A |  |  | Jul 2003
Total Cost (TY $M) |  | N/A |  |  | 914.4 |  |  |  | N/A |  |  | 2079.5
Total Quantity |  | N/A |  |  | 0 |  |  |  | N/A |  |  | 0
PAUC |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
The JTN products are not systems or end items but are components of software-defined radios; therefore, the JTN program has no Milestone C.

## Table 35
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
914.4 -- -- 914.4
Economic |  | 31 |  | -- |  | -- |  | 31
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | 725.3 |  | -- |  | -- |  | 725.3
Estimating |  | 426 |  | -- |  | -- |  | 426
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 1182.3 |  | -- |  | -- |  | 1182.3
Current Changes Economic |  | -3.3 |  | -- |  | -- |  | -3.3
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -13.9 |  | -- |  | -- |  | -13.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -17.2 |  | -- |  | -- |  | -17.2
Total Changes |  | 1165.1 |  | -- |  | -- |  | 1165.1
CE - Cost Variance |  | 2079.5 |  | -- |  | -- |  | 2079.5
CE - Cost & Funding |  | 2079.5 |  | -- |  | -- |  | 2079.5

## Table 36
Summary BY 2002 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
812.9 -- -- 812.9
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | 648.1 |  | -- |  | -- |  | 648.1
Estimating |  | 333.4 |  | -- |  | -- |  | 333.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 981.5 |  | -- |  | -- |  | 981.5
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -5.4 |  | -- |  | -- |  | -5.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -5.4 |  | -- |  | -- |  | -5.4
Total Changes |  | 976.1 |  | -- |  | -- |  | 976.1
CE - Cost Variance |  | 1789 |  | -- |  | -- |  | 1789
CE - Cost & Funding |  | 1789 |  | -- |  | -- |  | 1789
Previous Estimate: December 2013

## Table 37
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | -3.3
Adjustment for current and prior escalation. (Estimating) |  | 0.7 | 0.8
Revised estimate to reflect actual funding reductions (Navy). (Estimating) |  | -6.9 | -9.2
Revised estimate to reflect updated cost methodology based on actuals (Navy). |  | -5.2 | -9.8
(Estimating)
Revised estimate to reflect removal of funding associated with the Joint Tactical Networking Center (Army). (Estimating)
Revised estimate to reflect Small Business Innovation Research and Small Business Technology Transfer Assessment (Army). (Estimating)
Revised estimate to reflect transfer of funding to Army Program Element for execution. (Subtotal)
Revised estimate to reflect annual transfer of Air Force RDT&E to the Army as executing agent (Army). (Estimating)
Revised estimate to reflect annual transfer of Air Force RDT&E to the Army as executing agent (Air Force). (Estimating)
-6.2 -8.0
-1.8 -2.3
-0.1 0.0
(+4.2) (+5.6)
(-4.3) (-5.6)
Revised estimate to reflect actuals between O&M and RDT&E funding (Army). (Estimating) +20.5 +28.1 Revised estimate to reflect updated cost methodology (Army). (Estimating) -6.3 -10.7
Revised estimate to reflect actuals between O&M and RDT&E funding (Air Force). (Estimating)
+5.6 +7.5
Revised estimate to reflect updated cost methodology (Air Force). (Estimating) | -5.7 |  |  | -10.3
RDT&E Subtotal | -5.4 |  |  | -17.2

## Table 38
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: UHF/HF SwISS
Contractor: Rockwell Collins, Inc.
Contractor Location: 400 Collins Road NE
Cedar Rapids, IA 52406
Contract Number: N00039-09-D-0021
Contract Type: Cost Plus Fixed Fee (CPFF), Cost Plus Incentive Fee (CPIF)
Award Date: June 19, 2009
Definitization Date: June 04, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
23.9 N/A 0 21.3 N/A 0 21.3 21.3
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the difference between the cumulative total of initial prices of the task orders issued versus the authorized funding against the same task orders. The initial contract price is the cumulative total of the initial price of the task orders issued under the base contract as reported on the Contract Funds Status Report (CFSR). The current contract price represents the cumulative total of the funding authorized for the task orders issued as reported on the CFSR.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date 0.0 0.0
Previous Cumulative Variances 0.0 0.0
Net Change +0.0 +0.0
Cost and Schedule Variance Explanations
None
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because the cost portion does not meet the threshold requirements for EVM reporting.

## Table 39
Notes
The High Frequency/Ultra High Frequency Sateliite Communications Software In-Service Support contract is a hybrid Indefinite Delivery/Indefinite Quantity (ID/IQ) cost type contract. This contract provides for technical/general support (Cost Plus Fixed Fee), upgrades/maintenance (Cost Plus Incentive Fee (CPIF)) as well as enhancements (CPIF) for the waveform/net services. The contract was awarded to Rockwell Collins, Inc. in June 2009 with an total estimated value of
$45.4M and a five-year period of performance. Five task orders (TOs) were issued under the base contract with
a cumulative total of $21.3M as reported on the Contract Funds Status Report (CFSR). All five TOs are complete. TO 0001, Tactical Data Controller (TDC), was awarded with a value greater than $20M. As such, a monthly Cost Performance Report (CPR) Contract Data Requirements List (CDRL) was required for upload to the Defense Cost and Resource Center EVM repository. The TDC Formal Qualification Test (FQT) was completed in April 2011 and the TO was closed out in September 2011, eliminating the monthly CPR CDRL requirement.
(1) Task Order 1: Enterprise Network Services Phase 1: TDC; Value = $20.5M; Period of Performance is Complete; EVMS
= Yes.
(2) Task Order 2: Technical Support; Value = $0.187M; Period of Performance is Complete; EVMS = No.
(3) Task Order 3: HF Information Assurance (IA) Lean Six Sigma; Value = $0.136M; Period of Performance is Complete; EVMS = No.
(4) Task Order 4: Full Duplex; Value = $0.325M; Period of Performance is Complete; EVMS = No.
(5) Task Order 5: HF IA Burn-down; Value = $0.143M; Period of Performance is Complete; EVMS = No.
The Period of Performance of this contract ended in June 2014.
Contractor and PM Estimated Ceiling Price is N/A because of the ID/IQ nature of the contracts. Estimate at Completion is the sum of the awarded task orders under the contract.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 40
Contract Identification
Appropriation: RDT&E
Contract Name: SINCGARS SwISS
Contractor: ITT Corporation
Contractor Location: 1919 W Cook Road
Fort Wayne, IN 46818
Contract Number: N00039-09-D-0020/1
Contract Type: Cost Plus Fixed Fee (CPFF), Cost Plus Incentive Fee (CPIF)
Award Date: May 15, 2009
Definitization Date: April 29, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
62.0 N/A 0 62.0 N/A 0 29.2 29.2
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date 0.0 0.0
Previous Cumulative Variances 0.0 0.0
Net Change +0.0 +0.0
Cost and Schedule Variance Explanations
None
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because the cost or incentive portion does not meet the threshold requirements for earned value management reporting.

## Table 41
Notes
The Single Channel Ground and Airborne Radio System Enterprise Network Services (ENS) Phase 1 (Software Internet Controller (SoftINC)) Software In-Service Support contract is a hybrid Indefinite Delivery/Indefinite Quantity (ID/IQ) cost type contract. This contract provides for technical/general support (Cost Plus Fixed Fee), upgrades/maintenance (Cost Plus Incentive Fee (CPIF)) as well as enhancements (CPIF) for the waveform/net services. The contract was awarded to ITT/Exelis in May 2009 with a contract price of $62.0M and a five-year period of performance. There are five Task Orders (TO) on contract; all five are complete. At time of contract award, TO 1 (SoftINC) was awarded, and because the value was greater than $20M, a monthly Cost Performance Report (CPR) Contract Data Requirements List (CDRL) was required for upload to the Defense Cost and Resource Center EVM repository. The SoftINC Formal Qualification Test was completed in April 2011 and the TO was closed out in November 2011, eliminating the monthly CPR CDRL requirement.
(1) Task Order 1: ENS Phase 1: SoftINC; Value = $25.2M; Period of Performance is Complete; EVMS = Yes.
(2) Task Order 2: Technical Support; Value = $0.133M; Period of Performance is Complete; EVMS = No.
(3) Task Order 3: General Support; Value = $0.319M; Period of Performance is Complete; EVMS= No.
(4) Task Order 4: Packet Mode; Value = $1.7M; Period of Performance is Complete; EVMS = No.
(5) Task Order 5: Technical Support; Value = $1.8M; Period of Performance is complete; EVMS = No.
Efforts for this contract completed in May 2014.
Contractor and PM Estimated Ceiling Price is N/A because of the ID/IQ nature of the contracts. Estimate at Completion is the sum of the awarded task orders under the contract.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 42
Contract Identification
Appropriation: RDT&E
Contract Name: Bowman VHF WF
Contractor: ITT Corporation
Contractor Location: 1919 W Cook Road
Fort Wayne, IN 46818
Contract Number: N00039-10-D-0047
Contract Type: Cost Plus Fixed Fee (CPFF), Cost Plus Incentive Fee (CPIF)
Award Date: September 16, 2010
Definitization Date: September 25, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
49.5 N/A 0 49.5 N/A 0 4.9 4.9
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date 0.0 0.0
Previous Cumulative Variances 0.0 0.0
Net Change +0.0 +0.0
Cost and Schedule Variance Explanations
None
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because the cost portion does not meet the threshold requirements for EVM reporting.

## Table 43
Notes
The JTRS Bowman (JBW) Software In-Service Support (SwISS) contract is a hybrid Indefinite Delivery/Indefinite Quantity (ID/IQ) cost type contract. This contract provides for technical/general support (Cost Plus Fixed Fee), upgrades/maintenance (Cost Plus Incentive Fee (CPIF)) as well as enhancements (CPIF) for the waveform. The contract value is $49.5M. There are five Task Orders (TO) on the contract, and all TOs are complete. None of these efforts require EVM.
(1) Task Order 1: SwISS Information Assurance (IA) Standards; Value = $4.5M; Period of Performance is Complete; EVMS
= No.
(2) Task Order 2: Test and Evaluation on Technical Support for Communication and Electronic Security Group; Value =
$0.074M; Period of Performance is Complete; EVMS = No.
(3) Task Order 3: Technical Maintenance/Support for Radios; Value = $0.027M; Period of Performance is Complete; EVMS
= No.
(4) Task Order 4: Re-port JBW on Soldier Radio Multifunction; Value = $0.051M; Period of Performance is Complete; EVMS
= No.
(5) Task Order 5: IA Remediation; Value = $0.297M; Period of Performance is Complete; EVMS = No.
Contractor and PM Estimated Ceiling Price is N/A because of the ID/IQ nature of the contracts. Estimate at Completion is the sum of the awarded task orders under the contract. The effort on this contract completed in September 2014.
Contract performance data is not required for this contract as no active task order exceeds the monetary threshold for earned value metrics reporting.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 44
Contract Identification
Appropriation: RDT&E
Contract Name: Wideband Networking WF
Contractor: General Dynamics C4 Systems, Incorporated
Contractor Location: 8201 E McDowell Road
Scottsdale, AZ 85257
Contract Number: N65236-11-D-4806
Contract Type: Cost Plus Fixed Fee (CPFF), Cost Plus Incentive Fee (CPIF)
Award Date: September 20, 2011
Definitization Date: April 17, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
64.6 N/A 0 64.6 N/A 0 18.9 18.9
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date 0.0 0.0
Previous Cumulative Variances 0.0 0.0
Net Change +0.0 +0.0
Cost and Schedule Variance Explanations
None
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because the cost portion does not meet the threshold requirements for EVM reporting.

## Table 45
Notes
The Wideband Networking Waveform (WNW) Software In-Service Supportcontract is a hybrid Indefinite Delivery/Indefinite Quantity (ID/IQ) cost type contract. This contract provides for technical/general support (Cost Plus Fixed Fee), upgrades/maintenance (Cost Plus Incentive Fee (CPIF)) as well as enhancements (CPIF) for the waveform/net services. The contract value is $64.6M. There are ten Task Orders (TO) on the contract, and TOs 1 -5, 7,and 8 are complete. None of these efforts require EVM.
(1) Task Order 1: Technical Support; Value = $1.2M; Period of Performance is Complete; EVMS = No.
(2) Task Order 2: Network Integration EvaluationSupport; Value = $0.148M; Period of Performance is Complete; EVMS = No.
(3) Task Order 3: Waveform Development Environment (WDE)/Waveform Testing Environment (WTE) Stand up; Value =
$0.826; Period of Performance is Complete; EVMS = No.
(4) Task Order 4: WNW 4.0.7 Information Assurance (IA) Fixes; Value = $2.7M; Period of Performance through November 2013; EVMS = No.
(5) Task Order 5: Technical Support; Value = $1.3M; Period of Performance is complete; EVMS = No.
(6) Task Order 6: High Assurance Internet Protocol Encryptor and Mobile Ad hoc Network Updates/Modifications; Value =
$5.8M; Period of Performance through January 2014; EVMS = No.
(7) Task Order 7: Critical IA Fixes; Value = $1.2M; Period of Performance through December 2013; EVMS = No.
(8) Task Order 8: Data Dictionary; Value = $0.400M; Period of Performance is complete; EVMS = No.
(9) Task Order 9: WDE and WTE Phase 2; Value = $0.977M; PoP is through May 2014; EVMS = No.
(10) Task Order 10: Technical Support - Year 3; Value = $0.999M; Period of Performance is through September 2014; EVMS = No.
(11) Task Order 11: Critical IA Fixes; Value = $0.799M; Period of Performance is through September 2014; EVMS = No.
(12) Task Order 12: Radio Mission Data Set Update; Value = $0.22M; Period of Performance is through December 2014; EVMS = No.
(13) Task Order 13: Technical Support; Value = $0.73M; Period of Performance is through September 2015; EVMS = No.
(14) Task Order 14: Greenhill's License Renewal; Value = $0.27M; Period of Performance is through October 2015; EVMS
= No.
(15) Task Order 15: Electronic Protection Enhancements; Value = $1.24M; Period of Performance is through November 2015; EVMS = No.
Contractor and PM Estimated Ceiling Price is N/A because of the ID/IQ nature of the contracts. Estimate at Completion is the sum of the awarded task orders under the contract.
Contract performance data is not required for this contract as no active task order exceeds the monetary threshold for earned value metrics reporting.

## Table 46
Contract Identification
Appropriation: RDT&E
Contract Name: Soldier Radio Waveform SwISS
Contractor: Harris Corporation
Contractor Location: 1680 University Ave
Rochester, NY 14610
Contract Number: N66001-12-D-0043
Contract Type: Cost Plus Fixed Fee (CPFF), Cost Plus Incentive Fee (CPIF)
Award Date: April 30, 2012
Definitization Date: July 10, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
25.8 N/A 0 25.8 N/A 0 14.6 14.6
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date 0.0 0.0
Previous Cumulative Variances 0.0 0.0
Net Change +0.0 +0.0
Cost and Schedule Variance Explanations
None
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because the cost portion does not meet the threshold requirements for EVM reporting.

## Table 47
Notes
The Soldier Radio Waveform Software In-Service Support contract is a hybrid Indefinite Delivery/Indefinite Quantity (ID/IQ) cost type contract. This contract provides for technical/general support (Cost Plus Fixed Fee), upgrades/maintenance (Cost Plus Incentive Fee (CPIF)) as well as enhancements (CPIF) for the waveform/net services. The contract value is
$25.8M. There are nine Task Orders (TO) on the contract, and TO 1, 2, 3, 4, 5 and 7 are complete. This effort does not require EVM.
(1) Task Order 1: Technical Support; Value = $1.0M; Period of Performance is Complete; EVMS = No.
(2) Task Order 2: Combat Network Radio Pre-emption Implementation; Value = $1.0M; Period of Performance is through March 2014; EVMS = No.
(3) Task Order 3: Waveform Development Environment / Waveform Testing Environment Stand-up; Value = $2.6M; Period of Performance is throughAugust 2014; EVMS = No.
(4) Task Order 4: Technical Support; Value = $1.3M; Period of Performance is through April 2014; EVMS = No.
(5) Task Order 5: Problem Report and Network Enterprise Domain Change Proposal Implementation; Value = $1.9M; Period of Performance is through August 2014; EVMS = No.
(6) Task Order 6: Over the Air Management (OTAM); Value = $5.8M; Period of Performance is through September 2015; EVMS = No.
(7) Task Order 7: RDT&E Technical Support; Value = $1.0M; Period of Performance is through October 2014; EVMS = No.
(8) Task Order 8: General Technical Support; Value; $1.2M; Period of Performance is through 02 June 2015; EVMS= No.
(9) Task Order 9: OTAM 1.0 Release & Problem Report Implementation; Value; $1.3M; Period of Performance is through 23 September 2015; EVMS = No.
Contractor and PM Estimated Ceiling Price is N/A because of the ID/IQ nature of the contracts. Estimate at Completion is the sum of the awarded task orders under the contract.
Contract performance data is not required for this contract as no active task order exceeds the monetary threshold for earned value metrics reporting.

## Table 48
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 0 | 0 | 0 | --
Total Program Quantity Delivered | 0 | 0 | 0 | --
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
2079.5
1875.2
90.18%
36
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
18
50%
1923.2
92.48%
The above data is current as of February 04, 2015.

## Table 49
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 30, 2015
Source of Estimate: POE
Quantity to Sustain: 0
Unit of Measure: software maintenance year
Service Life per Unit: 25.00 Years
Fiscal Years in Service: FY 2009 - FY 2033
There are no quantities associated with JTN; the unit of measure is the average annual cost to maintain the software code.
Sustainment Strategy
The JTN program office maintains software only and does not have any hardware (no quantities). JTN products are integrated (ported) onto radios and network managers that are maintained by hardware programs. Software Maintenance will continue from FY 2009 through FY 2033. Original Software Maintenance estimate was based on the methodology that maintenance begins at the end of each waveform's Formal Qualification Test and is applied as a declining percentage of initially-estimated development cost. This costing methodology was established per the Office of the
Deputy Assistant Secretary of the Army for Cost and Economics recommendation (in accordance with Cost Assessment and Program Evaluation Office-accepted National Aeronautics and Space Administration standard for expected software maintenance levels) and as approved by the USD(AT&L) during the Network Enterprise Domain's FY 2008 APB reset.
However, the January 2014 ADM provided the opportunity for a revised software maintenance methodology. Starting in FY 2016, the updated cost methodology uses historical actual costs as the basis for developing Cost Estimating Relationships to project future sustainment costs.
Sustainment support for the waveforms and network managers is accomplished via the Software In-Service
Support contracts. These contracts provide both the waveforms and net managers technical support, maintenance, and upgrades. JTN software is in initial fielding.
Software modifications and upgrades include repair of deficiencies reported by the user, preplanned product improvements based on emerging requirements and other types of system change packages. After testing of the modified code, updates will be released to the field as integrated builds. Major changes to the code will be released as a new version. The hardware platforms will be responsible for updating fielded system.
Antecedent Information
No Antecedent

## Table 50
Annual O&S Costs BY2002 $M
Cost Element |  | JTN Average Annual Cost Per Software Maintenance Year | [5 empty] | No Antecedent (Antecedent) N/A
Unit-Level Manpower |  | 0 | [5 empty] | 0
Unit Operations |  | 0 | [5 empty] | 0
Maintenance |  | 0 | [5 empty] | 0
Sustaining Support |  | 23.002 | [5 empty] | 0
Continuing System Improvements |  | 0 | [5 empty] | 0
Indirect Support |  | 0 | [5 empty] | 0
Other |  | 0 | [5 empty] | 0
Total |  | 23.002 | [5 empty] | --
Item | Total O&S Cost $M
| JTN | [7 empty] | No Antecedent (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 739 |  |  | 812.9 |  |  | 575.1 |  | N/A
Then Year | 1221 |  |  | N/A |  |  | 992.6 |  | N/A
Overall, the current estimates are lower than the APB estimate due to the revised software maintenance methodology and removal of the Joint Tactical Networking Center costs per the January 2014 ADM.
Equation to Translate Annual Cost to Total Cost
Total O&S Cost is the average annual cost of software maintenance * planned service years: $23.002M * 25 years =
$575.054M.
O&S Cost Variance
Category |  |  | BY 2002 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2013 SAR
563.5
Programmatic/Planning Factors 11.6 Reduced funding in FYDP caused efforts to move to out years increasing overall costs.
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 11.6
Current Estimate 575.1

## Table 51
Costs have increased since the December 2013 SAR but remain lower than the APB.
Disposal Estimate Details
Date of Estimate: January 30, 2015
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2002 $M): Total costs for disposal of all software maintenance year are
0
Disposal Costs are not applicable for this software program.