## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-252
RQ-4A/B Global Hawk Unmanned Aircraft System (RQ-4A/B Global Hawk)
As of FY 2016 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 9
Schedule 10
Performance 13
Track to Budget 18
Cost and Funding 20
Low Rate Initial Production 33
Foreign Military Sales 34
Nuclear Costs 35
Unit Cost 36
Cost Variance 39
Contracts 43
Deliveries and Expenditures 47
Operating and Support Cost 48

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
RQ-4A/B Global Hawk Unmanned Aircraft System (RQ-4A/B Global Hawk)
DoD Component
Air Force
Responsible Office
Col Carlin Heimann 2530 Loop Road West
Wright-Patterson Air Force Base, OH 45433-7106
carlin.heimann@us.af.mil
Phone: 937-255-7764
Fax: 937-656-4024
DSN Phone: 785-7764
DSN Fax:
Date
Assigned: August 3, 2012
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated March 6, 2001
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated February 23, 2015

## Table 6
Mission and Description
The RQ-4A/B Global Hawk Unmanned Aircraft System (RQ-4A/B Global Hawk) is a high altitude, long endurance Unmanned Aircraft System (UAS) with an integrated sensor suite and ground segment that provides Intelligence, Surveillance, and Reconnaissance (ISR) capabilities to joint warfighters. The system provides high-resolution, high-quality, digital Synthetic Aperture Radar (SAR) to include Ground Moving Target Indicator, plus Electro-Optical (EO), and medium wave Infrared (IR) imagery of targets and other critical areas of interest. The program does not have an antecedent system.
The current program profile consists of: Block 20, 30, and 40 aircraft which are larger than Block 10 aircraft and capable of carrying up to a 3,000-pound (lb) payload. All Block 10 aircraft have either been retired or transferred to the Navy or National Aeronautics and Space Administration. Block 20 was designed to be Image Intelligence only and carries an Enhanced Integrated Sensor Suite (EISS) that is designed for increased performance range and location accuracy over the Block 10 payload. The operational Block 20 aircraft have been converted to the Battlefield Airborne Communications Node (BACN) configuration, which provides airborne communications relay and gateway that allows real-time information exchanges between different tactical data link systems and provides decision makers with critical information. Block 30 carries the Airborne Signals Intelligence Payload that brings Signals Intelligence capability with the EISS. Block 40 incorporates the Multi-Platform Radar Technology Insertion Program Radar as its only sensor.

## Table 7
Executive Summary
Pertinent Program Background
As previously reported in the December 2010 SAR, on February 17, 2011, the Global Hawk Program Manager submitted a Program Deviation Report on a likely Nunn-McCurdy critical unit cost breach. On April 6, 2011, the Secretary of the Air Force (SECAF) notified Congress and the USD(AT&L) of the Nunn-McCurdy critical cost breach. Subsequently, the USD (AT&L) initiated a Nunn-McCurdy review of the program, which resulted in a certification of the Global Hawk program (in accordance with section 2433a of Title 10, United States Code). By law, the Global Hawk program requires a Milestone C to formally re-enter the acquisition framework; thus, establishing a foundation from which to execute ongoing development, production, and modification efforts, as well as, any approved modernization or preplanned product improvement efforts in the future. The required Milestone C DAB, originally scheduled for September 2011, was delayed as a result of budget driven program changes. The Milestone C DAB was also planned in 2012, 2013, and 2014, but each time was delayed due to ongoing budgetary and programmatic changes. The Global Hawk program office has spent significant time and resources over the last three to four years to successfully achieve a new Milestone C and re-enter the acquisition process.
The FY 2013 PB proposed termination of future Blk 30 production and divestiture of all Blk 30 systems previously procured. The FY 2013 National Defense Authorization Act (NDAA) included direction that none of the FY 2013 funds authorized for the DoD may be obligated or expended to retire, prepare to retire, or place in storage a RQ-4 Blk 30, as well as direction that during the period preceding December 31, 2014, in supporting the operational requirements of the combatant commands, the SECAF shall maintain the operational capability of each RQ-4 Blk 30 belonging to the Air Force or delivered to the Air Force during such period. The FY 2013 Appropriations Act also included a provision that required the SECAF to obligate and expend funds previously appropriated for the procurement of RQ-4 aircraft.
The FY 2014 NDAA included direction that none of the FY 2014 funds authorized for the DoD may be obligated or expended to retire, prepare to retire, or place in storage an RQ-4 Blk 30, as well as direction that during the period preceding December 31, 2016, in supporting the operational requirements of the combatant commands, the SECAF shall maintain the operational capability of each RQ-4 Blk 30 belonging to the Air Force or delivered to the Air Force during such period.
The FY 2015 PB and subsequent NDAA restored Blk 30's and all the modernization activities necessary to keep the entire RQ-4 fleet viable throughout the envisioned life cycle. The FY 2015 NDAA directed a High-Altitude Intelligence, Surveillance and Reconnaissance study and the Air Force is responding to that direction.
On February 23, 2015, the USD(AT&L) signed the RQ-4A/B Global Hawk Acquisition Strategy, APB and ADM, approving Milestone C.
Award of Major Contracts or Contract Modifications
The Global Hawk Program Office awarded numerous major contracts and contract modifications to include: initial spares, software upgrades, aircrew training, sustainment support, and FMS activities.
Status of Major Global Hawk System Efforts:
The Global Hawk weapon system surpassed 140,000 flight hours and 100,000 combat flight hours and continues to demonstrate superior improved sustainment performance and exceeded operational performance targets. For 2014, the Global Hawk fleet had an actual Aircraft Availability rate of 79.7%, exceeding the target rate of 72.0%. The Global Hawk cost per flying hour has decreased by more than 50% in the past two years.
Blk 30 Production and Fielding: The Pacific Command (PACOM) and European Command (EUCOM) Forward Operating Locations (FOL) currently consist of two Blk 30 aircraft at Andersen Air Force Base (AFB), Guam and one Blk 30 at Naval Air Station (NAS) Sigonella, Sicily. Both 30's stationed at Guam rotated to Misawa, Japan in May 2014 to increase sortie success rates during the monsoon season in the Pacific. The Blk 30's returned to Andersen AFB, Guam in early October

## Table 8
2014, flying 28 sorties and over 420 hours at Misawa, Japan. All FOLs are accomplishing multi-intelligence missions. NAS Sigonella, Sicily is flying missions in support of EUCOM, African Command (AFRICOM), and Central Command (CENTCOM). CENTCOM currently has two Blk 30 aircraft flying combat sorties. Blk 30's have flown over 21,500 combat hours. On August 15, 2014, the Global Hawk program office awarded the RQ-4B Global Hawk LRIP Lot 11 contract. This contract purchases three Blk 30 RQ-4B air vehicles and two Airborne Signals Intelligence Payload (ASIP) sensors as retrofit kits. Deliveries are expected in FY 2017. During 2014, four ASIP and two ASIP sensors, as retrofit kits, were delivered.
Blk 40 Production and Fielding: Blk 40 Early Operational Capability (EOC) was completed with two Blk 40 aircraft arriving in theater at the end of September 2013. Air Combat Command deployed two additional aircraft to the PACOM Area of Responsibility (AOR) in 2014. This compliments the two aircraft that continue to support the CENTCOM/AFRICOM AORs. The Blk 40 system is performing its Ground Moving Target Indicator (GMTI) detection mission in both theaters with a high level of mission effectiveness (95.1% CENTCOM; 88.7 % PACOM). As of January 15, 2015, over 180 missions and over 4,200 combat fight hours have flown since the IOC declaration, and the system has performed with a 94.6% mission effectiveness rating. The final two production Blk 40s were delivered to Grand Forks AFB, North Dakota during this period. Two Blk 40s were deployed from Grand Forks AFB, North Dakota to PACOM Andersen AFB, Guam in June 2014 for operations.
Battlefield Airborne Communications Node (BACN): Since deployment, the fleet of Global Hawk BACN aircraft has flown over 900 combat sorties and over 23,500 flying hours. During 2014, over 350 sorties and over 9,000 hours were flown, and a Global Hawk-BACN aircraft was in the air almost constantly.
Main Operating Base (MOB) Support: Grand Forks AFB currently has five Blk 40 aircraft with sensors. Beale AFB currently has ten Blk 30 aircraft supporting Northern Command, Southern Command and local operations. The multiple Mission Control Elements at Beale AFB (Blk 30) and Grand Forks AFB (Blk 40) control the missions after handoff from the Launch and Recovery Elements at the FOLs (EUCOM, PACOM and CENTCOM).
The Blk 30 Test Program: In FY 2014, the Blk 30 test program consisted primarily of test planning. Developmental testing occurred for known deficiency fixes and Diminishing Manufacturing Sources issues. The Blk 30 test program is poised to execute several critical enhancement programs in FY 2015 including Synthetic Aperture Radar, Complex Imagery and ASIP upgrade efforts. Both of these are critical operational responses to recognized warfighter needs.
The Blk 40 Test Program: The Blk 40 completed Developmental Test & Evaluation during FY 2014, which included evaluation of the latest sensor software version and end-to-end testing of the Blk 40 enterprise. Following an Initial Operational Test & Evaluation in FY 2015, the Blk 40 will add Synthetic Aperture Radar imagery to the currently fielded GMTI capability. FY 2015 testing will include a major software upgrade, evaluation of classified capabilities, and support to the development of maritime modes for the North Atlantic Treaty Organization Alliance Ground Surveillance program.
There are no significant software-related issues with this program at this time.
This is the final SAR submission for the RQ-4 A/B Global Hawk program.
Pursuant to section 2432 of title 10, United States Code, this is the final SAR submission for RQ-4 A/B Global Hawk, because the program is 90% or more delivered.

## Table 9
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
Classified Threshold Breaches information is provided in the classified annex to this submission.

## Table 10
Schedule

## Table 11
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Block 5: Approved for EMD/ LRIP | Feb 2001 | Mar 2001 | Mar 2001 | Mar 2001
Delivery of first AV with initial Spiral 1 capability | N/A | Sep 2003 | Sep 2003 | Sep 2003
Increment Zero: Delivery of first AV with initial Spiral 1 capability | N/A | Sep 2003 | Sep 2003 | Sep 2003
Block 10: Start Development | Oct 2003 | N/A | N/A | N/A
Block 5: Start IOT&E Phase I | Oct 2003 | N/A | N/A | N/A
Block 5: Complete IOT&E Phase I | Dec 2003 | N/A | N/A | N/A
Block 5: MS III Full Rate Production (FRP) Review | Mar 2004 | N/A | N/A | N/A
Operational Assessment
Start | N/A | Jul 2005 | Jul 2005 | Jul 2005
Complete | N/A | Mar 2007 | Mar 2007 | Mar 2007
Block 5: Initial Operational Capability (IOC) | Sep 2005 | N/A | N/A | N/A
Complete Delivery of Blk 10 aircraft | N/A | Aug 2006 | Aug 2006 | Aug 2006
Block 10: LRIP Interim Program Review (IPR) | Feb 2007 | N/A | N/A | N/A
Delivery of first Blk 20 aircraft | N/A | Mar 2007 | Mar 2007 | Mar 2007
Block 10: Start Production | Oct 2007 | N/A | N/A | N/A
Deliver first ASIP ready Blk 30 aircraft | N/A | Nov 2007 | Nov 2007 | Nov 2007
Block 10: Start IOT&E Phase II | Jul 2010 | N/A | N/A | N/A
Deliver first MP-RTIP Blk 40 aircraft | N/A | Aug 2010 | Aug 2010 | Aug 2010
IOT&E Blk 20/30
Start | N/A | Sep 2010 | Sep 2010 | Sep 2010
Complete | N/A | Dec 2010 | Dec 2010 | Dec 2010
Block 10: Complete IOT&E Phase II | Oct 2010 | N/A | N/A | N/A
Block 10: MS III FRP IPR | Jan 2011 | N/A | N/A | N/A
IOC | N/A | Aug 2011 | Aug 2011 | Aug 2011
Deliver first ASIP in-line (production) Blk 30 aircraft | N/A | Oct 2011 | Oct 2011 | Oct 2011
Blk 40 IOT&E
Start | N/A | Jul 2015 | Jan 2016 | Jul 2015
Stop | N/A | Sep 2015 | Mar 2016 | Sep 2015
Milestone C Blk 30/40 | N/A | Jan 2015 | Jul 2015 | Feb 2015
Blk 40 RAA | N/A | Nov 2015 | May 2016 | Nov 2015
(Ch-1)
(Ch-1)
(Ch-2)
(Ch-3)

## Table 12
Change Explanations
(Ch-1) The Blk 40 IOT&E Start current estimate changed from Jan 2015 to Jul 2015 and the Blk 40 IOT&E Stop current estimate changed from Mar 2015 to Sep 2015 due to delays in the Processing, Exploitation, and Dissemination system upgrades, which is necessary for conducting IOT&E.
(Ch-2) The Milestone C Blk 30/40 current estimate was update to reflect the actual completion. (Ch-3) The Blk 40 RAA was added with Milestone C APB.
Acronyms and Abbreviations
ASIP - Airborne Signals Intelligence Payload AV - Air Vehicle (same as aircraft)
IOT&E - Initial Operational Test & Evaluation
MP-RTIP - Multi Platform Radar Technology Insertion Program MS - Milestone

## Table 13
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Block 5: Endurance - Air Vehicle (AV)
Should be capable of flying an enroute distance of 3000 NM, remaining on-station 24 hours, and recover at the launch base. | N/A | N/A | N/A | N/A
Block 5: Airspace Coordination - Global Hawk System
The Global Hawk system must be sufficiently robust to allow world wide system employment in all classes of airspace. | N/A | N/A | N/A | N/A
Block 5: Mission Execution - Ground Station
The ground station will allow UAV operators to perform NRT mission control, mission monitoring, and mission updates/ modifications to include dymanic platform and payload control and retasking. | N/A | N/A | N/A | N/A
Block 5: Information Exchange Requirements (IERs)
100% of all top-level IERs. | N/A | N/A | N/A | N/A
Block 10: System Survivability - AV
The AV must be equipped to employ active counter measures against radar and IR-guided threats to the system as identified in the STAR. | N/A | N/A | N/A | N/A
Block 10: Mean Time Between Critical Failure (MTBCF)
System MTBCF of | N/A | N/A | N/A | N/A

## Table 14
160 hours.
Block 10: Signal Intelligence (SIGINT)
TBD | N/A | N/A | N/A | N/A
Endurance (Block 30 and Block 40)
N/A | A mission configured, | (T=O) A mission | TBD | A mission configured,
| MC RQ-4B Block 30 | configured, MC RQ-4B |  | MC RQ-4B Block 30
| or Block 40 aircraft | Block 30 or Block 40 |  | or Block 40 aircraft
| must have a minimum | aircraft must have a |  | must have a minimum
| endurance of 28 hours | minimum endurance of |  | endurance of 28 hours
| plus appropriate fuel | 28 hours plus |  | plus appropriate fuel
| reserves IAW AFI 11- | appropriate fuel |  | reserves IAW AFI 11-
| 202V3, General Flight | reserves IAW AFI 11- |  | 202V3, General Flight
| Rules. | 202V3, General Flight |  | Rules.
Rules.
Worldwide Operations
Block 30
N/A | The RQ-4B Block 30 | The RQ-4B Block 30 | TBD | The RQ-4B Block 30
| system must be | system must be |  | system must be
| equipped to allow | equipped to allow |  | equipped to allow
| worldwide operations | worldwide operations in |  | worldwide operations
| in all classes of | all classes of airspace |  | in all classes of
| airspace with minimal | using procedural |  | airspace with minimal
| procedural | workarounds, air traffic |  | procedural
| workarounds, air | control agreements, |  | workarounds, air
| traffic control | and special use |  | traffic control
| agreements, and | airspace. |  | agreements, and
| special use airspace. |  |  | special use airspace.
Block 40
N/A | The RQ-4B Block 40 | The RQ-4B Block 40 | TBD | The RQ-4B Block 40
| system must be | system must be |  | system must be
| sufficiently robust to | sufficiently robust to |  | sufficiently robust to
| allow worldwide | allow worldwide |  | allow worldwide
| operations in all | operations in all |  | operations in all
| classes of airspace. | classes of airspace |  | classes of airspace.
using procedural
workarounds, air traffic
control agreements,
and special use
airspace.
Dynamic Re-tasking (Block 30 and Block 40)
N/A | The RQ-4B Block 30 | The RQ-4B Block 30 | TBD | The RQ-4B Block 30
| and Block 40 ground | and Block 40 ground |  | and Block 40 ground
| segment must allow | segment must allow |  | segment must allow
| operators to perform | operators to perform |  | operators to perform
| NRT mission control, | NRT mission and |  | NRT mission control,
| mission monitoring, | payload control and |  | mission monitoring,
| mission updates and | monitoring, manual |  | mission updates and
| modifications for | aircraft override control |  | modifications for
| dynamic aircraft and | and manual target |  | dynamic aircraft and
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)

## Table 15
| payload control and re -tasking. | changes to accomplish ad-hoc mission re- tasking. |  | payload control and re -tasking.
Battlespace Awareness (Block 30)
EO Sensor
N/A | EO sensor must | (T=O) EO sensor must | TBD | EO sensor must
| provide a search rate | provide a search rate |  | provide a search rate
| of at least 23,000 sq | of at least 23,000 sq |  | of at least 23,000 sq
| km per hour at an | km per hour at an |  | km per hour at an
| average NIIRS of 5.0 | average NIIRS of 5.0 or |  | average NIIRS of 5.0
| or better on actionable | better on actionable |  | or better on actionable
| imagery. | imagery. |  | imagery.
IR Sensor
N/A | IR sensor must | (T=O) IR sensor must | TBD | IR sensor must
| provide a search rate | provide a search rate |  | provide a search rate
| of at least 12,000 sq | of at least 12,000 sq |  | of at least 12,000 sq
| km per hour at an | km per hour at an |  | km per hour at an
| average NIIRS of 4.7 | average NIIRS of 4.7 or |  | average NIIRS of 4.7
| or better on actionable | better on actionable |  | or better on actionable
| imagery. | imagery. |  | imagery.
SAR Spot Mode
N/A | SAR spot mode | (T=O) SAR spot mode | TBD | SAR spot mode
| (Block 30) will provide | (Block 30) will provide |  | (Block 30) will provide
| a minimum average | a minimum average |  | a minimum average
| NIIRS of 5.5 from 20- | NIIRS of 5.5 from 20- |  | NIIRS of 5.5 from 20-
| 160 km (16-86.5 NM) | 160 km (16-86.5 NM) at |  | 160 km (16-86.5 NM)
| at aircraft broadside ± | aircraft broadside ± 30 |  | at aircraft broadside ±
| 30 degrees. | degrees. |  | 30 degrees.
Net Ready (Block 30 and Block 40)
N/A | The RQ-4B Block 30 | (T=O) The RQ-4B | TBD | The RQ-4B Block 30
| and Block 40 system | Block 30 and Block 40 |  | and Block 40 system
| must support military | system must support |  | must support military
| operations, be able to | military operations, be |  | operations, be able to
| enter and be managed | able to enter and be |  | enter and be managed
| in the network, and | managed in the |  | in the network, and
| exchange information. | network, and exchange |  | exchange information.
information.
Survivability (Block 30 and Block 40)
N/A | The RQ-4B Block 30 | The RQ-4B Block 30 | TBD | The RQ-4B Block 30
| and Block 40 aircraft | and Block 40 system |  | and Block 40 aircraft
| must provide onboard | must receive and |  | must provide onboard
| threat warning and/or | disseminate to |  | threat warning and/or
| autonomous threat | operators on-going |  | autonomous threat
| reaction. | situational awareness |  | reaction.
and dynamic situational
updates from external
sources regarding
threats to the aircraft.
Energy (Block 30 and Block 40)
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)

## Table 16
N/A | The RQ-4 Block 30 and Block 40 will not impact forward deployed logistic infrastructure in support of contingency operations. | (T=O) The RQ-4 Block 30 and Block 40 will not impact forward deployed logistic infrastructure in support of contingency operations. | TBD | The RQ-4 Block 30 and Block 40 will not impact forward deployed logistic infrastructure in support of contingency operations.
Materiel Availability Rate (Block 30 and Block 40)
Aircraft
N/A | The RQ-4B Block 30 and Block 40 aircraft must achieve a materiel availability rate of 60%. | (T=O) The RQ-4B Block 30 and Block 40 aircraft must achieve a materiel availability rate of 60%. | TBD | The RQ-4B Block 30 and Block 40 aircraft must achieve a materiel availability rate of 60%.
MCE
N/A | The MCE must achieve a materiel availability rate of 95%. | (T=O) The MCE must achieve a materiel availability rate of 95%. | TBD | The MCE must achieve a materiel availability rate of 95%.
LRE
N/A | The LRE must achieve a materiel availability rate of 90%. | (T=O) The LRE must achieve a materiel availability rate of 90%. | TBD | The LRE must achieve a materiel availability rate of 90%.
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
RQ-4B Block 30 Capability Production Document dated November 20, 2014 and the RQ-4B Block 40 Capability Production Document dated January 13, 2015.
Change Explanations
(Ch-1) The changes in Performance reflect the approved Milestone C APB.

## Table 17
Acronyms and Abbreviations
DOF - Degrees of Freedom EO - Electro-Optical
GIG-KIP - Global Information Grid Key Interface Profile hrs - hours
IAW - In Accordance With IR - Infrared
Km - Kilometer
NCOW-RM - Net-Centric Operation and Warfare Reference Model NIIRS - National Image Interpretability Rating Scale
NM - Nautical Mile NRT - Near Real Time
SAR - Synthetic Aperture Radar
STAR - System Threat Assessment Report UAV - Unmanned Air Vehicle

## Table 18
Track to Budget
General Notes
The FY 2016 PB includes funding for RQ-4 follow-on efforts that are not part of the MDAP. Those funds are excluded from this report.
RDT&E
Appn |  | BA | PE
Air Force 3600 07 0305205F
Project | Name
4799 Global Hawk HAEUAV/Predator
Air Force 3600 07 0305220F
(Sunk)
Project | Name
5144 Global Hawk HAEUAV (Sunk) 5145 RQ-4 Block 30 (Shared)
Notes: This project is shared with other RQ-4 Block 30 follow-on efforts that are not a part of this MDAP.
5146 RQ-4 BLOCK 40 (Shared)
Notes: This project is shared with other RQ-4 Block 40 follow-on efforts that are not a part of this MDAP.
5147 RQ-4 GSRA/CSRA (Shared) (Sunk)
Notes: This project is shared with other Ground Station and Communications System follow-on efforts that are not a part of this MDAP.
Notes
Projects 5145, 5146 and 5147 share funding with other RQ-4 follow-on efforts that are not a part of this MDAP. Project 5147 is marked Sunk for funding for completed MDAP effort. This Project also identifies funding for upgrade work that will occur after the MDAP program has been completed.
Procurement
Appn |  | BA | PE
Air Force 3010 07 0305220F
Line Item | Name
000075 OTHER PRODUCTION
CHARGES RQ-4
(Shared) (Sunk)
Notes: This project is shared with other RQ-4 follow-on efforts that are not a part of this MDAP.
Air Force 3010 06 0305220F
Line Item | Name
000999 Initial Spares (Shared)
Notes: This project is shared with other RQ-4 follow-on
efforts that are not a part of this MDAP.

## Table 19
Air Force 3010 04 0305220F
Line Item | Name
HAEUAV RQ-4
Air Force 3010 04 0305205F
Line Item | Name
HAEUAV RQ-4 (Shared) (Sunk)
Air Force 3010 05 0305220F
Line Item | Name
HAWK00 RQ-4 Mods (Shared)
Notes: This project is shared with other RQ-4 follow-on efforts that are not a part of this MDAP.
Air Force 3010 04 0305220F
Line Item | Name
RQ440P RQ-4 BLOCK 40 PROC (Sunk)
Air Force 3010 05 0305220F
Line Item | Name
RQ4GCM RQ-4 GSRA/CSRA Mod (Shared) (Sunk)
Notes: This project is shared with other Ground Station and Communications System follow-on efforts that are not a part of this MDAP.
Air Force 3080 02 0305220F
Line Item | Name
821800 Base Communication
Infrastructure
Air Force 3080 03 0305220F
(Shared) (Sunk)
Line Item | Name
837300 Passenger Carrying Vehicles (Shared) (Sunk)
Notes
Line Items 000075, 000999, HAWK00, and RQ4GCM share funding with other RQ-4 follow-on efforts that are not a part of this MDAP. Although Line Items 000075, 000999, and HAWK00 have funding in future years, they are also marked sunk because the future efforts funded in those projects are not a part of this MDAP.
MILCON
Appn |  |  | BA | PE
Air Force |  | 3300 01 |  | 0305205F
|  | Project |  |  | Name
|  | F030011X F04000XX |  | (Air Force) (Air Force) |  | (Shared) | (Sunk) (Sunk)
Air Force |  | 3300 01 |  | 0305220F
|  | Project |  | Name
0501003X |  |  |  | (Air Force) | (Sunk)
06BAEY09 |  |  |  | (Air Force) | (Sunk)
07USAFE6 |  |  |  | (Air Force) | (Sunk)
1030060B |  |  |  | (Air Force) | (Sunk)

## Table 20
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2015 $M |  |  |  |  | BY 2015 $M |  | TY $M
| SAR Baseline Development Estimate |  | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Development Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E | 1116.4 |  |  | 4225.4 | 4647.9 |  | 4217.9 |  | 906.2 |  | 3767 |  | 3767
Procurement | 4628.6 |  |  | 5534.7 | 6088.2 |  | 5524.5 |  | 4459.8 |  | 5135.6 |  | 5135.6
Flyaway | -- |  |  | -- | -- |  | 4089.9 |  | -- |  | -- |  | 3750.7
Recurring | -- |  |  | -- | -- |  | 3953.2 |  | -- |  | -- |  | 3626
Non Recurring | -- |  |  | -- | -- |  | 136.7 |  | -- |  | -- |  | 124.7
Support | -- |  |  | -- | -- |  | 1434.6 |  | -- |  | -- |  | 1384.9
Other Support | -- |  |  | -- | -- |  | 636.1 |  | -- |  | -- |  | 637.4
Initial Spares | -- |  |  | -- | -- |  | 798.5 |  | -- |  | -- |  | 747.5
MILCON | 33.9 |  |  | 139 | 152.9 |  | 138.8 |  | 28 |  | 122.9 |  | 122.9
Acq O&M | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 5778.9 |  |  | 9899.1 | N/A |  | 9881.2 |  | 5394 |  | 9025.5 |  | 9025.5
Current APB Cost Estimate Reference
Global Hawk (RQ-4B) Air Force Service Cost Position (SCP), dated January 13, 2015
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The Life-Cycle Cost Estimate (LCCE) reflects the most probable cost. In this case, the confidence level of the cost estimate is 50%. It takes into consideration relevant risks, including ordinary levels of external and unforeseen events, aiming to provide sufficient resources to execute the program under normal conditions encountering average levels of technical, schedule, and programmatic risk and external influence.
The Base Year for the program has been updated from FY 2000 to FY 2015 using the following deflators:
Appn Category |  | Deflation Factor
RDT&E |  | 1.3284
Procurement |  | 1.3284
MILCON |  | 1.3284

## Table 21
Total Quantity
Quantity | SAR Baseline Development Estimate | Current APB Production | Current Estimate
RDT&E | 0 | 0 | 0
Procurement | 63 | 45 | 45
Total | 63 | 45 | 45

## Table 22
Cost and Funding
Funding Summary
Appropriation Summary
FY 2016 President's Budget / December 2014 SAR (TY$ M)
Appropriation | Prior | FY | 2015 | FY 2016 |  | FY 2017 | FY 2018 |  | FY 2 | 19 | FY | 2020 | To Complete |  |  | Total
RDT&E | 3288.5 | 118.7 |  |  | 179.6 | 134.5 | 45.7 |  | 0 |  | 0 |  | 0 |  | 3767
Procurement | 4691.3 | 51.2 |  |  | 88.8 | 68.2 | 18.7 |  | 56.4 |  | 29.9 |  | 131.1 |  | 5135.6
MILCON | 122.9 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 122.9
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2016 Total | 8102.7 | 169.9 |  |  | 268.4 | 202.7 | 64.4 |  | 56.4 |  | 29.9 |  | 131.1 |  | 9025.5
PB 2015 Total | 8273.1 | 244.3 |  |  | 310.3 | 198.2 | 69.9 |  | 15.2 |  | 10.9 |  | 7.8 |  | 9129.7
Delta | -170.4 | -74.4 |  |  | -41.9 | 4.5 | -5.5 |  | 41.2 |  | 19 |  | 123.3 |  | -104.2
Quantity Summary
FY 2016 President's Budget / December 2014 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2015 | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0
Production | 0 |  | 45 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 45
PB 2016 Total | 0 |  | 45 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 45
PB 2015 Total | 0 |  | 45 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 45
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0

## Table 23
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 129.5
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 198.3
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 329.1
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 351.6
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 368.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 254.7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 223.1
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 264.6
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 227.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 219.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 190.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 286.4
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 151.4
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 94
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 118.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 179.6
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 134.5
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 45.7
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3767

## Table 24
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 165.5
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 250.8
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 410.6
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 428
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 437.2
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 293.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 250.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 291.2
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 247.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 235.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 200.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 296.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 154
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 94.1
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 117.4
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 174.6
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 128.4
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42.8
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4217.9

## Table 25
Total Global Hawk PE includes post modernization outside of RQ-4A/B Global Hawk APB.

## Table 26
Annual Funding 3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.6 |  | 0.6
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.2 |  | 0.2
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.3 |  | 0.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.3 |  | 0.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.8 |  | 0.8
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.3 |  | 0.3
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | 2.5 |  | 2.5

## Table 27
Annual Funding 3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.7 |  | 0.7
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.2 |  | 0.2
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.4 |  | 0.4
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.3 |  | 0.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.9 |  | 0.9
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.3 |  | 0.3
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | 2.8 |  | 2.8

## Table 28
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | 21 |  | -- |  | -- |  | 21 |  | -- |  | 21
2002 |  | 3 | 144.4 |  | -- |  | 8.7 |  | 153.1 |  | 6.8 |  | 159.9
2003 |  | 3 | 136.4 |  | -- |  | 11.1 |  | 147.5 |  | 31.1 |  | 178.6
2004 |  | 4 | 210.4 |  | -- |  | 3.5 |  | 213.9 |  | 38.1 |  | 252
2005 |  | 4 | 252.3 |  | -- |  | 8.4 |  | 260.7 |  | 84.5 |  | 345.2
2006 |  | 5 | 290.3 |  | -- |  | 2.5 |  | 292.8 |  | 59.1 |  | 351.9
2007 |  | 5 | 328.2 |  | 7.5 |  | 12.2 |  | 347.9 |  | 75.2 |  | 423.1
2008 |  | 5 | 362.5 |  | 25.7 |  | 7.4 |  | 395.6 |  | 132 |  | 527.6
2009 |  | 5 | 388.3 |  | 84.7 |  | 32.4 |  | 505.4 |  | 240.1 |  | 745.5
2010 |  | 4 | 341.1 |  | 86.7 |  | 20.3 |  | 448.1 |  | 127.2 |  | 575.3
2011 |  | 4 | 415.4 |  | 84.2 |  | -- |  | 499.6 |  | 65.5 |  | 565.1
2012 |  | 3 | 206.5 |  | 55.1 |  | -- |  | 261.6 |  | 106.6 |  | 368.2
2013 |  | -- | -- |  | 7 |  | 7.2 |  | 14.2 |  | 115.5 |  | 129.7
2014 |  | -- | -- |  | 33 |  | 11 |  | 44 |  | 1.7 |  | 45.7
2015 |  | -- | -- |  | 22.4 |  | -- |  | 22.4 |  | 28.8 |  | 51.2
2016 |  | -- | -- |  | 43.6 |  | -- |  | 43.6 |  | 45.2 |  | 88.8
2017 |  | -- | -- |  | 52.2 |  | -- |  | 52.2 |  | 16 |  | 68.2
2018 |  | -- | -- |  | 14.3 |  | -- |  | 14.3 |  | 4.4 |  | 18.7
2019 |  | -- | -- |  | 12.7 |  | -- |  | 12.7 |  | 43.7 |  | 56.4
2020 |  | -- | -- |  | 0.1 |  | -- |  | 0.1 |  | 29.8 |  | 29.9
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | 43.6 |  | 43.6
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | 87.5 |  | 87.5
Subtotal |  | 45 | 3096.8 |  | 529.2 |  | 124.7 |  | 3750.7 |  | 1382.4 |  | 5133.1

## Table 29
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | 26.6 |  | -- |  | -- |  | 26.6 |  | -- |  | 26.6
2002 |  | 3 | 180.5 |  | -- |  | 10.9 |  | 191.4 |  | 8.5 |  | 199.9
2003 |  | 3 | 167.8 |  | -- |  | 13.7 |  | 181.5 |  | 38.2 |  | 219.7
2004 |  | 4 | 252.1 |  | -- |  | 4.2 |  | 256.3 |  | 45.6 |  | 301.9
2005 |  | 4 | 293.7 |  | -- |  | 9.8 |  | 303.5 |  | 98.4 |  | 401.9
2006 |  | 5 | 329.2 |  | -- |  | 2.8 |  | 332 |  | 67.1 |  | 399.1
2007 |  | 5 | 362.5 |  | 8.3 |  | 13.5 |  | 384.3 |  | 83.1 |  | 467.4
2008 |  | 5 | 394.1 |  | 27.9 |  | 8 |  | 430 |  | 143.6 |  | 573.6
2009 |  | 5 | 415.1 |  | 90.5 |  | 34.6 |  | 540.2 |  | 256.7 |  | 796.9
2010 |  | 4 | 357.8 |  | 90.9 |  | 21.3 |  | 470 |  | 133.4 |  | 603.4
2011 |  | 4 | 428.7 |  | 86.9 |  | -- |  | 515.6 |  | 67.6 |  | 583.2
2012 |  | 3 | 209.7 |  | 56 |  | -- |  | 265.7 |  | 108.3 |  | 374
2013 |  | -- | -- |  | 7 |  | 7.2 |  | 14.2 |  | 114.6 |  | 128.8
2014 |  | -- | -- |  | 32.3 |  | 10.7 |  | 43 |  | 1.7 |  | 44.7
2015 |  | -- | -- |  | 21.6 |  | -- |  | 21.6 |  | 27.7 |  | 49.3
2016 |  | -- | -- |  | 41.2 |  | -- |  | 41.2 |  | 42.7 |  | 83.9
2017 |  | -- | -- |  | 48.4 |  | -- |  | 48.4 |  | 14.8 |  | 63.2
2018 |  | -- | -- |  | 13 |  | -- |  | 13 |  | 4 |  | 17
2019 |  | -- | -- |  | 11.3 |  | -- |  | 11.3 |  | 39 |  | 50.3
2020 |  | -- | -- |  | 0.1 |  | -- |  | 0.1 |  | 26 |  | 26.1
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | 37.3 |  | 37.3
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | 73.5 |  | 73.5
Subtotal |  | 45 | 3417.8 |  | 535.4 |  | 136.7 |  | 4089.9 |  | 1431.8 |  | 5521.7

## Table 30
Total Global Hawk PE includes post modernization outside of RQ-4A/B Global Hawk APB.
Cost Quantity Information 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2015 $M
2001 | -- | --
2002 | 3 | 167.7
2003 | 3 | 159.3
2004 | 4 | 239.2
2005 | 4 | 284.4
2006 | 5 | 330.7
2007 | 5 | 359.3
2008 | 5 | 375.5
2009 | 5 | 437.7
2010 | 4 | 307.6
2011 | 4 | 465.1
2012 | 3 | 291.3
2013 | -- | --
2014 | -- | --
2015 | -- | --
2016 | -- | --
2017 | -- | --
2018 | -- | --
2019 | -- | --
2020 | -- | --
2021 | -- | --
2022 | -- | --
Subtotal | 45 | 3417.8

## Table 31
Annual Funding 3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | TY $M
Total Program
2003 | 11.7
2004 | 22.2
2005 | 9.8
2006 | 14.1
2007 | 48.6
2008 | --
2009 | --
2010 | 16.5
Subtotal | 122.9

## Table 32
Annual Funding 3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | BY 2015 $M
Total Program
2003 | 14.3
2004 | 26.4
2005 | 11.3
2006 | 15.9
2007 | 53.5
2008 | --
2009 | --
2010 | 17.4
Subtotal | 138.8

## Table 33
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2001-03-06 | 2013-09-09
Approved Quantity | 6 | 45
Reference | Milestone II ADM | LRIP ADM
Start Year | 2001 | 2001
End Year | 2004 | 2017
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the small RQ-4A/B Global Hawk fleet size of 45. This exaggerates the effects of the 10% boundary.
The FY 2014 PB procurement baseline includes 45 aircraft and associated ground stations (ten Launch and Recovery Elements and ten Mission Control Elements).

## Table 34
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
South Korea | 2014-03-26 | 4 | 693 | South Korea signed the Letter of Agreement on March 26, 2014. The South Korean Global Hawk program is a $693M FMS case (KS-D-SAD) to purchase 4 GH Block 30-I aircraft (capable for export,) 2 ground control elements (1 fixed, 1 transportable) and 2 spare engines. An Undefinitized Contract Action was issued to the contractor on December 16, 2014 in order to preserve the proposed first aircraft delivery in the 4th quarter of FY 2018. The initial efforts in this case will deliver the aircraft with the Enhanced Integrated Sensor Suite with the potential to add other payloads later in the program.
NATO | 2009-09-03 | 5 | 2383 | The North Atlantic Treaty Organization (NATO) Alliance Ground Surveillance (AGS) program has contracted with NGISSII (a Northrop Grumman company) through a Direct Commercial Sale (DCS) to obtain five RQ-4B Global Hawk Block 40- like aircraft equipped with the US Navy’s Q-4 TRITON COMMS/COMMS architecture; the Radar Technology Insertion Program (RTIP) Synthetic Aperture Radar sensor; and integrated with a NATO -unique ground station environment The program is a cooperative development effort with 15 of the 28 NATO nations funding the procurement effort; Poland officially joined in 2014. US Government (USG) funds approximately 41.7% of the cost.
Germany | 2007-09-25 | 1 | 675 | The Euro Hawk Risk Reduction Program (RRP) is the DCS between the German Government and Euro Hawk GmbH (Northrop Grumman/Cassidian partnership). The German Government purchased a Euro Hawk system to replace their current signals intelligence system. The system consists of one modified RQ-4B Global Hawk air vehicle and ground segment, and a German-built Signals Intelligence (SIGINT) sensor payload. The USG provides support through a $34.8M FMS case (GY- D-STY). The air vehicle was delivered to Germany for sensor integration in July 2011. Germany's sensor integration flight testing began on January 11, 2013. On May 14, 2013, the German government announced the decision to cancel the Euro Hawk program. Although Germany obtained airworthiness certification for experimental aircraft flight testing, the program was cancelled due to the perceived cost to obtain permanent airworthiness certification. Germany halted sensor flight testing at

## Table 35
the end of August 2013, but has since decided to reschedule flight test and reconsider options for system purchases.
Notes
Nuclear Costs
None

## Table 36
Unit Cost
Unit Cost Report
Item |  | BY 2015 $M | BY 2015 $M |  | % Change
|  | Current UCR Baseline (Feb 2015 APB) | Current Estimate (Dec 2014 SAR)
Program Acquisition Unit Cost
Cost | 9899.1 |  |  | 9881.2
Quantity | 45 |  |  | 45
Item | 219.98 |  |  | 219.582 |  | -0.18
Average Procurement Unit Cost
Cost | 5534.7 |  |  | 5524.5
Quantity | 45 |  |  | 45
Unit Cost | 122.993 |  |  | 122.767 |  | -0.18
Item |  | BY 2015 $M | BY 2015 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2014 SAR)
(Feb 2015 APB)
Program Acquisition Unit Cost
Cost | 9899.1 |  |  | 9881.2
Quantity | 45 |  |  | 45
Unit Cost | 219.98 |  |  | 219.582 |  | -0.18
Average Procurement Unit Cost
Cost | 5534.7 |  |  | 5524.5
Quantity | 45 |  |  | 45
Unit Cost | 122.993 |  |  | 122.767 |  | -0.18

## Table 37
Unit Cost History
Item |  |  |  |  | Date |  |  |  | BY 2015 $M | [8 empty] | TY $M
[9 empty] | PAUC |  |  |  | APUC |  |  |  |  | PAUC |  |  | APUC
Original APB |  |  | Mar 2001 | [5 empty] | 82.703 | [5 empty] | 66.244 |  |  |  | 85.619 |  |  | 70.79
APB as of January 2006 |  |  | Dec 2002 | [5 empty] | 122.033 | [5 empty] | 68.214 |  |  |  | 115.459 |  |  | 65.673
Revised Original APB |  |  | Feb 2015 | [5 empty] | 219.98 | [5 empty] | 122.993 |  |  |  | 200.567 |  |  | 114.124
Prior APB |  |  | Mar 2007 | [5 empty] | 179.728 | [5 empty] | 108.793 |  |  |  | 180.267 |  |  | 111.53
Current APB |  |  | Feb 2015 | [5 empty] | 219.98 | [5 empty] | 122.993 |  |  |  | 200.567 |  |  | 114.124
Prior Annual SAR |  |  | Dec 2013 | [5 empty] | 203.471 | [5 empty] | 114.502 |  |  |  | 202.882 |  |  | 116.08
Current Estimate |  |  | Dec 2014 | [5 empty] | 219.582 | [5 empty] | 122.767 |  |  |  | 200.567 |  |  | 114.124
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [18 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng |  | Est |  |  | Oth |  |  | Spt |  | Total
85.619 3.767 20.726 1.664 51.896 15.131 0.000 21.764 114.948 200.567
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [18 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  |  | Eng |  |  | Est |  | Oth |  |  | Spt |  | Total
70.790 1.844 14.795 -10.502 14.564 2.602 0.000 20.031 43.334 114.124

## Table 38
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone I | N/A | N/A | N/A | N/A
Milestone II | N/A | Feb 2001 | N/A | Mar 2001
Milestone III | N/A | N/A | N/A | N/A
IOC | N/A | N/A | N/A | Aug 2011
Total Cost (TY $M) | N/A | 5394 | N/A | 9025.5
Total Quantity | N/A | 63 | N/A | 45
PAUC | N/A | 85.619 | N/A | 200.567
The Global Hawk FRP Decision Review, which would have replaced the previously planned Milestone III decision, is no longer applicable. Production is nearly complete. The APB was reset at Milestone C on February 23, 2015.

## Table 39
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
906.2 4459.8 28.0 5394.0
Economic |  | 26.1 |  | 6.4 |  | 3.6 |  | 36.1
Quantity |  | -- |  | -608.5 |  | -- |  | -608.5
Schedule |  | 555.6 |  | -472.6 |  | -8.1 |  | 74.9
Engineering |  | 1562.9 |  | 655.4 |  | 117 |  | 2335.3
Estimating |  | 657.4 |  | 480.7 |  | -20.6 |  | 1117.5
Other |  | -- |  | -- |  | -- |  | --
Support |  | 75 |  | 702.4 |  | 3 |  | 780.4
Subtotal |  | 2877 |  | 763.8 |  | 94.9 |  | 3735.7
Current Changes Economic |  | 55 |  | 76.6 |  | 1.8 |  | 133.4
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -71.2 |  | -363.6 |  | -1.8 |  | -436.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 199 |  | -- |  | 199
Subtotal |  | -16.2 |  | -88 |  | -- |  | -104.2
Adjustments |  | -- |  | -- |  | -- |  | --
Total Changes |  | 2860.8 |  | 675.8 |  | 94.9 |  | 3631.5
CE - Cost Variance |  | 3767 |  | 5135.6 |  | 122.9 |  | 9025.5
CE - Cost & Funding |  | 3767 |  | 5135.6 |  | 122.9 |  | 9025.5

## Table 40
Summary BY 2015 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
1116.4 4628.6 33.9 5778.9
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -540.4 |  | -- |  | -540.4
Schedule |  | 550.5 |  | -474.5 |  | -2.8 |  | 73.2
Engineering |  | 1882.8 |  | 887 |  | 130.6 |  | 2900.4
Estimating |  | 652.6 |  | 476.7 |  | -24.2 |  | 1105.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | 97.9 |  | 737.3 |  | 3.3 |  | 838.5
Subtotal |  | 3183.8 |  | 1086.1 |  | 106.9 |  | 4376.8
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -82.3 |  | -358.9 |  | -2 |  | -443.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 168.7 |  | -- |  | 168.7
Subtotal |  | -82.3 |  | -190.2 |  | -2 |  | -274.5
Adjustments |  | -- |  | -- |  | -- |  | --
Total Changes |  | 3101.5 |  | 895.9 |  | 104.9 |  | 4102.3
CE - Cost Variance |  | 4217.9 |  | 5524.5 |  | 138.8 |  | 9881.2
CE - Cost & Funding |  | 4217.9 |  | 5524.5 |  | 138.8 |  | 9881.2
Previous Estimate: December 2013

## Table 41
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 55
Revised estimate to reflect prior year actuals. (Estimating) | -43.8 | -43
Revised estimate of costs for software integration. (Estimating) | -72.1 | -73.9
Revised estimate for government testing. (Estimating) | 17.2 | 18.1
Revised estimate for Program Office support costs. (Estimating) | 61.9 | 64.2
Revised estimate for Joint Mission Planning System development. (Estimating) | 1.6 | 1.4
Revised estimate for cost of Enhanced Weather Capability and Ice Shape Testing. | -1.9 | -1.7
(Estimating)
Revised estimate for reliability and maintainability. (Estimating) | 20.9 | 21.4
Revised estimate for contractor test support. (Estimating) | 4.9 | 5.8
Revised estimate for infrastructure costs. (Estimating) | 17.9 | 19
Revised estimate for Airborne Signals Intelligence Payload (ASIP) sensors. (Estimating) | -31.1 | -32.2
Adjustment for current and prior escalation. (Estimating) | -60.8 | -53.4
Revised estimate to reflect the application of new out year escalation indices. (Estimating) | 3 | 3.1
RDT&E Subtotal | -82.3 | -16.2
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 76.6
Revised estimate to reflect prior year actuals. (Estimating) | -126.6 | -125
Revised estimate for production line disposition. (Estimating) | -24.5 | -25.7
Revised estimate for diminishing manufacturing sources. (Estimating) | -22.5 | -24
Revised estimate of International Maritime Satellite/Communication Security modifications. | -40.8 | -42.7
(Estimating)
Revised estimate of cost of weather radar. (Estimating) | -5.3 | -5.9
Revised estimate for ASIP sensors. (Estimating) | -21 | -23.9
Revised estimate for program office management/other government costs. (Estimating) | -14.9 | -16.4
Revised estimate for change requests and low cost modifications. (Estimating) | -8.2 | -9
Revised estimate due to recategorization of Flyaway Costs. (Estimating) | -34 | -36
Adjustment for current and prior escalation. (Estimating) | -64.2 | -58.3
Revised estimate to reflect the application of new out year escalation indices. (Estimating) | 3.1 | 3.3
Adjustment for current and prior escalation. (Support) | -18 | -17
Increase in Other Support due to recategorization of Flyaway Costs and depot activation. | 236.3 | 269.3
(Support)
Decrease in Initial Spares due to removal of follow-on efforts that are not part of the MDAP. (Support)
-49.6 -53.3
Procurement Subtotal -190.2 -88.0
MILCON | $M
Current Change Explanations | Base Year | Then Year

## Table 42
Revised escalation indices. (Economic) Adjustment for current and prior escalation. (Estimating) | N/A -2.0 | +1.8 -1.8
MILCON Subtotal | -2 | 0

## Table 43
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: LRIP Lot 9 Payloads FFP
Contractor: Northrop Grumman Systems Corporation
Contractor Location: 17066 Goldentop Road
San Diego, CA 92127-2412
Contract Number: FA8620-10-C-4007/2
Contract Type: Firm Fixed Price (FFP)
Award Date: May 20, 2010
Definitization Date: August 12, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
20.1 N/A 15 137.9 N/A 522 137.9 137.9
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the strategy to add additional spares and Peculiar Support Equipment (PSE).
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This contract procures PSE (339 items) and Enhanced Integrated Sensor Suite and Airborne Signals Intelligence Payload spares (183 items) for the LRIP Lot 9 Payloads captured under the LRIP Lot 9 Payloads FPIF contract, as well as supporting labor for the PSE and spares.
This contract is 90% delivered and will no longer be reported.

## Table 44
Contract Identification
Appropriation: RDT&E
Contract Name: IDIQ Task Order 1 - Enterprise Management Services
Contractor: Northrop Grumman Contractor Location: San Diego, CA 92127-2412 Contract Number: FA8620-13-D-3014/1 Contract Type: Firm Fixed Price (FFP)
Award Date: May 15, 2013
Definitization Date: May 15, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
28.0 N/A N/A 28.0 N/A N/A 28.0 28.0
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This contract is for the procurement of Enterprise Management services.

## Table 45
Contract Identification
Appropriation: RDT&E
Contract Name: IDIQ Task Order 2 - Flight Test Support
Contractor: Northrop Grumman Contractor Location: SanDiego, CA 92127-2412 Contract Number: FA8620-13-D-3014/2 Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: May 15, 2013
Definitization Date: May 15, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
22.9 N/A N/A 45.6 N/A N/A 44.9 47.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the option year contract being executed.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2014) -0.7 -0.6
Previous Cumulative Variances -0.5 -0.3
Net Change -0.2 -0.3
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to allocated costs from a pool across a broad range of contracts higher than planned. This is a recurring variance and is expected to continue through the end of the PoP.
The unfavorable net change in the schedule variance is due to lagging invoices from the subcontractors.
Notes
This contract is for flight test support for the Global Hawk fleet.

## Table 46
Contract Identification
Appropriation: Procurement
Contract Name: Global Hawk LRIP Lot 11
Contractor: Northrop Grumman (Aerospace Systems)
Contractor Location: 17066 Goldentop Rd
San Diego, CA 92127
Contract Number: FA8620-13-C-3018
Contract Type: Firm Fixed Price (FFP)
Award Date: August 15, 2014
Definitization Date: August 15, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
355.0 N/A 3 355.0 N/A 3 355.0 355.0
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This is the first time this contract is being reported.
The LRIP Lot 11 contract procures three Blk 30 aircraft and two ASIP sensor kits.

## Table 47
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 45 | 42 | 45 | 93.33%
Total Program Quantity Delivered | 45 | 42 | 45 | 93.33%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
9025.5
7337
81.29%
22
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
15
68.18%
8272.6
91.66%
The above data is current as of January 31, 2015.

## Table 48
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 13, 2015
Source of Estimate: SCP
Quantity to Sustain: 45
Unit of Measure: Aircraft
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2003 - FY 2034
Current sustainment planning assumes that Block 30s will fly through 2032, while Block 40s will fly through 2034 (dates based on IOC +20 years). At this time, the Life Cycle Sustainment Plan, the Concept of Operations, and the Operations Tempo are all being re-examined in light of operational and budget decisions. Costs below span FY 2003 through FY 2034, the entire period of planned Global Hawk production fleet operations. Total quantity of aircraft supported over the life cycle is 45. Cost estimates assume all 45 aircraft will be operational. The service life of a Global Hawk air vehicle is planned for 20 years but may vary based on operational tempo.
The total estimated flying hours for the life of the program is 510,724, an increase from the previous estimated flying hours of 497,562. This increase includes Block 30s flying through FY 2032 and Block 40s through FY 2034.
Sustainment Strategy
Global Hawk sustainment is accomplished by a combination of civil service, military, and contractor personnel. The Global Hawk is being maintained using a two level maintenance (2LM) concept – Organizational and Depot, which supports the maximum use of rapid transportation, minimum turnaround times for repair, and a capability to deploy with minimum direct mission support equipment. The 2LM concept is used at both the Forward Operating Locations and Main Operating Bases. Air Combat Command accomplishes organizational level maintenance tasks via military, civilian, and contractor support. The contractor accomplishes depot level maintenance tasks and repair actions under a Contractor Logistics Support contract.
Antecedent Information
No Antecedent
Annual O&S Costs BY2015 $M
Cost Element | RQ-4A/B Global Hawk Average Annual Cost Per Aircraft | No Global Hawk Antecedent (Antecedent)
Unit-Level Manpower | 3.014 | 0
Unit Operations | 1.562 | 0
Maintenance | 4.091 | 0
Sustaining Support | 3.889 | 0
Continuing System Improvements | 0.87 | 0
Indirect Support | 2.257 | 0
Other | 0 | 0
Total | 15.683 | --

## Table 49
Item | Total O&S Cost $M
| RQ-4A/B Global Hawk | [5 empty] | No Global Hawk Antecedent (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 15724.8 |  | 17297.3 |  |  | 11872.5 | N/A
Then Year | 17835.9 |  | N/A |  |  | 17835.9 | N/A
Equation to Translate Annual Cost to Total Cost
Unitized costs are calculated by dividing total estimated O&S costs in BY 2000 dollars ($11,872.5M) by total life cycle operational aircraft years (757), resulting in an average annual O&S cost per aircraft of $15.68M.
O&S Cost Variance
Category |  | BY 2015 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2013 SAR
12909.7
Programmatic/Planning Factors -567.1 Sustainment costs that are no longer part of the MDAP. Cost Estimating Methodology 0.0
Cost Data Update -192.0 Manpower that is not associated with the MDAP. Labor Rate 0.0
Energy Rate 0.0
Technical Input -278.1 Reliability improvements resulting in lower maintenance cost.
Other 0.0
Total Changes -1037.2
Current Estimate 11872.5
Disposal Estimate Details
Date of Estimate: January 13, 2015
Source of Estimate: SCP
Disposal/Demilitarization Total Cost (BY 2015 $M): Total costs for disposal of all Aircraft are 6.4