## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-261
Advanced Extremely High Frequency Satellite (AEHF)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 6
Mission and Description 7
Executive Summary 8
Threshold Breaches 11
Schedule 12
Performance 15
Track to Budget 20
Cost and Funding 22
Low Rate Initial Production 45
Foreign Military Sales 46
Nuclear Costs 46
Unit Cost 47
Cost Variance 53
Contracts 59
Deliveries and Expenditures 62
Operating and Support Cost 63

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Advanced Extremely High Frequency Satellite (AEHF)
DoD Component
Air Force
Joint Participants
Canada; The Netherlands; United Kingdom
Responsible Office
Mr. Robert Tarleton
MILSATCOM Systems Directorate 483 N. Aviation Blvd.
El Segundo, CA 90245-2802
robert.tarleton@us.af.mil
Phone: | 310-653-9001
Fax: | 310-653-9636
DSN Phone: | 633-9001
DSN Fax: | 633-9636
Date Assigned: | February 10, 2014

## Table 6
References
AEHF SV 1-4
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated March 3, 2005
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated March 31, 2014
AEHF SV 5-6
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 23, 2012
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 23, 2012

## Table 7
Mission and Description
Advanced Extremely High Frequency Satellite (AEHF) is a joint service satellite communications system that provides global, survivable, secure, protected, and jam-resistant communications for high priority military ground, sea, and air assets. The system consists of four satellites in Geosynchronous Earth Orbit that provide 10 times the capacity of the 1990s-era Milstar Block II satellites. The system provides continuous 24-hour Extremely High Frequency Extended Data Rate coverage between 65 degrees north and 65 degrees south latitude. AEHF allows the National Security Council and Combatant Commanders to control their tactical and strategic forces at all levels of conflict up to and including general nuclear war, and it supports the attainment of information superiority.
The AEHF operational system is composed of three segments: space, terminals, and mission control. The space segment consists of a cross-linked constellation of satellites to provide worldwide coverage. The terminal segment includes fixed and mobile ground terminals, ship and submarine terminals, and airborne terminals. The mission control segment controls satellites on orbit, monitors satellite health, and provides communication system planning and monitoring. This segment is also survivable, with both fixed and mobile control stations.
International Cooperative Program – The three countries that have signed Memoranda of Understanding are as follows: Canada, November 16, 1999; the Netherlands, November 8, 2002; and the United Kingdom, September 9, 2003. These bilateral agreements allocate a portion of protected communication resources in exchange for financial participation in development. The Netherlands, Canada, and the United Kingdom signed Memoranda of Understanding in preparation for entering into a Foreign Military Sales case to purchase International Partnership variants of AEHF terminals.

## Table 8
Executive Summary
Program Highlights Since Last Report
The Advanced Extremely High Frequency (AEHF) program had many noteworthy achievements in 2015. The system met all ORD requirements and AEHF IOC was declared on July 28, 2015 allowing operators to transition from limited use to full operations and increasing the number of users/missions on the system, which is within the APB threshold of December 2015. AEHF-1/2/3 are fully integrated into the Milstar/AEHF constellation and performing well with AEHF-1 operating from 68 degrees West (covering the Eastern United States), AEHF-2 operating from 19 degrees East as of October 21, 2015 (covering Western Europe and Africa), and AEHF-3 operating from 152 degrees East (covering the Pacific Ocean). In an effort to provide better support to operational users, the 2015 constellation reconfiguration plan providing better support to operational users (AEHF-2 repositioning to 19 degrees East from 16.5 degrees West, AEHF-1 and AEHF-3 remaining in their current location) was approved June 10, 2015.
The AEHF-4 satellite bus is 91% complete and the payload is 85% complete. On October 14, 2014, Northrop Grumman delivered the payload to the AEHF prime contractor, Lockheed Martin, over four months ahead of the baseline schedule for Payload Integration and Test. The Payload Module and Core Module have been successfully mated, marking the beginning of single line flow integration and testing well ahead of the baseline schedule. Launch availability for AEHF-4 is on track for the 2nd Quarter of CY 2017.
AEHF 5-6 production has steadily progressed since contract definitization on October 31, 2013, with a value of $2.2B. The Lockheed Martin satellite buses for the combined AEHF 5-6 effort are 73% complete and the Northrop Grumman payloads for the combined effort are 69% complete. Launch availability for AEHF-5 and AEHF-6 are on track for CY 2018 and CY 2019, respectively.
There are no significant software-related issues with this program at this time.
History of Significant Developments Since Program Initiation
May 1999: The DAE signed the Milestone I ADM approving entry into Phase I, System Definition.
August 1999: Two competitive System Definition contracts were awarded to Lockheed/TRW (now Northrop Grumman) and Hughes (now Boeing Satellite Systems) teams. Following the System Requirements Review and the Milstar flight 3 launch failure, the AEHF competition was re-established into a National Team consisting of all three contractors with Lockheed as the prime integration contractor. A “pathfinder” concept was put into effect to mitigate the loss of Milstar 3 capability. This concept included the acceleration of a Milstar II capable AEHF satellite followed by delivery of four additional fully capable AEHF satellites.
May 26, 2000: An ADM was approved by USD(AT&L) that authorized a sole source Firm Fixed Price pathfinder concept award to a team of contractors.
FY 2002: Due to fiscal constraints the program was initially broken into two production cycles. The first cycle consisted of AEHF-1 & -2 and the Mission Control Segment (MCS) development for an FY 2008 IOC. The second cycle included AEHF- 3, -4, & -5 production for a FOC in FY 2012. After FY 2002 Congressional reductions and the initiation of the Transformational Communications Satellite (TSAT) program, the Deputy Secretary of Defense directed a change to the acquisition strategy in December 2002 removing AEHF-4 & -5 from the baseline.
December 2002: The contract launch dates for AEHF-1 & -2 were December 2006 and December 2007, and AEHF-3 was projected to be launched in April 2009. The definitized contract breached the APB IOC schedule threshold and overall program cost. An updated APB incorporating the new August 2009 IOC and revised strategy was signed in December 2002.
March 2005: A revised APB to include the launch slip and approval of AEHF-3 procurement was signed. Due to funding

## Table 9
constraints, the FY 2004 PB introduced a one-year production gap between AEHF-2 and AEHF-3. In addition to the cost of delaying AEHF-3 production, other subsequent cost drivers, including payload hardware testing, information assurance product delivery delays and replacement of critical electronic parts, drove a one-year launch delay. A Nunn-McCurdy significant unit cost breach was sent to Congress on December 2, 2004.
May 2007: The AEHF-1 & -2 and MCS developments were well underway. The program successfully completed run-for- record intersegment tests for AEHF/Milstar compatibility and Lockheed Martin also successfully demonstrated the ability of the AEHF Satellite Mission Control Subsystem to command and control the AEHF payload engineering model and the Interim Command and Control (C2) Terminal for Milstar.
September 2008: A Nunn-McCurdy critical unit cost breach notification occurred on September 5, 2008 due to the addition of AEHF-4 to the program and the AEHF-1 & -2 launch slips’ cascading cost and schedule impacts on AEHF-3. The Government had concluded the production gap of four years for AEHF-4 would cause significant cost impacts to obsolescence issues such as Monolithic Microwave Integrated Circuits. The Nunn-McCurdy breach was caused by additional funding required for obsolescence, a seven-month schedule delay due to AEHF-1 hardware issues, additional Thermal Vacuum tests, greater than expected AEHF-1 & -2 integration costs, and an overall IOC schedule slip. The USD (AT&L) signed an ADM on December 29, 2008 certifying the AEHF program to proceed with a fully-funded four-satellite baseline. The ADM established new launch dates of September 2010, 2011, 2012, and 2016.
June 2009: After the cancellation of the TSAT program, the DoD directed the procurement of additional AEHF satellites. The AEHF-4 contract was awarded for $1.4B in December 2010, and the MDA approved the AEHF 1-4 APB in June 2011. In December 2011, The MDA approved the AEHF 5-6 Acquisition Strategy as a DoD Efficient Space Procurement, and the APB designating AEHF 5-6 as a sub-program was approved by the MDA October 23, 2012. On October 31, 2013 the Fixed Price Incentive Fee contract was definitized for the block buy of AEHF 5-6.
May 2010: The AEHF program office completed the C2 transition of the five-satellite Milstar constellation from a legacy C2 system to the new AEHF C2 system. In December 2011 an Interim Contractor Support contract was awarded to Lockheed Martin to provide sustainment of the space and ground segments until IOC is achieved.
August 2010: AEHF-1 was successfully launched from Cape Canaveral Air Force Station (CCAFS) on August 14, 2010. AEHF-1 experienced an anomaly that resulted in the failure of a Liquid Apogee Engine. Orbit raising was completed using the Reaction Engine Assemblies on October 24, 2011 after a 14-month effort. Satellite Control Authority (SCA) was transferred on March 12, 2012.
May 2012: AEHF-2 was successfully launched from CCAFS on May 4, 2012 and the space vehicle successfully completed on-orbit testing on September 24, 2012. SCA was transferred on November 7, 2012.
September 2013: AEHF-3 was successfully launched from CCAFS on September 18, 2013. October 2013: AEHF 5-6 contract definitized with a value of $2.2B on October 31, 2013.
January 2014: AEHF-3 space vehicle arrived on-orbit and successfully completed on-orbit testing on January 6, 2014. March 2014: SCA was completed on March 21, 2014.
May 2014: U.S. Strategic Command declared early operational use of AEHF-1, 2, and 3 on May 12 2014. All three satellites fully integrated into the Milstar constellation.
October 2014: On October 16, 2014, the program received PEO certification for the systems (ground and space vehicle) to enter Air Force Operational Test and Evaluation Center System Dedicated Operational Test which began November 3, 2014 and ran through mid-January 2015.
January 2015: Multi-service Operational Test and Evaluation (MOT&E) completed on January 16, 2015 and AEHF-3 began repositioning from its interim (MOT&E) location of 155 degrees West on January 21, 2015.
March 2015: AEHF-3 arrived at its new operating location of 152 degrees East (covering the Western Pacific Ocean) on

## Table 10
March 18, 2015.
July 2015: Air Force Space Command Commander declared AEHF IOC on July 28, 2015. September 2015: USD(AT&L) redesignated AEHF as an ACAT IC on September 11, 2015.
October 2015: AEHF-2 arrived at its new operating location of 19 degrees East (covering Western Europe and Africa) on
October 21, 2015.

## Table 11
Threshold Breaches
AEHF SV 1-4
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
AEHF SV 5-6
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 12
Schedule

## Table 13
AEHF SV 1-4
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone I | Apr 1999 | Apr 1999 | Apr 1999 | Apr 1999
Contract Award System Definition | Aug 1999 | Aug 1999 | Aug 1999 | Aug 1999
Milestone B (DAB) | Jun 2001 | Sep 2001 | Sep 2001 | Sep 2001
Contract Award EMD/Production | Jun 2001 | Nov 2001 | Nov 2001 | Nov 2001
Follow on Buy Decision | Jun 2004 | Jun 2004 | Jun 2004 | Jun 2004
IOC | Jun 2010 | Jun 2015 | Dec 2015 | Jul 2015
(Ch-1)
Change Explanations
(Ch-1) IOC current estimate changed from June 2015 to July 2015 to reflect the actual IOC of July 28, 2015.
Notes
The IOC milestone is defined in the AEHF ORD dated October 1, 2000 and addresses the capability at the time satellite two is operational. It also includes missions supported, networks active and two separate satellites operating in the AEHF mode. The operational control segment consists of one fixed and one transportable control element and an interim fully operational communications management system.
Mission Planning Element Release 7.5 and AEHF Satellite Mission Control System Release 7.5.1 completed Multi-service Operational Test and Evaluation on January 16, 2015. Both releases were utilized for AEHF system IOC declaration in CY 2015.

## Table 14
AEHF SV 5-6
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
AEHF SV 5-6 Production Decision | May 2012 | May 2012 | May 2012 | May 2012
Launch Availability AEHF SV-5 | Jun 2018 | Jun 2018 | Dec 2018 | Jun 2018
Launch Availability AEHF SV-6 | Jun 2019 | Jun 2019 | Dec 2019 | Jun 2019
Change Explanations
None
Notes
Launch Availability is defined as all factory work completed and satellite readied for shipment to the launch base.

## Table 15
Performance
AEHF SV 1-4
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Capacity
1.2 Gbps CMTW, 600 | 1.2 Gbps CMTW, 600 | Support at least 500 | 1.0 Gbps CMTW | 1.2 Gbps CMTW, 600
Mbps Strategic | Mbps Strategic | Mbps for CMTW | Scenario, 600 Mbps | Mbps Strategic
|  | Scenario and at least | Strategic Scenario -
|  | 350 Mbps for | verified required
|  | Strategic Scenario | capability as part of
system requirement
sell-off prior to
AEHF-1 launch
Nuclear Protection
Provide assured | Provide assured | Provide assured | Verified required | Provide assured
communicat-ions to | communicat-ions to | communicat-ions to | capability as part of | communications to
survivable nuclear | survivable nuclear | survivable nuclear | system requirement | survivable nuclear forces
forces exposed to the | forces exposed to the | forces exposed to the | sell-off prior to | exposed to the
environment | environment | environment | AEHF-2 launch. | environment specified in
specified in NCGS-89 | specified in NCGS-89 | specified in NCGS-89 |  | NCGS-89-06, and for
-06, and for those | -06, and for those | -06, and for those |  | those critical networks
critical networks that | critical networks that | critical networks that |  | that support the following
support the following | support the following | support the following |  | critical functions:
critical functions: | critical functions: | critical functions: |  | situation monitoring,
situation monitoring, | situation monitoring, | situation monitoring, |  | decision making, force
decision making, | decision making, | decision making, |  | direction, force
force direc-tion, force | force direc-tion, force | force direc-tion, force |  | management, and
manage-ment, and | manage-ment, and | manage-ment, and |  | planning
planning | planning | planning
Access and Control
Provide users ability | Provide users ability | Provide users ability | Verified required | Provide users ability to
to plan, control, & | to plan, control, & | to plan, control, & | capability as part of | plan, control, &
reconfigure their | reconfigure their | reconfigure their | system requirement | reconfigure their
apportioned | apportioned | apportioned | sell-off prior to | apportioned resources;
resources; critical | resources; critical | resources; critical | AEHF-2 launch. | critical functions such as
functions such as | functions such as | functions such as | Demonstrated LDR | situation monitoring,
situation monitoring, | situation monitoring, | situation monitoring, | operationally ready | decision making, force
decision making, | decision making, | decision making, | capability in AEHF-1 | direction, force
force direct-ion, force | force direc-tion, force | force direc-tion, force | on-orbit test | management, & planning
manage-ment, & | manage-ment, & | manage-ment, & |  | shall not be disrupted by
planning shall not be | planning shall not be | planning shall not be |  | communications
disrupted by | disrupted by | disrupted by |  | configuration changes to
communicat-ions | communicat-ions | communicat-ions |  | noncritical functions.
configuration | configuration | configuration
changes to | changes to | changes to

## Table 16
noncritical functions | noncritical functions | noncritical functions
Interoperability
AEHF Interopera-bility
Support joint interop- | Support joint interop- | Support joint interop- | Verified required | Support joint
erable war-fighter | erable war-fighter | erable war-fighter | capability as part of | interoperable warfighter
communicat-ions | communicat-ions | communicat-ions | system requirement | communications among
among all military | among all military | among all military | sell-off prior to | all military branches EHF
branches EHF | branches EHF | branches EHF | AEHF-2 launch. | terminals
terminals | terminals | terminals | Demonstrated
operationally ready
capability in AEHF-1
on-orbit test.
Milstar Backward Compatible
Operate with the | Operate with the | Operate with the | Verified required | Operate with the Milstar
Milstar system, at all | Milstar system, at all | Milstar system, at all | capability as part of | system, at all LDR and
LDR and MDR | LDR and MDR | LDR and MDR | system requirement | MDR terminal supported
terminal supported | terminal supported | terminal supported | sell-off prior to | data rates, throughout
data rates, | data rates, | data rates, | AEHF-1 launch. | the Milstar transition to
throughout the Milstar | throughout the Milstar | throughout the Milstar | Demonstrated | the AEHF system
transition to the AEHF | transition to the AEHF | transition to the AEHF | operationally ready
system | system | system | capability in AEHF-1
on-orbit test.
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
ORD dated October 1, 2000
Change Explanations
None
Notes
Performance Characteristics are the same on the AEHF 1-4 and 5-6 subprograms.
The program completed Multi-service Operational Test and Evaluation in January 2015.

## Table 17
Acronyms and Abbreviations
AEHF - Advanced Extremely High Frequency
AFOTEC - Air Force Operational Test and Evaluation Center CMTW - Combined Major Theater Warfare
EHF - Extremely High Frequency Gbps - Giga bytes per second LDR - Low Data Rate
Mbps - Mega bytes per second MCS - Mission Control Segment MDR - Medium Data Rate
Milstar - Military Strategic and Tactical Relay NCGS - Nuclear Criteria Group Secretariat OUE - Operational Utility Evaluation

## Table 18
AEHF SV 5-6
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Capacity
1.2 Gbps CMTW, 600 | 1.2 Gbps CMTW, 600 | Support at least 500 | 1.0 Gbps CMTW | 1.2 Gbps CMTW, 600
Mbps Strategic | Mbps Strategic | Mbps for CMTW | Scenario, 600 Mbps | Mbps Strategic
|  | Scenario and at least | Strategic Scenario -
|  | 350 Mbps for | verified required
|  | Strategic Scenario | capability as part of
system requirement
sell-off prior to
AEHF-1 launch
Nuclear Protection
Provide assured | Provide assured | Provide assured | Verified required | Provide assured
communicat-ions to | communicat-ions to | communicat-ions to | capability as part of | communications to
survivable nuclear | survivable nuclear | survivable nuclear | system requirement | survivable nuclear forces
forces exposed to the | forces exposed to the | forces exposed to the | sell-off prior to | exposed to the
environment | environment | environment | AEHF-2 launch. | environment specified in
specified in NCGS-89 | specified in NCGS-89 | specified in NCGS-89 |  | NCGS-89-06, and for
-06, and for those | -06, and for those | -06, and for those |  | those critical networks
critical networks that | critical networks that | critical networks that |  | that support the following
support the following | support the following | support the following |  | critical functions:
critical functions: | critical functions: | critical functions: |  | situation monitoring,
situation monitoring, | situation monitoring, | situation monitoring, |  | decision making, force
decision making, | decision making, | decision making, |  | direction, force
force direc-tion, force | force direc-tion, force | force direc-tion, force |  | management, and
manage-ment, and | manage-ment, and | manage-ment, and |  | planning.
planning | planning | planning
Access and Control
Provide users ability | Provide users ability | Provide users ability | Verified required | Provide users ability to
to plan, control, & | to plan, control, & | to plan, control, & | capability as part of | plan, control, &
reconfigure their | reconfigure their | reconfigure their | system requirement | reconfigure their
apportioned | apportioned | apportioned | sell-off prior to | apportioned resources;
resources; critical | resources; critical | resources; critical | AEHF-2 launch. | critical functions such as
functions such as | functions such as | functions such as | Demonstrated LDR | situation monitoring,
situation monitoring, | situation monitoring, | situation monitoring, | operationally ready | decision making, force
decision making, | decision making, | decision making, | capability in AEHF-1 | direction, force
force direct-ion, force | force direct-ion, force | force direct-ion, force | on-orbit test | management, & planning
manage-ment, & | manage-ment, & | manage-ment, & |  | shall not be disrupted by
planning shall not be | planning shall not be | planning shall not be |  | communications
disrupted by | disrupted by | disrupted by |  | configuration changes to
communicat-ions | communicat-ions | communicat-ions |  | noncritical functions.
configuration | configuration | configuration
changes to | changes to | changes to
noncritical functions | noncritical functions | noncritical functions
AEHF Interoperability

## Table 19
Support joint interop- erable war-fighter communicat-ions among all military branches EHF terminals | Support joint interop- erable war-fighter communicat-ions among all military branches EHF terminals | Support joint interop- erable war-fighter communicat-ions among all military branches EHF terminals | Verified required capability as part of system requirement sell-off prior to AEHF-2 launch. Demonstrated operationally ready capability in AEHF-1 on-orbit test | Support joint interoperable war-fighter communications among all military branches EHF terminals
Milstar Backward Compatible
Operate with the | Operate with the | Operate with the | Verified required | Operate with the Milstar
Milstar system, at all | Milstar system, at all | Milstar system, at all | capability as part of | system, at all LDR and
LDR and MDR | LDR and MDR | LDR and MDR | system requirement | MDR terminal supported
terminal supported | terminal supported | terminal supported | sell-off prior to | data rates, throughout
data rates, | data rates, | data rates, | AEHF-1 launch. | the Milstar transition to
throughout the Milstar | throughout the Milstar | throughout the Milstar | Demonstrated | the AEHF system
transition to the AEHF | transition to the AEHF | transition to the AEHF | operationally ready
system | system | system | capability in AEHF-1
on-orbit test
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Operational Requirements Document (ORD), dated October 1, 2000
Change Explanations
None
Notes
Performance Characteristics are the same on the AEHF 1-4 and 5-6 subprograms.
The program completed Multi-service Operational Test and Evaluation in January 2015. A final report of AFOTEC's assessment of Dedicated Operational Test will be available 90 days after the conclusion of testing.
Acronyms and Abbreviations
AFOTEC - Air Force Operational Test and Evaluation Center CMTW - Combined Major Theater Warfare
EHF - Extremely High Frequency Gbps - Giga bytes per second LDR - Low Data Rate
Mbps - Mega bytes per second MCS - Mission Control Segment MDR - Medium Data Rate
Milstar - Military Strategic and Tactical Relay NCGS - Nuclear Criteria Group Secretariat OUE - Operational Utility Evaluation

## Table 20
Track to Budget
AEHF SV 1-4
General Notes
RDT&E is associated with AEHF Space Vehicles (SV) 1 and 2 and procurement is associated with AEHF SV 3 and 4.
In December 2014, the Office of Management and Budget directed the DoD to establish a new space procurement appropriation as a five-year availability account. Beginning in FY 2016, Air Force major procurement funding formerly under appropriation 3020F (Missile Procurement, Air Force) BA 05 will now be under 3021F (Space Procurement, Air Force) BA 01.
RDT&E
Appn |  | BA | PE
Air Force 3600 04 0603430F
Project | Name
644050 AEHF Military Satellite
Communications (MILSATCOM) (Space)
Air Force 3600 05 0605431F
(Sunk)
Project | Name
657103 AEHF MILSATCOM (Space)
Notes: FY 2013 only
657104 Evolved AEHF MILSATCOM
(EAM)
Notes: FY 2012, FY 2014 - 2019 only
(Shared)
Procurement
Appn |  | BA | PE
Air Force 3020 05 0303604F
Line Item | Name
ADV555 Advanced EHF (Sunk)
Air Force 3021 01 0303604F
Line Item | Name
ADV555 Advanced EHF
Notes
Due to the creation of a new appropriation for Space Procurement (3021), Satellite Vehicle quantities are accounted for under 3020 annual funding section.
AEHF SV 5-6
General Notes

## Table 21
In December 2014, the Office of Management and Budget directed the DoD to establish a new space procurement appropriation as a five-year availability account. Beginning in FY 2016, Air Force major procurement funding formerly under appropriation 3020F (Missile Procurement, Air Force) BA 05 will now be under 3021F (Space Procurement, Air Force) BA 01.
RDT&E
Appn |  | BA | PE
Air Force | 3600 04 |  | 0603430F
| Project |  | Name
| 644050 |  | AEHF MILSATCOM (Space) |  | (Sunk)
| Notes: |  | FY 2011 only
| 64A030 |  | Evolved AEHF MILSATCOM (EAM) |  | (Shared) (Sunk)
| Notes: |  | FY 2013 only
Air Force | 3600 05 |  | 0605431F
| Project |  | Name
| 657104 |  | Evolved AEHF MILSATCOM (EAM) |  | (Shared) (Sunk)
| Notes: |  | FY 2014 - 2015 only
Notes
Projects 64A030 and 657104 also fund the Military Satellite Communications (MILSATCOM) Space Modernization Initiative. AEHF RDT&E funding is for the AEHF SV 6 KI-54D cryptographic device. Project 644050 is FY 2011 only. Project 64A030 is FY 2013 only. Project 657104 is for FY 2014 - 2015 only.
Procurement
Air Force | 3020 05 |  | 0303604F
| Line Item |  |  | Name
| ADV555 |  | Advanced EHF |  |  | (Sunk)
Air Force | 3021 01 |  | 0303604F
| Line Item |  |  | Name
| ADV555 |  | Advanced EHF
Notes
Appn |  | BA | PE
Due to the creation of a new appropriation for Space Procurement (3021), satellite vehicle (SV) quantities are accounted for under 3020 annual funding section.

## Table 22
Cost and Funding
Cost Summary - Total Program
Total Acquisition Cost - Total Program
Appropriation | BY 2002 $M |  |  |  | BY 2002 $M |  | TY $M
| SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E | 5282.8 |  | 6489.3 | -- |  | 6880.7 |  | 5542.2 |  | 7117.8 |  | 7631
Procurement | 3233 |  | 5311.1 | -- |  | 4614.2 |  | 4031.7 |  | 6565.5 |  | 5709.7
Flyaway | -- |  | -- | -- |  | 4614.2 |  | -- |  | -- |  | 5709.7
Recurring | -- |  | -- | -- |  | 4614.2 |  | -- |  | -- |  | 5709.7
Non Recurring | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Other Support | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Initial Spares | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
MILCON | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Total | 8515.8 |  | 11800.4 | N/A |  | 11494.9 |  | 9573.9 |  | 13683.3 |  | 13340.7

## Table 23
Cost and Funding
Cost Summary - AEHF SV 1-4
Total Acquisition Cost - AEHF SV 1-4
Appropriation | BY 2002 $M | [6 empty] | BY 2002 $M |  | TY $M
| SAR Baseline Production Estimate |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 5223.7 |  |  | 6430.2 | 7073.2 |  |  | 6830.3 |  | 5468.4 |  |  | 7044 |  | 7567.8
Procurement |  | 577 |  |  | 2655.1 | 2920.6 |  |  | 2567.5 |  | 617.3 |  |  | 3151.1 |  | 3054.4
Flyaway |  | -- |  |  | -- | -- |  |  | 2567.5 |  | -- |  |  | -- |  | 3054.4
Recurring |  | -- |  |  | -- | -- |  |  | 2567.5 |  | -- |  |  | -- |  | 3054.4
Non Recurring |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Other Support |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Initial Spares |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
MILCON |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 5800.7 |  |  | 9085.3 | N/A |  |  | 9397.8 |  | 6085.7 |  |  | 10195.1 |  | 10622.2
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The ICE) that supports the AEHF SV 1-4, like all life-cycle cost estimates previously performed by CAPE, is built upon a product-oriented work breakdown structure, which is based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and Government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for MDAPs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.
Total Quantity - AEHF SV 1-4
Quantity |  |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  |  | 2 |  |  |  | 2 |  |  |  |  | 2
Procurement |  |  | 1 |  |  |  | 2 |  |  |  |  | 2
Total |  |  | 3 |  |  |  | 4 |  |  |  |  | 4

## Table 24
Cost Summary - AEHF SV 5-6
Total Acquisition Cost - AEHF SV 5-6
Appropriation | BY 2002 $M | [6 empty] | BY 2002 $M |  | TY $M
| SAR Baseline Production Estimate |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 59.1 |  |  | 59.1 | 65 |  |  | 50.4 |  | 73.8 |  |  | 73.8 |  | 63.2
Procurement |  | 2656 |  |  | 2656 | 2921.6 |  |  | 2046.7 |  | 3414.4 |  |  | 3414.4 |  | 2655.3
Flyaway |  | -- |  |  | -- | -- |  |  | 2046.7 |  | -- |  |  | -- |  | 2655.3
Recurring |  | -- |  |  | -- | -- |  |  | 2046.7 |  | -- |  |  | -- |  | 2655.3
Non Recurring |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Other Support |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Initial Spares |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
MILCON |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 2715.1 |  |  | 2715.1 | N/A |  |  | 2097.1 |  | 3488.2 |  |  | 3488.2 |  | 2718.5
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The Independent Cost Estimate (ICE) to support the AEHF SV 5-6 decision, like all life-cycle cost estimates previously performed by Cost Assessment and Program Evaluation (CAPE), is built upon a product-oriented work breakdown structure, which is based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and Government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for Major Defense Acquisition Programs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.
Cost Notes
The AEHF SV 5-6 current estimate reflects the ceiling price on SV 5/6 Fixed Price Incentive, Firm (FPIF) contract, including potential engineering change orders.
Total Quantity - AEHF SV 5-6
Quantity |  |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  |  | 2 |  |  |  | 2 |  |  |  |  | 2
Total |  |  | 2 |  |  |  | 2 |  |  |  |  | 2

## Table 25
Cost and Funding
Funding Summary - Total Program
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | To Complete | Total
RDT&E | 7433.9 | 77.7 | 62.9 | 42.1 | 14.4 | 0 | 0 | 0 | 7631
Procurement | 4587.6 | 327.4 | 645.6 | 56.9 | 29.3 | 31.2 | 31.7 | 0 | 5709.7
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2017 Total | 12021.5 | 405.1 | 708.5 | 99 | 43.7 | 31.2 | 31.7 | 0 | 13340.7
PB 2016 Total | 12024 | 411 | 688.5 | 70.3 | 29.5 | 31.4 | 16 | 0 | 13270.7
Delta | -2.5 | -5.9 | 20 | 28.7 | 14.2 | -0.2 | 15.7 | 0 | 70

## Table 26
Cost and Funding
Funding Summary - AEHF SV 1-4
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 7370.7 | 77.7 |  | 62.9 |  | 42.1 | 14.4 |  | 0 |  | 0 |  | 0 |  | 7567.8
Procurement | 2926.7 | 106.1 |  | 21.6 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 3054.4
MILCON | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 10297.4 | 183.8 |  | 84.5 |  | 42.1 | 14.4 |  | 0 |  | 0 |  | 0 |  | 10622.2
PB 2016 Total | 10307.7 | 170.8 |  | 58.5 |  | 13 | 0 |  | 0 |  | 0 |  | 0 |  | 10550
Delta | -10.3 | 13 |  | 26 |  | 29.1 | 14.4 |  | 0 |  | 0 |  | 0 |  | 72.2
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 2 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 2
Production | 0 |  | 2 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 2
PB 2017 Total | 2 |  | 2 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 4
PB 2016 Total | 2 |  | 2 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 4
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0

## Table 27
Funding Summary - AEHF SV 5-6
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 63.2 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 63.2
Procurement | 1660.9 | 221.3 |  | 624 |  | 56.9 | 29.3 |  | 31.2 |  | 31.7 |  | 0 |  | 2655.3
MILCON | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 1724.1 | 221.3 |  | 624 |  | 56.9 | 29.3 |  | 31.2 |  | 31.7 |  | 0 |  | 2718.5
PB 2016 Total | 1716.3 | 240.2 |  | 630 |  | 57.3 | 29.5 |  | 31.4 |  | 16 |  | 0 |  | 2720.7
Delta | 7.8 | -18.9 |  | -6 |  | -0.4 | -0.2 |  | -0.2 |  | 15.7 |  | 0 |  | -2.2
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0
Production | 0 |  | 2 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 2
PB 2017 Total | 0 |  | 2 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 2
PB 2016 Total | 0 |  | 2 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 2
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0

## Table 28
Cost and Funding
Annual Funding By Appropriation - AEHF SV 1-4
Annual Funding - AEHF SV 1-4 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.1
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.3
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.2
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.6
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 89.8
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 229.8
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 494.8
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 832.6
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 872.7
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 652.2
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 647.7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 599.3
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 659.1
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 440.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 456.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 364.8
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 288.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 137
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 205.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 225.1
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 77.7
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.9
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42.1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.4
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 7567.8

## Table 29
Annual Funding - AEHF SV 1-4 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2002 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.9
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.7
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 56.4
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 91.3
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 230.4
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 491.4
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 816.2
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 834.3
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 607.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 585.9
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 528.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 569.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 375.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 384.1
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 301.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 234
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 109.5
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 161.9
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 175.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.7
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.5
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.2
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.5
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 6830.3

## Table 30
The RDT&E APPN funding profile identified in this SAR includes $270.5M in International Partners (IP) funding, $175.2M in Capability Insertion Program (CIP) funding, and does not include $119M (FY 2003 - FY 2009) for Production and Qualification (P&Q) of Radiation Hardened Components.
The yearly breakout of the funding is as follows:
IP Funds (TY $M)
FY 2002 | 35.2
FY 2003 | 44
FY 2004 | 91
FY 2005 | 67
FY 2006 | 28.5
FY 2007 | 3
FY 2008 | 1.8
Total 270.5
The yearly breakout of the P&Q of Radiation Hardened Components funding is as follows:
P&Q (TY $M)
FY 2003 19.0
FY 2004 19.0
FY 2005 21.0
FY 2006 20.0
FY 2007 21.0
FY 2009 19.0
Total 119.0
The yearly breakout of the CIP funding from the Evolved AEHF Military Satellite Communications Budget Program Activity Code 657104, is as follows:
CIP (TY $M)
FY 2012 4.7
FY 2014 14.3
FY 2015 43.6
FY 2016 24.2
FY 2017 31.9
FY2018 42.1
FY2019 14.4
Total 175.2

## Table 31
Annual Funding - AEHF SV 1-4 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | 78.2 |  | -- |  | -- |  | 78.2 |  | -- |  | 78.2
2006 |  | 1 | 521.9 |  | -- |  | -- |  | 521.9 |  | -- |  | 521.9
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | 141.4 |  | -- |  | -- |  | 141.4 |  | -- |  | 141.4
2009 |  | -- | 181.2 |  | -- |  | -- |  | 181.2 |  | -- |  | 181.2
2010 |  | 1 | 1734.5 |  | -- |  | -- |  | 1734.5 |  | -- |  | 1734.5
2011 |  | -- | 29.7 |  | -- |  | -- |  | 29.7 |  | -- |  | 29.7
2012 |  | -- | 45.8 |  | -- |  | -- |  | 45.8 |  | -- |  | 45.8
2013 |  | -- | 68.7 |  | -- |  | -- |  | 68.7 |  | -- |  | 68.7
2014 |  | -- | 60 |  | -- |  | -- |  | 60 |  | -- |  | 60
2015 |  | -- | 65.3 |  | -- |  | -- |  | 65.3 |  | -- |  | 65.3
Subtotal |  | 2 | 2926.7 |  | -- |  | -- |  | 2926.7 |  | -- |  | 2926.7

## Table 32
Annual Funding - AEHF SV 1-4 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | BY 2002 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | 72 |  | -- |  | -- |  | 72 |  | -- |  | 72
2006 |  | 1 | 467.5 |  | -- |  | -- |  | 467.5 |  | -- |  | 467.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | 121.4 |  | -- |  | -- |  | 121.4 |  | -- |  | 121.4
2009 |  | -- | 153.3 |  | -- |  | -- |  | 153.3 |  | -- |  | 153.3
2010 |  | 1 | 1446 |  | -- |  | -- |  | 1446 |  | -- |  | 1446
2011 |  | -- | 24.3 |  | -- |  | -- |  | 24.3 |  | -- |  | 24.3
2012 |  | -- | 36.8 |  | -- |  | -- |  | 36.8 |  | -- |  | 36.8
2013 |  | -- | 54 |  | -- |  | -- |  | 54 |  | -- |  | 54
2014 |  | -- | 46.5 |  | -- |  | -- |  | 46.5 |  | -- |  | 46.5
2015 |  | -- | 50 |  | -- |  | -- |  | 50 |  | -- |  | 50
Subtotal |  | 2 | 2471.8 |  | -- |  | -- |  | 2471.8 |  | -- |  | 2471.8

## Table 33
Cost Quantity Information - AEHF SV 1-4 3020 ¦ Procurement ¦ Missile Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2002 $M
2005 | -- | --
2006 | 1 | 858
2007 | -- | --
2008 | -- | --
2009 | -- | --
2010 | 1 | 1613.8
2011 | -- | --
2012 | -- | --
2013 | -- | --
2014 | -- | --
2015 | -- | --
Subtotal | 2 | 2471.8

## Table 34
Annual Funding - AEHF SV 1-4 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | 106.1 |  | -- |  | -- |  | 106.1 |  | -- |  | 106.1
2017 |  | -- | 21.6 |  | -- |  | -- |  | 21.6 |  | -- |  | 21.6
Subtotal |  | -- | 127.7 |  | -- |  | -- |  | 127.7 |  | -- |  | 127.7

## Table 35
Annual Funding - AEHF SV 1-4 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | BY 2002 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | 79.8 |  | -- |  | -- |  | 79.8 |  | -- |  | 79.8
2017 |  | -- | 15.9 |  | -- |  | -- |  | 15.9 |  | -- |  | 15.9
Subtotal |  | -- | 95.7 |  | -- |  | -- |  | 95.7 |  | -- |  | 95.7

## Table 36
Cost Quantity Information - AEHF SV 1-4 3021 ¦ Procurement ¦ Space Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2002 $M
2006 | -- | 79.2
2007 | -- | --
2008 | -- | --
2009 | -- | --
2010 | -- | 16.5
2011 | -- | --
2012 | -- | --
2013 | -- | --
2014 | -- | --
2015 | -- | --
2016 | -- | --
2017 | -- | --
Subtotal | -- | 95.7

## Table 37
Annual Funding By Appropriation - AEHF SV 5-6
Annual Funding - AEHF SV 5-6 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.8
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 63.2

## Table 38
Annual Funding - AEHF SV 5-6 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2002 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.4
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.6
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 50.4

## Table 39
Annual Funding - AEHF SV 5-6 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2011 |  | -- | 227.2 |  | -- |  | -- |  | 227.2 |  | -- |  | 227.2
2012 |  | 2 | 524.1 |  | -- |  | -- |  | 524.1 |  | -- |  | 524.1
2013 |  | -- | 408 |  | -- |  | -- |  | 408 |  | -- |  | 408
2014 |  | -- | 268.4 |  | -- |  | -- |  | 268.4 |  | -- |  | 268.4
2015 |  | -- | 233.2 |  | -- |  | -- |  | 233.2 |  | -- |  | 233.2
Subtotal |  | 2 | 1660.9 |  | -- |  | -- |  | 1660.9 |  | -- |  | 1660.9

## Table 40
Annual Funding - AEHF SV 5-6 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | BY 2002 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2011 |  | -- | 185.8 |  | -- |  | -- |  | 185.8 |  | -- |  | 185.8
2012 |  | 2 | 421.2 |  | -- |  | -- |  | 421.2 |  | -- |  | 421.2
2013 |  | -- | 320.6 |  | -- |  | -- |  | 320.6 |  | -- |  | 320.6
2014 |  | -- | 207.9 |  | -- |  | -- |  | 207.9 |  | -- |  | 207.9
2015 |  | -- | 178.6 |  | -- |  | -- |  | 178.6 |  | -- |  | 178.6
Subtotal |  | 2 | 1314.1 |  | -- |  | -- |  | 1314.1 |  | -- |  | 1314.1

## Table 41
Cost Quantity Information - AEHF SV 5-6 3020 ¦ Procurement ¦ Missile Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2002 $M
2011 | -- | --
2012 | 2 | 1314.1
2013 | -- | --
2014 | -- | --
2015 | -- | --
Subtotal | 2 | 1314.1

## Table 42
Annual Funding - AEHF SV 5-6 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | 221.3 |  | -- |  | -- |  | 221.3 |  | -- |  | 221.3
2017 |  | -- | 624 |  | -- |  | -- |  | 624 |  | -- |  | 624
2018 |  | -- | 56.9 |  | -- |  | -- |  | 56.9 |  | -- |  | 56.9
2019 |  | -- | 29.3 |  | -- |  | -- |  | 29.3 |  | -- |  | 29.3
2020 |  | -- | 31.2 |  | -- |  | -- |  | 31.2 |  | -- |  | 31.2
2021 |  | -- | 31.7 |  | -- |  | -- |  | 31.7 |  | -- |  | 31.7
Subtotal |  | -- | 994.4 |  | -- |  | -- |  | 994.4 |  | -- |  | 994.4

## Table 43
Annual Funding - AEHF SV 5-6 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | BY 2002 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | 166.5 |  | -- |  | -- |  | 166.5 |  | -- |  | 166.5
2017 |  | -- | 460.8 |  | -- |  | -- |  | 460.8 |  | -- |  | 460.8
2018 |  | -- | 41.2 |  | -- |  | -- |  | 41.2 |  | -- |  | 41.2
2019 |  | -- | 20.8 |  | -- |  | -- |  | 20.8 |  | -- |  | 20.8
2020 |  | -- | 21.7 |  | -- |  | -- |  | 21.7 |  | -- |  | 21.7
2021 |  | -- | 21.6 |  | -- |  | -- |  | 21.6 |  | -- |  | 21.6
Subtotal |  | -- | 732.6 |  | -- |  | -- |  | 732.6 |  | -- |  | 732.6

## Table 44
Cost Quantity Information - AEHF SV 5-6 3021 ¦ Procurement ¦ Space Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2002 $M
2012 | -- | 732.6
2013 | -- | --
2014 | -- | --
2015 | -- | --
2016 | -- | --
2017 | -- | --
2018 | -- | --
2019 | -- | --
2020 | -- | --
2021 | -- | --
Subtotal | -- | 732.6

## Table 45
Low Rate Initial Production
There is no LRIP for this program.

## Table 46
Foreign Military Sales
AEHF SV 1-4
Country | Date of Sale | Quantity | Total Cost $M | Description
United Kingdom 9/9/2003 84.0
Netherlands 11/8/2002 39.8
Canada 11/16/1999 146.2
Notes
The AEHF program has no FMS; all sales in the table are International Partner (IP) cooperation. The IPs access the antennas and a portion of the capacity on the AEHF satellites. The total IP O&S contribution of $114.3M is not included in the table sales above. O&S costs are commensurate with system resource usage respectively. The specific break out by IP is as follows:
Canada: $68.2M
The Netherlands: $14.8M United Kingdom: $31.3M
AEHF SV 5-6
None
Nuclear Costs
AEHF SV 1-4
None
AEHF SV 5-6
None

## Table 47
Unit Cost
AEHF SV 1-4
Unit Cost Report
Item |  | BY 2002 $M | BY 2002 $M |  | % Change
|  | Current UCR Baseline (Mar 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 9085.3 |  |  | 9397.8
Quantity | 4 |  |  | 4
Unit Cost | 2271.325 |  |  | 2349.45 |  | 3.44
Average Procurement Unit Cost
Cost | 2655.1 |  |  | 2567.5
Quantity | 2 |  |  | 2
Unit Cost | 1327.55 |  |  | 1283.75 |  | -3.3
Item |  | BY 2002 $M | BY 2002 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Mar 2014 APB)
Program Acquisition Unit Cost
Cost | 9085.3 |  |  | 9397.8
Quantity | 4 |  |  | 4
Unit Cost | 2271.325 |  |  | 2349.45 |  | 3.44
Average Procurement Unit Cost
Cost | 2655.1 |  |  | 2567.5
Quantity | 2 |  |  | 2
Unit Cost | 1327.55 |  |  | 1283.75 |  | -3.3

## Table 48
AEHF SV 1-4
Unit Cost History
Item | [5 empty] | Date |  |  |  | BY 2002 $M | [6 empty] | TY $M
[10 empty] | PAUC |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Oct 2001 |  |  |  |  | 1055.84 |  |  |  | 401.667 |  |  |  | 1129.06 |  |  |  | 460.133
APB as of January 2006 |  |  |  |  | Mar 2005 |  |  |  |  | 1933.567 |  |  |  | 577 |  |  |  | 2028.567 |  |  |  | 617.3
Revised Original APB |  |  |  |  | Mar 2014 |  |  |  |  | 2271.325 |  |  |  | 1327.55 |  |  |  | 2548.775 |  |  |  | 1575.55
Prior APB |  |  |  |  | Oct 2012 |  |  |  |  | 2271.325 |  |  |  | 1327.55 |  |  |  | 2548.775 |  |  |  | 1575.55
Current APB |  |  |  |  | Mar 2014 |  |  |  |  | 2271.325 |  |  |  | 1327.55 |  |  |  | 2548.775 |  |  |  | 1575.55
Prior Annual SAR |  |  |  |  | Dec 2014 |  |  |  |  | 2334.35 |  |  |  | 1280.8 |  |  |  | 2637.5 |  |  |  | 1524.1
Current Estimate |  |  |  |  | Dec 2015 |  |  |  |  | 2349.45 |  |  |  | 1283.75 |  |  |  | 2655.55 |  |  |  | 1527.2
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [18 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  |  | Sch |  | Eng |  | Est |  | Oth |  |  | Spt |  | Total
1129.060 -35.225 -291.584 262.425 0.000 342.633 0.000 -0.275 277.974 2028.567
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [16 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  |  | Sch | Eng |  | Est | Oth |  |  | Spt |  | Total
2028.567 39.775 -270.642 316.800 69.325 471.725 0.000 0.000 626.983 2655.550

## Table 49
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [15 empty] | APUC Production Estimate
| Econ | Qty |  |  | Sch |  | Eng |  | Est |  | Oth |  | Spt |  | Total
460.133 -3.250 912.967 88.600 0.000 998.650 0.000 -0.550 1996.417 617.300
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [15 empty] | APUC Current Estimate
| Econ |  | Qty |  |  | Sch |  | Eng |  | Est |  | Oth |  | Spt |  | Total
617.300 23.700 164.350 -30.900 7.000 745.750 0.000 0.000 909.900 1527.200
SAR Baseline History
Item |  |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate | [5 empty] | SAR Production Estimate |  |  |  | Current Estimate
Milestone I |  |  |  | Apr 1999 |  |  |  | Apr 1999 | [5 empty] | Apr 1999 |  |  |  | Apr 1999
Milestone B |  |  |  | Feb 2001 |  |  |  | Jun 2001 | [5 empty] | Jun 2001 |  |  |  | Sep 2001
Milestone C |  |  |  | Feb 2001 |  |  |  | Jun 2004 | [5 empty] | Jun 2004 |  |  |  | Jun 2004
IOC |  |  |  | Nov 2007 |  |  |  | Jul 2008 | [5 empty] | Jun 2010 |  |  |  | Jul 2015
Total Cost (TY $M) |  |  |  | 2690.6 |  |  |  | 5645.3 | [5 empty] | 6085.7 |  |  |  | 10622.2
Total Quantity |  |  |  | 2 |  |  |  | 5 | [5 empty] | 3 |  |  |  | 4
PAUC |  |  |  | 1345.3 |  |  |  | 1129.06 | [5 empty] | 2028.567 |  |  |  | 2655.55

## Table 50
Unit Cost Report
Item |  | BY 2002 $M | BY 2002 $M |  | % Change
|  | Current UCR Baseline (Oct 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2715.1 |  |  | 2097.1
Quantity | 2 |  |  | 2
Unit Cost | 1357.55 |  |  | 1048.55 |  | -22.76
Average Procurement Unit Cost
Cost | 2656 |  |  | 2046.7
Quantity | 2 |  |  | 2
Unit Cost | 1328 |  |  | 1023.35 |  | -22.94
Item |  | BY 2002 $M | BY 2002 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Oct 2012 APB)
Program Acquisition Unit Cost
Cost | 2715.1 |  |  | 2097.1
Quantity | 2 |  |  | 2
Unit Cost | 1357.55 |  |  | 1048.55 |  | -22.76
Average Procurement Unit Cost
Cost | 2656 |  |  | 2046.7
Quantity | 2 |  |  | 2
Unit Cost | 1328 |  |  | 1023.35 |  | -22.94

## Table 51
Unit Cost History
Item |  |  | Date |  | BY 2002 $M | [5 empty] | TY $M
[5 empty] | PAUC |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  | Mar 2014 |  |  | 1357.55 |  |  | 1328 |  |  |  | 1744.1 |  |  | 1707.2
APB as of January 2006 |  | N/A |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Revised Original APB |  | N/A |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Prior APB |  | N/A |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Current APB |  | Mar 2014 |  |  | 1357.55 |  |  | 1328 |  |  |  | 1744.1 |  |  | 1707.2
Prior Annual SAR |  | Dec 2014 |  |  | 1045.15 |  |  | 1020.05 |  |  |  | 1360.35 |  |  | 1328.75
Current Estimate |  | Dec 2015 |  |  | 1048.55 |  |  | 1023.35 |  |  |  | 1359.25 |  |  | 1327.65
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Production Estimate | Changes | [11 empty] | PAUC Current Estimate
| Econ | Qty | Sch | Eng | Est | Oth |  |  | Spt | Total
1744.100 27.450 0.000 0.000 0.000 -412.300 0.000 0.000 -384.850 1359.250

## Table 52
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Production Estimate | Changes | [10 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt |  | Total
1707.200 27.150 0.000 0.000 0.000 -406.700 0.000 0.000 -379.550 1327.650
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone C |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
IOC |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Total Cost (TY $M) |  |  | N/A |  |  | N/A |  |  |  | 3488.2 |  |  | 2718.5
Total Quantity |  |  | N/A |  |  | N/A |  |  |  | 2 |  |  | 2
PAUC |  |  | N/A |  |  | N/A |  |  |  | 1744.1 |  |  | 1359.25

## Table 53
Cost Variance
AEHF SV 1-4
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
5468.4 617.3 -- 6085.7
Economic |  | 118 |  | 49.4 |  | -- |  | 167.4
Quantity |  | -- |  | 946 |  | -- |  | 946
Schedule |  | 1329 |  | -61.8 |  | -- |  | 1267.2
Engineering |  | 202.6 |  | -- |  | -- |  | 202.6
Estimating |  | 383.8 |  | 1497.3 |  | -- |  | 1881.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 2033.4 |  | 2430.9 |  | -- |  | 4464.3
Current Changes Economic |  | -6.3 |  | -2 |  | -- |  | -8.3
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | 60.7 |  | 14 |  | -- |  | 74.7
Estimating |  | 11.6 |  | -5.8 |  | -- |  | 5.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 66 |  | 6.2 |  | -- |  | 72.2
Adjustments |  | -- |  | -- |  | -- |  | --
Total Changes |  | 2099.4 |  | 2437.1 |  | -- |  | 4536.5
CE - Cost Variance |  | 7567.8 |  | 3054.4 |  | -- |  | 10622.2
CE - Cost & Funding |  | 7567.8 |  | 3054.4 |  | -- |  | 10622.2

## Table 54
Summary BY 2002 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
5223.7 577.0 -- 5800.7
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 784.9 |  | -- |  | 784.9
Schedule |  | 1091.3 |  | -- |  | -- |  | 1091.3
Engineering |  | 164.8 |  | -- |  | -- |  | 164.8
Estimating |  | 296 |  | 1199.7 |  | -- |  | 1495.7
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 1552.1 |  | 1984.6 |  | -- |  | 3536.7
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | 45.2 |  | 10.4 |  | -- |  | 55.6
Estimating |  | 9.3 |  | -4.5 |  | -- |  | 4.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 54.5 |  | 5.9 |  | -- |  | 60.4
Adjustments |  | -- |  | -- |  | -- |  | --
Total Changes |  | 1606.6 |  | 1990.5 |  | -- |  | 3597.1
CE - Cost Variance |  | 6830.3 |  | 2567.5 |  | -- |  | 9397.8
CE - Cost & Funding |  | 6830.3 |  | 2567.5 |  | -- |  | 9397.8
Previous Estimate: December 2014

## Table 55
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -6.3
Adjustment for current and prior escalation. (Estimating) +5.2 +6.0
Revised estimate for Next-Generation Ground crypto key management system. (Estimating)
+7.5 +10.0
Revised estimate for Below Threshold Reprogramming. (Estimating) | 0.6 |  |  | 0.7
Revised estimate due to application of Congressional General Reduction. (Estimating) | -4 |  |  | -5.1
Additional funding for Increment 8 Capability Insertion Program. (Engineering) | 45.2 |  |  | 60.7
RDT&E Subtotal | 54.5 |  |  | 66
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -2.0
Adjustment for current and prior escalation. (Estimating) +1.4 +1.9
Revised estimate for Next-Generation Ground crypto key management system. (Estimating)
-5.9 -7.7
Additional funding for Increment 8 Capability Insertion Program. (Engineering) +10.4 +14.0
Procurement Subtotal +5.9 +6.2

## Table 56
Cost Variance
AEHF SV 5-6
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 73.8 | 3414.4 | -- | 3488.2
Previous Changes
Economic | 0.8 | 66.3 | -- | 67.1
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -11.4 | -823.2 | -- | -834.6
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -10.6 | -756.9 | -- | -767.5
Current Changes
Economic | -0.2 | -12 | -- | -12.2
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 0.2 | 9.8 | -- | 10
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -- | -2.2 | -- | -2.2
Total Changes | -10.6 | -759.1 | -- | -769.7
CE - Cost Variance | 63.2 | 2655.3 | -- | 2718.5
CE - Cost & Funding | 63.2 | 2655.3 | -- | 2718.5

## Table 57
Summary BY 2002 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 59.1 | 2656 | -- | 2715.1
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -8.9 | -615.9 | -- | -624.8
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -8.9 | -615.9 | -- | -624.8
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 0.2 | 6.6 | -- | 6.8
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | 0.2 | 6.6 | -- | 6.8
Total Changes | -8.7 | -609.3 | -- | -618
CE - Cost Variance | 50.4 | 2046.7 | -- | 2097.1
CE - Cost & Funding | 50.4 | 2046.7 | -- | 2097.1
Previous Estimate: December 2014

## Table 58
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.2
Adjustment for current and prior escalation. (Estimating) | 0.2 | 0.2
RDT&E Subtotal | 0.2 | 0
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -12.0
Adjustment for current and prior escalation. (Estimating) +5.0 +6.5
Funding realignments between subprograms to cover production activities (Missile Procurement, Air Force (MPAF)). (Estimating)
Funding realignments between subprograms to cover production activities (Space Procurement, Air Force (SPAF)). (Estimating)
+6.0 +7.8
-10.3 -13.7
Revised estimate for increase in funding for baseline extension (SPAF). (Estimating) +10.9 +16.0
Revised estimate due to application of Congressional General Reduction (SPAF). (Estimating)
Revised estimate due to application of Air Force-wide inflationary adjustments (SPAF). (Estimating)
-4.5 -6.0
-4.5 -6.3
Revised estimate due to application of new outyear inflation indices (SPAF). (Estimating) +4.0 +5.5
Procurement Subtotal +6.6 -2.2

## Table 59
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: AEHF 4 Production and Launch, 5/6 Long Lead, KI-54
Contractor: Lockheed Martin Corp.
Contractor Location: 1111 Lockheed Martin Way
Sunnyvale, CA 94089
Contract Number: F04701-02-C-0002/2
Contract Type: Cost Plus Incentive Fee (CPIF), Cost Plus Fixed Fee (CPFF)
Award Date: December 15, 2010
Definitization Date: December 15, 2010
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1396.5 N/A 1 1701.1 N/A 2 1673.0 1673.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract modifications for AEHF 4 Launch Operations, AEHF 5-6 Long Lead, KI-54D cryptographic devices, X37 integration and analysis, Protected Key Management Architecture, and studies.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/31/2016) +78.9 +17.2
Previous Cumulative Variances +49.7 +15.9
Net Change +29.2 +1.3
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to support sharing with other AEHF activities, lower negotiated material cost with vendors on some parts and credits for transfers of excess material to other programs. Integration & Test required less support than anticipated because software related issues were minimal. Also, there was a favorable net change in cost variance due to early payload delivery, subject matter expert reductions, and material/subcontracts transfers.
The favorable net change in the schedule variance is due to the following: Pre launch system test had early start associated with system test preparations. Lockheed Martin assembly integration and test is performing ahead of schedule on pre- acoustic and Fully Integrated System Test; ahead of schedule due to successful execution of accelerated schedule. The tasks that are ahead of schedule are the post-Thermal Vacuum Remove & Replace, acoustic preps/testing and post acoustic deployments.

## Table 60
Notes
This contract includes AEHF 4 Production, AEHF 4 Launch Operations, AEHF 5/6 Long Lead, KI-54D, X37 and studies.

## Table 61
Contract Identification
Appropriation: Procurement
Contract Name: AEHF 5-6 Production and Launch
Contractor: Lockheed Martin
Contractor Location: 1111 Lockheed Martin Way
Sunnyvale, CA 94089
Contract Number: FA8808-12-C-0010/1
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: May 12, 2012
Definitization Date: October 31, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1914.4 2001.6 2 1917.8 2001.6 2 1917.8 1914.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the addition of the AEHF 5/6 acoustic test (CLIN 4000) for $2.22M, the AEHF-5 Lithium-Ion (LiIon) battery test study (CLIN 0410) for $0.48M, and the addition of the AEHF-6 LiIon battery test study (CLIN 0410) for $0.38M.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/31/2016) +53.9 -31.8
Previous Cumulative Variances +44.6 -6.1
Net Change +9.3 -25.7
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to resource sharing with other AEHF activities, reduced support required for material handling, favorable labor rate delta, slower staff buildup of program management personnel, less Integrated Baseline Review support; cable and harness fabrication efficiencies due to lessons learned on AEHF-4, and elimination of Integration and Test deputy.
The unfavorable net change in the schedule variance is due to Deficiency Report (DR) resolutions and troubleshooting for Program Control and Coding units - Demodulator & Configurable Onboard Router delays due to late and damaged parts delaying all plug-ins for unit kit, Resource Control Computer delays for Non-Volatile Random Access Memory plug-in test failure requiring rework, and Gimble Control Unit delays for priorities given to High Efficiency Converters which delayed the Power Converter slice components; delays in Interface Downconverter Assembly Manufacturing & Support due to backlog at conductive bond and Tunable Super High Frequency Modulator Exciter Manufacturing and Support from higher priority given to other Radio Frequency units (Noise Amplifier Deconvertor, Frequency Generator Unit & Fixed Extremely High Frequency Converter) and Modem delays for Demodulator slice DR resolution and rework.

## Table 62
Deliveries and Expenditures
AEHF SV 1-4
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 2 | 2 | 2 | 100%
Production | 1 | 1 | 2 | 50%
Total Program Quantity Delivered | 3 | 3 | 4 | 75%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
10622.2
9500
89.44%
25
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
22
88%
10481.2
98.67%
The above data is current as of February 09, 2016.
AEHF SV 5-6
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 0 | 0 | 2 | 0%
Total Program Quantity Delivered | 0 | 0 | 2 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
2718.5
1451.2
53.38%
11
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
6
54.55%
1945.4
71.56%
The above data is current as of February 09, 2016.

## Table 63
Operating and Support Cost
AEHF SV 1-4
Cost Estimate Details
Date of Estimate: December 31, 2011
Source of Estimate: POE
Quantity to Sustain: 1
Unit of Measure: System
Service Life per Unit: 14.00 Years
Fiscal Years in Service: FY 2015 - FY 2030
The December 2011 O&S POE included AEHF 1-4 through FY 2030. The MILSATCOM Directorate is currently developing a new O&S cost model based on the award of the Combined Orbital Operation, Logistics Sustainment (COOLS) contract, it will be completed and coordinated in CY 2016. The AEHF system being sustained consists of a four satellite constellation and associated ground segment.
Sustainment Strategy
The O&S costs support a four satellite constellation from FY 2015 through FY 2030. The estimates assume that AEHF and Milstar will be operated in parallel by the 4th Space Operations Squadron at Schriever Air Force Base (AFB). Due to the proprietary nature of the AEHF Space Satellite (on-orbit) Segment, this segment is not considered core and the Depot Source of Repair is Contractor Logistics Support for the life of the satellites. Sustainment of the AEHF Space Satellite (on
-orbit) Segment transferred to the COOLS contract post-IOC. All other AEHF workloads were designated as core. Tobyhanna Army Depot is the candidate depot for hardware and Ogden Air Logistics Center (OO-ALC), Hill AFB UT for software. A Public Private Partnership is in place and will continue to ramp up the OO-ALC ground software capability over the life of the COOLS contract.
Antecedent Information
The antecedent system for AEHF is Milstar which consists of a five satellite constellation and associated ground segment. The cost estimate is based on validated requirements in the Air Force Space Command Logistics Support Requirements Brochures built for the FY 2004 President's Budget Request. The Milstar O&S costs cover all operational activities for both the space and ground segment for FY 2009 - FY 2018.
The antecedent Milstar program office estimate is from April 2003 finalized in Air Force Space Command's budget request to Headquaters Air Force.

## Table 64
Annual O&S Costs BY2002 $M
Cost Element |  |  | AEHF SV 1-4 Average Annual Cost Per System | [5 empty] | Milstar (Antecedent) Average Annual Cost Per System
Unit-Level Manpower |  |  | 19.42 | [5 empty] | 16.9
Unit Operations |  |  | 0.053 | [5 empty] | 13.2
Maintenance |  |  | 14.294 | [5 empty] | 3.9
Sustaining Support |  |  | 54.956 | [5 empty] | 39
Continuing System Improvements |  |  | 34.611 | [5 empty] | 0
Indirect Support |  |  | 3.22 | [5 empty] | 7.2
Other |  |  | 0 | [5 empty] | 0
Total |  |  | 126.554 | [5 empty] | 80.2
AEHF Average Annual Cost Per System numbers above reflect costs for planning usage and monitoring health of the AEHF constellation.
Item | Total O&S Cost $M
| AEHF SV 1-4 | [8 empty] | Milstar (Antecedent)
| Current Production APB Objective/Threshold | [5 empty] | Current Estimate
Base Year |  | 1143.6 |  |  | 1258 |  |  | 1143.6 |  |  | 801.5
Then Year |  | 1593.6 |  |  | N/A |  |  | 1593.6 |  |  | N/A
.
Equation to Translate Annual Cost to Total Cost
(AEHF SV1-4 Total O&S Cost + AEHF 5-6 Total O&S Cost)/16 years = Average Annual O&S cost ($1143.6M + $881.3M)/16 = $126.5M
The O&S estimate developed in FY 2011 covers the 14 year design life of the AEHF system (4 satellite constellation and associated ground segment) starting in FY 2017 and going through FY 2030. Sustainment of the system executed under the RDT&E Interim Contractor Support contract when the first AEHF satellite launched in FY 2010 and transitioned to O&S funding once IOC was declared on July 28, 2015. The 16 year divisor in the equation is based on the O&S start date in FY 2015 carrying through FY 2030.
O&S Cost Variance
Category |  |  |  | BY 2002 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
1143.6
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0

## Table 65
Energy Rate | 0
Technical Input | 0
Other | 0
Total Changes | 0
Current Estimate | 1143.6
Disposal Estimate Details
Date of Estimate: Source of Estimate:
Disposal/Demilitarization Total Cost (BY 2002 $M):
The disposal estimate is in development and will be included in the new O&S cost model planned for CY 2016.

## Table 66
AEHF SV 5-6
Cost Estimate Details
Date of Estimate: December 31, 2011
Source of Estimate: POE
Quantity to Sustain: 1
Unit of Measure: System
Service Life per Unit: 14.00 Years
Fiscal Years in Service: FY 2015 - FY 2030
The December 2011 O&S POE included AEHF 1-6 through FY 2030. The MILSATCOM Directorate is currently developing a new O&S cost model based on the award of the Combined Orbital Operation, Logistics Sustainment (COOLS) contract, it will be completed and coordinated in CY 2016. The AEHF system being sustained consists of a four satellite constellation and associated ground segment.
Sustainment Strategy
The O&S costs support a four satellite constellation from FY 2015 through FY 2030. The estimates assume that AEHF and Milstar will be operated in parallel by the 4th Space Operations Squadron at Schriever AFB. Due to the proprietary nature of the AEHF Space Satellite (on-orbit) Segment, this segment is not considered core and the Depot Source of Repair is Contractor Logistics Support (CLS) for the life of the satellites. Sustainment of the AEHF Space Satellite (on- orbit) Segment transferred to the COOLS contract post-IOC. All other AEHF workloads were designated as core.
Tobyhanna Army Depot (TYAD) is the candidate depot for hardware and OO-ALC Hill AFB UT for software. A Public Private Partnership is in place and will continue to ramp up the OO-ALC ground software capability over the life of the COOLS contract..
Antecedent Information
The antecedent system for AEHF is Milstar which consists of a five satellite constellation and associated ground segment. The cost estimate is based on validated requirements in the Air Force Space Command Logistics Support Requirements Brochures built for the FY 2004 President's Budget Request. The Milstar O&S costs cover all operational activities for both the space and ground segment for FY 2009 - FY 2018.
The antecedent Milstar program office estimate is from April 2003 finalized in Air Force Space Command's budget request to Headquaters Air Force.

## Table 67
Annual O&S Costs BY2002 $M
Cost Element |  |  | AEHF SV 5-6 Average Annual Cost Per System | [5 empty] | Milstar (Antecedent) Average Annual Cost Per System
Unit-Level Manpower |  |  | 19.42 | [5 empty] | 16.9
Unit Operations |  |  | 0.053 | [5 empty] | 13.2
Maintenance |  |  | 14.294 | [5 empty] | 3.9
Sustaining Support |  |  | 54.956 | [5 empty] | 39
Continuing System Improvements |  |  | 34.611 | [5 empty] | 0
Indirect Support |  |  | 3.22 | [5 empty] | 7.2
Other |  |  | 0 | [5 empty] | 0
Total |  |  | 126.554 | [5 empty] | 80.2
AEHF Average Annual Cost Per System numbers above reflect costs for planning usage and monitoring health of the AEHF constellation.
Item | Total O&S Cost $M
| AEHF SV 5-6 | [8 empty] | Milstar (Antecedent)
| Current Production APB Objective/Threshold | [5 empty] | Current Estimate
Base Year |  | 881.3 |  |  | 969.4 |  |  | 881.3 |  |  | 801.5
Then Year |  | 1453.8 |  |  | N/A |  |  | 1453.8 |  |  | N/A
.
Equation to Translate Annual Cost to Total Cost
(AEHF SV1-4 Total O&S Cost + AEHF 5-6 Total O&S Cost)/16 years = Average Annual O&S cost ($1143.6M + $881.3M)/16 = $126.5M
The O&S estimate developed in FY 2011 covers the 14 year design life of the AEHF system (4 satellite constellation and associated ground segment) starting in FY 2017 and going through FY 2030. Sustainment of the system executed under the RDT&E Interim Contractor Support contract when the first AEHF satellite launched in FY 2010 and transitioned to O&S funding once IOC was declared on July 28, 2015. The 16 year divisor in the equation is based on the O&S start date in FY 2015 carrying through FY 2030.
O&S Cost Variance
Category |  |  |  | BY 2002 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
881.3
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0

## Table 68
Cost Data Update | 0
Labor Rate | 0
Energy Rate | 0
Technical Input | 0
Other | 0
Total Changes | 0
Current Estimate | 881.3
Disposal Estimate Details
Date of Estimate: Source of Estimate:
Disposal/Demilitarization Total Cost (BY 2002 $M):
The disposal estimate is in development and will be included in the new O&S cost model planned for CY 2016.