## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-468
B61 Mod 12 Life Extension Program Tailkit Assembly (B61 Mod 12 LEP TKA)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 13
Cost and Funding 14
Low Rate Initial Production 20
Foreign Military Sales 21
Nuclear Costs 21
Unit Cost 22
Cost Variance 25
Contracts 28
Deliveries and Expenditures 29
Operating and Support Cost 30

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
B61 Mod 12 Life Extension Program Tailkit Assembly (B61 Mod 12 LEP TKA)
DoD Component
Air Force
Responsible Office
Mr. John Mistretta
207 West D Ave, Bldg 350 Eglin Air Force Base, FL 32542
john.mistretta@us.af.mil
Phone: | 850-883-0671
Fax: | 850-882-6637
DSN Phone: | 875-0671
DSN Fax: | 872-6637
Date Assigned: | January 1, 2012
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated December 14, 2012
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated December 14, 2012

## Table 6
Mission and Description
The B61 Mod 12 Life Extension Program (LEP) will consolidate Mods 3, 4, 7 and 10 into a single Mod (B61-12) while extending the system's service life. B61-12 is an air-delivered nuclear gravity weapon providing nuclear capability on existing legacy aircraft and dual capable aircraft. The single variant will operate in two modes, System 1 (analog/ballistic mode) and System 2 (digital/guided mode).
The B61 Mod 12 LEP Tailkit Assembly (TKA) (hereby referred to as B61-12 TKA) is the enabler for realizing System 2. This is an Air Force led ACAT ID Program. The DoD responsibility is executed by the Air Force Nuclear Weapons Center (AFNWC). In accordance with the Air Force Materiel Command mission assignment memorandum (dated February 11, 2011) and the National Nuclear Security Administration (NNSA)/AFNWC Memorandum of Understanding (dated June 28, 2012), AFNWC/NDB (Eglin) is responsible for the development, acquisition, and delivery of a guided TKA and AFNWC/NTW (Kirtland) is responsible for All Up Round technical integration, system qualification, Operational Safety, Suitability, and Effectiveness and fielding of the B61-12 variant.
The DOE/NNSA is responsible for the B61-12 Bomb Assembly and all aspects of the nuclear warhead, including design, manufacture, and portions of sustainment. Funding of these activities will be shared between the DoD and DOE.

## Table 7
Executive Summary
In November 2012, in conjunction with the Milestone B decision, certification was made pursuant to section 2366b of Title 10, United States Code. Based on program maturity, the B61-12 TKA was deemed ready to enter the EMD phase; however, the USD(AT&L) waived four of the 2366b provisions. In July 2014, the program satisfied two of the four waived provisions, (a)(1)(B) and (a)(1)(D) (now (a)(3)(B) and (a)(3)(D), respectively), on the basis that the program was fully funded in the FYDP associated with the FY 2015 PB. In November 2014, the program satisfied the requirement for provision, (a)(2) (now (a)(1)) following completion of the Preliminary Design Review (PDR) and post-PDR assessment (the program demonstrated a high likelihood of accomplishing its intended mission). Based on the maturity of the required technology, USD(AT&L) determined that a Technology Readiness Assessment for the B61-12 TKA is not needed; however, the Assistant Secretary of Defense for Research and Engineering will conduct an independent review and assessment to satisfy the certification requirement for the fourth waived provision, (a)(3)(D) (now (a)(2)). This review will be based upon the point of departure design, test data from a guided test flight, and the change point analysis between the point of departure design and guided test configuration. Initial data to support this assessment will be available in April 2016. The Department will continue to review the B61-12 TKA program at least annually until this last certification component is satisfied.
In May 2015, B61-12 TKA provided a program briefing to USD(AT&L) and members of the Nuclear Weapons Council. The program briefing highlighted the implementation plan for the radiation hardened inertial measurement unit (IMU 3.5), which will be integrated into the TKA and support DoD and Department of Energy (DOE) B61-12 testing.
During July - November 2015, the B61-12 TKA conducted three guided test flights to verify design performance leading to Critical Design Review (CDR). B61-12 CDR was conducted January 2016. Additionally B61-12 TKA provided deliverables in support of DOE Flight Test Development Unit tests occurring from July - October 2015.
In December 2015, the B61-12 TKA program office awarded a Cost Plus Incentive Fee contract to Boeing for EMD Phase 2.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
(Ch-1)
(Ch-2)
(Ch-3)
(Ch-3)
(Ch-3)
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | Nov 2012 | Nov 2012 | Nov 2012 | Nov 2012
Preliminary Design Review | Jan 2014 | Jan 2014 | Jul 2014 | Jul 2014
First TKA Developmental Test Flight | Nov 2015 | Nov 2015 | May 2016 | Jul 2015
Critical Design Review | Oct 2015 | Oct 2015 | Apr 2016 | Jan 2016
Milestone C | Apr 2018 | Apr 2018 | Apr 2019 | Oct 2018
First TKA Production Delivery | Jun 2019 | Jun 2019 | Jun 2020 | Dec 2019
Full Rate Production Decision | Sep 2019 | Sep 2019 | Sep 2020 | Mar 2020
Change Explanations
(Ch-1) The First TKA Developmental Test Flight event changed from November 2015 to July 2015 which is when the GTV 1 flight test was conducted.
(Ch-2) The CDR event changed from October 2015 to January 2016 which is when the CDR was conducted. The shift in the CDR date allowed for finalization of flight test data and requirements update.
(Ch-3) The Milestone C event changed from April 2018 to October 2018. Similarly The First TKA Production Delivery event changed from June 2019 to December 2019. The FRP Decision event shifted from September 2019 to March 2020. At Milestone B, the TKA program planned on utilizing some DOE AUR System Qualification tests to support the evaluation of the TKA reliability prior to Milestone C. Given schedule adjustments to both DOE and DoD efforts, leveraging AUR System Qualification flight test for the TKA may not be feasible. The TKA program is pursuing a plan for additional TKA flight test to ensure the TKA program can adequately address its reliability requirement prior to Milestone C. To accommodate a total of 35 TKA development flight tests, a shift in Milestone C to October 2018 is projected. Similarly, a 6 month Milestone C shift, equates to a First TKA Production Delivery and FRP Decision shift by 6 months.
Notes

## Table 10
Risks associated with parallel development activities being conducted by the DoD and the DOE drive threshold dates that are one year beyond objective dates for Milestone C, First TKA Production Delivery, and FRP Decision.
Delivery of the first production unit (First TKA Production Delivery) is used as a surrogate for IOC; DOE is responsible for production integration of the Bomb Assembly with the TKA and subsequent AUR deliveries to the field for IOC.
Acronyms and Abbreviations
AUR - All Up Round
CDR - Critical Design Review DOE - Department of Energy GTV - Guided Test Vehicle
PDR - Preliminary Design Review

## Table 11
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Aircraft Integration (KPP)
B61-12 TKA, when | B61-12 TKA, when | B61-12 TKA, when | TBD | B61-12 TKA, when
mated to the B61-12 BA, | mated to the B61-12 | mated to the B61- |  | mated to the B61-12
must be integrated on | BA, must be integrated | 12 BA, must be |  | BA, must be integrated
the F-35A and LRS-B for | on the F-35A and LRS- | integrated on B-2A |  | on the B-2A, F-15E, F-
System 2 guided | B for System 2 guided | and F-15E aircraft |  | 35A and LRS-B for
delivery; F-16C/D (Blk 40 | delivery; F-16C/D (Blk | for System 2 |  | System 2 guided
-52), F-16 MLU, and PA- | 40-52), F-16 MLU, and | guided delivery. |  | delivery; F-16C/D (Blk
200 for System 1 ballistic | PA-200 for System 1 |  |  | 40-52), F-16 MLU, and
delivery. | ballistic delivery. |  |  | PA-200 for System 1
ballistic delivery.
WS3 Vault Compatibility (KPP)
B61-12 TKA, while | B61-12 TKA, while | B61-12 TKA, while | Verified by fit | B61-12 TKA, while
mated to the B61-12 BA, | mated to the B61-12 | mated to the B61- | checks conducted | mated to the B61-12
must permit the storage | BA, must permit the | 12 BA, must permit | at Sheppard AFB | BA, must permit the
of four (4) B61-12 AURs | storage of four (4) B61- | the storage of four | on April 9, 2013. | storage of four (4) B61-
in a single WS3 vault. | 12 AURs in a single | (4) B61-12 AURs |  | 12 AURs in a single
| WS3 vault. | in a single WS3 |  | WS3 vault.
vault.
HEMP Survivability (KSA)
B61 TKA achieves the | B61 TKA achieves the | B61 TKA achieves | TBD | B61 TKA achieves the
accuracy KPP after | accuracy KPP after | the accuracy KPP |  | accuracy KPP after
exposure to the HEMP | exposure to the HEMP | after exposure to |  | exposure to the HEMP
environment. | environment. | the HEMP |  | environment.
environment.
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
CDD dated September 20, 2012
Change Explanations
None

## Table 12
Acronyms and Abbreviations
AFB - Air Force Base AUR - All Up Round BA - Bomb Assembly
HEMP - High Altitude Electro-Magnetic Pulse KSA - Key System Attribute
LRS-B - Long Range Strike-Bomber MLU - Mid-Life Upgrade
TKA - Tailkit Assembly
WS3 - Weapon Storage and Security System

## Table 13
Track to Budget
RDT&E
Appn |  | BA | PE
Air Force 3600 05 0101125F
Project | Name
657007 B61 LEP
Procurement
Appn |  | BA | PE
Air Force 3011 01 0101125F
Line Item | Name
354040 B61

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2012 $M | [6 empty] | BY 2012 $M |  | TY $M
| SAR Baseline Development Estimate |  |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E |  | 1007.6 |  |  | 1007.6 | 1108.4 |  |  | 892.9 |  | 1090.7 |  |  | 1090.7 |  | 958.3
Procurement |  | 314 |  |  | 314 | 345.4 |  |  | 301.2 |  | 361.1 |  |  | 361.1 |  | 355.1
Flyaway |  | -- |  |  | -- | -- |  |  | 301.2 |  | -- |  |  | -- |  | 355.1
Recurring |  | -- |  |  | -- | -- |  |  | 301.2 |  | -- |  |  | -- |  | 355.1
Non Recurring |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Other Support |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Initial Spares |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
MILCON |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 1321.6 |  |  | 1321.6 | N/A |  |  | 1194.1 |  | 1451.8 |  |  | 1451.8 |  | 1313.4
Confidence Level
Confidence Level of cost estimate for current APB: 56%
The confidence level for the EMD total estimate is 56%; the confidence level for the Procurement estimate is 51%; and the confidence level for the (O&S) estimate is 50%.
The APB costs reflect the SCP, which was approved on October 19, 2012. The SCP aims to provide sufficient resources to execute the program under normal conditions, encountering average levels of technical, schedule, and programmatic risk and external interference. It is consistent with average resource expenditures on historical efforts of similar size, scope, and complexity. Therefore, the approved SCP represents a mean cost estimate.
Total Quantity
Quantity |  |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  |  | 77 |  |  |  | 77 |  |  |  |  | 77
Procurement |  |  | 813 |  |  |  | 813 |  |  |  |  | 813
Total |  |  | 890 |  |  |  | 890 |  |  |  |  | 890

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 325.3 | 212.1 |  | 137.9 |  | 151 |  | 95.6 |  | 36.4 |  | 0 |  | 0 |  | 958.3
Procurement | 0 | 0 |  | 0 |  | 145.4 |  | 207.2 |  | 2.5 |  | 0 |  | 0 |  | 355.1
MILCON | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 325.3 | 212.1 |  | 137.9 |  | 296.4 |  | 302.8 |  | 38.9 |  | 0 |  | 0 |  | 1313.4
PB 2016 Total | 345.4 | 212.1 |  | 206.3 |  | 299 |  | 308.3 |  | 50.7 |  | 0 |  | 0 |  | 1421.8
Delta | -20.1 | 0 |  | -68.4 |  | -2.6 |  | -5.5 |  | -11.8 |  | 0 |  | 0 |  | -108.4
Funding Notes
Prior year decrements represent a Below Threshold Reprogramming and Small Business Innovation Research reduction for a total of $20.1M. An Above Threshold Reprogramming for $40M was also approved but it is not reflected in the current or prior year PB totals.
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 77 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 77
Production | 0 |  | 0 |  | 0 | 0 | 250 |  | 563 |  | 0 |  | 0 |  | 0 |  | 813
PB 2017 Total | 77 |  | 0 |  | 0 | 0 | 250 |  | 563 |  | 0 |  | 0 |  | 0 |  | 890
PB 2016 Total | 77 |  | 0 |  | 0 | 0 | 250 |  | 563 |  | 0 |  | 0 |  | 0 |  | 890
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 81.6
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.4
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 148.3
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 212.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 137.9
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 151
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 95.6
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36.4
Subtotal |  | 77 | -- |  | -- |  | -- |  | -- |  | -- |  | 958.3

## Table 17
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2012 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 80.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 60.8
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.7
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 141.2
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 198.9
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 126.9
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 136.4
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 84.6
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.6
Subtotal |  | 77 | -- |  | -- |  | -- |  | -- |  | -- |  | 892.9

## Table 18
Annual Funding 3011 ¦ Procurement ¦ Procurement of Ammunition, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2018 |  | 250 | 145.4 |  | -- |  | -- |  | 145.4 |  | -- |  | 145.4
2019 |  | 563 | 207.2 |  | -- |  | -- |  | 207.2 |  | -- |  | 207.2
2020 |  | -- | -- |  | 2.5 |  | -- |  | 2.5 |  | -- |  | 2.5
Subtotal |  | 813 | 352.6 |  | 2.5 |  | -- |  | 355.1 |  | -- |  | 355.1

## Table 19
Annual Funding 3011 ¦ Procurement ¦ Procurement of Ammunition, Air Force
Fiscal Year | Quantity |  | BY 2012 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2018 |  | 250 | 124.8 |  | -- |  | -- |  | 124.8 |  | -- |  | 124.8
2019 |  | 563 | 174.3 |  | -- |  | -- |  | 174.3 |  | -- |  | 174.3
2020 |  | -- | -- |  | 2.1 |  | -- |  | 2.1 |  | -- |  | 2.1
Subtotal |  | 813 | 299.1 |  | 2.1 |  | -- |  | 301.2 |  | -- |  | 301.2

## Table 20
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2012-11-19 | 2012-11-19
Approved Quantity | 250 | 250
Reference | Milestone B ADM | Milestone B ADM
Start Year | 2018 | 2018
End Year | 2019 | 2019
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the low production run and the need to sychronize DoD deliveries with the Department of Energy B61-12 Bomb Assembly program.

## Table 21
Foreign Military Sales
None
Nuclear Costs
Nuclear costs related to the B61-12 TKA program are captured in the Department of Energy Bomb Assembly SAR.

## Table 22
Unit Cost
Unit Cost Report
Item |  | BY 2012 $M | BY 2012 $M |  | % Change
|  | Current UCR Baseline (Dec 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1321.6 |  |  | 1194.1
Quantity | 890 |  |  | 890
Unit Cost | 1.485 |  |  | 1.342 |  | -9.63
Average Procurement Unit Cost
Cost | 314 |  |  | 301.2
Quantity | 813 |  |  | 813
Unit Cost | 0.386 |  |  | 0.37 |  | -4.15
Item |  | BY 2012 $M | BY 2012 $M |  | % Change
|  | Original UCR Baseline (Dec 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1321.6 |  |  | 1194.1
Quantity | 890 |  |  | 890
Unit Cost | 1.485 |  |  | 1.342 |  | -9.63
Average Procurement Unit Cost
Cost | 314 |  |  | 301.2
Quantity | 813 |  |  | 813
Unit Cost | 0.386 |  |  | 0.37 |  | -4.15

## Table 23
Unit Cost History
Item |  |  |  |  | Date |  |  |  |  | BY 2012 $M | [5 empty] | TY $M
[10 empty] | PAUC |  |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Dec 2012 | [6 empty] | 1.485 |  |  |  | 0.386 |  |  | 1.631 |  |  | 0.444
APB as of January 2006 |  |  | N/A | [6 empty] | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A | [6 empty] | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | N/A | [6 empty] | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Current APB |  |  | Dec 2012 | [6 empty] | 1.485 |  |  |  | 0.386 |  |  | 1.631 |  |  | 0.444
Prior Annual SAR |  |  | Dec 2014 | [6 empty] | 1.458 |  |  |  | 0.386 |  |  | 1.598 |  |  | 0.44
Current Estimate |  |  | Dec 2015 | [6 empty] | 1.342 |  |  |  | 0.37 |  |  | 1.476 |  |  | 0.437
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [16 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  |  | Eng |  | Est |  |  | Oth | Spt |  | Total
1.631 -0.004 0.000 -0.076 0.000 -0.075 0.000 0.000 -0.155 1.476
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [16 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng |  | Est |  |  | Oth |  | Spt |  | Total
0.444 0.011 0.000 0.000 0.000 -0.019 0.000 0.000 -0.008 0.437

## Table 24
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Nov 2012 | N/A | Nov 2012
Milestone C | N/A | Apr 2018 | N/A | Oct 2018
IOC | N/A | N/A | N/A | N/A
Total Cost (TY $M) | N/A | 1451.8 | N/A | 1313.4
Total Quantity | N/A | 890 | N/A | 890
PAUC | N/A | 1.631 | N/A | 1.476
First Tailkit Assembly (TKA) Production Delivery is used as a surrogate for IOC; the Department of Energy is responsible for production integration of the Bomb Assembly/TKA and subsequent All Up Round deliveries to the field for IOC.

## Table 25
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 1090.7 | 361.1 | -- | 1451.8
Previous Changes
Economic | -6.4 | -2.6 | -- | -9
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -20.2 | -0.8 | -- | -21
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -26.6 | -3.4 | -- | -30
Current Changes
Economic | -6.4 | 11.8 | -- | 5.4
Quantity | -- | -- | -- | --
Schedule | -68.4 | -- | -- | -68.4
Engineering | -- | -- | -- | --
Estimating | -31 | -14.4 | -- | -45.4
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -105.8 | -2.6 | -- | -108.4
Total Changes | -132.4 | -6 | -- | -138.4
CE - Cost Variance | 958.3 | 355.1 | -- | 1313.4
CE - Cost & Funding | 958.3 | 355.1 | -- | 1313.4

## Table 26
Summary BY 2012 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 1007.6 | 314 | -- | 1321.6
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -23.5 | -0.5 | -- | -24
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -23.5 | -0.5 | -- | -24
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -62.9 | -- | -- | -62.9
Engineering | -- | -- | -- | --
Estimating | -28.3 | -12.3 | -- | -40.6
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -91.2 | -12.3 | -- | -103.5
Total Changes | -114.7 | -12.8 | -- | -127.5
CE - Cost Variance | 892.9 | 301.2 | -- | 1194.1
CE - Cost & Funding | 892.9 | 301.2 | -- | 1194.1
Previous Estimate: December 2014

## Table 27
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -6.4
Revised estimate to align with FY 2017 PB which resulted in program rephasing. (Schedule)
-62.9 -68.4
Revised estimate due to Small Business Innovative Research reduction. (Estimating) | -9.6 | -10.1
Revised estimate due to Below Threshold Reprogramming action taken. (Estimating) | -9.5 | -10
Revised estimate due to Air Force-wide inflationary adjustment. (Estimating) | -11.8 | -13.6
Adjustment for current and prior escalation. (Estimating) | 2.6 | 2.7
RDT&E Subtotal | -91.2 | -105.8
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 11.8
Revised estimate due to Air Force-wide inflationary adjustments. (Estimating) | -2.2 | -2.6
Adjustment for current and prior escalation. (Estimating) | -10.1 | -11.8
Procurement Subtotal | -12.3 | -2.6

## Table 28
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: B61-12 TKA EMD Phase 1
Contractor: Boeing
Contractor Location: 2600 N 3rd Street
St. Charles, MO 63301
Contract Number: FA2103-13-C-0006
Contract Type: Cost Plus Incentive Fee (CPIF)
Award Date: November 27, 2012
Definitization Date: November 27, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
178.6 N/A N/A 186.3 N/A N/A 184.9 193.4
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to additional modifications post initial contract award.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (9/30/2015) -1.3 -11.4
Previous Cumulative Variances +3.0 -4.8
Net Change -4.3 -6.6
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to increased cost in performance of work packages for the Inertial Measurement Unit, primary structure; environmental testing, munitions software, on board test equipment, and guidance algorithms.
The unfavorable net change in the schedule variance is due to delays regarding the actuators, munitions assembly test and checkout, environmental testing, and mission computer.
Notes
Cost and Schedule variances are as of September 30, 2015. Boeing has declared an Over Target Schedule for EMD Phase 1. The EVM data has been temporarily suspended until the action items from the February Integrated Baseline Review are complete.

## Table 29
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 77 | 0%
Production | 0 | 0 | 813 | 0%
Total Program Quantity Delivered | 0 | 0 | 890 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
1313.4
274.3
20.88%
9
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
5
55.56%
537.4
40.92%
The above data is current as of February 29, 2016.

## Table 30
Operating and Support Cost
Cost Estimate Details
Date of Estimate: October 19, 2012
Source of Estimate: SCP
Quantity to Sustain: 824
Unit of Measure: Tailkit Assembly (TKA)
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2019 - FY 2040
- Unit of Measure = Tailkit Assembly (TKA)
- Total Quantity = 824
-- Production quantity: 813
-- Development Trainers: 11
- 77 test assets in RDT&E are expended; not sustained. The 11 development trainers are not included in this number.
- Estimate assumes wooden round -- Production Lifetime Sparing Concept
- Contractor services retained for failure analysis, test support, logistical support, destructive testing, etc.
- Projected contractor labor rates are through FY 2040
-- Used 4% increase in base pay rate to account for differences in contractor inflation versus OSD published inflation
- No nuclear certification required for Tailkit Assembly Stand-Alone Test Sets
- Continental United States (CONUS) shipping costs for Weapon System Evaluation Program assets paid by the Department of Energy
- Personnel Outside of the CONUS locations exist solely to support this weapon
Sustainment Strategy
B61-12 TKA Sustainment Strategy is based on system reliability requirements/projections. Planned Material Availability is sustained through a 20-year service life spares buy that is included in the TKA production quantities. Air Force Materiel Command (AFMC) has determined no organic depot level repair requirements at this time. Organizational/Intermediate level maintenance is limited to replacement, inspection, disassembly/reassembly of TKA from All Up Round (B61-12 All Up Round). A TKA Business Case Analysis (BCA) projected for late FY 2016 will evaluate cost effectiveness of selecting an optional warranty, organic, or Contractor Logistics Support (CLS) based on final reliability projections, test set design, support equipment, and engineering requirements.
Antecedent Information
No Antecedent

## Table 31
Annual O&S Costs BY2012 $M
Cost Element |  | B61 Mod 12 LEP TKA Average Annual Cost Per Tailkit Assembly (TKA) | [5 empty] | No Antecedent (Antecedent)
Unit-Level Manpower |  | 0.069 | [5 empty] | --
Unit Operations |  | 0.001 | [5 empty] | --
Maintenance |  | 0.005 | [5 empty] | --
Sustaining Support |  | 0.015 | [5 empty] | --
Continuing System Improvements |  | 0 | [5 empty] | --
Indirect Support |  | 0.042 | [5 empty] | --
Other |  | 0 | [5 empty] | --
Total |  | 0.132 | [5 empty] | --
Data Source: SCP
Item | Total O&S Cost $M
| B61 Mod 12 LEP TKA | [7 empty] | No Antecedent (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 2283.3 |  |  | 2511.6 |  |  | 2283.3 |  | N/A
Then Year | 2887.3 |  |  | N/A |  |  | 2887.3 |  | N/A
.
Equation to Translate Annual Cost to Total Cost
Average Annual Unitized Cost = (Total O&S Cost/Quantity)/(Service Life plus trainer lead-in time) = ($2283.3M/824)/ (20+1)
O&S Cost Variance
Category |  |  | BY 2012 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
2283.3
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 2283.3
Disposal Estimate Details

## Table 32
Date of Estimate: October 19, 2012
Source of Estimate: SCP
Disposal/Demilitarization Total Cost (BY 2012 $M): Total costs for disposal of all Tailkit Assembly (TKA) are 0.1
$0.190M in TY dollars ~ $.120M in BY 2012 dollars.