## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-374
Littoral Combat Ship (LCS)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 9
Schedule 10
Performance 12
Track to Budget 15
Cost and Funding 17
Low Rate Initial Production 32
Foreign Military Sales 33
Nuclear Costs 33
Unit Cost 34
Cost Variance 37
Contracts 41
Deliveries and Expenditures 47
Operating and Support Cost 48

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Littoral Combat Ship (LCS)
DoD Component
Navy
Responsible Office
CAPT Tom Anderson
Naval Sea Systems Command 1333 Isaac Hull Ave SE
Washington Navy Yard, DC 20376-7003
thomas.j.anderson3@navy.mil
Phone: | 202-781-1918
Fax: | 202-781-4573
DSN Phone: | 326-1918
DSN Fax: Date Assigned: | November 16, 2012
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 7, 2011
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 7, 2011

## Table 6
Mission and Description
The role of the Littoral Combat Ship (LCS) is to provide joint forces access in the littoral. LCS is designed to be a fast, agile, and networked surface combatant. It will focus on three primary anti-access mission areas within Littoral Surface Warfare operations: prosecution of small boats, mine warfare, and littoral anti-submarine warfare. Its high speed and ability to operate at economical loiter speeds will enable fast and calculated responses to small boat threats, mine laying and quiet diesel submarines. LCS employment of networked sensors for Intelligence, Surveillance, and Reconnaissance in support of Special Operations Forces will directly enhance littoral mobility. Its shallow draft will allow easier excursion into shallower areas for both mine countermeasures and small boat prosecution. Using LCS against these asymmetric threats will enable Joint Commanders to concentrate multi-mission combatants on primary missions such as precision strike, battle group escort and theater air defense.

## Table 7
Executive Summary
In 2015, the LCS Program continued to validate and deliver capability to the Fleet. Each LCS variant has achieved IOC and twenty-four LCS Seaframes have been awarded to date: six have delivered to the Navy, 14 are in various stages of production, and four are in pre-production status.
USS CORONADO (LCS 4) conducted Initial Operational Test & Evaluation events in August and September 2015 with the Surface Warfare Mission Package Increment II embarked, leading to declaration of IOC for the Independence variant. LCS 4 also conducted the first ever at-sea firing of the Sea Rolling Airframe Missile Anti-Ship Cruise Missile defense system successfully, against an aerial target. LCS 4 recently completed Total Ship Survivability Trial, and is currently preparing for her maiden deployment to the Western Pacific in summer 2016.
USS MILWAUKEE (LCS 5) and USS JACKSON (LCS 6) delivered to the Navy in October and August 2015, respectively. LCS 5 and LCS 6 delivered with the fewest number of starred and trial cards of their respective variants, to date. Following commissioning in first quarter FY 2016 both vessels transited to Mayport, Florida to undergo final preparations for Full Ship Shock Trials scheduled for summer 2016.
For ships in construction, hull over hull performance continues to improve. With the stabilization of the front-end of production, both shipyards have transitioned to serial trials and delivery. DETROIT (LCS 7) and MONTGOMERY (LCS 8) are preparing for Acceptance Trial followed by Delivery in third quarter FY 2016. LCS 9 through LCS 20 are in various stages of production.
On March 31, 2015, the Navy executed the USD(AT&L) approved FY 2015/FY 2016 LCS acquisition strategy by funding three FY 2015 ships, two to Austal (LCS 22 and LCS 24) and one to Lockheed Martin (LCS 21), plus advance procurement for LCS 23. The Navy also added one FY 2016 priced option ship for LM and Austal based on the competitive prices of the block buy.
On November 24, 2015, the Navy executed the remaining funding for LCS 23, the final LCS of the block buy. The remaining two FY 2016 LCS, LCS 25 and LCS 26 are priced options under the 2010-2016 block buy contracts and are required to be funded no later than March 31, 2016.
The FY 2017 PB submission requests $1,126M to procure two LCS in FY 2017. This represents a quantity reduction of one
(1) LCS from the FY 2016 PB. On December 14, 2015 the Secretary of Defense directed that the Navy build a total of 40 LCS and Frigates, and down-select to one variant in FY 2019. The FY 2017 acquisition strategy supporting the final procurement of LCS is currently under review. The estimate reflected in this SAR represents the costs of the budgeted 40 ship program (vice the required 52 ship program of record). This represents an increase of 8 ships from the December 2014 32 ship SAR.
Sequestration and Congressional reductions in FY 2010 – FY 2013 reduced LCS 5 – LCS 16 budgets by $213M impacting the program’s ability to fund shipbuilding contracts to the PM’s estimate. FY 2017 PB requests $86M of cost to complete for the FY 2012 and FY 2013 LCS.
In April 2011, in conjunction with the LCS Seaframe Milestone B decision, USD(AT&L) certified the LCS Seaframe program pursuant to section 2366b of title 10, United States Code, with waivers. Specifically, USD(AT&L) was unable to certify three provisions and that without these waivers the Department would be unable to meet critical national security objectives.
Provisions (a)1(B) (affordability) and 1(D) (funding available) were waived due to a total resource and funding shortfall in the period covered by the FYDP submitted in FY 2011 when the certification was made. The remaining resources required to complete the small surface combatant program remain outside the FYDP as submitted for FY 2017 PB. For the waiver to provision (a)1(C) (reasonable cost estimates with concurrence of Director (D),CAPE), the D,CAPE continues to monitor the cost estimates as the program progresses through the budget cycles and participates in annual DAB In-Process Reviews conducted by USD(AT&L).

## Table 8
Current Contract Price ($M), Estimated Price at Completion ($M) and Cost and Schedule Variance for the contracts included in this report are For Official Use Only - Exempt from FOIA release under 5 U.S.C. 552(b)(4).
There are no significant software-related issues with this program at this time.

## Table 9
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
The LCS 2 Initial Operational Test & Evaluation (IOT&E)/IOC schedule breach was previously reported in the December 2013 SAR. These requirements were subsequently resolved though the USS CORONADO (LCS 4) conduct of IOT&E events in August- October 2015, leading to declaration of IOC for the INDEPENDENCE variant.
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 10
Schedule
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone A/Program Initiation | May 2004 | May 2004 | May 2004 | May 2004
Final Design and Construction Contract Award | May 2004 | May 2004 | May 2004 | May 2004
Lead Ship Award | Dec 2004 | Dec 2004 | Dec 2004 | Dec 2004
First Ship Delivery | Sep 2008 | Sep 2008 | Sep 2008 | Sep 2008
FY 2010 Contract Award | Dec 2010 | Dec 2010 | Jun 2011 | Dec 2010
Milestone B | Feb 2011 | Feb 2011 | Aug 2011 | Feb 2011
Milestone C | Jan 2012 | Jan 2012 | Jul 2012 | Jan 2012
Initial Operational Capability | Jan 2014 | Jan 2014 | Jul 2014 | Apr 2014
IOT&E LCS 1 with one Mission Package | Dec 2013 | Dec 2013 | Jun 2014 | Apr 2014
IOT&E LCS 2 with one Mission Package | Dec 2013 | Dec 2013 | Jun 2014 | Oct 20151
IOC LCS 2 | Jan 2014 | Jan 2014 | Jul 2014 | Oct 20151
1 APB Breach
(Ch-1)
(Ch-2)
Change Explanations
(Ch-1) IOT&E LCS 2 with one Mission Package changed from August 2015, as previously reported, to October 2015 to reflect the completion of IOT&E for the LCS 2 (INDEPENDENCE) variant in support of declaration of IOC.
(Ch-2) IOC LCS 2 changed from September 2015, as previously reported, to October 2015 to reflect the completion of IOT&E for the LCS 2 (INDEPENCENCE) variant in support of declaration of IOC.

## Table 11
Acronyms and Abbreviations
IOT&E - Initial Operational, Test and Evaluation

## Table 12
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Navigational Draft (ft)
10 | 10 | 20 | 15.7 / 15.4 ft | 15.7 / 15.4 ft
Sprint Speed (kts)
50 | 50 | 40 | 38.7 / 40.2 kts | 40 / 40.2 kts
Range at Transit Speed (includes payload)
4,300 nm @ 16 kts | 4,300 nm @ 16 kts | 3,500 nm @ 14 kts | 3405nm / 4285nm @ 14 kts | 3500nm / 4285nm @ 14 kts
Mission Package Payload (Weight)
210 MT (130 MT) mission package/80 MT mission package fuel) | 210 MT (130 MT) mission package/80 MT mission package fuel) | 180 MT (105 MT mission package/75 MT mission package fuel) | 180 MT / 180 MT | 180 MT / 180 MT - (105 MT) mission package/75 MT mission package fuel)
Net- Ready: The system must support Net-Centric military operations. The system must be able to enter and be managed in the network, and exchange data in a secure manner to enhance mission effectiveness. The system must continuously provide survivable, interoperable, secure, and operationally effective information exchanges to enable a Net-Centric military capability.
The system must fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net- Centric military operations to include 1) DISR mandated GIG IT standards and profiles identified in the TV-1, 2) DISR mandated GIG KIPs identified in the KIP declaration table, 3) NCOW RM Enterprise Services 4) IA requirements including availability, integrity, authenticat- ion, confidential-ity, and | The system must fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net- Centric military operations to include 1) DISR mandated GIG IT standards and profiles identified in the TV-1, 2) DISR mandated GIG KIPs identified in the KIP declaration table, 3) NCOW RM Enterprise Services 4) IA requirements including availability, integrity, authenticat- | The system must fully support execution of joint critical operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for transition to Net- Centric military operations to include 1) DISR mandated GIG IT standards and profiles identified in the TV-1, 2) DISR mandated GIG KIPs identified in the KIP declaration table, 3) NCOW RM Enterprise Services 4) IA requirements | TBD / TBD | The system for both LCS variants will fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net- Centric military operations to include 1) DISR mandated GIG IT standards and profiles identified in the TV-1, 2) DISR mandated GIG KIPs identified in the KIP declaration table, 3) NCOW RM Enterprise Services 4) IA requirements including availability,
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)

## Table 13
nonrepudiat-ion, and issuance of an ATO by the DAA, And 5) Operationally effective information exchanges; and mission critical performance and IA attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture views. | ion, confidential-ity, and nonrepudiat-ion, and issuance of an ATO by the DAA, And 5) Operationally effective information exchanges; and mission critical performance and IA attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture views. | including availability, integrity, authenticat- ion, confidential-ity, and nonrepudiat-ion, and issuance of an IATO by the DAA, and 5) Operationally effective information exchanges; and mission critical performance and IA attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture views. |  | integrity, authenticat- ion, confidential-ity, and nonrepudiat-ion, and issuance of an ATO by the DAA, And 5) Operationally effective information exchanges; and mission critical performance and IA attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture views.
Core Crew Manning (# Core Crew Members)
15 | 15 | 50 | 50 Core Crew / 50 Core Crew | 50 Core Crew / 50 Core Crew
Materiel Availability
0.712 | 0.712 | 0.64 | TBD / TBD | 0.64 / 0.64
Systems Training (Core Crew)
Trained-to-Certify at all Team (Watch Section) levels | Trained-to-Certify at all Team (Watch Section) levels | Trained-to-Qualify at individual level (billet/watch station) | TBD / TBD | Trained-to-Qualify at Individual level (billet/watch station) / Trained-to-Qualify at Individual level (billet/watch station)
(Ch-1)
(Ch-1)
(Ch-1)
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Flight 0+ Capability Development Document (CDD) dated June 17, 2008
Change Explanations
(Ch-1) The demonstrated performance and current estimates for all KPPs changed to reflect the addition of the INDEPENDENCE variant. For each of these fields, the first values reflect the FREEDOM estimate and performance, as reported in the December 2014 SAR.
Acronyms and Abbreviations
ATO - Authority to Operate
DAA - Designated Approval Authority DISR - DoD IT Standards Registry

## Table 14
ft - Feet
GIG - Global Information Grid IA - Information Assurance
IATO - Interim Authority to Operate IT - Information Technology
KIP - Key Interface Profile kts - Knots
MT - Metric Ton
NCOW RM - Net-Centric Operations Warfare Reference Model nm - Nautical Miles
TV - Technical View

## Table 15
Track to Budget
RDT&E
Appn |  |  |  | BA | PE
Navy |  | 1319 04 |  |  | 0603581N
|  | Project |  |  | Name
|  | 3096 |  |  | Littoral Combat Ship/Littoral Combat Ship Development | (Shared)
|  | 4018 |  |  | Littoral Combat Ship/Littoral Combat Ship Construction |  | (Sunk)
|  | 4506 |  |  | LCS Training
|  | 9999 |  |  | LCS Training Courseware |  | (Sunk)
|  | Notes: |  |  | Congressional Add
|  | 9999 |  |  | Littoral Combat Ship/Revised Acquisition Strategy |  | (Sunk)
|  | Notes: |  |  | Congressional Add
Navy |  | 1319 04 |  |  | 0603599N
|  | Project |  |  | Name
|  | 3086 |  |  | Frigate Development
Navy |  | 1611 | 2 |  | 0204230N
|  | Line | Item |  | Name
|  | 2127 |  |  | Littoral Combat Ship
Navy |  | 1611 | 5 |  | 0204230N
|  | Line | Item |  | Name
|  | 5110 |  |  | Outfitting |  |  | (Shared)
|  | 5300 |  |  | Completion of Prior Year Shipbuilding Programs |  |  | (Shared)
Navy |  | 1810 | 1 |  | 0204230N
|  | Line | Item |  | Name
|  | 944 |  |  | LCS Class Equipment |  |  | (Shared)
|  | 1320 |  |  | Other Ship Training Equipment |  |  | (Shared) (Sunk)
|  | 1604 |  |  | LCS In-Service Modernization
Navy |  | 1810 | 4 |  | 0204230N
|  | Line | Item |  | Name
|  | 5664 |  |  | Surface Training Equipment |  |  | (Shared)
Procurement
Appn |  |  |  | BA | PE
MILCON
Appn |  |  |  | BA | PE
Navy 1205 01 0203176N
Project | Name
00245499 LCS Facility Support (Sunk)

## Table 16
| 245500 | LCS Training Facility |  | (Sunk)
| 60201425 | LCS Logistics Support Facility | (Shared) | (Sunk)
Navy | 1205 01 | 0815976N
| Project | Name
| 60201423 | LCS Operational Trainer Facility | (Shared) | (Sunk)
Navy | 1205 03 | 0901211N
| Project | Name
| 64482044 | Planning | (Shared) | (Sunk)

## Table 17
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2010 $M | [6 empty] | BY 2010 $M |  | TY $M
| SAR Baseline Development Estimate |  |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E |  | 3433.3 |  |  | 3433.3 | 3776.6 |  |  | 3564.5 |  | 3481.7 |  |  | 3481.7 |  | 3662.6
Procurement |  | 28369.2 |  |  | 28369.2 | 31206.1 |  |  | 20130.2 |  | 33720.5 |  |  | 33720.5 |  | 24970.6
Flyaway |  | -- |  |  | -- | -- |  |  | 20130.2 |  | -- |  |  | -- |  | 24970.6
Recurring |  | -- |  |  | -- | -- |  |  | 20130.2 |  | -- |  |  | -- |  | 24970.6
Non Recurring |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Other Support |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Initial Spares |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
MILCON |  | 208.5 |  |  | 208.5 | 229.4 |  |  | 224.1 |  | 236.6 |  |  | 236.6 |  | 267.5
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 32011 |  |  | 32011 | N/A |  |  | 23918.8 |  | 37438.8 |  |  | 37438.8 |  | 28900.7
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The estimate to support this program, like most cost estimates, is built upon a product-oriented work breakdown structure based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which we have been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for Major Defense Acquisition Programs (MDAPs). Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about as likely the estimate will prove too low or too high for the program as described.
Cost Notes
The FY 2017 PB submission requests $1,126M to procure two LCS in FY 2017. This represents a quantity reduction of one LCS from the FY 2016 PB. The estimate reflected in this SAR represents the costs of the budgeted 40 ship program (vice the required 52 ship program of record).
Total Quantity
Quantity |  |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate

## Table 18
RDT&E | 2 | 2 | 2
Procurement | 53 | 53 | 38
Total | 55 | 55 | 40

## Table 19
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 2799 | 121.4 |  | 136.5 |  | 103.6 |  | 105.5 |  | 44 |  | 43.8 |  | 308.8 |  | 3662.6
Procurement | 10790 | 1691.6 |  | 1461.7 |  | 992.5 |  | 1236.8 |  | 978.2 |  | 1605.8 |  | 6214 |  | 24970.6
MILCON | 100.9 | 37.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 129.2 |  | 267.5
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 13689.9 | 1850.4 |  | 1598.2 |  | 1096.1 |  | 1342.3 |  | 1022.2 |  | 1649.6 |  | 6652 |  | 28900.7
PB 2016 Total | 13876.9 | 1847.9 |  | 1872.5 |  | 1817.1 |  | 446.6 |  | 523.4 |  | 882.3 |  | 575.6 |  | 21842.3
Delta | -187 | 2.5 |  | -274.3 |  | -721 |  | 895.7 |  | 498.8 |  | 767.3 |  | 6076.4 |  | 7058.4
Funding Notes
On December 14, 2015 the Secretary of Defense directed that the Navy build a total of 40 LCS and Frigates, and down- select to one variant (Frigate) in FY 2019. The estimate reflected in this SAR represents the costs of the budgeted 40 ship program (vice the required 52 ship program of record). This represents an increase of 8 ships from the December 2014 32 ship SAR.
PB17 OPN LI 9020 funds that were identified as being LCS specific are not part of the LCS Seaframe acquisition program.
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 2 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2
Production | 0 |  | 21 |  | 3 | 2 | 1 |  | 1 |  | 1 |  | 2 |  | 7 |  | 38
PB 2017 Total | 2 |  | 21 |  | 3 | 2 | 1 |  | 1 |  | 1 |  | 2 |  | 7 |  | 40
PB 2016 Total | 2 |  | 21 |  | 3 | 3 | 3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 32
Delta | 0 |  | 0 |  | 0 | -1 | -2 |  | 1 |  | 1 |  | 2 |  | 7 |  | 8

## Table 20
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.8
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 116.8
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 369.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 384.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 573.1
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 200.9
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 197.4
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 260.1
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 99
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 147
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 168.9
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 165.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 80.2
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 121.4
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 136.5
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 103.6
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 105.5
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.8
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 61.9
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49.7
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 105.4
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.1
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.5
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.2
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 3662.6

## Table 21
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.1
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 130.5
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 402.7
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 406.1
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 590.8
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 203.4
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 197.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 256.1
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 95.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 139.1
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 158.1
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 152.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 73.1
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 108.9
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 120.3
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 89.5
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 89.4
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36.6
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.7
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49.4
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.9
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 80.9
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.9
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.7
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 3564.5

## Table 22
RDT&E for the Program includes the detail design and construction of two Flight 0 ships in addition to the program development, test and evaluation, training development, and sustained engineering for both LCS and Frigate.

## Table 23
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | -- |  | 20.4 |  | -- |  | 20.4 |  | -- |  | 20.4
2013 |  | -- | -- |  | 30.8 |  | -- |  | 30.8 |  | -- |  | 30.8
2014 |  | -- | -- |  | 68.3 |  | -- |  | 68.3 |  | -- |  | 68.3
2015 |  | -- | -- |  | 35.4 |  | -- |  | 35.4 |  | -- |  | 35.4
2016 |  | -- | -- |  | 88.5 |  | -- |  | 88.5 |  | -- |  | 88.5
2017 |  | -- | -- |  | 73.7 |  | -- |  | 73.7 |  | -- |  | 73.7
2018 |  | -- | -- |  | 131.8 |  | -- |  | 131.8 |  | -- |  | 131.8
2019 |  | -- | -- |  | 112.4 |  | -- |  | 112.4 |  | -- |  | 112.4
2020 |  | -- | -- |  | 82.7 |  | -- |  | 82.7 |  | -- |  | 82.7
2021 |  | -- | -- |  | 65.6 |  | -- |  | 65.6 |  | -- |  | 65.6
2022 |  | -- | -- |  | 1.1 |  | -- |  | 1.1 |  | -- |  | 1.1
2023 |  | -- | -- |  | 10.7 |  | -- |  | 10.7 |  | -- |  | 10.7
2024 |  | -- | -- |  | 103.9 |  | -- |  | 103.9 |  | -- |  | 103.9
2025 |  | -- | -- |  | 1.9 |  | -- |  | 1.9 |  | -- |  | 1.9
Subtotal |  | -- | -- |  | 827.2 |  | -- |  | 827.2 |  | -- |  | 827.2

## Table 24
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | -- |  | 19.2 |  | -- |  | 19.2 |  | -- |  | 19.2
2013 |  | -- | -- |  | 28.6 |  | -- |  | 28.6 |  | -- |  | 28.6
2014 |  | -- | -- |  | 62.6 |  | -- |  | 62.6 |  | -- |  | 62.6
2015 |  | -- | -- |  | 32 |  | -- |  | 32 |  | -- |  | 32
2016 |  | -- | -- |  | 78.7 |  | -- |  | 78.7 |  | -- |  | 78.7
2017 |  | -- | -- |  | 64.3 |  | -- |  | 64.3 |  | -- |  | 64.3
2018 |  | -- | -- |  | 112.8 |  | -- |  | 112.8 |  | -- |  | 112.8
2019 |  | -- | -- |  | 94.3 |  | -- |  | 94.3 |  | -- |  | 94.3
2020 |  | -- | -- |  | 68.1 |  | -- |  | 68.1 |  | -- |  | 68.1
2021 |  | -- | -- |  | 52.9 |  | -- |  | 52.9 |  | -- |  | 52.9
2022 |  | -- | -- |  | 0.9 |  | -- |  | 0.9 |  | -- |  | 0.9
2023 |  | -- | -- |  | 8.3 |  | -- |  | 8.3 |  | -- |  | 8.3
2024 |  | -- | -- |  | 79 |  | -- |  | 79 |  | -- |  | 79
2025 |  | -- | -- |  | 1.4 |  | -- |  | 1.4 |  | -- |  | 1.4
Subtotal |  | -- | -- |  | 703.1 |  | -- |  | 703.1 |  | -- |  | 703.1

## Table 25
OPN for the Program includes the battle spares and shore based trainers for both LCS and Frigate.

## Table 26
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2009 |  | 2 | 1341.6 |  | -- |  | -- |  | 1341.6 |  | -- |  | 1341.6
2010 |  | 2 | 1044.9 |  | -- |  | -- |  | 1044.9 |  | -- |  | 1044.9
2011 |  | 2 | 1189.1 |  | -- |  | -- |  | 1189.1 |  | -- |  | 1189.1
2012 |  | 4 | 1719.6 |  | -- |  | -- |  | 1719.6 |  | -- |  | 1719.6
2013 |  | 4 | 1787.7 |  | -- |  | -- |  | 1787.7 |  | -- |  | 1787.7
2014 |  | 4 | 1862.2 |  | -- |  | -- |  | 1862.2 |  | -- |  | 1862.2
2015 |  | 3 | 1690 |  | -- |  | -- |  | 1690 |  | -- |  | 1690
2016 |  | 3 | 1603.1 |  | -- |  | -- |  | 1603.1 |  | -- |  | 1603.1
2017 |  | 2 | 1388 |  | -- |  | -- |  | 1388 |  | -- |  | 1388
2018 |  | 1 | 860.7 |  | -- |  | -- |  | 860.7 |  | -- |  | 860.7
2019 |  | 1 | 1124.4 |  | -- |  | -- |  | 1124.4 |  | -- |  | 1124.4
2020 |  | 1 | 895.5 |  | -- |  | -- |  | 895.5 |  | -- |  | 895.5
2021 |  | 2 | 1540.2 |  | -- |  | -- |  | 1540.2 |  | -- |  | 1540.2
2022 |  | 2 | 1618.6 |  | -- |  | -- |  | 1618.6 |  | -- |  | 1618.6
2023 |  | 2 | 1469.1 |  | -- |  | -- |  | 1469.1 |  | -- |  | 1469.1
2024 |  | 2 | 1564.1 |  | -- |  | -- |  | 1564.1 |  | -- |  | 1564.1
2025 |  | 1 | 942.2 |  | -- |  | -- |  | 942.2 |  | -- |  | 942.2
2026 |  | -- | 148.2 |  | -- |  | -- |  | 148.2 |  | -- |  | 148.2
2027 |  | -- | 142.6 |  | -- |  | -- |  | 142.6 |  | -- |  | 142.6
2028 |  | -- | 129 |  | -- |  | -- |  | 129 |  | -- |  | 129
2029 |  | -- | 82.6 |  | -- |  | -- |  | 82.6 |  | -- |  | 82.6
Subtotal |  | 38 | 24143.4 |  | -- |  | -- |  | 24143.4 |  | -- |  | 24143.4

## Table 27
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2009 |  | 2 | 1289.4 |  | -- |  | -- |  | 1289.4 |  | -- |  | 1289.4
2010 |  | 2 | 970.2 |  | -- |  | -- |  | 970.2 |  | -- |  | 970.2
2011 |  | 2 | 1069.1 |  | -- |  | -- |  | 1069.1 |  | -- |  | 1069.1
2012 |  | 4 | 1512 |  | -- |  | -- |  | 1512 |  | -- |  | 1512
2013 |  | 4 | 1541 |  | -- |  | -- |  | 1541 |  | -- |  | 1541
2014 |  | 4 | 1575.7 |  | -- |  | -- |  | 1575.7 |  | -- |  | 1575.7
2015 |  | 3 | 1405.6 |  | -- |  | -- |  | 1405.6 |  | -- |  | 1405.6
2016 |  | 3 | 1309.2 |  | -- |  | -- |  | 1309.2 |  | -- |  | 1309.2
2017 |  | 2 | 1112.1 |  | -- |  | -- |  | 1112.1 |  | -- |  | 1112.1
2018 |  | 1 | 676.2 |  | -- |  | -- |  | 676.2 |  | -- |  | 676.2
2019 |  | 1 | 866 |  | -- |  | -- |  | 866 |  | -- |  | 866
2020 |  | 1 | 676.2 |  | -- |  | -- |  | 676.2 |  | -- |  | 676.2
2021 |  | 2 | 1140.2 |  | -- |  | -- |  | 1140.2 |  | -- |  | 1140.2
2022 |  | 2 | 1174.8 |  | -- |  | -- |  | 1174.8 |  | -- |  | 1174.8
2023 |  | 2 | 1045.4 |  | -- |  | -- |  | 1045.4 |  | -- |  | 1045.4
2024 |  | 2 | 1091.2 |  | -- |  | -- |  | 1091.2 |  | -- |  | 1091.2
2025 |  | 1 | 644.4 |  | -- |  | -- |  | 644.4 |  | -- |  | 644.4
2026 |  | -- | 99.4 |  | -- |  | -- |  | 99.4 |  | -- |  | 99.4
2027 |  | -- | 93.7 |  | -- |  | -- |  | 93.7 |  | -- |  | 93.7
2028 |  | -- | 83.1 |  | -- |  | -- |  | 83.1 |  | -- |  | 83.1
2029 |  | -- | 52.2 |  | -- |  | -- |  | 52.2 |  | -- |  | 52.2
Subtotal |  | 38 | 19427.1 |  | -- |  | -- |  | 19427.1 |  | -- |  | 19427.1

## Table 28
SCN for the Program includes construction, outfitting, and post-delivery requirements for LCS and Frigate.
Cost Quantity Information 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2010 $M
2009 | 2 | 1400.3
2010 | 2 | 1087.9
2011 | 2 | 1107.1
2012 | 4 | 1790.4
2013 | 4 | 1730.2
2014 | 4 | 1706.6
2015 | 3 | 1373.7
2016 | 3 | 1314.2
2017 | 2 | 994.8
2018 | 1 | 542.6
2019 | 1 | 690.6
2020 | 1 | 601.8
2021 | 2 | 1135.3
2022 | 2 | 1122.2
2023 | 2 | 1110.5
2024 | 2 | 1111.6
2025 | 1 | 607.3
2026 | -- | --
2027 | -- | --
2028 | -- | --
2029 | -- | --
Subtotal | 38 | 19427.1

## Table 29
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
2013 62.3
2014 16.1
2015 22.5
2016 37.4
2017 --
2018 --
2019 --
2020 --
2021 --
2022 129.2
Subtotal 267.5

## Table 30
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 2010 $M
Total Program
2013 57.0
2014 14.5
2015 20.0
2016 32.6
2017 --
2018 --
2019 --
2020 --
2021 --
2022 100.0
Subtotal 224.1

## Table 31
MILCON for the Program reflects requirements for both LCS and Frigate.

## Table 32
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2011-02-18 | 2014-10-17
Approved Quantity | 24 | 26
Reference | Milestone B ADM | LCS 2016 Acquisition Strategy
Start Year | 2005 | 2005
End Year | 2015 | 2016
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the Milestone B decision that includes the ships through FY 2015, and subsequent extension through 2016, in order to cover the LCS Seaframe program requirements.
The LRIP decision of 26 ships includes two ships procured with RDT&E, two ships procured in FY 2009, and the 22 ships being procured in a block buy arrangement in FY 2010 through FY 2016.

## Table 33
Foreign Military Sales
None
Nuclear Costs
None

## Table 34
Unit Cost
Unit Cost Report
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
|  | Current UCR Baseline (Apr 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 32011 |  |  | 23918.8
Quantity | 55 |  |  | 40
Unit Cost | 582.018 |  |  | 597.97 |  | 2.74
Average Procurement Unit Cost
Cost | 28369.2 |  |  | 20130.2
Quantity | 53 |  |  | 38
Unit Cost | 535.268 |  |  | 529.742 |  | -1.03
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
|  | Original UCR Baseline (Apr 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 32011 |  |  | 23918.8
Quantity | 55 |  |  | 40
Unit Cost | 582.018 |  |  | 597.97 |  | 2.74
Average Procurement Unit Cost
Cost | 28369.2 |  |  | 20130.2
Quantity | 53 |  |  | 38
Unit Cost | 535.268 |  |  | 529.742 |  | -1.03

## Table 35
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2010 $M | [7 empty] | TY $M
[8 empty] | PAUC |  |  |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  |  | Apr 2011 |  |  |  |  | 582.018 |  |  |  |  | 535.268 |  |  |  | 680.705 |  |  | 636.236
APB as of January 2006 |  |  | May 2004 |  |  |  |  | 547.2 |  |  |  |  | 424.45 |  |  |  | 502.925 |  |  | 400
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A
Prior APB |  |  | May 2004 |  |  |  |  | 547.2 |  |  |  |  | 424.45 |  |  |  | 502.925 |  |  | 400
Current APB |  |  | Apr 2011 |  |  |  |  | 582.018 |  |  |  |  | 535.268 |  |  |  | 680.705 |  |  | 636.236
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 594.162 |  |  |  |  | 521.857 |  |  |  | 682.572 |  |  | 614.487
Current Estimate |  |  | Dec 2015 |  |  |  |  | 597.97 |  |  |  |  | 529.742 |  |  |  | 722.518 |  |  | 657.121
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [16 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng |  | Est |  | Oth |  |  |  | Spt | Total
680.705 65.482 4.933 27.698 55.100 -111.400 0.000 0.000 41.813 722.518
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [16 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch |  | Eng |  | Est |  | Oth |  |  | Spt | Total
636.236 68.153 -12.363 32.482 42.826 -110.213 0.000 0.000 20.885 657.121

## Table 36
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | May 2004 | May 2004 | N/A | May 2004
Milestone B | Jan 2007 | Feb 2011 | N/A | Feb 2011
Milestone C | Dec 2010 | Jan 2012 | N/A | Jan 2012
IOC | Oct 2007 | Jan 2014 | N/A | Apr 2014
Total Cost (TY $M) | 1211.7 | 37438.8 | N/A | 28900.7
Total Quantity | 2 | 55 | N/A | 40
PAUC | 605.85 | 680.705 | N/A | 722.518

## Table 37
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
3481.7 33720.5 236.6 37438.8
Economic |  | 27.9 |  | 2562.9 |  | 6.8 |  | 2597.6
Quantity |  | -- |  | -16427.6 |  | -- |  | -16427.6
Schedule |  | -108.9 |  | 738.2 |  | -17.5 |  | 611.8
Engineering |  | -- |  | 157.8 |  | -- |  | 157.8
Estimating |  | -247 |  | -2317.2 |  | 28.1 |  | -2536.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -328 |  | -15285.9 |  | 17.4 |  | -15596.5
Current Changes Economic |  | -3.6 |  | 26.9 |  | -1.6 |  | 21.7
Quantity |  | -- |  | 6414.3 |  | -- |  | 6414.3
Schedule |  | -- |  | 496.1 |  | -- |  | 496.1
Engineering |  | 576.6 |  | 1469.6 |  | -- |  | 2046.2
Estimating |  | -64.1 |  | -1870.9 |  | 15.1 |  | -1919.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 508.9 |  | 6536 |  | 13.5 |  | 7058.4
Adjustments |  | -- |  | -- |  | -- |  | --
Total Changes |  | 180.9 |  | -8749.9 |  | 30.9 |  | -8538.1
Current Estimate |  | 3662.6 |  | 24970.6 |  | 267.5 |  | 28900.7

## Table 38
Summary BY 2010 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
3433.3 28369.2 208.5 32011.0
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -11562.5 |  | -- |  | -11562.5
Schedule |  | -75.8 |  | 574.5 |  | -12.5 |  | 486.2
Engineering |  | -- |  | 133.6 |  | -- |  | 133.6
Estimating |  | -213.8 |  | -1859.1 |  | 17.8 |  | -2055.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -289.6 |  | -12713.5 |  | 5.3 |  | -12997.8
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 4533.8 |  | -- |  | 4533.8
Schedule |  | -- |  | 296 |  | -- |  | 296
Engineering |  | 471.4 |  | 1062.5 |  | -- |  | 1533.9
Estimating |  | -50.6 |  | -1417.8 |  | 10.3 |  | -1458.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 420.8 |  | 4474.5 |  | 10.3 |  | 4905.6
Adjustments |  | -- |  | -- |  | -- |  | --
Total Changes |  | 131.2 |  | -8239 |  | 15.6 |  | -8092.2
Current Estimate |  | 3564.5 |  | 20130.2 |  | 224.1 |  | 23918.8
Previous Estimate: December 2014

## Table 39
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -3.6
Increased cost due to engineering support, test and evaluation, and training development requirements in support of Frigate related design enhancements (FY 2016 - FY 2027). (Engineering)
Revised estimate for LCS test and evaluation, engineering support, and training development requirements (FY 2010 - FY 2021). (Estimating)
+471.4 +576.6
-55.2 -69.1
Congressional addition in FY 2016 for LCS Training Courseware. (Estimating) +13.5 +15.0
Congressional reduction in FY 2016 to test and evaluation, system of systems engineering development, and support. (Estimating)
-10.8 -12.0
Adjustment for current and prior escalation. (Estimating) +1.9 +2.0
RDT&E Subtotal +420.8 +508.9
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A +26.9
Quantity variance resulting from an increase of 8 ships from 30 to 38. (Subtotal) +3467.8 +4873.8
Quantity variance resulting from an increase of 8 ship from 30 to 38. (Quantity) (+4186.1) (+5884.0) Allocation to Schedule resulting from Quantity change. (Schedule) (QR) (+296.0) (+416.3) Allocation to Engineering resulting from Quantity change. (Engineering) (QR) (+63.2) (+88.8) Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (-1077.5) (-1515.3)
Additional Quantity variance resulting from increased outfitting and post-delivery requirements (FY 2024 - FY 2029). (Quantity)
+347.7 +530.3
Stretch-out of procurement buy profile from FY 2018 to FY 2021. (Schedule) 0.0 +79.8
Revised estimate for current acquisition strategy and procurement profile (FY 2017 - FY 2025). (Estimating) (QR)
Increased cost due to incorporation of Frigate related enhancements to LCS baseline (FY 2021 - FY 2025). (Engineering) (QR)
Increased cost due to incorporation of Frigate related enhancements to LCS baseline (FY 2019 - FY 2021). (Engineering)
Revised estimate for realignment of Other Procurement, Navy design enhancements in LCS baseline (FY 2017 - FY 2020). (Estimating)
Congressional reduction in FY 2016 deferring habitability and safety modifications. (Estimating)
+229.0 +269.7
+714.9 +1004.3
+284.4 +376.5
-10.3 -12.3
-8.1 -9.1
Revised estimate to reflect LCS actuals. (Estimating) | -223.9 |  |  | -175.3
Revised estimate for proper pricing of outfitting and post-delivery requirements (FY 2017 - | -415.1 |  |  | -545.6
FY 2026). (Estimating)
Revised estimate for proper pricing of additional trainer and battle spare requirements (FY 2022 - FY 2025). (Estimating)
Revised estimate for proper pricing of LCS trainer and battle spare requirements (FY 2014, FY 2016 - FY 2021). (Estimating)
+89.6 +117.6
+16.5 +20.4
Adjustment for current and prior escalation. (Estimating) -18.0 -21.0
Procurement Subtotal +4474.5 +6536.0

## Table 40
(QR) Quantity Related
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -1.6
Revised estimate for proper pricing of MILCON requirements (FY 2015, FY 2021 - FY 2022). (Estimating)
+9.6 +14.4
Adjustment for current and prior escalation. (Estimating) +0.7 +0.7
MILCON Subtotal +10.3 +13.5

## Table 41
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: Construction - LCS 5
Contractor: Lockheed Martin
Contractor Location: 2323 Eastern Boulevard
Middle River, MD 21220
Contract Number: N00024-11-C-2300/1
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 29, 2010
Definitization Date: December 29, 2010
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
436.8 498.1 1 1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the execution of change order budget on the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (10/25/2015) Previous Cumulative Variances
Net Change
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to inefficiencies during the test and trials phase of ship construction.
The favorable net change in the schedule variance is due to completion of work scope in advance of trials and delivery.
Notes
USS MILWAUKEE (LCS 5) was delivered to the Navy on October 16, 2015.
Upon ship delivery the earned value (CPR) requirement is modified. The October 2015 report is the most recent CPR.
Current Contract Price ($M), Estimated Price at Completion ($M) and Cost and Schedule variance for this contract is For Official Use Only - Exempt from FOIA release under 5 U.S.C 552(b)(4).
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 42
Contract Identification
Appropriation: Procurement
Contract Name: Construction - LCS 6
Contractor: Austal USA
Contractor Location: 1 Dunlap Drive
Mobile, AL 36602
Contract Number: N00024-11-C-2301/1
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 29, 2010
Definitization Date: December 29, 2010
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
432.0 480.4 1 1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the execution of change order budget on the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date Previous Cumulative Variances Net Change
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to inefficiencies in the test and trial phase of ship construction.
The favorable net change in the schedule variance is due to completion of scope in advance of trials and delivery.
Notes
USS JACKSON (LCS 6) was delivered to the Navy on August 11, 2015.
Upon delivery the earned value (CPR) requirement is modified. The October 2015 report is the most recent CPR.
Current Contract Price ($M), Estimated Price at Completion ($M) and Cost and Schedule Variance for this contract is For Official Use Only - Exempt from FOIA release under 5 U.S.C. 552(b)(4).
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 43
Contract Identification
Appropriation: Procurement
Contract Name: Construction - LCS 7
Contractor: Lockheed Martin
Contractor Location: 2323 Eastern Boulevard
Middle River, MD 21220
Contract Number: N00024-11-C-2300/2
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: March 17, 2011
Definitization Date: March 17, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
376.6 430.4 1 1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the execution of change order budget on the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/27/2015) Previous Cumulative Variances
Net Change
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to inefficiencies during the system completion and test phase of ship construction.
The favorable net change in the schedule variance is due to completion of work scope in advance of trials.
Notes
Award date corrected from December 2014 SAR.
Current Contract Price ($M), Estimated Price at Completion ($M) and Cost and Schedule Variance for this contract is For Official Use Only - Exempt from FOIA release under 5 U.S.C. 552(b)(4).
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 44
Contract Identification
Appropriation: Procurement
Contract Name: Construction - LCS 8
Contractor: Austal USA
Contractor Location: 1 Dunlap Drive
Mobile, AL 36602
Contract Number: N00024-11-C-2301/2
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: March 17, 2011
Definitization Date: March 17, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
368.6 405.7 1 1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the execution of change order budget on the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) Previous Cumulative Variances
Net Change
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to inefficiencies during the system completion and test phase of ship construction.
The unfavorable net change in the schedule variance is due to inefficiencies during the system completion and test phase of ship construction
Notes
Current Contract Price ($M), Estimated Price at Completion ($M) and Cost and Schedule Variance for this contract is For Official Use Only - Exempt from FOIA release under 5 U.S.C. 552(b)(4).
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 45
Contract Identification
Appropriation: Procurement
Contract Name: Construction - LCS 9
Contractor: Lockheed Martin
Contractor Location: 2323 Eastern Boulevard
Middle River, MD 21220
Contract Number: N00024-11-C-2300/3
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: March 16, 2012
Definitization Date: March 16, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
363.6 416.2 1 1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the execution of change order budget on the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/27/2015) Previous Cumulative Variances
Net Change
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to inefficiencies in the production completion and test phase of construction.
The favorable net change in the schedule variance is due to increased manning levels to support launch and the production completion phase of ship construction.
Notes
Current Contract Price ($M), Estimated Price at Completion ($M) and Cost and Schedule Variance for this contract is For Official Use Only - Exempt from FOIA release under 5 U.S.C. 552(b)(4).

## Table 46
Contract Identification
Appropriation: Procurement
Contract Name: Construction - LCS 10
Contractor: Austal USA
Contractor Location: 1 Dunlap Drive
Mobile, AL 36610-1703
Contract Number: N00024-11-C-2301/3
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: March 16, 2012
Definitization Date: March 16, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
348.8 383.7 1 1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the execution of change order budget on the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date Previous Cumulative Variances Net Change
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to inefficiencies in the production completion and test phase of construction.
The unfavorable net change in the schedule variance is due to reduced manning levels in the production completion and test phase of construction.
Notes
Current Contract Price ($M), Estimated Price at Completion ($M) and Cost and Schedule Variance for this contract is For Official Use Only - Exempt from FOIA release under 5 U.S.C. 552(b)(4).
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 47
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 2 | 2 | 2 | 100%
Production | 5 | 4 | 38 | 10.53%
Total Program Quantity Delivered | 7 | 6 | 40 | 15%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
28900.7
9508.5
32.9%
27
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
14
51.85%
15540.3
53.77%
The above data is current as of February 04, 2016.

## Table 48
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 01, 2016
Source of Estimate: POE
Quantity to Sustain: 40
Unit of Measure: Ship
Service Life per Unit: 25.00 Years
Fiscal Years in Service: FY 2009 - FY 2053
Costs are incurred in preparation for and after the fielding of each LCS Seaframe. O&S cost estimate assumes:
a) Crews:
44 LCS crews: 50 personnel (8 Officers, 42 Enlisted)
17 Frigate crews: 100 personnel (12 Officers, 88 Enlisted)
b) Steaming hours underway/not underway: LCS - 4421 underway/718 not underway Frigate - 4583 underway/273 not underway
c) Defense Logistics Agency Acquisition Price of Fuel (CY 2010) $112.56/barrel
d) Government Furnished Equipment and Contractor Furnished Equipment systems are based on the configuration decisions made during ship design and construction
e) Reflects 29 LCS and 11 Frigate program consistent with PB 2017
Sustainment Strategy
The PEO LCS Fleet Introduction and Sustainment branch is responsible for the operation, maintenance, and support of the LCS Seaframe systems.
Sustainment execution includes maintenance execution planning, planned and emergent maintenance; planning for scheduled availabilities, facilities maintenance; fly-away support; modernization and engineering support services of LCS ships homeported in San Diego, California, Mayport, Florida, and deploying worldwide. Full transition to In-Service sustainment under a Product Support Plan will occur in FY 2016.
Antecedent Information
The LCS Seaframe program does not have an antecedent system. LCS was envisioned to fill a role in operations satisfying identified capability gaps. The LCS Seaframe fills a void where no system exists.
LCS is a focused-mission, modular, surface combatant. LCS is smaller than a Frigate (FFG) but larger than a Patrol Costal (PC) ship or Mine Countermeasures (MCM) ship. A LCS Seaframe with an embarked Mission Package (MP) allows the Navy to conduct most missions currently performed by a PC, MCM, or FFG, dependent on which MP is embarked. While parts of each of these platforms are potentially analogous, none are truly comparable.
LCS are minimally manned, and shore support is required to manage some functions traditionally assigned to ship’s

## Table 49
force. Shore personnel are required to support LCS administrative functions, supply support, training, and ship specific preventive maintenance. Additionally, the LCS concept of operations and fleet requirements call for greater deployed time than other ship classes, allowed by rotational crewing. While the LCS provides the Fleet some of the capabilities currently provided by the FFG, PC and MCM classes; the LCS Seaframe cannot be compared to any one class discretely.
Today, the LCS Seaframe plus one embarked MP is designed to enhance the Fleet's current anti-submarine capabilities, exceed current Fleet MCM capabilities, and fulfill current surface warfare capability gaps. The associated mission capabilities provided by the MPs are managed and reported by other program offices. As an example; for the MCM MP, the separate reportable programs would include: Remote Minehunting System, unmanned aerial and underwater vehicles, airborne laser mine detection, mine neutralization systems, MH-60S, various support equipment, and crew detachments.
The LCS Seaframe’s organic mission capability cannot be directly compared on a cost by cost basis to any other current ship program due to operational and mission capability differences as well as how costs are captured and reported.
Annual O&S Costs BY2010 $M
Cost Element |  | LCS Average Annual Cost Per Ship |  |  |  | No Antecedent (Antecedent)
Unit-Level Manpower |  | 10.783 |  |  |  | --
Unit Operations |  | 9.99 |  |  |  | --
Maintenance |  | 17.814 |  |  |  | --
Sustaining Support |  | 5.052 |  |  |  | --
Continuing System Improvements |  | 6.516 |  |  |  | --
Indirect Support |  | 5.151 |  |  |  | --
Other |  | -- |  |  |  | --
Total |  | 55.306 |  |  |  | --
Unitized cost estimate reflects the weighted average for a 40 ship (29 LCS / 11 Frigate) program.
Item | Total O&S Cost $M
| LCS | [5 empty] | No Antecedent (Antecedent)
| Current Development APB Objective/Threshold |  |  | Current Estimate
Base Year | 50479 |  | 55526.9 |  | 55305.7 |  | 0
Then Year | 87089.3 |  | N/A |  | 82435.5 |  | N/A
Disposal Cost is included in the Operating and Support Cost of the current APB objective and threshold for this program.
Current Development APB is for 55 LCS. The O&S cost estimate reflects the current estimate for a 40 ship (29 LCS / 11 Frigate) program.
Equation to Translate Annual Cost to Total Cost
Total O&S Cost = Average Annual Cost per Ship * Number of Ships * Service Life per Ship Total O&S Cost = $55.306M * 40 * 25 = $55,306M
Average annual cost per ship is a weighted average of the O&S costs for the LCS and Frigate.

## Table 50
O&S Cost Variance
Category | BY 2010 $M | Change Explanations
Prior SAR Total O&S Estimates - Dec 2015 SAR
39796
Programmatic/Planning Factors 15696.4 Updated Ship Building Profile; based on Revised Quantity;
Production Schedule; Updated Crew Phasing Profile; Increased Ship Capabilities
Cost Estimating Methodology 0.0
Cost Data Update -1059.9 Updated Visibility And Management of Operating and Support Costs, Manpower cost Estimating Tool for Enhanced Online Reporting, Space and Naval Warfare Systems Command data
Labor Rate 0.0
Energy Rate 0.0
Technical Input 873.2 Updated OPNAV 4700 and updated Other Restricted Availability/Technical Availability, Emergent Restricted Availability/Technical Availability, and 2S COG requirements
Other 0.0
Total Changes 15509.7
Current Estimate 55305.7
Disposal Estimate Details
Date of Estimate: January 01, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2010 $M): Total costs for disposal of all Ship are 152.1
The disposal cost increase for the program is driven by the quantity increase of eleven Frigates from the 2014 SAR, a reduction of three LCS, and higher disposal cost for the Frigate. The increased Frigate disposal cost is driven by increased organic capability.