## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-560
Joint Primary Aircraft Training System (JPATS)
As of December 31, 2012
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 4
Executive Summary |  | 5
Threshold Breaches |  | 7
Schedule |  | 8
Performance |  | 9
Track To Budget |  | 11
Cost and Funding |  | 13
Low Rate Initial Production |  | 31
Foreign Military Sales |  | 32
Nuclear Cost |  | 32
Unit Cost |  | 33
Cost Variance |  | 36
Contracts |  | 40
Deliveries and Expenditures |  | 42
Operating and Support Cost |  | 43

## Table 3
Program Information
Program Name
Joint Primary Aircraft Training System (JPATS)
DoD Component
Air Force
Joint Participants
United States Air Force; United States Navy
Responsible Office
Responsible Office
Mr. Stephen G. Henrich Building 11A Room 204.10 1970 Monahan Way
Wright-Patterson Air Force Base, OH 45433-7211
Phone Fax
DSN Phone DSN Fax
937-255-0817
937-656-7201
785-0817
--
stephen.henrich@wpafb.af.mil Date Assigned February 15, 2011
References
SAR Baseline (Production Estimate)
Air Force Acquisition Executive (AFAE) Approved Acquisition Program Baseline (APB) dated February 28, 2002
Approved APB
Air Force Acquisition Executive (AFAE) Approved Acquisition Program Baseline (APB) dated September 26, 2007

## Table 4
Mission and Description
The Joint Primary Aircraft Training System (JPATS) is a United States Air Force (USAF)/United States Navy (USN)/United States Army (USA) program to replace USAF's T-37B aircraft, USN's T-34C aircraft, and the associated Ground Based Training Systems (GBTS); and add four T-6B aircraft with hardpoint wings for the Army Test and Evaluation Command mission requirements. The Air Force and Navy aircraft and GBTS are being used to train entry-level students in the fundamentals of flying so they can transition into advanced training tracks leading to rated qualification. The Army aircraft will be used as chase assets for test and evaluation missions.
The program represents a systems approach to aviator training requiring the purchase of air vehicles (750 production units), aircrew training devices (126), associated ground based training devices, an integrated training management system (TIMS), instructional courseware, as well as the entire logistics and sustainment of the training system which includes contractor logistics support (CLS).
The USAF will train at six bases and the USN at three bases. Each operational training location will be equipped with a full complement of operational flight trainers, instrument flight trainers, unit training devices and egress training devices. Courseware has been developed for the T-6A and converted from existing courseware for other platforms where appropriate. The TIMS will provide a training and scheduling management capability which will tie the efforts and activities of all Air Education and Training Command (AETC) and Chief of Naval Air Training operating locations together. The Army is planning on locating aircraft at two locations in support of test flights.
The USAF will have CLS for most of the off-aircraft equipment maintenance. The on-aircraft equipment maintenance will be performed by third party contractor or organically supported. The USN will employ total CLS for the entire aircraft. The GBTS will be a total CLS effort for both services.

## Table 5
Executive Summary
JPATS continued to meet mission requirements of the Air Force’s Air Education and Training Command and the Chief of Naval Air Training through delivery and sustainment of T-6 aircraft and Ground Based Training Systems (GBTS). In 2012 performance of this mission was significantly characterized by the prime contractor’s bankruptcy filing and transition to a Contractor Operated and Maintained Base Supply (COMBS) contractor.
Significant events in 2012 included: Lot 18 (36 a/c) contract award; Hawker Beechcraft Company (HBC) Chapter 11 Bankruptcy filing; COMBS source selection and transition to a new contractor, DynCorp International (DCI); delivery of initial aircraft to Naval Air Station, Corpus Christi, Texas; acquisition planning and inclusion for procurement of four Army T-6B variants; resolution of the ejection seat cartridge obsolescence issue; redesign of the flight control stick, and significant progress toward improving the flight control system.
In January 2012 JPATS awarded production of Lot 18 aircraft. This contract award followed an FY 2011 Congressional Mark of 38 aircraft. Hawker Beechcraft Defense Corporation (HBDC) continued production at risk and extended FY 2011 pricing into FY 2012. This allowed the government to order the planned FY 2012 lot buy of 36 aircraft without repricing and maintained the existing production schedule but placed HBDC at financial risk (est.
$100M termination liability) for 10-12 months of long-lead parts. The 38 marked aircraft were restored in FY 2013 and FY 2014. HBDC submitted an updated proposal for Lots 19 and 20 in March 2012. HBDC incurred risks associated with long-lead parts for these final T-6B lots throughout 2012.
On May 3, 2012 HBC (parent of HBDC) filed for Chapter 11 Bankruptcy protection and received court approval to conduct “ordinary course of business” operations. In June, following a three week production line shutdown, HBDC resumed production of Lot 17 aircraft. The company’s reorganization plan was approved by the bankruptcy court in October 2012 and HBC emerged from bankruptcy in February 2013. The JPATS program office continues to proceed with due diligence on business actions, to include negotiating Lots 19 and 20 aircraft, and sustaining engineering and program management support contracts. In 2012, the program office continued procurement actions with HBDC on a limited basis. Lack of a Forward Pricing Rate Agreement coupled with HBDC’s financial instability significantly hindered contracting efforts. Defense Contractor Auditing Agency (DCAA) completed audit of the Lot 19 and 20 proposal in October 2012 and Defense Contractor Management Agency provided an updated Forward Pricing Rate Recommendation in December 2012. JPATS entered negotiations on Lots 19 and 20 (final lots) in December 2012. Entering 2013 HBDC is eight (8) aircraft ahead of the Lot 18 contract production schedule.
In 2012, JPATS received an Acquisition Decision Memorandum for procurement of four (4) U.S. Army T-6B variants anticipated to deliver in 2014 and 2015. These airplanes will replace T-34 C aircraft fulfilling Army Test and Evaluation Command mission requirements and are planned to be contracted with Lots 19 and 20.
JPATS continues to meet mission requirements of Air Force and Navy training commands though 2012, but aircraft readiness declined in both services due to increased Not Mission Capable due to Supply (NMCS) rates following source selection of a new COMBS contractor, DynCorp International (DCI) in June 2012. In the period following contract award, it was discovered that the previous COMBS provider had not ordered sufficient quantities of consumable, time change, and long-lead parts up through the contract period of performance. This created a supply chain deficit, which though aggressively addressed by the new vendor, will impact the fleet through most of 2013, with slow improvement evident at the close of 2012. In addition to NMCS issues, sustainment funding requirements shortfalls continue to impact engine overhaul and repair functions increasing risk to meeting aircrew production requirements. Cost savings afforded by the new COMBS contract allowed the program to buy back some engine and all of the propeller and landing gear overhauls in 2012. Current Weapon System Sustainment reductions in FY 2013 allow for funding of 3 engine overhauls out of a total 54 required in FY 2013. Cumulative unfunded engine overhauls are projected to total 108 by the end of FY 2014.

## Table 6
In July of 2012, the Navy accepted delivery of the first two aircraft designated for NAS Corpus Christi. These aircraft will facilitate initial flight instructor and maintenance training and are significant to meeting the Initial Operational Capability (IOC) milestone established for February 2013.
Throughout 2012, the program office took continued steps to mitigate ejection seat propellant cartridge shortages caused by lot acceptance test failures in November 2010; a new design was completed. The redesign effort of the primary cartridge, originally scheduled for completion in August 2011 was expanded to include the secondary cartridge, due to primary cartridge technical challenges. Requalification was completed in November 2012 and the first new cartridges were delivered to the production line in December 2012. As these cartridges are procured in quantity, this significant sustainment issue will close.
On September 13, 2011, a Sheppard AFB aircraft experienced an in-flight emergency caused by the fracture of the aft stick control assembly housing, resulting in loss of aileron control in the front cockpit and loss of pitch control in the aft cockpit; All Navy/Air Force aircraft were grounded until they successfully passed inspection. By November 2012 a machined design had been validated and cut into production. The new machined control stick lever design will replace cast control sticks on fielded aircraft; contract award for this effort will occur in June 2013.
During a November 2012 training flight at NAS Pensacola the right hand aft rudder pedal became separated from its mounting and the rudder controls froze in a neutral position. Post flight inspection revealed that the inboard retaining clip had dislodged. Following fleet inspections, additional engineering analysis is being conducted to determine whether a redesign is warranted. In November 2012 the System Program Manager initiated independent review team to conduct a thorough evaluation of the T-6 flight control system to find areas where design improvements may be required.
There are no significant software-related issues with this program at this time.

## Table 7
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 8
Schedule
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
Milestone 0/I | JAN 1993 | JAN 1993 | JUL 1993 | JAN 1993
Milestone II | AUG 1995 | AUG 1995 | AUG 1995 | AUG 1995
Aircraft Critical Design Review (CDR) | JUN 1996 | JUN 1996 | DEC 1996 | NOV 1996
Start MOT&E | APR 2000 | APR 2000 | OCT 2000 | JUN 2000
Milestone III | NOV 2001 | NOV 2001 | MAY 2002 | DEC 2001
AF Req'd Asset Availability | JUN 2002 | JUN 2002 | DEC 2002 | JUN 2002
Navy Req'd Asset Availability | AUG 2003 | AUG 2003 | FEB 2004 | AUG 2003
Acronyms And Abbreviations
AF - Air Force
MOT&E - Multi-Service Operational Test and Evaluation Req'd - Required
Change Explanations
None

## Table 9
Performance
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Syllabus Maneuvers Mission Profiles (Contact, Familiarization, Precision Aerobatics, Instrument, and Navigation -High and Low) | Accomplish all five mission profiles | Accomplish all five mission profiles | Accomplish all five mission profiles | Demon- strated all five mission profiles | Demonstrat- ed all five mission profiles
Sustained Speed at 1000 ft MSL, hot day (KTAS) | 270 | 270 | 250 (270 Dash) | 250 (270 Dash) | 250 (270 Dash)
Operational G Envelope (Gs) | +7 to -3 symmetric | +7 to -3 symmetric | +6 to -3 symmetric; +4 to 0 asymmetric | +7 to -3.5 symmetric +4.0 to 0 asymmetric | +7 to -3.5 symmetric +4.0 to 0 asymmetric
Pressurization (PSI Differential) | 5 | 5 | 3.5 | 3.5 | 3.5
Bird Strike Capability (4 lb bird, no catastropic damage) (KTAS) | Max Low Level Airspeed | Max Low Level Airspeed | 270 | 270 | 270
Ejection Seat with Survival Kit (Altitude/Airspeed in Knots) | 0/0 | 0/0 | 0/60 | 0/0 | 0/0
Able To Perform an Engine Out Landing | Unprepared surface | Unprepared surface | Runway | Runway | Runway
Anthropometric Accommodation (Sitting Height in inches) | 31.0 to 40.0 | 31.0 to 40.0 | 32.8 to 40.0 | 31.0 to 40.0 | 31.0 to 40.0
Cockpit Configuration | Interchange- able Instructor/ Student | Interchange- able Instructor/ Student | Yes | Interchange- able Instructor/Stu- den | Interchange- able Instructor/Stu- dent
Cockpit Seating Configuration | 0 Degree Over-the- Nose Visibility from the Rear Cockpit at Design Eye Height | 0 Degree Over-the- Nose Visibility from the Rear Cockpit at Design Eye Height | Stepped Tandem | Stepped Tandem | Stepped Tandem

## Table 10
Exterior Noise | FAR Part 36, Most Restrictive Applicable Standard | FAR Part 36, Most Restrictive Applicable Standard | FAR Part 36, Most Restrictive Applicable Standard | FAR Part 36, Most Restrictive Applicable Standard | FAR Part 36, Most Restrictive Applicable Standard
Takeoffs/Touch & Go/Land (Wx, Weight, Configuration) at Main Operating Bases (Runway Length - FT) | 4000 | 4000 | 5000 | 4000 | 4000
IFR Certified Instrumentation | All Digital except Backups | All Digital except Backups | IFR Certified (Selectable EADI/EHSI) | IFR Certified (Select-able EADI/EHSI) | IFR Certified (Select-able EADI/EHSI)
Visual System For IFT/OFT | Yes | Yes | Provide a visual field of view commens- urate with the JPPT syllabus training requirements | Provide a visual field of view commens- urate with the JPPT syllabus training requirements | Provide a visual field of view commens- urate with the JPPT syllabus training requirements
Requirements Source: Operational Requirements Document (ORD) 005-88-III dated April 1, 2000
Acronyms And Abbreviations
EADI - Electronic Attitude/Directional Indicator EHSI - Electronic Horizontal Situation Indicator FAR - Federal Aviation Regulation
FT - Feet
G - Gravitational Acceleration IFR - Instrument Flight Rules IFT - Instrument Flight Trainer
JPPT - Joint Primary Pilot Training KTAS - Knots True Airspeed
lb - Pound
MSL - Mean Sea Level
OFT - Operational Flight Trainer PSI - Pounds Per Square Inch Wx - Weather
Change Explanations
None
Memo
Demonstrated performance for JPATS meets all Key Performance Parameters.

## Table 11
Track To Budget
RDT&E
APPN 1319 | BA 05 | PE 0603208N | (Navy)
|  | Training System Aircraft |  | (Sunk)
APPN 3600 | BA 05 | PE 0604233F | (Air Force)
| Project 4102 | Specialized Undergraduate Pilot Training | (Shared)
Procurement
APPN 1506 | BA 03 | PE 0804745N | (Navy)
| ICN 033900 | Undergraduate Pilot Training
APPN 1506 | BA 05 | PE 0804745N | (Navy)
| ICN 057100 | Undergraduate Pilot Training
APPN 1506 | BA 06 | PE 0804745N | (Navy)
| ICN 060500 | Undergraduate Pilot Training | (Shared)
APPN 2031 | BA 01 | PE 0210100A | (Army)
| ICN A11300 | Utility F/W Aircraft | (Shared)
APPN 3010 | BA 06 | PE 0804740F | (Air Force)
| ICN 000999 | T-6 | (Shared)
APPN 3010 | BA 05 | PE 0804740F | (Air Force)
| ICN JPAT00 | AETC Aircraft Systems Modification | (Shared)
APPN 3010 | BA 07 | PE 0804740F | (Air Force)
| ICN JPATP0 | T-6 |  | (Sunk)

## Table 12
APPN 3010 | BA 03 ICN JPATS0 | PE 0804740F New AETC Aircraft Systems | (Air Force) (Sunk)
MILCON
APPN 1205 |  | PE 0212176N | (Navy)
| Project N1000203 (Sunk) Project N1000205 (Sunk) | Operational Facilities for T-6 T-6 Outlying Landing Field
APPN 1205 |  | PE 0805796N | (Navy)
| (Sunk) | Base Operations, Training
APPN 3300 |  | PE 0804741F | (Air Force)
| (Sunk) | Undergraduate Pilot Training
| Project 05000212 (Sunk) Project 06VNVP01 (Sunk) | Columbus T-6 Parts Warehouse T-6 Combs Warehouse

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
|  | BY2002 $M | [6 empty] | BY2002 $M
Appropriation |  | SAR Baseline Prod Est |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate
TY $M
SAR Baseline Prod Est | Current APB Production Objective |  |  | Current Estimate
RDT&E |  | 289.2 |  |  |  | 302.4 |  | 332.6 |  | 308.7 |  | 275.5 | 293.3 | 301.3
Procurement |  | 4177.1 |  |  |  | 4512.4 |  | 4963.6 |  | 4322.5 |  | 4699.2 | 5139 | 4889.4
Flyaway |  | 3277.3 |  |  |  | -- |  | -- |  | 3463.1 |  | 3700.1 | -- | 3928.4
Recurring |  | 3250.4 |  |  |  | -- |  | -- |  | 3406.7 |  | 3666.2 | -- | 3856.6
Non Recurring |  | 26.9 |  |  |  | -- |  | -- |  | 56.4 |  | 33.9 | -- | 71.8
Support |  | 899.8 |  |  |  | -- |  | -- |  | 859.4 |  | 999.1 | -- | 961
Other Support |  | 776.6 |  |  |  | -- |  | -- |  | 632.5 |  | 860.7 | -- | 712.2
Initial Spares |  | 123.2 |  |  |  | -- |  | -- |  | 226.9 |  | 138.4 | -- | 248.8
MILCON |  | 62.7 |  |  |  | 103.8 |  | 114.2 |  | 95.8 |  | 66.4 | 120.5 | 110.5
Acq O&M |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Total |  | 4529 |  |  |  | 4918.6 |  | N/A |  | 4727 |  | 5041.1 | 5552.8 | 5301.2
Quantity |  |  | SAR Baseline Prod Est |  |  |  | Current APB Production |  |  |  | Current Estimate
RDT&E |  |  | 1 |  |  |  | 1 |  |  |  | 1
Procurement |  |  | 782 |  |  |  | 767 |  |  |  | 751
Total |  |  | 783 |  |  |  | 768 |  |  |  | 752

## Table 14
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2014 President's Budget / December 2012 SAR (TY$ M)
RDT&E | 291.4 |  |  | 2.3 |  |  | 2.3 |  |  |  | 2.7 |  | 2.6 |  |  | 0 |  |  | 0 |  |  | 0 |  | 301.3
Procurement | 4229.7 |  |  | 319.6 |  |  | 274 |  |  |  | 33.1 |  | 16.8 |  |  | 16.2 |  |  | 0 |  |  | 0 |  | 4889.4
MILCON | 110.5 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 110.5
Acq O&M | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
PB 2014 Total | 4631.6 |  |  | 321.9 |  |  | 276.3 |  |  |  | 35.8 |  | 19.4 |  |  | 16.2 |  |  | 0 |  |  | 0 |  | 5301.2
PB 2013 Total | 4659.7 |  |  | 305.6 |  |  | 316.8 |  |  |  | 33.2 |  | 17.9 |  |  | 2.7 |  |  | 0 |  |  | 0 |  | 5335.9
Delta | -28.1 |  |  | 16.3 |  |  | -40.5 |  |  |  | 2.6 |  | 1.5 |  |  | 13.5 |  |  | 0 |  |  | 0 |  | -34.7
The FY 2011 Defense Appropriations Bill marked all 38 Navy aircraft in FY 2011. The 2014 Presidents Budget procures the remaining 29 aircraft (other 9 aircraft procured in FY 2013) to restore the Navy program of record of 295 aircraft. This includes a reduction of 2 aircraft in FY 2014 to adjust for an anticipated but unrealized loss of 2 aircraft in FY 2012. The addition of 2 Army aircraft in FY 2014 results in a net zero quantity change in FY 2014.
May 2012 Acquisition Decision Memorandum added 4 Army Aircraft in the JPATS program (2 FY 2013/2 FY 2014) to be delivered in FY 2014. Full reporting for the Army aircraft and funding begins with the December 2012 Selected Acquisition Report.
Program funding and production quantities listed in this SAR are consistent with the FY 2014 President's Budget (PB). The FY 2014 PB did not reflect the enacted DoD appropriation for FY 2013, nor sequestration; it reflected the President's requested amounts for FY 2013.
Appropriation |  | Prior | FY2013 |  |  | FY2014 |  |  | FY2015 |  |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  |  | To Complete |  | Total
Quantity | Undistributed |  |  |  | Prior |  |  | FY2013 |  | FY2014 |  | FY2015 |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  | To Complete |  |  | Total
Development | 1 |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 1
Production | 0 |  |  |  | 685 |  |  | 35 |  | 31 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 751
PB 2014 Total | 1 |  |  |  | 685 |  |  | 35 |  | 31 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 752
PB 2013 Total | 1 |  |  |  | 685 |  |  | 33 |  | 31 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 750
Delta | 0 |  |  |  | 0 |  |  | 2 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 2

## Table 15
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1994 | -- | -- | -- | -- | -- | -- | 3.6
1995 | -- | -- | -- | -- | -- | -- | 3.7
1996 | -- | -- | -- | -- | -- | -- | 1.1
1997 | -- | -- | -- | -- | -- | -- | 1.7
1998 | -- | -- | -- | -- | -- | -- | 0.3
1999 | -- | -- | -- | -- | -- | -- | 0.6
2000 | -- | -- | -- | -- | -- | -- | 0.3
Subtotal | -- | -- | -- | -- | -- | -- | 11.3

## Table 16
Annual Funding BY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1994 | -- | -- | -- | -- | -- | -- | 4
1995 | -- | -- | -- | -- | -- | -- | 4
1996 | -- | -- | -- | -- | -- | -- | 1.2
1997 | -- | -- | -- | -- | -- | -- | 1.8
1998 | -- | -- | -- | -- | -- | -- | 0.3
1999 | -- | -- | -- | -- | -- | -- | 0.6
2000 | -- | -- | -- | -- | -- | -- | 0.3
Subtotal | -- | -- | -- | -- | -- | -- | 12.2

## Table 17
Annual Funding TY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1992 | -- | -- | -- | -- | -- | -- | 0.9
1993 | -- | -- | -- | -- | -- | -- | 1.9
1994 | -- | -- | -- | -- | -- | -- | 2.6
1995 | -- | -- | -- | -- | -- | -- | 35.4
1996 | -- | -- | -- | -- | -- | -- | 27.1
1997 | -- | -- | -- | -- | -- | -- | 40.9
1998 | -- | -- | -- | -- | -- | -- | 49.4
1999 | -- | -- | -- | -- | -- | -- | 38.3
2000 | -- | -- | -- | -- | -- | -- | 36.4
2001 | -- | -- | -- | -- | -- | -- | 23.8
2002 | -- | -- | -- | -- | -- | -- | 1.8
2003 | -- | -- | -- | -- | -- | -- | 1.8
2004 | -- | -- | -- | -- | -- | -- | 1.8
2005 | -- | -- | -- | -- | -- | -- | 1.6
2006 | -- | -- | -- | -- | -- | -- | 1.6
2007 | -- | -- | -- | -- | -- | -- | 2.5
2008 | -- | -- | -- | -- | -- | -- | 2
2009 | -- | -- | -- | -- | -- | -- | 2.2
2010 | -- | -- | -- | -- | -- | -- | 1.4
2011 | -- | -- | -- | -- | -- | -- | 2.1
2012 | -- | -- | -- | -- | -- | -- | 4.6
2013 | -- | -- | -- | -- | -- | -- | 2.3
2014 | -- | -- | -- | -- | -- | -- | 2.3
2015 | -- | -- | -- | -- | -- | -- | 2.7
2016 | -- | -- | -- | -- | -- | -- | 2.6
Subtotal | 1 | -- | -- | -- | -- | -- | 290

## Table 18
Annual Funding BY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1992 | -- | -- | -- | -- | -- | -- | 1
1993 | -- | -- | -- | -- | -- | -- | 2.1
1994 | -- | -- | -- | -- | -- | -- | 2.9
1995 | -- | -- | -- | -- | -- | -- | 38.4
1996 | -- | -- | -- | -- | -- | -- | 28.8
1997 | -- | -- | -- | -- | -- | -- | 43
1998 | -- | -- | -- | -- | -- | -- | 51.6
1999 | -- | -- | -- | -- | -- | -- | 39.6
2000 | -- | -- | -- | -- | -- | -- | 37
2001 | -- | -- | -- | -- | -- | -- | 23.9
2002 | -- | -- | -- | -- | -- | -- | 1.8
2003 | -- | -- | -- | -- | -- | -- | 1.8
2004 | -- | -- | -- | -- | -- | -- | 1.7
2005 | -- | -- | -- | -- | -- | -- | 1.5
2006 | -- | -- | -- | -- | -- | -- | 1.4
2007 | -- | -- | -- | -- | -- | -- | 2.2
2008 | -- | -- | -- | -- | -- | -- | 1.7
2009 | -- | -- | -- | -- | -- | -- | 1.9
2010 | -- | -- | -- | -- | -- | -- | 1.2
2011 | -- | -- | -- | -- | -- | -- | 1.7
2012 | -- | -- | -- | -- | -- | -- | 3.7
2013 | -- | -- | -- | -- | -- | -- | 1.8
2014 | -- | -- | -- | -- | -- | -- | 1.8
2015 | -- | -- | -- | -- | -- | -- | 2.1
2016 | -- | -- | -- | -- | -- | -- | 1.9
Subtotal | 1 | -- | -- | -- | -- | -- | 296.5

## Table 19
Annual Funding TY$
3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1995 | 9 | 59.9 | -- | -- | 59.9 | 20.6 | 80.5
1996 | 4 | 13.7 | -- | -- | 13.7 | 1.2 | 14.9
1997 | 11 | 37.7 | -- | -- | 37.7 | 22.7 | 60.4
1998 | 22 | 65.2 | -- | -- | 65.2 | 6.7 | 71.9
1999 | 22 | 76.7 | -- | -- | 76.7 | 31.1 | 107.8
2000 | 29 | 71.7 | -- | -- | 71.7 | 35.7 | 107.4
2001 | 34 | 101.7 | -- | -- | 101.7 | 37.8 | 139.5
2002 | 40 | 178.2 | -- | -- | 178.2 | 40.8 | 219
2003 | 35 | 171 | -- | -- | 171 | 64.1 | 235.1
2004 | 52 | 220.5 | -- | -- | 220.5 | 61.7 | 282.2
2005 | 53 | 270.1 | -- | -- | 270.1 | 40.8 | 310.9
2006 | 54 | 290.6 | -- | -- | 290.6 | 43.5 | 334.1
2007 | 48 | 238.5 | -- | -- | 238.5 | 90.9 | 329.4
2008 | 39 | 208.4 | -- | -- | 208.4 | 31.7 | 240.1
2009 | -- | 7.5 | -- | -- | 7.5 | 34.2 | 41.7
2010 | -- | 17.4 | 1.3 | -- | 18.7 | 17.2 | 35.9
2011 | -- | 30.9 | 3.1 | -- | 34 | 0.5 | 34.5
2012 | -- | 12.1 | 2.6 | -- | 14.7 | 1.9 | 16.6
2013 | -- | 12.8 | 2.7 | -- | 15.5 | -- | 15.5
2014 | -- | 3.3 | 3.1 | -- | 6.4 | 0.6 | 7
2015 | -- | 11.6 | 3 | -- | 14.6 | 1 | 15.6
2016 | -- | 11.1 | 3.1 | -- | 14.2 | 0.9 | 15.1
2017 | -- | 10.4 | 3.2 | -- | 13.6 | 0.9 | 14.5
Subtotal | 452 | 2121 | 22.1 | -- | 2143.1 | 586.5 | 2729.6

## Table 20
Annual Funding BY$
3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1995 | 9 | 63.5 | -- | -- | 63.5 | 21.8 | 85.3
1996 | 4 | 14.3 | -- | -- | 14.3 | 1.3 | 15.6
1997 | 11 | 39.1 | -- | -- | 39.1 | 23.5 | 62.6
1998 | 22 | 67.1 | -- | -- | 67.1 | 6.9 | 74
1999 | 22 | 78.1 | -- | -- | 78.1 | 31.7 | 109.8
2000 | 29 | 71.9 | -- | -- | 71.9 | 35.8 | 107.7
2001 | 34 | 101 | -- | -- | 101 | 37.5 | 138.5
2002 | 40 | 174.8 | -- | -- | 174.8 | 40 | 214.8
2003 | 35 | 165 | -- | -- | 165 | 61.9 | 226.9
2004 | 52 | 207.3 | -- | -- | 207.3 | 58 | 265.3
2005 | 53 | 246.8 | -- | -- | 246.8 | 37.2 | 284
2006 | 54 | 258.6 | -- | -- | 258.6 | 38.7 | 297.3
2007 | 48 | 206.7 | -- | -- | 206.7 | 78.8 | 285.5
2008 | 39 | 177.8 | -- | -- | 177.8 | 27 | 204.8
2009 | -- | 6.3 | -- | -- | 6.3 | 28.7 | 35
2010 | -- | 14.3 | 1.1 | -- | 15.4 | 14.1 | 29.5
2011 | -- | 24.9 | 2.5 | -- | 27.4 | 0.4 | 27.8
2012 | -- | 9.6 | 2 | -- | 11.6 | 1.5 | 13.1
2013 | -- | 9.8 | 2.1 | -- | 11.9 | -- | 11.9
2014 | -- | 2.5 | 2.3 | -- | 4.8 | 0.5 | 5.3
2015 | -- | 8.6 | 2.3 | -- | 10.9 | 0.7 | 11.6
2016 | -- | 8.1 | 2.2 | -- | 10.3 | 0.7 | 11
2017 | -- | 7.4 | 2.3 | -- | 9.7 | 0.6 | 10.3
Subtotal | 452 | 1963.5 | 16.8 | -- | 1980.3 | 547.3 | 2527.6

## Table 21
Cost Quantity Information
3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
End Item
Recurring
Flyaway
Fiscal Year | Quantity | (Aligned with
Quantity)
BY 2002
$M
1995 | 9 | 65.8
1996 | 4 | 15.3
1997 | 11 | 41.9
1998 | 22 | 72.6
1999 | 22 | 83.5
2000 | 29 | 78.9
2001 | 34 | 109.2
2002 | 40 | 184.3
2003 | 35 | 174.2
2004 | 52 | 220
2005 | 53 | 258.1
2006 | 54 | 266.1
2007 | 48 | 212.6
2008 | 39 | 181
2009 | -- | --
2010 | -- | --
2011 | -- | --
2012 | -- | --
2013 | -- | --
2014 | -- | --
2015 | -- | --
2016 | -- | --
2017 | -- | --
Subtotal | 452 | 1963.5

## Table 22
Annual Funding TY$
1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2000 | 12 | 44.1 | -- | -- | 44.1 | 14.5 | 58.6
2001 | 24 | 77 | -- | -- | 77 | 3.6 | 80.6
2002 | 7 | 34.6 | -- | 0.1 | 34.7 | 4.1 | 38.8
2003 | 4 | 18.8 | -- | 0.1 | 18.9 | 10.6 | 29.5
2004 | 2 | 8.5 | -- | 0.2 | 8.7 | 14.3 | 23
2005 | 3 | 13.2 | -- | 0.2 | 13.4 | 4.7 | 18.1
2006 | 2 | 11.8 | -- | 5.5 | 17.3 | 4.8 | 22.1
2007 | 20 | 118.7 | -- | 3.8 | 122.5 | 30.2 | 152.7
2008 | 44 | 262.1 | -- | 0.1 | 262.2 | 43.6 | 305.8
2009 | 43 | 254 | -- | 2.4 | 256.4 | 47.6 | 304
2010 | 36 | 218.2 | -- | 4.6 | 222.8 | 46.8 | 269.6
2011 | -- | 1.8 | -- | 2.4 | 4.2 | 23.7 | 27.9
2012 | 36 | 194.1 | -- | 4.3 | 198.4 | 38.7 | 237.1
2013 | 33 | 241.7 | -- | 12.2 | 253.9 | 34 | 287.9
2014 | 29 | 184.3 | -- | 17.5 | 201.8 | 51.5 | 253.3
2015 | -- | 1.6 | -- | 15.9 | 17.5 | -- | 17.5
2016 | -- | 1.7 | -- | -- | 1.7 | -- | 1.7
2017 | -- | 1.7 | -- | -- | 1.7 | -- | 1.7
Subtotal | 295 | 1687.9 | -- | 69.3 | 1757.2 | 372.7 | 2129.9

## Table 23
Annual Funding BY$
1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
2000 | 12 | 44.3 | -- | -- | 44.3 | 14.6 | 58.9
2001 | 24 | 76.4 | -- | -- | 76.4 | 3.6 | 80
2002 | 7 | 33.9 | -- | 0.1 | 34 | 4 | 38
2003 | 4 | 18.1 | -- | 0.1 | 18.2 | 10.1 | 28.3
2004 | 2 | 8 | -- | 0.2 | 8.2 | 13.3 | 21.5
2005 | 3 | 12 | -- | 0.2 | 12.2 | 4.3 | 16.5
2006 | 2 | 10.5 | -- | 4.9 | 15.4 | 4.2 | 19.6
2007 | 20 | 102.8 | -- | 3.3 | 106.1 | 26.1 | 132.2
2008 | 44 | 223.5 | -- | 0.1 | 223.6 | 37.2 | 260.8
2009 | 43 | 213.6 | -- | 2 | 215.6 | 40 | 255.6
2010 | 36 | 179.4 | -- | 3.8 | 183.2 | 38.4 | 221.6
2011 | -- | 1.4 | -- | 1.9 | 3.3 | 19.1 | 22.4
2012 | 36 | 152.9 | -- | 3.4 | 156.3 | 30.4 | 186.7
2013 | 33 | 186.7 | -- | 9.4 | 196.1 | 26.3 | 222.4
2014 | 29 | 139.7 | -- | 13.3 | 153 | 39.1 | 192.1
2015 | -- | 1.2 | -- | 11.8 | 13 | -- | 13
2016 | -- | 1.2 | -- | -- | 1.2 | -- | 1.2
2017 | -- | 1.2 | -- | -- | 1.2 | -- | 1.2
Subtotal | 295 | 1406.8 | -- | 54.5 | 1461.3 | 310.7 | 1772

## Table 24
Cost Quantity Information
1506 ¦ Procurement ¦ Aircraft Procurement, Navy
End Item
Recurring
Flyaway
Fiscal Year | Quantity | (Aligned with
Quantity)
BY 2002
$M
2000 | 12 | 47
2001 | 24 | 81.7
2002 | 7 | 35.4
2003 | 4 | 18.9
2004 | 2 | 7.9
2005 | 3 | 11.5
2006 | 2 | 10.2
2007 | 20 | 104.4
2008 | 44 | 223.8
2009 | 43 | 211.2
2010 | 36 | 178.5
2011 | -- | --
2012 | 36 | 153.3
2013 | 33 | 186.2
2014 | 29 | 136.8
2015 | -- | --
2016 | -- | --
2017 | -- | --
Subtotal | 295 | 1406.8

## Table 25
Annual Funding TY$
2031 ¦ Procurement ¦ Aircraft Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2013 | 2 | 12.7 | -- | 2.5 | 15.2 | 1 | 16.2
2014 | 2 | 12.9 | -- | -- | 12.9 | 0.8 | 13.7
Subtotal | 4 | 25.6 | -- | 2.5 | 28.1 | 1.8 | 29.9

## Table 26
Annual Funding BY$
2031 ¦ Procurement ¦ Aircraft Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
2013 | 2 | 9.8 | -- | 1.9 | 11.7 | 0.8 | 12.5
2014 | 2 | 9.8 | -- | -- | 9.8 | 0.6 | 10.4
Subtotal | 4 | 19.6 | -- | 1.9 | 21.5 | 1.4 | 22.9

## Table 27
Annual Funding TY$
3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | Total Program TY $M
1998 2.5
1999 3.3
2000 3.2
2001 --
2002 --
2003 6.0
2004 2.2
2005 --
2006 3.0
Subtotal | 20.2

## Table 28
BY 2002 $M
1998 |  | 2.6
1999 |  | 3.4
2000 |  | 3.2
2001 |  | --
2002 |  | --
2003 |  | 5.7
2004 |  | 2
2005 |  | --
2006 |  | 2.6
Subtotal |  | 19.5

## Table 29
Annual Funding TY$
1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | Total Program TY $M
1998 1.4
1999 1.4
2000 5.2
2001 5.4
2002 --
2003 --
2004 --
2005 --
2006 --
2007 --
2008 23.9
2009 --
2010 23.9
2011 29.1
Subtotal | 90.3

## Table 30
Annual Funding BY$
1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | Total Program BY 2002 $M
1998 1.4
1999 1.4
2000 5.2
2001 5.4
2002 --
2003 --
2004 --
2005 --
2006 --
2007 --
2008 20.3
2009 --
2010 19.5
2011 23.1
Subtotal | 76.3

## Table 31
Low Rate Initial Production
The Current Total LRIP Quantity is more than 10% of the total production quantity due to more efficient manufacturing capability. LRIP for 108 aircraft was included in the Acquisition Decision Memorandum (ADM) dated August 9, 1995. LRIP quantity increased to 170 aircraft in ADM dated February 21, 2001.
| Initial LRIP Decision | Current Total LRIP
Approval Date | 8/9/1995 2/21/2001 108 170 ADM ADM 1996 1996 2000 2004
Approved Quantity
Reference
Start Year
End Year

## Table 32
Foreign Military Sales
The Iraq LOA was split in two to accommodate reduced Iraq funds availability.
Country | Date of Sale | Quantity | Total Cost $M | Memo
Iraq | 2009-06-23 | 7 | 100 | The Letter of Offer and Acceptance (LOA) signed June 23, 2009 is Foreign Military Sales (FMS) Case # (E4-D-SBU) using Iraq Special Forces Fund FY 2009 appropriated funds for seven T-6A aircraft. All aircraft have been delivered. Still supporting contractor logistics support.
Iraq | 2009-05-20 | 8 | 110 | The LOA signed May 20, 2009 for eight T-6A aircraft is FMS Case # (IQ-D-SAD) using Iraqi country funds. All aircraft have been delivered. Still supporting contractor logistics support.
Israel | 2008-09-11 | 20 | 153.6 | The LOA signed September 11, 2008 is FMS Case # (IS-D-SAB), all aircraft have been delivered. Letter of Request (LOR) received December 20, 2010 requesting the procurement of one additional aircraft delivered September 23, 2012 and Technical Orders.
Morocco | 2008-06-18 | 24 | 205.9 | The LOA signed June 18, 2008 is FMS Case # (MO-D-SAB) for 24 T-6C aircraft. All aircraft have been delivered. Working on addendum for Engineering Change Proposals (ECPs) and Customer Specific Technical Orders (CSTOs).
Nuclear Cost
None

## Table 33
Unit Cost
Unit Cost Report
|  | BY2002 $M | BY2002 $M
Unit Cost |  | Current UCR Baseline (SEP 2007 APB) | Current Estimate (DEC 2012 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 4918.6 |  |  | 4727
Quantity | 768 |  |  | 752
Unit Cost | 6.404 |  |  | 6.286 |  | -1.84
Average Procurement Unit Cost (APUC)
Cost | 4512.4 |  |  | 4322.5
Quantity | 767 |  |  | 751
Unit Cost | 5.883 |  |  | 5.756 |  | -2.16
|  | BY2002 $M | BY2002 $M
Unit Cost |  | Revised Original UCR Baseline (SEP 2007 APB) | Current Estimate (DEC 2012 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 4918.6 |  |  | 4727
Quantity | 768 |  |  | 752
Unit Cost | 6.404 |  |  | 6.286 |  | -1.84
Average Procurement Unit Cost (APUC)
Cost | 4512.4 |  |  | 4322.5
Quantity | 767 |  |  | 751
Unit Cost | 5.883 |  |  | 5.756 |  | -2.16

## Table 34
Unit Cost History
[12 empty] | BY2002 $M | [6 empty] | TY $M
[5 empty] | Date | [6 empty] | PAUC |  |  | APUC |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | AUG 1995 | [6 empty] | 4.439 |  |  | 3.861 |  |  |  | 5.689 |  |  |  | 5.068
APB as of January 2006 |  |  |  |  | FEB 2002 | [6 empty] | 5.784 |  |  | 5.342 |  |  |  | 6.438 |  |  |  | 6.009
Revised Original APB |  |  |  |  | SEP 2007 | [6 empty] | 6.404 |  |  | 5.883 |  |  |  | 7.23 |  |  |  | 6.7
Prior APB |  |  |  |  | FEB 2002 | [6 empty] | 5.784 |  |  | 5.342 |  |  |  | 6.438 |  |  |  | 6.009
Current APB |  |  |  |  | SEP 2007 | [6 empty] | 6.404 |  |  | 5.883 |  |  |  | 7.23 |  |  |  | 6.7
Prior Annual SAR |  |  |  |  | DEC 2011 | [6 empty] | 6.356 |  |  | 5.824 |  |  |  | 7.115 |  |  |  | 6.575
Current Estimate |  |  |  |  | DEC 2012 | [6 empty] | 6.286 |  |  | 5.756 |  |  |  | 7.049 |  |  |  | 6.511
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Dev Est | Changes | [20 empty] | PAUC Prod Est
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  |  | Oth |  |  | Spt |  |  | Total
5.689 -0.750 -0.035 -0.155 0.000 1.550 0.000 0.139 0.749 6.438
Current SAR Baseline to Current Estimate (TY $M)
PAUC Prod Est |  | Changes | [18 empty] | PAUC Current Est
|  | Econ |  | Qty |  |  | Sch | Eng |  | Est |  |  | Oth |  |  | Spt |  | Total
6.438 0.034 -0.004 0.093 0.564 -0.053 0.068 -0.091 0.611 7.049

## Table 35
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Dev Est | Changes | [12 empty] | APUC Prod Est
| Econ |  | Qty |  | Sch |  | Eng |  | Est | Oth | Spt |  | Total
5.068 -0.753 0.021 -0.151 0.000 1.680 0.000 0.144 0.941 6.009
Current SAR Baseline to Current Estimate (TY $M)
APUC Prod Est | Changes | [12 empty] | APUC Current Est
| Econ | Qty |  |  | Sch | Eng |  | Est |  | Oth | Spt |  | Total
6.009 0.032 -0.020 0.093 0.551 -0.063 0.000 -0.091 0.502 6.511
SAR Baseline History
Item/Event |  |  |  | SAR Planning Estimate (PE) |  |  |  | SAR Development Estimate (DE) |  |  |  | SAR Production Estimate (PdE) |  |  | Current Estimate
Milestone I |  |  |  | N/A |  |  |  | JAN 1993 |  |  |  | JAN 1993 |  |  | JAN 1993
Milestone II |  |  |  | N/A |  |  |  | AUG 1995 |  |  |  | AUG 1995 |  |  | AUG 1995
Milestone III |  |  |  | N/A |  |  |  | SEP 1999 |  |  |  | NOV 2001 |  |  | DEC 2001
IOC |  |  |  | N/A |  |  |  | JUN 2002 |  |  |  | JUN 2002 |  |  | JUN 2002
Total Cost (TY $M) |  |  |  | N/A |  |  |  | 4050.6 |  |  |  | 5041.1 |  |  | 5301.2
Total Quantity |  |  |  | N/A |  |  |  | 712 |  |  |  | 783 |  |  | 752
Prog. Acq. Unit Cost (PAUC) |  |  |  | N/A |  |  |  | 5.689 |  |  |  | 6.438 |  |  | 7.049
Initial Operational Capability (IOC) is equal to Air Force Required Assets Available (RAA) and occurred June 2002.
IOC is equal to United States Navy RAA and occurred August 2003.

## Table 36
Cost Variance
Summary Then Year $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 275.5 4699.2 66.4 5041.1
Previous Changes
Economic |  | 1.6 |  | 8.9 |  | -1 |  | 9.5
Quantity |  | -- |  | -162.3 |  | -- |  | -162.3
Schedule |  | -- |  | 70.1 |  | -- |  | 70.1
Engineering |  | 10.3 |  | 415.7 |  | -- |  | 426
Estimating |  | 13.4 |  | -43.2 |  | -5.9 |  | -35.7
Other |  | -- |  | -- |  | 51 |  | 51
Support |  | -- |  | -63.8 |  | -- |  | -63.8
Subtotal |  | 25.3 |  | 225.4 |  | 44.1 |  | 294.8
Current Changes Economic |  | 0.1 |  | 15.3 |  | 0.5 |  | 15.9
Quantity |  | -- |  | -39.4 |  | -- |  | -39.4
Schedule |  | -- |  | -0.4 |  | -- |  | -0.4
Engineering |  | -- |  | -2.2 |  | -- |  | -2.2
Estimating |  | 0.4 |  | -3.8 |  | -0.5 |  | -3.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -4.7 |  | -- |  | -4.7
Subtotal |  | 0.5 |  | -35.2 |  | -- |  | -34.7
Total Changes |  | 25.8 |  | 190.2 |  | 44.1 |  | 260.1
CE - Cost Variance |  | 301.3 |  | 4889.4 |  | 110.5 |  | 5301.2
CE - Cost & Funding |  | 301.3 |  | 4889.4 |  | 110.5 |  | 5301.2

## Table 37
Summary Base Year 2002 $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 289.2 4177.1 62.7 4529.0
Previous Changes
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -127.3 |  | -- |  | -127.3
Schedule |  | -- |  | 8.7 |  | -- |  | 8.7
Engineering |  | 8.9 |  | 323.6 |  | -- |  | 332.5
Estimating |  | 10.3 |  | 17.3 |  | -7.6 |  | 20
Other |  | -- |  | -- |  | 41.1 |  | 41.1
Support |  | -- |  | -37.1 |  | -- |  | -37.1
Subtotal |  | 19.2 |  | 185.2 |  | 33.5 |  | 237.9
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -30.7 |  | -- |  | -30.7
Schedule |  | -- |  | -0.3 |  | -- |  | -0.3
Engineering |  | -- |  | -1.7 |  | -- |  | -1.7
Estimating |  | 0.3 |  | -3.8 |  | -0.4 |  | -3.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -3.3 |  | -- |  | -3.3
Subtotal |  | 0.3 |  | -39.8 |  | -0.4 |  | -39.9
Total Changes |  | 19.5 |  | 145.4 |  | 33.1 |  | 198
CE - Cost Variance |  | 308.7 |  | 4322.5 |  | 95.8 |  | 4727
CE - Cost & Funding |  | 308.7 |  | 4322.5 |  | 95.8 |  | 4727
Previous Estimate: December 2011

## Table 38
RDT&E |  | $M
Current Change Explanations |  | Base Year |  | Then Year
Revised escalation indices. (Economic) |  | N/A |  | 0.1
Adjustment for current and prior escalation. (Estimating) |  | 0.3 |  | 0.4
RDT&E Subtotal |  | 0.3 |  | 0.5
Procurement |  | $M
Current Change Explanations |  | Base Year |  | Then Year
Revised escalation indices. (Economic) N/A +15.3
Total Quantity variance resulting from a decrease of 2 T-6's from 297 to 295. (Navy) (Subtotal)
Quantity variance resulting from a decrease of 2 T-6's from 297 to 295. (Navy) (Quantity) (QR)
-9.5 -12.5
(-7.7) (-10.2)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) | -0.3 |  | -0.4
Allocation to Engineering resulting from Quantity change. (Engineering) (QR) | -1.7 |  | -2.2
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) | -0.2 |  | -0.3
Additional Quantity variance due to change in estimating assumptions with the addition of Army Aircraft (Navy). (Quantity) (QR)
Quantity variance resulting from an increase of 4 T-6s from 0 to 4 (Army). (Quantity) (QR)
Total Quantity variance resulting from a decrease of 2 T-6's from 297 to 295 (Army). (Quantity) (QR)
-44.5 -57.3
+19.0 +24.8
+2.5 +3.3
Adjustment for current and prior escalation. (Estimating) |  | -6.4 |  |  | -7.9
Increase due to corrections of deficiencies in FY 2017 (Air Force). (Estimating) |  | -0.7 |  |  | -1.2
Revised estimate to reflect application of new escalation indicies (Navy). (Estimating) |  | 9 |  |  | 12.7
Decrease due to higher Navy priorities (Navy). (Estimating) |  | -5.9 |  |  | -7.7
Adjustment for current and prior escalation. (Support) |  | -1.1 |  |  | -1.5
Increase in Other Support due to site activation for Corpus Christi and increase in Aircrew Training Device support (Navy). (Support) |  | 7.5 |  |  | 9.3
Decrease in Initial Spares Requirements due to unrealized risk (Navy). (Support) |  | -11.7 |  |  | -15.2
Increase in Other Support for Army Aircraft added to program (Army). (Support) (QR) |  | 0.6 |  |  | 0.8
Increase in Initial Spares for Army Aircraft added to program (Army). (Support) (QR) Increase in Initial Spares due to correction of deficiencies in FY 2017 modifications (Air Force). (Support) |  | +0.8 +0.6 |  |  | +1.0 +0.9
Procurement Subtotal |  | -39.8 |  |  | -35.2
(QR) Quantity Related
MILCON |  | $M
Current Change Explanations |  | Base Year |  | Then Year
Revised escalation indices. (Economic) N/A +0.5

## Table 39
Adjustment for current and prior escalation. (Estimating) | -0.4 | -0.5
MILCON Subtotal | -0.4 | 0

## Table 40
Contracts
Appropriation: Procurement
Contract Name JPATS Follow-on Production Contract Lot 17
Contractor Hawker Beechcraft Defense Corporation
Contractor Location Wichita, KS 67201
Contract Number, Type FA8617-07-D-6151/17, FFP
Award Date February 18, 2011
Definitization Date March 31, 2011
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
255.9 N/A 36 255.9 N/A 36 255.9 255.9
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP contract.
Contract Comments
This contract includes both Aircrew Training Devices and Aircraft for Lot 17.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 41
Appropriation: Procurement
Contract Name JPATS Follow-on Production Contract Lot 18
Contractor Hawker Beechcraft Defense Corporation
Contractor Location Wichita, KS 67201
Contract Number, Type FA8617-07-D-6151/18, FFP
Award Date January 19, 2012
Definitization Date January 19, 2012
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
195.3 N/A 36 195.3 N/A 36 195.3 195.3
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP contract.

## Table 42
Deliveries and Expenditures
Deliveries To Date | Plan To Date |  | Actual To Date | Total Quantity |  | Percent Delivered
Development | 1 |  | 1 |  | 1 | 100%
Production | 656 |  | 663 |  | 751 | 88.28%
Total Program Quantities Delivered | 657 |  | 664 |  | 752 | 88.3%
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 5301.2 | Years Appropriated |  |  | 22
Expenditures To Date | 4341 | Percent Years Appropriated |  |  | 84.62%
Percent Expended | 81.89% | Appropriated to Date |  |  | 4953.5
Total Funding Years | 26 | Percent Appropriated |  |  | 93.44%
The above data is current as of 3/31/2013.

## Table 43
Operating and Support Cost
JPATS
Assumptions and Ground Rules
Cost Estimate Reference:
Source for operating & support (O&S) costs is the JPATS Program Office Life Cycle Cost Estimate (POE) dated January 2012. O&S cost elements are combined Air Force and Navy requirements for Air Vehicle (AV) and Ground Based Training Systems (GBTS) in Base Year 2002 dollars. The POE was derived from historical cost for the JPATS program, extrapolated to future years, and from the approved program office estimate for the AV Contractor Logistics Support (CLS) source selection.
Sustainment Strategy:
O&S costs are based on the purchase of 747 operational aircraft, 126 Aircrew Training Devices, Training Integration Management System (TIMS), development and conversion courseware, and AV CLS which will be provided by Dyncorp International LLC. GBTS CLS support is provided separately. The JPATS logistics support concept assumes that organizational, intermediate and depot support are CLS; therefore, there is no additional cost for intermediate or depot level maintenance. Useful life for the Air Force is FY2005-2035 (36 years), and FY2003-2039 for the Navy (37 years). $320.5M is the total annual cost for both the Air Force and the Navy based on an average useful life of 36.5 years. It is derived by taking the total annual cost of $11,697.8M and dividing it by the 36.5 average useful life.
Antecedent Information:
The antecedent system is the T-37 for the Air Force and the T-34 for the Navy. At the JPATS Milestone I Decision, the requirement for a Cost/Operations Effectiveness Analysis was waived due to the streamlining initiatives for pilot programs. Thus, the direct comparison to the antecedent system was not prepared. Program Authorized Aircraft of 346 T-37 aircraft was used to determine the antecedent O&S per steady state year cost per aircraft. T-37 only per steady state year antecedent costs are derived from the Air Force Total Ownership Cost (AFTOC) and the Naval Visibility and Management of Operating and Support Cost (VAMOSC) databases for the years 1996 through 2000. T-37 total O&S costs are not available.

## Table 44
Unitized O&S Costs BY2002 $K
Cost Element | JPATS average annual per aircraft | Antecedent: T-37 (AF Only) (Antecedent) per steady state year per aircraft
Unit-Level Manpower | 0.18 | 0.26
Unit Operations | 0.052 | 0.31
Maintenance | 0.095 | 0.02
Sustaining Support | 0.062 | 0.11
Continuing System Improvements | 0 | 0
Indirect Support | 0.04 | 0.2
Other | 0 | 0
Total | 0.429 | 0.9
Unitized Cost Comments:
The estimate consists of six elements. Unit Level Manpower includes the cost of military and civilian system-related personnel involved in the operation of this system. Unit Operations include the cost of fuel resources and unit level consumables. Maintenance costs for contract support include contract labor, materials, and overhead incurred in providing the logistics support required by an aircraft system, subsystem or associated support equipment.
Sustaining Support includes the cost of replacement support equipment, modification kits, sustaining engineering, software maintenance, and simulator operations for the aircraft system. Indirect Support includes the costs of personnel support for specialty training, permanent changes of station, and medical care.
$320.5M is the total annual cost for both the Air Force and the Navy. This does not include 4 Army Aircraft that were added to the JPATS program in the May 2012 Acquisition Decision Memorandum. The O&S costs associated with the Army aircraft are in development and not included in this report. $.429M is the annual per aircraft cost for the
Air Force and Navy. It is derived by taking the total O&S cost of $11,697.8, divided by the average useful life of 36.5 years, divided by 747 aircraft.

## Table 45
Total O&S Cost $M
| Current Production APB Objective/Threshold | Current Estimate
| JPATS | JPATS | Antecedent: T-37 (AF Only) (Antecedent)
Base Year | 0.0 0.0 11697.8 N/A
Then Year | 0.0 N/A 19448.8 N/A
Total O&S Costs Comments:
The $11,697.8M is the estimated cost of operating both fleets during their useful lives as reflected in the projected buy/delivery profiles at the time of the POE. There is no cost variance between this estimate and the estimate presented in the prior SAR submission.
Disposal Costs
Total O&S costs do not include the cost of disposal or demilitarization and at this time an estimate of disposal or demilitarization costs has not been developed.