## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-182
Light Utility Helicopter (LUH)
As of December 31, 2012
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 4
Executive Summary |  | 5
Threshold Breaches |  | 6
Schedule |  | 7
Performance |  | 8
Track To Budget |  | 10
Cost and Funding |  | 11
Low Rate Initial Production |  | 17
Foreign Military Sales |  | 18
Nuclear Cost |  | 18
Unit Cost |  | 19
Cost Variance |  | 22
Contracts |  | 25
Deliveries and Expenditures |  | 26
Operating and Support Cost |  | 27

## Table 3
Program Information
Program Name
Light Utility Helicopter (LUH)
DoD Component
Army
Responsible Office
Responsible Office
COL Thomas H. Todd
Utility Helicopters Project Office SFAE-AV-UH
Program Executive Office Aviation Redstone Arsenal, AL 35898-5000
Phone Fax
DSN Phone DSN Fax
256-955-8939
256-955-8109
645-8939
--
Thomas.Todd@us.army.mil Date Assigned June 29, 2011
References
SAR Baseline (Production Estimate)
Army Acquisition Executive (AAE) Approved Acquisition Program Baseline (APB) dated June 29, 2006
Approved APB
Army Acquisition Executive (AAE) Approved Acquisition Program Baseline (APB) dated August 22, 2007

## Table 4
Mission and Description
The Army currently utilizes a mix of rotary wing aircraft to accomplish a wide range of administrative and logistical missions, as well as supporting the Homeland Security (HLS) role assigned to selected units of the Army National Guard. These aircraft provide General Support (GS) at various posts, camps, and stations both in the Continental United States and Outside the Continental United States. In most instances, the aircraft now assigned to these missions have reached their serviceable life limit and must be replaced. In other cases, the aircraft used in this role are UH-60 Black Hawks, which are much more capable than required for the role and are more costly to operate and maintain. The light, GS mission requirements are satisfied by Tables of Organization and Equipment (TOE) and Tables of Distribution and Allowances (TDA) aircraft within both active and reserve components. GS TOE mission requirements include time-sensitive transport for urgently needed supplies, parts, equipment, documents, and/or personnel. The TDA light GS mission needs include observer/controller aircraft at Combat Training Centers, aircraft to provide force protection and installation security in sensitive areas (e.g., test sites, ranges, etc.), and chase/instrumentation aircraft for technical or operational testing.
The Light Utility Helicopter (LUH) UH-72A Lakota platform will provide the flexibility to respond to HLS requirements, conduct civil search and rescue operations, support test and training centers, support counterdrug operations, and perform Medical Evacuation (MEDEVAC) missions. The UH-72A Lakota will conduct GS utility helicopter missions and execute tasks as part of an integrated effort with other joint services, government agencies, and non- governmental organizations. The UH-72A Lakota is to be deployed only to non-combat, permissive environments and is to conduct primarily three missions: medical and casualty evacuations, general support, and reconnaissance and surveillance.
Crew seating is comprised of two individual longitudinally adjustable energy absorbing pilot and copilot seats with head rest and four-point safety belts with automatic locking system. The passenger seats have a four-point restraint harness with adjusters in both shoulder straps and the lap belt with a single-action, 45-degree lost-motion rotary buckle. When equipped for MEDEVAC operations to accommodate two North Atlantic Treaty Organization standard litters, passenger seating is limited to a medical attendant and a crew chief.
The aircraft is equipped with modern cockpit communication and navigation avionics required to operate with civilian airspace systems. The cockpit is arranged and lit to be compatible with night vision devices. Included in the avionics are a radar altimetry, full autopilot, and a unique First Limit Indicator, which further simplifies engine monitoring and reduces pilot workload.
The UH-72A is a Federal Aviation Administration (FAA) rotorcraft certified to the airworthiness standards of Title 14, Federal Aviation Regulations Part 29. Part 29 applies to transport category rotorcraft, which are defined as having nine or more seats and gross weights of more than 7,000 pounds.
In addition, the aircraft include provisions for MEDEVAC and hoist kits, as well as four approved modifications: Secure Communications, Cabin Temperature/Ventilation System, Engine Inlet Barrier Filter, and MEDEVAC Interior Kit (storage).
Operational Needs Statements (ONS) have also been issued that approve requirements for the following modifications: Environmental Control Unit, Very Important Personnel (VIP) Mission Kit, and Combat Training Center Mission Equipment Package.

## Table 5
Executive Summary
Since the completion of the three-phase production duplication in October 2010, American Eurocopter (AE) has been focusing on continuous improvement. AE has increased the number of quality gates by reorganizing the number of work stations, which also reduces redundancy and enhances the material flow and production process.
During 2012, UH-72A Security and Support (S&S) Mission Equipment Package (MEP) aircraft began support of
U.S. Customs and Border Protection (CBP) with advanced aerial surveillance, reconnaissance, and air mobility to detect and deter illegal activity at the U.S./Mexico border at three separate locations: Tucson, AZ, Laredo, TX, and Harlingen, TX. To date, the UH-72A aircraft have flown approximately 7,580 hours in support of the mission. The aircraft have aided in more than 26,000 apprehension assists and resulted in the confiscation of over 126,500 pounds of marijuana and 100 pounds of cocaine.
The UH-72A aircraft also continue to support the National Guard's Homeland Security mission by providing aerial surveillance and reconnaissance. A recent example of this is the support the aircraft provided during Hurricane Sandy. UH-72A also support air movement operations, civil search and rescue, counter-drug operations, Medical Evacuation (MEDEVAC), and Casulty Evacuation (CASEVAC). Fifty-four S&S MEP equipped aircraft have been fielded as of March 31, 2013, with an additional 46 planned for fielding by the end of FY 2015.
The Program Year (PY) 8 contract option was awarded on November 5, 2012, for 34 aircraft.
Current funding procures 315 aircraft; Authorized Acquisition Objective (AAO) remains unchanged at 345. Contract options remain available for procurement of aircraft through FY 2015.
Current funding limits future modifications to include: Wide Area Augmentation Systems (WAAS) for 100 aircraft and crash survivable Cockpit Voice Data Recorders (CVDR)/Flight Data Recorders (FDR) for 139 aircraft.
Two hundred and fifty-five UH-72A aircraft have been delivered as of March 31, 2013. Fifty-four aircraft have been equipped with the Engine Inlet Barrier Filter (EIBF). Seventy-eight aircraft have the MEDEVAC mission kit. Ninety- two aircraft have been outfitted with Environmental Control Units (ECU). Two hundred and twenty-nine aircraft have been equipped with secure communications. Twelve aircraft have been equipped with the Very Important Personnel (VIP) package.
This is the final SAR submission for the LUH UH-72A Lakota because the program is 90% or more expended.
There are no significant software-related issues with this program at this time.

## Table 6
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
Explanation of Breach
The Operating and Support (O&S) estimate for the Full Rate Production (FRP) Acquisition Program Baseline (APB) estimate in 2007 did not include military pay or training and was based on an expected Economic Useful Life (EUL) of 20 years. The APB is representative of ownership cost instead of true O&S cost.
The current O&S estimate includes the military pay and training of personnel, an expected EUL of 25 years, additional costs due to schedule and fielding location changes, and additional Department of the Army (DA) directed Operational Needs Statement (ONS) approved modifications support cost.
Nunn-McCurdy Breaches

## Table 7
Schedule
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
Milestone C - LRIP | JUN 2006 | JUN 2006 | DEC 2006 | JUN 2006
IOT/SLT - Start | FEB 2007 | FEB 2007 | AUG 2007 | MAR 2007
IOT/SLT - End | MAR 2007 | MAR 2007 | SEP 2007 | MAR 2007
FUE | MAR 2007 | MAR 2007 | SEP 2007 | MAY 2007
FRP Decision | MAY 2007 | JUL 2007 | JAN 2008 | AUG 2007
Acronyms And Abbreviations
FRP - Full Rate Production FUE - First Unit Equipped IOT - Initial Operational Test
LRIP - Low Rate Initial Production SLT - System Level Test
Change Explanations
None

## Table 8
Performance
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Net Ready / Voice Interoperability (KPP)% | 100% Secure Comms | 100% Secure Comms | 100% Military/Civil- ian Public Safety Comms | 100% Military/Civil- ian Public Safety Comms | 100% Military/Civil- ian Public Safety Comms
Cabin Size (KPP) | 6 Seats/ 2 NATO Litters & 1 Medical Attendant | 6 Seats/ 2 NATO Litters & 1 Medical Attendant | 6 Seats/ 2 NATO Litters & 1 Medical Attendant | 6 Seats/ 2 NATO Litters & 1 Medical Attendant | 6 Seats/ 2 NATO Litters & 1 Medical Attendant
Force Protection (KPP) | Air Warrior | Air Warrior | Air Warrior Ensemble | Air Warrior Ensemble | Air Warrior Ensemble
Survivability (KPP) | 1994 FAA STD | 1994 FAA STD | 1989 FAA STD | 1994 FAA STD | 1994 FAA STD
Performance (KPP) | HOGE at STD Day | HOGE at STD Day | HOGE at STD Day | HOGE at STD Day | HOGE at STD Day
Requirements Source: Capability Development Document (CDD) Version 9.0 dated September 30, 2005 (Joint Requirements Oversight Council Memorandum 216-06 dated October 18, 2006 accepted the CDD in lieu of a separate Capability Production Document (CPD))
Acronyms And Abbreviations
Comms - Communications
FAA - Federal Aviation Administration HOGE - Hover Out of Ground Effect NATO - North Atlantic Treaty Organization STD - Standard
Change Explanations
None
Memo
In reference to the Net Ready/Voice Interoperability KPP, the UH-72A Lakota has demonstrated and currently meets the threshold and commercial secure communication requirements. UH-72A Lakota public safety radios can be encrypted and provide commercial secure communications. A modification to integrate the ARC-231 radio into the UH-72A will provide for military secure communications.
In reference to the Force Protection KPP, the Air Warrior ensemble includes chemical protective undergarment, anti-exposure suite, primary survival gear carrier, flotation collar and survival knife with sheath. It excludes the Air Warrior MicroClimate Unit.

## Table 9
In reference to the Survivability KPP, the UH-72A platform meets the requirements of Title 14 of the Code of Federal Regulations (CFR), Part 29, Sections 561, 562, 785 and 952 as of December 31, 1994. These sections define Federal Aviation Regulations for design and qualification of seating, restraint systems, fuel systems and aircraft structure. These standards protect aircraft occupants from excessive impact loads through dissipation of crash energy via deformation of structure, flammability requirements, and retention of objects inside the aircraft to reduce the severity and occurrence of secondary impacts.
Regarding the Performance KPP, STD day is sea level pressure and altitude, and 59 degrees Fahrenheit conditions. Numerical values assigned to this KPP are 906 pounds HOGE at STD day conditions for both Threshold and Objective. Current demonstrated performance value is 1244 pounds HOGE at STD day conditions.
The UH-72A aircraft continues to perform to these KPPs and there has been no change since the December 2007 SAR.

## Table 10
Track To Budget
RDT&E
APPN 2040 BA 07 PE 0273744A (Army)
Project D16 Light Utility Helicopter (Shared) (Sunk)
Shared with the UH-60M Black Hawk Program
Procurement
APPN 2031 BA 01 (Army)
ICN A05001 Light Utility Helicopter (Shared)

## Table 11
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
|  | BY2006 $M | [6 empty] | BY2006 $M
Appropriation |  | SAR Baseline Prod Est |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate
TY $M
SAR Baseline Prod Est | Current APB Production Objective |  |  | Current Estimate
RDT&E |  | 3.2 |  |  |  | 3.2 |  | 4.2 |  | 3.2 |  | 3.1 | 3.1 | 3.1
Flyaway |  | -- |  |  |  | -- |  | -- |  | 3.2 |  | -- | -- | 3.1
Recurring |  | -- |  |  |  | -- |  | -- |  | 3.2 |  | -- | -- | 3.1
Non Recurring |  | -- |  |  |  | -- |  | -- |  | 0 |  | -- | -- | 0
Support |  | -- |  |  |  | -- |  | -- |  | 0 |  | -- | -- | 0
Procurement |  | 1635.1 |  |  |  | 1704.9 |  | 1875.4 |  | 1623.7 |  | 1879.9 | 1958.6 | 1806.2
Flyaway |  | 1564.9 |  |  |  | -- |  | -- |  | 1532.1 |  | 1798.5 | -- | 1702.3
Recurring |  | 1546 |  |  |  | -- |  | -- |  | 1513 |  | 1777.5 | -- | 1681.5
Non Recurring |  | 18.9 |  |  |  | -- |  | -- |  | 19.1 |  | 21 | -- | 20.8
Support |  | 70.2 |  |  |  | -- |  | -- |  | 91.6 |  | 81.4 | -- | 103.9
Other Support |  | 70.2 |  |  |  | -- |  | -- |  | 91.6 |  | 81.4 | -- | 103.9
Initial Spares |  | 0 |  |  |  | -- |  | -- |  | 0 |  | 0 | -- | 0
MILCON |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Acq O&M |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Total |  | 1638.3 |  |  |  | 1708.1 |  | N/A |  | 1626.9 |  | 1883 | 1961.7 | 1809.3
Quantity |  |  | SAR Baseline Prod Est |  |  |  | Current APB Production |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  | 0
Procurement |  |  | 322 |  |  |  | 322 |  |  |  | 315
Total |  |  | 322 |  |  |  | 322 |  |  |  | 315

## Table 12
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2014 President's Budget / December 2012 SAR (TY$ M)
RDT&E | 3.1 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 3.1
Procurement | 1524.3 |  |  | 201.5 |  |  | 80.4 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 1806.2
MILCON | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
PB 2014 Total | 1527.4 |  |  | 201.5 |  |  | 80.4 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 1809.3
PB 2013 Total | 1527.2 |  |  | 201.5 |  |  | 179.8 |  |  |  | 82.9 |  | 13.3 |  |  | 0 |  |  | 0 |  |  | 0 |  | 2004.7
Delta | 0.2 |  |  | 0 |  |  | -99.4 |  |  |  | -82.9 |  | -13.3 |  |  | 0 |  |  | 0 |  |  | 0 |  | -195.4
Modification costs are not included in the reported UH-72A Lakota program acquisition costs and are currently estimated at $185.4 (TY$M). Yearly breakdown of modification costs are as follows: Prior $99.3, FY 2013
$70.2, FY 2014 $15.9 (TY$M).
Current funding limits future modifications to 100 Wide Area Augmentation Systems (WAAS) and 139 Cockpit Voice Data Recorders (CVDR)/Flight Data Recorders (FDR).
Program funding and production quantities listed in this SAR are consistent with the FY 2014 President's Budget (PB). The FY 2014 PB did not reflect the enacted DoD appropriation for FY 2013, nor sequestration; it reflected the President's requested amounts for FY 2013.
Appropriation |  | Prior | FY2013 |  |  | FY2014 |  |  | FY2015 |  |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  |  | To Complete |  | Total
Quantity | Undistributed |  |  |  | Prior |  |  | FY2013 |  | FY2014 |  | FY2015 |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  | To Complete |  |  | Total
Development | 0 |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
Production | 0 |  |  |  | 271 |  |  | 34 |  | 10 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 315
PB 2014 Total | 0 |  |  |  | 271 |  |  | 34 |  | 10 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 315
PB 2013 Total | 0 |  |  |  | 271 |  |  | 34 |  | 30 |  | 10 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 345
Delta | 0 |  |  |  | 0 |  |  | 0 |  | -20 |  | -10 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | -30

## Table 13
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2004 -- -- 3.1 -- 3.1 -- 3.1
Subtotal | -- | -- | 3.1 | -- | 3.1 | -- | 3.1

## Table 14
Annual Funding BY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2006 $M | Non End Item Recurring Flyaway BY 2006 $M | Non Recurring Flyaway BY 2006 $M | Total Flyaway BY 2006 $M | Total Support BY 2006 $M | Total Program BY 2006 $M
2004 -- -- 3.2 -- 3.2 -- 3.2
Subtotal | -- | -- | 3.2 | -- | 3.2 | -- | 3.2

## Table 15
Annual Funding TY$
2031 ¦ Procurement ¦ Aircraft Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2005 | -- | -- | 2 | -- | 2 | -- | 2
2006 | 16 | 79.9 | 7 | 1 | 87.9 | 0.8 | 88.7
2007 | 26 | 123.4 | 7.4 | 3.2 | 134 | 8.6 | 142.6
2008 | 42 | 204.1 | 5.4 | 3.3 | 212.8 | 4.5 | 217.3
2009 | 44 | 218.1 | 9 | 3.1 | 230.2 | 12.1 | 242.3
2010 | 54 | 275.8 | 9.5 | 3.4 | 288.7 | 12.6 | 301.3
2011 | 50 | 262.5 | 9.8 | 3.7 | 276 | 17 | 293
2012 | 39 | 206.6 | 10.1 | 3.1 | 219.8 | 17.3 | 237.1
2013 | 34 | 178.1 | 9 | -- | 187.1 | 14.4 | 201.5
2014 | 10 | 54.8 | 9 | -- | 63.8 | 16.6 | 80.4
Subtotal | 315 | 1603.3 | 78.2 | 20.8 | 1702.3 | 103.9 | 1806.2

## Table 16
Annual Funding BY$
2031 ¦ Procurement ¦ Aircraft Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2006 $M | Non End Item Recurring Flyaway BY 2006 $M | Non Recurring Flyaway BY 2006 $M | Total Flyaway BY 2006 $M | Total Support BY 2006 $M | Total Program BY 2006 $M
2005 | -- | -- | 2 | -- | 2 | -- | 2
2006 | 16 | 77.3 | 6.8 | 1 | 85.1 | 0.8 | 85.9
2007 | 26 | 117.1 | 7 | 3 | 127.1 | 8.2 | 135.3
2008 | 42 | 190.6 | 5 | 3.1 | 198.7 | 4.2 | 202.9
2009 | 44 | 200.8 | 8.3 | 2.9 | 212 | 11.1 | 223.1
2010 | 54 | 249.4 | 8.6 | 3.1 | 261.1 | 11.4 | 272.5
2011 | 50 | 232.6 | 8.7 | 3.3 | 244.6 | 15 | 259.6
2012 | 39 | 179 | 8.7 | 2.7 | 190.4 | 15 | 205.4
2013 | 34 | 150.6 | 7.6 | -- | 158.2 | 12.2 | 170.4
2014 | 10 | 45.4 | 7.5 | -- | 52.9 | 13.7 | 66.6
Subtotal | 315 | 1442.8 | 70.2 | 19.1 | 1532.1 | 91.6 | 1623.7

## Table 17
Low Rate Initial Production
The Current Total LRIP Quantity is more than 10% of the total production quantity due to this being the minimum quantity necessary to establish an initial production base for the system and to permit an orderly increase in the production rate sufficient to lead to Full Rate Production (FRP) upon successful completion of the testing.
LRIP aircraft were procured in FY 2006 and FY 2007 and Full Rate Production (FRP) aircraft were procured in FY 2008 and beyond.
| Initial LRIP Decision | Current Total LRIP
Approval Date | 6/20/2006 6/20/2006 42 42 ADM ADM 2006 2006 2007 2007
Approved Quantity
Reference
Start Year
End Year

## Table 18
Foreign Military Sales
None
Nuclear Cost
None

## Table 19
Unit Cost
Unit Cost Report
|  | BY2006 $M | BY2006 $M
Unit Cost |  | Current UCR Baseline (AUG 2007 APB) | Current Estimate (DEC 2012 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 1708.1 |  |  | 1626.9
Quantity | 322 |  |  | 315
Unit Cost | 5.305 |  |  | 5.165 |  | -2.64
Average Procurement Unit Cost (APUC)
Cost | 1704.9 |  |  | 1623.7
Quantity | 322 |  |  | 315
Unit Cost | 5.295 |  |  | 5.155 |  | -2.64
|  | BY2006 $M | BY2006 $M
Unit Cost |  | Original UCR Baseline (JUN 2006 APB) | Current Estimate (DEC 2012 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 1638.3 |  |  | 1626.9
Quantity | 322 |  |  | 315
Unit Cost | 5.088 |  |  | 5.165 |  | 1.51
Average Procurement Unit Cost (APUC)
Cost | 1635.1 |  |  | 1623.7
Quantity | 322 |  |  | 315
Unit Cost | 5.078 |  |  | 5.155 |  | 1.52

## Table 20
Unit Cost History
[7 empty] | BY2006 $M |  |  |  |  | TY $M
|  |  | Date |  |  |  | PAUC |  | APUC |  |  | PAUC |  | APUC
Original APB |  |  | JUN 2006 |  |  |  | 5.088 |  | 5.078 |  |  | 5.848 |  | 5.838
APB as of January 2006 |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Revised Original APB |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Prior APB |  |  | JUN 2006 |  |  |  | 5.088 |  | 5.078 |  |  | 5.848 |  | 5.838
Current APB |  |  | AUG 2007 |  |  |  | 5.305 |  | 5.295 |  |  | 6.092 |  | 6.083
Prior Annual SAR |  |  | DEC 2011 |  |  |  | 5.2 |  | 5.19 |  |  | 5.811 |  | 5.802
Current Estimate |  |  | DEC 2012 |  |  |  | 5.165 |  | 5.155 |  |  | 5.744 |  | 5.734
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Prod Est | Changes | [11 empty] | PAUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
5.848 -0.083 -0.001 -0.053 0.263 -0.298 0.000 0.068 -0.104 5.744

## Table 21
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Prod Est | Changes | [9 empty] | APUC Current Est
| Econ | Qty |  | Sch | Eng | Est | Oth | Spt |  | Total
5.838 -0.083 -0.001 -0.053 0.263 -0.298 0.000 0.068 -0.104 5.734
SAR Baseline History
Item/Event |  |  | SAR Planning Estimate (PE) |  |  | SAR Development Estimate (DE) |  |  | SAR Production Estimate (PdE) |  |  | Current Estimate
Milestone A |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Milestone C |  |  | N/A |  |  | N/A |  |  | JUN 2006 |  |  | JUN 2006
FUE |  |  | N/A |  |  | N/A |  |  | MAR 2007 |  |  | MAY 2007
Total Cost (TY $M) |  |  | N/A |  |  | N/A |  |  | 1883 |  |  | 1809.3
Total Quantity |  |  | N/A |  |  | N/A |  |  | 322 |  |  | 315
Prog. Acq. Unit Cost (PAUC) |  |  | N/A |  |  | N/A |  |  | 5.848 |  |  | 5.744

## Table 22
Cost Variance
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Prod Est) | 3.1 | 1879.9 | -- | 1883
Previous Changes
Economic | -- | -34.2 | -- | -34.2
Quantity | -- | 139.3 | -- | 139.3
Schedule | -- | -17 | -- | -17
Engineering | -- | 84.9 | -- | 84.9
Estimating | -- | -86.3 | -- | -86.3
Other | -- | -- | -- | --
Support | -- | 35 | -- | 35
Subtotal | -- | 121.7 | -- | 121.7
Current Changes
Economic | -- | 8 | -- | 8
Quantity | -- | -180.3 | -- | -180.3
Schedule | -- | 0.3 | -- | 0.3
Engineering | -- | -2.1 | -- | -2.1
Estimating | -- | -7.7 | -- | -7.7
Other | -- | -- | -- | --
Support | -- | -13.6 | -- | -13.6
Subtotal | -- | -195.4 | -- | -195.4
Total Changes | -- | -73.7 | -- | -73.7
CE - Cost Variance | 3.1 | 1806.2 | -- | 1809.3
CE - Cost & Funding | 3.1 | 1806.2 | -- | 1809.3

## Table 23
Summary Base Year 2006 $M
| RDT& | E | Proc | MILCON | Total
SAR Baseline (Prod Est) Previous Changes |  | 3.2 | 1635.1 | -- | 1638.3
Economic |  | -- | -- | -- | --
Quantity |  | -- | 110.5 | -- | 110.5
Schedule |  | -- | 19.9 | -- | 19.9
Engineering |  | -- | 74.4 | -- | 74.4
Estimating |  | -- | -81.4 | -- | -81.4
Other |  | -- | -- | -- | --
Support |  | -- | 32.2 | -- | 32.2
Subtotal |  | -- | 155.6 | -- | 155.6
Current Changes Economic |  | -- | -- | -- | --
Quantity |  | -- | -148.4 | -- | -148.4
Schedule |  | -- | 0.3 | -- | 0.3
Engineering |  | -- | -1.8 | -- | -1.8
Estimating |  | -- | -6.3 | -- | -6.3
Other |  | -- | -- | -- | --
Support |  | -- | -10.8 | -- | -10.8
Subtotal |  | -- | -167 | -- | -167
Total Changes |  | -- | -11.4 | -- | -11.4
CE - Cost Variance |  | 3.2 | 1623.7 | -- | 1626.9
CE - Cost & Funding |  | 3.2 | 1623.7 | -- | 1626.9
Previous Estimate: December 2011

## Table 24
Procurement |  |  | $M
Current Change Explanations |  |  | Base Year |  | Then Year
Revised escalation indices. (Economic) N/A +8.0
Total Quantity variance resulting from a decrease of 30 UH-72A aircraft from 345 to 315, and an overall acceleration of the procurement buy profile. (Subtotal) Quantity variance resulting from a decrease of 30 helicopters from 345 to 315.
(Quantity) (QR)
-136.5 -165.9
(-137.7) (-167.2)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) |  | -0.3 |  | -0.3
Allocation to Engineering resulting from Quantity change. (Engineering) (QR) |  | -0.6 |  | -0.7
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) |  | -1.5 |  | -1.7
Additional Quantity variance related acceleration of the procurement buy profile. (Quantity) (QR)
Decrease in engineering services required due to early completion of procurement. (Engineering)
-10.7 -13.1
-1.2 -1.4
Adjustment for current and prior escalation. (Estimating) | -3.2 |  |  |  |  | -3.7
Decrease in estimate to remove recompete of contract. (Estimating) | -4.6 |  |  |  |  | -5.7
Adjustment for current and prior escalation. (Support) | -0.1 |  |  |  |  | -0.1
Decrease in Other Support for fielding and training requirements associated with the reduction in quantity. (Support) (QR)
-10.7 -13.5
Procurement Subtotal -167.0 -195.4
(QR) Quantity Related

## Table 25
Contracts
Appropriation: RDT&E
Contract Name LUH Prod & Svcs Contract
Contractor EADS North America Defense Company
Contractor Location 1616 Fort Myer Dr. Ste. 1500 Arlington, VA 22209
Contract Number, Type W58RGZ-06-C-0194, FFP
Award Date June 30, 2006
Definitization Date June 30, 2006
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
51.1 N/A 8 1757.5 N/A 305 1757.5 1757.5
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP contract.
Contract Comments
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the purchase of an additional 297 aircraft, bringing the total number of aircraft purchased to date to 305. Other items that have increased contract value include the purchase of a procedural trainer, additional hoist and MEDical EVACuation (MEDEVAC) B kits, pilot and maintainer training, additional Contractor Field Service Representative (CFSR) support, Contractor Field Team (CFT) support, engineering service efforts, and Contractor Logistics Support (CLS). Approved modifications include: cabin temperature ventilation kits, engine inlet barrier filter kits, ARC-231 radios, MEDEVAC mission kits, environmental control units, and very important personnel kits. Future modifications include: Cockpit Voice Data Recorders (CVDR) and Wide Area Augmentation Systems (WAAS).
The UH-72A Lakota production contract was awarded on June 30, 2006, for Federal Aviation Administration (FAA) certified, commercial/Non-Development Item aircraft to European Aeronautical Defense and Space Company - North America. These aircraft will be operated and maintained in accordance with FAA regulations and Original Equipment Manufacturer (OEM) procedures for the life of the system; support will be executed through life-cycle CLS (Full and/or Hybrid).
The Program Year (PY) 8 contract option was awarded on November 5, 2012, for 34 aircraft.
Current funding procures 315 aircraft; Authorized Acquisition Objective (AAO) remains unchanged at 345. Contract options remain available for procurement of aircraft through FY 2015.
The estimated price at completion reflects the value of the contract options exercised as of March 31, 2013, and includes modification procurement costs.

## Table 26
Deliveries and Expenditures
Deliveries To Date | Plan To Date |  | Actual To Date | Total Quantity |  | Percent Delivered
Development | 0 |  | 0 |  | 0 | --
Production | 255 |  | 255 |  | 315 | 80.95%
Total Program Quantities Delivered | 255 |  | 255 |  | 315 | 80.95%
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 1809.3 | Years Appropriated |  |  | 10
Expenditures To Date | 1636.1 | Percent Years Appropriated |  |  | 90.91%
Percent Expended | 90.43% | Appropriated to Date |  |  | 1728.9
Total Funding Years | 11 | Percent Appropriated |  |  | 95.56%
The above data is current as of 3/31/2013.
Planned quantity for December 31, 2012, was 242 aircraft; actual delivered quantity was 246 aircraft. Current delivered quantity as of March 31, 2013, was 255 aircraft.

## Table 27
Operating and Support Cost
LUH
Assumptions and Ground Rules
Cost Estimate Reference:
The current Lakota estimate was based on the original Army Cost Position (ACP), which was approved in May 2006 and updated in July 2007 in support of the Full Rate Production (FRP) decision. This estimate was based on an Economic Useful Life (EUL) of 20 years.
Since the last ACP in March 2011, the Program Office Estimate (POE) has been updated to incorporate the revised EUL expectancy of 25 years as identified in the April 22, 2012, memorandum from the Assistant Secretary of the Army (Acquisition, Logistics and Technology) (ASA(ALT)). The current estimate also includes fact of life changes since 2007 that include additional costs due to schedule and fielding location changes and additional Department of the Army (DA) directed Operational Needs Statement (ONS) approved modifications support cost.
Sustainment Strategy:
The Lakota is a Federal Aviation Administration (FAA) certified, Commercial/Non-Development Item (C/NDI) aircraft to be operated and maintained in accordance with FAA regulations and Original Equipment Manufacturer (OEM) procedures for the life of the system; support will be executed through life-cycle Contractor Logistics Support (CLS); the Army National Guard (ARNG) will perform only field-level maintenance with the contractor providing depot/sustainment level maintenance and all other aspects of Integrated Logistics Support (ILS) at both field and depot/sustainment levels. Hybrid CLS will be executed as a contract option. Lakota will have an expected 25-year useful life for 315 operational aircraft when fully fielded, and an average Operating Tempo (OPTEMPO) flying hour profile of 250 hours per year.
Average Annual Cost Per Aircraft is calculated based on total operational cost divided by the number of systems, then divided by the expected useful life of the system. All unit costs are in BY 2006 dollars in thousands, and the current estimate is as of December 31, 2012.
Equation: Average Annual Cost Per Aircraft * Quantity Fielded * Expected System Life = ($766.000 * 315 * 25 =
$6,032.250 BY 2006 Dollars in Thousands)
Antecedent Information:
The antecedent system used for this comparison to the Lakota is the UH-60L. While these systems are both utility helicopters, they are supported very differently. The table below reflects the UH-60L Operating and Support (O&S) data for an organically supported system. It does not include any costs for the maintenance labor, which is provided by military personnel. The Lakota is supported by life-cycle CLS; therefore, the cost element categories are not directly comparable.
The information in the O&S cost table for UH-60L is based on Operation and Support Management Information Systems (OSMIS) data for the UH-60L (excluding Contingency Operations (CONOPS)). Sustaining support costs for the UH-60L aircraft are not included in the table because the costs (software maintenance, system specific base operations, systems engineering/program management, and transportation) are not collected in the OSMIS database. The antecedent system cost for Black Hawk UH-60L has been escalated to BY 2006 dollars in thousands for comparison purposes.

## Table 28
Unitized O&S Costs BY2006 $K
Cost Element | LUH Average Annual Cost Per Aircraft | Black Hawk UH-60L (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower | 187.164 | 440.372
Unit Operations | 87.23 | 55.788
Maintenance | 0 | 293.167
Sustaining Support | 4.04 | 0
Continuing System Improvements | 0 | 0
Indirect Support | 63.21 | 223.048
Other | 424.356 | 0
Total | 766 | 1012.375
Unitized Cost Comments:
The "Other" cost category above includes the following average annual cost per aircraft (in thousands): CLS, installation support, and overhaul and rework. CLS is accounted for in the "Other" cost category because it is power by the hour, which includes field and depot level maintenance as well as parts and labor supplied by the contractor.
Lakota O&S unitized cost has decreased since 2011 from $801.3K to $766.0K per aircraft as a direct result of an decrease in the definitized CLS support cost per hour and a decrease in the total number of aircraft fielded from 345 to 315. However, the total O&S cost has increased since 2011 from $5,529M to $6,032.2M due to an increased useful life expectancy from 20 to 25 years.
The antecedent system cost for Black Hawk UH-60L uses BY 2006 dollars as the program basis, so the UH-60L costs were escalated to BY 2006 dollars for comparison purposes.

## Table 29
Total O&S Cost $M
| Current Production APB Objective/Threshold | Current Estimate
| LUH | LUH | Black Hawk UH-60L (Antecedent)
Base Year | 2763.6 3040.0 6032.2 1 0.0
Then Year | 3891.5 N/A 8709.7 0.0
1 APB O&S Cost Breach
Total O&S Costs Comments:
The O&S estimate for the Full Rate Production (FRP) Acquisition Program Baseline (APB) estimate in 2007 did not include military pay or training and was based on an expected Economic Useful Life (EUL) of 20 years. The APB is representative of ownership cost instead of true O&S cost.
The current O&S estimate includes the military pay and training of personnel, an expected EUL of 25 years, additional costs due to schedule and fielding location changes, and additional DA directed ONS approved modifications support cost.
Disposal Costs
Demilitarization/disposal costs are estimated to be $4.762M (BY 2006) and are not included in the O&S estimate but are part of program life-cycle costs.