## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-166
NAVSTAR Global Positioning System (NAVSTAR GPS)
As of December 31, 2012
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 4
Executive Summary |  | 5
Threshold Breaches |  | 7
Schedule |  | 8
Performance |  | 11
Track To Budget |  | 13
Cost and Funding |  | 14
Low Rate Initial Production |  | 32
Foreign Military Sales |  | 33
Nuclear Cost |  | 33
Unit Cost |  | 34
Cost Variance |  | 40
Contracts |  | 46
Deliveries and Expenditures |  | 57
Operating and Support Cost |  | 58

## Table 3
Program Information
Program Name
NAVSTAR Global Positioning System (NAVSTAR GPS)
DoD Component
Air Force
Responsible Office
Responsible Office
Col Bernard Gruber | Phone | 310-653-3001
483 North Aviation Boulevard | Fax | 310-653-3005
El Segundo, CA 90245-2808 | DSN Phone | 633-3001
| DSN Fax | 633-3005
Bernard.Gruber@us.af.mil | Date Assigned | July 19, 2010
References
SPACE & CONTROL
SAR Baseline (Production Estimate)
Under Secretary of the Air Force (USecAF) Approved Acquisition Program Baseline (APB) dated February 26, 2002
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated February 9, 2007
USER EQUIPMENT
SAR Baseline (Production Estimate)
Under Secretary of the Air Force (USecAF) Approved Acquisition Program Baseline (APB) dated February 26, 2002
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated February 9, 2007

## Table 4
Mission and Description
The Navstar Global Positioning System (GPS) is a space-based radio positioning, navigation, and time distribution system. GPS provides precise, continuous, all-weather, common-grid positioning, velocity, navigation, and time reference capability to civil, commercial, and military users worldwide. Military mission areas supported include: navigation and position fixing; air interdiction; close air support; special operations; strategic attack; counter-air and aerospace defense; theater and tactical command, control, communications and intelligence; precision munitions guidance; and ground/sea warfare. GPS also carries a suite of nuclear detonation detection system sensors as a secondary payload. These sensors provide worldwide, near realtime, 3-dimensional location of nuclear detonations.
The Modernized Space and Control portion reported here includes Block IIR, IIR-M, and IIF satellite capabilities and associated control segments. The Modernized User Equipment program is currently developing two prototype M- Code form factors to mature the technology and industrial base necessary to support the Military GPS User Equipment (MGUE) Program.

## Table 5
Executive Summary
GPS Space Segment
Global Positioning System (GPS) IIF satellites provide improved accuracy, greater security, anti-jam capabilities, and add the new L5 signal, a dedicated civilian safety-of-life signal, while maintaining baseline legacy GPS performance. Twelve Space Vehicles (SVs) are on contract, with SVs 1-3 awarded as Cost-Plus-Award-Fee and SVs 4-12 as Fixed-Price-Incentive-Fee. The program remains focused on mission assurance, satellite production and launch, and on-orbit sustainment. SV-1 (launched May 27, 2010), SV-2 (launched July 16, 2011), and SV-4 (launched October 4, 2012) transitioned to operations and are among the most accurate in the constellation. The remaining nine GPS IIF SVs on contract are in storage or various stages of assembly, integration and test. SV-3 is in storage with acceptance pending an investigation of a bus power system issue. Final delivery of SV-3 will mark the closeout of the FY 2003 Cost-Plus production effort. SV-5 has been called up for launch in May 2013, and is at Cape Canaveral Air Force Station for launch processing. SV-6 and SV-7 were delivered in August 2012, placed into storage at the factory, and are awaiting installation of Rubidium Frequency Standards (RFS). SV-8 and 9 finished production and were placed in storage in December 2012. SV-8 was accepted at that time. The DD250 was delayed on SV-9 pending resolution of a battery charger performance issue. Subsequently, the path forward on the SV-9 battery charger has now been resolved clearing the path for acceptance of SV-9 in June 2013. SVs 10-12 are scheduled for delivery in June, August, and October of 2013, respectively.
In 2011, the program began work on re-designing the L1 transmitter in order to bring the IIF operational signal power into line with the rest of the constellation. This improved design will be implemented on two vehicles (SVs 9 and 12). The modified transmitter components experienced design and manufacturing challenges in 2012 which delayed the delivery of the final three SVs. Due to repeated test failures on the new flight parts, the contractor has started a second source to deliver this component. The first one is expected by June 2013.
Production testing of the RFS revealed unexpected depletion of the xenon gas pressure in the lamps that could pose a threat to mission life from the dual RFSs on each SV. In response, the IIF program successfully tested an increase in xenon gas pressure that will ensure on-orbit mission reliability requirements are met.
The 2011 SAR reported on a technical concern regarding the SV-2 Cesium Frequency Standard (CFS) that suffered a corona event and is no longer usable. All remaining SVs had their CFS reworked and this issue is considered closed.
The period of performance for the IIF contract ended December 31, 2012. The production Contract Line Item Number (CLIN) on that contract was extended at no cost through May 2013 to complete production, and will require an additional no-cost extension through October 2013 based on the SV 10-12 production schedule. On December 28, 2012 the government awarded a follow-on contract to continue GPS IIF Launch Operations and On-Orbit Support services through 2017.
GPS Control Segment
Both operational Architectural Evolution Plan (AEP) and the Launch/Early Orbit, Anomaly Resolution and Disposal Operations (LADO) satellite command and control (C2) systems continue to perform well. Availability and dependability metrics for both systems continue to exceed standards.
The program fielded the next major AEP upgrade (V5.8) in July 2012 without any impacts to world-wide operational users. AEP V5.8 provided needed C2 improvements to implement the U.S. Strategic Command Selective Availability Anti-Spoofing Module (SAASM) Operational Concept. It also removed unneeded limitations and

## Table 6
restrictions on extended SAASM functionality. The successful fielding and operational acceptance of the AEP V5.8 software was a result of the extensive testing that was conducted in CY 2011.
Another major accomplishment for the control segment was the successful launch of the third GPS IIF satellite vehicle using the LADO system in October 2012. After accomplishing initial satellite vehicle bus checkout with LADO, the new IIF satellite was transferred to AEP for payload checkout and set operational to world-wide users in November 2012.
Finally, the contract for sustainment of AEP was recompeted this year and awarded to Lockheed Martin in December 2012. The GPS Control Segment (GCS) sustainment contract is a one year base plus five one year options on a firm fixed price contract valued at $104M. This successful, full and open, competition resulted in the government realizing over 40% savings from our FY 2012 baseline under the previous contract. The GCS contract insures that AEP will be supported until the fielding of the Next Generation Operational Control System.
GPS User Equipment
The Modernized User Equipment (MUE) effort was initiated in 2006 to demonstrate the "proof of principal" and mature the critical technologies necessary to realize modernized GPS capabilities. Rockwell Collins, L-3, and Raytheon execute contracts for the MUE efforts. The contracts have continued to mature Military-Code (M-Code) capable GPS receiver technology. The contractors began Functional Qualification Testing (FQT) of the ground based receiver card in April 2010 and completed the final Functional Quality Review (FQR) in October
2011. Independent government testing is underway and is scheduled to conclude no later than third quarter FY 2013. The delay allows for refined test plans to assess the Anti-Spoof Critical Technology Element (CTE).
Test results have demonstrated a Technical Readiness Level (TRL) 6 for the CTEs of M-Code Acquisition Engine, M-Code Crypto, Anti-Tamper, and SAASM Crypto. FQR for avionics based receiver cards was held in December
2011, independent government testing has begun, and the testing is scheduled to conclude in the fourth quarter of FY 2013.
The prototype receiver cards built under this activity are currently undergoing testing and will be evaluated by an independent Technology Readiness Assessment (TRA) team. Security evaluation, receiver card characterization, integration into operational platforms, and Government testing results will form the basis for the assessment. The TRA will support Military GPS User Equipment (MGUE) Increment 1 Milestone B. The MGUE Increment 1 program will leverage the technology development under the MUE program and develop two production ready status GPS receiver form factors for the joint services.
In addition to testing prototype cards, the program continues to leverage the MUE contracts by implementing several updates to Interface Control Documents (ICDs) and fixing deficiencies found during FQT. All three contractors have completed all software fixes. All three contractors will hold technical demonstrations this fiscal year to demonstrate success of their software fixes.
There are no significant software-related issues with this program at this time.
This is the final SAR for the MUE program, because the program is more than 90% complete.

## Table 7
Threshold Breaches
SPACE & CONTROL
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Explanation of Breach
This breach was previously reported in the December 2009 SAR.
APB Breaches
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
USER EQUIPMENT
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Explanation of Breach
This breach was previously reported in the December 2010 SAR.
APB Breaches
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 8
Schedule

## Table 9
SPACE & CONTROL
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
Space Segment IIR
Block IIR Contract Award | JUN 1989 | JUN 1989 | DEC 1989 | JUN 1989
1st IIR SV Contract Delivery | AUG 1996 | AUG 1996 | FEB 1997 | SEP 1996
2nd IIR SV Contract Delivery | NOV 1996 | NOV 1996 | MAY 1997 | MAY 1997
1st IIR SV Available for Launch | JAN 1997 | JAN 1997 | JUL 1997 | JAN 1997
Space Segment IIR-M
Start Production | MAR 2001 | MAR 2001 | MAR 2001 | MAR 2001
1st IIR-M SV available for launch | MAY 2003 | MAY 2005 | NOV 2005 | SEP 2005
Space Segment IIF
Start Production | JUN 2002 | JUN 2002 | DEC 2002 | JUN 2002
1st IIF SV available for launch | JUN 2005 | JAN 2009 | JUL 2009 | MAR 2010 1
Operational Control System
OCS Ver 5.2.1 transition to operations with Accuracy Improvement and M- Code, L2C, and L5 test capability | N/A | JUN 2007 | DEC 2007 | SEP 2007
OCS Ver 5.2.2 transition to operations with OCS V5.2.1 and IIF capabilities | N/A | APR 2008 | OCT 2008 | OCT 2008
Version 5.5 with SAASM Capability for IIR & IIF available for transition to operations | N/A | MAR 2009 | SEP 2009 | JAN 2011 1
1APB Breach
Acronyms And Abbreviations
L2C - 2nd Civil Signal L5 - 3rd Civil Signal
M-Code - Military Code
OCS - Operational Control Segment
SAASM - Selective Availability/Anti-Spoofing Module SV - Space Vehicle
Ver - Version
Change Explanations
None

## Table 10
USER EQUIPMENT
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
SAASM capability available | JAN 2002 | JAN 2002 | JUL 2002 | JAN 2002
YMCA receiver card prototype complete | N/A | MAR 2010 | SEP 2010 | N/A 1
YMCA receiver card ready for delivery to platform | N/A | MAY 2011 | NOV 2011 | N/A 1
1APB Breach
Acronyms And Abbreviations
SAASM - Selective Availability/Anti-Spoofing Module YMCA - Y-Code/M-Code/Coarse-Acquisition
Change Explanations
None
Memo
As reported in the 2010 SAR, based on the recommendation of the Undersecretary of Defense for Acquisition, Technology and Logistics (AT&L) at the January 29, 2010 Annual Global Positioning System Enterprise Review, and recorded in a May 24, 2010 memo, the Modernized User Equipment milestones in the Navstar Acquisition Program Baseline are no longer applicable.

## Table 11
Performance
Requirements Source: Operational Requirements Document (ORD) dated February 18, 2000
SPACE & CONTROL
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
PPS System Perf
Pos Accuracy | 2.1m H 4.0m V | 1.3m H 2.6m V | 17m H 35m V | TBD | 2.8m H 5.8m V
Time Transfer | 10nsec | 3.3ns | 40ns | TBD | 6.7ns
SPS System Perf
Pos Accuracy | 1.0m H 4.0m V | 1.3m H 2.6m V | 17m H 35m V | TBD | 2.8m H 5.8m V
Time Transfer | 40nsec | 3.3ns | 40ns | TBD | 6.7ns
L5 Signal Power | -154dBW | -154.0dB W | -154.9dB W | TBD | -154.3dB W
Flexible Power
Max L1 P-Code | N/A | -152.6dB W | -155.2dB W | TBD | -152.8dBW
Max L2 P-Code | N/A | -152.9dB W | -156.6dB W | TBD | -154.0dBW
L2C Signal Power | N/A | -158.5dB W | -160.0dB W | TBD | -158.0dBW
Acronyms And Abbreviations
dBW - Decibel Watt (Decibels relative to one Watt) L2C - 2nd Civil Signal
L5 - 3rd Civil Signal
m H - Meters Horizontal m V - Meters Vertical N/A - Not Available ns/nsec - Nanoseconds Perf - Performance Pos - Position
PPS - Precise Positioning Service SPS - Standard Positioning Service TBD - To Be Determined
Change Explanations
None

## Table 12
USER EQUIPMENT
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
PPS System Performance
Time-To-First-Fix | 1 min | 1 min | 2 min | TBD | .8 Min
Pos Accuracy | 2.1m H 4.0m V | 2.1m H 4.0m V | 19m H 38m V | TBD | 7.9m H 16.2m V
Velocity | 0.01m/s | 0.01m/s | 0.1 m/s | TBD | .01 m/s
Time Transfer | 10nsec | 10 ns | 44ns | TBD | 10ns
Requirements Source: Capability Development Document (CDD) dated December 15, 2009
Acronyms And Abbreviations
m H - Meters Horizontal m V - Meters Vertical m/s - Meters per Second min - Minute
ns/nsec - Nanoseconds Pos - Position
PPS - Precise Positioning Service TBD - To Be Determined
Change Explanations
None

## Table 13
Track To Budget
SPACE & CONTROL
RDT&E
APPN 3600 | BA 07 | PE 0305165F | (Air Force)
| Project 3030 | NAVSTAR GPS (Space and Control) Air Force |  | (Sunk)
Air Force
Procurement
APPN 3020 | BA 05 | PE 0305165F | (Air Force)
| ICN MGPS00 | NAVSTAR GPS (Space and Control) Air Force
APPN 3080 | BA 03 | PE 0305165F | (Air Force)
| ICN 836730 | NAVSTAR GPS (Space and Control) Air Force | (Shared) | (Sunk)
| ICN 836790 | NAVSTAR GPS (Space and Control) Air Force | (Shared)
APPN 3080 | BA 05 | PE 0305165F | (Air Force)
| ICN 861900 | NAVSTAR GPS (Space and Control) Air Force | (Shared)
USER EQUIPMENT
RDT&E
APPN 3600 BA 07 |  | PE 0305164F | (Air Force)
Project 3028 |  | NAVSTAR GPS (User Equip) | (Shared) (Sunk)
Shared funding line supports both Modernized User Equipment (MUE) and Military Global Positioning System User Equipment (MGUE), however only MUE funding is included and reported in the Cost and Funding Section of this Selected Acquisition Report (SAR).

## Table 14
Cost and Funding
Cost Summary - Total Program
Total Acquisition Cost and Quantity - Total Program
|  | BY2000 $M |  |  |  |  | BY2000 $M
Appropriation |  | SAR Baseline Prod Est |  | Current APB Production Objective/Threshold |  |  | Current Estimate
TY $M
SAR Baseline Prod Est | Current APB Production Objective |  | Current Estimate
RDT&E |  | 2319.7 |  |  | 3650.4 | -- |  | 3379.4 | 2430.2 | 3984.8 | 3659.1
Procurement |  | 3493.7 |  |  | 4025.8 | -- |  | 4057.3 | 3565.1 | 4259 | 4336.7
Flyaway |  | 3205.8 |  |  | -- | -- |  | 3658.8 | 3259.8 | -- | 3868.6
Recurring |  | 2996.5 |  |  | -- | -- |  | 3454.8 | 3043.2 | -- | 3653
Non Recurring |  | 209.3 |  |  | -- | -- |  | 204 | 216.6 | -- | 215.6
Support |  | 287.9 |  |  | -- | -- |  | 398.5 | 305.3 | -- | 468.1
Other Support |  | 254.3 |  |  | -- | -- |  | 392.5 | 273.5 | -- | 461.1
Initial Spares |  | 33.6 |  |  | -- | -- |  | 6 | 31.8 | -- | 7
MILCON |  | 0 |  |  | 0 | -- |  | 0 | 0 | 0 | 0
Acq O&M |  | 0 |  |  | 0 | -- |  | 0 | 0 | 0 | 0
Total |  | 5813.4 |  |  | 7676.2 | N/A |  | 7436.7 | 5995.3 | 8243.8 | 7995.8

## Table 15
Cost and Funding
Cost Summary - SPACE & CONTROL
Total Acquisition Cost and Quantity - SPACE & CONTROL
|  | BY2000 $M | [6 empty] | BY2000 $M
Appropriation |  | SAR Baseline Prod Est |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate
TY $M
SAR Baseline Prod Est | Current APB Production Objective |  |  | Current Estimate
RDT&E |  | 1776.2 |  |  |  | 2219.1 |  | 2441 |  | 2141.6 |  | 1829.3 | 2330.2 | 2240.4
Procurement |  | 3239.4 |  |  |  | 3768.6 |  | 4145.5 |  | 4057.3 |  | 3291.6 | 3977.8 | 4336.7
Flyaway |  | 3205.8 |  |  |  | -- |  | -- |  | 3658.8 |  | 3259.8 | -- | 3868.6
Recurring |  | 2996.5 |  |  |  | -- |  | -- |  | 3454.8 |  | 3043.2 | -- | 3653
Non Recurring |  | 209.3 |  |  |  | -- |  | -- |  | 204 |  | 216.6 | -- | 215.6
Support |  | 33.6 |  |  |  | -- |  | -- |  | 398.5 |  | 31.8 | -- | 468.1
Other Support |  | 0 |  |  |  | -- |  | -- |  | 392.5 |  | 0 | -- | 461.1
Initial Spares |  | 33.6 |  |  |  | -- |  | -- |  | 6 |  | 31.8 | -- | 7
MILCON |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Acq O&M |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Total |  | 5015.6 |  |  |  | 5987.7 |  | N/A |  | 6198.9 |  | 5120.9 | 6308 | 6577.1
Quantity |  |  | SAR Baseline Prod Est |  |  |  | Current APB Production |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  | 0
Procurement |  |  | 33 |  |  |  | 33 |  |  |  | 33
Total |  |  | 33 |  |  |  | 33 |  |  |  | 33

## Table 16
Cost Summary - USER EQUIPMENT
Total Acquisition Cost and Quantity - USER EQUIPMENT
|  | BY2000 $M | [6 empty] | BY2000 $M
Appropriation |  | SAR Baseline Prod Est |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate
TY $M
SAR Baseline Prod Est | Current APB Production Objective |  |  | Current Estimate
RDT&E |  | 543.5 |  |  |  | 1431.3 |  | 1574.4 |  | 1237.8 |  | 600.9 | 1654.6 | 1418.7
Procurement |  | 254.3 |  |  |  | 257.2 |  | 282.9 |  | 0 |  | 273.5 | 281.2 | 0
Flyaway |  | 0 |  |  |  | -- |  | -- |  | 0 |  | 0 | -- | 0
Recurring |  | 0 |  |  |  | -- |  | -- |  | 0 |  | 0 | -- | 0
Non Recurring |  | 0 |  |  |  | -- |  | -- |  | 0 |  | 0 | -- | 0
Support |  | 254.3 |  |  |  | -- |  | -- |  | 0 |  | 273.5 | -- | 0
Other Support |  | 254.3 |  |  |  | -- |  | -- |  | 0 |  | 273.5 | -- | 0
Initial Spares |  | 0 |  |  |  | -- |  | -- |  | 0 |  | 0 | -- | 0
MILCON |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Acq O&M |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Total |  | 797.8 |  |  |  | 1688.5 |  | N/A |  | 1237.8 |  | 874.4 | 1935.8 | 1418.7
Quantity |  |  | SAR Baseline Prod Est |  |  |  | Current APB Production |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  | 0
Procurement |  |  | 0 |  |  |  | 0 |  |  |  | 0
Total |  |  | 0 |  |  |  | 0 |  |  |  | 0

## Table 17
Cost and Funding
Funding Summary - Total Program
Appropriation and Quantity Summary - Total Program FY2014 President's Budget / December 2012 SAR (TY$ M)
Appropriation | Prior | FY2013 |  | FY2014 |  | FY2015 |  | FY2016 |  | FY2017 |  | FY2018 |  | To Complete |  | Total
RDT&E | 3615.2 |  | 43.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3659.1
Procurement | 4145.7 |  | 65.8 |  | 67.8 |  | 33.5 |  | 21 |  | 2.4 |  | 0.5 |  | 0 |  | 4336.7
MILCON | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2014 Total | 7760.9 |  | 109.7 |  | 67.8 |  | 33.5 |  | 21 |  | 2.4 |  | 0.5 |  | 0 |  | 7995.8
PB 2013 Total | 7773.8 |  | 109.9 |  | 85.5 |  | 15.8 |  | 2.4 |  | 0.4 |  | 0 |  | 0 |  | 7987.8
Delta | -12.9 |  | -0.2 |  | -17.7 |  | 17.7 |  | 18.6 |  | 2 |  | 0.5 |  | 0 |  | 8

## Table 18
Cost and Funding
Funding Summary - SPACE & CONTROL
Appropriation and Quantity Summary - SPACE & CONTROL FY2014 President's Budget / December 2012 SAR (TY$ M)
RDT&E | 2226.1 |  |  | 14.3 |  |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 2240.4
Procurement | 4145.7 |  |  | 65.8 |  |  | 67.8 |  |  |  | 33.5 |  | 21 |  |  | 2.4 |  |  | 0.5 |  |  | 0 |  | 4336.7
MILCON | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
PB 2014 Total | 6371.8 |  |  | 80.1 |  |  | 67.8 |  |  |  | 33.5 |  | 21 |  |  | 2.4 |  |  | 0.5 |  |  | 0 |  | 6577.1
PB 2013 Total | 6397 |  |  | 80.3 |  |  | 85.5 |  |  |  | 15.8 |  | 2.4 |  |  | 0.4 |  |  | 0 |  |  | 0 |  | 6581.4
Delta | -25.2 |  |  | -0.2 |  |  | -17.7 |  |  |  | 17.7 |  | 18.6 |  |  | 2 |  |  | 0.5 |  |  | 0 |  | -4.3
Program funding and production quantities listed in this SAR are consistent with the FY 2014 President's Budget (PB). The FY 2014 PB did not reflect the enacted DoD appropriation for FY 2013, nor sequestration; it reflected the President's requested amounts for FY 2013.
Appropriation |  | Prior | FY2013 |  |  | FY2014 |  |  | FY2015 |  |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  |  | To Complete |  | Total
Quantity | Undistributed |  |  |  | Prior |  |  | FY2013 |  | FY2014 |  | FY2015 |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  | To Complete |  |  | Total
Development | 0 |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
Production | 0 |  |  |  | 33 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 33
PB 2014 Total | 0 |  |  |  | 33 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 33
PB 2013 Total | 0 |  |  |  | 33 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 33
Delta | 0 |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0

## Table 19
Funding Summary - USER EQUIPMENT
Appropriation and Quantity Summary - USER EQUIPMENT
FY2014 President's Budget / December 2012 SAR (TY$ M)
RDT&E | 1389.1 |  |  | 29.6 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 1418.7
Procurement | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
MILCON | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
PB 2014 Total | 1389.1 |  |  | 29.6 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 1418.7
PB 2013 Total | 1376.8 |  |  | 29.6 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 1406.4
Delta | 12.3 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 12.3
Program funding and production quantities listed in this SAR are consistent with the FY 2014 President's Budget (PB). The FY 2014 PB did not reflect the enacted DoD appropriation for FY 2013, nor sequestration; it reflected the President's requested amounts for FY 2013.
All procurement fund (Aircraft Procurement, Air Force and Other Procurement, Air Force) along with the Department of Defense (DoD) funds (Research Development Test and Evaluation (RDT&E)) have been removed from the Selected Acquisition Report (SAR). The User Equipment (UE) portion of the SAR only covers Modernized UE (MUE). All MUE activities are paid for by RDT&E, Air Force funds and thus we were incorrectly carrying the other funding.
Appropriation |  | Prior | FY2013 |  |  | FY2014 |  | FY2015 |  |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  |  | To Complete |  | Total
Quantity | Undistributed |  |  |  | Prior |  | FY2013 |  | FY2014 |  | FY2015 |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  | To Complete |  |  | Total
Development | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
Production | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
PB 2014 Total | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
PB 2013 Total | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
Delta | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0

## Table 20
Cost and Funding
Annual Funding By Appropriation - SPACE & CONTROL
Annual Funding TY$ - SPACE & CONTROL
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year |  | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M |  | Total Flyaway TY $M |  | Total Support TY $M |  | Total Program TY $M
1986 | -- |  | -- | -- | -- | -- |  | -- |  | 1.2
1987 | -- |  | -- | -- | -- | -- |  | -- |  | 12.8
1988 | -- |  | -- | -- | -- | -- |  | -- |  | 13.8
1989 | -- |  | -- | -- | -- | -- |  | -- |  | 34
1990 | -- |  | -- | -- | -- | -- |  | -- |  | 22.2
1991 | -- |  | -- | -- | -- | -- |  | -- |  | 35.1
1992 | -- |  | -- | -- | -- | -- |  | -- |  | 36.2
1993 | -- |  | -- | -- | -- | -- |  | -- |  | 46.6
1994 | -- |  | -- | -- | -- | -- |  | -- |  | 24.1
1995 | -- |  | -- | -- | -- | -- |  | -- |  | 35.2
1996 | -- |  | -- | -- | -- | -- |  | -- |  | 43.2
1997 | -- |  | -- | -- | -- | -- |  | -- |  | 84.3
1998 | -- |  | -- | -- | -- | -- |  | -- |  | 96.7
1999 | -- |  | -- | -- | -- | -- |  | -- |  | 100.9
2000 | -- |  | -- | -- | -- | -- |  | -- |  | 93.2
2001 | -- |  | -- | -- | -- | -- |  | -- |  | 183.4
2002 | -- |  | -- | -- | -- | -- |  | -- |  | 183.6
2003 | -- |  | -- | -- | -- | -- |  | -- |  | 286.2
2004 | -- |  | -- | -- | -- | -- |  | -- |  | 132.5
2005 | -- |  | -- | -- | -- | -- |  | -- |  | 128.3
2006 | -- |  | -- | -- | -- | -- |  | -- |  | 174.5
2007 | -- |  | -- | -- | -- | -- |  | -- |  | 160.6
2008 | -- |  | -- | -- | -- | -- |  | -- |  | 110.2
2009 | -- |  | -- | -- | -- | -- |  | -- |  | 86.6
2010 | -- |  | -- | -- | -- | -- |  | -- |  | 50.5
2011 | -- |  | -- | -- | -- | -- |  | -- |  | 33.4

## Table 21
2012 | -- | -- | -- | -- | -- | -- | 16.8
2013 | -- | -- | -- | -- | -- | -- | 14.3
Subtotal | -- | -- | -- | -- | -- | -- | 2240.4

## Table 22
Annual Funding BY$ - SPACE & CONTROL
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2000 $M | Non End Item Recurring Flyaway BY 2000 $M | Non Recurring Flyaway BY 2000 $M | Total Flyaway BY 2000 $M | Total Support BY 2000 $M | Total Program BY 2000 $M
1986 | -- | -- | -- | -- | -- | -- | 1.7
1987 | -- | -- | -- | -- | -- | -- | 16.9
1988 | -- | -- | -- | -- | -- | -- | 17.8
1989 | -- | -- | -- | -- | -- | -- | 41.8
1990 | -- | -- | -- | -- | -- | -- | 26.5
1991 | -- | -- | -- | -- | -- | -- | 40.4
1992 | -- | -- | -- | -- | -- | -- | 40.4
1993 | -- | -- | -- | -- | -- | -- | 51
1994 | -- | -- | -- | -- | -- | -- | 25.9
1995 | -- | -- | -- | -- | -- | -- | 37.2
1996 | -- | -- | -- | -- | -- | -- | 44.8
1997 | -- | -- | -- | -- | -- | -- | 86.3
1998 | -- | -- | -- | -- | -- | -- | 98.3
1999 | -- | -- | -- | -- | -- | -- | 101.5
2000 | -- | -- | -- | -- | -- | -- | 92.4
2001 | -- | -- | -- | -- | -- | -- | 179.3
2002 | -- | -- | -- | -- | -- | -- | 177.6
2003 | -- | -- | -- | -- | -- | -- | 273.1
2004 | -- | -- | -- | -- | -- | -- | 123.4
2005 | -- | -- | -- | -- | -- | -- | 116.5
2006 | -- | -- | -- | -- | -- | -- | 153.8
2007 | -- | -- | -- | -- | -- | -- | 137.9
2008 | -- | -- | -- | -- | -- | -- | 92.7
2009 | -- | -- | -- | -- | -- | -- | 71.9
2010 | -- | -- | -- | -- | -- | -- | 41.4
2011 | -- | -- | -- | -- | -- | -- | 26.9
2012 | -- | -- | -- | -- | -- | -- | 13.2
2013 | -- | -- | -- | -- | -- | -- | 11
Subtotal | -- | -- | -- | -- | -- | -- | 2141.6

## Table 23
Annual Funding TY$ - SPACE & CONTROL
3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year |  | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M |  | Total Flyaway TY $M |  | Total Support TY $M |  | Total Program TY $M
1987 | -- |  | -- | -- | -- | -- |  | 2.6 |  | 2.6
1988 | -- |  | -- | -- | -- | -- |  | 8.3 |  | 8.3
1989 | -- |  | -- | -- | -- | -- |  | -- |  | --
1990 | -- |  | -- | -- | -- | -- |  | -- |  | --
1991 | -- |  | -- | -- | -- | -- |  | -- |  | --
1992 | -- |  | -- | -- | -- | -- |  | -- |  | --
1993 | -- |  | -- | -- | -- | -- |  | 5.5 |  | 5.5
1994 | -- |  | -- | -- | -- | -- |  | 4.2 |  | 4.2
1995 | -- |  | -- | -- | -- | -- |  | 4.9 |  | 4.9
1996 | -- |  | -- | -- | -- | -- |  | 6.7 |  | 6.7
1997 | -- |  | -- | -- | -- | -- |  | 10.6 |  | 10.6
1998 | -- |  | -- | -- | -- | -- |  | 9.2 |  | 9.2
1999 | -- |  | -- | -- | -- | -- |  | 6.4 |  | 6.4
2000 | -- |  | -- | -- | -- | -- |  | 6.6 |  | 6.6
2001 | -- |  | -- | -- | -- | -- |  | 14.7 |  | 14.7
2002 | -- |  | -- | -- | -- | -- |  | 10.3 |  | 10.3
2003 | -- |  | -- | -- | -- | -- |  | 20 |  | 20
2004 | -- |  | -- | -- | -- | -- |  | 13.4 |  | 13.4
2005 | -- |  | -- | -- | -- | -- |  | 7.8 |  | 7.8
2006 | -- |  | -- | -- | -- | -- |  | 13.5 |  | 13.5
2007 | -- |  | -- | -- | -- | -- |  | 10.3 |  | 10.3
2008 | -- |  | -- | -- | -- | -- |  | 8 |  | 8
2009 | -- |  | -- | -- | -- | -- |  | 5.3 |  | 5.3
2010 | -- |  | -- | -- | -- | -- |  | 7.5 |  | 7.5
2011 | -- |  | -- | -- | -- | -- |  | 7.7 |  | 7.7
2012 | -- |  | -- | -- | -- | -- |  | 4.8 |  | 4.8
2013 | -- |  | -- | -- | -- | -- |  | 7.7 |  | 7.7
2014 | -- |  | -- | -- | -- | -- |  | 11.8 |  | 11.8
2015 | -- |  | -- | -- | -- | -- |  | 13.2 |  | 13.2

## Table 24
2016 | -- | -- | -- | -- | -- | 12.4 | 12.4
2017 | -- | -- | -- | -- | -- | 2.4 | 2.4
2018 | -- | -- | -- | -- | -- | 0.5 | 0.5
Subtotal | -- | -- | -- | -- | -- | 236.3 | 236.3

## Table 25
Annual Funding BY$ - SPACE & CONTROL
3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2000 $M |  | Non End Item Recurring Flyaway BY 2000 $M |  | Non Recurring Flyaway BY 2000 $M |  | Total Flyaway BY 2000 $M |  | Total Support BY 2000 $M | Total Program BY 2000 $M
1987 | -- |  | -- |  | -- |  | -- |  | -- | 3.3 | 3.3
1988 | -- |  | -- |  | -- |  | -- |  | -- | 10.2 | 10.2
1989 | -- |  | -- |  | -- |  | -- |  | -- | -- | --
1990 | -- |  | -- |  | -- |  | -- |  | -- | -- | --
1991 | -- |  | -- |  | -- |  | -- |  | -- | -- | --
1992 | -- |  | -- |  | -- |  | -- |  | -- | -- | --
1993 | -- |  | -- |  | -- |  | -- |  | -- | 5.9 | 5.9
1994 | -- |  | -- |  | -- |  | -- |  | -- | 4.4 | 4.4
1995 | -- |  | -- |  | -- |  | -- |  | -- | 5.1 | 5.1
1996 | -- |  | -- |  | -- |  | -- |  | -- | 6.9 | 6.9
1997 | -- |  | -- |  | -- |  | -- |  | -- | 10.7 | 10.7
1998 | -- |  | -- |  | -- |  | -- |  | -- | 9.2 | 9.2
1999 | -- |  | -- |  | -- |  | -- |  | -- | 6.3 | 6.3
2000 | -- |  | -- |  | -- |  | -- |  | -- | 6.4 | 6.4
2001 | -- |  | -- |  | -- |  | -- |  | -- | 14.1 | 14.1
2002 | -- |  | -- |  | -- |  | -- |  | -- | 9.7 | 9.7
2003 | -- |  | -- |  | -- |  | -- |  | -- | 19.1 | 19.1
2004 | -- |  | -- |  | -- |  | -- |  | -- | 12.5 | 12.5
2005 | -- |  | -- |  | -- |  | -- |  | -- | 7.1 | 7.1
2006 | -- |  | -- |  | -- |  | -- |  | -- | 11.9 | 11.9
2007 | -- |  | -- |  | -- |  | -- |  | -- | 8.9 | 8.9
2008 | -- |  | -- |  | -- |  | -- |  | -- | 6.7 | 6.7
2009 | -- |  | -- |  | -- |  | -- |  | -- | 4.4 | 4.4
2010 | -- |  | -- |  | -- |  | -- |  | -- | 6.1 | 6.1
2011 | -- |  | -- |  | -- |  | -- |  | -- | 6.2 | 6.2
2012 | -- |  | -- |  | -- |  | -- |  | -- | 3.8 | 3.8
2013 | -- |  | -- |  | -- |  | -- |  | -- | 6 | 6
2014 | -- |  | -- |  | -- |  | -- |  | -- | 9 | 9
2015 | -- |  | -- |  | -- |  | -- |  | -- | 9.8 | 9.8

## Table 26
2016 | -- | -- | -- | -- | -- | 9.1 | 9.1
2017 | -- | -- | -- | -- | -- | 1.7 | 1.7
2018 | -- | -- | -- | -- | -- | 0.4 | 0.4
Subtotal | -- | -- | -- | -- | -- | 214.9 | 214.9

## Table 27
Annual Funding TY$ - SPACE & CONTROL
3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1991 | -- | 79.8 | -- | 7.9 | 87.7 | -- | 87.7
1992 | 4 | 155.3 | -- | 7.7 | 163 | -- | 163
1993 | 4 | 151.9 | -- | 8.7 | 160.6 | -- | 160.6
1994 | 4 | 160.4 | -- | 7.9 | 168.3 | -- | 168.3
1995 | 5 | 198.8 | -- | 8.8 | 207.6 | -- | 207.6
1996 | 4 | 136.7 | -- | 8.3 | 145 | -- | 145
1997 | 3 | 179.1 | -- | 9.1 | 188.2 | -- | 188.2
1998 | 3 | 168.7 | -- | 9 | 177.7 | -- | 177.7
1999 | -- | 69.5 | -- | 10.9 | 80.4 | -- | 80.4
2000 | -- | 105.9 | -- | 13.5 | 119.4 | -- | 119.4
2001 | -- | 152.1 | -- | 13.5 | 165.6 | -- | 165.6
2002 | -- | 138.6 | -- | 11.9 | 150.5 | -- | 150.5
2003 | -- | 270.8 | -- | 13.4 | 284.2 | -- | 284.2
2004 | -- | 322.8 | -- | 13.6 | 336.4 | -- | 336.4
2005 | 3 | 352.5 | -- | 13.8 | 366.3 | -- | 366.3
2006 | 3 | 357.5 | -- | 14.3 | 371.8 | -- | 371.8
2007 | -- | 91.1 | -- | 14.4 | 105.5 | -- | 105.5
2008 | -- | 126.8 | 68.7 | -- | 195.5 | 32 | 227.5
2009 | -- | 80 | 21.1 | -- | 101.1 | 41 | 142.1
2010 | -- | 60.8 | 49.5 | -- | 110.3 | 27.3 | 137.6
2011 | -- | 0.2 | 25.2 | -- | 25.4 | 38.9 | 64.3
2012 | -- | -- | 55.2 | 26.8 | 82 | 25.7 | 107.7
2013 | -- | -- | 11.5 | 2.1 | 13.6 | 44.5 | 58.1
2014 | -- | -- | 35.8 | -- | 35.8 | 20.2 | 56
2015 | -- | -- | 18.1 | -- | 18.1 | 2.2 | 20.3
2016 | -- | -- | 8.6 | -- | 8.6 | -- | 8.6
Subtotal | 33 | 3359.3 | 293.7 | 215.6 | 3868.6 | 231.8 | 4100.4

## Table 28
Annual Funding BY$ - SPACE & CONTROL
3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2000 $M | Non End Item Recurring Flyaway BY 2000 $M | Non Recurring Flyaway BY 2000 $M | Total Flyaway BY 2000 $M | Total Support BY 2000 $M | Total Program BY 2000 $M
1991 | -- | 88.4 | -- | 8.8 | 97.2 | -- | 97.2
1992 | 4 | 170 | -- | 8.4 | 178.4 | -- | 178.4
1993 | 4 | 163 | -- | 9.3 | 172.3 | -- | 172.3
1994 | 4 | 168.7 | -- | 8.3 | 177 | -- | 177
1995 | 5 | 207.2 | -- | 9.1 | 216.3 | -- | 216.3
1996 | 4 | 140.6 | -- | 8.5 | 149.1 | -- | 149.1
1997 | 3 | 181.6 | -- | 9.3 | 190.9 | -- | 190.9
1998 | 3 | 169.5 | -- | 9 | 178.5 | -- | 178.5
1999 | -- | 68.9 | -- | 10.9 | 79.8 | -- | 79.8
2000 | -- | 103.9 | -- | 13.2 | 117.1 | -- | 117.1
2001 | -- | 147.6 | -- | 13.1 | 160.7 | -- | 160.7
2002 | -- | 132.3 | -- | 11.3 | 143.6 | -- | 143.6
2003 | -- | 255.5 | -- | 12.6 | 268.1 | -- | 268.1
2004 | -- | 298 | -- | 12.6 | 310.6 | -- | 310.6
2005 | 3 | 316.4 | -- | 12.4 | 328.8 | -- | 328.8
2006 | 3 | 311.9 | -- | 12.5 | 324.4 | -- | 324.4
2007 | -- | 77.5 | -- | 12.3 | 89.8 | -- | 89.8
2008 | -- | 106 | 57.4 | -- | 163.4 | 26.7 | 190.1
2009 | -- | 65.9 | 17.4 | -- | 83.3 | 33.8 | 117.1
2010 | -- | 49.3 | 40.2 | -- | 89.5 | 22.2 | 111.7
2011 | -- | 0.2 | 20 | -- | 20.2 | 30.8 | 51
2012 | -- | -- | 43 | 20.8 | 63.8 | 20 | 83.8
2013 | -- | -- | 8.7 | 1.6 | 10.3 | 33.5 | 43.8
2014 | -- | -- | 26.5 | -- | 26.5 | 15 | 41.5
2015 | -- | -- | 13.1 | -- | 13.1 | 1.6 | 14.7
2016 | -- | -- | 6.1 | -- | 6.1 | -- | 6.1
Subtotal | 33 | 3222.4 | 232.4 | 204 | 3658.8 | 183.6 | 3842.4

## Table 29
Cost Quantity Information - SPACE & CONTROL 3020 ¦ Procurement ¦ Missile Procurement, Air Force
End Item
Recurring
Flyaway
Fiscal Year | Quantity | (Aligned with
Quantity)
BY 2000
$M
1991 | -- | --
1992 | 4 | 178.6
1993 | 4 | 178.6
1994 | 4 | 178.6
1995 | 5 | 223.4
1996 | 4 | 178.6
1997 | 3 | 576.8
1998 | 3 | 576.8
1999 | -- | --
2000 | -- | --
2001 | -- | --
2002 | -- | --
2003 | -- | --
2004 | -- | --
2005 | 3 | 565.5
2006 | 3 | 565.5
2007 | -- | --
2008 | -- | --
2009 | -- | --
2010 | -- | --
2011 | -- | --
2012 | -- | --
2013 | -- | --
2014 | -- | --
2015 | -- | --
2016 | -- | --
Subtotal | 33 | 3222.4

## Table 30
Annual Funding By Appropriation - USER EQUIPMENT
Annual Funding TY$ - USER EQUIPMENT
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1994 | -- | -- | -- | -- | -- | -- | 1.1
1995 | -- | -- | -- | -- | -- | -- | 1.5
1996 | -- | -- | -- | -- | -- | -- | 9.3
1997 | -- | -- | -- | -- | -- | -- | 24.2
1998 | -- | -- | -- | -- | -- | -- | 34.2
1999 | -- | -- | -- | -- | -- | -- | 36.1
2000 | -- | -- | -- | -- | -- | -- | 32.2
2001 | -- | -- | -- | -- | -- | -- | 41.4
2002 | -- | -- | -- | -- | -- | -- | 36.4
2003 | -- | -- | -- | -- | -- | -- | 67.5
2004 | -- | -- | -- | -- | -- | -- | 92.1
2005 | -- | -- | -- | -- | -- | -- | 91
2006 | -- | -- | -- | -- | -- | -- | 111.7
2007 | -- | -- | -- | -- | -- | -- | 130.3
2008 | -- | -- | -- | -- | -- | -- | 154.6
2009 | -- | -- | -- | -- | -- | -- | 121.8
2010 | -- | -- | -- | -- | -- | -- | 131.6
2011 | -- | -- | -- | -- | -- | -- | 155.8
2012 | -- | -- | -- | -- | -- | -- | 116.3
2013 | -- | -- | -- | -- | -- | -- | 29.6
Subtotal | -- | -- | -- | -- | -- | -- | 1418.7

## Table 31
Annual Funding BY$ - USER EQUIPMENT
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2000 $M | Non End Item Recurring Flyaway BY 2000 $M | Non Recurring Flyaway BY 2000 $M | Total Flyaway BY 2000 $M | Total Support BY 2000 $M | Total Program BY 2000 $M
1994 | -- | -- | -- | -- | -- | -- | 1.2
1995 | -- | -- | -- | -- | -- | -- | 1.6
1996 | -- | -- | -- | -- | -- | -- | 9.6
1997 | -- | -- | -- | -- | -- | -- | 24.8
1998 | -- | -- | -- | -- | -- | -- | 34.8
1999 | -- | -- | -- | -- | -- | -- | 36.3
2000 | -- | -- | -- | -- | -- | -- | 31.9
2001 | -- | -- | -- | -- | -- | -- | 40.5
2002 | -- | -- | -- | -- | -- | -- | 35.2
2003 | -- | -- | -- | -- | -- | -- | 64.4
2004 | -- | -- | -- | -- | -- | -- | 85.7
2005 | -- | -- | -- | -- | -- | -- | 82.6
2006 | -- | -- | -- | -- | -- | -- | 98.4
2007 | -- | -- | -- | -- | -- | -- | 111.9
2008 | -- | -- | -- | -- | -- | -- | 130.1
2009 | -- | -- | -- | -- | -- | -- | 101.2
2010 | -- | -- | -- | -- | -- | -- | 107.9
2011 | -- | -- | -- | -- | -- | -- | 125.3
2012 | -- | -- | -- | -- | -- | -- | 91.6
2013 | -- | -- | -- | -- | -- | -- | 22.8
Subtotal | -- | -- | -- | -- | -- | -- | 1237.8

## Table 32
Low Rate Initial Production
SPACE & CONTROL
Low Rate Initial Production (LRIP) is not applicable for the Space and Control program.
USER EQUIPMENT
Low Rate Initial Production (LRIP) is not applicable for the User Equipment program.

## Table 33
Foreign Military Sales
SPACE & CONTROL
None
USER EQUIPMENT
None
Nuclear Cost
SPACE & CONTROL
None
USER EQUIPMENT
None

## Table 34
Unit Cost
SPACE & CONTROL
Unit Cost Report
|  | BY2000 $M | BY2000 $M
Unit Cost |  | Current UCR Baseline (FEB 2007 APB) | Current Estimate (DEC 2012 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 5987.7 |  |  | 6198.9
Quantity | 33 |  |  | 33
Unit Cost | 181.445 |  |  | 187.845 |  |  | 3.53
Average Procurement Unit Cost (APUC)
Cost | 3768.6 |  |  | 4057.3
Quantity | 33 |  |  | 33
Unit Cost | 114.2 |  |  | 122.948 |  |  | 7.66
|  | BY2000 $M | BY2000 $M
Unit Cost |  | Original UCR Baseline (FEB 2002 APB) | Current Estimate (DEC 2012 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 5015.6 |  |  | 6198.9
Quantity | 33 |  |  | 33
Unit Cost | 151.988 |  |  | 187.845 |  | 23.59
Average Procurement Unit Cost (APUC)
Cost | 3239.4 |  |  | 4057.3
Quantity | 33 |  |  | 33
Unit Cost | 98.164 |  |  | 122.948 |  | 25.25

## Table 35
SPACE & CONTROL
Unit Cost History
[7 empty] | BY2000 $M |  |  |  |  | TY $M
|  |  | Date |  |  |  | PAUC |  | APUC |  |  | PAUC |  | APUC
Original APB |  |  | FEB 2002 |  |  |  | 151.988 |  | 98.164 |  |  | 155.179 |  | 99.745
APB as of January 2006 |  |  | FEB 2003 |  |  |  | 150.5 |  | 97.811 |  |  | 154.914 |  | 101.105
Revised Original APB |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Prior APB |  |  | FEB 2003 |  |  |  | 150.5 |  | 97.811 |  |  | 154.914 |  | 101.105
Current APB |  |  | FEB 2007 |  |  |  | 181.445 |  | 114.2 |  |  | 191.152 |  | 120.539
Prior Annual SAR |  |  | DEC 2011 |  |  |  | 188.079 |  | 123.158 |  |  | 199.436 |  | 131.518
Current Estimate |  |  | DEC 2012 |  |  |  | 187.845 |  | 122.948 |  |  | 199.306 |  | 131.415
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Prod Est | Changes | [11 empty] | PAUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
155.179 1.076 -0.070 0.252 13.209 16.936 0.000 12.724 44.127 199.306

## Table 36
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Prod Est | Changes | [10 empty] | APUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth | Spt |  | Total
99.745 0.779 -0.069 0.252 2.815 14.848 0.000 13.045 31.670 131.415
SAR Baseline History
Item/Event |  |  | SAR Planning Estimate (PE) |  |  |  | SAR Development Estimate (DE) |  |  | SAR Production Estimate (PdE) |  |  | Current Estimate
Milestone I |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Milestone II |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Milestone III |  |  | N/A |  |  |  | N/A |  |  | JUN 1989 |  |  | JUN 1989
IOC |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Total Cost (TY $M) |  |  | N/A |  |  |  | N/A |  |  | 5120.9 |  |  | 6577.1
Total Quantity |  |  | N/A |  |  |  | N/A |  |  | 33 |  |  | 33
Prog. Acq. Unit Cost (PAUC) |  |  | N/A |  |  |  | N/A |  |  | 155.179 |  |  | 199.306
Milestone III represents the GPS IIR Contract Award milestone.

## Table 37
USER EQUIPMENT
Unit Cost Report
|  |  | BY2000 $M | BY2000 $M
Unit Cost |  |  | Current UCR Baseline (FEB 2007 APB) | Current Estimate (DEC 2012 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 1688.5 |  |  |  | 1237.8
Quantity | 0 |  |  |  | 0
Unit Cost | -- |  |  |  | -- |  | --
Average Procurement Unit Cost (APUC)
Cost | 257.2 |  |  |  | 0
Quantity | 0 |  |  |  | 0
Unit Cost | -- |  |  |  | -- |  | --
|  |  | BY2000 $M | BY2000 $M
Unit Cost |  |  | Original UCR Baseline (FEB 2002 APB) | Current Estimate (DEC 2012 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost |  | 797.8 |  |  | 1237.8
Quantity Unit Cost |  | 0 -- |  |  | 0 -- |  | --
Average Procurement Unit Cost (APUC)
Cost |  | 254.3 |  |  | 0
Quantity Unit Cost |  | 0 -- |  |  | 0 -- |  | --

## Table 38
USER EQUIPMENT
Unit Cost History
[7 empty] | BY2000 $M |  |  |  |  | TY $M
|  |  | Date |  |  |  | PAUC |  | APUC |  |  | PAUC |  | APUC
Original APB |  |  | FEB 2002 |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
APB as of January 2006 |  |  | FEB 2003 |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Revised Original APB |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Prior APB |  |  | FEB 2003 |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Current APB |  |  | FEB 2007 |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Prior Annual SAR |  |  | DEC 2011 |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Current Estimate |  |  | DEC 2012 |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Prod Est | Changes | [11 empty] | PAUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000

## Table 39
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Prod Est | Changes | [9 empty] | APUC Current Est
| Econ | Qty |  | Sch | Eng | Est | Oth | Spt |  | Total
0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000
SAR Baseline History
Item/Event |  |  | SAR Planning Estimate (PE) |  |  | SAR Development Estimate (DE) |  |  | SAR Production Estimate (PdE) |  |  | Current Estimate
Milestone I |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Milestone II |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Milestone III |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
IOC |  |  | N/A |  |  | N/A |  |  | JAN 2002 |  |  | JAN 2002
Total Cost (TY $M) |  |  | N/A |  |  | 874.4 |  |  | 874.4 |  |  | 1418.7
Total Quantity |  |  | N/A |  |  | N/A |  |  | 0 |  |  | 0
Prog. Acq. Unit Cost (PAUC) |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A

## Table 40
Cost Variance
SPACE & CONTROL
Summary Then Year $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 1829.3 3291.6 -- 5120.9
Previous Changes
Economic |  | 9.7 |  | 22.3 |  | -- |  | 32
Quantity |  | -- |  | -2.3 |  | -- |  | -2.3
Schedule |  | -- |  | 8.3 |  | -- |  | 8.3
Engineering |  | 343 |  | 92.9 |  | -- |  | 435.9
Estimating |  | 69.9 |  | 473.7 |  | -- |  | 543.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -10.6 |  | 453.6 |  | -- |  | 443
Subtotal |  | 412 |  | 1048.5 |  | -- |  | 1460.5
Current Changes Economic |  | 0.1 |  | 3.4 |  | -- |  | 3.5
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -1 |  | 16.3 |  | -- |  | 15.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -23.1 |  | -- |  | -23.1
Subtotal |  | -0.9 |  | -3.4 |  | -- |  | -4.3
Total Changes |  | 411.1 |  | 1045.1 |  | -- |  | 1456.2
CE - Cost Variance |  | 2240.4 |  | 4336.7 |  | -- |  | 6577.1
CE - Cost & Funding |  | 2240.4 |  | 4336.7 |  | -- |  | 6577.1

## Table 41
Summary Base Year 2000 $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 1776.2 3239.4 -- 5015.6
Previous Changes
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 20 |  | -- |  | 20
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | 320.7 |  | 71.6 |  | -- |  | 392.3
Estimating |  | 55.9 |  | 350.9 |  | -- |  | 406.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -10.4 |  | 382.3 |  | -- |  | 371.9
Subtotal |  | 366.2 |  | 824.8 |  | -- |  | 1191
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -0.8 |  | 10.5 |  | -- |  | 9.7
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -17.4 |  | -- |  | -17.4
Subtotal |  | -0.8 |  | -6.9 |  | -- |  | -7.7
Total Changes |  | 365.4 |  | 817.9 |  | -- |  | 1183.3
CE - Cost Variance |  | 2141.6 |  | 4057.3 |  | -- |  | 6198.9
CE - Cost & Funding |  | 2141.6 |  | 4057.3 |  | -- |  | 6198.9
Previous Estimate: December 2011

## Table 42
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 0.1
Adjustment for current and prior escalation. (Estimating) | -0.1 | -0.1
Decrease due to Congressional reduction. (Estimating) | -0.7 | -0.9
RDT&E Subtotal | -0.8 | -0.9
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 3.4
Adjustment for current and prior escalation. (Estimating) | -0.3 | -0.5
Below Threshold Reprogramming to GPS III for Technical Operating Report (TOR) -12.9 -16.0
Reduction due to higher Air Force priorities. (Estimating) | -4.5 | -5.6
Increased allocated budget to fund launch and checkout costs. (Estimating) | 5.1 | 6.8
Increased allocated budget to sustain launch and checkout support. (Estimating) | 19 | 26.4
Adjustment for current and prior escalation. (Support) | -0.8 | -0.9
Increase in other support to fund modifications, antennas, master control stations and obsolescence issues. (Support) | 12.8 | 17.3
Increase in Initial Spares. (Support) | 0.4 | 0.5
Reclassification of funds from Support to Flyaway(-$5.2); Decrease in Technical and On-Orbit support due to a change in the GPS IIF launch manifest schedule (-$34.8M). | -29.8 | -40
(Subtotal)
Decrease in Technical and On-Orbit support due to a change in the GPS IIF launch manifest schedule. (Support) | -25.7 | -34.8
Reclassification of funds from Support to Flyaway. (Support) | -4.1 | -5.2
Reclassification of funds from Support to Flyaway. (Estimating) | 4.1 | 5.2
Procurement Subtotal | -6.9 | -3.4
Request for Equitable Adjustment (REA). (Estimating)

## Table 43
Cost Variance
USER EQUIPMENT
Summary Then Year $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 600.9 273.5 -- 874.4
Previous Changes
Economic |  | -1.9 |  | 0.2 |  | -- |  | -1.7
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | 307.4 |  | -- |  | -- |  | 307.4
Estimating |  | 500 |  | 0.4 |  | -- |  | 500.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -274.1 |  | -- |  | -274.1
Subtotal |  | 805.5 |  | -273.5 |  | -- |  | 532
Current Changes Economic |  | 0.4 |  | -- |  | -- |  | 0.4
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 11.9 |  | -- |  | -- |  | 11.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 12.3 |  | -- |  | -- |  | 12.3
Total Changes |  | 817.8 |  | -273.5 |  | -- |  | 544.3
CE - Cost Variance |  | 1418.7 |  | -- |  | -- |  | 1418.7
CE - Cost & Funding |  | 1418.7 |  | -- |  | -- |  | 1418.7

## Table 44
Summary Base Year 2000 $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 543.5 254.3 -- 797.8
Previous Changes
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | 274.6 |  | -- |  | -- |  | 274.6
Estimating |  | 410.3 |  | -- |  | -- |  | 410.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -254.3 |  | -- |  | -254.3
Subtotal |  | 684.9 |  | -254.3 |  | -- |  | 430.6
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 9.4 |  | -- |  | -- |  | 9.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 9.4 |  | -- |  | -- |  | 9.4
Total Changes |  | 694.3 |  | -254.3 |  | -- |  | 440
CE - Cost Variance |  | 1237.8 |  | -- |  | -- |  | 1237.8
CE - Cost & Funding |  | 1237.8 |  | -- |  | -- |  | 1237.8
Previous Estimate: December 2011

## Table 45
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A +0.4
Adjustment for current and prior escalation. (Estimating) -0.3 -0.4
Realignment of funds from Military GPS User Equipment (MGUE) to cover increased Modernized User Equipment (MUE) requirements. (Estimating)
+9.7 +12.3
RDT&E Subtotal +9.4 +12.3

## Table 46
Contracts
Appropriation: RDT&E
Contract Name GPS IIF Space Production Lot 1
Contractor The Boeing Company
Contractor Location 2201 Seal Beach Blvd. Seal Beach, CA 90740
Contract Number, Type F04701-96-C-0025/3, CPAF
Award Date April 22, 1996
Definitization Date April 22, 1996
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
157.6 N/A 3 194.7 N/A 3 711.4 696.0
Variance |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date (2/28/2013) |  |  |  | -254.8 |  |  | -1.5
Previous Cumulative Variances |  |  |  | -235.9 |  |  | -4.3
Net Change |  |  |  | -18.9 |  |  | 2.8
Cost And Schedule Variance Explanations
The unfavorable net change in the cost variance is due to resolution/exoneration of various technical issues in the Bus Power System, Attitude Determination Control System, and Thermal Control System. Likewise, excessive out- gassing observed on Space Vehicle (SV)-7 necessitated investigation and exoneration on SV-3.
The favorable net change in the schedule variance is due to completion of the majority of final SV-3 work packages.

## Table 47
Contract Comments
This contract is more than 90% complete; therefore, this is the final report for this contract.
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the GPS IIF satellite modernization contract rebaseline. This baseline implemented the direction given in the Acquisition Decision Memorandum dated May 2000. The current contract price is comprised of the baseline settlement funding adjustments for the actual work performed under the orginal baseline plus the final negotiated price for three modernized GPS IIF satellites (SV 1-3).
The contract information above pertains to the Block IIF Modernization 3020 Cost Plus Award Fee Production efforts for the first three space vehicles.
In December 2007, Boeing notified the government of their intention to implement an Over Target Baseline (OTB) for Space Vehicle (SV)1-3 production. With the government's concurrence, the "partial" OTB (for schedule only) was implemented in January 2008. This $47.6M adjustment to schedule variance brought the Program Adjustment total to $262.4M.
The new Budget at Completion (BAC) value after the March 2008 replan was $434M which fully budgeted the contractor's estimate to complete. The new program management baseline was validated with an Integrated Baseline Review (IBR) in June 2008, although the government remained concerned about the schedule and allocation of management reserve due to additional schedule erosion that was reported after December 2007.
Since the June 2008 IBR, Boeing has submitted quarterly estimated price changes and the Government has updated its independent estimated price at completion to account for these changes. As of December 2012, the contractor is reporting an estimated price at completion of $688.9M against a negotiated cost of $172.3M. The Government has reduced the Program Manager estimated price at completion from $702M in 2011 to $689.0M for 2012.

## Table 48
Appropriation: Procurement
Contract Name GPS IIF Sat Production SVs 4-6
Contractor The Boeing Company
Contractor Location Seal Beach, CA 90740
Contract Number, Type F04701-96-C-0025/4, FPIF
Award Date April 22, 1996
Definitization Date September 05, 2003
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
145.8 169.1 3 151.0 171.7 3 151.0 171.7
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FPIF contract.
General Contract Variance Explanation
The GPS IIF Sat Production Space Vehicles (SVs) 4-6 contract does not require Earned Value Management (EVM) as it is a Fixed Price Contract. The basis for not requiring EVM is predicated on the decision made in 1996 by the GPS program office. The program office has looked into adding EVM to this contract but the price of doing so greatly outweighed the benefits.
Contract Comments
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to changes in spacecraft configuration and design. Technical anomalies found during unit and system level testing drove upgrades in unit hardware to preserve mission assurance.
This contract is more than 90% complete; therefore, this is the final report for this contract.
The Government is responsible for 70% of any costs over the Target cost (and the contractor pays 30%) up to the ceiling price.

## Table 49
Appropriation: Procurement
Contract Name GPS IIF Sat Production SVs 7-9
Contractor The Boeing Company
Contractor Location Seal Beach, CA 90740
Contract Number, Type F04701-96-C-0025/5, FPIF
Award Date April 22, 1996
Definitization Date October 31, 2003
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
174.3 192.2 3 189.4 209.9 3 209.9 209.9
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FPIF contract.
General Contract Variance Explanation
The GPS IIF Sat Production SVs 7-9 contract does not require Earned Value Management (EVM) as it is a Fixed Price Contract.The basis for not requiring EVM is predicated on the decision made in 1996 by the GPS program office. The program office has looked into adding EVM to this contract but the price of doing so greatly outweighed the benefits.
Contract Comments
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to changes in spacecraft configuration and design. Technical anomalies found during unit and system level testing drove upgrades in unit hardware to preserve mission assurance.
The Government is responsible for 70% of any costs over the Target cost (and the contractor pays 30%) up to the ceiling price.
The Estimated Price at Completion increase is primarily due to a Crosslink Transponder and Data Unit modification ($16.3M), anomaly resolution, and integration/execution issues ($5.0M).

## Table 50
Appropriation: Procurement
Contract Name GPS IIF Sat Production SVs 10-12
Contractor The Boeing Company
Contractor Location Seal Beach, CA 90740
Contract Number, Type F04701-96-C-0025/6, FPIF
Award Date April 22, 1996
Definitization Date June 22, 2003
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
166.8 183.8 3 175.5 193.3 3 193.3 193.3
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FPIF contract.
General Contract Variance Explanation
The GPS IIF Sat Production SVs10-12 contract does not require Earned Value Management (EVM) as it is a Fixed Price Contract. The basis for not requiring EVM is predicated on the decision made in 1996 by the GPS program office. The program office has looked into adding EVM to this contract but the price of doing so greatly outweighed the benefits.
Contract Comments
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to changes in spacecraft configuration and design. Technical anomalies found during unit and system level testing drove upgrades in unit hardware to preserve mission assurance.
The Current Contract Price Ceiling and Contractor Estimated Price at Completion changed due to an L1 Power Undefinitized Contract Action in February 2012.
The Government is responsible for 70% of any costs over the Target cost (and the contractor pays 30%) up to the ceiling price.

## Table 51
Appropriation: RDT&E
Contract Name MUE RCD : Rockwell Collins
Contractor Rockwell-Collins
Contractor Location Cedar Rapids, IA 52498
Contract Number, Type FA8807-06-C-0001, CPAF
Award Date May 26, 2006
Definitization Date May 26, 2006
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
82.3 N/A 31 160.8 N/A 31 126.3 130.6
Variance |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date (3/31/2013) |  |  |  | -3.9 |  |  | -0.3
Previous Cumulative Variances |  |  |  | -17.5 |  |  | -0.6
Net Change |  |  |  | 13.6 |  |  | 0.3
Cost And Schedule Variance Explanations
The favorable net change in the cost variance is due to the execution of Modernized User Equipment (MUE) Completion (MUE-C) contract and the execution of an Over Target Baseline (OTB) total value of approximately
$35M.
The favorable net change in the schedule variance is due to the OTB mentioned above. This contractor has maintained a slightly ahead of schedule stance since the OTB and MUE-C contract award January 2012.

## Table 52
Contract Comments
This contract is more than 90% complete; therefore, this is the final report for this contract.
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to Rockwell Collins employing a model-based software engineering tool, which was unfamiliar to their staff. This caused them to underestimate the software engineering level of effort in their proposal and created the need for more engineers than planned to be applied to the task. Also, extremely poor digital Application Specific Integrated Circuits fabrication yields caused insufficient available hardware to employ in system integration, which led to delays and additional unplanned cost. In addition, the MUE-C Effort has been included in the contract price.
The cumulative variances decreased primarily due to an Over Target Baseline (OTB) conducted during FY 2012.
The Current Contract Quantity value was not previously reported in the SAR due to an oversight. The original and current contract quantity is 31, which is the number of ground-based receivers delivered to the program office.
The Contractor’s Estimated Price at Completion decreased from $130.5M at the end of December 2011 to
$126.3M at the end of March 2013 due to the final negotiated cost of the Completion effort and the OTB value.
The Government’s Estimated Price at Completion decreased from $135.0M at the end of December 2011 to
$130.6M at the end of March 2013. This decrease is due to adequate execution of the baseline after the OTB.
The contract price changed from $122.2M at the end of December 2011 to $160.8M at the end of March 2013. An OTB along with MUE-C effort was awarded early in 2012 of approximately $35M for Functional Qualification Test fixes and Interface Capabilities Document updates.

## Table 53
Appropriation: RDT&E
Contract Name MUE: L-3
Contractor L-3 Communications Corporation
Contractor Location 2 Federal Street Camden, NJ 08102-1004
Contract Number, Type FA8807-06-C-0003, CPAF
Award Date May 26, 2006
Definitization Date May 26, 2006
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
32.5 N/A 31 152.8 N/A 31 140.8 146.1
Variance |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date (3/31/2013) |  |  |  | 0 |  |  | -0.2
Previous Cumulative Variances |  |  |  | -18.2 |  |  | 0
Net Change |  |  |  | 18.2 |  |  | -0.2
Cost And Schedule Variance Explanations
The favorable net change in the cost variance is due to the execution of an Over Target Baseline (OTB) total value of approximately $23M.
The unfavorable net change in the schedule variance is due to delays in board layout activities on Modernized User Equipment (MUE) Completion (MUE-C) efforts.

## Table 54
Contract Comments
This contract is more than 90% complete; therefore, this is the final report for this contract.
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to engineering issues reported in the previous SAR.
The increased variances reported in the Contractor Comments section of this report are mainly attributable to an inscope contract modification referred to as the MUE-C effort. This in-scope effort is to address deficiencies identified during contractor functional qualification tests and to address updates to the system specification.
Variances were reset after the Over Target Baseline (OTB)/Integrated Basline Review in June 2012.
The Current Contract Quantity value was not previously reported in the SAR due to an oversight. The original and current contract quantity is 31, which is the number of ground-based receivers delivered to the program office.
The Contractor’s Estimated Price at Completion increased from $120.3M at the end of December 2011 to $140.8M at the end of March 2013. The increase is due to resulting final negotiations for the MUE-C efforts.
The Government’s Estimated Price at Completion increased from $124.5M at the end of December 2011 to
$146.1M at the end of March 2013. This increase incorporates the MUE-C effort as well as capture the latest contractor’s factored risks and additional software growth.
The contract price changed from $123.6M at the end of December 2011 to $152.8M at the end of March 2013 due an OTB along with MUE-C effort that was awarded early in 2012 of approximately $23M for Functional Qualification Testfixes and Interface Capabilities Documentupdates.
The initial contract Price was corrected from $77.4M to $32.5M to reflect the End of Month November 2007 Contract Performance Report (earliest archived).

## Table 55
Appropriation: RDT&E
Contract Name MUE: Raytheon
Contractor Raytheon Company
Contractor Location 2000 East El Segundo Blvd El Segundo, CA 90245-3507
Contract Number, Type FA8807-06-C-0004, CPAF
Award Date May 26, 2006
Definitization Date May 26, 2006
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
40.3 N/A 62 163.8 N/A 62 153.9 159.7
Variance |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date (3/31/2013) |  |  |  | -2.7 |  |  | -1
Previous Cumulative Variances |  |  |  | -17.9 |  |  | -0.2
Net Change |  |  |  | 15.2 |  |  | -0.8
Cost And Schedule Variance Explanations
The favorable net change in the cost variance is due to the Over-Target Baseline (OTB) conducted during FY 2012.
The unfavorable net change in the schedule variance is due to the contractor running slightly behind on multiple tasks and is negligible at this time.

## Table 56
Contract Comments
This contract is more than 90% complete; therefore, this is the final report for this contract.
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to unexpected problems with their cryptography design in preparation for their Ground Based-GPS Receiver Application Module- Standard Electronic Module Test Readiness Review caused delay and additional subcontractor costs. Previously, Raytheon experienced difficulty with their digital Application Specific Integrated Circuit requiring rework.
The Contractor’s Estimated Price at Completion of $114.3M at the end of December 2011 increased to $153.9M at the end of March 2013. This increase is due to the inclusion of the Modernized User Equipment (MUE) Completion (MUE-C) final negotiations along with an OTB valued at approx $35M.
The Government’s Estimated Price at Completion of $117.7M at the end of December 2011 increased to $159.7M at the end of March 2013.
The Current Contract Quantity value was not previously reported in the SAR due to an oversight. The original and current contract quantity is 62, which includes the 31 ground-based receivers and 31 aviation receivers delivered to the program office.
The contract price changed from $132.1M at the end of December 2011 to $163.8M at the end of March 2013. An OTB along with MUE-C effort was awarded early in 2012 of approximately $35M for Functional Qualification Testfixes and Interface Capabilities Document updates.
The initial contract Price was corrected from $105.7M to $40.3M to reflect the end of November 2007 Contractor Performance Report (earliest archived).

## Table 57
Deliveries and Expenditures SPACE & CONTROL
Deliveries To Date | Plan To Date | Actual To Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 33 | 27 | 33 | 81.82%
Total Program Quantities Delivered | 33 | 27 | 33 | 81.82%
Expenditures and Appr |  | opriations (TY $M)
Total Acquisition Cost | 6577.1 | Years Appropriated |  | 28
Expenditures To Date | 5365.3 | Percent Years Appropriated |  | 84.85%
Percent Expended | 81.58% | Appropriated to Date |  | 6451.9
Total Funding Years | 33 | Percent Appropriated |  | 98.1%
The above data is current as of 2/20/2013.
USER EQUIPMENT
Deliveries To Date | Plan To Date | Actual To Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 0 | 0 | 0 | --
Total Program Quantities Delivered | 0 | 0 | 0 | --
Expenditures and Appr |  | opriations (TY $M)
Total Acquisition Cost | 1418.7 | Years Appropriated |  | 20
Expenditures To Date | 1357.3 | Percent Years Appropriated |  | 100%
Percent Expended | 95.67% | Appropriated to Date |  | 1418.7
Total Funding Years | 20 | Percent Appropriated |  | 100%
The above data is current as of 2/20/2013.

## Table 58
Operating and Support Cost
SPACE & CONTROL
Assumptions and Ground Rules
Cost Estimate Reference:
None
Sustainment Strategy:
Operating and Support (O&S) costs include all costs of operating, maintaining, and supporting the Navstar Global Positioning System (GPS) spacecraft from the dedicated Master Control Station (MCS) located at Schriever Air Force Base (AFB), Colorado (CO) and the Alternate MCS (AMCS) located at Vandenberg AFB, California (CA). Also included are the costs of operating, maintaining, and supporting four dedicated GPS Ground Antennas (GAs) (located at Cape Canaveral Air Force Station (AFS), Florida (FL), Kwajalein Atoll, the Ascension Islands, and Diego Garcia); and six monitor stations (located at Schriever AFB, Maui, HI, Cape Canaveral, Kwajalein Atoll, the Ascension Islands, and Diego Garcia). Satellite operations at the MCS include mission planning, mission payload operations, and monitoring of satellite state of health. GAs transmit navigation data uploads and commands to the GPS spacecraft, and receive telemetry data from the spacecraft. Monitor stations receive mission payload data and transfer this data to the MCS to ensure spacecraft are operating as desired. These costs do not include the unallocated costs associated with the shared use of remote tracking stations, which are programmed and funded by the Air Force Satellite Control Network program elements. Costs reflect updates as of December 31, 2012.
The total O&S costs for the Space and Control system are not calculable in a manner that is relevant for comparison to other space systems, as each element within the system has a different life cycle and associated upgrade, repair, and/or replacement sustainment cycle.
The O&S budget is derived by collecting the United States Air Force (USAF) Force and Financial plan dollars in 3400 and 3080. These dollars, combined with the 3400 Depot Purchased Equipment Maintenance and Logistics Commodities make up our total O&S costs. The O&S costs are calculated taking a combination of actuals to date and programmatic funding/budget amounts from FY 2010-2018.
Antecedent Information:
None

## Table 59
Unitized O&S Costs BY2000 $M
Cost Element |  | SPACE & CONTROL Avg Annual Cost for 24-Sat Constellation |  |  | Block I/II Legacy (Antecedent) Avg Annual Cost for 24-Sat Constellation
Unit-Level Manpower |  |  | 27.5 |  | 19.2
Unit Operations |  |  | 0 |  | 0
Maintenance |  |  | 27.5 |  | 16.8
Sustaining Support |  |  | 6.9 |  | 2.4
Continuing System Improvements |  |  | 0 |  | 0
Indirect Support |  |  | 6.9 |  | 2.4
Other |  |  | 0 |  | 0
Total |  |  | 68.8 |  | 40.8
Unitized Cost Comments: The costs are calculated in the following manner:
The total cost per year is comprised of adding the 3400 and 3080 funds together. This year total is divided by 24 to get a per satellite cost (24 Satellite constellation). That number is then split into the four categories at the following percentages: Unit-Level Manpower 40%, Maintenance 40%, Sustaining Support 10%, Indirect Support 10%.
Once each cost element is calculated for the years in the SAR, an average of those 9 years is taken. The average is then multiplied back by 24 to get the cost of the 24 Satellite Constellation.
Total O&S Cost $M
| Current Production APB Objective/Threshold |  |  | Current Estimate
| SPACE & CONTROL |  |  | SPACE & CONTROL |  | Block I/II Legacy (Antecedent)
Base Year | 0.0 0.0 619.0 N/A
Then Year | 0.0 N/A 820.4 N/A
Total O&S Costs Comments:
The current O&S budget matches the FY 2014 President's Budget (PB) while the previous SARs did not fully report the PB.
Disposal Costs
None

## Table 60
USER EQUIPMENT
Assumptions and Ground Rules
Cost Estimate Reference: None
Sustainment Strategy:
The Modernized User Equipment program will not procure user equipment, but will instead develop User Equipment enabling technologies, demonstrate solutions, deliver prototypes, and assist platform managers.
Antecedent Information:
None
Unitized O&S Costs BY2000 $M
Cost Element |  | USER EQUIPMENT |  | Antecedent System (Antecedent)
Unit-Level Manpower |  | 0 |  | 0
Unit Operations |  | 0 |  | 0
Maintenance |  | 0 |  | 0
Sustaining Support |  | 0 |  | 0
Continuing System Improvements |  | 0 |  | 0
Indirect Support |  | 0 |  | 0
Other |  | 0 |  | 0
Total |  | -- |  | --
Unitized Cost Comments: None
Total O&S Cost $M
| Current Production APB Objective/Threshold |  | Current Estimate
| USER EQUIPMENT |  | USER EQUIPMENT |  | Antecedent System (Antecedent)
Base Year | 0.0 0.0 N/A N/A
Then Year | 0.0 N/A N/A N/A
Total O&S Costs Comments:
None
Disposal Costs
None