## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-239
NPOESS
As of December 31, 2011
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 3
Executive Summary |  | 4
Threshold Breaches |  | 5
Schedule |  | 6
Performance |  | 8
Track To Budget |  | 12
Cost and Funding |  | 13
Low Rate Initial Production |  | 16
Foreign Military Sales |  | 16
Nuclear Cost |  | 17
Unit Cost |  | 18
Cost Variance |  | 21
Contracts |  | 24
Deliveries and Expenditures |  | 25
Operating and Support Cost |  | 26

## Table 3
Program Information
Designation And Nomenclature (Popular Name)
National Polar-orbiting Operational Environmental Satellite System (NPOESS)
DoD Component
Air Force
Responsible Office
Responsible Office
Lt Col Edward Hospodar | Phone | 310-653-0746
Defense Weather Systems Directorate SMC/WM | Fax | 310-653-3337
483 North Aviation Blvd | DSN Phone | 633-0746
El Segundo, CA 90245-2808 | DSN Fax | 633-3337
Edward.Hospodar@losangeles.af.mil | Date Assigned | October 1, 2011
References
SAR Baseline (Production Estimate)
Under Secretary of the Air Force (USecAF) Approved Acquisition Program Baseline (APB) dated August 22, 2002
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated December 11, 2008
Mission and Description
The National Polar-orbiting Operational Environmental Satellite System (NPOESS) program was required to provide, for a period of at least 10 years, a remote sensing capability to acquire, receive at ground terminals, and disseminate to processing centers, global and regional environmental imagery and specialized meteorological information. This includes climatic, terrestrial, oceanographic, solar-geophysical and other data supporting Department of Commerce (DoC)/National Oceanic and Atmospheric Administration (NOAA) mission requirements, and Department of Defense (DoD) peacetime and wartime missions.

## Table 4
Executive Summary
NPOESS was planned to provide timely, high-quality weather and environmental information to military commanders enabling effective conduct of operations and to civil leaders for the protection of citizens, national resources and commerce.
On December 31, 2011, the FY 2012 National Defense Authorization Act (NDAA) and FY 2012 Appropriations Act were signed directing termination of the Defense Weather Satellite System (DWSS) program. Budget for FY 2012 was $43M to be used for termination activities (Program Element 0305178F). The Program Office is in the process of implementing the FY 2012 budget as enacted.
There are no significant software-related issues with this program at this time.
This is the final SAR submission for the program, because the program is terminated per Congressional direction in FY 2012.

## Table 5
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Unit Cost PAUC APUC
Explanation of Breach
Schedule breach was reported in the December 2010 SAR.
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 6
Schedule

## Table 7
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
Milestone I | MAR 1997 | MAR 1997 | SEP 1997 | MAR 1997
Payload Contract Awards | JUL 1997 | JUL 1997 | JAN 1998 | JUL 1997
Pre-Total System Performance Responsibility (pre-TSPR) Contract Award | NOV 2000 | NOV 2000 | MAY 2001 | DEC 1999
Milestone II/III | FEB 2002 | FEB 2002 | AUG 2002 | AUG 2002
Total System Responsibility (TSPR) Contract Award | MAR 2002 | MAR 2002 | SEP 2002 | AUG 2002
Initial Operational Capability (IOC) | JUL 2011 | APR 2013 | OCT 2013 | N/A 1
Follow-on Decision | OCT 2013 | N/A | N/A | N/A
Acquisitions and Operations System Contract | N/A | JUL 2007 | JUL 2007 | JUL 2007
Critical Design Review | N/A | APR 2009 | OCT 2009 | APR 2009
Build Approval (Procurement Option Decision) | N/A | JUN 2010 | DEC 2010 | N/A 1
C-1 Available for Launch | N/A | JAN 2013 | JUL 2013 | N/A 1
C-2 Available for Launch | N/A | JAN 2016 | JUL 2016 | N/A 1
Upgrade Decision (Follow-on Decision) | N/A | JUL 2016 | JAN 2017 | N/A 1
Full Operational Capability (FOC) | N/A | APR 2017 | OCT 2017 | N/A 1
C-3 Available for Launch | N/A | JAN 2018 | JUL 2018 | N/A 1
C-4 Available for Launch | N/A | JAN 2020 | JUL 2020 | N/A 1
1APB Breach
Change Explanations
None
Memo
On February 1, 2010, the Executive Office of the President restructured the NPOESS program. This restructure resulted in the Department of Defense (DoD), Department of Commerce (DoC), and National Aeronautics and Space Administration (NASA) no longer jointly acquiring the NPOESS program. Therefore, the current estimates for future NPOESS Schedule milestones no longer apply.
On December 31, 2011, the FY 2012 National Defense Authorization Act (NDAA) and FY 2012 Appropriations Act were signed directing termination of the Defense Weather Satellite System (DWSS) program. Budget for FY 2012 was $43M to be used for termination activities (Program Element 0305178F). The Program Office is in the process of implementing the FY 2012 budget as enacted.

## Table 8
Performance
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Key EDR Parameters
Atmospheric Vertical Moisture Profile
Measurement Uncertainty (Clear: Surface - 600mb) | +/- 10% | +/- 10% | Contract/Thre shold Value: Greater of 20% or 0.2 g kg-1 | TBD | 9.1% OR 0.2 g kg-1
Measurement Uncertainty (Cloudy: Surface - 600 mb) | +/- 10% | +/- 10% | Contract Value: Greater of 20% or 0.2g kg-1; Threshold Value: Greater of 25% or 0.25 g /kg | TBD | 13.3% or 0.2 g kg-1
Atmospheric Vertical Temperature Profile
Measurement Uncertainty (Clear: Surface - 300mb) | +/- 0.5K | +/- 0.5K | Contract Value: +/- 1.6K per 1 km layer; Threshold Value: +/- 2.5 to +/- 1.5K per 2km layer | TBD | 0.8K per 1 km layer
Measurement Uncertainty (Cloudy: Surface - 700mb) | +/- 0.5K | +/- 0.5K | Contract Value: +/- 2.5K per 1 km layer; Threshold Value: +/- 3.0 to +/- 1.5K per 2.5 km layer | TBD | 1.3K per 1 km layer
Imagery
Horizontal Resolution
Horizontal Cell Size at Nadir, clear | 0.1 km | 0.1 km | Contract Value: 0.4 km; Threshold | TBD | 0.4 km

## Table 9
Value: Regional .65 km (fine), Global 2.5 km (smooth)
Refresh Visible and IR bands
Average Revisit Time | 1 hr | 1 hr | Contract Value: At any location, the avg revisit time will be 4 hrs or less.; Threshold Value: Less than 4 hrs | TBD | At any location, the avg revisit time will be 4 hrs or less
Maximum Revisit Time | 1 hr | 1 hr | Contract Value: At any location, the max revisit time will be 6 hrs or less.; Threshold Value: 365 min (~6.1 hrs) | TBD | At any location, the max revisit time will be 6 hrs or less
Percent Compliance | N/A | 1 hr | Contract Value: At any location, at least 75% of the revisit times will be 4 hrs or less; Threshold Value: 56.0% of points with a refresh of 4 hrs or less | TBD | At any location, at least 75% of the revisit times will be 4 hrs or less
Sea Surface Temperature
Horizontal Resolution
Horizontal Cell Size at Nadir, clear | 0.25 km | 0.25 km | Contract Value: 1.0 km; Threshold Value: 1.1 km (Regiona l) 8.0 km (Global) | TBD | 0.75 km

## Table 10
Measurement Uncertainty, clear | +/- 0.1 deg C | +/- 0.1 deg C | Contract Value: +/- 0.5 deg C. Threshold Value: +/- 1.0 C (Coastal)+/- 0.5 C (Global- Nighttime) +/- 0.6 C (Global- Daytime). | TBD | 0.4K
Global Sea Surface Winds
Measurement Accuracy (Speed) | Greater of +/- 1 m/s or +/- 10% | Greater of +/- 1 m/s or +/- 10% | Contract Value: Greater of +/- 2 m/s or +/- 10%; Threshold Value: 2 m/s for WS < 5 m/s; 1 m/s for 5 m/s < WS < 20 m/s; No capability for WS > 20 m/s | TBD | Greater of +/- 2 m/s or +/- 10%
Soil Moisture (Surface) Sensing Depth | Surface to - 80 cm | Surface to - 80 cm | Contract Value: Surface (skin layer: - 0.1cm).; Threshold Value: Wet or Dry determinatio n of bare soil surface | TBD | Surface (skin layer: - 0.1cm
Key System Parameters
Data Access | Selective denial of all U.S. data (ARGOS and SARSAT excepted) | Selective denial of all U.S. environmenta l sensor data (ARGOS and SARSAT excepted) | Contract Value: Selective denial of all U.S. environmenta l sensor data (ARGOS and SARSAT excepted); | TBD | Select denial of all U.S. data (ARGOS and SARSAT excepted)

## Table 11
Threshold Value: Capability to deny exists but it is not "Selectab le"
Interoperability | 100% of top- level IERs | 100% of top- level IERs | Contract Value: 100% of critical top- level IERs; Threshold Value: Yes - Spacecraft to Field Terminals, Spacecraft to Centrals | TBD | 100% of critical top- level IERs
Requirements Source: Initial Operational Requirements Document (IORD II) dated December 10, 2001. Joint Requirements Oversight Council Memorandum (JROCM) 101-06 , dated June 2, 2006 .
Acronyms And Abbreviations
ARGOS - French Data Collection and Location System avg - average
C - Celsius
cm - centimeter deg - degree
EDR - Environmental Data Record g kg-1 - grams per kilogram
hr/hrs - hour/hours
IER - Information Exchange Requirements IR - Infrared
K - Kelvin
km - kilometer
m/s - meters per second max - maximum
mb - millibars
SARSAT - Search and Rescue Satellite Aided Tracking WS - Wind Speed
Change Explanations
None
Memo
The requirements in this section reflect the NPOESS program and do not necessarily represent the final Defenese Weather Satellite System (DWSS) requirements.

## Table 12
Track To Budget
General Memo
NPOESS was a Presidentially directed Tri-agency program composed of Department of Defense (DoD), Department of Commerce (DoC) and National Aeronautics and Space Administration (NASA) personnel. The Tri- agency Memorandum of Agreement (MOA) states that funding is provided jointly by DoD, through the Air Force, and DoC, through the National Oceanic and Atmospheric Administration (NOAA).
On February 1, 2010, the Executive Office of the President (EOP) restructured the National Polar-orbiting Operational Satellite System (NPOESS) Program. The DoD, the DoC, and NASA will no longer jointly acquire the NPOESS program.
The DoD component of the restructured NPOESS program was planned to be the Defense Weather Satellite System (DWSS) program. DWSS was planned to be a DoD only program, the DoC component of the NPOESS program was extracted (50% of total funding) from FY 1995 - FY 2010; DoD funds NPOESS through FY 2004 with Research, Development, Test, and Evaluation (RDT&E) via Program Element (PE) 0603434F and in FY 2005 - FY 2012 via PE 0301578F.
Launch Services were planned to be funded entirely with Missile Procurement, AF (MPAF) via Evolved Expendable Launch Vehicle (EELV) PE 0305393F. These costs were planned to be reported as part of the EELV program.
On December 31, 2011, the FY 2012 National Defense Authorization Act (NDAA) and FY 2012 Appropriations Act were signed directing termination of the DWSS program. Budget for FY 2012 was $43M to be used for termination activities (PE 0305178F). The Program Office is in the process of implementing the FY 2012 budget as enacted.
RDT&E
APPN 3600 BA 05 PE 0305178F (Air Force)
Project 4056 National Polar-orbiting
Operational Environmental Sat. Sys./National Polar-orbiting Operational Environmental Sat. Syst.
(Sunk)
APPN 3600 BA 04 PE 0603434F (Air Force)
Project 4056 National Polar-orbiting
Operational Environmental Sat. Sys./National Polar-orbiting Operational Environmental Sat. Syst.
(Sunk)
Procurement
APPN 3020 BA 05 PE 0305178F (Air Force)
ICN NPS000 National Polar-orbiting
Operational Environmental Satellite System.
(Sunk)

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
| BY2002 $M |  |  |  |  | BY2002 $M |  | TY $M
Appropriation | SAR Baseline Prod Est |  | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Prod Est | Current APB Production Objective | Current Estimate
RDT&E | 4401.7 |  | 7346.8 |  | 8113.7 | 2837.6 |  | 4765.5 | 8412.1 | 3130.6
Procurement | 1136.3 |  | 2446.9 |  | 2691.6 | 0 |  | 1352.1 | 3332 | 0
Flyaway | 1136.3 |  | -- |  | -- | 0 |  | 1352.1 | -- | 0
Recurring | 1136.3 |  | -- |  | -- | 0 |  | 1352.1 | -- | 0
Non Recurring | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Support | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Other Support | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Initial Spares | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
MILCON | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Acq O&M | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Total | 5538 |  | 9793.7 |  | N/A | 2837.6 |  | 6117.6 | 11744.1 | 3130.6
The total NPOESS program costs include both Department of Commerce (DoC) and Department of Defense (DoD) funding budgeted on a 50/50-share basis by year. The numbers listed in the Production Estimate represent the total NPOESS satellites, ground activities, launch support, Government Program Office support, Integrated Program Office (IPO) share of National Aeronautics and Space Administration (NASA)/IPO NPOESS Preparatory Program, and related risk reduction efforts.
On February 1, 2010, the Executive Office of the President (EOP) restructured the National Polar-orbiting Operational Satellite System (NPOESS) Program. The DoD, the DoC, and NASA will no longer jointly acquire the NPOESS program.
On December 31, 2011, the FY 2012 National Defense Authorization Act (NDAA) and FY 2012 Appropriations Act were signed directing termination of the Defense Weather Satellite System (DWSS) program. Budget for FY 2012 was $43M to be used for termination activities (Program Element 0305178F). The Program Office is in the process of implementing the FY 2012 budget as enacted.
Quantity |  | SAR Baseline Prod Est |  | Current APB Production |  |  | Current Estimate
RDT&E |  | 2 |  | 2 |  |  | 0
Procurement |  | 4 |  | 2 |  |  | 0
Total |  | 6 |  | 4 |  |  | 0
The Current Estimate (CE) in the SAR reflects the current DoD plan to acquire zero (0) satellites.

## Table 14
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2013 President's Budget / December 2011 SAR (TY$ M)
On February 1, 2010, the Executive Office of the President (EOP) restructured the National Polar-orbiting Operational Satellite System (NPOESS) Program. The DoD, the DoC, and NASA will no longer jointly acquire the NPOESS program.
On December 31, 2011, the FY 2012 National Defense Authorization Act (NDAA) and FY 2012 Appropriations Act were signed directing termination of the Defense Weather Satellite System (DWSS) program. Budget for FY 2012 was $43M to be used for termination activities (Program Element 0305178F). The Program Office is in the process of implementing the FY 2012 budget as enacted.
Appropriation |  | Prior | FY2012 |  | FY2013 |  | FY2014 |  | FY2015 |  | FY2016 |  | FY2017 |  | To Complete |  | Total
RDT&E |  | 3087.6 | 43 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3130.6
Procurement |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
MILCON |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2013 Total |  | 3087.6 | 43 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3130.6
PB 2012 Total |  | 3088.6 | 444.9 |  | 526.8 |  | 515.6 |  | 423.7 |  | 417.9 |  | 390.7 |  | 1495.1 |  | 7303.3
Delta |  | -1 | -401.9 |  | -526.8 |  | -515.6 |  | -423.7 |  | -417.9 |  | -390.7 |  | -1495.1 |  | -4172.7
Quantity | Undistributed |  |  | Prior |  | FY2012 |  | FY2013 | FY2014 | FY2015 |  | FY2016 |  | FY2017 |  | To Complete |  | Total
Development | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Production | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2013 Total | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2012 Total | 2 |  |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 2
Delta | -2 |  |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | -2

## Table 15
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1995 | -- | -- | -- | -- | -- | -- | 11.7
1996 | -- | -- | -- | -- | -- | -- | 14
1997 | -- | -- | -- | -- | -- | -- | 28.2
1998 | -- | -- | -- | -- | -- | -- | 32.6
1999 | -- | -- | -- | -- | -- | -- | 56.2
2000 | -- | -- | -- | -- | -- | -- | 58.3
2001 | -- | -- | -- | -- | -- | -- | 72.1
2002 | -- | -- | -- | -- | -- | -- | 154.2
2003 | -- | -- | -- | -- | -- | -- | 227.5
2004 | -- | -- | -- | -- | -- | -- | 269.7
2005 | -- | -- | -- | -- | -- | -- | 303.3
2006 | -- | -- | -- | -- | -- | -- | 319
2007 | -- | -- | -- | -- | -- | -- | 340.4
2008 | -- | -- | -- | -- | -- | -- | 331
2009 | -- | -- | -- | -- | -- | -- | 300.5
2010 | -- | -- | -- | -- | -- | -- | 394.9
2011 | -- | -- | -- | -- | -- | -- | 174
2012 | -- | -- | -- | -- | -- | -- | 43
Subtotal | -- | -- | -- | -- | -- | -- | 3130.6

## Table 16
Annual Funding BY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1995 | -- | -- | -- | -- | -- | -- | 12.7
1996 | -- | -- | -- | -- | -- | -- | 14.9
1997 | -- | -- | -- | -- | -- | -- | 29.6
1998 | -- | -- | -- | -- | -- | -- | 34
1999 | -- | -- | -- | -- | -- | -- | 58
2000 | -- | -- | -- | -- | -- | -- | 59.3
2001 | -- | -- | -- | -- | -- | -- | 72.3
2002 | -- | -- | -- | -- | -- | -- | 153.1
2003 | -- | -- | -- | -- | -- | -- | 222.8
2004 | -- | -- | -- | -- | -- | -- | 257.6
2005 | -- | -- | -- | -- | -- | -- | 282.5
2006 | -- | -- | -- | -- | -- | -- | 288.4
2007 | -- | -- | -- | -- | -- | -- | 299.9
2008 | -- | -- | -- | -- | -- | -- | 285.8
2009 | -- | -- | -- | -- | -- | -- | 256.1
2010 | -- | -- | -- | -- | -- | -- | 332.3
2011 | -- | -- | -- | -- | -- | -- | 143.5
2012 | -- | -- | -- | -- | -- | -- | 34.8
Subtotal | -- | -- | -- | -- | -- | -- | 2837.6
Low Rate Initial Production
There is no Low Rate Initial Production (LRIP) for NPOESS.
Foreign Military Sales
None

## Table 17
Nuclear Cost
None

## Table 18
Unit Cost
Unit Cost Report
|  | BY2002 $M | BY2002 $M
Unit Cost |  | Current UCR Baseline (DEC 2008 APB) | Current Estimate (DEC 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 9793.7 |  |  | 2837.6
Quantity | 4 |  |  | 0
Unit Cost | 2448.425 |  |  | -- |  | --
Average Procurement Unit Cost (APUC)
Cost | 2446.9 |  |  | 0
Quantity | 2 |  |  | 0
Unit Cost | 1223.45 |  |  | -- |  | --
|  | BY2002 $M | BY2002 $M
Unit Cost |  | Revised Original UCR Baseline (DEC 2008 APB) | Current Estimate (DEC 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 9793.7 |  |  | 2837.6
Quantity | 4 |  |  | 0
Unit Cost | 2448.425 |  |  | -- |  | --
Average Procurement Unit Cost (APUC)
Cost | 2446.9 |  |  | 0
Quantity | 2 |  |  | 0
Unit Cost | 1223.45 |  |  | -- |  | --
The Executive Office of the President (EOP) restructured the National Polar-orbiting Operational Satellite System (NPOESS) Program. The Department of Defense (DoD), the Department of Commerce (DoC), and the National Aeronautics and Space Administration (NASA) will no longer jointly acquire NPOESS program.
On December 31, 2011, the FY 2012 National Defense Authorization Act (NDAA) and FY 2012 Appropriations Act were signed directing termination of the Defense Weather Satellite System (DWSS) program. Budget for FY 2012 was $43M to be used for termination activities (Program Element 0305178F). The Program Office is in the process of implementing the FY 2012 budget as enacted.

## Table 19
Unit Cost History
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
[7 empty] | BY2002 $M |  |  |  |  | TY $M
|  |  | Date |  |  |  | PAUC |  | APUC |  |  | PAUC |  | APUC
Original APB |  |  | AUG 2002 |  |  |  | 923 |  | 284.075 |  |  | 1019.6 |  | 338.025
APB as of January 2006 |  |  | JAN 2005 |  |  |  | 1046.083 |  | 312.25 |  |  | 1132.583 |  | 367.05
Revised Original APB |  |  | DEC 2008 |  |  |  | 2448.425 |  | 1223.45 |  |  | 2936.025 |  | 1666
Prior APB |  |  | JAN 2005 |  |  |  | 1046.083 |  | 312.25 |  |  | 1132.583 |  | 367.05
Current APB |  |  | DEC 2008 |  |  |  | 2448.425 |  | 1223.45 |  |  | 2936.025 |  | 1666
Prior Annual SAR |  |  | DEC 2010 |  |  |  | 3013.15 |  | N/A |  |  | 3651.65 |  | N/A
Current Estimate |  |  | DEC 2011 |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Initial PAUC Prod Est | Changes | [11 empty] | PAUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
1019.600 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Prod Est | Changes | [11 empty] | APUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
338.025 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000

## Table 20
SAR Baseline History
Item/Event | SAR Planning Estimate (PE) | SAR Development Estimate (DE) | SAR Production Estimate (PdE) | Current Estimate
Milestone I | MAR 1997 | N/A | MAR 1997 | MAR 1997
Milestone II | SEP 2000 | N/A | FEB 2002 | AUG 2002
Milestone III | DEC 2011 | N/A | OCT 2013 | N/A
IOC | DEC 2010 | N/A | JUL 2011 | N/A
Total Cost (TY $M) | 5329 | N/A | 6117.6 | 3130.6
Total Quantity | 5 | N/A | 6 | 0
Prog. Acq. Unit Cost (PAUC) | 1065.8 | N/A | 1019.6 | N/A

## Table 21
Cost Variance
Cost Variance Summary
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Prod Est) | 4765.5 | 1352.1 | -- | 6117.6
Previous Changes
Economic | 65.5 | -63.1 | -- | 2.4
Quantity | 1840.4 | -3782.8 | -- | -1942.4
Schedule | 897.6 | 82.6 | -- | 980.2
Engineering | -567.6 | -292.1 | -- | -859.7
Estimating | 301.9 | 2703.3 | -- | 3005.2
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | 2537.8 | -1352.1 | -- | 1185.7
Current Changes
Economic | 70.8 | -- | -- | 70.8
Quantity | -4234.1 | -- | -- | -4234.1
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -9.4 | -- | -- | -9.4
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -4172.7 | -- | -- | -4172.7
Total Changes | -1634.9 | -1352.1 | -- | -2987
CE - Cost Variance | 3130.6 | -- | -- | 3130.6
CE - Cost & Funding | 3130.6 | -- | -- | 3130.6

## Table 22
Summary Base Year 2002 $M
| RDT&E |  | Proc | MILCON | Total
SAR Baseline (Prod Est) Previous Changes |  | 4401.7 | 1136.3 | -- | 5538
Economic |  | -- | -- | -- | --
Quantity |  | 1299.7 | -2897.4 | -- | -1597.7
Schedule |  | 682.2 | -- | -- | 682.2
Engineering |  | -437.9 | -239.2 | -- | -677.1
Estimating |  | 80.6 | 2000.3 | -- | 2080.9
Other |  | -- | -- | -- | --
Support |  | -- | -- | -- | --
Subtotal |  | 1624.6 | -1136.3 | -- | 488.3
Current Changes Economic |  | -- | -- | -- | --
Quantity |  | -3180.9 | -- | -- | -3180.9
Schedule |  | -- | -- | -- | --
Engineering |  | -- | -- | -- | --
Estimating |  | -7.8 | -- | -- | -7.8
Other |  | -- | -- | -- | --
Support |  | -- | -- | -- | --
Subtotal |  | -3188.7 | -- | -- | -3188.7
Total Changes |  | -1564.1 | -1136.3 | -- | -2700.4
CE - Cost Variance |  | 2837.6 | -- | -- | 2837.6
CE - Cost & Funding |  | 2837.6 | -- | -- | 2837.6
Previous Estimate: December 2010

## Table 23
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 70.8
Quantity decreased from two (2) to zero (0) based on the FY 2012 National Defense Authorization Act and FY 2012 Appropriations Act directing termination of the | -3180.9 | -4234.1
Defense Weather Satellite System (DWSS) program. (Quantity)
Adjustment for current and prior escalation. (Estimating) | -7.8 | -9.4
RDT&E Subtotal | -3188.7 | -4172.7

## Table 24
Contracts
Appropriation: RDT&E
Contract Name NPOESS A&O
Contractor Northrop Grumman Aerospace System
Contractor Location Redondo Beach, CA 90278
Contract Number, Type F04701-02-C-0502, CPAF
Award Date August 23, 2002
Definitization Date August 23, 2002
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
2942.7 N/A 2 5919.0 N/A 2 5951.9 5934.3
Variance |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date (9/30/2010) |  |  |  | -196 |  |  | -29
Previous Cumulative Variances |  |  |  | -196 |  |  | -29
Net Change |  |  |  | 0 |  |  | 0
Cost And Schedule Variance Explanations
None
Contract Comments
The difference between the initial contract price target and the current contract price target is due to program restructure and subsequent termination.
Earned Value Management reporting was suspended August 2010.

## Table 25
Deliveries and Expenditures
The Executive Office of the President (EOP) restructured the National Polar-orbiting Operational Satellite System (NPOESS) Program. The Department of Defense (DoD), the Department of Commerce (DoC), and the National Aeronautics and Space Administration (NASA) will no longer jointly acquire NPOESS program.
Defense Weather Satellite System (DWSS) will be funded by DoD only, so the DoC component of the old NPOESS program has been extracted (50% of total funding) from FY 1995 - FY 2010. FY 2011 - FY 2012 will consist of Air Force Research Development Test & Evaluation (RDT&E) funding only for the DWSS program.
Deliveries To Date | Plan To Date |  | Actual To Date | Total Quantity |  | Percent Delivered
Development | 0 |  | 0 |  | 0 | --
Production | 0 |  | 0 |  | 0 | --
Total Program Quantities Delivered | 0 |  | 0 |  | 0 | --
Expenditures and |  | Appropriations (TY $M)
Total Acquisition Cost | 3130.6 | Years Appropriated |  |  | 18
Expenditures To Date | 2990.2 | Percent Years Appropriated |  |  | 100%
Percent Expended | 95.52% | Appropriated to Date |  |  | 3130.6
Total Funding Years | 18 | Percent Appropriated |  |  | 100%

## Table 26
Operating and Support Cost
Assumptions And Ground Rules
As part of the NPOESS restructure into Defense Weather Satellite System (DWSS) and Joint Polar Satellite System (JPSS), the Common Ground System (CGS) was planned to be developed and funded by NOAA/NASA through JPSS. The cost sharing agreement between National Oceanic and Atmospheric Administration (NOAA)/National Aeronautics and Space Administration (NASA) and the Department of Defense (DoD) for the Operating and Support (O&S) costs of the CGS was under review.
On December 31, 2011, the FY 2012 National Defense Authorization Act (NDAA) and FY 2012 Appropriations Act were signed directing termination of the Defense Weather Satellite System (DWSS) program. Budget for FY 2012 was $43M to be used for termination activities (Program Element 0305178F). The Program Office is in the process of implementing the FY 2012 budget as enacted.
Antecedent Systems: NPOESS was planned to replace the following civil and DoD polar-orbiting environmental satellite systems: Defense Meteorological Satellite Program, National Oceanic and Atmospheric Administration Polar Operational Environmental Satellite, and the National Aeronautics and Space Administration Earth Observing System. However, data is not available for comparison.
Costs BY2002 $M
Cost Element | NPOESS Average Annual System Cost | Antecedent Systems
Unit-Level Manpower | -- | --
Unit Operations | -- | --
Maintenance | -- | --
Sustaining Support | -- | --
Continuing System Improvements | -- | --
Indirect Support | -- | --
Other | -- | --
Total Unitized Cost (Base Year 2002 $) | -- | --
Total O&S Costs $M | NPOESS | Antecedent Systems
Base Year | -- | --
Then Year | -- | --