## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-289
Tactical Tomahawk RGM-109E/UGM 109E Missile (Tactical Tomahawk)
As of December 31, 2012
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 4
Executive Summary |  | 5
Threshold Breaches |  | 6
Schedule |  | 7
Performance |  | 9
Track To Budget |  | 10
Cost and Funding |  | 11
Low Rate Initial Production |  | 17
Foreign Military Sales |  | 18
Nuclear Cost |  | 18
Unit Cost |  | 19
Cost Variance |  | 22
Contracts |  | 25
Deliveries and Expenditures |  | 27
Operating and Support Cost |  | 28

## Table 3
Program Information
Program Name
Tactical Tomahawk RGM-109E/UGM 109E Missile (Tactical Tomahawk)
DoD Component
Navy
Responsible Office
Responsible Office
CAPT Joe Mauser Program Executive Office
Unmanned Aviation and Strike Weapons 47123 Buse Rd., Bldg. 2272, Rm. 247
Patuxent River, MD 20670-1547
Phone Fax
DSN Phone DSN Fax
301-757-6408
301-757-6412
757-6408
--
joe.mauser@navy.mil Date Assigned July 29, 2011
References
SAR Baseline (Production Estimate)
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated August 3, 2004
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated April 11, 2011

## Table 4
Mission and Description
The Tomahawk Missile counters threats against United States Forces by destroying fixed and mobile targets, which include command, control and logistic systems, industrial and other high value targets, and fixed and mobile defense systems. The Tomahawk Weapons System (TWS) consists of the Block IV Tactical Tomahawk All-Up-Round (AUR) missile, the Tomahawk Command and Control System (TC2S), and the Tactical Tomahawk Weapons Control System (TTWCS). The AUR is an Acquisition Category (ACAT) IC program, TC2S is an ACAT II program, and TTWCS is an ACAT III program. Block IV Tactical Tomahawk provides major modernization to the existing Tomahawk technology by increasing responsiveness and flexibility at a more affordable production unit cost.
Key elements of the Block IV Tactical Tomahawk AUR design are an improved navigation and guidance computer, improved anti-jam Global Positioning System (GPS) capability, improved responsiveness and flexibility through two- way satellite communications for in-flight re-targeting, a loiter capability, and the ability to send a single-frame Battle Damage Indication Image (BDII) of over-flown areas prior to impact. Modern manufacturing techniques and Commercial Off-the-Shelf/Government Off-the-Shelf (COTS/GOTS) hardware provide this improved capability.
Additionally, the life cycle costs are significantly reduced by extending the re-certification interval from eight years for the currently fielded Block III to 15 years for the Block IV Tactical Tomahawk AUR. The Block IV Tactical Tomahawk AUR will maximize the use of existing TWS program and logistic support. There is no change to the system's overall support concept.

## Table 5
Executive Summary
An FY 2012 production contract for the procurement of 361 Block IV Tactical Tomahawk AUR Missiles was signed on June 7, 2012. The FY 2012 contract utilized additional FY 2011 funding received through an OMNIBUS reprogramming action (DOD Serial Number FY 11-21-R PA signed September 13, 2011) to replenish the 221 Tomahawk missile expenditures incurred during Libyan Operations. The FY 2013 contract option was exercised on December 17, 2012 for an additional 252 Block IV Tactical Tomahawk AUR Missiles. As of April 30, 2013, a total of 2947 Block IV Tactical Tomahawk AUR missiles have been delivered, which includes 65 FMS missiles for the United Kingdom. To address rising unit costs, the program successfully implemented Cost Reduction Initiatives (CRIs) that resulted in $15M of cost avoidance benefits applicable to the FY 2009 - FY 2011 missile procurements. Additional cost savings were achieved during FY 2012 - FY 2013 contract negotiations, which was driven by lowering cost of key suppliers, significant reductions in RMS fixed labor costs, and rate-related savings associated with the procurement of higher quantities of missiles.
As of April 30, 2013, RMS has achieved 46 consecutive months of meeting or exceeding the contracted Block IV Tactical Tomahawk AUR missile delivery requirements. The current combined Block III and IV fleet inventory is sufficient to satisfy projected 2013 USN operational load-outs.
The FY 2009 - FY 2011 follow-on production contract for Block IV Tactical Tomahawk AUR with RMS was fully delivered in April 2013, four months ahead of schedule.
There are no significant software-related issues with this program at this time.

## Table 6
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 7
Schedule
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
Milestone II Development Contract Award | JUN 1998 | JUN 1998 | DEC 1998 | JUN 1998
LRIP Authorization | SEP 2002 | SEP 2002 | MAR 2003 | SEP 2002
LRIP 2 | JAN 2003 | JAN 2003 | JUL 2003 | JAN 2003
Operational Assessment | JAN 2003 | JAN 2003 | JUL 2003 | JAN 2003
TECHEVAL
Start | MAR 2003 | MAR 2003 | SEP 2003 | MAR 2003
Complete | OCT 2003 | OCT 2003 | APR 2004 | OCT 2003
OPEVAL
Start | DEC 2003 | DEC 2003 | JUN 2004 | DEC 2003
Complete | MAR 2004 | MAR 2004 | SEP 2004 | MAR 2004
Initial Operational Capability | MAR 2004 | MAR 2004 | SEP 2004 | MAY 2004
Milestone III | MAY 2004 | MAY 2004 | NOV 2004 | AUG 2004
FRP Contract Award | MAY 2004 | MAY 2004 | NOV 2004 | AUG 2004

## Table 8
Acronyms And Abbreviations
FRP - Full Rate Production
LRIP - Low Rate Initial Production OPEVAL - Operational Evaluation TECHEVAL - Technical Evaluation
Change Explanations
None

## Table 9
Performance
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
MR (%) | 0.9 | 0.9 | 0.86 | 0.93 | 0.93
CR (%) | 0.96 | 0.96 | 0.94 | 1 | 1
(Ch-1)
Requirements Source: Operational Requirements Document (ORD) #641-76-04 dated August 11, 2004
Acronyms And Abbreviations
CR - Cruise Reliability MR - Mission Reliability
Change Explanations
(Ch-1) MR (%) Current estimate decreased from 0.96 to 0.93 upon integration of Operation Odyssey Dawn reliability performance data. Reliability performance continues to exceed threshold requirements.
Classified Performance information is provided in the classified annex to this submission.
Memo
The data set for CR and MR includes Operational Test Launches (OTLs), combat expenditures, and accounting for corrective actions in the missile inventory. Test events include Operational Evaluation (OPEVAL), Technical Evaluation (TECHEVAL), Tactical Tomahawk Penetrating Vehicle flights, contractor flights, ground tests, and combat expenditures. Corrected failures that meet all of the following criteria have been removed from the data set: root cause of a failure is known, the failure mode is eliminated by hardware or software modification, the modification has been appropriately verified by test, and the modification has been implemented throughout the entire missile population.

## Table 10
Track To Budget
RDT&E
APPN 1319 BA 07 PE 0204229N (Navy)
Project A0545 TACTICAL
TOMAHAWK/TACTICAL TOMAHAWK
Project A2658 TACTICAL
TOMAHAWK/TACTICAL TOMAHAWK
Project A2659 TACTICAL
TOMAHAWK/TACTICAL TOMAHAWK
(Shared) (Sunk)
(Sunk)
(Sunk)
Procurement
APPN 1507 BA 02 PE 0204229N (Navy)
ICN 210100 TACTICAL TOMAHAWK

## Table 11
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
|  | BY1999 $M | [6 empty] | BY1999 $M
Appropriation |  | SAR Baseline Prod Est |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate
TY $M
SAR Baseline Prod Est | Current APB Production Objective |  |  | Current Estimate
RDT&E |  | 564.9 |  |  |  | 564.9 |  | 621.4 |  | 565.1 |  | 581 | 581.9 | 581.9
Procurement |  | 2412.4 |  |  |  | 4962.6 |  | 5458.8 |  | 5071.4 |  | 2709.3 | 6303.5 | 6527.1
Flyaway |  | 2378.8 |  |  |  | -- |  | -- |  | 4978.2 |  | 2671.3 | -- | 6407.5
Recurring |  | 2342.9 |  |  |  | -- |  | -- |  | 4942.9 |  | 2633.2 | -- | 6369.8
Non Recurring |  | 35.9 |  |  |  | -- |  | -- |  | 35.3 |  | 38.1 | -- | 37.7
Support |  | 33.6 |  |  |  | -- |  | -- |  | 93.2 |  | 38 | -- | 119.6
Other Support |  | 33.6 |  |  |  | -- |  | -- |  | 93.2 |  | 38 | -- | 119.6
Initial Spares |  | 0 |  |  |  | -- |  | -- |  | 0 |  | 0 | -- | 0
MILCON |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Acq O&M |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Total |  | 2977.3 |  |  |  | 5527.5 |  | N/A |  | 5636.5 |  | 3290.3 | 6885.4 | 7109
Confidence Level for Current APB Cost 51% - The estimate to support this program, like most cost estimates, is built upon a product-oriented work breakdown structure based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which we have been successful.
Quantity |  |  | SAR Baseline Prod Est |  |  |  | Current APB Production |  |  |  | Current Estimate
RDT&E |  |  | 10 |  |  |  | 10 |  |  |  | 10
Procurement |  |  | 2780 |  |  |  | 4730 |  |  |  | 4951
Total |  |  | 2790 |  |  |  | 4740 |  |  |  | 4961

## Table 12
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2014 President's Budget / December 2012 SAR (TY$ M)
RDT&E | 581.9 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 581.9
Procurement | 3792.1 |  |  | 309 |  |  | 312.4 |  |  | 322.8 |  | 330.2 |  |  | 336.2 |  |  | 342.2 |  |  | 782.2 |  |  | 6527.1
MILCON | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Acq O&M | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
PB 2014 Total | 4374 |  |  | 309 |  |  | 312.4 |  |  | 322.8 |  | 330.2 |  |  | 336.2 |  |  | 342.2 |  |  | 782.2 |  |  | 7109
PB 2013 Total | 4374 |  |  | 309 |  |  | 323 |  |  | 329.2 |  | 336.6 |  |  | 342.6 |  |  | 384.5 |  |  | 786 |  |  | 7184.9
Delta | 0 |  |  | 0 |  |  | -10.6 |  |  | -6.4 |  | -6.4 |  |  | -6.4 |  |  | -42.3 |  |  | -3.8 |  |  | -75.9
Program funding and production quantities listed in this SAR are consistent with the FY 2014 President's Budget (PB). The FY 2014 PB did not reflect the enacted DoD appropriation for FY 2013, nor sequestration; it reflected the President's requested amounts for FY 2013.
Appropriation |  | Prior | FY2013 |  |  | FY2014 |  |  | FY2015 |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  |  | To Complete |  |  | Total
Quantity | Undistributed |  |  |  | Prior |  |  | FY2013 |  | FY2014 | FY2015 |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  |  | To Complete |  |  | Total
Development | 10 |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 10
Production | 0 |  |  |  | 3298 |  |  | 196 |  | 196 | 196 |  | 196 |  |  | 196 |  |  | 196 |  |  | 477 |  |  | 4951
PB 2014 Total | 10 |  |  |  | 3298 |  |  | 196 |  | 196 | 196 |  | 196 |  |  | 196 |  |  | 196 |  |  | 477 |  |  | 4961
PB 2013 Total | 10 |  |  |  | 3298 |  |  | 196 |  | 196 | 196 |  | 196 |  |  | 196 |  |  | 225 |  |  | 448 |  |  | 4961
Delta | 0 |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  |  | 0 |  |  | -29 |  |  | 29 |  |  | 0

## Table 13
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1998 | -- | -- | -- | -- | -- | -- | 49.8
1999 | -- | -- | -- | -- | -- | -- | 122.4
2000 | -- | -- | -- | -- | -- | -- | 164.2
2001 | -- | -- | -- | -- | -- | -- | 105.4
2002 | -- | -- | -- | -- | -- | -- | 63
2003 | -- | -- | -- | -- | -- | -- | 57.3
2004 | -- | -- | -- | -- | -- | -- | 19.8
Subtotal | 10 | -- | -- | -- | -- | -- | 581.9

## Table 14
Annual Funding BY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 1999 $M | Non End Item Recurring Flyaway BY 1999 $M | Non Recurring Flyaway BY 1999 $M | Total Flyaway BY 1999 $M | Total Support BY 1999 $M | Total Program BY 1999 $M
1998 | -- | -- | -- | -- | -- | -- | 49.9
1999 | -- | -- | -- | -- | -- | -- | 121.3
2000 | -- | -- | -- | -- | -- | -- | 160.3
2001 | -- | -- | -- | -- | -- | -- | 101.5
2002 | -- | -- | -- | -- | -- | -- | 60.1
2003 | -- | -- | -- | -- | -- | -- | 53.9
2004 | -- | -- | -- | -- | -- | -- | 18.1
Subtotal | 10 | -- | -- | -- | -- | -- | 565.1

## Table 15
Annual Funding TY$
1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2002 | 25 | 46.2 | -- | 24 | 70.2 | 2.4 | 72.6
2003 | 377 | 420.9 | -- | 13.7 | 434.6 | 2.9 | 437.5
2004 | 322 | 344.6 | -- | -- | 344.6 | 7.4 | 352
2005 | 298 | 268.5 | -- | -- | 268.5 | 8.7 | 277.2
2006 | 409 | 363.1 | -- | -- | 363.1 | 9.9 | 373
2007 | 355 | 345.3 | -- | -- | 345.3 | 7.7 | 353
2008 | 496 | 470.8 | -- | -- | 470.8 | 5 | 475.8
2009 | 207 | 275.2 | -- | -- | 275.2 | 5 | 280.2
2010 | 196 | 270.2 | -- | -- | 270.2 | 6.3 | 276.5
2011 | 417 | 587.7 | -- | -- | 587.7 | 9 | 596.7
2012 | 196 | 292 | -- | -- | 292 | 5.6 | 297.6
2013 | 196 | 303.2 | -- | -- | 303.2 | 5.8 | 309
2014 | 196 | 306.5 | -- | -- | 306.5 | 5.9 | 312.4
2015 | 196 | 316.8 | -- | -- | 316.8 | 6 | 322.8
2016 | 196 | 324 | -- | -- | 324 | 6.2 | 330.2
2017 | 196 | 329.9 | -- | -- | 329.9 | 6.3 | 336.2
2018 | 196 | 335.8 | -- | -- | 335.8 | 6.4 | 342.2
2019 | 239 | 381.9 | -- | -- | 381.9 | 6.5 | 388.4
2020 | 238 | 387.2 | -- | -- | 387.2 | 6.6 | 393.8
Subtotal | 4951 | 6369.8 | -- | 37.7 | 6407.5 | 119.6 | 6527.1

## Table 16
Annual Funding BY$
1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 1999 $M | Non End Item Recurring Flyaway BY 1999 $M | Non Recurring Flyaway BY 1999 $M | Total Flyaway BY 1999 $M | Total Support BY 1999 $M | Total Program BY 1999 $M
2002 | 25 | 43.5 | -- | 22.6 | 66.1 | 2.3 | 68.4
2003 | 377 | 388.4 | -- | 12.7 | 401.1 | 2.7 | 403.8
2004 | 322 | 308.8 | -- | -- | 308.8 | 6.7 | 315.5
2005 | 298 | 234.2 | -- | -- | 234.2 | 7.6 | 241.8
2006 | 409 | 308.9 | -- | -- | 308.9 | 8.4 | 317.3
2007 | 355 | 287.5 | -- | -- | 287.5 | 6.4 | 293.9
2008 | 496 | 385.8 | -- | -- | 385.8 | 4.1 | 389.9
2009 | 207 | 222.2 | -- | -- | 222.2 | 4.1 | 226.3
2010 | 196 | 214.3 | -- | -- | 214.3 | 5 | 219.3
2011 | 417 | 455.8 | -- | -- | 455.8 | 7 | 462.8
2012 | 196 | 222.1 | -- | -- | 222.1 | 4.3 | 226.4
2013 | 196 | 226.3 | -- | -- | 226.3 | 4.3 | 230.6
2014 | 196 | 224.5 | -- | -- | 224.5 | 4.3 | 228.8
2015 | 196 | 227.7 | -- | -- | 227.7 | 4.3 | 232
2016 | 196 | 228.5 | -- | -- | 228.5 | 4.4 | 232.9
2017 | 196 | 228.4 | -- | -- | 228.4 | 4.3 | 232.7
2018 | 196 | 228.1 | -- | -- | 228.1 | 4.4 | 232.5
2019 | 239 | 254.6 | -- | -- | 254.6 | 4.3 | 258.9
2020 | 238 | 253.3 | -- | -- | 253.3 | 4.3 | 257.6
Subtotal | 4951 | 4942.9 | -- | 35.3 | 4978.2 | 93.2 | 5071.4

## Table 17
Low Rate Initial Production
Low Rate Initial Production (LRIP-1) was 25 missiles, LRIP-2 was 167 missiles, and LRIP-3 was 210 missiles, which brings the total Block IV Tactical Tomahawk All-Up-Round LRIP quantity to 402 missiles.
| Initial LRIP Decision | Current Total LRIP
Approval Date | 4/12/2001 8/26/2003 25 402 LRIP ADM LRIP III ASR/AP 2002 2002 2007 2007
Approved Quantity
Reference
Start Year
End Year

## Table 18
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Memo
United Kingdom | 2013-03-11 | 4 | 5.7 | Torpedo Tube Launch (TTL) Block IV missiles were purchased in FY 2013; cost includes missiles and ancillary equipment.
United Kingdom | 2006-02-10 | 65 | 64 | TTL Block IV missiles were purchased in FY 2006; cost includes missiles and ancillary equipment. All United Kingdom missiles on contract have been delivered.
Nuclear Cost
None

## Table 19
Unit Cost
Unit Cost Report
|  | BY1999 $M | BY1999 $M
Unit Cost |  | Current UCR Baseline (APR 2011 APB) | Current Estimate (DEC 2012 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 5527.5 |  |  | 5636.5
Quantity | 4740 |  |  | 4961
Unit Cost | 1.166 |  |  | 1.136 |  |  | -2.57
Average Procurement Unit Cost (APUC)
Cost | 4962.6 |  |  | 5071.4
Quantity | 4730 |  |  | 4951
Unit Cost | 1.049 |  |  | 1.024 |  |  | -2.38
|  | BY1999 $M | BY1999 $M
Unit Cost |  | Original UCR Baseline (SEP 1999 APB) | Current Estimate (DEC 2012 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 1683.7 |  |  | 5636.5
Quantity | 1365 |  |  | 4961
Unit Cost | 1.233 |  |  | 1.136 |  | -7.87
Average Procurement Unit Cost (APUC)
Cost | 1158.4 |  |  | 5071.4
Quantity | 1353 |  |  | 4951
Unit Cost | 0.856 |  |  | 1.024 |  | 19.63

## Table 20
Unit Cost History
[12 empty] | BY1999 $M | [5 empty] | TY $M
[5 empty] | Date | [6 empty] | PAUC |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  |  |  |  | SEP 1999 | [6 empty] | 1.233 |  | 0.856 |  |  |  | 1.365 |  |  | 0.984
APB as of January 2006 |  |  |  |  | APR 2005 | [6 empty] | 1.076 |  | 0.913 |  |  |  | 1.237 |  |  | 1.069
Revised Original APB |  |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  |  | N/A |  |  | N/A
Prior APB |  |  |  |  | APR 2005 | [6 empty] | 1.076 |  | 0.913 |  |  |  | 1.237 |  |  | 1.069
Current APB |  |  |  |  | APR 2011 | [6 empty] | 1.166 |  | 1.049 |  |  |  | 1.453 |  |  | 1.333
Prior Annual SAR |  |  |  |  | DEC 2011 | [6 empty] | 1.153 |  | 1.042 |  |  |  | 1.448 |  |  | 1.334
Current Estimate |  |  |  |  | DEC 2012 | [6 empty] | 1.136 |  | 1.024 |  |  |  | 1.433 |  |  | 1.318
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Dev Est | Changes | [18 empty] | PAUC Prod Est
| Econ |  | Qty |  |  | Sch |  | Eng |  | Est |  |  | Oth |  |  | Spt |  | Total
1.365 -0.015 0.324 0.117 0.000 -0.716 0.000 0.104 -0.186 1.179
Current SAR Baseline to Current Estimate (TY $M)
PAUC Prod Est |  | Changes | [16 empty] | PAUC Current Est
|  | Econ |  | Qty |  |  | Sch |  | Eng |  | Est |  | Oth |  | Spt |  | Total
1.179 0.030 -0.128 0.071 0.025 0.241 0.000 0.015 0.254 1.433

## Table 21
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Dev Est | Changes | [13 empty] | APUC Prod Est
| Econ |  | Qty |  | Sch | Eng |  | Est |  | Oth | Spt |  | Total
0.984 -0.015 0.325 0.097 0.000 -0.520 0.000 0.104 -0.009 0.975
Current SAR Baseline to Current Estimate (TY $M)
APUC Prod Est | Changes | [13 empty] | APUC Current Est
| Econ | Qty |  |  | Sch |  | Eng |  | Est | Oth | Spt |  |  | Total
0.975 0.030 -0.041 0.072 0.025 0.242 0.000 0.015 0.343 1.318
SAR Baseline History
Item/Event |  |  |  | SAR Planning Estimate (PE) |  |  |  |  | SAR Development Estimate (DE) |  |  | SAR Production Estimate (PdE) |  |  |  | Current Estimate
Milestone I |  |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  |  | N/A
Milestone II |  |  |  | N/A |  |  |  |  | JUN 1998 |  |  | JUN 1998 |  |  |  | JUN 1998
Milestone III |  |  |  | N/A |  |  |  |  | JUN 2003 |  |  | MAY 2004 |  |  |  | AUG 2004
IOC |  |  |  | N/A |  |  |  |  | APR 2003 |  |  | MAR 2004 |  |  |  | MAY 2004
Total Cost (TY $M) |  |  |  | N/A |  |  |  |  | 1863.4 |  |  | 3290.3 |  |  |  | 7109
Total Quantity |  |  |  | N/A |  |  |  |  | 1365 |  |  | 2790 |  |  |  | 4961
Prog. Acq. Unit Cost (PAUC) |  |  |  | N/A |  |  |  |  | 1.365 |  |  | 1.179 |  |  |  | 1.433

## Table 22
Cost Variance
Summary Then Year $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 581.0 2709.3 -- 3290.3
Previous Changes
Economic |  | 0.9 |  | 100 |  | -- |  | 100.9
Quantity |  | -- |  | 1920.9 |  | -- |  | 1920.9
Schedule |  | -- |  | 352.8 |  | -- |  | 352.8
Engineering |  | -- |  | 43 |  | -- |  | 43
Estimating |  | -- |  | 1403.4 |  | -- |  | 1403.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 73.6 |  | -- |  | 73.6
Subtotal |  | 0.9 |  | 3893.7 |  | -- |  | 3894.6
Current Changes Economic |  | -- |  | 46.7 |  | -- |  | 46.7
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 1.2 |  | -- |  | 1.2
Engineering |  | -- |  | 80.7 |  | -- |  | 80.7
Estimating |  | -- |  | -207.2 |  | -- |  | -207.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 2.7 |  | -- |  | 2.7
Subtotal |  | -- |  | -75.9 |  | -- |  | -75.9
Total Changes |  | 0.9 |  | 3817.8 |  | -- |  | 3818.7
CE - Cost Variance |  | 581.9 |  | 6527.1 |  | -- |  | 7109
CE - Cost & Funding |  | 581.9 |  | 6527.1 |  | -- |  | 7109

## Table 23
Summary Base Year 1999 $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 564.9 2412.4 -- 2977.3
Previous Changes
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 1357.4 |  | -- |  | 1357.4
Schedule |  | -- |  | 274.3 |  | -- |  | 274.3
Engineering |  | -- |  | 32.6 |  | -- |  | 32.6
Estimating |  | 0.2 |  | 1022.9 |  | -- |  | 1023.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 57.4 |  | -- |  | 57.4
Subtotal |  | 0.2 |  | 2744.6 |  | -- |  | 2744.8
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | 56.5 |  | -- |  | 56.5
Estimating |  | -- |  | -144.3 |  | -- |  | -144.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 2.2 |  | -- |  | 2.2
Subtotal |  | -- |  | -85.6 |  | -- |  | -85.6
Total Changes |  | 0.2 |  | 2659 |  | -- |  | 2659.2
CE - Cost Variance |  | 565.1 |  | 5071.4 |  | -- |  | 5636.5
CE - Cost & Funding |  | 565.1 |  | 5071.4 |  | -- |  | 5636.5
Previous Estimate: December 2011

## Table 24
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A +46.7
Stretched out the procurement buy profile in FY 2018-2020 to remain within budget controls. (Schedule)
0.0 +1.2
Increased costs required to resolve missile component obsolescence. (Engineering) | 56.5 |  |  | 80.7
Adjustment for current and prior escalation. (Estimating) | -7.5 |  |  | -9.6
Decrease in hardware estimates based on contract negotiations. (Estimating) | -136.8 |  |  | -197.6
Adjustment for current and prior escalation. (Support) | 0 |  |  | -0.2
Increase in Other Support due to stretch out of procurement profile. (Support) | 2.2 |  |  | 2.9
Procurement Subtotal | -85.6 |  |  | -75.9

## Table 25
Contracts
Appropriation: Procurement
Contract Name BLK IV TACTOM FRP FY09-11
Contractor Raytheon Missile Systems
Contractor Location Tucson, AZ 85747
Contract Number, Type N00019-09-C-0007, FFP
Award Date March 31, 2009
Definitization Date March 31, 2009
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
207.3 N/A 207 710.2 N/A 599 710.2 710.2
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP contract.
Contract Comments
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to each of the two procurement options being exercised for 196 missiles, resulting in 392 additional missiles.
The FY 2009 base year contract was awarded in March 2009 for the procurement of 207 missiles at a contract price of $207.3M. Both the FY 2010 and FY 2011 missile and capsule options have been exercised, increasing the total contract procurement quantity to 599 missiles and the total contract price to $710.2M (as of April 30, 2013).
Full Rate Production (FY 2009 - FY 2011) includes a base year plus two option years. Contract was signed on March 31, 2009 to procure up to 1050 Block IV Tactical Tomahawk All-Up-Round (AUR) missiles.
Current contract price includes United States Navy missiles, subsurface variant capsules, production support and ancillary equipment.
Deliveries complete as of April 30, 2013. December 2012 SAR will be the final report for this contract.

## Table 26
Appropriation: Procurement
Contract Name BLK IV TACTOM FRP FY12-13
Contractor Raytheon Missile Systems
Contractor Location Tucson, AZ 85747
Contract Number, Type N00019-12-C-2000, FFP
Award Date June 07, 2012
Definitization Date June 07, 2012
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
377.8 N/A 361 690.7 N/A 613 690.7 690.7
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP contract.
Contract Comments
This is the first time this contract is being reported.
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the FY 2013 procurement option being exercised for an additional 252 missiles.
The FY 2012 base year contract was awarded in June 2012 for the procurement of 361 missiles at a price of
$377.8M. The FY 2013 contract option for United States Navy (USN) missiles was exercised in December 2012. An additional option was also exercised in March 2013 to procure four (4) Foreign Military Sales (FMS) missiles resulting in an increase of the total contract procurement quantity to 617 missiles (USN and FMS) and the total contract price to $690.7M (as of April 30, 2013).
Full Rate Production (FY 2012 - FY 2013) includes a base year plus one option year. Contract was signed on June 7, 2012 to procure up to 740 Block IV Tactical Tomahawk All-Up-Round (AUR) missiles.
Current contract price includes USN missiles, subsurface variant capsules, production support and ancillary equipment, in addition to $5.7M Foreign Military Sales (FMS) Torpedo Tube Launch (TTL) procurement dollars.
Additional FY 2011 funding was received through OMNIBUS reprogramming action to replenish the 221 Tomahawk missile expenditures during Libyan Operations.
Libyan Operations replenishment missiles were procured utilizing the FY 2012 procurement contract.

## Table 27
Deliveries and Expenditures
Deliveries To Date | Plan To | Date | Actual To Date | Total Quantity |  | Percent Delivered
Development | 10 |  | 10 |  | 10 | 100%
Production | 2840 |  | 2882 |  | 4951 | 58.21%
Total Program Quantities Delivered | 2850 |  | 2892 |  | 4961 | 58.29%
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 7109 | Years Appropriated |  |  | 16
Expenditures To Date | 3766 | Percent Years Appropriated |  |  | 69.57%
Percent Expended | 52.98% | Appropriated to Date |  |  | 4683
Total Funding Years | 23 | Percent Appropriated |  |  | 65.87%
The above data is current as of 4/30/2013.

## Table 28
Operating and Support Cost
Tactical Tomahawk
Assumptions and Ground Rules
Cost Estimate Reference:
The Block IV Tactical Tomahawk All-Up-Round (AUR) estimate is from the Life Cycle Cost Estimate prepared for the MS III decision in May of 2004. This original estimate was revalidated in February 2013.
Sustainment Strategy:
The Operating and Support costs include: maintenance, recertification, and demilitarization and disposal costs of the AUR; an Operational flight test program to track Tomahawk Weapons System performance; and sustainment of Tactical Tomahawk Command and Control/Weapons Control Systems.
The Block IV Tactical Tomahawk AUR Sustainment Strategy is based on the original Tomahawk Program “Wooden Round" concept which relies upon a fifteen (15) year missile warranty, and features limited maintenance outside of the Original Equipment Manufacturer (OEM). The OEM serves as the depot activity and is responsible for conducting the majority of the maintenance for the Block IV missile, and their efforts are largely covered by the 15 year warranty. The Block IV Tactical Tomahawk depot maintenance is expected to be less than the Block III Tomahawk due to a 15 year recertification interval, for a total inventory of 4,730 missiles. Recertifications are anticipated to begin in FY 2019. The total life of a Block IV Tactical Tomahawk is anticipated to be thirty (30)
years.
Organizational level maintenance is limited to visual inspections, nitrogen checks (Torpedo Tube Launch (TTL) variant only), missile inventory checks (surface only), Mode 7 alignment confidence checks (submarine only) and minor unscheduled maintenance (corrosion control, etc.). Intermediate level maintenance is limited to missile ID checks, receipt inspections, and nitrogen checks.
Antecedent Information:
The Block III Tomahawk AUR is the antecedent system of the Block IV Tactical Tomahawk AUR.

## Table 29
Unitized O&S Costs BY1999 $M
Cost Element | Tactical Tomahawk Average Annual Cost of Block IV Missile Inventory | Tomahawk Block III (Antecedent) Average Annual Cost of Block III Missile Inventory
Unit-Level Manpower | 0 | 0
Unit Operations | 0 | 0
Maintenance | 0 | 0
Sustaining Support | 35.2 | 36.6
Continuing System Improvements | 0 | 0
Indirect Support | 0 | 0
Other | 21.5 | 65.4
Total | 56.7 | 102
Unitized Cost Comments:
The unit represented is the average annual cost (FY 2004 - FY 2049) of the Block IV Tactical Tomahawk missile inventory in BY 1999 dollars.
As a result of the February 2013 revalidation, the average annual cost was reduced. Realized costs were utilized through FY 2012, and revised budget projections through FY 2049 to derive the average annual costs reported in the December 2012 SAR.
Depot recertification activities at the Original Equipment Manufacturer (OEM) facility will begin in FY 2019 and are captured in the 'Other' cost section.

## Table 30
Total O&S Cost $M
| Current Production APB Objective/Threshold | Current Estimate
| Tactical Tomahawk | Tactical Tomahawk | Tomahawk Block III (Antecedent)
Base Year | 0.0 0.0 2549.0 3058.4
Then Year | 0.0 N/A 3855.5 N/A
Total O&S Costs Comments:
The Block IV Tactical Tomahawk O&S Costs from the May 2004 Life Cycle Cost Estimate have been reviewed and revalidated as of February 2013.
The revalidated O&S estimate is based on actual and projected expenditures from program inception in FY 2004 through end of service life in FY 2049. The unitized costs shown above are the total Base Year O&S total shown below, divided by the expected 45 year service life (FY 2004 - FY 2049). Missile recertification costs (shown as "other" in the unitized cost summary above) is an estimate for recertifying the entire APB quantity (4,730 missiles), divided by 45 years. The recertification program, however, is only scheduled to last for approximately 15 years, so the unitized recertification cost should not be used for annual budging purposes. The current estimated cost of recertifying a Block IV missile is based on a Block III recertification cost, plus inflation. Additionally, the actual number of recertifications expected per year was based on delivery date plus an initial 15 year service life. After 15 years, missiles should be returned for recertification. Historically, budget constraints have caused schedule variances between anticipated recertification dates and actual recertification dates. As a result, while the duration of the Block IV Tactical Tomahawk missile recertification program is estimated to last 15 years, the actual program is likely to extend beyond 15 years. Demilitarization and disposal costs were removed from the O&S total as part of the revalidation.
Disposal Costs
Disposal costs for the Block IV Tactical Tomahawk AUR were estimated to be $48.2M in FY 1999 dollars.