## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-220
C-130J Hercules Transport Aircraft (C-130J)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 12
Cost and Funding 13
Low Rate Initial Production 23
Foreign Military Sales 24
Nuclear Costs 24
Unit Cost 25
Cost Variance 28
Contracts 31
Deliveries and Expenditures 35
Operating and Support Cost 36

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
C-130J Hercules Transport Aircraft (C-130J)
DoD Component
Air Force
Responsible Office
Mr. Anthony Zompetti 2275 D Street
Bldg. 16 Rm.149
Wright Patterson Air Force Base, OH 45433-7142
anthony.zompetti.1@us.af.mil
Phone: | 937-255-7100
Fax: | 937-255-3207
DSN Phone: | 785-7100
DSN Fax: | 785-3207
Date Assigned: | July 1, 2013
References
SAR Baseline (Production Estimate)
Air Force Acquisition Executive (AFAE) Approved Acquisition Program Baseline (APB) dated October 25, 1996
Approved APB
Air Force Acquisition Executive (AFAE) Approved Acquisition Program Baseline (APB) dated April 25, 2007

## Table 6
Mission and Description
The C-130J Hercules Transport Aircraft (C-130J) is a medium-range, tactical airlift aircraft designed primarily for transport of cargo and personnel within a theater of operations. Variants of the C-130J perform other missions including rescue and recovery, air refueling, special operations, fire-fighting and weather reconnaissance.
The C-130J can carry more than 40,000 pounds of cargo (pallets or a varied number of wheeled vehicles) or be configured to carry up to 84 paratroopers. The enhanced cargo handling system reduces crew workload and can be quickly adapted to accommodate any combination of passenger, cargo or aero-medical airlift missions. Two primary methods of aerial delivery are used for equipment delivery: parachutes pulling the load from the aircraft; and the Container Delivery System that uses the force of gravity to pull supplies from the aircraft. The C-130J can also operate from austere landing zones with as little as 3,000 feet of dirt runway.
A stretched version of the C-130J offers aircrews 55 feet of cargo compartment length. The additional 15 feet in length over previous versions of the C-130 translates into 30% more useable volume for increased seating, litters, pallets or airdrop platforms thus providing a significant advantage in the reduction of sorties necessary for mission completion. The C-130J offers a greater value when compared to any other tactical airlifter.

## Table 7
Executive Summary
The C-130J Program Office continued to support warfighter requirements worldwide. Program Office efforts included continued management of all United States Government (USG) C-130J variant aircraft production and initial sparing, several USG specific modification programs, management of twelve FMS cases and an international development program for block upgrades for the C-130J fleet.
Lockheed Martin delivered a total of nineteen aircraft in CY 2015 to USG and FMS customers. Twenty-four USG and five FMS C-130J aircraft are estimated for delivery in CY 2016.
In CY 2015, the C-130J Program Office continued toward awarding a second Multi-Year Procurement (MYP II: 78 aircraft plus options) across FY 2014 through FY 2018 buy years. Due to prolonged MYP II negotiations, FY 2014 and FY 2015 obligations were behind OSD goals for most of the year. MYP II negotiations concluded on October 8, 2015. In November 2015, the C-130J Program Office issued two Undefinitized Contract Actions for the FY 2014 procurement (17 aircraft) and FY 2015 Advance Procurement for FY 2016 buys (28 aircraft). On November 6, 2015, the CAPE provided an updated independent estimate of savings for MYP II. The CAPE estimated the MYP II provided a substantial cost savings of 11.5% over annual year procurements. MYP II contract award occurred on December 30, 2015 following 30-Day Congressional Notification, which began on November 30, 2015.
The Army-led and funded, Extracted Container Delivery System – High Speed (formerly named the High Speed Container Delivery System) expanded the C-130J airdrop performance envelope and reduced the altitude required for airdrops. The Air Force released the initial capability in March 2014 and flight release for operational evaluation at Yuma Proving Grounds in January 2015. Based on the program success, U.S. Army Natick Soldier Systems and Air Mobility Command are continuing airdrop procedure and capability evaluation through FY 2016 for transition of the capability to follow-on airdrop programs and incorporation into operations.
In February 2015, a major fire completely destroyed the production facility of General Electric (GE) Dowty, the manufacturer of the C-130J's propeller blades. A robust effort was undertaken by GE Dowty, Lockheed Martin, Rolls-Royce, and the USG to mitigate the effects this catastrophic event would have on supporting the fielded C-130J fleet and the C-130J production line in Marietta, GA. The USG provided assets to GE Dowty and the C-130J production line to help further mitigate any effect the gap in blade production would have on the delivery of new C-130Js to the USG. To date, GE Dowty has been able to re-establish their propeller blade production capability and have shipped the first production blades to the C-130J production line to facilitate continued delivery of C-130J aircraft to the USG. Based upon projected yield of the production blades from the new facility, full catch-up (to include the payback of borrowed assets from the USG) will occur in September 2017.
International Collaborative Block Upgrade (BU) Programs:
The initial BU 8.1 program incorporates ten new capabilities with emphasis on the Civil Data Link, Automatic Dependent Surveillance Broadcast-Out, and Identification Friend or Foe Transponder Mode-5. The BU 8.1 program increased scope in July 2015 by adding seven high priority capabilities. BU 8.1 common core completion is estimated for August 2016.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Program Initiation | Jun 1996 | Jun 1996 | Jan 1997 | Jun 1996
FY 1996 Basic Aircraft Contract | Nov 1996 | Nov 1996 | May 1997 | Nov 1996
First Delivery | Oct 1997 | Mar 1999 | Sep 1999 | Mar 1999
Change Explanations

## Table 10
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Cockpit Crew (All Missions)
2 | 2 | 2 | 2 | 2
Maximum Payload (lbs)
39311 | 39311 | 38910 | 39311 | 39311
Normal Maximum Take-off Gross Weight (lbs)
155000 | 155000 | 155000 | 155000 | 155000
Design Landing Gross Weight (lbs)
130000 | 130000 | 130000 | 130000 | 130000
Take-off Distance at Max Take-off Weight over 50 ft Obstacle (ft)
4530 | 4530 | 5142 | 4530 | 4530
Landing Distance at Design Landing Weight Over 50 ft Obstacle (ft)
2500 | 2500 | 2550 | 2500 | 2500
Shortfield Capability
Assault Take-off Distance (Takeoff Ground Roll) (ft)
2700 | 2700 | 2700 | 2700 | 2700
Assault Landing Distance (Ground Roll) (ft)
1800 | 1800 | 1800 | 1800 | 1800
IMC Airdrop Accuracy - Total System Error (ft)
158 | 158 | 158 | 158 | 158
Cruising Speed at 100,000 lbs @25,000 ft (KTAS)
342 | 342 | 315 | 342 | 342
Max Range with 42,764 lbs fuel & 29,722 lbs Payload (NM)
3070 | 3070 | 2350 | 3070 | 3070
Environmental Factors - Operational Ambient Temperature (deg F)
-40 -+120 | -40 -+120 | -40 -+120 | -40 -+120 | -40 -+120
Sortie Reliability (SR) (%)
95.4 | 95.4 | 94.2 | 97.7% | 94.2
Mission Capable Rate (MC) (%)
84 | 84 | 81 | 76.8 | 81
Mean Repair Time (hrs)
6.3 | 6.3 | 7.4 | 5.7hrs | 7.4

## Table 11
Mean Time Between Removal (MTBR) (hrs)
4.6 | 4.6 | 3.8 | 4.6 hrs | 3.8
Mean-Time Between Maintenance Corrective Actions (MTBMC) (hrs)
1.2 | 1.2 | 1 | 1.0 hrs | 1
Requirements Reference
ORD AMC 205-91-IV/III-A (Revision II) dated January 21, 2005
Change Explanations
None
Acronyms and Abbreviations
% - Percent
deg F - degree Farenheit ft - feet
hrs - Hours
IMC - Instrument Meteorological Conditions KTAS - Knots True Airspeed
lbs - Pounds
NM - Nautical Miles

## Table 12
Track to Budget
RDT&E
Appn |  |  | BA | PE
Air Force 3600 07 0401132F
Project | Name
675061 C-130J (Shared)
675062 C-130J Trainers (Sunk)
Air Force 3600 04 0603852F
|  | Project |  |  | Name
|  | 644025 |  | C-130J |  | (Sunk)
Procurement
Air Force |  | 3010 02 |  | 0401132F
|  | Line Item |  |  | Name
|  | C130J |  | C-130J |  | (Sunk)
Air Force |  | 3010 05 |  | 0401132F
|  | Line Item |  |  | Name
|  | C130J |  | C-130J Mods |  | (Shared)
MILCON
Air Force |  | 3300 01 |  | 0401132F
|  | Project |  |  | Name
|  | VARIOUS |  | Military Construction
Acq O&M
Air Force |  | 3400 01 |  | 0401132F
|  | Project |  |  | Name
Appn |  |  | BA | PE
Appn |  |  | BA | PE
Appn |  |  | BA | PE
021M Operation & Maintenance - AF (Shared) (Sunk)

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 1996 $M | [5 empty] | BY 1996 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  |  | Current APB Production Objective |  | Current Estimate
RDT&E | 8.9 |  |  | 349.1 | 384 |  |  | 281 |  | 9.2 |  |  |  | 446.6 |  | 361.4
Procurement | 721.8 |  |  | 13041 | 14345.1 |  |  | 11844.9 |  | 830.5 |  |  |  | 15910.8 |  | 15371.6
Flyaway | -- |  |  | -- | -- |  |  | 9728.8 |  | -- |  |  |  | -- |  | 12750.5
Recurring | -- |  |  | -- | -- |  |  | 9590.2 |  | -- |  |  |  | -- |  | 12560.5
Non Recurring | -- |  |  | -- | -- |  |  | 138.6 |  | -- |  |  |  | -- |  | 190
Support | -- |  |  | -- | -- |  |  | 2116.1 |  | -- |  |  |  | -- |  | 2621.1
Other Support | -- |  |  | -- | -- |  |  | 1096.6 |  | -- |  |  |  | -- |  | 1375.2
Initial Spares | -- |  |  | -- | -- |  |  | 1019.5 |  | -- |  |  |  | -- |  | 1245.9
MILCON | 0 |  |  | 153 | 168.3 |  |  | 147.3 |  | 0 |  |  |  | 182.4 |  | 187.2
Acq O&M | 0 |  |  | 45 | 49.5 |  |  | 17.3 |  | 0 |  |  |  | 51.7 |  | 23.7
Total | 730.7 |  |  | 13588.1 | N/A |  |  | 12290.5 |  | 839.7 |  |  |  | 16591.5 |  | 15943.9
RDT&E | 0 | [6 empty] | 0 |  |  |  | 0
Procurement | 11 | [6 empty] | 168 |  |  |  | 169
Total | 11 | [6 empty] | 168 |  |  |  | 169
Total Quantity
Quantity |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
Quantity Notes
FY 2017 PB includes an Overseas Contingency Operations aircraft in FY 2017 to replace one lost in Afghanistan. The lost aircraft is included in the prior year totals. Beyond FYDP buys were reduced by one aircraft. Total aircraft procurement remains 169 aircraft.

## Table 14
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 301.5 | 18.6 |  |  | 14.8 | 16.3 | 8.8 |  | 0.7 |  | 0.7 |  |  | 0 |  | 361.4
Procurement | 10865.3 | 920.8 |  |  | 296.6 | 123.5 | 156.5 |  | 140.9 |  | 143.5 |  |  | 2724.5 |  | 15371.6
MILCON | 148.7 | 8.5 |  |  | 30 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 187.2
Acq O&M | 23.7 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 23.7
PB 2017 Total | 11339.2 | 947.9 |  |  | 341.4 | 139.8 | 165.3 |  | 141.6 |  | 144.2 |  |  | 2724.5 |  | 15943.9
PB 2016 Total | 11337.6 | 1024.5 |  |  | 580.5 | 416.5 | 322.6 |  | 142 |  | 594 |  |  | 1381.3 |  | 15799
Delta | 1.6 | -76.6 |  |  | -239.1 | -276.7 | -157.3 |  | -0.4 |  | -449.8 |  |  | 1343.2 |  | 144.9
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Production | 0 |  | 137 |  | 14 | 3 | 0 |  | 0 |  | 0 | 0 |  | 15 |  | 169
PB 2017 Total | 0 |  | 137 |  | 14 | 3 | 0 |  | 0 |  | 0 | 0 |  | 15 |  | 169
PB 2016 Total | 0 |  | 137 |  | 14 | 5 | 3 |  | 2 |  | 0 | 4 |  | 4 |  | 169
Delta | 0 |  | 0 |  | 0 | -2 | -3 |  | -2 |  | 0 | -4 |  | 11 |  | 0

## Table 15
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.1
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.7
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.3
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.5
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.2
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.6
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.8
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.3
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.8
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.7
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.7
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 361.4

## Table 16
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 1996 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.1
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.6
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.6
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.7
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.4
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.6
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.8
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.8
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.3
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.3
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.3
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.2
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.9
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 281

## Table 17
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1994 |  | 2 | 66.8 |  | -- |  | -- |  | 66.8 |  | -- |  | 66.8
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1996 |  | 5 | 225.2 |  | -- |  | -- |  | 225.2 |  | 8.2 |  | 233.4
1997 |  | 9 | 433.9 |  | -- |  | -- |  | 433.9 |  | 72.7 |  | 506.6
1998 |  | 7 | 352.8 |  | 2.9 |  | -- |  | 355.7 |  | 92 |  | 447.7
1999 |  | 5 | 271 |  | -- |  | -- |  | 271 |  | 174.5 |  | 445.5
2000 |  | 1 | 67 |  | -- |  | -- |  | 67 |  | 73.1 |  | 140.1
2001 |  | 3 | 184.8 |  | -- |  | -- |  | 184.8 |  | 120.6 |  | 305.4
2002 |  | 5 | 365.8 |  | -- |  | -- |  | 365.8 |  | 73.2 |  | 439
2003 |  | 1 | 157.2 |  | -- |  | -- |  | 157.2 |  | 171.9 |  | 329.1
2004 |  | 4 | 380.6 |  | 9.6 |  | -- |  | 390.2 |  | 83.2 |  | 473.4
2005 |  | 11 | 754.2 |  | 41.9 |  | -- |  | 796.1 |  | 147.4 |  | 943.5
2006 |  | 12 | 682.9 |  | 4.8 |  | 15.8 |  | 703.5 |  | 257.7 |  | 961.2
2007 |  | 14 | 835.8 |  | 14.8 |  | 24.8 |  | 875.4 |  | 242.5 |  | 1117.9
2008 |  | 30 | 1653.2 |  | 25.5 |  | 37.9 |  | 1716.6 |  | 126 |  | 1842.6
2009 |  | -- | -- |  | 24.6 |  | -- |  | 24.6 |  | 85.4 |  | 110
2010 |  | 4 | 296.5 |  | -- |  | 5.6 |  | 302.1 |  | 138.2 |  | 440.3
2011 |  | 8 | 332.3 |  | 5.6 |  | 12 |  | 349.9 |  | 119.5 |  | 469.4
2012 |  | 1 | 65.8 |  | 12.6 |  | 4.4 |  | 82.8 |  | 10.8 |  | 93.6
2013 |  | 1 | 131 |  | 3.3 |  | 10.1 |  | 144.4 |  | 22.8 |  | 167.2
2014 |  | 6 | 565.6 |  | 0.4 |  | 8.9 |  | 574.9 |  | 64.8 |  | 639.7
2015 |  | 8 | 590.2 |  | 0.6 |  | 5.5 |  | 596.3 |  | 96.6 |  | 692.9
2016 |  | 14 | 790.5 |  | 29.2 |  | 21.5 |  | 841.2 |  | 79.6 |  | 920.8
2017 |  | 3 | 150.8 |  | 77.9 |  | 4.7 |  | 233.4 |  | 63.2 |  | 296.6
2018 |  | -- | -- |  | 78.9 |  | 4.7 |  | 83.6 |  | 39.9 |  | 123.5
2019 |  | -- | -- |  | 120.4 |  | 4.7 |  | 125.1 |  | 31.4 |  | 156.5
2020 |  | -- | -- |  | 132.5 |  | -- |  | 132.5 |  | 8.4 |  | 140.9
2021 |  | -- | -- |  | 135 |  | -- |  | 135 |  | 8.5 |  | 143.5
2022 |  | 8 | 779.5 |  | 165.5 |  | 4.9 |  | 949.9 |  | 89.7 |  | 1039.6
2023 |  | 7 | 726.3 |  | 185 |  | 4.9 |  | 916.2 |  | 46.3 |  | 962.5
2024 |  | -- | -- |  | 180 |  | 4.9 |  | 184.9 |  | 21 |  | 205.9
2025 |  | -- | -- |  | 160 |  | 4.9 |  | 164.9 |  | 21.7 |  | 186.6
2026 |  | -- | -- |  | 160 |  | 4.9 |  | 164.9 |  | 17.4 |  | 182.3
2027 |  | -- | -- |  | 90 |  | 4.9 |  | 94.9 |  | 12.9 |  | 107.8
2028 |  | -- | -- |  | 39.8 |  | -- |  | 39.8 |  | -- |  | 39.8
Subtotal |  | 169 | 10859.7 |  | 1700.8 |  | 190 |  | 12750.5 |  | 2621.1 |  | 15371.6

## Table 18
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | BY 1996 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1994 |  | 2 | 66.7 |  | -- |  | -- |  | 66.7 |  | -- |  | 66.7
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1996 |  | 5 | 218.6 |  | -- |  | -- |  | 218.6 |  | 8 |  | 226.6
1997 |  | 9 | 417.1 |  | -- |  | -- |  | 417.1 |  | 69.9 |  | 487
1998 |  | 7 | 336.4 |  | 2.8 |  | -- |  | 339.2 |  | 87.7 |  | 426.9
1999 |  | 5 | 255.9 |  | -- |  | -- |  | 255.9 |  | 164.8 |  | 420.7
2000 |  | 1 | 62.3 |  | -- |  | -- |  | 62.3 |  | 68 |  | 130.3
2001 |  | 3 | 170 |  | -- |  | -- |  | 170 |  | 111 |  | 281
2002 |  | 5 | 332.7 |  | -- |  | -- |  | 332.7 |  | 66.6 |  | 399.3
2003 |  | 1 | 140.7 |  | -- |  | -- |  | 140.7 |  | 153.9 |  | 294.6
2004 |  | 4 | 332 |  | 8.4 |  | -- |  | 340.4 |  | 72.5 |  | 412.9
2005 |  | 11 | 638.2 |  | 35.5 |  | -- |  | 673.7 |  | 124.7 |  | 798.4
2006 |  | 12 | 563.6 |  | 4 |  | 13 |  | 580.6 |  | 212.7 |  | 793.3
2007 |  | 14 | 671.6 |  | 11.9 |  | 19.9 |  | 703.4 |  | 194.9 |  | 898.3
2008 |  | 30 | 1307.3 |  | 20.2 |  | 30 |  | 1357.5 |  | 99.6 |  | 1457.1
2009 |  | -- | -- |  | 19.1 |  | -- |  | 19.1 |  | 66.5 |  | 85.6
2010 |  | 4 | 226.2 |  | -- |  | 4.3 |  | 230.5 |  | 105.4 |  | 335.9
2011 |  | 8 | 249.6 |  | 4.2 |  | 9 |  | 262.8 |  | 89.8 |  | 352.6
2012 |  | 1 | 48.7 |  | 9.2 |  | 3.3 |  | 61.2 |  | 8 |  | 69.2
2013 |  | 1 | 94.9 |  | 2.4 |  | 7.3 |  | 104.6 |  | 16.6 |  | 121.2
2014 |  | 6 | 404.5 |  | 0.3 |  | 6.4 |  | 411.2 |  | 46.2 |  | 457.4
2015 |  | 8 | 416.5 |  | 0.4 |  | 3.9 |  | 420.8 |  | 68.2 |  | 489
2016 |  | 14 | 547.5 |  | 20.2 |  | 14.9 |  | 582.6 |  | 55.1 |  | 637.7
2017 |  | 3 | 102.5 |  | 52.9 |  | 3.2 |  | 158.6 |  | 43 |  | 201.6
2018 |  | -- | -- |  | 52.6 |  | 3.1 |  | 55.7 |  | 26.6 |  | 82.3
2019 |  | -- | -- |  | 78.7 |  | 3.1 |  | 81.8 |  | 20.5 |  | 102.3
2020 |  | -- | -- |  | 84.9 |  | -- |  | 84.9 |  | 5.4 |  | 90.3
2021 |  | -- | -- |  | 84.8 |  | -- |  | 84.8 |  | 5.3 |  | 90.1
2022 |  | 8 | 479.8 |  | 101.9 |  | 3 |  | 584.7 |  | 55.2 |  | 639.9
2023 |  | 7 | 438.5 |  | 111.5 |  | 3 |  | 553 |  | 28 |  | 581
2024 |  | -- | -- |  | 106.5 |  | 2.9 |  | 109.4 |  | 12.4 |  | 121.8
2025 |  | -- | -- |  | 92.9 |  | 2.8 |  | 95.7 |  | 12.6 |  | 108.3
2026 |  | -- | -- |  | 91 |  | 2.8 |  | 93.8 |  | 9.9 |  | 103.7
2027 |  | -- | -- |  | 50.3 |  | 2.7 |  | 53 |  | 7.1 |  | 60.1
2028 |  | -- | -- |  | 21.8 |  | -- |  | 21.8 |  | -- |  | 21.8
Subtotal |  | 169 | 8521.8 |  | 1068.4 |  | 138.6 |  | 9728.8 |  | 2116.1 |  | 11844.9

## Table 19
Annual Funding 3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | TY $M
Total Program
2002 10.4
2003 26.1
2004 26.2
2005 5.0
2006 --
2007 25.3
2008 --
2009 21.0
2010 4.5
2011 --
2012 --
2013 30.2
2014 --
2015 --
2016 8.5
2017 30.0
Subtotal 187.2

## Table 20
Annual Funding 3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | BY 1996 $M
Total Program
2002 9.4
2003 23.2
2004 22.6
2005 4.2
2006 --
2007 20.3
2008 --
2009 16.4
2010 3.4
2011 --
2012 --
2013 21.8
2014 --
2015 --
2016 5.8
2017 20.2
Subtotal 147.3

## Table 21
Annual Funding 3400 ¦ Acq O&M ¦ Operation and Maintenance, Air Force
Fiscal Year | TY $M
Total Program
2003 | 6.8
2004 | 9.3
2005 | 7.6
Subtotal | 23.7

## Table 22
Annual Funding 3400 ¦ Acq O&M ¦ Operation and Maintenance, Air Force
Fiscal Year | BY 1996 $M
Total Program
2003 | 5.1
2004 | 6.8
2005 | 5.4
Subtotal | 17.3

## Table 23
Low Rate Initial Production
There is no LRIP for this program.

## Table 24
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Australia | 2014-02-18 | 0 | 47.7 | FMS Case AT-D-QAY. Aircraft modifications only.
India | 2013-12-27 | 6 | 1011.6 | FMS Case IN-D-SAD
Saudi Arabia | 2013-02-06 | 2 | 202.8 | FMS Case SR-D-SAQ
Norway | 2012-07-20 | 1 | 122.8 | FMS Case NO-D-SAG To replace diverted USAF aircraft. Delivery slated for Air Mobility Command in CY 2015.
Norway | 2011-11-24 | 0 | 30.5 | FMS Case NO-D-QAQ. Capability upgrades only.
Australia | 2010-04-13 | 0 | 30.5 | FMS Case AT-D-QAB. Capability upgrades only.
Israel | 2010-03-25 | 6 | 322.7 | FMS Case IS-D-SAD Denotes 4 full aircraft + long lead for 2 aircraft.
Italy | 2009-12-01 | 1 | 61.1 | FMS Case IT-D-QAB. Capability upgrades only.
Denmark | 2009-04-22 | 0 | 16.2 | FMS Case DE-D-QOH. Capability upgrades only.
Iraq | 2008-09-14 | 6 | 700.6 | FMS Cases IQ-D-SAB, IQ-D-QAO, IQ-D-QAP, G8- D-QAB
India | 2008-01-31 | 6 | 962.5 | FMS Case IN-D-SAA
Norway | 2007-06-29 | 4 | 491.3 | FMS Case NO-D-SAF Amendment 5 signed on July 19, 2012 (drawdown) for closure, Period of Performance ended June 16, 2012.
Notes
The C-130J FMS Program Management Office continues to manage twelve FMS cases worth over $2.8B on behalf of eight countries. Existing case workload includes acquisition cases for the production, delivery, retrofit/modification, and/or sustainment for Saudi Arabia, India, Iraq, Israel, Denmark, Italy, Australia, and Norway.
Nuclear Costs
None

## Table 25
Unit Cost
Unit Cost Report
Item |  |  | BY 1996 $M | BY 1996 $M |  | % Change
|  |  | Current UCR Baseline (Apr 2007 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 13588.1 |  |  |  | 12290.5
Quantity | 168 |  |  |  | 169
Unit Cost | 80.882 |  |  |  | 72.725 |  | -10.09
Average Procurement Unit Cost
Cost | 13041 |  |  |  | 11844.9
Quantity | 168 |  |  |  | 169
Unit Cost | 77.625 |  |  |  | 70.088 |  | -9.71
Item |  |  | BY 1996 $M | BY 1996 $M |  | % Change
|  |  | Original UCR Baseline (Oct 1996 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost |  | 730.7 |  |  | 12290.5
Quantity |  | 11 |  |  | 169
Unit Cost |  | 66.427 |  |  | 72.725 |  | 9.48
Average Procurement Unit Cost
Cost |  | 721.8 |  |  | 11844.9
Quantity |  | 11 |  |  | 169
Unit Cost |  | 65.618 |  |  | 70.088 |  | 6.81

## Table 26
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 1996 $M | [5 empty] | TY $M
[8 empty] | PAUC |  |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Oct 1996 |  |  |  |  | 66.427 |  |  |  | 65.618 |  |  | 76.336 |  |  | 75.5
APB as of January 2006 |  |  | Mar 2003 |  |  |  |  | 80.023 |  |  |  | 77.625 |  |  | 97.517 |  |  | 94.707
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | Mar 2003 |  |  |  |  | 80.023 |  |  |  | 77.625 |  |  | 97.517 |  |  | 94.707
Current APB |  |  | Apr 2007 |  |  |  |  | 80.882 |  |  |  | 77.625 |  |  | 98.759 |  |  | 94.707
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 72.424 |  |  |  | 69.785 |  |  | 93.485 |  |  | 90.125
Current Estimate |  |  | Dec 2015 |  |  |  |  | 72.725 |  |  |  | 70.088 |  |  | 94.343 |  |  | 90.956
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Production Estimate | Changes | [14 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  |  | Total
76.336 0.452 -4.889 -2.428 1.196 9.586 0.000 14.090 18.007 94.343
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Production Estimate | Changes | [14 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  |  | Total
75.500 0.366 -4.107 -2.402 0.000 7.509 0.000 14.090 15.456 90.956

## Table 27
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone I | N/A | N/A | N/A | N/A
Milestone II | N/A | N/A | N/A | N/A
Milestone III | N/A | N/A | Jun 1996 | Jun 1996
IOC | N/A | N/A | N/A | N/A
Total Cost (TY $M) | N/A | 839.7 | 839.7 | 15943.9
Total Quantity | N/A | 11 | 11 | 169
PAUC | N/A | 76.336 | 76.336 | 94.343

## Table 28
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Acq O&M |  | Total
SAR Baseline (Production Estimate)
Previous Changes
9.2 830.5 -- -- 839.7
Economic |  | 4.9 |  | 99.7 |  | 4.1 |  | 1.1 |  | 109.8
Quantity |  | -- |  | 11234.8 |  | -- |  | -- |  | 11234.8
Schedule |  | -- |  | -510.2 |  | -4.5 |  | -- |  | -514.7
Engineering |  | 169.1 |  | -- |  | 26.7 |  | -- |  | 195.8
Estimating |  | 179.7 |  | 1325.4 |  | 154.9 |  | 22.6 |  | 1682.6
Other |  | -- |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 2251 |  | -- |  | -- |  | 2251
Subtotal |  | 353.7 |  | 14400.7 |  | 181.2 |  | 23.7 |  | 14959.3
Current Changes Economic |  | -0.4 |  | -37.8 |  | -0.3 |  | 5.1 |  | -33.4
Quantity |  | -- |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 104.3 |  | -- |  | -- |  | 104.3
Engineering |  | 6.4 |  | -- |  | -- |  | -- |  | 6.4
Estimating |  | -7.5 |  | -56.3 |  | 6.3 |  | -5.1 |  | -62.6
Other |  | -- |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 130.2 |  | -- |  | -- |  | 130.2
Subtotal |  | -1.5 |  | 140.4 |  | 6 |  | -- |  | 144.9
Total Changes |  | 352.2 |  | 14541.1 |  | 187.2 |  | 23.7 |  | 15104.2
CE - Cost Variance |  | 361.4 |  | 15371.6 |  | 187.2 |  | 23.7 |  | 15943.9
CE - Cost & Funding |  | 361.4 |  | 15371.6 |  | 187.2 |  | 23.7 |  | 15943.9

## Table 29
Summary BY 1996 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Acq O&M |  | Total
SAR Baseline (Production Estimate)
Previous Changes
8.9 721.8 -- -- 730.7
Economic |  | -- |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 8648.3 |  | -- |  | -- |  | 8648.3
Schedule |  | -- |  | -264.1 |  | -3 |  | -- |  | -267.1
Engineering |  | 126.2 |  | -- |  | 17.7 |  | -- |  | 143.9
Estimating |  | 147.1 |  | 831.7 |  | 128.1 |  | 21 |  | 1127.9
Other |  | -- |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 1855.9 |  | -- |  | -- |  | 1855.9
Subtotal |  | 273.3 |  | 11071.8 |  | 142.8 |  | 21 |  | 11508.9
Current Changes Economic |  | -- |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 21.8 |  | -- |  | -- |  | 21.8
Engineering |  | 4.6 |  | -- |  | -- |  | -- |  | 4.6
Estimating |  | -5.8 |  | -49 |  | 4.5 |  | -3.7 |  | -54
Other |  | -- |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 78.5 |  | -- |  | -- |  | 78.5
Subtotal |  | -1.2 |  | 51.3 |  | 4.5 |  | -3.7 |  | 50.9
Total Changes |  | 272.1 |  | 11123.1 |  | 147.3 |  | 17.3 |  | 11559.8
CE - Cost Variance |  | 281 |  | 11844.9 |  | 147.3 |  | 17.3 |  | 12290.5
CE - Cost & Funding |  | 281 |  | 11844.9 |  | 147.3 |  | 17.3 |  | 12290.5
Previous Estimate: December 2014

## Table 30
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.4
Adjustment for current and prior escalation. (Estimating) | 0.2 | 0.3
Revised estimated risk for Block 7.0/8.1 upgrade national integration effort. (Estimating) | -6 | -7.8
Congressional add for in-flight Prop Balance program. (Engineering) | 4.6 | 6.4
RDT&E Subtotal | -1.2 | -1.5
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -37.8
Adjustment for current and prior escalation. (Estimating) +7.7 +11.1
Stretch-out of procurement buy profile by moving seven aircraft from FY 2017 - FY 2019 to FY 2022 - FY 2023. (Schedule)
Additional Schedule variance associated with moving seven aircraft from FY 2017 - FY 2019 to FY 2022 - FY 2023. (Schedule)
0.0 +71.4
+21.8 +32.9
Revised estimate for Blk 7.0/8.1 National Integration. (Estimating) +42.8 +69.3
Revised estimate for aircraft prices based on negotiated Multi-Year II contract award. (Estimating)
Revised estimate based on programmatic changes (e.g. technical production support). (Estimating)
-114.2 -164.1
+14.7 +27.4
Adjustment for current and prior escalation. (Support) +0.7 +1.4
Increase in Other Support due to seven aircraft buys being rephased into FY 2022 - FY 2023. (Support)
Increase in Initial Spares due to seven aircraft buys being rephased into FY 2022 - FY 2023. (Support)
+74.0 +115.1
+3.8 +13.7
Procurement Subtotal +51.3 +140.4
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.3
Revised estimate based on updates to Yokota beddown requirement. (Estimating) | 4.5 | 6.3
MILCON Subtotal | 4.5 | 6
Acq O&M | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 5.1
Adjustment for current and prior escalation. (Estimating) | -3.7 | -5.1
Acq O&M Subtotal | -3.7 | 0

## Table 31
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: C-130J - BUIC: Blk 8.1
Contractor: Lockheed Martin
Contractor Location: 86 South Cobb Drive
Marietta, GA 30063-0001
Contract Number: FA8625-04-D-6452/7 Contract Type: Cost Plus Award Fee (CPAF) Award Date: November 18, 2011
Definitization Date: November 18, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
166.7 N/A N/A 172.8 N/A N/A 182.6 198.4
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the test venue change from Edwards Air Force Base to Marietta, GA and unearned award fees for periods 1 through 3. The difference is also due to increases for:
1. Block 8.1 compatibility incorporation into Color Multi-Function Display Unit Diminishing Manufacturing Sources replacement hardware;
2. Implementation of Air Mobility Command Aircraft Communications Addressing and Reporting System Standard Message Set (SMS) Version 3.2 and Barometric Vertical Navigation;
3. Block 8.1 Airline Operational Control SMS addition of crew select messaging On/Off switch and metric conversion; and
4. Block 8.1 expanded scope to add seven additional capabilities above the original ten in the Common Core program.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/27/2015) -3.5 -3.0
Previous Cumulative Variances -1.3 -1.9
Net Change -2.2 -1.1
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to additional software development and testing.
The unfavorable net change in the schedule variance is due to additional software development and testing.

## Table 32
Contract Identification
Appropriation: Procurement
Contract Name: C-130J FYOC III
Contractor: Lockheed Martin
Contractor Location: 86 South Cobb Drive
Marietta, GA 39963-0290
Contract Number: FA8625-06-C-6456
Contract Type: Firm Fixed Price (FFP)
Award Date: February 01, 2006
Definitization Date: February 01, 2006
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
8.5 N/A 0 2830.2 N/A 42 2830.2 2830.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the addition of aircraft buys, spares, support equipment, engineering changes, Diminishing Manufacturing Sources effort and other production related efforts.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 33
Contract Identification
Appropriation: Procurement
Contract Name: C-130J FYOC IV
Contractor: Lockheed Martin
Contractor Location: 86 South Cobb Drive
Marietta, GA 39963-0290
Contract Number: FA8625-11-C-6597
Contract Type: Firm Fixed Price (FFP)
Award Date: March 16, 2011
Definitization Date: March 16, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
6.4 N/A 0 220.7 N/A 2 220.7 220.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the addition of aircraft buys, spares, support equipment, engineering changes, Diminishing Manufacturing Sources effort and other production related efforts.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 34
Contract Identification
Appropriation: Procurement
Contract Name: C-130J Multi-Year II Procurement Contract
Contractor: Lockheed Martin Aeronautics Company
Contractor Location: 86 South Cobb Drive
Marietta, GA 39963-0290
Contract Number: FA8625-14-C-6450
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 09, 2013
Definitization Date: December 30, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
50.8 50.8 0 1833.8 1893.7 29 0.0 1893.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to Advance Procurement being used to initiate the Multi-Year II contract. Upon definitization, the quantities and prices were set to the definitized amounts.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date 0.0 0.0
Previous Cumulative Variances 0.0 0.0
Net Change +0.0 +0.0
Cost and Schedule Variance Explanations
None
General Contract Variance Explanation
Cost and schedule variances are not reported for this FPIF contract, because EVM reporting has been waived. A class deviation to exclude Defense Federal Acquisition Regulation Supplement clauses 252.234-7001 and 252.234-7002 was approved by Headquarters Air Force Materiel Command on February 13, 2014.

## Table 35
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 123 | 123 | 169 | 72.78%
Total Program Quantity Delivered | 123 | 123 | 169 | 72.78%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
15943.9
10211.7
64.05%
35
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
23
65.71%
12287.1
77.06%
The above data is current as of February 09, 2016.

## Table 36
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 27, 2016
Source of Estimate: POE
Quantity to Sustain: 168
Unit of Measure: Aircraft
Service Life per Unit: 30.00 Years
Fiscal Years in Service: FY 2000 - FY 2057
There have been two C-130J aircraft lost in Afghanistan. A total of two Overseas Contingency Operations (OCO) aircraft were added in the FY 2015 and FY 2017 PBs. Both lost aircraft are included in the procurement total of 169. However, O&S costs are for 168 aircraft, which is based on C-130J's current program office estimate.
Sustainment Strategy
The C-130J ensures continued aircraft availability to the warfighter within the financial constraints defined by the owning commands and the United States Air Force (USAF) by using a Long Term Sustainment contract with Lockheed Martin, a Power-By-The-Hour engine contract with Rolls Royce, and C-130 Legacy common organic resources.
Antecedent Information
The C-130H1 and C-130H2 are antecedent aircraft. The Air Force Total Ownership Cost (AFTOC) database for the fourth quarter of CY 2015 was used to obtain costs. Costs assume a 30 year life span.
Annual O&S Costs BY1996 $M
Cost Element | C-130J Average Annual Cost Per Aircraft | C-130H1 & H2 (Antecedent) Avg Annual Cost Per Aircraft
Unit-Level Manpower | 3 | 2.693
Unit Operations | 1.14 | 1.146
Maintenance | 1.47 | 1.62
Sustaining Support | 0.26 | 0.039
Continuing System Improvements | 0.02 | 0.073
Indirect Support | 0.2 | 0.319
Other | 0 | 0
Total | 6.09 | 5.89

## Table 37
Item | Total O&S Cost $M
| C-130J | [5 empty] | C-130H1 & H2 (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | N/A |  | N/A |  |  | 30693.6 | 27388.5
Then Year | N/A |  | N/A |  |  | 54628 | N/A
There are no O&S cost Objective or Threshold values listed in the APB.
Equation to Translate Annual Cost to Total Cost
The unitized cost multiplied by the quantity (168) multiplied by the service life (30 yrs) equals the Total O&S cost in BY$.
O&S Cost Variance
Category |  | BY 1996 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
28022.4
Programmatic/Planning Factors -219.0 Decrease due to 2% reduction in Flight Hours (FH) per
Primary Authorized Aircraft (PAA).
Cost Estimating Methodology 3844.0 Previous Year O&S estimate only included O&S years (FY2014-2053). The 2014 SAR O&S amount should have been $31,924.9 BY 1996 $M and covered O&S years (FY 2000-2057).
Cost Data Update 374.0 Higher historical data for Repair parts, common Depot Level Reparables (DLRs), higher scheduled maintenance, and software sustainment.
Labor Rate -1565.1 Decrease due to revised manpower per PAA, decrease in military pay rates, and decrease in civilian pay rates.
Energy Rate 3.8 Increase in fuel price (per gallon) from $3.62 to $3.70 (+2%).
Technical Input 233.5 Increase in engine contractor costs. Other 0.0
Total Changes 2671.2
Current Estimate 30693.6
Disposal Estimate Details
Date of Estimate: January 27, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 1996 $M): Total costs for disposal of all Aircraft are 6.5

## Table 38
The disposal cost estimate will be refined as the System Disposal Plan Annex to the Life Cycle Sustainment Plan is developed.