## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-199
Family of Advanced Beyond Line-of-Sight Terminals (FAB-T)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 6
Mission and Description 7
Executive Summary 8
Threshold Breaches 9
Schedule 10
Performance 13
Track to Budget 29
Cost and Funding 32
Low Rate Initial Production 59
Foreign Military Sales 60
Nuclear Costs 60
Unit Cost 61
Cost Variance 67
Contracts 75
Deliveries and Expenditures 77
Operating and Support Cost 78

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Family of Beyond Line-of-Sight - Terminals (FAB-T)
DoD Component
Air Force
Joint Participants
US Navy (E-6 TACAMO aircraft); US Navy (Ground Terminals); US Army (Ground Terminals)
Responsible Office
Mr. Robert Tarleton
MILSATCOM Systems Directorate 483 N. Aviation Blvd.
El Segundo, CA 90245
robert.tarleton@us.af.mil
Phone: | 310-653-9001
Fax: | 310-653-9636
DSN Phone: | 633-9001
DSN Fax: | 633-9636
Date Assigned: | February 10, 2014

## Table 6
References
CPT
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated December 23, 2007
Approved APB
Under Secretary of Defense (Acquisition, Technology & Logistics) Approved Acquisition Program Baseline (APB) dated March 3, 2016
FET
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated December 23, 2007
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated March 3, 2016

## Table 7
Mission and Description
The Family of Advanced Beyond Line-of-Sight Terminals (FAB-T) program will develop nuclear event-survivable terminals capable of communicating with the Milstar and Advanced Extremely High Frequency (AEHF) satellite constellations using both the Extremely High Frequency and AEHF jam-resistant, low probability of intercept and low probability of detection waveforms. These terminals will be an essential component of the strategic nuclear execution system.
The CPT subprogram provides a nuclear survivable terminal capable of communicating with the Milstar and AEHF satellites from airborne and ground fixed and mobile locations, provides an interface for the Presidential and National Voice Conferencing (PNVC) function; the Telemetry, Tracking & Control for the Milstar and AEHF constellations, for Nuclear Command, Control, & Communications (NC3) data transport services [Emergency Action Message (EAM) injection, dissemination and reportback], and for Integrated Tactical Warning and Attack Assessment survivable data relay. The CPT will replace existing Milstar-only terminals for ground fixed and mobile command locations, as well as in the airborne E-4B and E-6 aircraft.
The FET subprogram provides a nuclear survivable terminal capable of communicating with the Milstar and AEHF satellites, and provides for survivable NC3 data transport services (EAM dissemination and force reportback) for airborne platforms.
The FET is for the B-2, B-52, and select RC-135 aircraft and will not provide satellite control or PNVC functionality. The initial installation and integration is a significant effort with antenna configurations which will differ from one aircraft type to another.

## Table 8
Executive Summary
In 2015, the FAB-T program experienced programmatic successes in three areas: creation of the CPT and FET subprograms, Milestone C achievement for the CPT subprogram, and development of a new APB incorporating both subprograms.
In preparation for the Milestone C decision, the contractor successfully accomplished all ground and airborne system-level qualification testing for the terminal and the ground and airborne antennas with modification kits. The contractor also conducted factory payload (Milstar and AEHF) satellite control risk reduction testing. The government Lead Developmental Test & Evaluation Organization (46th Test Squadron) performed successful flight testing and the first phase of Interoperability testing for Joint Interoperability Test Command certification of the FAB-T that included 15 Nuclear Command, Control, and Communications (NC3) terminals, operational baseband crypto and messaging devices, and 13 distinct communications networks emulating multiple operational configurations.
On July 30, 2015, USD(AT&L) notified Congress that the FAB-T program is being restructured into the CPT and FET subprograms. This FAB-T SAR has been structured to comply with this new direction. While the FET remains a valid requirement for the FAB-T program, it is currently unfunded and the Air Force has not yet finalized its strategy for FET development. The subprogram cost estimates were revised and based on the SCP signed on July 7, 2015. Allocations of sunk costs between the CPT and FET subprograms are based on the OSD CAPE assessment in preparation for the Milestone C DAB.
FAB-T conducted a CPT-only Milestone C DAB, resulting in the October 26, 2015 ADM authorizing a total LRIP quantity of 53 FAB-T CPT terminals. The first LRIP terminal delivery is projected for the end of the 4th Quarter CY 2016. SAF/AQ and SAF/FM signed a Full Funding Memo on September 15, 2015, fully endorsing the July 7, 2015 CPT SCP. An APB reflecting the restructure of the FAB-T program was approved on March 3, 2016 and includes updated cost, performance, schedule, and quantity distributions to support re-baselining the program.
The CPT schedule is holding with no changes to IOC or FOC. However, there was a minor schedule adjustment to the Initial Operational Test & Evaluation (IOT&E) event due to delays resulting from concurrent development and testing of three antenna configurations and availability of Engineering Development Models (EDMs). In addition, the increased LRIP quantity of 53 terminals is now sufficient to satisfy IOC requirements and affords schedule flexibility to accommodate a shift of
FRP to the right without impacting the IOC date.
There are no significant software-related issues with this program at this time.

## Table 9
Threshold Breaches
CPT
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
FET
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 10
Schedule

## Table 11
CPT
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Contract Award (Increment 1) | Sep 2002 | Sep 2002 | Sep 2002 | Sep 2002
System Requirements Review | Jan 2003 | Jan 2003 | Jan 2003 | Jan 2003
System Design Review | Jul 2003 | Jul 2003 | Jul 2003 | Jul 2003
Conduct Low Data Rate (LDR) System Critical Design Review (CDR) | Feb 2007 | Feb 2007 | Feb 2007 | Feb 2007
Conduct eXtended High Data Rate (XDR) System CDR | Oct 2008 | Oct 2008 | Oct 2008 | Oct 2008
Deliver First LDR System Engineering Development Model (EDM) | Dec 2008 | Jan 2009 | Jan 2009 | Jan 2009
LRIP Decision System LDR and XDR | Feb 2010 | Sep 2015 | Sep 2015 | Sep 2015
Operational Test & Evaluation (OT&E) Complete | Jul 2011 | Dec 2017 | Jun 2018 | Nov 2017
FRP Decision | Dec 2011 | Apr 2018 | Oct 2018 | Apr 2018
IOC | Jun 2013 | Dec 2019 | Jun 2020 | Dec 2019
FOC | Sep 2016 | Dec 2021 | Jun 2022 | Dec 2021
(Ch-1)
(Ch-2)
(Ch-2)
Change Explanations
(Ch-1) LRIP Decision System LDR Current Estimate changed from August 2015 to September 2015 to reflect actual date of occurrence.
(Ch-2) OT&E Complete and FRP Decision Current Estimates changed from July 2017 to November 2017 and November 2017 to April 2018, respectively.
Acronyms and Abbreviations
CDR - Critical Design Review
EDM - Engineering Development Model IOT&E - Initial Operational Test & Evaluation LDR - Low Data Rate
NLT - No Later Than
OT&E - Operational Test & Evaluation XDR - eXtended Data Rate

## Table 12
FET
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Contract Award (Increment 1) | Sep 2002 | Sep 2002 | Sep 2002 | Sep 2002
System Requirements Review | Jan 2003 | Jan 2003 | Jan 2003 | Jan 2003
System Design Review | Jul 2003 | Jul 2003 | Jul 2003 | Jul 2003
Conduct Low Data Rate (LDR) System Critical Design Review (CDR) | Feb 2007 | Feb 2007 | Feb 2007 | Feb 2007
Conduct eXtended High Data Rate (XDR) System CDR | Oct 2008 | Oct 2008 | Oct 2008 | Oct 2008
Deliver First LDR System Engineering Development Model (EDM) | Dec 2008 | Jan 2009 | Jan 2009 | Jan 2009
LRIP Decision System LDR and XDR | Feb 2010 | TBD | TBD | TBD
Operational Test & Evaluation (OT&E) Complete | Jul 2011 | TBD | TBD | TBD
FRP Decision | Dec 2011 | TBD | TBD | TBD
IOC | N/A | N/A | N/A | N/A
FOC | N/A | N/A | N/A | N/A
(Ch-1)
(Ch-1)
Change Explanations
(Ch-1) IOC and FOC schedule events will remain "N/A" pending AF decision on how and when to include FETs in the AF budget, as well as development of an acquisition strategy to support that plan.
Notes
The FET subprogram schedule for LRIP, IOT&E, and FRP are TBD at this time. While the FET remains a valid requirement for the FAB-T program, it is currently unfunded and the Air Force has not yet finalized its strategy for FET development.
Acronyms and Abbreviations
IOT&E - Initial Operational Test & Evaluation LDR - Low Data Rate
XDR - eXtended Data Rate

## Table 13
Performance
CPT
Performance Characteristics
SAR Baseline Development Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Interoperability
Enable all top- | N/A | N/A | All top-level | Enable all top-level IERs,
level IERs, as |  |  | information | as depicted by mission
depicted by |  |  | exchange | area and designated
mission area |  |  | requirements | critical between sending
and designated |  |  | (IERs) have been | and receiving nodes
critical |  |  | incorporated into
between |  |  | the CPT design
sending and |  |  | and were
receiving |  |  | demonstrated in
nodes |  |  | qualification
testing. The 46th
Test Squadron
has performed
flight testing and
ground
interoperability
testing in
coordination with
JITC and the
JTEO to
independently
evaluate the
CPT’s IER
performance
across multiple
mission areas.
Additional NC3
and satellite C2
test events are
scheduled in 2016.
Information Assurance
Meet DoD IA | N/A | N/A | System is being | Meet DoD IA criteria and
criteria and be |  |  | built to DIACAP | be certified/ accredited
certified/ |  |  | controls and | IAW DoD 8510.1-M, DoD
accredited IAW |  |  | Security Technical | 8500.1, and DoDI 8500.2,
DoD 8510.1-M, |  |  | Implementation | or DoD certification and
DoD 8500.1, |  |  | Guides (STIGs). | accreditation process at
and DoDI |  |  | STIG testing | time of contract award
8500.2, or DoD |  |  | against Operator
certification |  |  | Processing Unit

## Table 14
and |  |  | (OPU) performed
accreditation |  |  | in April 2014,
process at |  |  | November 2014,
time of |  |  | and October 2015.
contract award |  |  | Initial DIACAP
demonstration
testing completed
in January 2015.
DIACAP control
inspection
completed in June
2015. Program
has developed
mitigations to non-
compliant
controls/STIG
rules and reviewed
with Space
Authorizing Official
in October 2015.
Survivability
FMC w/o | N/A | N/A | Tested parts for | FMC w/o damage/
damage/ |  |  | radiation | degradation, throughout
degradation, |  |  | hardness, analysis | the nuclear environment
throughout the |  |  | validated terminal | that the aircraft is
nuclear |  |  | level probability of | expected to survive,
environment |  |  | survival; NSV | while meeting PCMR
that the aircraft |  |  | testing for Block 1 | requirements
is expected to |  |  | completed in June
survive, while |  |  | 2015. Dose rate
meeting PCMR |  |  | testing for the new
requirements |  |  | airborne antenna
is planned to
complete in 1st
Quarter FY 2016.
CPT Control Interface
Support use of | N/A | N/A | Raytheon testing | Support use of ASMCS
ASMCS and |  |  | demonstrated FAB | and MPSS satellite/
MPSS satellite/ |  |  | -T supports | network/ terminal control
network/ |  |  | ASMCS and | equipment.
terminal control |  |  | MPSS interfaces
equipment |  |  | and
communications
during Satellite
Command and
Control test events
on the AEHF and
Milstar factory
payloads at the
NAST-T and CMS
facilities as well as
during system-

## Table 15
level Prime Item Block 2 testing. The 46th Test Squadron will further demonstrate satellite control via an operational ASMCS during TT&C testing.
CPT Backwards Compatability
Compatibility | N/A | N/A | Demonstrated all | Compatibility with legacy
with legacy |  |  | serial interfaces | EHF baseband functions
EHF baseband |  |  | with FAB-T | associated with individual
functions |  |  | communicating | AEHF service/ networks,
associated |  |  | over Milstar and | SCIS, NPES, IEMATS,
with individual |  |  | AEHF satellites in | DIRECT and the Red
AEHF service/ |  |  | May 2015. | Switch.
networks, |  |  | Compatibility with
SCIS, NPES, |  |  | the Milstar
IEMATS, |  |  | Messaging
DIRECT and |  |  | Application (MMA)
the Red Switch |  |  | and DIRECT
systems was
demonstrated in
4th Quarter FY
2015
CPT Existing Terminal Coexistence
Inter-operable | N/A | N/A | Interoperability | Interoperable with
with existing |  |  | with legacy | existing EHF terminals
EHF terminals |  |  | AFCPT, NMT,
SMART-T, MMPU,
FOT, DMU, and
SCAMP terminals
was demonstrated
in FY15 using
Milstar and AEHF
satellites. Link
quality testing as
well as simulated
EAMs, FDMs, and
Reportbacks have
been exchanged.
CPT Satellite Constellation Coexistences
Inter-operable | N/A | N/A | Simultaneous use | Interoperable with the
with the AEHF, |  |  | of the legacy | AEHF, APS, Milstar, and
APS, Milstar, |  |  | AFCPT with the | UFO-E/EE
and UFO-E/EE |  |  | FAB-T CPT in
Milstar and AEHF
networks was
successfully
conducted

## Table 16
November 2014 and June 2015. Satellite control coexistence with ACF-IC2 on Milstar and AEHF was demonstrated in FY 2015 and will be repeated during TT&C testing.
Network Ready: The system must support Net-Centric military operations. The system must be able to enter and be managed in the network, and exchange data in a secure manner to enhance mission effectiveness. The system must continuously provide survivable, interoperable, secure, and operationally effective information exchanges to enable a Net-Centric military capability.
N/A | The FAB-T system must | (T=O) The FAB-T | TBD | The FAB-T system must
| support net-centric | system must support net |  | support net-centric
| military operations, enter | -centric military |  | military operations, enter
| and be managed in the | operations, enter and be |  | and be managed in the
| network, and exchange | managed in the network, |  | network, and exchange
| information as described | and exchange |  | information as described
| in Table 6 of the CPD. | information as described |  | in Table 6 of the CPD.
| FAB-T is a BLOS | in Table 6 of the CPD. |  | FAB-T is a BLOS
| Transport Layer element | FAB-T is a BLOS |  | Transport Layer element
| of communication | Transport Layer element |  | of communication
| infrastructures and as | of communication |  | infrastructures and as
| such several NR-KPP | infrastructures and as |  | such several NR-KPP
| attributes and measures | such several NR-KPP |  | attributes and measures
| are described in other | attributes and measures |  | are described in other
| KPPs. FAB-T | are described in other |  | KPPs. FAB-T
| architecture products are | KPPs. FAB-T |  | architecture products are
| compliant with CJCSI | architecture products are |  | compliant with CJCSI
| 6212.01F dated 21 Mar | compliant with CJCSI |  | 6212.01F dated 21 Mar
| 12 | 6212.01F dated 21 Mar |  | 12
12
Strategic Services: FAB-T provides positive control of strategic information exchange.
N/A | Terminals supporting | (T=O) Terminals | TBD | Terminals supporting
| nuclear/strategic | supporting |  | nuclear/strategic
| operations will enable | nuclear/strategic |  | operations will enable
| Emergency Action | operations will enable |  | Emergency Action
| Message dissemination | Emergency Action |  | Message dissemination
| while meeting the | Message dissemination |  | while meeting the
| Probability of Correct | while meeting the |  | Probability of Correct
| Message Receipt | Probability of Correct |  | Message Receipt
| requirements stated in | Message Receipt |  | requirements stated in
| Appendix F to Enclosure | requirements stated in |  | Appendix F to Enclosure
| A of CJCSI 6811.01. | Appendix F to Enclosure |  | A of CJCSI 6811.01.
| Terminals will be capable | A of CJCSI 6811.01. |  | Terminals will be capable
| of supporting improved | Terminals will be capable |  | of supporting improved
| Senior Leadership | of supporting improved |  | Senior Leadership
| conferencing. Terminals | Senior Leadership |  | conferencing. Terminals
| used for POTUS and | conferencing. Terminals |  | used for POTUS and
| SECDEF voice | used for POTUS and |  | SECDEF voice

## Table 17
| conferencing will support | SECDEF voice |  | conferencing will support
| the Milstar and AEHF | conferencing will support |  | the Milstar and AEHF
| CONOPS using up to | the Milstar and AEHF |  | CONOPS using up to
| twelve simultaneous | CONOPS using up to |  | twelve simultaneous
| voice networks. FAB-T | twelve simultaneous |  | voice networks. FAB-T
| will provide interfaces to | voice networks. FAB-T |  | will provide interfaces to
| support PNVC and | will provide interfaces to |  | support PNVC and
| Survivable Emergency | support PNVC and |  | Survivable Emergency
| Conferencing Network | Survivable Emergency |  | Conferencing Network
| equipment. PNVC and | Conferencing Network |  | equipment. PNVC and
| SECN equipment are | equipment. PNVC and |  | SECN equipment are
| external to the FAB-T. | SECN equipment are |  | external to the FAB-T.
| Each nuclear Command | external to the FAB-T. |  | Each nuclear Command
| Center node must be | Each nuclear Command |  | Center node must be
| able to simultaneously | Center node must be |  | able to simultaneously
| support all services | able to simultaneously |  | support all services
| assigned to that | support all services |  | assigned to that
| node/platform as | assigned to that |  | node/platform as
| mandated in the | node/platform as |  | mandated in the
| Emergency Action | mandated in the |  | Emergency Action
| Procedures of the Joint | Emergency Action |  | Procedures of the Joint
| Staff Volume VII for Joint | Procedures of the Joint |  | Staff Volume VII for Joint
| Staff directed networks | Staff Volume VII for Joint |  | Staff directed networks
| and the USSTRATCOM | Staff directed networks |  | and the USSTRATCOM
| Network Operating | and the USSTRATCOM |  | Network Operating
| Instruction for | Network Operating |  | Instruction for
| USSTRATCOM directed | Instruction for |  | USSTRATCOM directed
| networks. FAB-T | USSTRATCOM directed |  | networks. FAB-T
| Command Center nodes | networks. FAB-T |  | Command Center nodes
| will perform this function | Command Center nodes |  | will perform this function
| with no more than two | will perform this function |  | with no more than two
| FAB-Ts. | with no more than two |  | FAB-Ts.
FAB-Ts.
Terminal Survivability: The FAB-T functions through the nuclear environment that the platform must endure.
N/A | The FAB-T does not | (T=O) The FAB-T does | TBD | The FAB-T does not
| contribute to the | not contribute to the |  | contribute to the
| protection of personnel or | protection of personnel or |  | protection of personnel or
| to the survivability of | to the survivability of |  | to the survivability of
| manned systems since it | manned systems since it |  | manned systems since it
| is not an occupied | is not an occupied |  | is not an occupied
| system. Protection for | system. Protection for |  | system. Protection for
| the FAB-T and its crew | the FAB-T and its crew |  | the FAB-T and its crew
| must be provided by | must be provided by |  | must be provided by
| external means (e.g. | external means (e.g. |  | external means (e.g.
| revetments, | revetments, |  | revetments,
| concealment, etc.). The | concealment, etc.). The |  | concealment, etc.). The
| manned and direct | manned and direct kinetic |  | manned and direct
| kinetic aspects of the | aspects of the mandatory |  | kinetic aspects of the
| mandatory Survivability | Survivability KPP do not |  | mandatory Survivability
| KPP do not apply. The | apply. The detectability |  | KPP do not apply. The
| detectability and | and countermeasure |  | detectability and
| countermeasure aspects | aspects of the |  | countermeasure aspects

## Table 18
| of the Survivability KPP | Survivability KPP do |  | of the Survivability KPP
| do apply and are defined | apply and are defined |  | do apply and are defined
| here as the Terminal | here as the Terminal |  | here as the Terminal
| Survivability KPP, which | Survivability KPP, which |  | Survivability KPP, which
| has been tailored to the | has been tailored to the |  | has been tailored to the
| FAB-T mission | FAB-T mission |  | FAB-T mission
| environment. FAB-T is | environment. FAB-T is |  | environment. FAB-T is
| expected to survive and | expected to survive and |  | expected to survive and
| operate in CBRN | operate in CBRN |  | operate in CBRN
| environments. As such, | environments. As such, |  | environments. As such,
| the system is designated | the system is designated |  | the system is designated
| CBRN Mission Critical | CBRN Mission Critical |  | CBRN Mission Critical
| IAW DoDI 3150.09. | IAW DoDI 3150.09. |  | IAW DoDI 3150.09.
| Terminals supporting | Terminals supporting |  | Terminals supporting
| nuclear operations must | nuclear operations must |  | nuclear operations must
| be fully mission capable | be fully mission capable |  | be fully mission capable
| up to the maximum | up to the maximum |  | up to the maximum
| nuclear environment that | nuclear environment that |  | nuclear environment that
| the platform is expected | the platform is expected |  | the platform is expected
| to survive. Any recovery | to survive. Any recovery |  | to survive. Any recovery
| from circumvention | from circumvention |  | from circumvention
| required for a dose rate | required for a dose rate |  | required for a dose rate
| event will not be part of | event will not be part of |  | event will not be part of
| the EAM transmission | the EAM transmission |  | the EAM transmission
| timeline. | timeline. |  | timeline.
Capacity: Terminals must support data rates required by the airborne platforms and ground terminals missions utilizing the capabilities defined in the AEHF and Milstar Operational Requirements Documents (ORDs).
N/A | The CPT will | (T=O) The CPT will | TBD | The CPT will
| simultaneously support | simultaneously support |  | simultaneously support
| up to 47 services, | up to 47 services, |  | up to 47 services,
| including up to 30 | including up to 30 |  | including up to 30
| Transmit/ Receive | Transmit/ Receive |  | Transmit/ Receive
| services, nine receive | services, nine receive |  | services, nine receive
| only services, and eight | only services, and eight |  | only services, and eight
| transmit only services. | transmit only services. |  | transmit only services.
| The terminal will support | The terminal will support |  | The terminal will support
| a cumulative transmit | a cumulative transmit |  | a cumulative transmit
| rate of at least 8.100 | rate of at least 8.100 |  | rate of at least 8.100
| megabits per second | megabits per second |  | megabits per second
| (Mbps) and a cumulative | (Mbps) and a cumulative |  | (Mbps) and a cumulative
| receive rate of at least | receive rate of at least |  | receive rate of at least
| 17.700 Mbps. Terminals | 17.700 Mbps. Terminals |  | 17.700 Mbps. Terminals
| will include all equipment | will include all equipment |  | will include all equipment
| necessary to accept | necessary to accept |  | necessary to accept
| system data at data rates | system data at data rates |  | system data at data rates
| defined in the Milstar and | defined in the Milstar and |  | defined in the Milstar and
| AEHF satellite system | AEHF satellite system |  | AEHF satellite system
| ORDs as described in | ORDs as described in |  | ORDs as described in
| Table 7 of the CPD. | Table 7 of the CPD. |  | Table 7 of the CPD.
Sustainment (Materiel Availability): Determined by system downtime, both planned and unplanned, requiring the early examination and determination of critical factors such as the total number of end items to be fielded and the major categories and drivers of system downtime. Per the operational concept, all

## Table 19
FAB-T end items will be placed into operational service without terminal-level float spares. Terminal must sustain the overall reliability and availability requirements specified in the AEHF satellite system ORD. The Line Replaceable Units (LRUs) on the antenna system are included in the MRT. MRT does not apply to environments where personnel are required to wear Mission Oriented Protective Posture (MOPP) or cold weather gear.
N/A | The FAB-T must meet | (T=O) The FAB-T must | TBD | The FAB-T must meet
| the Reliability and | meet the Reliability and |  | the Reliability and
| Maintainability | Maintainability |  | Maintainability
| requirements as follows: | requirements as follows: |  | requirements as follows:
| Fixed Ground Command | Fixed Ground Command |  | Fixed Ground Command
| Post (CP) – 0.9957 | Post (CP) – 0.9957 |  | Post (CP) – 0.9957
| Transportable CP – | Transportable CP – |  | Transportable CP –
| 0.9920 Airborne CP – | 0.9920 Airborne CP – |  | 0.9920 Airborne CP –
| 0.9884. MRT is the | 0.9884. MRT is the |  | 0.9884. MRT is the
| average on-equipment, | average on-equipment, |  | average on-equipment,
| organizational level | organizational level |  | organizational level
| corrective maintenance | corrective maintenance |  | corrective maintenance
| time to return a system | time to return a system to |  | time to return a system
| to operational status. | operational status. MRT |  | to operational status.
| MRT (excluding the | (excluding the antenna/ |  | MRT (excluding the
| antenna/ pedestal) | pedestal) should not |  | antenna/ pedestal)
| should not exceed 30 | exceed 30 minutes. MRT |  | should not exceed 30
| minutes. MRT will be | will be achievable in a |  | minutes. MRT will be
| achievable in a deployed | deployed environment. |  | achievable in a deployed
| environment. |  |  | environment.
Training
N/A | Using the Instructional | (T=O) Using the | TBD | Using the Instructional
| Systems Development | Instructional Systems |  | Systems Development
| (ISD) process, the FAB-T | Development (ISD) |  | (ISD) process, the FAB-T
| program shall deliver a | process, the FAB-T |  | program shall deliver a
| training system capable | program shall deliver a |  | training system capable
| of developing, | training system capable |  | of developing,
| conducting, and | of developing, |  | conducting, and
| controlling training | conducting, and |  | controlling training
| without impacting | controlling training |  | without impacting
| operations. FAB-T | without impacting |  | operations. FAB-T
| training shall naturally | operations. FAB-T |  | training shall naturally
| extend and be consistent | training shall naturally |  | extend and be consistent
| with existing CPT training | extend and be consistent |  | with existing CPT training
| delivered by Air | with existing CPT training |  | delivered by Air
| Education and Training | delivered by Air |  | Education and Training
| Command (AETC). The | Education and Training |  | Command (AETC). The
| training system delivered | Command (AETC). The |  | training system delivered
| by the FAB-T Program | training system delivered |  | by the FAB-T Program
| Office will comprise of | by the FAB-T Program |  | Office will comprise of
| technical data necessary | Office will comprise of |  | technical data necessary
| for training (e.g. | technical data necessary |  | for training (e.g.
| operations, maintenance | for training (e.g. |  | operations, maintenance
| and equipment manuals | operations, maintenance |  | and equipment manuals
| and/or TOs), Contract | and equipment manuals |  | and/or TOs), Contract
| Special Training (Type | and/or TOs), Contract |  | Special Training (Type
| 1), associated training | Special Training (Type 1), |  | 1), associated training

## Table 20
course material, and installed and functional operational terminal(s) for AETC-provided training. AETC will implement FAB-T initial qualification training and AFSPC will implement unit qualification training.
(U) Type 1 Training: Type 1 training shall provide operational and maintenance training to unit personnel, test agency personnel, initial AFSPC cadre, and AETC instructors prior to start of OT&E. Type 1 training shall continue until activation of AETC provided training. Training course(s) shall be tailored to meet the learning objectives of each duty position using the most cost-efficient training media, as determined by the AF ISD process. Type 1 training course material shall be delivered in Microsoft Office® editable format to applicable AFSPC and AETC units no later than 30 days after the completion of Type 1 training. Training Equipment and Material: The FAB T Program Office shall provide operational FAB-T hardware, Type 1 training material, and technical data to applicable AFSPC and AETC units for their development and implementation of AETC provided and unit qualification training. The operational hardware will be capable of performing 90% of operational tasks identified in the ISD
associated training course material, and installed and functional operational terminal(s) for AETC-provided training. AETC will implement FAB-T initial qualification training and AFSPC will implement unit qualification training. (U) Type 1 Training: Type 1 training shall provide operational and maintenance training to unit personnel, test agency personnel, initial AFSPC cadre, and AETC instructors prior to start of OT&E. Type 1 training shall continue until activation of AETC provided training. Training course(s) shall be tailored to meet the learning objectives of each duty position using the most cost-efficient training media, as determined by the AF ISD process. Type 1 training course material shall be delivered in Microsoft Office® editable format to applicable AFSPC and AETC units no later than 30 days after the completion of Type 1 training. Training Equipment and Material: The FAB T Program Office shall provide operational FAB-T hardware, Type 1 training material, and technical data to applicable AFSPC and AETC units for their development and implementation of AETC provided and unit qualification training. The operational hardware will be capable of performing 90% of operational tasks identified in the ISD
course material, and installed and functional operational terminal(s) for AETC-provided training. AETC will implement FAB-T initial qualification training and AFSPC will implement unit qualification training.
(U) Type 1 Training: Type 1 training shall provide operational and maintenance training to unit personnel, test agency personnel, initial AFSPC cadre, and AETC instructors prior to start of OT&E. Type 1 training shall continue until activation of AETC provided training. Training course(s) shall be tailored to meet the learning objectives of each duty position using the most cost-efficient training media, as determined by the AF ISD process. Type 1 training course material shall be delivered in Microsoft Office® editable format to applicable AFSPC and AETC units no later than 30 days after the completion of Type 1 training. Training Equipment and Material: The FAB T Program Office shall provide operational FAB-T hardware, Type 1 training material, and technical data to applicable AFSPC and AETC units for their development and implementation of AETC provided and unit qualification training. The operational hardware will be capable of performing 90% of operational tasks identified in the ISD

## Table 21
| process. | process. | process.
Requirements Reference
CPD dated August 5, 2015
Change Explanations
None
Notes
The KPPs were updated in accordance with Joint Capabilities Integration and Development System guidance - supersedes KPPs reported in 2007 APB.
The following footnotes 1 through 4 apply to the above sections as listed:
CPT Control Interface: 1
CPT Backwards Compatibility: 2
CPT Existing Terminal Coexistence: 3
CPT Satellite Constellation Coexistences: 4
Footnotes:
1/ For FAB-T, access to privileged Tracking Telemetry and Control (TT&C) capabilities and resource controller capabilities is restricted through a minor hardware difference in the System INFOSEC Module (SIM) specific to TT&C nodes, mission planning data sets, and dedicated COMSEC algorithms and associated keys. Terminal software shall assign privileges to ensure that only designated terminals at TT&C nodes will have TT&C capabilities and that only designated terminals at resource controller nodes will have resource controller capabilities.
2/ The FAB-T interface to the Red Switch is via the Advanced Narrowband Digital Voice Terminal (ANDVT), and the interface to NPES is via SCIS.
3/ FAB-T complies with the CPT interoperability requirements defined in the Terminal Segment Specification for the Milstar II Satellite Communications Program SR-2300 (excluding Digital Secure Voice Terminal (DSVT) KY-68, Asynchronous T1, Demand Assignment Multiple Access (DAMA) Limited Beam Management, LDR Full Beam Management of default agile locations, and Medium Data Rate (MDR) Capabilities) and Joint Terminal Segment Specification for the EHF Satellite Communications Program SR-3300.
4/ Interoperability with UFO/E and UFO/EE is predicated on the development by the AEHF Program of the capability for the terminal to receive mission planning data and TRANSEC keys from the Mission Planning Element. FAB-T is not expected to produce or deploy the capability associated with Advanced Polar System satellite interoperability. Terminal modifications for Advanced Polar System satellites are not funded. Note: Advanced Polar System is now Enhanced Polar System.

## Table 22
Acronyms and Abbreviations
AEHF - Advanced Extremely High Frequency AFCPT - Air Force Command Post Terminal AFRB - Air Force Report Back
APS - Advanced Polar System
ASMCS - AEHF Satellite Mission Control Subsystem BC - Backwards Compatible
CMS - Constellation Management System CPT - Command Post Terminal
DAMA - Demand Assignment Multiple Access
DIACAP - DoD Information Assurance Certification & Accreditation Process DIRECT - Defense IEMATS Replacement Command and Control Terminal DMU - Dual Modem Unit
DoDI - Department of Defense Instruction EAM - Emergency Action Message
EHF - Extremely High Frequency
FAB-T - Family of Advanced Beyond Line-of-Sight Terminals FDM - Force Direction Message
FET - Force Element Terminal (formerly known as Airborne Wideband Terminal, or AWT) FMC - Fully Mission Capable
IA - Information Assurance IAW - In Accordance With
IEMATS - Improved Emergency Message Automatic Transmission System IER - Information Exchange Requirement
LDR - Low Data Rate
MEECN - Minimum Essential Emergency Communications Network MMA - Milstar Messaging Application
MMPU - Minuteman MEECN Program Update MPSS - Mission Planning Sub System
NAST-T - Networked AEHF Satellite Test Tool
NC3 - Nuclear Command, Control & Communications NMT - Navy Multi-Band Terminal
NPES - Nuclear Planning and Execution System NRB - Navy Report Back
NSV - Nuclear Survivability and Vulnerability OPU - Operator Processing Unit
PCMR - Probability of Correct Message Receipt SCIS - Secure Communications Integrated System
SMART-T - Secure Mobile Anti-Jam Reliable Tactical Terminal STIG - Security Technical Implementation Guidance
TT&C - Telemetry, Tracking & Control
UFO-E/EE - UHF Follow On - EHF/EHF Enhanced UHF - Ultra High Frequency

## Table 23
FET
Performance Characteristics
SAR Baseline Development Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Interoperability
Enable all top-level | N/A | N/A | TBD | Enable all top-level IERs,
IERs, as depicted by |  |  |  | as depicted by mission
mission area and |  |  |  | area and designated
designated critical |  |  |  | critical between sending
between sending and |  |  |  | and receiving nodes
receiving nodes
Information Assurance
Meet DoD IA criteria | N/A | N/A | TBD | Meet DoD IA criteria and
and be certified/ |  |  |  | be certified/ accredited
accredited IAW DoD |  |  |  | IAW DoD 8510.1-M, DoD
8510.1-M, DoD |  |  |  | 8500.1, and DoDI 8500.2,
8500.1, and DoDI |  |  |  | or DoD certification and
8500.2, or DoD |  |  |  | accreditation process at
certification and |  |  |  | time of contract award
accreditation process
at time of contract
award
Survivability
FMC w/o | N/A | N/A | TBD | FMC w/o
damage/degradation, |  |  |  | damage/degradation,
throughout the |  |  |  | throughout the nuclear
nuclear environment |  |  |  | environment that the
that the aircraft is |  |  |  | aircraft is expected to
expected to survive, |  |  |  | survive, while meeting
while meeting PCMR |  |  |  | PCMR requirements
requirements
FET Legacy Milstar Support
Provide legacy Milstar | N/A | N/A | TBD | Provide legacy Milstar
dedicated |  |  |  | dedicated connections to
connections to |  |  |  | transmit/ receive functions
transmit/ receive |  |  |  | associated with individual
functions associated |  |  |  | Milstar service/nets
with individual Milstar |  |  |  | (Milstar LDR BC and
service/nets (Milstar |  |  |  | AEHF equivalent BC)
LDR BC and AEHF
equivalent BC)
FET Nuclear Interoperability
Inter-operate with | N/A | N/A | TBD | Inter-operate with platform
platform required |  |  |  | required JCS nuclear
JCS nuclear |  |  |  | protected IER
protected IER

## Table 24
FET Security Protection
Protect all transmitted and received Information | N/A | N/A | TBD | Protect all transmitted and received Information
FET Security Levels
Process and/or disseminate information products at any single level of classification up to and including TS/SCI | N/A | N/A | TBD | Process and/or disseminate information products at any single level of classification up to and including TS/SCI
FET Force Direction/Reportback
Enable EAM dissemination and FE report back | N/A | N/A | TBD | Enable EAM dissemination and FE report back
Network Ready
N/A | The system must fully support execution of all operational activities identified in the applicable joint and system integrated architectures. The system must also satisfy the technical requirements for Net- Centric military operations to include 1) Solution architecture products compliant with DoD Enterprise Architecture based on integrated DoD Defense Architecture Framework (DoDAF) content, including specified operational effective information exchanges 2) Compliant with Net- centric Data Strategy and Net-Centric Services Strategy, and the principles and rules identified in the DoD Information Enterprise Architecture (DoD IEA), excepting tactical and non-operational (OP) communications 3) Compliant with GIG | The system must fully support execution of joint critical operational activities identified in the applicable joint and system integrated architectures. The system must also satisfy the technical requirements for transition to Net- Centric military operations to include 1) Solution architecture products compliant with DoD Enterprise Architecture based on integrated DoD Defense Architecture Framework (DoDAF) content, including specified operational effective information exchanges 2) Compliant with Net- centric Data Strategy and Net-Centric Services Strategy, and the principles and rules identified in the DoD DoD IEA, excepting tactical and non-OP communications 3) | TBD | The system must fully support execution of all operational activities identified in the applicable joint and system integrated architectures. The system must also satisfy the technical requirements for Net-Centric military operations to include 1) Solution architecture products compliant with DoD Enterprise Architecture based on integrated DoD Defense Architecture Framework (DoDAF) content, including specified operational effective information exchanges 2) Compliant with Net-centric Data Strategy and Net-Centric Services Strategy, and the principles and rules identified in the DoD Information Enterprise Architecture (DoD IEA), excepting tactical and non- operational (OP) communications 3) Compliant with GIG Technical Guidance (GTG) to include Information Technology (IT) standards identified in the Standards

## Table 25
| Technical Guidance | Compliant GTG to |  | Profile View (StdV-1) and
| (GTG) to include | include IT standards |  | implementation guidance
| Information Technology | identified in the StdV-1 |  | GIG Enterprise Service
| (IT) standards identified | and implementation |  | Profiles (GESPs)
| in the Standards Profile | guidance of GESPs |  | necessary to meet all
| View (StdV-1) and | necessary to meet all |  | operational requirements
| implementation | operational |  | specified in the DoD
| guidance GIG | requirements specified |  | Enterprise Architecture
| Enterprise Service | in the DoD Enterprise |  | and solution architecture
| Profiles (GESPs) | Architecture and |  | views 4) Information
| necessary to meet all | solution architecture |  | assurance requirements
| operational | views 4) Information |  | including availability,
| requirements specified | assurance |  | integrity, authentication,
| in the DoD Enterprise | requirements including |  | confidentiality, and non-
| Architecture and | availability, integrity, |  | repudiation, and issuance
| solution architecture | authentication, |  | of an Authorization to
| views 4) Information | confidentiality, and non |  | Operate (ATO) by the
| assurance | -repudiation, and |  | Designated Accrediting
| requirements including | issuance of an Interim |  | Authority (DAA), and 5)
| availability, integrity, | Authorization to |  | Supportability
| authentication, | Operate (IATO) or |  | requirements to include
| confidentiality, and non- | ATO by the DAA, and |  | Selective Availability Anti-
| repudiation, and | 5) Supportability |  | spoofing Module (SAASM),
| issuance of an | requirements to |  | Spectrum and Joint
| Authorization to | include Selective |  | Tactical Radio System
| Operate (ATO) by the | Availability Anti- |  | (JTRS) requirements.
| Designated Accrediting | spoofing Module
| Authority (DAA), and 5) | (SAASM), Spectrum
| Supportability | and JTRS
| requirements to include | requirements.
Selective Availability
Anti-spoofing Module
(SAASM), Spectrum
and Joint Tactical
Radio System (JTRS)
requirements.
Strategic Services
N/A | Terminals supporting | (T=O) Terminals | TBD | Terminals supporting
| nuclear/strategic | supporting |  | nuclear/strategic
| operations will enable | nuclear/strategic |  | operations will enable
| emergency action | operations will enable |  | emergency action
| message | emergency action |  | message dissemination
| dissemination while | message |  | while meeting the
| meeting the Probability | dissemination while |  | Probability of Correct
| of Correct Message | meeting the Probability |  | Message Receipt (PCMR)
| Receipt (PCMR) | of Correct Message |  | requirements stated in
| requirements stated in | Receipt (PCMR) |  | Appendix F to Enclosure A
| Appendix F to | requirements stated in |  | CJCSI) 6811.01. Each
| Enclosure A CJCSI) | Appendix F to |  | Nuclear Command Center
| 6811.01. Each Nuclear | Enclosure A CJCSI) |  | node or force element
| Command Center node | 6811.01. Each Nuclear |  | platform must be able to
| or force element | Command Center |  | simultaneously support all
| platform must be able | node or force element |  | services assigned to that

## Table 26
| to simultaneously | platform must be able |  | node/platform as
| support all services | to simultaneously |  | mandated in the
| assigned to that | support all services |  | Emergency Action
| node/platform as | assigned to that |  | Procedures of the Joint
| mandated in the | node/platform as |  | Staff directed networks
| Emergency Action | mandated in the |  | and the USSTRATCOM
| Procedures of the Joint | Emergency Action |  | Network Operating
| Staff directed networks | Procedures of the |  | Instruction for
| and the USSTRATCOM | Joint Staff directed |  | USSTRATCOM directed
| Network Operating | networks and the |  | networks. FE platforms will
| Instruction for | USSTRATCOM |  | be required to perform this
| USSTRATCOM | Network Operating |  | function with a single FAB-
| directed networks. FE | Instruction for |  | T.
| platforms will be | USSTRATCOM
| required to perform this | directed networks. FE
| function with a single | platforms will be
| FAB-T. | required to perform
this function with a
single FAB-T.
Terminal Survivability
N/A | Terminals supporting | (T=O) Terminals | TBD | Terminals supporting
| nuclear operations | supporting nuclear |  | nuclear operations must
| must be fully mission | operations must be |  | be fully mission capable up
| capable up to the | fully mission capable |  | to the maximum nuclear
| maximum nuclear | up to the maximum |  | environment that the
| environment that the | nuclear environment |  | platform is expected to
| platform is expected to | that the platform is |  | survive. Any recovery from
| survive. Any recovery | expected to survive. |  | circumvention required for
| from circumvention | Any recovery from |  | a dose rate event will not
| required for a dose rate | circumvention required |  | be part of the Emergency
| event will not be part of | for a dose rate event |  | Action Message (EAM)
| the Emergency Action | will not be part of the |  | transmission timeline.
| Message (EAM) | Emergency Action
| transmission timeline. | Message (EAM)
transmission timeline.
Capacity
N/A | The FET, in conjunction | (T=O) The FET, in | TBD | The FET, in conjunction
| with ancillary | conjunction with |  | with ancillary cryptographic
| cryptographic | ancillary cryptographic |  | equipment, will support up
| equipment, will support | equipment, will support |  | to seven simultaneous
| up to seven | up to seven |  | protected EHF networks
| simultaneous protected | simultaneous |  | (Point-to-Point [PTP] calls,
| EHF networks (Point-to | protected EHF |  | conference networks,
| -Point [PTP] calls, | networks (Point-to- |  | reportback service, and
| conference networks, | Point [PTP] calls, |  | simplex broadcast
| reportback service, and | conference networks, |  | service). Terminals will
| simplex broadcast | reportback service, |  | include all equipment
| service). Terminals will | and simplex broadcast |  | necessary to accept
| include all equipment | service). Terminals will |  | system data rates defined
| necessary to accept | include all equipment |  | in the Milstar and AEHF
| system data rates | necessary to accept |  | satellite system ORDs and
| defined in the Milstar | system data rates |  | EPS CDD as described in

## Table 27
| and AEHF satellite system ORDs and EPS CDD as described in Table 4 of the CDD. | defined in the Milstar and AEHF satellite system ORDs and EPS CDD as described in Table 4 of the CDD. |  | Table 4 of the CDD.
Sustainment
N/A | The FAB-T FET must | The FAB-T FET must | TBD | The FAB-T FET must
| meet a Reliability, | meet a Reliability, |  | meet a Reliability,
| Maintainability and | Maintainability and |  | Maintainability and
| Dependability | Dependability |  | Dependability requirement
| requirement of 0.9923. | requirement of 0.9923. |  | of 0.9923. Mean Repair
| Mean Repair Time | Mean Repair Time |  | Time (MRT) is the average
| (MRT) is the average | (MRT) is the average |  | on-equipment,
| on-equipment, | on-equipment, |  | organizational level
| organizational level | organizational level |  | corrective maintenance
| corrective maintenance | corrective |  | time to return a system to
| time to return a system | maintenance time to |  | operational status. The
| to operational status. | return a system to |  | MRT (excluding the
| The MRT (excluding the | operational status. The |  | antenna/pedestal) will not
| antenna/pedestal) will | MRT (excluding the |  | exceed 15 minutes. MRT
| not exceed 15 minutes. | antenna/pedestal) |  | will be achievable in a
| MRT will be achievable | should not exceed 30 |  | deployed environment.
| in a deployed | minutes. MRT will be
| environment. | achievable in a
deployed environment.
Training
N/A | Contractor is | (T=O) Contractor is | TBD | Contractor is developing
| developing Type 1 | developing Type 1 |  | Type 1 operator and
| operator and maintainer | operator and |  | maintainer course material
| course material along | maintainer course |  | along with Computer
| with Computer Based | material along with |  | Based Training as part of
| Training as part of the | Computer Based |  | the development contract.
| development contract. | Training as part of the |  | Training materials will be
| Training materials will | development contract. |  | supplied to all services. A
| be supplied to all | Training materials will |  | joint Training Program
| services. A joint | be supplied to all |  | need not be developed.
| Training Program need | services. A joint
| not be developed. | Training Program need
not be developed.
Requirements Reference
CDD dated February 15, 2013
Change Explanations
None
Notes

## Table 28
The KPPs were updated in accordance with Joint Capabilities Integration and Development System guidance - supersedes KPPs reported in 2007 APB.
This section is TBD at this time. While the FET remains a valid requirement for the FAB-T program, it is currently unfunded and the Air Force has not yet finalized its strategy for FET development.
The following footnotes 1 & 2 apply to the above sections as listed: Interoperability: 2
Information Assurance: 2
Survivability: 2
FET Legacy Milstar Support: 2 FET Nuclear Interoperability: 2 FET Security Protection: 2 FET Security Levels: 1 & 2
FET Force Direction/Reportback: 2
1/ Threshold requirements (single level security) placed on contract; objective requirements (multi-level security) not proposed by contractor. This performance parameter only applies to the FET configuration.
2/ The LDR System provided to the strategic forces must meet the following Performance parameters in Section A: Interoperability, Information Assurance, Survivability, FET Legacy Milstar, FET Nuclear Interoperability, FET Security Protection, FET Security Levels, and FET Force Direction/Reportback. The Extended Data Rate (XDR) System must meet all the Performance parameters in Section A.
Acronyms and Abbreviations
AEHF - Advanced Extremely High Frequency AWT - Advanced Wideband Terminal
BC - Backward Compatibility
DoDI - Department of Defense Instruction EAM - Emergency Action Message
FE - Force Element
FET - Force Element Terminal FMC - Fully Mission Capable IA - Information Assurance
IER - Information Exchange Requirement JCS - Joint Chiefs of Staff
LDR - Low Data Rate
ORD - Operational Requirement Document PCMR - Probability of Correct Message Receipt SCI - Sensitive Compartmented Information
TS - Top Secret w/o - without
XDR - Extended Data Rate

## Table 29
Track to Budget
CPT
General Notes
The appropriation 3021 (Space Procurement, Air Force) which was not part of the previous SAR has been added in place of 3080 for FY16-21 based on the current Air Force funding position.
RDT&E
Appn |  |  | BA | PE
Air Force 3600 07 0303001F
Project | Name
672490 Family of Adv Beyond Line of Sight Terminals (FAB-T)
Air Force 3600 07 0303601F
Project | Name
672487 MILSATCOM Terminals (Shared) (Sunk) 672489 FAB-T Alternative (Sunk)
672490 Family of Adv Beyond Line of Sight Terminals (FAB-T)
(Sunk)
Procurement
Appn |  |  | BA | PE
Air Force 3010 06 0303001F
|  | Line Item |  | Name
|  | 999 |  | Initial Spares/Repair Parts | (Shared)
Air Force |  | 3010 | 6 | 0303601F
|  | Line Item |  | Name
|  | 999 |  | Initial Spares/Repair Parts | (Shared) | (Sunk)
Air Force |  | 3010 05 |  | 0303601F
|  | Line Item |  | Name
|  | FBLOST |  | Family of Beyond Line-of-Sight Terminals |  | (Sunk)
Air Force |  | 3010 05 |  | 0303001F
|  | Line Item |  | Name
|  | FBLOST |  | Family of Beyond Line-of-Sight Terminals
Air Force |  | 3010 05 |  | 0303601F
|  | Line Item |  | Name
|  | OTHACF |  | Other Aircraft | (Shared) | (Sunk)
Air Force |  | 3021 01 |  | 0303001F
|  | Line Item |  | Name
FBLOST Family of Advanced Beyond Line of Sight
Terminals

## Table 30
|  | SSPARE |  | Initial Spares/Repair Parts (Shared)
Air Force |  | 3080 03 |  | 0303001F
|  | Line Item |  | Name
|  | 836700 |  | Family of Beyond Line-of-Sight Terminals (Sunk)
Air Force |  | 3080 03 |  | 0303601F
|  | Line Item |  | Name
|  | 836700 |  | Family of Beyond Line-of-Sight Terminals |  | (Sunk)
|  | 836780 |  | MILSATCOM Space | (Shared) | (Sunk)
Air Force |  | 3080 | 5 | 0303001F
|  | Line Item |  | Name
|  | 861900 |  | Spares and Repair Parts | (Shared)
Air Force |  | 3080 | 5 | 0303601F
|  | Line Item |  | Name
861900 Spares and Repair Parts (Shared) (Sunk)
Notes
FAB-T shares the Other Aircraft (OTHACF) line item with other modification programs. Procurement funding for six terminals for the President of the United States aircraft are included in OTHACF line item. Procurement funding for all other FAB-T airborne terminals are included in the Family of Beyond Line-of-Sight Terminals (FBLOST) line item. FAB- T shares the 000999 SSPARE Initial Spares line item with other programs, and shares 836780 with other Military Satellite Communication (MILSATCOM) programs.
FET
General Notes
The appropriation 3021 (Space Procurement, Air Force) which was not part of the previous SAR has been added in place of 3080 based on the current Air Force funding position for CPT.
RDT&E
Appn |  |  | BA | PE
Air Force 3600 07 0303001F
Project | Name
672490 Family of Adv Beyond Line of Sight Terminals (FAB-T)
Air Force 3600 07 0303601F
Project | Name
672487 MILSATCOM Terminals (Shared) (Sunk) 672489 FAB-T Alternative (Sunk)
672490 Family of Adv Beyond Line of Sight Terminals (FAB-T)
(Sunk)
Procurement
Appn |  |  | BA | PE

## Table 31
Air Force | 3010 06 | 0303001F
| Line Item | Name
| 999 | Initial Spares/Repair Parts | (Shared)
Air Force | 3010 06 | 0303601F
| Line Item | Name
| 999 | Initial Spares/Repair Parts | (Shared) | (Sunk)
Air Force | 3010 05 | 0303601F
| Line Item | Name
| FBLOST | Family of Beyond Line-of-Sight Terminals |  | (Sunk)
Air Force | 3010 05 | 0303001F
| Line Item | Name
| FBLOST | Family of Beyond Line-of-Sight Terminals
Air Force | 3010 05 | 0303601F
| Line Item | Name
| OTHACF | Other Aircraft | (Shared) | (Sunk)
Air Force | 3021 01 | 0303001F
| Line Item | Name
| FBLOST | Family of Advanced Beyond Line-of-Sight Terminals
Air Force | 3021 02 | 0303001F
| Line Item | Name
| SSPARE | Initial Spares/Repair Parts | (Shared)
Air Force | 3080 03 | 0303001F
| Line Item | Name
| 836700 | Family of Beyond Line-of-Sight Terminals |  | (Sunk)
Air Force | 3080 03 | 0303601F
| Line Item | Name
| 836700 | Family of Beyond Line-of-Sight Terminals |  | (Sunk)
| 836780 | MILSATCOM Space | (Shared) | (Sunk)
Air Force | 3080 05 | 0303001F
| Line Item | Name
| 861900 | Spares and Repair Parts | (Shared)
Air Force | 3080 05 | 0303601F
| Line Item | Name
| 861900 | Spares and Repair Parts | (Shared) | (Sunk)
Notes
FAB-T shares the Other Aircraft (OTHACF) line item with other modification programs. Procurement funding for six terminals for the President of the United States aircraft are included in OTHACF line item. Procurement funding for all other FAB-T airborne terminals are included in the Family of Beyond Line-of-Sight Terminals (FBLOST) line item. FAB- T shares the 000999 and SSPARE Initial Spares line item with other programs, and shares 836780 with other Military Satellite Communication (MILSATCOM) programs.

## Table 32
Cost and Funding
Cost Summary - Total Program
Total Acquisition Cost - Total Program
Appropriation | BY 2015 $M |  |  |  | BY 2015 $M |  | TY $M
| SAR Baseline Development Estimate | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Development Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E | 1273.8 |  | 3083.1 | -- |  | 2987.2 |  | 1431.1 |  | 2924.7 |  | 2909.1
Procurement | 1368.6 |  | 1459 | -- |  | 1399.7 |  | 1736.3 |  | 1688.9 |  | 1723.5
Flyaway | -- |  | -- | -- |  | 930.6 |  | -- |  | -- |  | 1139.2
Recurring | -- |  | -- | -- |  | 930.6 |  | -- |  | -- |  | 1139.2
Non Recurring | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support | -- |  | -- | -- |  | 469.1 |  | -- |  | -- |  | 584.3
Other Support | -- |  | -- | -- |  | 143.2 |  | -- |  | -- |  | 177.1
Initial Spares | -- |  | -- | -- |  | 325.9 |  | -- |  | -- |  | 407.2
MILCON | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Total | 2642.4 |  | 4542.1 | N/A |  | 4386.9 |  | 3167.4 |  | 4613.6 |  | 4632.6

## Table 33
Cost and Funding
Cost Summary - CPT
Total Acquisition Cost - CPT
Appropriation | BY 2015 $M |  |  |  |  | BY 2015 $M |  | TY $M
| SAR Baseline Development Estimate |  | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Development Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E | 633.2 |  |  | 1159 | 1274.9 |  | 1140.9 |  | 556.5 |  | 1075.7 |  | 1060
Procurement | 667.1 |  |  | 584 | 642.4 |  | 618.9 |  | 666.9 |  | 622.4 |  | 656.9
Flyaway | -- |  |  | -- | -- |  | 431.6 |  | -- |  | -- |  | 458.9
Recurring | -- |  |  | -- | -- |  | 431.6 |  | -- |  | -- |  | 458.9
Non Recurring | -- |  |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support | -- |  |  | -- | -- |  | 187.3 |  | -- |  | -- |  | 198
Other Support | -- |  |  | -- | -- |  | 71.4 |  | -- |  | -- |  | 76.1
Initial Spares | -- |  |  | -- | -- |  | 115.9 |  | -- |  | -- |  | 121.9
MILCON | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 1300.3 |  |  | 1743 | N/A |  | 1759.8 |  | 1223.4 |  | 1698.1 |  | 1716.9
Current APB Cost Estimate Reference
Air Force SCP dated July 07, 2015
Confidence Level
Confidence Level of cost estimate for current APB: 55%
A mathematically derived confidence level was not computed for this life-cycle cost estimate (LCCE). This LCCE represents the expected value, taking into consideration relevant risks, including ordinary levels of external and unforeseen events. It aims to provide sufficient resources to execute the program under normal conditions encountering average levels of technical, schedule, and programmatic risk and external influence
The Base Year for the program has been updated from FY 2002 to FY 2015 using the following deflators:
Appn Category |  | Deflation Factor
RDT&E 1.27811861
Procurement 1.27811861
Cost Notes
The CPT and FET program were combined in the 2014 SAR and are now broken into subprograms to reflect the March 3, 2016 APB.

## Table 34
Total Quantity - CPT
Quantity | SAR Baseline Development Estimate | Current APB Production | Current Estimate
RDT&E | 10 | 25 | 25
Procurement | 76 | 84 | 84
Total | 86 | 109 | 109
Quantity Notes
For CPT there are a total of 109 systems, which includes 25 EDMs (12 Boeing and 13 Raytheon) and 84 production systems. All quantities shown reflect the program baseline as approved in the Milestone C ADM.

## Table 35
Cost Summary - FET
Total Acquisition Cost - FET
Appropriation | BY 2015 $M |  |  |  |  | BY 2015 $M |  | TY $M
| SAR Baseline Development Estimate |  | Current APB Development Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Development Estimate |  | Current APB Development Objective |  | Current Estimate
RDT&E | 994.9 |  |  | 1924.1 | 2116.5 |  | 1846.3 |  | 874.6 |  | 1849 |  | 1849.1
Procurement | 1082.2 |  |  | 875 | 962.5 |  | 780.8 |  | 1069.4 |  | 1066.5 |  | 1066.6
Flyaway | -- |  |  | -- | -- |  | 499 |  | -- |  | -- |  | 680.3
Recurring | -- |  |  | -- | -- |  | 499 |  | -- |  | -- |  | 680.3
Non Recurring | -- |  |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support | -- |  |  | -- | -- |  | 281.8 |  | -- |  | -- |  | 386.3
Other Support | -- |  |  | -- | -- |  | 71.8 |  | -- |  | -- |  | 101
Initial Spares | -- |  |  | -- | -- |  | 210 |  | -- |  | -- |  | 285.3
MILCON | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 2077.1 |  |  | 2799.1 | N/A |  | 2627.1 |  | 1944 |  | 2915.5 |  | 2915.7
Current APB Cost Estimate Reference
Air Force SCP dated July 07, 2015
Confidence Level
Confidence Level of cost estimate for current APB: 54%
A mathematically derived confidence level was not computed for this life-cycle cost estimate (LCCE). This LCCE represents the expected value, taking into consideration relevant risks, including ordinary levels of external and unforeseen events. It aims to provide sufficient resources to execute the program under normal conditions encountering average levels of technical, schedule, and programmatic risk and external influence
The Base Year for the program has been updated from FY 2002 to FY 2015 using the following deflators:
Appn Category |  | Deflation Factor
RDT&E 1.27811861
Procurement 1.27811861
Cost Notes
The CPT and FET program were combined in the 2014 SAR and are now broken into subprograms to reflect the March 3, 2016 APB.

## Table 36
Total Quantity - FET
Quantity | SAR Baseline Development Estimate | Current APB Development | Current Estimate
RDT&E | 15 | 26 | 26
Procurement | 115 | 132 | 132
Total | 130 | 158 | 158
Quantity Notes
There are 158 FETs planned, which includes 26 EDM terminals (18 from the original Boeing contract and 8 for the future program) and 132 procurement terminals all associated with the future program.

## Table 37
Cost and Funding
Funding Summary - Total Program
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | To Complete | Total
RDT&E | 2247.7 | 3.9 | 14.6 | 0 | 0 | 0 | 0 | 642.9 | 2909.1
Procurement | 142.6 | 143.7 | 111.2 | 152.3 | 62.6 | 34.3 | 10.2 | 1066.6 | 1723.5
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2017 Total | 2390.3 | 147.6 | 125.8 | 152.3 | 62.6 | 34.3 | 10.2 | 1709.5 | 4632.6
PB 2016 Total | 2457.7 | 175.4 | 179.4 | 60.5 | 89.5 | 150.1 | 130.9 | 1021.2 | 4264.7
Delta | -67.4 | -27.8 | -53.6 | 91.8 | -26.9 | -115.8 | -120.7 | 688.3 | 367.9

## Table 38
Cost and Funding
Funding Summary - CPT
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 1041.5 | 3.9 |  | 14.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1060
Procurement | 142.6 | 143.7 |  | 111.2 |  | 152.3 |  | 62.6 |  | 34.3 |  | 10.2 |  | 0 |  | 656.9
MILCON | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 1184.1 | 147.6 |  | 125.8 |  | 152.3 |  | 62.6 |  | 34.3 |  | 10.2 |  | 0 |  | 1716.9
PB 2016 Total | -- | -- |  | -- |  | -- |  | -- |  | -- |  | -- |  | -- |  | 0
Delta | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1716.9
Funding Notes
For FY 2016, PB funding was not previously broken out between the subprograms for CPT and FET.
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 25 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25
Production | 0 |  | 19 |  | 20 | 17 | 26 |  | 2 |  | 0 |  | 0 |  | 0 |  | 84
PB 2017 Total | 25 |  | 19 |  | 20 | 17 | 26 |  | 2 |  | 0 |  | 0 |  | 0 |  | 109
PB 2016 Total | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Delta | 25 |  | 19 |  | 20 | 17 | 26 |  | 2 |  | 0 |  | 0 |  | 0 |  | 109

## Table 39
Funding Summary - FET
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 1206.2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 642.9 |  | 1849.1
Procurement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1066.6 |  | 1066.6
MILCON | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 1206.2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1709.5 |  | 2915.7
PB 2016 Total | -- | -- |  | -- |  | -- |  | -- |  | -- |  | -- |  | -- |  | 0
Delta | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2915.7
Funding Notes
For FY 2016, PB funding was not previously broken out between the subprograms for CPT and FET.
Follow-on Development and Production of FET to be procured beyond the FYDP.
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 26 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 26
Production | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 132 |  | 132
PB 2017 Total | 26 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 132 |  | 158
PB 2016 Total | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Delta | 26 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 132 |  | 158

## Table 40
Cost and Funding
Annual Funding By Appropriation - CPT
Annual Funding - CPT 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.1
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.1
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.2
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44.6
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 67.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 76.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 75.1
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 108
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 81.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 73.7
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 102.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 161.5
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 118.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57.9
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.9
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.6
Subtotal |  | 25 | -- |  | -- |  | -- |  | -- |  | -- |  | 1060

## Table 41
Annual Funding - CPT 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.7
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.2
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.1
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 79.6
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 87.7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 84.1
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 118.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 88.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 78.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 107.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 166.5
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 118.9
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57.4
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.8
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14
Subtotal |  | 25 | -- |  | -- |  | -- |  | -- |  | -- |  | 1140.9

## Table 42
Annual Funding - CPT 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | 4.3 |  | -- |  | -- |  | 4.3 |  | -- |  | 4.3
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | 1.3 |  | -- |  | -- |  | 1.3 |  | -- |  | 1.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | 3.7 |  | -- |  | -- |  | 3.7 |  | -- |  | 3.7
2013 |  | -- | 4.6 |  | -- |  | -- |  | 4.6 |  | -- |  | 4.6
2014 |  | -- | 1.9 |  | -- |  | -- |  | 1.9 |  | -- |  | 1.9
2015 |  | 10 | 47.7 |  | -- |  | -- |  | 47.7 |  | 13.6 |  | 61.3
2016 |  | 8 | 40 |  | -- |  | -- |  | 40 |  | 7.1 |  | 47.1
2017 |  | 1 | 2.6 |  | -- |  | -- |  | 2.6 |  | 5.6 |  | 8.2
2018 |  | 2 | 19.6 |  | -- |  | -- |  | 19.6 |  | 3.9 |  | 23.5
2019 |  | 2 | 11.8 |  | -- |  | -- |  | 11.8 |  | 8.8 |  | 20.6
2020 |  | -- | 1.5 |  | -- |  | -- |  | 1.5 |  | 0.5 |  | 2
2021 |  | -- | 1.6 |  | -- |  | -- |  | 1.6 |  | -- |  | 1.6
Subtotal |  | 23 | 140.6 |  | -- |  | -- |  | 140.6 |  | 39.5 |  | 180.1

## Table 43
Annual Funding - CPT 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | 4.7 |  | -- |  | -- |  | 4.7 |  | -- |  | 4.7
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | 1.4 |  | -- |  | -- |  | 1.4 |  | -- |  | 1.4
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | 3.8 |  | -- |  | -- |  | 3.8 |  | -- |  | 3.8
2013 |  | -- | 4.6 |  | -- |  | -- |  | 4.6 |  | -- |  | 4.6
2014 |  | -- | 1.9 |  | -- |  | -- |  | 1.9 |  | -- |  | 1.9
2015 |  | 10 | 46.1 |  | -- |  | -- |  | 46.1 |  | 13.2 |  | 59.3
2016 |  | 8 | 38 |  | -- |  | -- |  | 38 |  | 6.7 |  | 44.7
2017 |  | 1 | 2.4 |  | -- |  | -- |  | 2.4 |  | 5.2 |  | 7.6
2018 |  | 2 | 17.9 |  | -- |  | -- |  | 17.9 |  | 3.6 |  | 21.5
2019 |  | 2 | 10.6 |  | -- |  | -- |  | 10.6 |  | 7.8 |  | 18.4
2020 |  | -- | 1.3 |  | -- |  | -- |  | 1.3 |  | 0.5 |  | 1.8
2021 |  | -- | 1.4 |  | -- |  | -- |  | 1.4 |  | -- |  | 1.4
Subtotal |  | 23 | 134.1 |  | -- |  | -- |  | 134.1 |  | 37 |  | 171.1

## Table 44
Cost Quantity Information - CPT 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2015 $M
2007 | -- | --
2008 | -- | --
2009 | -- | --
2010 | -- | --
2011 | -- | --
2012 | -- | --
2013 | -- | --
2014 | -- | --
2015 | 10 | 58.3
2016 | 8 | 46.6
2017 | 1 | 5.8
2018 | 2 | 11.7
2019 | 2 | 11.7
2020 | -- | --
2021 | -- | --
Subtotal | 23 | 134.1

## Table 45
Annual Funding - CPT 3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2010 |  | -- | 1.9 |  | -- |  | -- |  | 1.9 |  | -- |  | 1.9
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | 5 |  | -- |  | -- |  | 5 |  | -- |  | 5
2014 |  | -- | 0.4 |  | -- |  | -- |  | 0.4 |  | 2.9 |  | 3.3
2015 |  | 9 | 43.1 |  | -- |  | -- |  | 43.1 |  | 12.2 |  | 55.3
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | 44.4 |  | 44.4
Subtotal |  | 9 | 50.4 |  | -- |  | -- |  | 50.4 |  | 59.5 |  | 109.9

## Table 46
Annual Funding - CPT 3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2010 |  | -- | 2 |  | -- |  | -- |  | 2 |  | -- |  | 2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | 5.1 |  | -- |  | -- |  | 5.1 |  | -- |  | 5.1
2014 |  | -- | 0.4 |  | -- |  | -- |  | 0.4 |  | 2.9 |  | 3.3
2015 |  | 9 | 42.7 |  | -- |  | -- |  | 42.7 |  | 12.1 |  | 54.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | 43.4 |  | 43.4
Subtotal |  | 9 | 50.2 |  | -- |  | -- |  | 50.2 |  | 58.4 |  | 108.6

## Table 47
Cost Quantity Information - CPT 3080 ¦ Procurement ¦ Other Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2015 $M
2010 | -- | --
2011 | -- | --
2012 | -- | --
2013 | -- | --
2014 | -- | --
2015 | 9 | 50.2
2016 | -- | --
Subtotal | 9 | 50.2

## Table 48
Annual Funding - CPT 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | 12 | 31.9 |  | -- |  | -- |  | 31.9 |  | 20.3 |  | 52.2
2017 |  | 16 | 74.6 |  | -- |  | -- |  | 74.6 |  | 28.4 |  | 103
2018 |  | 24 | 108.8 |  | -- |  | -- |  | 108.8 |  | 20 |  | 128.8
2019 |  | -- | 12.9 |  | -- |  | -- |  | 12.9 |  | 29.1 |  | 42
2020 |  | -- | 31.1 |  | -- |  | -- |  | 31.1 |  | 1.2 |  | 32.3
2021 |  | -- | 8.6 |  | -- |  | -- |  | 8.6 |  | -- |  | 8.6
Subtotal |  | 52 | 267.9 |  | -- |  | -- |  | 267.9 |  | 99 |  | 366.9

## Table 49
Annual Funding - CPT 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | 12 | 30.5 |  | -- |  | -- |  | 30.5 |  | 19.4 |  | 49.9
2017 |  | 16 | 70 |  | -- |  | -- |  | 70 |  | 26.7 |  | 96.7
2018 |  | 24 | 100.2 |  | -- |  | -- |  | 100.2 |  | 18.4 |  | 118.6
2019 |  | -- | 11.6 |  | -- |  | -- |  | 11.6 |  | 26.3 |  | 37.9
2020 |  | -- | 27.5 |  | -- |  | -- |  | 27.5 |  | 1.1 |  | 28.6
2021 |  | -- | 7.5 |  | -- |  | -- |  | 7.5 |  | -- |  | 7.5
Subtotal |  | 52 | 247.3 |  | -- |  | -- |  | 247.3 |  | 91.9 |  | 339.2

## Table 50
Cost Quantity Information - CPT 3021 ¦ Procurement ¦ Space Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2015 $M
2016 | 12 | 57.1
2017 | 16 | 76.1
2018 | 24 | 114.1
2019 | -- | --
2020 | -- | --
2021 | -- | --
Subtotal | 52 | 247.3

## Table 51
Annual Funding By Appropriation - FET
Annual Funding - FET 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.2
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.4
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.7
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 70.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 105.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 119.9
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 117.9
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 169.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 128.4
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 115.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 161.3
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 118.7
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 50.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.1
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.9
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.3
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 192.7
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 237
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 147.1
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49.5
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.8
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.6
Subtotal |  | 26 | -- |  | -- |  | -- |  | -- |  | -- |  | 1849.1

## Table 52
Annual Funding - FET 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.1
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.1
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.5
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 85.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 125.1
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 137.7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 132
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 186.2
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 139.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 123.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 169.3
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 122.4
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 50.9
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.1
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.9
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.9
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 157.9
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 190.3
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 115.7
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.2
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.6
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
Subtotal |  | 26 | -- |  | -- |  | -- |  | -- |  | -- |  | 1846.3

## Table 53
Annual Funding - FET 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2027 |  | 8 | 50.4 |  | -- |  | -- |  | 50.4 |  | 21.7 |  | 72.1
2028 |  | 30 | 157.8 |  | -- |  | -- |  | 157.8 |  | 68.9 |  | 226.7
2029 |  | 42 | 179.4 |  | -- |  | -- |  | 179.4 |  | 108 |  | 287.4
2030 |  | 43 | 171.7 |  | -- |  | -- |  | 171.7 |  | 108.7 |  | 280.4
2031 |  | -- | 19.4 |  | -- |  | -- |  | 19.4 |  | 17.6 |  | 37
2032 |  | -- | 19.9 |  | -- |  | -- |  | 19.9 |  | 17.3 |  | 37.2
2033 |  | -- | 18.7 |  | -- |  | -- |  | 18.7 |  | 13.5 |  | 32.2
2034 |  | -- | 6.6 |  | -- |  | -- |  | 6.6 |  | 2.2 |  | 8.8
Subtotal |  | 123 | 623.9 |  | -- |  | -- |  | 623.9 |  | 357.9 |  | 981.8

## Table 54
Annual Funding - FET 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2027 |  | 8 | 38.5 |  | -- |  | -- |  | 38.5 |  | 16.6 |  | 55.1
2028 |  | 30 | 118.3 |  | -- |  | -- |  | 118.3 |  | 51.6 |  | 169.9
2029 |  | 42 | 131.7 |  | -- |  | -- |  | 131.7 |  | 79.3 |  | 211
2030 |  | 43 | 123.7 |  | -- |  | -- |  | 123.7 |  | 78.3 |  | 202
2031 |  | -- | 13.7 |  | -- |  | -- |  | 13.7 |  | 12.4 |  | 26.1
2032 |  | -- | 13.8 |  | -- |  | -- |  | 13.8 |  | 12 |  | 25.8
2033 |  | -- | 12.7 |  | -- |  | -- |  | 12.7 |  | 9.1 |  | 21.8
2034 |  | -- | 4.4 |  | -- |  | -- |  | 4.4 |  | 1.5 |  | 5.9
Subtotal |  | 123 | 456.8 |  | -- |  | -- |  | 456.8 |  | 260.8 |  | 717.6

## Table 55
Cost Quantity Information - FET 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2015 $M
2027 | 8 | 29.7
2028 | 30 | 111.4
2029 | 42 | 156
2030 | 43 | 159.7
2031 | -- | --
2032 | -- | --
2033 | -- | --
2034 | -- | --
Subtotal | 123 | 456.8

## Table 56
Annual Funding - FET 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2027 |  | 2 | 11.7 |  | -- |  | -- |  | 11.7 |  | 4.8 |  | 16.5
2028 |  | 4 | 19.7 |  | -- |  | -- |  | 19.7 |  | 9.4 |  | 29.1
2029 |  | 3 | 15.4 |  | -- |  | -- |  | 15.4 |  | 8.4 |  | 23.8
2030 |  | -- | 3.7 |  | -- |  | -- |  | 3.7 |  | 1.2 |  | 4.9
2031 |  | -- | 1.8 |  | -- |  | -- |  | 1.8 |  | 1.6 |  | 3.4
2032 |  | -- | 1.8 |  | -- |  | -- |  | 1.8 |  | 1.6 |  | 3.4
2033 |  | -- | 1.7 |  | -- |  | -- |  | 1.7 |  | 1.2 |  | 2.9
2034 |  | -- | 0.6 |  | -- |  | -- |  | 0.6 |  | 0.2 |  | 0.8
Subtotal |  | 9 | 56.4 |  | -- |  | -- |  | 56.4 |  | 28.4 |  | 84.8

## Table 57
Annual Funding - FET 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2027 |  | 2 | 9 |  | -- |  | -- |  | 9 |  | 3.7 |  | 12.7
2028 |  | 4 | 14.9 |  | -- |  | -- |  | 14.9 |  | 7.1 |  | 22
2029 |  | 3 | 11.4 |  | -- |  | -- |  | 11.4 |  | 6.2 |  | 17.6
2030 |  | -- | 2.7 |  | -- |  | -- |  | 2.7 |  | 0.9 |  | 3.6
2031 |  | -- | 1.3 |  | -- |  | -- |  | 1.3 |  | 1.1 |  | 2.4
2032 |  | -- | 1.3 |  | -- |  | -- |  | 1.3 |  | 1.1 |  | 2.4
2033 |  | -- | 1.2 |  | -- |  | -- |  | 1.2 |  | 0.8 |  | 2
2034 |  | -- | 0.4 |  | -- |  | -- |  | 0.4 |  | 0.1 |  | 0.5
Subtotal |  | 9 | 42.2 |  | -- |  | -- |  | 42.2 |  | 21 |  | 63.2

## Table 58
Cost Quantity Information - FET 3021 ¦ Procurement ¦ Space Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2015 $M
2027 | 2 | 9.4
2028 | 4 | 18.7
2029 | 3 | 14.1
2030 | -- | --
2031 | -- | --
2032 | -- | --
2033 | -- | --
2034 | -- | --
Subtotal | 9 | 42.2

## Table 59
Low Rate Initial Production
CPT
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2009-07-05 | 2015-10-26
Approved Quantity | 101 | 53
Reference | Acquisition Strategy Production Phase Addendum | Milestone C ADM
Start Year | 2010 | 2015
End Year | 2012 | 2017
The Current Total LRIP Quantity is more than 10% of the total production quantity because an LRIP quantity of 53 terminals is required to satisfy IOC requirements and affords schedule flexibility to accommodate a shift of FRP to the right without impacting the IOC date.
The previous SAR reported the July 5, 2009 Acquisition Strategy Production Phase Addendum, which included FETs [formerly known as Advanced Wideband Terminals (AWTs)] to accomplish Initial Operational Test & Evaluation with LRIP assets. Due to programmatic and schedule changes no LRIP terminals were purchased using this approval.
The October 26, 2015 Milestone C ADM reflects an updated approved quantity removing the yet to be developed FET quantities and updating the CPT quantities to accommodated a shift of FRP to the right without impacting the CPT IOC date.

## Table 60
Foreign Military Sales
CPT
None
FET
None
Nuclear Costs
CPT
None
FET
None

## Table 61
Unit Cost
CPT
Unit Cost Report
Item |  | BY 2015 $M | BY 2015 $M |  | % Change
|  | Current UCR Baseline (Mar 2016 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1743 |  |  | 1759.8
Quantity | 109 |  |  | 109
Unit Cost | 15.991 |  |  | 16.145 |  | 0.96
Average Procurement Unit Cost
Cost | 584 |  |  | 618.9
Quantity | 84 |  |  | 84
Unit Cost | 6.952 |  |  | 7.368 |  | 5.98
Item |  | BY 2015 $M | BY 2015 $M |  | % Change
|  | Original UCR Baseline (Dec 2007 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1639.1 |  |  | 1759.8
Quantity | 95 |  |  | 109
Unit Cost | 17.254 |  |  | 16.145 |  | -6.43
Average Procurement Unit Cost
Cost | 939.8 |  |  | 618.9
Quantity | 84 |  |  | 84
Unit Cost | 11.188 |  |  | 7.368 |  | -34.14

## Table 62
CPT
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2015 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Dec 2007 |  |  |  |  | 17.254 |  |  | 11.188 |  |  | 16.589 |  |  | 11.37
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | Dec 2007 |  |  |  |  | 17.254 |  |  | 11.188 |  |  | 16.589 |  |  | 11.37
Current APB |  |  | Mar 2016 |  |  |  |  | 15.991 |  |  | 6.952 |  |  | 15.579 |  |  | 7.41
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Current Estimate |  |  | Dec 2015 |  |  |  |  | 16.145 |  |  | 7.368 |  |  | 15.751 |  |  | 7.82
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
14.226 0.026 -2.760 0.947 0.623 3.025 0.000 -0.336 1.525 15.751

## Table 63
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [10 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt |  | Total
8.775 -0.076 -0.770 1.064 0.000 -0.737 0.000 -0.436 -0.955 7.820
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone C |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
IOC |  |  | N/A |  |  | Jun 2013 |  |  |  | N/A |  |  | Dec 2019
Total Cost (TY $M) |  |  | N/A |  |  | 1260.2 |  |  |  | N/A |  |  | 1716.9
Total Quantity |  |  | N/A |  |  | 86 |  |  |  | N/A |  |  | 109
PAUC |  |  | N/A |  |  | 14.653 |  |  |  | N/A |  |  | 15.751

## Table 64
Unit Cost Report
Item |  | BY 2015 $M | BY 2015 $M |  | % Change
|  | Current UCR Baseline (Mar 2016 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2799.1 |  |  | 2627.1
Quantity | 158 |  |  | 158
Unit Cost | 17.716 |  |  | 16.627 |  | -6.15
Average Procurement Unit Cost
Cost | 875 |  |  | 780.8
Quantity | 132 |  |  | 132
Unit Cost | 6.629 |  |  | 5.915 |  | -10.77
Item |  | BY 2015 $M | BY 2015 $M |  | % Change
|  | Original UCR Baseline (Dec 2007 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2144.8 |  |  | 2627.1
Quantity | 127 |  |  | 158
Unit Cost | 16.888 |  |  | 16.627 |  | -1.55
Average Procurement Unit Cost
Cost | 1204 |  |  | 780.8
Quantity | 113 |  |  | 132
Unit Cost | 10.655 |  |  | 5.915 |  | -44.49

## Table 65
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2015 $M | [5 empty] | TY $M
[8 empty] | PAUC |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  |  | Dec 2007 |  |  |  |  | 16.888 |  |  |  | 10.655 |  |  | 16.112 |  |  | 10.717
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | Dec 2007 |  |  |  |  | 16.888 |  |  |  | 10.655 |  |  | 16.112 |  |  | 10.717
Current APB |  |  | Mar 2016 |  |  |  |  | 17.716 |  |  |  | 6.629 |  |  | 18.453 |  |  | 8.08
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Current Estimate |  |  | Dec 2015 |  |  |  |  | 16.627 |  |  |  | 5.915 |  |  | 18.454 |  |  | 8.08
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [14 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth |  | Spt |  | Total
14.954 0.011 -1.378 1.242 0.676 1.197 0.000 1.752 3.500 18.454

## Table 66
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [9 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt | Total
9.299 -0.082 0.206 1.487 0.000 -4.927 0.000 2.097 -1.219 8.080
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Milestone C |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
IOC |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Total Cost (TY $M) |  |  | N/A |  |  | 1907.2 |  |  | N/A |  |  | 2915.7
Total Quantity |  |  | N/A |  |  | 130 |  |  | N/A |  |  | 158
PAUC |  |  | N/A |  |  | 14.671 |  |  | N/A |  |  | 18.454

## Table 67
Cost Variance
CPT
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 556.5 | 666.9 | -- | 1223.4
Previous Changes
Economic | 3.6 | -6 | -- | -2.4
Quantity | 21 | -- | -- | 21
Schedule | -- | 86.6 | -- | 86.6
Engineering | 67.9 | -- | -- | 67.9
Estimating | 397.2 | 43.6 | -- | 440.8
Other | -- | -- | -- | --
Support | -- | 76.8 | -- | 76.8
Subtotal | 489.7 | 201 | -- | 690.7
Current Changes
Economic | 5.6 | -0.4 | -- | 5.2
Quantity | -- | 5.5 | -- | 5.5
Schedule | 13.8 | 2.8 | -- | 16.6
Engineering | -- | -- | -- | --
Estimating | -5.6 | -105.5 | -- | -111.1
Other | -- | -- | -- | --
Support | -- | -113.4 | -- | -113.4
Subtotal | 13.8 | -211 | -- | -197.2
Adjustments | -- | -- | -- | --
Total Changes | 503.5 | -10 | -- | 493.5
CE - Cost Variance | 1060 | 656.9 | -- | 1716.9
CE - Cost & Funding | 1060 | 656.9 | -- | 1716.9

## Table 68
Summary BY 2015 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 633.2 | 667.1 | -- | 1300.3
Previous Changes
Economic | -- | -- | -- | --
Quantity | 22.4 | -- | -- | 22.4
Schedule | -- | 0.1 | -- | 0.1
Engineering | 72.5 | -- | -- | 72.5
Estimating | 405.8 | 105.5 | -- | 511.3
Other | -- | -- | -- | --
Support | -- | 53.5 | -- | 53.5
Subtotal | 500.7 | 159.1 | -- | 659.8
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -3.3 | -- | -3.3
Schedule | 13.1 | 1.5 | -- | 14.6
Engineering | -- | -- | -- | --
Estimating | -6.1 | -99.5 | -- | -105.6
Other | -- | -- | -- | --
Support | -- | -106 | -- | -106
Subtotal | 7 | -207.3 | -- | -200.3
Adjustments | -- | -- | -- | --
Total Changes | 507.7 | -48.2 | -- | 459.5
CE - Cost Variance | 1140.9 | 618.9 | -- | 1759.8
CE - Cost & Funding | 1140.9 | 618.9 | -- | 1759.8
Previous Estimate: June 2015

## Table 69
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 5.6
Adjustment for current and prior escalation. (Estimating) | -6.1 | -5.6
Stretch-out of required testing into FY 2017. (Schedule) | 13.1 | 13.8
RDT&E Subtotal | 7 | 13.8
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.4
Adjustment for current and prior escalation. (Estimating) | -0.3 | -0.4
Adjustment for current and prior escalation. (Support) | 0.1 | 0.2
Quantity variance resulting from an increase of 52 ground terminals from 0 to 52 based on current fielding priorities and the realignment from Other Procurement, Air Force (OPAF) | 256.3 | 274.3
for all ground terminals after FY 2015 to Space Procurement, Air Force (SPAF). (Subtotal)
Quantity variance resulting from an increase of 52 ground terminals from 0 to 52 (SPAF). (Quantity)
(+195.3) (+209.0)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) (+40.6) (+43.5) Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (+20.4) (+21.8)
Acceleration of procurement buy profile from FY 2017 to FY 2015 and 2016 based on current fielding priorities (Aircraft Procurement, Air Force (APAF)). (Schedule)
Stretch-out of procurement buy profile based on current fielding priorities (OPAF). (Schedule)
Quantity variance resulting from a decrease of 54 ground terminals from 63 to 9 based on current fielding priorities and the realignment to SPAF for all ground terminals after FY 2015 (OPAF). (Subtotal)
Quantity variance resulting from a decrease of 54 ground terminals from 63 to 9 (OPAF). (Quantity)
0.0 -1.0
0.0 +0.5
-267.1 -274.8
(-205.9) (-211.7)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) (-40.8) (-42.1) Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (-20.4) (-21.0)
Quantity variance resulting from an increase of 2 Airborne CPTs from 21 to 23 based on current fielding priorities (APAF). (Subtotal)
Quantity variance resulting from an increase of 2 Airborne CPTs from 21 to 23 based on current fielding priorities (APAF). (Quantity)
+9.8 +10.9
(+7.3) (+8.2)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) (+1.7) (+1.9)
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (+0.8) (+0.8) Revised estimate based on current fielding plan (APAF). (Estimating) +4.2 +4.6
Revised estimate based on savings from competitive down select, including realignment from OPAF to appropriation SPAF (OPAF). (Estimating)
Revised estimate based on savings from competitive down select, including realignment from OPAF to appropriation SPAF (SPAF). (Estimating)
Decrease in Other Support as a result of reallocated logistics support between appropriations to better align with current fielding plan (APAF). (Support)
Increase in Initial Spares due to updated assumptions regarding number of terminals requiring sparing (APAF). (Support) (QR)
-95.1 -104.9
-9.1 -6.4
-23.5 -25.3
+11.9 +12.6

## Table 70
Decrease in Other as a result of reallocated logistics support between appropriations to better align with current fielding plan and realignment between Procurement appropriations (OPAF). (Support)
Decrease in Initial Spares due to realized savings impact as a result of competitive down select, updated assumptions regarding number of terminals requiring sparing, and realignment between Procurement appropriations (OPAF). (Support) (QR)
Increase in Other Support as a result of reallocated logistics support between appropriations to better align with current fielding plan and realignment between Procurement appropriations (SPAF). (Support)
Increase in Initial Spares due to a realignment between Procurement appropriations (SPAF). (Support)
-33.9 -35.6
-152.5 -164.3
+56.6 +60.5
+35.3 +38.5
Procurement Subtotal -207.3 -211.0
(QR) Quantity Related

## Table 71
Cost Variance
FET
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 874.6 | 1069.4 | -- | 1944
Previous Changes
Economic | 5.7 | -9.4 | -- | -3.7
Quantity | -- | 177.3 | -- | 177.3
Schedule | -- | 136 | -- | 136
Engineering | 106.8 | -- | -- | 106.8
Estimating | 461.3 | -591.9 | -- | -130.6
Other | -- | -- | -- | --
Support | -- | 120.8 | -- | 120.8
Subtotal | 573.8 | -167.2 | -- | 406.6
Current Changes
Economic | 6.9 | -1.4 | -- | 5.5
Quantity | 15.6 | 8 | -- | 23.6
Schedule | -- | 60.3 | -- | 60.3
Engineering | -- | -- | -- | --
Estimating | 378.2 | -58.5 | -- | 319.7
Other | -- | -- | -- | --
Support | -- | 156 | -- | 156
Subtotal | 400.7 | 164.4 | -- | 565.1
Adjustments | -- | -- | -- | --
Total Changes | 974.5 | -2.8 | -- | 971.7
CE - Cost Variance | 1849.1 | 1066.6 | -- | 2915.7
CE - Cost & Funding | 1849.1 | 1066.6 | -- | 2915.7

## Table 72
Summary BY 2015 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 994.9 | 1082.2 | -- | 2077.1
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | 170.6 | -- | 170.6
Schedule | -- | 0.3 | -- | 0.3
Engineering | 113.9 | -- | -- | 113.9
Estimating | 441.4 | -594 | -- | -152.6
Other | -- | -- | -- | --
Support | -- | 83.7 | -- | 83.7
Subtotal | 555.3 | -339.4 | -- | 215.9
Current Changes
Economic | -- | -- | -- | --
Quantity | 9.9 | -0.2 | -- | 9.7
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 286.2 | -53.7 | -- | 232.5
Other | -- | -- | -- | --
Support | -- | 91.9 | -- | 91.9
Subtotal | 296.1 | 38 | -- | 334.1
Adjustments | -- | -- | -- | --
Total Changes | 851.4 | -301.4 | -- | 550
CE - Cost Variance | 1846.3 | 780.8 | -- | 2627.1
CE - Cost & Funding | 1846.3 | 780.8 | -- | 2627.1
Previous Estimate: June 2015

## Table 73
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A +6.9
Adjustment for current and prior escalation. (Estimating) -8.0 -7.3
8 additional Engineering Development Models added to support FET follow on development. (Quantity)
Revised estimate for separate FET acquisition beyond the FYDP incorporating updated baseline per the Milestone C approved SCP. (Estimating)
+9.9 +15.6
+294.2 +385.5
RDT&E Subtotal +296.1 +400.7
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -1.4
Quantity variance resulting from a decrease of 9 ground terminals from 9 to 0 due to a realignment from SPAF to OPAF based on the current Air Force funding position (OPAF). (Subtotal)
Quantity variance resulting from a decrease of 9 ground terminals from 9 to 0 due to a realignment from SPAF to OPAF based on the current Air Force funding position (OPAF). (Quantity)
-29.5 -34.9
(-58.0) (-68.7)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) (-8.5) (-10.0) Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (+37.0) (+43.8)
Quantity variance resulting from an increase of 9 ground terminals from 0 to 9 due to a realignment from SPAF to OPAF based on the current Air Force funding position (SPAF). (Subtotal)
Quantity variance resulting from an increase of 9 ground terminals from 0 to 9 due to a realignment from SPAF to OPAF based on the current Air Force funding position (SPAF). (Quantity)
+29.4 +38.9
(+57.8) (+76.7)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) (+8.5) (+11.3) Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (-36.9) (-49.1)
Stretch-out of procurement buy profile from FY 2022-2025 to FY 2027-2030 to separate FET acquisition beyond the FYDP (APAF). (Schedule)
Revised estimate for separate FET acquisition beyond the FYDP incorporating updated baseline per the milestone C approved SCP (APAF). (Estimating)
Revised estimate for separate FET acquisition beyond the FYDP incorporating updated baseline per the milestone C approved SCP including realignment between OPAF and procurement appropriation SPAF. (SPAF) (Estimating)
Revised estimate for separate FET acquisition beyond the FYDP incorporating updated baseline per the milestone C approved SCP including realignment between OPAF and procurement appropriation SPAF (OPAF). (Estimating)
Increase in Other Support for separate FET acquisition beyond the FYDP incorporating updated baseline per the milestone C approved SCP (APAF). (Support)
Increase in Initial Spares for separate FET acquisition beyond the FYDP incorporating updated baseline per the milestone C approved SCP (APAF). (Support)
Increase in Other Support for separate FET acquisition beyond the FYDP incorporating updated baseline per the milestone C approved SCP including realignment between
0.0 +59.0
-56.8 -59.1
+12.8 +17.5
-9.8 -11.6
+33.1 +52.6
+47.1 +86.0
+6.0 +8.4

## Table 74
OPAF and procurement appropriation SPAF (SPAF). (Support)
Increase in Initial Spares for separate FET acquisition beyond the FYDP incorporating updated baseline per the milestone C approved SCP including realignment between OPAF and procurement appropriation SPAF (SPAF). (Support)
Decrease in Other Support due to realignment between OPAF and procurement appropriation SPAF (OPAF). (Support)
Decrease in Initial Spares due to realignment between OPAF and procurement appropriation SPAF (OPAF). (Support)
+15.0 +20.0
-1.7 -2.0
-7.6 -9.0
Procurement Subtotal +38.0 +164.4
(QR) Quantity Related

## Table 75
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: FAB-T CPT Development
Contractor: Raytheon
Contractor Location: 1001 Boston Post Road E
Marlborough, MA 01752-2377
Contract Number: FA8307-12-C-0013
Contract Type: Firm Fixed Price (FFP), Fixed Price Incentive(Firm Target) (FPIF)
Award Date: September 07, 2012
Definitization Date: April 10, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
215.3 215.3 N/A 215.3 215.3 13 215.3 215.3
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date 0.0 0.0
Previous Cumulative Variances 0.0 0.0
Net Change +0.0 +0.0
Cost and Schedule Variance Explanations
None
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because the cost or incentive portion does not meet the threshold requirements for earned value management reporting.
Notes
Thirteen EDMs will be produced under the contract; six will be delivered to the Government and seven will be retained by the contractor for testing purposes.
"Initial Contract Price" changed from $70.0M to $215.3M due to a correction of previously reported values

## Table 76
Contract Identification
Appropriation: Procurement
Contract Name: FAB-T CPT Production
Contractor: Raytheon
Contractor Location: 1001 Boston Post Road East
Marlborough, MA 01752-2377
Contract Number: FA8705-13-C-0005
Contract Type: Firm Fixed Price (FFP)
Award Date: September 27, 2013
Definitization Date: June 02, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
298.5 N/A 84 298.5 N/A 84 298.5 298.5
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 77
Deliveries and Expenditures
CPT
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 15 | 15 | 25 | 60%
Production | 0 | 0 | 84 | 0%
Total Program Quantity Delivered | 15 | 15 | 109 | 13.76%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
1716.9
950.8
55.38%
21
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
16
76.19%
1331.7
77.56%
The above data is current as of February 10, 2016.
Total CPT Quantity for Development includes 13 Raytheon EDMs. Planned/Actual reflect 12 deliveries under the Boeing contract and 3 to date under the Raytheon contract.
FET
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 18 | 18 | 26 | 69.23%
Production | 0 | 0 | 132 | 0%
Total Program Quantity Delivered | 18 | 18 | 158 | 11.39%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
2915.7
1206.2
41.37%
34
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
16
47.06%
1206.2
41.37%
The above data is current as of February 10, 2016.
Quantity reflects 26 total FET EDM systems, 18 Boeing FET systems delivered to date and 8 additional FET EDM required to complete the EDM development effort per the Service Cost Position approved July 7, 2015.

## Table 78
Operating and Support Cost
CPT
Cost Estimate Details
Date of Estimate: July 07, 2015
Source of Estimate: SCP
Quantity to Sustain: 84
Unit of Measure: Terminals
Service Life per Unit: 33.00 Years
Fiscal Years in Service: FY 2017 - FY 2049
Costs based on the SCP approved July 7, 2015 in support of Milestone C. FAB-T CPT O&S consists of 84 Production Systems; there are 25 Engineering Development Models (EDMs) that will not be sustained after the program transitions to O&S. Interim Contractor Support (ICS) costs are included in the Production contract and are not included in the O&S Cost.
Sustainment Strategy
The product support strategy is structured to optimize customer support and system availability, minimize ownership costs and logistics footprint, and make the best use of public and private sector capabilities. The FAB-T maintenance concept employs two levels of support: Organizational Level Maintenance (O-Level) and Depot Level (D-Level). O-Level support will be provided by organic O&M personnel upon successful installation and government acceptance of the first LRIP terminal. They will be supported with initial spares, support equipment, and training. Since the Ground Fixed CPTs will replace existing Milstar terminals in existing fixed facilities, no new facilities are required. Additionally, FAB-T does not require the creation of a new Air Force Specialty Code (AFSC) for O&M. The production contract includes four consecutive twelve-month options for D-Level ICS and continues until the transition to organic depot level support or a combination of public and private support. The FAB-T technical data rights strategy is structured to support full organic and/or competitive contractor logistics support in the future with specifications, software documents, system drawings, and other engineering data to facilitate future competition for sustainment.
Antecedent Information
For CPTs, FAB-T is a replacement terminal for the existing Milstar CPTs at ground (fixed and mobile) sites and E-4 and E
-6 airborne platforms. There are 82 Milstar terminals, each with an expected service life of 18 years. Antecedent Costs were not normalized to reflect operational/capability differences between the FAB-T and Milstar terminals.
The antecedent Milstar CPT POE is from April 2003 finalized in Air Force Space Command's budget request to Headquarters Air Force.

## Table 79
Annual O&S Costs BY2015 $K
Cost Element |  | CPT Average Annual Cost Per Terminals | [5 empty] | MILSTAR CPT (Antecedent) Average Annual Cost Per Terminal
Unit-Level Manpower |  | 29.208 | [5 empty] | 0
Unit Operations |  | 68.163 | [5 empty] | 234
Maintenance |  | 115.363 | [5 empty] | 0
Sustaining Support |  | 86.128 | [5 empty] | 180
Continuing System Improvements |  | 105.229 | [5 empty] | 0
Indirect Support |  | 25.657 | [5 empty] | 0
Other |  | 0 | [5 empty] | 0
Total |  | 429.748 | [5 empty] | 414
Item | Total O&S Cost $M
| CPT | [7 empty] | MILSTAR CPT (Antecedent)
| Current Production APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 1191.3 |  |  | 1310.4 |  |  | 1191.3 |  | 0
Then Year | 1788.3 |  |  | N/A |  |  | 1788.3 |  | N/A
Equation to Translate Annual Cost to Total Cost
Total O&S Cost = service life per system * number of systems * unitized cost
Total O&S Cost = 33 years per terminal * 84 terminals * $429.748K
O&S Cost Variance
Category |  |  | BY 2015 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Jun 2015 SAR
2168
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input -976.7 Previous O&S estimate, CAPE ICE from 2009, was based on the program before the down select. As a result of the competitive process a different technical solution was selected with lower upfront as well as lower estimated maintenance costs.
Other 0.0
Total Changes -976.7
Current Estimate 1191.3

## Table 80
Disposal Estimate Details
Date of Estimate: July 07, 2015
Source of Estimate: SCP
Disposal/Demilitarization Total Cost (BY 2015 $M): Total costs for disposal of all Terminals are 8.5
Updated from 2009 CAPE ICE to 2015 SCP used in support of Milestone C. 2009 estimate did not include disposal costs.

## Table 81
FET
Cost Estimate Details
Date of Estimate: July 07, 2015
Source of Estimate: SCP
Quantity to Sustain: 132
Unit of Measure: Terminals
Service Life per Unit: 26.00 Years
Fiscal Years in Service: FY 2024 - FY 2049
Costs based on the SCP approved July 7, 2015 in support of Milestone C. FAB-T FET O&S consists of 132 Production terminals; there are 26 EDM terminals that will not be sustained after the program transitions to O&S. ICS costs are included in the Production contract and are not included in the O&S Cost.
The Air Force is currently working to determine the FET strategy; therefore, specific fiscal year placed in service and fiscal year retired are notional pending an approved strategy.
Sustainment Strategy
The FET sustainment strategy cannot be determined until the overall strategy is defined. While the FET remains a valid requirement for the FAB-T program, it is currently unfunded and the Air Force has not yet finalized its strategy for FET development.
Antecedent Information
No Antecedent
Annual O&S Costs BY2015 $K
Cost Element | FET Average Annual Cost Per Terminals | No Antecedent (Antecedent)
Unit-Level Manpower | 16.893 | --
Unit Operations | 0 | --
Maintenance | 205.923 | --
Sustaining Support | 0 | --
Continuing System Improvements | 30.137 | --
Indirect Support | 8.355 | --
Other | -- | --
Total | 261.308 | --

## Table 82
Item | Total O&S Cost $M
| FET | [5 empty] | No Antecedent (Antecedent)
| Current Development APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 896.8 |  | 986.5 |  |  | 896.8 | N/A
Then Year | 1438.4 |  | N/A |  |  | 1438.4 | N/A
Equation to Translate Annual Cost to Total Cost
Total O&S Cost = service life per system * number of systems * unitized cost
Total O&S Cost = 26 years per terminal * 132 terminals * $261.308K
O&S Cost Variance
Category |  | BY 2015 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Jun 2015 SAR
3406.9
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input -2510.1 Previous O&S estimate, CAPE ICE from 2009, was based on the program before the down select. As a result of the competitive process a different technical solution was selected with lower upfront as well as lower estimated maintenance costs.
Other 0.0
Total Changes -2510.1
Current Estimate 896.8
Disposal Estimate Details
Date of Estimate: July 07, 2015
Source of Estimate: SCP
Disposal/Demilitarization Total Cost (BY 2015 $M): Total costs for disposal of all Terminals are 13.3
Updated from 2009 CAPE ICE to 2015 SCP used in support of Milestone C. 2009 estimate did not include disposal costs.