## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-498
Air Force Intercontinental Ballistic Missile Fuze Modernization (ICBM Fuze Mod)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 9
Schedule 10
Performance 12
Track to Budget 13
Cost and Funding 14
Low Rate Initial Production 21
Foreign Military Sales 22
Nuclear Costs 22
Unit Cost 23
Cost Variance 26
Contracts 29
Deliveries and Expenditures 30
Operating and Support Cost 31

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Air Force Intercontinental Ballistic Missile Fuze Modernization (ICBM Fuze Mod)
DoD Component
Air Force
Responsible Office
Lt Col Cory Brown
6077 Indigo Lane, Building 1530 Hill Air Force Base, UT 84056
cory.brown@us.af.mil
Phone: | 801-777-4284
Fax: | 801-586-5643
DSN Phone: | 777-4284
DSN Fax: | 586-5643
Date Assigned: | June 27, 2013
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated September 29, 2014
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated September 29, 2014

## Table 6
Mission and Description
The mission of the Air Force Intercontinental Ballistic Missile Fuze Modernization program is to develop and produce a form, fit, functional replacement Mk21 Arming and Fuzing Assembly for the legacy Mk21 fuze, which is utilized with the W87 warhead.
The Air Force ICBM Minuteman III (MMIII) fuzes require recapitalization due to the legacy fuze being three times past the original design life. In MMIII sustainment, there is an ongoing refurbishment program; however, this activity will not meet fuze quantity requirements under the current known force structure. The Mk21 replacement fuze is being designed for a 30-year design life which will meet current and future Combatant Command ICBM needs for MMIII and Ground Based Strategic Deterrent. The Air Force is leveraging the Navy's Mk5 Alteration 370 program to maximize commonality and achieve cost savings/avoidance over the lifecycle.

## Table 7
Executive Summary
The ICBM Fuze Modernization Program is using Department of Defense Instruction (DoDI) 5030.55, Procedures for Joint DoD-Department of Energy (DOE) Nuclear Weapons Life-Cycle Activities (Phase 6.X Process), as the governing acquisition directive for program milestones and activities, with Sandia National Laboratories (SNL) and National Security Campus (NSC) to develop and produce replacement ICBM Fuzes. The program, not categorized as a MDAP when it entered into Phase 6.3, Development Engineering, in August 2013, is now executing a tailored acquisition in compliance with MDAP statutory requirements applicable to entering into Milestone B, the Engineering and Manufacturing Development Phase.
The Air Force and Navy jointly executed an Integrated Baseline Review (IBR) from February 26, 2015 - March 6, 2015, and upon final concurrence of an executable baseline, the design agent, SNL began to officially report EVM data. The program plans for a FY 2022 First Production Unit and delivery of 693 War Reserve fuzes by FY 2030. The fielding plan is contingent upon Air Force Global Strike Command maintenance and logistics planning.
ADM dated September 22, 2015, directed the Air Force to continue to plan and execute the program based on Nuclear Weapons Council, Phase 6.X guidelines while also ensuring all MDAP statutory requirements are met. Since this decision was made after the Phase 6.X equivalent of Milestone B, the program is now working to meet or determine equivalency for all Milestone B relevant statutory requirements.
There are six MDAP statutory requirements not yet complete: Section 2366b Certification, ICE, Replaced System Sustainment Plan (RSSP), Programmatic Environmental Safety & Occupational Health Evaluation (PESHE), LRIP quantities, and Technology Readiness Assessment (TRA). The current 2366b requests and recommends a waiver for the TRA due to the differences in processes used by the National Nuclear Security Administration (NNSA) and the DoD.
1. Section 2366b Certification – entered Secretary of the Air Force/Acquisition (SAF/AQ) coordination on December 28, 2015, estimated approval third quarter FY 2016.
2. ICE – currently under development by Cost Assessment and Program Evaluation (CAPE).
3. RSSP – currently completed as stand-alone document; being incorporated in next version of Life Cycle Sustainment Plan (LCSP); estimated completion third quarter FY 2016.
4. PESHE and National Environmental Policy Act (NEPA)/Executive Order 12114 Compliance Schedule – the PESHE is in development and design considerations are documented in the draft Systems Engineering Plan (SEP). The program submitted the draft SEP for Deputy Assistant Secretary of Defense for Systems Engineering (DASD(SE)) and Secretary of the Air Force for Acquisition of Science and Technology (SAF/AQR) coordination and is adjudicating comments.
5. LRIP Quantities – LRIP Quantities from DoDI 5000.02 do not easily translate to the Phase 6.X process, so the program is working with SAF/AQ to identify how to meet this statutory requirement. The program recommends that Phase 6.5, “First Production Unit,” be equivalent to LRIP and Milestone C. There is no IOC date due to the number of logistics actions out of program control; therefore, the APB established a Required Assets Available (RAA) date. For RAA, the program will deliver 10 fuzes and associated support equipment, and the program recommends this should equal LRIP quantities.
6. TRA – there is a significant distinction between the DoD TRA/Technology Readiness Level (TRL) process and how the NNSA complex and SNL establishes TRLs and conducts TRAs. Currently, DASD(SE) and SAF/AQR maintain that an independent TRA be completed on SNL. The program is partnering with DASD(SE) and SAF/AQR to help them understand the SNL process and determine the best way to tailor the TRA statutory requirement.
The next major milestone is Baseline Design Review (BDR) scheduled for May 2017. The Air Force supported common component BDRs with the Navy in CY 2015 and will begin executing AF-unique component BDRs in mid-FY 2016.

## Table 8
There are no significant software-related issues with this program at this time.

## Table 9
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 10
Schedule
(Ch-1)
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
DOE Phase 6.3 Milestone Decision (Program Initiation) | Aug 2013 | Aug 2013 | Aug 2013 | Aug 2013
Component Conceptual Design Review | Oct 2014 | Oct 2014 | Apr 2015 | Oct 2014
Baseline Design Review | Mar 2017 | Mar 2017 | Sep 2017 | May 2017
Prototype Design Review | Feb 2018 | Feb 2018 | Aug 2018 | Feb 2018
DOE Phase 6.4 Milestone Decision (Production Engineering) | Jan 2019 | Jan 2019 | Jan 2020 | Jan 2019
Final Design Review | Dec 2019 | Dec 2019 | Jun 2020 | Dec 2019
Production Readiness Review | Feb 2022 | Feb 2022 | Aug 2022 | Feb 2022
DOE Phase 6.5 Milestone Decision (First Production) | Sep 2022 | Sep 2022 | Sep 2023 | Sep 2022
DOE Phase 6.6 Milestone Decision (Full Scale Production) | Apr 2023 | Apr 2023 | Apr 2024 | Apr 2023
RAA | Jul 2023 | Jul 2023 | Jul 2024 | Jul 2023

## Table 11
Change Explanations
(Ch-1) The projected date for BDR slipped from March 2017 to May 2017, which still meets the APB threshold. The delay was primarily caused by technical issues with the MICM as well as a mechanical envelope height issue. Sandia is aggressively working these issues, which are on the critical path to BDR. The PM is assessing the impact of this slip, however it appears there is sufficient margin in the schedule to meet future APB threshold dates. These issues are watch items for EVM and PMR reporting.
Notes
(1) The USD(AT&L), as the Chairman of the Nuclear Weapons Council, authorized entry into Phase 6.3 Development Engineering in a memo dated August 18, 2013, titled "Air Force Intercontinental Ballistic Missile Fuze Program Phase 6.3 Development Engineering Authorization." For the purpose of acquisition oversight and the APB, the Phase 6.3 milestone is roughly equivalent to Milestone B. During Phase 6.3, the program is executing a LOPB strategy as authorized in the FY 2015 National Defense Authorization Act to maintain commonality with the Navy's Mk5 Alteration 370 program. The production funding supporting LOPB is only being utilized to procure raw materials and sub-parts to reduce nuclear qualification costs during Phase 6.3.
(2) Phase 6.4, "Production Engineering," does not have an equivalent milestone under DoDI 5000.02. The purpose of Phase
6.4 is to adapt the development design into a design suitable for quantity production. At this point, the provisioning of spares also occurs in conjunction with the DoD. At Phase 6.4, the program will seek authorization from the MDA to execute production funding to build components and fuzes supporting test. There is no equivalent LRIP decision point in the program; however, the PEO will review program status before concurring with Phase 6.4 entry. In addition, the program will brief the Nuclear Weapons Council on plans to enter Phase 6.4. Between Phase 6.4 and Phase 6.5 "First Production" the program will execute production funding to support build-up, production process prove-in, and nuclear certification of the ICBM Fuze.
(3) Milestones with threshold dates of 12 months beyond the objective dates reflect the nominal time to recover from an ICBM flight test failure.
(4) RAA is being used as a surrogate for IOC. RAA is defined as ten Mk21 fuzes available for deployment with the technical data, test equipment, and technical training materials required to support wing operations.
Acronyms and Abbreviations
BDR - Baseline Design Review DOE - Department of Energy
ICBM - Intercontinental Ballistic Missile LOPB - Life of Program Buy
MICM - Missile Interface and Controller Module PMR - Program Management Review
RAA - Required Assets Available

## Table 12
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
System Qualification Attribute 4: Fuze Replacement Design Life
30-year service life upon DoD custody. | 30-year service life upon DoD custody. | 20-year service life upon DoD custody. | TBD | 30-year service life upon DoD custody.
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
AFGSC ICBM Fuze Program Requirements Traceability Memorandum dated December 12, 2013
Change Explanations
None
Notes
The ICBM Fuze Modernization program is a form, fit, and functional equivalent replacement for the existing legacy Mk21 AFA with no planned capability increase. AFGSC published the ICBM Fuze Modernization Program Requirements Traceability Memorandum documenting the requirements that must be met by the replacement fuze.
Acronyms and Abbreviations
AFA - Arming and Fuzing Assembly AFGSC - Air Force Global Strike Command

## Table 13
Track to Budget
RDT&E
Appn |  | BA | PE
Air Force | 3600 05 |  | 0604222F
| Project |  | Name
| 654236 |  | Engineering Analysis | (Sunk)
Air Force | 3600 05 |  | 0604851F
| Project |  | Name
| 657006 |  | ICBM EMD: Fuze Support | (Sunk)
Air Force | 3600 05 |  | 0604933F
| Project |  | Name
| 655082 |  | ICBM Fuze Modernization
Notes
In FY 2011, program efforts began in PE 0604222F and are represented in the Joint Fuze major thrust of project 654236. In FY 2012, program efforts were assigned the unique project number 657006 and were transferred to PE 0604851F. In FY 2013, program efforts were assigned the unique project number 655082 and were transferred to the unique PE 0604933F. Funding remains in PE 0604933F throughout the remainder of the life of the RDT&E efforts.
Procurement
Appn |  | BA | PE
Air Force 3020 03 0101213F
Line Item Name
M30FLH MM III Modifications (Shared) Air Force 3020 03 0604933F
Line Item Name
M30FLH ICBM Fuze Mod Air Force 3020 03 0101213F
Line Item Name
M30MLG MM III Modifications (Shared)
Notes: The ICBM Fuze Mod has an individual modification number of 5915 / ICBM Fuze Modernization (Service Life Extension).
Notes
FY 2015 and FY 2016, program efforts are in PE 0101213F and are represented in the MM III Modifications line item 5915 ICBM Fuze Modernization. The FY 2017 production documents reflect PE 0604933 but the funds remain in PE 0101213F in this budget cycle.

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2014 $M |  |  |  | BY 2014 $M |  | TY $M
| SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Development Estimate |  | Current APB Development Objective |  | Current Estimate
RDT&E | 1151.3 |  | 1151.3 | 1266.4 |  | 1166.8 |  | 1246.1 |  | 1246.1 |  | 1246.1
Procurement | 663.5 |  | 663.5 | 729.9 |  | 665.5 |  | 829.6 |  | 829.6 |  | 823.8
Flyaway | -- |  | -- | -- |  | 665.5 |  | -- |  | -- |  | 823.8
Recurring | -- |  | -- | -- |  | 665.5 |  | -- |  | -- |  | 823.8
Non Recurring | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Other Support | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Initial Spares | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
MILCON | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 1814.8 |  | 1814.8 | N/A |  | 1832.3 |  | 2075.7 |  | 2075.7 |  | 2069.9
Current APB Cost Estimate Reference
Service Cost Position dated June 12, 2014
Confidence Level
Confidence Level of cost estimate for current APB: 55%
The life-cycle cost estimate reflects the expected value, or mean, of the cost estimate distribution. It takes into consideration relevant risks, including ordinary levels of external and unforeseen events, aiming to provide sufficient resources to execute the program under normal conditions encountering average levels of technical, schedule, and programmatic risk and external influence.

## Table 15
Total Quantity
Quantity | SAR Baseline Development Estimate | Current APB Development | Current Estimate
RDT&E | 88 | 88 | 88
Procurement | 693 | 693 | 693
Total | 781 | 781 | 781
Quantity Notes
The funded quantity of 781 includes all of the units necessary for development, testing, operational fielding, aging/surveillance, and replenishment spares.

## Table 16
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 255.1 | 142.6 |  | 189.8 |  | 178.5 |  | 168 |  | 157.7 |  | 123.6 |  | 30.8 |  | 1246.1
Procurement | 4.7 | 13.7 |  | 17.1 |  | 6.3 |  | 9.8 |  | 12.1 |  | 34.1 |  | 726 |  | 823.8
MILCON | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 259.8 | 156.3 |  | 206.9 |  | 184.8 |  | 177.8 |  | 169.8 |  | 157.7 |  | 756.8 |  | 2069.9
PB 2016 Total | 255.9 | 156.3 |  | 208.4 |  | 186.6 |  | 179.6 |  | 171.5 |  | 162.8 |  | 754.9 |  | 2076
Delta | 3.9 | 0 |  | -1.5 |  | -1.8 |  | -1.8 |  | -1.7 |  | -5.1 |  | 1.9 |  | -6.1
Funding Notes
The ICBM Fuze Mod program is being executed via a "Work for Others" agreement with the National Nuclear Security Administration and is 100% funded by the Air Force. There are no Department of Energy funds being used to support the design and production of the ICBM Fuze Mod program.
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 88 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 88
Production | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 6 |  | 20 |  | 667 |  | 693
PB 2017 Total | 88 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 6 |  | 20 |  | 667 |  | 781
PB 2016 Total | 88 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 6 |  | 20 |  | 667 |  | 781
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Table 17
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.7
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.4
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 82.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57.9
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 142.6
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 189.8
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 178.5
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 168
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 157.7
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 123.6
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.8
Subtotal |  | 88 | -- |  | -- |  | -- |  | -- |  | -- |  | 1246.1

## Table 18
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2014 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.1
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40.5
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 81.6
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 56.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 137.7
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 179.8
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 166
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 153.1
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 141
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 108.3
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.4
Subtotal |  | 88 | -- |  | -- |  | -- |  | -- |  | -- |  | 1166.8

## Table 19
Annual Funding 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2015 |  | -- | -- |  | 4.7 |  | -- |  | 4.7 |  | -- |  | 4.7
2016 |  | -- | -- |  | 13.7 |  | -- |  | 13.7 |  | -- |  | 13.7
2017 |  | -- | -- |  | 17.1 |  | -- |  | 17.1 |  | -- |  | 17.1
2018 |  | -- | -- |  | 6.3 |  | -- |  | 6.3 |  | -- |  | 6.3
2019 |  | -- | -- |  | 9.8 |  | -- |  | 9.8 |  | -- |  | 9.8
2020 |  | 6 | 9.2 |  | 2.9 |  | -- |  | 12.1 |  | -- |  | 12.1
2021 |  | 20 | 27.5 |  | 6.6 |  | -- |  | 34.1 |  | -- |  | 34.1
2022 |  | 80 | 80.1 |  | 8.5 |  | -- |  | 88.6 |  | -- |  | 88.6
2023 |  | 106 | 92.3 |  | 20.3 |  | -- |  | 112.6 |  | -- |  | 112.6
2024 |  | 118 | 105.4 |  | 24.2 |  | -- |  | 129.6 |  | -- |  | 129.6
2025 |  | 121 | 113.2 |  | 26.5 |  | -- |  | 139.7 |  | -- |  | 139.7
2026 |  | 121 | 98.8 |  | 30.4 |  | -- |  | 129.2 |  | -- |  | 129.2
2027 |  | 121 | 75.6 |  | 31.9 |  | -- |  | 107.5 |  | -- |  | 107.5
2028 |  | -- | -- |  | 7.7 |  | -- |  | 7.7 |  | -- |  | 7.7
2029 |  | -- | -- |  | 5.2 |  | -- |  | 5.2 |  | -- |  | 5.2
2030 |  | -- | -- |  | 5.9 |  | -- |  | 5.9 |  | -- |  | 5.9
Subtotal |  | 693 | 602.1 |  | 221.7 |  | -- |  | 823.8 |  | -- |  | 823.8

## Table 20
Annual Funding 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | BY 2014 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2015 |  | -- | -- |  | 4.5 |  | -- |  | 4.5 |  | -- |  | 4.5
2016 |  | -- | -- |  | 12.9 |  | -- |  | 12.9 |  | -- |  | 12.9
2017 |  | -- | -- |  | 15.9 |  | -- |  | 15.9 |  | -- |  | 15.9
2018 |  | -- | -- |  | 5.7 |  | -- |  | 5.7 |  | -- |  | 5.7
2019 |  | -- | -- |  | 8.7 |  | -- |  | 8.7 |  | -- |  | 8.7
2020 |  | 6 | 8 |  | 2.6 |  | -- |  | 10.6 |  | -- |  | 10.6
2021 |  | 20 | 23.6 |  | 5.6 |  | -- |  | 29.2 |  | -- |  | 29.2
2022 |  | 80 | 67.3 |  | 7.1 |  | -- |  | 74.4 |  | -- |  | 74.4
2023 |  | 106 | 76 |  | 16.7 |  | -- |  | 92.7 |  | -- |  | 92.7
2024 |  | 118 | 85.1 |  | 19.5 |  | -- |  | 104.6 |  | -- |  | 104.6
2025 |  | 121 | 89.6 |  | 21 |  | -- |  | 110.6 |  | -- |  | 110.6
2026 |  | 121 | 76.7 |  | 23.6 |  | -- |  | 100.3 |  | -- |  | 100.3
2027 |  | 121 | 57.5 |  | 24.2 |  | -- |  | 81.7 |  | -- |  | 81.7
2028 |  | -- | -- |  | 5.7 |  | -- |  | 5.7 |  | -- |  | 5.7
2029 |  | -- | -- |  | 3.8 |  | -- |  | 3.8 |  | -- |  | 3.8
2030 |  | -- | -- |  | 4.2 |  | -- |  | 4.2 |  | -- |  | 4.2
Subtotal |  | 693 | 483.8 |  | 181.7 |  | -- |  | 665.5 |  | -- |  | 665.5

## Table 21
Low Rate Initial Production
There is no LRIP for this program.

## Table 22
Foreign Military Sales
None
Nuclear Costs
None

## Table 23
Unit Cost
Unit Cost Report
Item |  | BY 2014 $M | BY 2014 $M |  | % Change
|  | Current UCR Baseline (Sep 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1814.8 |  |  | 1832.3
Quantity | 781 |  |  | 781
Unit Cost | 2.324 |  |  | 2.346 |  | 0.95
Average Procurement Unit Cost
Cost | 663.5 |  |  | 665.5
Quantity | 693 |  |  | 693
Unit Cost | 0.957 |  |  | 0.96 |  | 0.31
Item |  | BY 2014 $M | BY 2014 $M |  | % Change
|  | Original UCR Baseline (Sep 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1814.8 |  |  | 1832.3
Quantity | 781 |  |  | 781
Unit Cost | 2.324 |  |  | 2.346 |  | 0.95
Average Procurement Unit Cost
Cost | 663.5 |  |  | 665.5
Quantity | 693 |  |  | 693
Unit Cost | 0.957 |  |  | 0.96 |  | 0.31
.

## Table 24
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2014 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Sep 2014 |  |  |  |  | 2.324 |  |  | 0.957 |  |  | 2.658 |  |  | 1.197
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Current APB |  |  | Sep 2014 |  |  |  |  | 2.324 |  |  | 0.957 |  |  | 2.658 |  |  | 1.197
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 2.339 |  |  | 0.962 |  |  | 2.658 |  |  | 1.198
Current Estimate |  |  | Dec 2015 |  |  |  |  | 2.346 |  |  | 0.96 |  |  | 2.65 |  |  | 1.189
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
2.658 -0.035 0.000 0.000 0.000 0.027 0.000 0.000 -0.008 2.650
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
1.197 -0.013 0.000 0.000 0.000 0.005 0.000 0.000 -0.008 1.189

## Table 25
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Aug 2013 | N/A | Aug 2013
Milestone C | N/A | Feb 2022 | N/A | Feb 2022
IOC | N/A | Jul 2023 | N/A | Jul 2023
Total Cost (TY $M) | N/A | 2075.7 | N/A | 2069.9
Total Quantity | N/A | 781 | N/A | 781
PAUC | N/A | 2.658 | N/A | 2.65

## Table 26
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 1246.1 | 829.6 | -- | 2075.7
Previous Changes
Economic | -10.3 | -4.4 | -- | -14.7
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 10.3 | 4.7 | -- | 15
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -- | 0.3 | -- | 0.3
Current Changes
Economic | -7.3 | -4.6 | -- | -11.9
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 7.3 | -1.5 | -- | 5.8
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -- | -6.1 | -- | -6.1
Total Changes | -- | -5.8 | -- | -5.8
CE - Cost Variance | 1246.1 | 823.8 | -- | 2069.9
CE - Cost & Funding | 1246.1 | 823.8 | -- | 2069.9

## Table 27
Summary BY 2014 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
1151.3 663.5 -- 1814.8
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 8.6 |  | 3.3 |  | -- |  | 11.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 8.6 |  | 3.3 |  | -- |  | 11.9
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 6.9 |  | -1.3 |  | -- |  | 5.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 6.9 |  | -1.3 |  | -- |  | 5.6
Total Changes |  | 15.5 |  | 2 |  | -- |  | 17.5
CE - Cost Variance |  | 1166.8 |  | 665.5 |  | -- |  | 1832.3
CE - Cost & Funding |  | 1166.8 |  | 665.5 |  | -- |  | 1832.3
Previous Estimate: December 2014

## Table 28
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -7.3
Adjustment due to return of OMNIBUS. (Estimating) | 5.8 | 5.8
Adjustment due to Small Business Innovation Research. (Estimating) | -1.9 | -1.9
Adjustment for current and prior escalation. (Estimating) | 1.5 | 1.5
Adjustment due to escalation changes. (Estimating) | 1.5 | 1.9
RDT&E Subtotal | 6.9 | 0
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -4.6
Adjustment due to escalation indices (Estimating) | -1.3 | -1.5
Procurement Subtotal | -1.3 | -6.1

## Table 29
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: ICBM Fuze Weapons System Integration
Contractor: Lockheed Martin Corporation
Contractor Location: 230 Mall Blvd
King of Prussia, PA 19406-2902
Contract Number: FA8214-14-D-0002/3
Contract Type: Cost Plus Fixed Fee (CPFF), Cost (CR)
Award Date: January 29, 2015
Definitization Date: January 29, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
96.2 N/A 0 96.2 N/A 0 96.2 96.2
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/27/2015) +0.7 -0.2
Previous Cumulative Variances 0.0 0.0
Net Change +0.7 -0.2
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to efficiencies and better than expected performance on several activities.
The unfavorable cumulative schedule variance is due to some analysis work being more complex than planned and there was a change in government requirements (de-scope) on contract. The contractor was originally tasked to develop a Software Transition Plan that is now not required. This task is being removed from the contract in an upcoming modification.

## Table 30
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 3 | 3 | 88 | 3.41%
Production | 0 | 0 | 693 | 0%
Total Program Quantity Delivered | 3 | 3 | 781 | 0.38%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
2069.9
240.7
11.63%
20
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
6
30%
416.1
20.1%
The above data is current as of February 09, 2016.
The funded quantity of 781 includes all of the units necessary for development, testing, operational fielding, aging/surveillance, and replenishment spares.

## Table 31
Operating and Support Cost
Cost Estimate Details
Date of Estimate: June 12, 2014
Source of Estimate: SCP
Quantity to Sustain: 450
Unit of Measure: Missile
Service Life per Unit: 30.00 Years
Fiscal Years in Service: FY 2027 - FY 2060
ICBM Fuze Mod O&S costs are the additive costs for sustaining the Mk21 replacement fuze being delivered by this program. O&S costs for the Mk21 replacement fuze, and current Mk12A and Mk21 fuzes, will be collected as part of the overall Minuteman III weapon system. The funded quantity of 781 includes all of the units necessary for development, testing, operational fielding, aging/surveillance, and replenishment spares. The sustainment strategy is built around sustaining the 450 operational missiles, not the total quantity of fuzes.
Sustainment Strategy
Throughout the O&S phase, National Security Campus (formerly Kansas City Plant) will provide aging/surveillance and depot level testing and support for the new fuze; Sandia National Laboratories will provide systems engineering, sustainment engineering support, and surveillance engineering support from both California and New Mexico.
It is anticipated that there will be annual shipments of Mk21 replacement fuzes from the three wings to the new National Security Campus depot each year for aging/surveillance, reliability testing and depot repair. As items are received at the depot from the wings, replenishment spares will be shipped to the wings from the depot on an annual basis.
The National Nuclear Security Administration will provide management and oversight support to the Intercontinental
Ballistic Missile Systems Directorate for the Mk21 replacement fuzes throughout their 30-year life cycle.
Antecedent Information
No Antecedent
Annual O&S Costs BY2014 $K
Cost Element | ICBM Fuze Mod Average Annual Cost Per Missile | None (Antecedent) None
Unit-Level Manpower | 0 | --
Unit Operations | 0 | --
Maintenance | 6.873 | --
Sustaining Support | 11.994 | --
Continuing System Improvements | 0 | --
Indirect Support | 0 | --
Other | 0 | --
Total | 18.867 | --
Because the fuze is a relatively small component within the framework of the much larger Minuteman III weapon system it is not expected that there will be any change to unit level manpower, continuing system improvements, or indirect support at the wings or depot.

## Table 32
Item | Total O&S Cost $M
| ICBM Fuze Mod | [5 empty] | None (Antecedent)
| Current Development APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 259 |  | 285 |  |  | 254.7 | N/A
Then Year | 466 |  | N/A |  |  | 456 | N/A
Disposal Cost is included in the Operating and Support Cost of the current APB objective and threshold for this program.
Equation to Translate Annual Cost to Total Cost
Average Annual Missile O&S Cost = Total O&S cost / number of missiles / service life of fuze
$18.9K = $254.7M / 450 / 30
O&S Cost Variance
Category |  | BY 2014 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
254.7
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 254.7
Disposal Estimate Details
Date of Estimate: June 12, 2014
Source of Estimate: SCP
Disposal/Demilitarization Total Cost (BY 2014 $M): Total costs for disposal of all Missile are 4.3
Demilitarization and disposal will be a coordinated effort between the Air Force and the National Nuclear Security Administration Complex. Older fuzes that are no longer fielded will remain in storage in the Nuclear Materials storage facility located at Hill Air Force Base (AFB), Utah, until demilitarization begins in FY 2056.
Beginning in FY 2056, the Air Force will begin receiving shipments of aged-out fuzes for demilitarization and disposal. It is expected that quarterly shipments from each wing will be sent to the Nuclear Materials storage area at Hill AFB in preparation for demilitarization and disposal.
Demilitarization engineering support will be provided by a support contractor to coordinate removal of precious and environmentally sensitive material from the Mk21 replacement fuzes prior to disposal.

## Table 33
An environmentally protective container will be used to house the demilitarized fuzes for the disposal process. Each container is estimated to hold approximately 66 fuzes.
Fuzes ready for disposal will be transferred from the National Security Campus to the approved disposal site. The projected disposal process will consist of deep earth burial on the Utah Test and Training Range in demilitarized containers.