## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-503
Joint Direct Attack Munition (JDAM)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 12
Track to Budget 14
Cost and Funding 15
Low Rate Initial Production 26
Foreign Military Sales 27
Nuclear Costs 29
Unit Cost 30
Cost Variance 33
Contracts 36
Deliveries and Expenditures 38
Operating and Support Cost 39

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Joint Direct Attack Munition (JDAM)
DoD Component
Air Force
Joint Participants
Navy
Responsible Office
Col W. Scott Bell
6033 Elm Lane, Bldg 1247 Hill AFB, UT 84056
william.bell@us.af.mil
Phone: 801-777-5434
Fax: 801-777-2099
DSN Phone: 777-5434
DSN Fax:
Date Assigned: June 15, 2015
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated March 23, 2001
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated June 30, 2015

## Table 6
Mission and Description
The Joint Direct Attack Munition (JDAM) program is a joint Air Force/Navy program with the Air Force as the lead acquisition service. Designated Acquisition Category IC, this program upgrades the existing inventory of general purpose bombs (MK- 84, BLU-109, MK-82 and MK-83) by integrating the bombs with a field installed guidance kit using a Global Positioning System Aided Inertial Navigation System. JDAM provides an accurate, adverse weather capability. JDAM is integrated with the B-52H, B-2A, B-1B, F-16C/D, F/A-18A+/C/D/E/F, F-15E, A-10C, AV-8B and F-22A aircraft. Follow-on integration with the MQ-9 and F-35 Joint Strike Fighter are in progress.

## Table 7
Executive Summary
The Government reached a settlement with Boeing on a final contract price on November 6, 2015 for the Lot 18-22 Indefinite Delivery/Indefinite Quantity contract, and is now working to definitize the contract and increase the current production capacity ceiling from 15,000 tail kits per lot to 36,500 tail kits per lot.
An updated APB was approved on June 30, 2015, and is reflected in this document. The new APB cleared a breach for exceeding total Procurement dollars due to continued JDAM demand over the life of the program.
There are no significant software-related issues with the program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule

## Table 10
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone 0 | Jun 1992 | Jun 1992 | Jun 1992 | Jun 1992
Milestone I | Oct 1993 | Oct 1993 | Oct 1993 | Oct 1993
Dem/Val Contract Award | Apr 1994 | Apr 1994 | Apr 1994 | Apr 1994
Critical Design Review Complete | Aug 1995 | Aug 1995 | Aug 1995 | Aug 1995
Milestone II | Sep 1995 | Sep 1995 | Sep 1995 | Sep 1995
Exercise EMD Contract Option | Oct 1995 | Oct 1995 | Oct 1995 | Oct 1995
Operational Assessment
Start | Oct 1995 | Oct 1995 | Oct 1995 | Oct 1995
Complete | Mar 1997 | Jan 1997 | Jan 1997 | Jan 1997
DT&E/TECHEVAL
Start (Flight Tests) | Oct 1995 | Dec 1995 | Dec 1995 | Dec 1995
Complete (2000 lb Kit) | Dec 1997 | Jun 1998 | Jun 1998 | Jun 1998
Complete (1000 lb Kit) - Weapon Only | Feb 1998 | Aug 1998 | Aug 1998 | Aug 1998
Exercise Lot 1 Option | Apr 1997 | Apr 1997 | Apr 1997 | Apr 1997
Lot 1 Production First Delivery | Apr 1998 | May 1998 | May 1998 | May 1998
Exercise Lot 2 Option (LRIP) | Apr 1998 | Jun 1998 | Jun 1998 | Jun 1998
Required Assets Availability (AF) | Mar 1999 | Mar 1999 | Mar 1999 | Mar 1999
Award Lot 3 (LRIP) | Jun 1999 | Jun 1999 | Jun 1999 | Jun 1999
IOT&E/OPEVAL (Dedicated 2000 lb Kit) Complete | Sep 2000 | Sep 2000 | Sep 2000 | Sep 2000
IOC (FA-18) | Nov 2000 | Feb 2001 | Feb 2001 | Feb 2001
Milestone III (2000 lb) | Nov 2000 | Mar 2001 | Mar 2001 | Mar 2001
OT&E/OPEVAL Complete (1000 lb Kit/FA-18C/D) | Jul 2001 | N/A | N/A | N/A
Milestone III (1000 lb on FA-18C/D) | Feb 2002 | N/A | N/A | N/A
Milestone I JDAM PIP | Sep 2002 | N/A | N/A | N/A
OT&E/OPEVAL Complete (1000 lb Kit/FA-18C/D) | N/A | Jul 2003 | Jul 2003 | Jul 2003
Initial Production (500 lb kit) | N/A | Jul 2003 | Jul 2003 | Jul 2003
Required Assets Availability (RAA) (500 lb on B-2) | N/A | Nov 2004 | Nov 2004 | Nov 2004
IOC (500 lb kit on FA-18C/D) | N/A | Feb 2005 | Feb 2005 | Feb 2005
Selective Availability Anti-Spoofing Module (SAASM)/GPS Anti-Jam Production Award | N/A | Mar 2005 | Mar 2005 | Mar 2005
Change Explanations
None

## Table 11
Acronyms and Abbreviations
AF - Air Force
Dem/Val - Demonstration/Validation DT&E - Development Test and Evaluation GPS - Global Positioning System
IOT&E - Initial Operational Test and Evaluation lb - Pound
OPEVAL - Operational Evaluation
OT&E - Operational Test and Evaluation PIP - Product Improvement Program TECHEVAL - Technical Evaluation

## Table 12
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Weather Capability
Adverse | Adverse | (T=O) Adverse | Adverse | Adverse
Accuracy (CEP) (Meters)
GPS Available, Impact Angles > 60 Deg
13 Horizontal Targets | 5 Horizontal targets | 13 | 4.3 | 5 Horizontal Targets
Inflight Re-targeting Capability (captive carry)
Yes | Yes | (T=O) Yes | Yes | Yes
Carrier Operability
Yes | Yes | (T=O) Yes | Yes | Yes
Warhead Compatibility
MK-82/BLU-111, MK- 83, Improved 1000-lbs, BLU-113/116/117 | MK-82/BLU-111, MK- 83, Improved 1000-lbs, BLU-113/116/117 | BLU-109, MK-84, MK-83 (F-22) | BLU-109, MK-84, MK-83 (F-22), MK- 82 | BLU-109, MK-84, MK-83 (F-22), MK-82
Aircraft Compatibility
Bomber
B-1B, B-2 | B-1B, B-2 | B-52H | Yes | B-52H, B-1B, B-2
Fighter Attack
F-16C/D, F/A-18E/F, F- 117A, F-15E, F- 14A/B/D, P-3, S-3, JSF, A-10 | F-16C/D, F/A-18E/F, F- 117A, F-15E, F- 14A/B/D, P-3, S-3, JSF, A-10 | F/A-18C/D, F-22 (MK-83), AV-8B & F/A-18C/D (MK- 83) | Yes | F-16C/D, F-117, F/A- 18A+/C/D/E/F, F-15E, AV-8B, A-10, F-22A
Mission Reliability
0.9 | 0.9 | (T=O) .90 | 0.983 | 0.9
JDAM PIP Accuracy (CEP) (Meters)
3 | N/A | N/A | N/A | N/A
JDAM PIP Weather Capability
Adverse | N/A | N/A | N/A | N/A
JDAM PIP Warhead Compatibility
MK-82, MK-83 | N/A | N/A | N/A | N/A
Interoperability
N/A | Satisfy 100% of critical IERs | (T=O) Satisfy 100% of critical IERs | Satisfied | Satisfied

## Table 13
Requirements Reference
ORD dated March 10, 2001
Change Explanations
None
Acronyms and Abbreviations
CEP - Circular Error Probable Deg - Degree
GPS - Global Positioning System
IER - Information Exchange Requirement JSF - Joint Strike Fighter
lbs - Pounds
PIP - Product Improvement Program

## Table 14
Track to Budget
RDT&E
Appn |  |  | BA | PE
Navy | 1319 05 |  |  | 0604618N
| Project |  |  |  | Name
| 2137 |  |  | JDAM
Air Force | 3600 05 |  |  | 0604618F
| Project |  |  |  | Name
| 3890 |  |  | JDAM
Air Force | 3600 04 |  |  | 0604618F
| Project |  |  |  | Name
| 641200 |  |  | JDAM Development & Prototyping
Air Force | 3600 |  | 7 | 0604618F
| Project |  |  | Name
(Sunk)
(Sunk)
(Sunk)
653891 M-Code Integration
674138 JDAM Development
Procurement
Appn |  |  | BA | PE
Navy 1508 01 0204162N
| Line Item |  |  | Name
| 145 |  |  | General Purpose Bombs
Navy | 1508 | 1 |  | 0206138M
| Line Item |  |  |  |  | Name
| 148 |  |  | JDAM
Navy | 1508 01 |  |  | 0204162N
| Line Item |  |  |  |  | Name
| 148 |  |  | JDAM
Air Force | 3011 01 |  |  | 0207583F
| Line Item |  |  |  |  | Name
| 353620 |  |  | JDAM
(Shared)
(Sunk)
(Sunk)

## Table 15
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 1995 $M | [5 empty] | BY 1995 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E | 490.3 |  |  | 572.8 | 630.1 |  |  | 610.3 |  | 517.3 |  |  | 602.3 |  | 658.3
Procurement | 1810 |  |  | 6091.9 | 6701.1 |  |  | 6347.4 |  | 2089.4 |  |  | 7861.2 |  | 8440
Flyaway | -- |  |  | -- | -- |  |  | 5924.4 |  | -- |  |  | -- |  | 7891.4
Recurring | -- |  |  | -- | -- |  |  | 5922.6 |  | -- |  |  | -- |  | 7888.7
Non Recurring | -- |  |  | -- | -- |  |  | 1.8 |  | -- |  |  | -- |  | 2.7
Support | -- |  |  | -- | -- |  |  | 423 |  | -- |  |  | -- |  | 548.6
Other Support | -- |  |  | -- | -- |  |  | 423 |  | -- |  |  | -- |  | 548.6
Initial Spares | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
MILCON | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 2300.3 |  |  | 6664.7 | N/A |  |  | 6957.7 |  | 2606.7 |  |  | 8463.5 |  | 9098.3
Current APB Cost Estimate Reference
Procurement costs and RDT&E costs for this APB are based on the FY 2016 PB dated February 19, 2015 and the O&S cost are based on an ICE dated August 28, 2014
Confidence Level
Confidence Level of cost estimate for current APB: 50%
A mathematically derived confidence level was not computed for this Life-Cycle Cost Estimate (LCCE). This LCCE represents the expected value, taking into consideration relevant risks, including ordinary levels of external and unforeseen events. It aims to provide sufficient resources to execute the program under normal conditions encountering average levels of technical, schedule, and programmatic risk and external influence.
Total Quantity
Quantity |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  | 630 |  |  |  | 804 |  |  |  |  | 804
Procurement |  | 88435 |  |  |  | 321182 |  |  |  |  | 355445
Total |  | 89065 |  |  |  | 321986 |  |  |  |  | 356249

## Table 16
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 602.3 | 0 |  |  | 9.9 | 14.9 | 31.2 |  | 0 |  |  | 0 |  | 0 | 658.3
Procurement | 5669.5 | 559.5 |  |  | 777.2 | 256 | 346 |  | 423.2 |  |  | 408.6 |  | 0 | 8440
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  | 0 |  | 0 | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  | 0 |  | 0 | 0
PB 2017 Total | 6271.8 | 559.5 |  |  | 787.1 | 270.9 | 377.2 |  | 423.2 |  |  | 408.6 |  | 0 | 9098.3
PB 2016 Total | 6273.2 | 579.1 |  |  | 354.1 | 245.5 | 330 |  | 386.9 |  |  | 0 |  | 0 | 8168.8
Delta | -1.4 | -19.6 |  |  | 433 | 25.4 | 47.2 |  | 36.3 |  |  | 408.6 |  | 0 | 929.5
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 804 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 804
Production | 0 |  | 242380 |  | 23560 | 33953 | 9781 13559 |  |  | 16604 |  | 15608 |  | 0 |  | 355445
PB 2017 Total | 804 |  | 242380 |  | 23560 | 33953 | 9781 13559 |  |  | 16604 |  | 15608 |  | 0 |  | 356249
PB 2016 Total | 804 |  | 242024 |  | 20425 | 11649 | 7678 10127 |  |  | 11450 |  | 0 |  | 0 |  | 304157
Delta | 0 |  | 356 |  | 3135 | 22304 | 2103 |  | 3432 | 5154 |  | 15608 |  | 0 |  | 52092

## Table 17
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.2
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.8
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.4
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.1
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.6
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.1
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.2
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.3
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.5
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.3
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
Subtotal |  | 114 | -- |  | -- |  | -- |  | -- |  | -- |  | 194.3

## Table 18
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 1995 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.8
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.8
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.7
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.7
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.2
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.7
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.7
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.7
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.8
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
Subtotal |  | 114 | -- |  | -- |  | -- |  | -- |  | -- |  | 184.8

## Table 19
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.5
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 61.9
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.9
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 76.4
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.7
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.1
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.7
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.3
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.7
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.5
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.3
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.9
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.9
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.2
Subtotal |  | 690 | -- |  | -- |  | -- |  | -- |  | -- |  | 464

## Table 20
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 1995 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.1
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 74
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.2
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.9
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.4
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.8
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.9
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.1
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.3
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.8
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.8
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.6
Subtotal |  | 690 | -- |  | -- |  | -- |  | -- |  | -- |  | 425.5

## Table 21
Annual Funding 1508 ¦ Procurement ¦ Procurement of Ammunition, Navy and Marine Corps
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1998 |  | 547 | 10 |  | -- |  | -- |  | 10 |  | 10.9 |  | 20.9
1999 |  | 745 | 14.6 |  | -- |  | -- |  | 14.6 |  | 20.6 |  | 35.2
2000 |  | 916 | 19.3 |  | -- |  | -- |  | 19.3 |  | 15.7 |  | 35
2001 |  | 2325 | 50.2 |  | -- |  | -- |  | 50.2 |  | 15.4 |  | 65.6
2002 |  | 14551 | 292.4 |  | -- |  | -- |  | 292.4 |  | 10.1 |  | 302.5
2003 |  | 12280 | 242.4 |  | -- |  | -- |  | 242.4 |  | 8.5 |  | 250.9
2004 |  | 12422 | 243.7 |  | -- |  | -- |  | 243.7 |  | 8.2 |  | 251.9
2005 |  | 6876 | 142.5 |  | -- |  | -- |  | 142.5 |  | 8.6 |  | 151.1
2006 |  | 3288 | 72.5 |  | -- |  | -- |  | 72.5 |  | 9 |  | 81.5
2007 |  | 3324 | 73.9 |  | -- |  | -- |  | 73.9 |  | 12.7 |  | 86.6
2008 |  | 1422 | 35.5 |  | -- |  | -- |  | 35.5 |  | 7.1 |  | 42.6
2009 |  | 560 | 13.3 |  | -- |  | -- |  | 13.3 |  | 5.2 |  | 18.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | 2 |  | 2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | 1137 | 23.8 |  | -- |  | -- |  | 23.8 |  | -- |  | 23.8
2015 |  | 876 | 18.7 |  | -- |  | -- |  | 18.7 |  | -- |  | 18.7
2016 |  | 1201 | 25.5 |  | -- |  | -- |  | 25.5 |  | -- |  | 25.5
2017 |  | 3289 | 70.1 |  | -- |  | -- |  | 70.1 |  | -- |  | 70.1
2018 |  | 2404 | 52 |  | -- |  | -- |  | 52 |  | -- |  | 52
2019 |  | 2356 | 52 |  | -- |  | -- |  | 52 |  | -- |  | 52
2020 |  | 2310 | 52 |  | -- |  | -- |  | 52 |  | -- |  | 52
2021 |  | 2265 | 52 |  | -- |  | -- |  | 52 |  | -- |  | 52
Subtotal |  | 75094 | 1556.4 |  | -- |  | -- |  | 1556.4 |  | 134 |  | 1690.4

## Table 22
Annual Funding 1508 ¦ Procurement ¦ Procurement of Ammunition, Navy and Marine Corps
Fiscal Year | Quantity |  | BY 1995 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1998 |  | 547 | 9.4 |  | -- |  | -- |  | 9.4 |  | 10.2 |  | 19.6
1999 |  | 745 | 13.5 |  | -- |  | -- |  | 13.5 |  | 19.1 |  | 32.6
2000 |  | 916 | 17.6 |  | -- |  | -- |  | 17.6 |  | 14.4 |  | 32
2001 |  | 2325 | 45.3 |  | -- |  | -- |  | 45.3 |  | 13.9 |  | 59.2
2002 |  | 14551 | 261.2 |  | -- |  | -- |  | 261.2 |  | 9 |  | 270.2
2003 |  | 12280 | 211.7 |  | -- |  | -- |  | 211.7 |  | 7.4 |  | 219.1
2004 |  | 12422 | 207.3 |  | -- |  | -- |  | 207.3 |  | 7 |  | 214.3
2005 |  | 6876 | 117.8 |  | -- |  | -- |  | 117.8 |  | 7.1 |  | 124.9
2006 |  | 3288 | 58.5 |  | -- |  | -- |  | 58.5 |  | 7.2 |  | 65.7
2007 |  | 3324 | 58.2 |  | -- |  | -- |  | 58.2 |  | 10.1 |  | 68.3
2008 |  | 1422 | 27.6 |  | -- |  | -- |  | 27.6 |  | 5.5 |  | 33.1
2009 |  | 560 | 10.2 |  | -- |  | -- |  | 10.2 |  | 4 |  | 14.2
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | 1.5 |  | 1.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | 1137 | 16.8 |  | -- |  | -- |  | 16.8 |  | -- |  | 16.8
2015 |  | 876 | 13 |  | -- |  | -- |  | 13 |  | -- |  | 13
2016 |  | 1201 | 17.4 |  | -- |  | -- |  | 17.4 |  | -- |  | 17.4
2017 |  | 3289 | 47 |  | -- |  | -- |  | 47 |  | -- |  | 47
2018 |  | 2404 | 34.2 |  | -- |  | -- |  | 34.2 |  | -- |  | 34.2
2019 |  | 2356 | 33.5 |  | -- |  | -- |  | 33.5 |  | -- |  | 33.5
2020 |  | 2310 | 32.8 |  | -- |  | -- |  | 32.8 |  | -- |  | 32.8
2021 |  | 2265 | 32.2 |  | -- |  | -- |  | 32.2 |  | -- |  | 32.2
Subtotal |  | 75094 | 1265.2 |  | -- |  | -- |  | 1265.2 |  | 116.4 |  | 1381.6

## Table 23
Annual Funding 3011 ¦ Procurement ¦ Procurement of Ammunition, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1997 |  | 937 | 16.6 |  | -- |  | -- |  | 16.6 |  | 6.4 |  | 23
1998 |  | 1828 | 33.5 |  | -- |  | -- |  | 33.5 |  | 5.7 |  | 39.2
1999 |  | 3778 | 72.4 |  | -- |  | -- |  | 72.4 |  | 7.1 |  | 79.5
2000 |  | 8725 | 180.1 |  | -- |  | -- |  | 180.1 |  | 9.1 |  | 189.2
2001 |  | 8904 | 189.9 |  | -- |  | -- |  | 189.9 |  | 13.6 |  | 203.5
2002 |  | 14392 | 285.9 |  | -- |  | -- |  | 285.9 |  | 14.5 |  | 300.4
2003 |  | 23420 | 458.5 |  | -- |  | -- |  | 458.5 |  | 18.6 |  | 477.1
2004 |  | 20476 | 404.2 |  | -- |  | -- |  | 404.2 |  | 20.3 |  | 424.5
2005 |  | 22880 | 491.8 |  | -- |  | -- |  | 491.8 |  | 22.6 |  | 514.4
2006 |  | 8205 | 200.8 |  | -- |  | -- |  | 200.8 |  | 24.4 |  | 225.2
2007 |  | 7261 | 163.6 |  | 17.1 |  | -- |  | 180.7 |  | 13.4 |  | 194.1
2008 |  | 4319 | 102.1 |  | -- |  | -- |  | 102.1 |  | 22 |  | 124.1
2009 |  | 6340 | 149.1 |  | -- |  | -- |  | 149.1 |  | 16.9 |  | 166
2010 |  | 7488 | 169.5 |  | 7.6 |  | -- |  | 177.1 |  | 21.3 |  | 198.4
2011 |  | 14551 | 350.6 |  | 6.9 |  | -- |  | 357.5 |  | 15.9 |  | 373.4
2012 |  | 4637 | 111.5 |  | -- |  | -- |  | 111.5 |  | 15.7 |  | 127.2
2013 |  | 4728 | 113.8 |  | 19.9 |  | -- |  | 133.7 |  | 10.9 |  | 144.6
2014 |  | 8604 | 191.9 |  | 47 |  | -- |  | 238.9 |  | 11.6 |  | 250.5
2015 |  | 9638 | 211 |  | -- |  | -- |  | 211 |  | 17.4 |  | 228.4
2016 |  | 22359 | 482.2 |  | 29.4 |  | 2.7 |  | 514.3 |  | 19.7 |  | 534
2017 |  | 30664 | 663.7 |  | 21.5 |  | -- |  | 685.2 |  | 21.9 |  | 707.1
2018 |  | 7377 | 162.1 |  | 21.9 |  | -- |  | 184 |  | 20 |  | 204
2019 |  | 11203 | 251.2 |  | 21.8 |  | -- |  | 273 |  | 21 |  | 294
2020 |  | 14294 | 326.9 |  | 22.3 |  | -- |  | 349.2 |  | 22 |  | 371.2
2021 |  | 13343 | 311.2 |  | 22.8 |  | -- |  | 334 |  | 22.6 |  | 356.6
Subtotal |  | 280351 | 6094.1 |  | 238.2 |  | 2.7 |  | 6335 |  | 414.6 |  | 6749.6

## Table 24
Annual Funding 3011 ¦ Procurement ¦ Procurement of Ammunition, Air Force
Fiscal Year | Quantity |  | BY 1995 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1997 |  | 937 | 15.5 |  | -- |  | -- |  | 15.5 |  | 6 |  | 21.5
1998 |  | 1828 | 30.9 |  | -- |  | -- |  | 30.9 |  | 5.2 |  | 36.1
1999 |  | 3778 | 66.1 |  | -- |  | -- |  | 66.1 |  | 6.5 |  | 72.6
2000 |  | 8725 | 162.3 |  | -- |  | -- |  | 162.3 |  | 8.2 |  | 170.5
2001 |  | 8904 | 168 |  | -- |  | -- |  | 168 |  | 12.1 |  | 180.1
2002 |  | 14392 | 247.9 |  | -- |  | -- |  | 247.9 |  | 12.6 |  | 260.5
2003 |  | 23420 | 388.5 |  | -- |  | -- |  | 388.5 |  | 15.7 |  | 404.2
2004 |  | 20476 | 332.8 |  | -- |  | -- |  | 332.8 |  | 16.7 |  | 349.5
2005 |  | 22880 | 394 |  | -- |  | -- |  | 394 |  | 18.1 |  | 412.1
2006 |  | 8205 | 157.8 |  | -- |  | -- |  | 157.8 |  | 19.1 |  | 176.9
2007 |  | 7261 | 126.7 |  | 13.2 |  | -- |  | 139.9 |  | 10.4 |  | 150.3
2008 |  | 4319 | 78 |  | -- |  | -- |  | 78 |  | 16.8 |  | 94.8
2009 |  | 6340 | 112 |  | -- |  | -- |  | 112 |  | 12.7 |  | 124.7
2010 |  | 7488 | 125.1 |  | 5.6 |  | -- |  | 130.7 |  | 15.7 |  | 146.4
2011 |  | 14551 | 254.5 |  | 5 |  | -- |  | 259.5 |  | 11.6 |  | 271.1
2012 |  | 4637 | 79.4 |  | -- |  | -- |  | 79.4 |  | 11.2 |  | 90.6
2013 |  | 4728 | 80 |  | 13.9 |  | -- |  | 93.9 |  | 7.7 |  | 101.6
2014 |  | 8604 | 132.8 |  | 32.5 |  | -- |  | 165.3 |  | 8 |  | 173.3
2015 |  | 9638 | 143.1 |  | -- |  | -- |  | 143.1 |  | 11.8 |  | 154.9
2016 |  | 22359 | 320.7 |  | 19.6 |  | 1.8 |  | 342.1 |  | 13.1 |  | 355.2
2017 |  | 30664 | 432.8 |  | 14 |  | -- |  | 446.8 |  | 14.3 |  | 461.1
2018 |  | 7377 | 103.7 |  | 14 |  | -- |  | 117.7 |  | 12.8 |  | 130.5
2019 |  | 11203 | 157.5 |  | 13.6 |  | -- |  | 171.1 |  | 13.2 |  | 184.3
2020 |  | 14294 | 200.9 |  | 13.8 |  | -- |  | 214.7 |  | 13.5 |  | 228.2
2021 |  | 13343 | 187.5 |  | 13.7 |  | -- |  | 201.2 |  | 13.6 |  | 214.8
Subtotal |  | 280351 | 4498.5 |  | 158.9 |  | 1.8 |  | 4659.2 |  | 306.6 |  | 4965.8

## Table 25
FY 2016 includes Overseas Contingency Operations (OCO) funding of $184.412M and OCO quantity if 8,511. FY 2017 includes OCO funding of $403.126M and OCO funding of 18,531.
Laser JDAM (LJDAM) costs are included under the Non End Item Related Recurring Flyaway costs. This includes 2,581 LJDAM kits for FY 2016 and 1,500 LJDAM kits per year from FY 2017 to FY 2021.
FY 2016 Nonrecurring Flyaway costs include investments in LJDAM facilitization, and a Life of Type Buy (LOTB) procurement. The LOTB cost is for the acquisition of one LJDAM component that is reaching obsolescence, and will allow for LJDAM production over the next four contract lots without causing schedule delays or cost increases.

## Table 26
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 1995-09-20 | 2000-01-21
Approved Quantity | 425 | 15998
Reference | Milestone II ADM | LRIP 4 ADM
Start Year | 1997 | 1997
End Year | 1998 | 2000

## Table 27
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Belgium | 2015-11-20 | 60 | 1.3 | JDAM Kits
Canada | 2015-11-20 | 350 | 7.9 | JDAM Kits
Denmark | 2015-11-20 | 50 | 1.2 | JDAM Kits
Finland | 2015-11-20 | 18 | 0.4 | JDAM Kits
Israel | 2015-11-20 | 100 | 2.4 | JDAM Kits
Netherlands | 2015-11-20 | 300 | 6.6 | JDAM Kits
Singapore | 2015-11-20 | 917 | 22 | JDAM Kits
Taiwan | 2015-11-20 | 1 | 0 | JDAM Kit
Turkey | 2015-11-20 | 400 | 9.4 | JDAM Kits
Israel | 2014-10-31 | 3000 | 65.5 | JDAM kits
Norway | 2014-10-31 | 238 | 4.9 | JDAM kits
Morocco | 2014-10-30 | 20 | 0.4 | JDAM kits
United Arab Emirates | 2014-10-30 | 3600 | 74.4 | JDAM kits
Oman | 2013-07-01 |  | 0.9 | Fuzes
Belgium | 2013-05-15 |  | 0.1 | Fuzes
Norway | 2013-03-08 |  | 2.8 | Fuzes
Israel | 2013-03-07 | 3113 | 88.8 | JDAM Kits and Support
Korea | 2013-03-07 | 210 | 7.8 | JDAM Kits, Fuzes
Japan | 2013-03-01 | 68 | 4.2 | JDAM Kits
Poland | 2013-01-31 |  | 1.1 | JDAM Manpower
Turkey | 2012-12-19 | 300 | 13.4 | JDAM Kits, Fuzes
Korea | 2012-11-27 | 140 | 5.1 | JDAM Kits, Fuzes
Israel | 2012-11-21 | 1500 | 40.8 | JDAM Kits
Finland | 2012-07-15 |  | 0.2 | Repair and Return, Spares, Support
Korea | 2012-05-01 | 106 | 3.6 | JDAM Kits
Iraq | 2012-04-19 | 358 | 2 | Fuzes
Canada | 2012-04-17 | 0 | 0.2 | Fuzes
Saudi Arabia | 2012-02-22 | 0 | 61.4 | Engineering Support
Saudi Arabia | 2012-02-22 |  | 5.4 | Repair and Return, Spares, Support
Saudi Arabia | 2012-02-11 | 600 | 154.5 | JDAM Kits, PLGS, Fuzes
Japan | 2011-10-12 | 16 | 0.7 | JDAM Kits
Japan | 2011-10-12 | 8 | 0.7 | JDAM Kits
Belgium | 2011-09-08 | 180 | 5.4 | JDAM Kits, Fuzes
Malaysia | 2011-08-23 | 0 | 1.8 | JDAM Spares, Test Assets
Canada | 2011-08-11 | 533 | 15.9 | JDAM Kits, Integration Support
Japan | 2011-07-15 | 0 | 2.7 | Fuzes
Chile | 2011-06-10 | 210 | 8 | JDAM Kits, Fuzes
Norway | 2011-04-26 | 254 | 9.5 | JDAM Kits
Denmark | 2011-04-11 | 210 | 8.9 | JDAM Kits
Belgium | 2011-02-02 | 30 | 0.8 | Spares
Brazil | 2011-01-28 | 0 | 0.3 | Fuzes
Morocco | 2010-09-08 | 10 | 6 | JDAM Kits
Japan | 2010-02-09 | 96 | 4.9 | JDAM Kits, Fuzes

## Table 28
Japan | 2010-01-29 | 31 | 1.7 | JDAM Kits, Fuzes
Singapore | 2010-01-27 | 670 | 35.5 | JDAM Kits
Israel | 2010-01-22 | 150 | 2.1 | Precision Laser Guidance Set
Israel | 2010-01-12 | 150 | 3.5 | JDAM Kits
Netherlands | 2009-12-04 | 0 | 2.8 | Fuzes
South Korea | 2009-11-30 | 0 | 3.8 | JDAM Integration on F-16
Malaysia | 2009-09-28 | 50 | 5.8 | JDAM Kits
Norway | 2009-06-10 | 30 | 5.2 | JDAM Kits, Support
Kuwait | 2009-03-31 | 51 | 5.9 | JDAM Kits, Support
United Arab Emirates | 2009-03-24 | 0 | 1.1 | Repair and Return, Spares, Support
Japan | 2009-03-12 | 120 | 9.2 | JDAM Kits
Finland | 2009-02-25 | 96 | 7 | JDAM Kits
Singapore | 2009-02-11 | 35 | 4.1 | JDAM Kits
Japan | 2009-02-03 | 36 | 3.1 | JDAM Kits, Fuzes
Oman | 2009-02-02 | 0 | 0.8 | Repair and Return, Spares, Support
Israel | 2009-01-12 | 500 | 14.9 | JDAM Kits
Israel | 2009-01-12 | 2950 | 71.6 | JDAM Kits
South Korea | 2008-12-29 |  | 0.4 | Fuzes
South Korea | 2008-12-16 | 4 | 0.5 | JDAM Kits
Germany | 2008-10-28 |  | 0.2 | Fuzes
South Korea | 2008-09-03 |  | 0.2 | Fuzes
Israel | 2008-07-21 |  | 0.6 | Engineering Support
Saudi Arabia | 2008-07-02 | 900 | 44.2 | JDAM Kits, Support
South Korea | 2008-03-11 |  | 2.2 | Fuzes
Japan | 2008-03-07 | 36 | 2.1 | JDAM Kits, Fuzes
United Arab Emirates | 2008-02-21 | 300 | 70.6 | JDAM Kits
South Korea | 2008-02-19 |  | 4.3 | Fuzes, Global Positioning System (GPS) Security
South Korea | 2007-12-28 |  | 0.4 | Fuzes
South Korea | 2007-12-28 |  | 0.4 | Fuzes
Australia | 2007-12-11 |  | 2.6 | Engineering Support
Greece | 2007-11-20 | 100 | 21.9 | JDAM Kits, Integration Support
Netherlands | 2007-10-24 |  | 2.8 | Fuzes
Israel | 2007-10-02 | 1000 | 28 | JDAM Kits
Israel | 2007-09-26 | 650 | 17.3 | JDAM Kits
Israel | 2007-07-13 | 300 | 8.3 | JDAM Kits
Turkey | 2007-05-29 |  | 0.4 | Fuzes
Israel | 2007-03-05 | 500 | 12.9 | JDAM Kits
Japan | 2006-12-18 | 42 | 1.8 | JDAM Kits
Spain | 2006-12-14 | 40 | 2.5 | JDAM Kits
Pakistan | 2006-09-30 | 500 | 23.6 | JDAM Kits
Israel | 2006-07-25 |  | 0.1 | Engineering Support
Japan | 2006-03-27 | 44 | 3.5 | JDAM Kits
Japan | 2006-03-17 |  | 0.1 | Engineering Support
Turkey | 2005-12-28 | 398 | 9.9 | JDAM Kits
Turkey | 2005-12-28 |  | 6.9 | Integration
Greece | 2005-12-13 |  | 2.3 | Integration Support
Netherlands | 2005-10-07 | 56 | 1.7 | JDAM Kits
Turkey | 2005-04-26 |  | 4.7 | Integration Support

## Table 29
Australia | 2005-04-05 |  | 0.3 | Integration Support
Netherlands | 2005-03-01 | 360 | 8.7 | JDAM Kits, Support
Japan | 2005-01-25 | 27 | 8.5 | JDAM Kits, Integration, Test Assets
Belgium | 2004-12-22 | 300 | 7.9 | JDAM Kits
Israel | 2004-08-16 |  | 17.6 | F-15 Integration
Israel | 2004-07-14 | 840 | 18.1 | JDAM Kits, Integration
Portugal | 2004-04-15 | 50 | 3.7 | JDAM Kits, Support
Netherlands | 2004-02-23 | 350 | 13.8 | JDAM Kits, Support
Oman | 2004-02-15 | 20 | 0.5 | JDAM Kits
Israel | 2003-07-03 | 1000 | 21.5 | JDAM Kits
Poland | 2003-04-18 | 272 | 10.6 | JDAM Kits, Integration, Test Assets
Denmark | 2002-12-20 | 274 | 11 | JDAM Kits, Support
United Arab Emirates | 2002-08-20 | 300 | 9 | JDAM Kits
South Korea | 2002-06-12 | 14 | 1.1 | JDAM Kits
Oman | 2002-05-02 | 80 | 3.2 | JDAM Kits
Belgium | 2002-02-11 |  | 0.8 | Fuzes
Chile | 2002-02-01 | 12 | 3 | JDAM Kits, Integration, Test Assets
Australia | 2000-11-28 |  | 3.2 | Fuzes
Australia | 2000-11-28 |  | 6.8 | Fuzes
United Arab Emirates | 2000-08-08 |  | 1.3 | Integration, Test Assets
Israel | 2000-02-09 | 700 | 31.5 | JDAM Kits, Integration
Notes
Nuclear Costs
None

## Table 30
Unit Cost
Unit Cost Report
Item |  | BY 1995 $M | BY 1995 $M |  | % Change
|  | Current UCR Baseline (Jun 2015 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 6664.7 |  |  | 6957.7
Quantity | 321986 |  |  | 356249
Unit Cost | 0.021 |  |  | 0.02 |  | -4.76
Average Procurement Unit Cost
Cost | 6091.9 |  |  | 6347.4
Quantity | 321182 |  |  | 355445
Unit Cost | 0.019 |  |  | 0.018 |  | -5.26
Item |  | BY 1995 $M | BY 1995 $M |  | % Change
|  | Original UCR Baseline (Sep 1995 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2720.4 |  |  | 6957.7
Quantity | 88126 |  |  | 356249
Unit Cost | 0.031 |  |  | 0.02 |  | -35.48
Average Procurement Unit Cost
Cost | 2090.6 |  |  | 6347.4
Quantity | 87496 |  |  | 355445
Unit Cost | 0.024 |  |  | 0.018 |  | -25

## Table 31
Unit Cost History
Item | [7 empty] | Date |  |  |  | BY 1995 $M | [7 empty] | TY $M
[12 empty] | PAUC |  |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Sep 1995 | [6 empty] | 0.031 |  |  |  |  | 0.024 |  |  |  | 0.038 |  |  |  | 0.033
APB as of January 2006 |  |  |  |  | Oct 2002 | [6 empty] | 0.022 |  |  |  |  | 0.019 |  |  |  | 0.025 |  |  |  | 0.023
Revised Original APB |  |  |  |  | N/A | [6 empty] | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | Oct 2002 | [6 empty] | 0.022 |  |  |  |  | 0.019 |  |  |  | 0.025 |  |  |  | 0.023
Current APB |  |  |  |  | Jun 2015 | [6 empty] | 0.021 |  |  |  |  | 0.019 |  |  |  | 0.026 |  |  |  | 0.024
Prior Annual SAR |  |  |  |  | Dec 2014 | [6 empty] | 0.021 |  |  |  |  | 0.019 |  |  |  | 0.027 |  |  |  | 0.025
Current Estimate |  |  |  |  | Dec 2015 | [6 empty] | 0.02 |  |  |  |  | 0.018 |  |  |  | 0.026 |  |  |  | 0.024
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [21 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  |  | Oth |  | Spt |  |  | Total
0.038 -0.002 -0.005 0.002 0.001 -0.005 0.000 0.000 -0.009 0.029
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [19 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng | Est |  | Oth |  | Spt |  |  | Total
0.029 0.001 -0.006 0.000 0.000 0.001 0.000 0.001 -0.003 0.026

## Table 32
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [9 empty] | APUC Production Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt | Total
0.033 -0.002 -0.003 0.002 0.000 -0.006 0.000 0.000 -0.009 0.024
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [9 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt | Total
0.024 0.001 -0.003 0.000 0.000 0.001 0.000 0.001 0.000 0.024
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone I |  |  | Oct 1993 |  |  | Oct 1993 |  |  | Oct 1993 |  |  | Oct 1993
Milestone II |  |  | Oct 1995 |  |  | Sep 1995 |  |  | Sep 1995 |  |  | Sep 1995
Milestone III |  |  | Jul 1999 |  |  | Nov 2000 |  |  | Nov 2000 |  |  | Mar 2001
IOC |  |  | Sep 1999 |  |  | Sep 1999 |  |  | Nov 2000 |  |  | Feb 2001
Total Cost (TY $M) |  |  | 681.5 |  |  | 3392.3 |  |  | 2606.7 |  |  | 9098.3
Total Quantity |  |  | 378 |  |  | 88126 |  |  | 89065 |  |  | 356249
PAUC |  |  | 1.803 |  |  | 0.038 |  |  | 0.029 |  |  | 0.026
IOC of February 2001 is specifically for the F/A-18C/D.

## Table 33
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
517.3 2089.4 -- 2606.7
Economic |  | 3.5 |  | 78.3 |  | -- |  | 81.8
Quantity |  | -- |  | 4160.8 |  | -- |  | 4160.8
Schedule |  | -- |  | -86.4 |  | -- |  | -86.4
Engineering |  | 15.5 |  | -- |  | -- |  | 15.5
Estimating |  | 66 |  | 986.6 |  | -- |  | 1052.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 337.8 |  | -- |  | 337.8
Subtotal |  | 85 |  | 5477.1 |  | -- |  | 5562.1
Current Changes Economic |  | -0.1 |  | 135.2 |  | -- |  | 135.1
Quantity |  | -- |  | 1525.7 |  | -- |  | 1525.7
Schedule |  | -- |  | -34.5 |  | -- |  | -34.5
Engineering |  | 56 |  | -- |  | -- |  | 56
Estimating |  | 0.1 |  | -797.1 |  | -- |  | -797
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 44.2 |  | -- |  | 44.2
Subtotal |  | 56 |  | 873.5 |  | -- |  | 929.5
Total Changes |  | 141 |  | 6350.6 |  | -- |  | 6491.6
CE - Cost Variance |  | 658.3 |  | 8440 |  | -- |  | 9098.3
CE - Cost & Funding |  | 658.3 |  | 8440 |  | -- |  | 9098.3

## Table 34
Summary BY 1995 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
490.3 1810.0 -- 2300.3
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 3015.2 |  | -- |  | 3015.2
Schedule |  | -- |  | -7.5 |  | -- |  | -7.5
Engineering |  | 12.5 |  | -- |  | -- |  | 12.5
Estimating |  | 70 |  | 825.6 |  | -- |  | 895.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 260.7 |  | -- |  | 260.7
Subtotal |  | 82.5 |  | 4094 |  | -- |  | 4176.5
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 945.6 |  | -- |  | 945.6
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | 37.4 |  | -- |  | -- |  | 37.4
Estimating |  | 0.1 |  | -527.9 |  | -- |  | -527.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 25.7 |  | -- |  | 25.7
Subtotal |  | 37.5 |  | 443.4 |  | -- |  | 480.9
Total Changes |  | 120 |  | 4537.4 |  | -- |  | 4657.4
CE - Cost Variance |  | 610.3 |  | 6347.4 |  | -- |  | 6957.7
CE - Cost & Funding |  | 610.3 |  | 6347.4 |  | -- |  | 6957.7
Previous Estimate: December 2014

## Table 35
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.1
Adjustment for current and prior escalation. (Estimating) | 0.1 | 0.1
Additional funding was provided for Global Positioning System M-Code integration efforts. (Engineering) | 37.4 | 56
RDT&E Subtotal | 37.5 | 56
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A +135.2
Adjustment for current and prior escalation. (Estimating) -94.2 -118.4
Quantity variance resulting from an increase of 8,829 tail kits from 66,265 to 75,094 (Navy). (Quantity)
Quantity variance resulting from an increase of 43,263 tail kits from 237,088 to 280,351 (Air Force). (Quantity)
Acceleration of procurement buy profile from FY 2015 to FY 2021 due to increased production capacity based on urgent operational need by the Warfighter (Navy). (Schedule)
Acceleration of procurement buy profile from FY 2015 to FY 2021 due to increased production capacity based on urgent operational need by the Warfighter (Air Force). (Schedule)
Lower unit pricing due to contract negotiations and increased quantities procured; funds reinvested internally to procure additional tail kits (Navy). (Estimating) (QR)
Lower unit pricing due to contract negotiations and increased quantities procured; funds reinvested internally to procure additional tail kits (Air Force). (Estimating) (QR)
+160.2 +251.4
+785.4 +1274.3
0.0 -3.2
0.0 -31.3
-65.3 -99.7
-367.7 -577.9
Revised estimate to reflect actuals (Air Force). (Estimating) -0.7 -1.1
Adjustment for current and prior escalation. (Support) -6.3 -7.6
Increase in Other Support to align with engineering efforts for software updates and M-Code integration (Air Force). (Support)
+32.0 +51.8
Procurement Subtotal +443.4 +873.5
(QR) Quantity Related

## Table 36
Contracts
General Notes
Ongoing strategy change requiring Certified Cost or Pricing data has put pressure on the procurement schedule for Lots 18 through 22; risk mitigated with an Undefinitized Contract Action (UCA).
Contract Identification
Appropriation: Procurement
Contract Name: JDAM Lot 18 UCA
Contractor: Boeing
Contractor Location: 6200 JS McDonnell Blvd
Saint Louis, MO 63134
Contract Number: FA8213-15-D-0002/1
Contract Type: Firm Fixed Price (FFP)
Award Date: October 30, 2014
Definitization Date:
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
213.9 N/A 9202 204.2 N/A 9202 204.2 204.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to lower unit prices resulting from contract negotiations.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
Data includes Air Force and Navy only. Foreign Military Sales data is not included in the contract price or quantity.

## Table 37
Contract Identification
Appropriation: Procurement
Contract Name: JDAM Lot 19 UCA
Contractor: Boeing
Contractor Location: 6200 JS McDonnell Blvd
Saint Louis, MO 63134
Contract Number: FA8213-15-D-0002/2
Contract Type: Firm Fixed Price (FFP)
Award Date: November 20, 2015
Definitization Date:
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
286.7 N/A 13127 286.7 N/A 13127 286.7 286.7
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This is the first time this contract is being reported.
Data includes Air Force and Navy only. Foreign Military Sales data is not included in the contract price or quantity.

## Table 38
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 804 | 804 | 804 | 100%
Production | 226796 | 226104 | 355445 | 63.61%
Total Program Quantity Delivered | 227600 | 226908 | 356249 | 63.69%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
9098.3
5847.5
64.27%
29
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
24
82.76%
6831.3
75.08%
The above data is current as of February 09, 2016.
Deliveries and Expenditures include both U.S. Air Force (USAF) and U.S. Navy (USN).
This SAR report does not include quantities or costs paid for with Defense Emergency Response Funds (DERF). DERF funds acquired 6,348 USAF tail kits and 7,890 USN tail kits. The previous SAR report had included these quantities.

## Table 39
Operating and Support Cost
Cost Estimate Details
Date of Estimate: August 28, 2014
Source of Estimate: POE
Quantity to Sustain: 356249
Unit of Measure: Total Quantity
Service Life per Unit: 35.00 Years
Fiscal Years in Service: FY 1998 - FY 2049
The JDAM O&S cost estimate was based on the Joint Munitions Operations & Support Model which was tailored to reflect specific JDAM program attributes. This model estimated Air Force and Navy O&S costs for the JDAM tail kits only. The ground rules used in the O&S cost estimate are as follows: The total JDAM inventory that had been expended was 88,569 tail kits. JDAM uses a 20 year extended warranty to cover all tail kit repairs except for government induced failures. In the model, one half of a percent of the total JDAM failures were assumed to be induced out-of-warranty failures. The base year of the estimate was FY 2015 (all sunk costs from FY 1998 to FY 2014 are excluded from the estimate). The estimate included calculations for 35 years (FY 2015 to FY 2049) to cover unwarranted failures for 15 years after the warranty period ended. The fiscal years in service is stated to end in FY 2049; however, the actual program complete date is indefinite as long as there is continued demand for JDAM.
Sustainment Strategy
The JDAM system support strategy is a 20-year warranty that includes both the guidance kit and container. Boeing is the Source of Repair (SOR) under the warranty. Non-warranty repairs and sustaining engineering support are covered under separate technical support contracts with Boeing.
Antecedent Information
No Antecedent
Annual O&S Costs BY1995 $M
Cost Element | JDAM Average Annual Cost Per Total Quantity | No Antecedent (Antecedent)
Unit-Level Manpower | 0.647 | --
Unit Operations | 15.671 | --
Maintenance | 0.001 | --
Sustaining Support | 3.562 | --
Continuing System Improvements | -- | --
Indirect Support | 0.477 | --
Other | -- | --
Total | 20.358 | --

## Table 40
Item | Total O&S Cost $M
| JDAM | [5 empty] | No Antecedent (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 712.5 |  | 783.8 |  |  | 712.5 | N/A
Then Year | 1494.9 |  | N/A |  |  | 1494.9 | N/A
Equation to Translate Annual Cost to Total Cost
Total O&S Cost = Average Annual Cost x Assumed Life in Years = $20.358M x 35 years = $712.5M (BY 1995$)
O&S Cost Variance
Category |  | BY 1995 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
712.5
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 712.5
Disposal Estimate Details
Date of Estimate: August 28, 2014
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 1995 $M): Total costs for disposal of all Total Quantity are 51.3