## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-387
KC-46A Tanker Modernization (KC-46A)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 11
Schedule 12
Performance 13
Track to Budget 20
Cost and Funding 21
Low Rate Initial Production 34
Foreign Military Sales 35
Nuclear Costs 35
Unit Cost 36
Cost Variance 39
Contracts 43
Deliveries and Expenditures 48
Operating and Support Cost 49

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
KC-46A Tanker Modernization (KC-46A)
DoD Component
Air Force
Responsible Office
Brig Gen Duke Z. Richardson 2590 Loop Road West, Bldg 558
Wright-Patterson Air Force Base, OH 45433
duke.richardson@us.af.mil
Phone: | 937-255-9734
Fax: | 937-255-6350
DSN Phone: | 785-9734
DSN Fax: | 785-6350
Date Assigned: | September 26, 2014
.
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated August 24, 2011
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated August 24, 2011

## Table 6
Mission and Description
The KC-46A Tanker Modernization (KC-46A) will replace the U.S. Air Force's aging fleet of Tankers which have been the primary refueling aircraft for more than 50 years. The KC-46A will have enhanced refueling capabilities with greater capacity, and both cargo and aeromedical evacuation with improved efficiency and increased capabilities. The KC-46A will provide aerial refueling support to the United States Air Force, Navy, and Marine Corps, as well as allied nation coalition aircraft.
The KC-46A will have the ability to refuel any fixed-wing receiver capable aircraft on any mission. The KC-46A will be equipped with a modernized KC-10 refueling boom integrated with a fly-by-wire control system, and will be capable of delivering a fuel offload rate required for large aircraft. Furthermore, a hose and drogue system will add additional mission capability which will be independently operable from the refueling boom system. The centerline drogue and wing aerial refueling pods (WARPs) will be used to refuel aircraft fitted with probes. All KC-46A aircraft will be configured for the installation of a Multi-Point Refueling System capable of refueling two receiver aircraft simultaneously from the WARPs mounted under the wings. One Aerial Refueling Operator will control the boom, centerline drogue, and WARPs during refueling operations. Panoramic displays will provide the Aerial Refueling Operator with wing-tip to wing-tip situational awareness.
A cargo deck above the refueling system will accommodate a mixed load of passengers, patients, and cargo. The KC-46A will carry up to eighteen 463L cargo pallets. Seat tracks and the onboard cargo handling system will make it possible to simultaneously carry palletized cargo, seats, and patient support pallets in a variety of combinations. The KC-46A will offer significantly increased cargo and aeromedical evacuation capabilities compared to the KC-135R.
The aircrew compartment will include 15 permanent seats for aircrew, which will include permanent seating for the Aerial Refueling Operators and an optional Aerial Refueling Instructor.
Two high-bypass turbofans, mounted under 34-degree swept wings, will power the KC-46A to take off at gross weights up to 415,000 pounds.

## Table 7
Executive Summary
Program Highlights Since Last Report
Due to schedule delays, the program is estimating several APB schedule date changes beyond the six-month SAR Current Estimate (CE) dates reported in December 2014. The CE changes for Milestone C (MS C), Initial Operational Test & Evaluation (IOT&E), and the FRP Decision milestones require a schedule update for this December 2015 SAR cycle.
The Engineering and Manufacturing Development (EMD) contract is 76.3% complete. Government funding has been stable with no Government-driven engineering changes to the design. In July 2015, Boeing self-identified a fuel contamination incident during fuel dock testing, affecting several fuel system components on EMD-2. Boeing conducted a Root Cause and Corrective Action review and outbriefed the Program Office on August 6, 2015. On August 25, 2015, EMD-2 was returned to complete fuel dock testing. Despite the offset, EMD-2 completed a successful first flight on September 25, 2015. Boeing continues to assess they can apply the necessary resources needed to achieve an on-time Required Assets Available (RAA) date. Delays and schedule pressures notwithstanding, the KC-46A program and strategy remain strong.
Government’s maximum liability on the EMD contract with Boeing remains capped at the ceiling price of $4.9B. The following paragraphs of this Executive Summary provide additional historical details and Calendar Year (CY) 2015 accomplishments.
Boeing's inability to meet internal program milestones has deteriorated all schedule margin to the contractual Required Assets Available (RAA) date of August 2017. Milestone C (MS C) is planned for April 2016, with four months of schedule pressure to the August 2017 contractual RAA date. The Program Office is working with Boeing to implement a program schedule re-baseline (hereafter referred to as “KCR-0700”), in addition to tracking performance against the new baseline. The Program Office continues to work with Boeing on schedule mitigation efforts.
The KCR-0700 schedule rebaseline was incorporated into the October 2015 month-end Integrated Master Schedule, which was delivered in November 2015. The Program Office, Boeing, and the Defense Contract Management Agency conducted an Integrated Risk Assessment (IRA) January 11 – 12, 2016 and Schedule Risk Assessment (SRA) January 26 – 28, 2016 to assess additional cost and schedule risks. SRA analysis/validation is on-going and results will be briefed to senior Air Force leadership in March 2016.
Boeing implemented an Over Target Baseline to the KC-46A Earned Value Management data. Regular reporting resumed with the October 2015 Contract Performance Report received in November 2015.
Summer and fall of 2015 saw a number of program accomplishments. EMD-1 began constant flight operations at the end of May 2015 and started initial flight testing, completing Flutter, Aero Stability and Control, and Auto-Pilot validation flights before going into a planned non-flying status period at the end of November 2015 through February 2016 to bring the fuel system up to a type design configuration. EMD-2 moved to the Boeing Finishing Center, after originally planned, to complete aircraft electrical build and military component installations to become the first KC-46A aircraft. In October and November 2015, EMD-2 completed initial airworthiness flights to support Federal Aviation Administration (FAA) certification as well as boom and drogue free air stability flights to support the use of the boom and both drogue systems in MS C refueling contact demonstrations. EMD-2 entered Fuel Dock 2 in late November 2015 in preparation for refueling contact demonstrations for MS C. In early January 2016, EMD-2 completed free air stability prerequisite flight tests in order to begin MS C in-flight aerial refueling demonstrations. At the end of January 2016, EMD-2 successfully completed in-flight rendezvous, contact, and fuel transfer demonstrations with the F-16C. Successful fuel transfer was then conducted with the F/A-18, and finally with the KC-46A as a receiver behind a KC-10, both in mid-February 2016. The KC-46A test team plans to conduct the remainder of the required MS C in-flight rendezvous, contact, and fuel transfer demonstrations with the C-17A, A-10C, and AV-8B in late February 2016. The test team is also focused on completing required actions to conduct EMD-4's first flight in late February or early March 2016.
Phase I Lab Verification Testing started November 24, 2014 and completed in June 2015. Phase 2 testing began January

## Table 8
14, 2015, and has completed 42 of 48 tests, with overall completion estimated for May 2016.
On September 15, 2015, the team successfully completed the ground mobility demonstration, proving the ability to accommodate various combinations of 463L pallets, aero-medical patient support pallets, and passenger pallets. The ability to use material handling equipment and processes employed by Air Mobility Command (AMC) on other airlift aircraft was also demonstrated. With only minor issues encountered, KC-46A meets its cargo handling and interior configuration requirements for MS C.
To date, 10 of 10 Live Fire Test & Evaluation (LFT&E) ballistic test series are complete. The final phase of the tenth ballistic test series completed on December 21, 2015 at China Lake, CA. The combat damage flight simulation exercises for score were completed on December 10, 2015 to support the overall survivability analysis of the KC-46A which will be captured in the LFT&E Consolidated Final Report.
As of February 22, 2016, the build status for EMD-3 and EMD-4 are 96% and 99%, respectively. EMD-4 has completed fuel dock testing and 98% of the functional testing. Currently, EMD-4 is performing pre-flight and classified testing in preparation for first flight. EMD-3 continues to make progress, completing 99% of the electrical connections and 90% of the functional testing. Additionally, EMD-3 was rolled to paint on February 21, 2016.
The Maintenance Training System Source Selection Plan was signed on April 10, 2015, and the Request For Proposal was finalized and released on April 10, 2015. Proposals were received on June 8, 2015, and source selection is ongoing.
The Aircrew Training System (ATS) team continues device engineering and manufacturing development. The ATS Program Office and FlightSafety Services Corporation conducted a Critical Design Review (CDR) Technical Interchange Meeting to define initial Increment 1 system Ready-For-Training (RFT) criteria. Progress continues on entry criteria for Increment 1 System CDR (projected mid-2016) and RFT (projected mid-2017). In addition, the first ATS production option was exercised to help mitigate predicted student production/throughput constraints in support of AMC’s Initial Operational Capability declaration.
The final report of the Product Support Business Case Analysis (BCA) was delivered in August 2015. The Independent Logistics Assessment (ILA) was completed in February 2015 and the last of five minor findings was closed on May 7, 2015; there were no major findings. Both the BCA and ILA will be incorporated into the Life Cycle Sustainment Plan in time to support MS C.
The Program Office has four CY 2016 focus areas: (1) completing all MS C entrance criteria and initiating Low Rate Initial Production, (2) continuing specification verification testing, (3) continuing FAA qualification and certification testing, and (4) initiating the implementation of the long-term sustainment strategy. Additionally, the KC-46A Program Office will continue to focus attention on maintaining program stability and returning margin back into the schedule for an on-time RAA declaration. Program execution will be carefully managed to ensure Boeing delivers what is required by the contract and the Government maintains the competitively-negotiated program cost, schedule, and performance baselines.
There are no significant software-related issues with this program at this time.
History of Significant Developments Since Program Initiation
General
February 23, 2011: The Under Secretary of Defense for Acquisition, Technology, and Logistics (USD(AT&L)) conducted a successful Milestone B (MS B) Defense Acquisition Board (DAB).
February 24, 2011: The USD(AT&L) signed the Acquisition Program Baseline (APB) reflecting the MS B approval.
February 24, 2011: The Boeing Company was awarded the KC-46A contract. The Fixed-Price Incentive Firm (FPIF) contract was awarded for the Engineering and Manufacturing Development program phase, with Firm-Fixed-Price contract options for Low Rate Initial Production Lots 1 and 2, and Not-to-Exceed contract options with Economic Price Adjustment

## Table 9
for Full Rate Production Lots 3 through 13.
August 24, 2011: The KC-46A Program Office and Boeing successfully concluded a comprehensive Integrated Baseline Review (IBR). The IBR approved a well-understood contract technical, cost, and schedule baseline from which the Government can measure and closely manage Boeing’s progress during contract execution.
November 2011: The KC-46A Program Office and Boeing successfully concluded the System Functional Review (SFR). The KC-46A SFR assessed the allocation and traceability of all program requirements from the System Specification to lower-level hardware and software requirements.
December 2011: Boeing conducted a non-contractual KC-46A Firm Configuration review—an internal Boeing commercial best practice. The KC-46A Firm Configuration validated that the aircraft configuration is sufficiently mature and stable to initiate detailed design of the militarized KC-46A tanker.
April 27, 2012: The KC-46A Preliminary Design Review (PDR) was successfully completed. The Government and Boeing successfully completed the first step of a two-step PDR process on March 21 -22, 2012, which consisted of a detailed review of the 89 contractual entrance criteria to PDR. The second step, conducted April 23 - 27 2012, consisted of a detailed review of the eight exit criteria and completion of all subsystem PDRs to Government satisfaction.
May 28, 2012: The Program Executive Officer (PEO) signed the Post-PDR Report.
June 20, 2012: Deputy Assistant Secretary of Defense, Systems Engineering (DASD/SE) validated successful completion of PDR.
May 1, 2013: The KC-46A Aircrew Training System (ATS) contract was awarded to FlightSafety Services Corporation.
June 26 - 28, 2013: The KC-46A ATS Program conducted a Program Startup Workshop with the assistance from Defense Acquisition University at Wright-Patterson Air Force Base, Ohio.
July 8 - 10, 2013: The KC-46A Program successfully completed the planned Weapon System Critical Design Review (CDR) at Boeing’s Harbour Pointe facility. Overall design maturity was demonstrated to be at a high level, consistent with the commercial derivative nature of the design approach. All action items were complete, and the Weapon System CDR was officially closed on August 21, 2013, one month ahead of the contractual requirement of September 24, 2013.
June 11, 2013: The KC-46A Operational Assessment-1 (OA-1) report was published, culminating a 7.5 month effort to assess the current weapon system design for CDR and IOT&E for readiness. The Air Force Operational Test and Evaluation Center assessment of the KC-46A confirmed that the program was on track to meet effectiveness, suitability, and mission capability requirements.
June 26, 2013: The EMD-1 aircraft began assembly, followed by EMD-2 on August 19, 2013, EMD-3 on October 17, 2013, and EMD-4 on January 16, 2014.
September 23 - 27, 2013: The KC-46A ATS conducted a System Requirement Review and SFR.
February 24, 2014: The KC-46A Program Office received confirmation that the Senate Committee on Appropriations approved a below threshold reprogramming request in the amount of $8.6M to purchase land necessary for the Tinker Air Force Base, Oklahoma weapon system support efforts. This request resulted in FY 2012 MILCON (3300) funds being reprogrammed into the KC-46A funding profile.
December 17, 2014: KC-46A Production Spares, Support Equipment, and Interim Contractor Support efforts awarded.
December 28, 2014: Successful first flight of the EMD-1 aircraft. This significant event started the flight test phase of the KC
-46A program.

## Table 10
September 25, 2015: EMD-2 completed a major milestone, KC-46A First Flight.
November 8 - 9, 2015: EMD-2 deployed the boom and both drogue systems in flight for the first time.
January 24, 2016: EMD-2 completed the first KC-46A aerial refueling by offloading 1,600 pounds of fuel to an F-16C.
February 10, 2016: EMD-2 completed fuel transfer with F/A-18 aircraft.
February 13, 2016: EMD-2 completed KC-10 fuel transfer conducted with KC-46A as a receiver.

## Table 11
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
The KC-46A previously reported an O&S cost growth breach in the December 2012 SAR. The breach was the result of Air Mobility Command’s desire to maximize the benefits of the KC-46A capabilities and leverage that capability across the total force through increased flight hours and increased crew ratios.
The Program will continue to carry this O&S cost growth until the next Milestone is reached and a new APB is established. The Air Force has committed to staying within Total Obligation Authority during the transition from the KC-135 to the KC-46A aircraft.
On January 7, 2015 a Program Deviation Report outlining the above was submitted.
Nunn-McCurdy Breaches

## Table 12
Schedule
(Ch-1)
(Ch-2)
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B and Contract Award | Feb 2011 | Feb 2011 | Feb 2011 | Feb 2011
Milestone C | Aug 2015 | Aug 2015 | Aug 2016 | Apr 2016
IOT&E Start | May 2016 | May 2016 | May 2017 | Apr 2017
RAA | Aug 2017 | Aug 2017 | Aug 2018 | Aug 2017
FRP Decision | Jun 2017 | Jun 2017 | Jun 2018 | Mar 2018
(Ch-3)
Change Explanations
(Ch-1) The current estimate for Milestone C has changed from September 2015 to April 2016 due to schedule rebaseline. (Ch-2) The current estimate for IOT&E Start has changed from October 2016 to April 2017 due to schedule rebaseline. (Ch-3) The current estimate for FRP Decision has changed from September 2017 to March 2018 due to schedule rebaseline.
Notes
IOT&E start represents the beginning of dedicated IOT&E, which will commence upon OSD approval of the Operational Test Readiness Review.
The Boeing contractual RAA date is directed to be no later than 78 months after contract award.
Acronyms and Abbreviations
IOT&E - Initial Operational Test and Evaluation RAA - Required Assets Available

## Table 13
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Tanker Air Refueling Capability
The aircraft should be | The aircraft should be | The aircraft shall be | TBD | Will meet or exceed
capable of accomplish- | capable of | capable of accomplish |  | Current APB
ing air refueling of all | accomplish-ing air | -ing air refueling of all |  | Threshold. The aircraft
current and | refueling of all current | current and |  | shall be capable of
programmed tilt rotor | and programmed tilt | programmed fixed- |  | accomplish-ing air
receiver aircraft in | rotor receiver aircraft | wing receiver aircraft |  | refueling of all current
accordance with | in accordance with | in accordance with |  | and programmed fixed
technical guidance and | technical guidance | technical guidance |  | -wing receiver aircraft
STANAGs using | and STANAGs using | and STANAGs using |  | in accordance with
current procedures and | current procedures | current procedures |  | technical guidance and
refueling airspeeds | and refueling | and refueling |  | STANAGs using
with no modification to | airspeeds with no | airspeeds with no |  | current procedures
existing receiver air | modification to | modification to |  | and refueling
refueling equipment | existing receiver air | existing receiver air |  | airspeeds with no
and no restrictions to | refueling equipment | refueling equipment |  | modification to existing
the refueling envelope | and no restrictions to | and no restrictions to |  | receiver air refueling
at its maximum inflight | the refueling envelope | the refueling envelope. |  | equipment and no
gross weight. While | at its maximum inflight | The aircraft shall be |  | restrictions to the
engaged, the KC-X | gross weight. While | able to effectively |  | refueling envelope.
should be capable of | engaged, the KC-X | conduct (non-simultan |  | The aircraft shall be
maneuvering | should be capable of | -eously) both boom |  | able to effectively
throughout the entire | maneuvering | and drogue air |  | conduct (non-simultan
refueling envelope, in | throughout the entire | refuelings on the |  | -eously) both boom
accordance with | refueling envelope, in | same mission. While |  | and drogue air
applicable air refueling | accordance with | engaged, the KC-X |  | refuelings on the same
manuals and standard | applicable air refueling | shall be capable of |  | mission. While
agreements, of any | manuals and standard | maneuvering |  | engaged, the KC-X
compatible current and | agreements, of any | throughout the entire |  | shall be capable of
programmed tilt rotor | compatible current | refueling envelope, in |  | maneuvering
receiver aircraft. | and programmed tilt | accordance with |  | throughout the entire
| rotor receiver aircraft. | applicable air refueling |  | refueling envelope, in
|  | manuals and standard |  | accordance with
|  | agreements, of any |  | applicable air refueling
|  | compatible current |  | manuals and standard
|  | and programmed fixed |  | agreements, of any
|  | wing receiver aircraft. |  | compatible current and
programmed fixed
wing receiver aircraft.
Fuel Offload versus Radius
The aircraft should be | The aircraft should be | The aircraft shall be | TBD | Will meet or exceed
capable of exceeding | capable of exceeding | capable, as a |  | Current APB
the offload versus | the offload versus | minimum, of an |  | Objective. The aircraft
radius as depicted in | radius as depicted in | offload versus radius |  | should be capable of

## Table 14
Figure 6.1. | Figure 6.1. | as depicted in Figure 6.1. |  | exceeding the offload versus radius as depicted in Figure 6.1.
Civil/Military CNS/ATM
Aircraft shall be | Aircraft shall be | Aircraft shall be | TBD | Will meet or exceed
capable of worldwide | capable of worldwide | capable of worldwide |  | Current APB
flight operations at all | flight operations at all | flight operations at all |  | Objective. Aircraft shall
times in all civil and | times in all civil and | times in all civil and |  | be capable of
military airspace at | military airspace at | military airspace at |  | worldwide flight
time of aircraft delivery, | time of aircraft | time of aircraft |  | operations at all times
including known future | delivery, including | delivery, including |  | in all civil and military
CNS/ATM require- | known future | known future |  | airspace at time of
ments, with redundant | CNS/ATM require- | CNS/ATM require- |  | aircraft delivery,
systems. Capability to | ments, with redundant | ments, with redundant |  | including known future
inhibit CNS/ATM | systems. Capability to | systems. Capability to |  | CNS/ATM require-
emissions and prohibit | inhibit CNS/ATM | inhibit CNS/ATM |  | ments, with redundant
transmission of | emissions and | emissions and prohibit |  | systems. Capability to
CNS/ATM-related data | prohibit transmission | transmission of |  | inhibit CNS/ATM
accumulated during the | of CNS/ATM-related | CNS/ATM-related data |  | emissions and prohibit
inhibited portion of the | data accumulated | accumulated during |  | transmission of
mission. Civil ATC data | during the inhibited | the inhibited portion of |  | CNS/ATM-related data
link media for LOS and | portion of the mission. | the mission. Civil ATC |  | accumulated during
BLOS communica- | Civil ATC data link | data link media for |  | the inhibited portion of
tions. | media for LOS and | LOS and BLOS |  | the mission. Civil ATC
| BLOS communica- | communica-tions. |  | data link media for
| tions. |  |  | LOS and BLOS
communica-tions.
Airlift Capability
The aircraft shall be | The aircraft shall be | The aircraft shall be | Completed the | Will meet or exceed
capable of efficiently | capable of efficiently | capable of efficiently | ground mobility | Current APB
transporting equipment | transporting | transporting | demonstration, | Objective. The aircraft
and personnel and fit | equipment and | equipment and | proving the ability | shall be capable of
seamlessly into the | personnel and fit | personnel and fit | to accommodate | efficiently transporting
Defense Transporta- | seamlessly into the | seamlessly into the | various | equipment and
tion System. The | Defense Transporta- | Defense Transporta- | configurations of | personnel and fit
aircraft’s entire main | tion System. The | tion System. The | 463L pallets, aero- | seamlessly into the
cargo deck must be | aircraft’s entire main | aircraft’s entire main | medical patient | Defense Transporta-
convertible to an all | cargo deck must be | cargo deck must be | support pallets, | tion System. The
cargo configuration that | convertible to an all | convertible to an all | and passenger | aircraft’s entire main
accommo-dates 463L | cargo configurat-ion | cargo configurat-ion | pallets. The ability | cargo deck must be
pallets, an all | that accommo-dates | that accommo-dates | to use material | convertible to an all
passenger | 463L pallets, an all | 463L pallets, an all | handling equipment | cargo configura-tion
configuration (plus | passenger | passenger | and processes | that accommo-dates
baggage) (or equivalent | configuration (plus | configuration (plus | employed by AMC | 463L pallets, an all
AE capability to include | baggage) (or | baggage) (or | on other airlift | passenger
ambulatory and/or | equivalent AE | equivalent AE | aircraft was also | configuration (plus
patient support pallets), | capability to include | capability to include | completed. With | baggage) (or
and must optimize a | ambulatory and/or | ambulatory and/or | only minor issues | equivalent AE
full range of palletized | patient support | patient support | encountered, KC- | capability to include
cargo, passengers, | pallets), and must | pallets), and must | 46A meets its | ambulatory and /or
and AE configurat-ions | optimize a full range | optimize a full range of | cargo handling and | patient support
that fully and efficiently | of palletized cargo, | palletized cargo, | interior | pallets), and must

## Table 15
utilize all available main | passengers, and AE | passengers, and AE | configuration | optimize a full range of
deck space. | configurat-ions that | configurat-ions that | requirements for | palletized cargo,
| fully and efficiently | fully and efficiently | MS C. | passengers, and AE
| utilize all available | utilize all available | Demonstrated | configura-tions that
| main deck space. | main deck space. | ability to use | fully and efficiently
|  |  | material handling | utilize all available
|  |  | equipment and | main deck space.
processes
employed by AMC
on other airlift
aircraft.
Receiver Air Refueling Capability
The aircraft must be | The aircraft must be | The aircraft must be | TBD | Will meet or exceed
capable of receiver air | capable of receiver air | capable of receiver air |  | Current APB
refueling (IAW current | refueling (IAW current | refueling (IAW current |  | Objective. The aircraft
technical directives) to | technical directives) to | technical directives) |  | must be capable of
its maximum inflight | its maximum inflight | from any compatible |  | receiver air refueling
gross weight from any | gross weight from any | tanker aircraft using |  | (IAW current technical
compatible tanker | compatible tanker | current air refueling |  | directives) to its
aircraft using current | aircraft using current | procedures. |  | maximum inflight
air refueling | air refueling |  |  | gross weight from any
procedures. | procedures. |  |  | compatible tanker
aircraft using current
air refueling
procedures.
Force Protection
Aircraft shall be able to | Aircraft shall be able | Aircraft shall be able | TBD | Will meet or exceed
operate in chemical | to operate in chemical | to operate in chemical |  | Current APB
and biological | and biological | and biological |  | Objective. Aircraft shall
environments | environments | environments |  | be able to operate in
chemical and
biological
environments
Net-Ready
The system must fully | The system must fully | The system must fully | TBD | Will meet or exceed
support execution of all | support execution of | support execution of |  | Current APB
operational activities | all operational | joint critical |  | Objective. The system
identified in the | activities identified in | operational activities |  | must fully support
applicable joint and | the applicable joint | identified in the |  | execution of all
system integrated | and system integrated | applicable joint and |  | operational activities
architectures and the | architectures and the | system integrated |  | identified in the
system must satisfy | system must satisfy | architectures and the |  | applicable joint and
the technical | the technical | system must satisfy |  | system integrated
requirements for Net- | requirements for Net- | the technical |  | architectures and the
Centric military | Centric military | requirements for |  | system must satisfy
operations to include: | operations to include: | transition to Net- |  | the technical
1) DISR-mandated GIG | 1) DISR-mandated | Centric military |  | requirements for Net-
IT standards and | GIG IT standards and | operations to include: |  | Centric military
profiles identified in the | profiles identified in | 1) DISR-mandated |  | operations to include:
TV-1, 2) DISR- | the TV-1, 2) DISR- | GIG IT standards and |  | 1) DISR-mandated
mandated GIG KIPs | mandated GIG KIPs | profiles identified in |  | GIG IT standards and
identified in the KIP | identified in the KIP | the TV-1, 2) DISR |  | profiles identified in the

## Table 16
declaration table, 3) | declaration table, 3) | mandated GIG KIPs |  | TV-1, 2) DISR-
NCOW RM Enterprise | NCOW RM Enterprise | identified in the KIP |  | mandated GIG KIPs
Services, 4) IA | Services, 4) IA | declaration table, 3) |  | identified in the KIP
requirements including | requirements | NCOW RM Enterprise |  | declaration table, 3)
availability, integrity, | including availability, | Services, 4) IA |  | NCOW RM Enterprise
authenticat-ion, | integrity, authenticat- | requirements |  | Services, 4) IA
confidential-ity, and non | ion, confidential-ity, | including availability, |  | requirements including
-repudiation, and | and non-repudiation, | integrity, authenticat- |  | availability, integrity,
issuance of an ATO by | and issuance of an | ion, confidential-ity, |  | authentica-tion,
the DAA, and 5) | ATO by the DAA, and | and non-repudiation, |  | confidentia-lity, and
Operationally effective | 5) Operationally | and issuance of an |  | non-repudiation, and
information exchanges; | effective information | IATO by the DAA, and |  | issuance of an ATO by
and mission critical | exchanges; and | 5) Operationally |  | the DAA, and 5)
performance and IA | mission critical | effective information |  | Operationally effective
attributes, data | performance and IA | exchanges; and |  | information
correctness, data | attributes, data | mission critical |  | exchanges; and
availability, and | correctness, data | performance and IA |  | mission critical
consistent data | availability, and | attributes, data |  | performance and IA
processing specified in | consistent data | correctness, data |  | attributes, data
the applicable joint and | processing specified | availability, and |  | correctness, data
system integrated | in the applicable joint | consistent data |  | availability, and
architecture views. | and system integrated | processing specified |  | consistent data
| architecture views. | in the applicable joint |  | processing specified in
|  | and system integrated |  | the applicable joint and
|  | architecture views. |  | system integrated
architecture views.
Survivability
Aircraft SPM. Tanker | Aircraft SPM. Tanker | Aircraft SPM. Tanker | TBD | Will meet or exceed
aircraft shall be able to | aircraft shall be able | aircraft shall be able to |  | Current APB
operate in hostile | to operate in hostile | operate in hostile |  | Threshold. Aircraft
environments as | environments as | environments as |  | SPM. Tanker aircraft
discussed in Section 4 | discussed in Section | discussed in Section |  | shall be able to
and AFTTP 3-3.22B. | 4 and AFTTP 3-3.22B. | 4 and AFTTP 3-3.22B. |  | operate in hostile
SPM shall provide | SPM shall provide | SPM shall provide |  | environments as
automated protection | automated protection | automated protection |  | discussed in Section 4
against IR threats as | against IR threats as | against IR threats as |  | and AFTTP 3-3.22B.
described in AMC | described in AMC | described in AMC |  | SPM shall provide
Annex to LAIRCM ORD | Annex to LAIRCM | Annex to LAIRCM |  | automated protection
314-92 dated January | ORD 314-92 dated | ORD 314-92 dated |  | against IR threats as
25, 2001. SPM shall | January 25, 2001. | January 25, 2001. |  | described in AMC
provide automated | SPM shall provide | SPM shall provide |  | Annex to LAIRCM
protection against RF | automated protection | automated protection |  | ORD 314-92 dated
threats as described in | against RF threats as | against RF threats as |  | January 25, 2001.
the ASACM CDD, May | described in the | described in the |  | SPM shall provide
22, 2006, with the | ASACM CDD, May 22, | ASACM CDD, May 22, |  | automated protection
exception of Reduction | 2006, with the | 2006, with the |  | against RF threats as
in Lethality values in | exception of | exception of |  | described in the
Table 28. The aircraft | Reduction in Lethality | Reduction in Lethality |  | ASACM CDD, May 22,
system shall support | values in Table 28. | values in Table 28. |  | 2006, with the
use of existing night | The aircraft system | The aircraft system |  | exception of Reduction
vision devices and | shall support use of | shall support use of |  | in Lethality values in
laser eye protection | existing night vision | existing night vision |  | Table 28. The aircraft
devices. The aircraft | devices and laser eye | devices and laser eye |  | system shall support

## Table 17
shall be capable of | protection devices. | protection devices. |  | use of existing night
takeoff, landing, and air | The aircraft shall be | The aircraft shall be |  | vision devices and
refueling, as a tanker | capable of takeoff, | capable of takeoff, |  | laser eye protection
and receiver in an NVIS | landing, and air | landing, and air |  | devices. The aircraft
environment. KC-X | refueling, as a tanker | refueling, as a tanker |  | shall be capable of
must be capable of | and receiver in an | and receiver in an |  | takeoff, landing, and air
flying tanker tactical | NVIS environment. KC | NVIS environment. KC |  | refueling, as a tanker
profiles as specified in | -X must be capable of | -X must be capable of |  | and receiver in an
MCM 3-1, Vol 22, AF | flying tanker tactical | flying tanker tactical |  | NVIS environment. KC
Tactics, Training, | profiles as specified in | profiles as specified in |  | -X must be capable of
Procedures, June | MCM 3-1, Vol 22, AF | MCM 3-1, Vol 22, AF |  | flying tanker tactical
2003. Aircraft shall | Tactics, Training, | Tactics, Training, |  | profiles as specified in
have the capability to | Procedures, June | Procedures, June |  | MCM 3-1, Vol 22, AF
receive off-board | 2003. Aircraft shall | 2003. Aircraft shall |  | Tactics, Training,
situational awareness | have the capability to | have the capability to |  | Procedures, June
data, correlate this data | receive off-board | receive off-board |  | 2003. Aircraft shall
with on-board sensor | situational awareness | situational awareness |  | have the capability to
data, display battle- | data, correlate this | data, correlate this |  | receive off-board
space information to | data with on-board | data with on-board |  | situational awareness
provide situational | sensor data, display | sensor data, display |  | data, correlate this
awareness, and assist | battle-space | battle-space |  | data with on-board
in using counter- | information to provide | information to provide |  | sensor data, display
measures and | situational awareness, | situational awareness, |  | battle-space
defensive systems to | and assist in using | and assist in using |  | information to provide
avoid potential threats | counter-measures | counter-measures |  | situational awareness,
as discussed in the | and defensive | and defensive |  | and assist in using
ASACM CDD. EMP | systems to avoid | systems to avoid |  | counter-measures and
protection for all | potential threats as | potential threats as |  | defensive systems to
mission components. | discussed in the | discussed in the |  | avoid potential threats
| ASACM CDD. EMP | ASACM CDD. The KC |  | as discussed in the
| protection for all | -X fleet shall have |  | ASACM CDD. The KC
| mission components. | EMP protection for |  | -X fleet shall have EMP
|  | flight-critical aircraft |  | protection for flight-
|  | systems. |  | critical aircraft
systems.
Simultaneous Multi-Point Refuelings
The aircraft shall be | The aircraft shall be | The aircraft shall be | TBD | Will meet or exceed
provisioned (including | provisioned (including | provisioned (including |  | Current APB
structural modificat- | structural modificat- | structural modificat- |  | Objective. The aircraft
ions, plumbing, | ions, plumbing, | ions, plumbing, |  | shall be provisioned
electrical, etc.) for | electrical, etc.) for | electrical, etc.) for |  | (including structural
simultaneous multi- | simultaneous multi- | simultaneous multi- |  | modifica-tions,
point drogue refueling. | point drogue refueling. | point drogue refueling. |  | plumbing, electrical,
etc.) for simultaneous
multi-point drogue
refueling.
Operational Availability
Operational availability | Operational availability | Operational availability | TBD | Will meet or exceed
shall be not less than | shall be not less than | shall be not less than |  | APB Objective.
89%. | 89%. | 80%. |  | Operational availability
shall be not less than
89%.

## Table 18
Mission Reliability
Break Rate shall be | Break Rate shall be | Break Rate shall be | TBD | Will meet or exceed
equal to or better than | equal to or better than | equal to or better than |  | Current APB
the 2006 KC-10 Six | the 2006 KC-10 Six | the 2006 KC-10 Six |  | Objective. Break Rate
Sigma mean BR of 1.3 | Sigma mean BR of | Sigma mean BR of |  | shall be equal to or
(breaks per 100 | 1.3 (breaks per 100 | 1.3 (breaks per 100 |  | better than the 2006
sorties). | sorties). | sorties). |  | KC-10 Six Sigma
mean BR of 1.3
(breaks per 100
sorties).
Requirements Reference
Capability Development Document (CDD) Version 7.0 dated December 27, 2006
Change Explanations
None
Notes
Tanker Air Refueling Capability: The KPP objective includes the KPP threshold requirement. Therefore, the KPP objective requires air refueling of all current and programmed fixed-wing receiver aircraft and air refueling of all current and programmed tilt rotor receiver aircraft. The ability to refuel at maximum inflight gross weight portion of this KPP
objective was not included as one of the contractually-required 372 mandatory requirements. Therefore, the KC-46A EMD contract does not require the contractor to meet this portion of the objective.
Fuel Offload versus Radius: Figure 6.1, as referenced in the objective and threshold values, is located in the KC-X CDD.
Survivability: Section 4, as referenced in the objective and threshold values, is located in the KC-X CDD. The Electromagnetic Pulse protection for all mission components portion of this KPP objective was not included as one of the contractually-required 372 mandatory requirements. Therefore, the KC-46A EMD contract does not require the contractor to meet this portion of the objective.
OA: OA equals the TAI less the number of depot possessed aircraft (including programmed depot maintenance and unscheduled depot maintenance) less the number of aircraft that are not mission capable divided by TAI. OA as stated in the CDD is equivalent to and meets the requirement for Materiel Availability as required by the Manual for the Operation of the JCIDS.
Mission Reliability: BR is defined in Air Force Instruction 21-101 and is the percentage of aircraft that land in “Code-3,” or “Alpha-3” for Mobility AF, status. BR (%) equals number of sorties that land in “Code-3” divided by total sorties flown times
100. Mission Reliability as stated in the CDD meets the requirement for Materiel Reliability as required by the Manual for the Operation of JCIDS.

## Table 19
Acronyms and Abbreviations
AE - Aeromedical Evacuation AF - Air Force
AFTTP - Air Force Tactics, Techniques, and Procedures AMC - Air Mobility Command
APB - Acquistion Program Baseline
ASACM - Advanced Situational Awareness and Countermeasures ATC - Air Traffic Control
ATO - Approval to Operate BLOS - Beyond Line of Sight BR - Break Rate
CDD - Capability Development Document
CNS/ATM - Communication Navigation Surveillance/Air Traffic Management DAA - Designated Approval Authority
DISR - DoD IT Standards Registry
EMD - Engineering and Manufacturing Development EMP - Electromagnetic Pulse
GIG - Global Information Grid IA - Information Assurance
IATO - Interim Authority to Operate IAW - In Accordance With
IR - Infrared
IT - Information Technology
JCIDS - Joint Capabilities Integration and Development System KIP - Key Interface Profile
KPP - Key Performance Parameter
LAIRCM - Large Aircraft Infrared Countermeasures LOS - Line of Sight
MCM - Multi-Command Manual
NCOW RM - Net Centric Operations Warfare Reference Model NVIS - Night Vision and Imaging Systems
OA - Operational Availability
ORD - Operational Requirements Document RF - Radio Frequency
SPM - Self-Protection Measures STANAGs - Standard Agreements TAI - Total Aircraft in the Inventory TBD - To Be Determined
TV - Technical View Vol - Volume

## Table 20
Track to Budget
RDT&E
Appn |  | BA | PE
Air Force | 3600 07 |  | 0401221F
| Project |  | Name
| 674927 |  | KC-135 Replacement Tanker |  | (Sunk)
Air Force | 3600 05 |  | 0605221F
| Project |  | Name
| 655271 |  | KC-46 RDT&E
Procurement
Appn |  | BA | PE
Air Force | 3010 06 |  | 0401221F
| Line Item |  |  | Name
| 999 |  | Initial Spares
Air Force | 3010 02 |  | 0401221F
| Line Item |  |  | Name
| KC046A |  | KC-46A Tanker
Notes
In the FY 2016 PB, Procurement funds were realigned from BA 02 to BA 06. A new funding line for BA 06 was added to the Track to Budget.
MILCON
Appn |  | BA | PE
Air Force | 3300 01 |  | 0401221F
| Project |  | Name
| VARIOUS |  | KC-46, MILCON
Air Force | 3730 01 |  | 0501221F
| Project |  | Name
| VARIOUS |  | KC-46A Air Force Reserve (AFR) MILCON
Air Force | 3730 01 |  | 0502576F
| Project |  | Name
| VARIOUS |  | Facilities Restoration and Modernization - AFR (Shared)
Air Force | 3830 01 |  | 0501413F
| Project |  | Name
| VARIOUS |  | KC-46, Air National Guard (ANG), MILCON
Notes
FY 2017 and FY 2018 Air Force Reserve MILCON for the KC46A program is contained within PE 050221F in the FY 2017 FYDP database, but is incorrectly associated with PE 0502576F in the PB17 budget exhibit.

## Table 21
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2011 $M | [6 empty] | BY 2011 $M |  | TY $M
| SAR Baseline Development Estimate |  |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E |  | 6804.2 |  |  | 6804.2 | 7484.6 |  |  | 5979.4 |  | 7149.6 |  |  | 7149.6 |  | 6259.6
Procurement |  | 33040.3 |  |  | 33040.3 | 36344.3 |  |  | 31371 |  | 40236 |  |  | 40236 |  | 38764.9
Flyaway |  | -- |  |  | -- | -- |  |  | 27214.7 |  | -- |  |  | -- |  | 33723.3
Recurring |  | -- |  |  | -- | -- |  |  | 27214.7 |  | -- |  |  | -- |  | 33723.3
Non Recurring |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support |  | -- |  |  | -- | -- |  |  | 4156.3 |  | -- |  |  | -- |  | 5041.6
Other Support |  | -- |  |  | -- | -- |  |  | 3139.9 |  | -- |  |  | -- |  | 3819.8
Initial Spares |  | -- |  |  | -- | -- |  |  | 1016.4 |  | -- |  |  | -- |  | 1221.8
MILCON |  | 3673.7 |  |  | 3673.7 | 4041.1 |  |  | 2589.7 |  | 4314.6 |  |  | 4314.6 |  | 3187.5
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 43518.2 |  |  | 43518.2 | N/A |  |  | 39940.1 |  | 51700.2 |  |  | 51700.2 |  | 48212
Confidence Level
Confidence Level of cost estimate for current APB: 55%
The Air Force Service Cost Position (SCP) for the KC-46A is at the mean of the cost estimate distribution (in this case the 55 percent confidence level). It takes into consideration all relevant program risks, providing sufficient resources to execute the program under normal conditions encountering average levels of technical, schedule, and programmatic risk and external influence.
Total Quantity
Quantity |  |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  |  | 4 |  |  |  | 4 |  |  |  |  | 4
Procurement |  |  | 175 |  |  |  | 175 |  |  |  |  | 175
Total |  |  | 179 |  |  |  | 179 |  |  |  |  | 179

## Table 22
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 5380 | 592.4 |  | 261.7 |  | 21.2 |  | 4.3 |  | 0 |  | 0 |  | 0 |  | 6259.6
Procurement | 1465.6 | 2403.6 |  | 3056.8 |  | 3150.8 |  | 3216.1 |  | 3233.1 |  | 3292.7 |  | 18946.2 |  | 38764.9
MILCON | 415.3 | 54.5 |  | 136.7 |  | 248.7 |  | 401.5 |  | 25.1 |  | 446.5 |  | 1459.2 |  | 3187.5
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 7260.9 | 3050.5 |  | 3455.2 |  | 3420.7 |  | 3621.9 |  | 3258.2 |  | 3739.2 |  | 20405.4 |  | 48212
PB 2016 Total | 7649 | 3062.6 |  | 3582.5 |  | 3511 |  | 3671.4 |  | 3292.6 |  | 3758.1 |  | 20382.3 |  | 48909.5
Delta | -388.1 | -12.1 |  | -127.3 |  | -90.3 |  | -49.5 |  | -34.4 |  | -18.9 |  | 23.1 |  | -697.5
Funding Notes
The final production for the KC-46A Program is 179 aircraft. Four of these aircraft are funded with RDT&E dollars and the quantities are identified in FY 2011 in the table below, as this is where the contract was awarded. The remaining aircraft are to be purchased using Procurement funds.
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 4 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4
Production | 0 |  | 7 |  | 12 | 15 | 15 |  | 15 |  | 15 |  | 15 |  | 81 |  | 175
PB 2017 Total | 4 |  | 7 |  | 12 | 15 | 15 |  | 15 |  | 15 |  | 15 |  | 81 |  | 179
PB 2016 Total | 4 |  | 7 |  | 12 | 15 | 15 |  | 15 |  | 15 |  | 15 |  | 81 |  | 179
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Table 23
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.2
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.1
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 67.8
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 305.1
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 538.9
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 818.9
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1550.3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1496
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 548.2
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 592.4
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 261.7
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.2
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.3
Subtotal |  | 4 | -- |  | -- |  | -- |  | -- |  | -- |  | 6259.6

## Table 24
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2011 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.4
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.9
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 71.6
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.2
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 307.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 533.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 796.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1483.5
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1411.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 512.2
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 545.3
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 236.6
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.8
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.7
Subtotal |  | 4 | -- |  | -- |  | -- |  | -- |  | -- |  | 5979.4

## Table 25
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | 9.5 |  | 9.5
2015 |  | 7 | 1138 |  | -- |  | -- |  | 1138 |  | 318.1 |  | 1456.1
2016 |  | 12 | 2070.4 |  | -- |  | -- |  | 2070.4 |  | 333.2 |  | 2403.6
2017 |  | 15 | 2553.3 |  | -- |  | -- |  | 2553.3 |  | 503.5 |  | 3056.8
2018 |  | 15 | 2692.9 |  | -- |  | -- |  | 2692.9 |  | 457.9 |  | 3150.8
2019 |  | 15 | 2639.8 |  | -- |  | -- |  | 2639.8 |  | 576.3 |  | 3216.1
2020 |  | 15 | 2643.4 |  | -- |  | -- |  | 2643.4 |  | 589.7 |  | 3233.1
2021 |  | 15 | 2824.2 |  | -- |  | -- |  | 2824.2 |  | 468.5 |  | 3292.7
2022 |  | 15 | 2987 |  | -- |  | -- |  | 2987 |  | 348.2 |  | 3335.2
2023 |  | 15 | 3008.1 |  | -- |  | -- |  | 3008.1 |  | 395.4 |  | 3403.5
2024 |  | 15 | 3060.1 |  | -- |  | -- |  | 3060.1 |  | 386.1 |  | 3446.2
2025 |  | 15 | 3190.1 |  | -- |  | -- |  | 3190.1 |  | 332.1 |  | 3522.2
2026 |  | 15 | 3310.5 |  | -- |  | -- |  | 3310.5 |  | 279.1 |  | 3589.6
2027 |  | 6 | 1605.5 |  | -- |  | -- |  | 1605.5 |  | 44 |  | 1649.5
Subtotal |  | 175 | 33723.3 |  | -- |  | -- |  | 33723.3 |  | 5041.6 |  | 38764.9

## Table 26
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | BY 2011 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | 8.8 |  | 8.8
2015 |  | 7 | 1037.8 |  | -- |  | -- |  | 1037.8 |  | 290.1 |  | 1327.9
2016 |  | 12 | 1854.1 |  | -- |  | -- |  | 1854.1 |  | 298.4 |  | 2152.5
2017 |  | 15 | 2243.3 |  | -- |  | -- |  | 2243.3 |  | 442.3 |  | 2685.6
2018 |  | 15 | 2319.8 |  | -- |  | -- |  | 2319.8 |  | 394.5 |  | 2714.3
2019 |  | 15 | 2229.5 |  | -- |  | -- |  | 2229.5 |  | 486.7 |  | 2716.2
2020 |  | 15 | 2188.8 |  | -- |  | -- |  | 2188.8 |  | 488.2 |  | 2677
2021 |  | 15 | 2292.6 |  | -- |  | -- |  | 2292.6 |  | 380.3 |  | 2672.9
2022 |  | 15 | 2377.2 |  | -- |  | -- |  | 2377.2 |  | 277.1 |  | 2654.3
2023 |  | 15 | 2347.1 |  | -- |  | -- |  | 2347.1 |  | 308.5 |  | 2655.6
2024 |  | 15 | 2340.8 |  | -- |  | -- |  | 2340.8 |  | 295.4 |  | 2636.2
2025 |  | 15 | 2392.4 |  | -- |  | -- |  | 2392.4 |  | 249.1 |  | 2641.5
2026 |  | 15 | 2434 |  | -- |  | -- |  | 2434 |  | 205.2 |  | 2639.2
2027 |  | 6 | 1157.3 |  | -- |  | -- |  | 1157.3 |  | 31.7 |  | 1189
Subtotal |  | 175 | 27214.7 |  | -- |  | -- |  | 27214.7 |  | 4156.3 |  | 31371

## Table 27
Cost Quantity Information 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2011 $M
2014 | -- | --
2015 | 7 | 1037.8
2016 | 12 | 1854.1
2017 | 15 | 2243.2
2018 | 15 | 2319.8
2019 | 15 | 2229.5
2020 | 15 | 2188.8
2021 | 15 | 2292.6
2022 | 15 | 2377.2
2023 | 15 | 2347.1
2024 | 15 | 2340.9
2025 | 15 | 2392.4
2026 | 15 | 2434
2027 | 6 | 1157.3
Subtotal | 175 | 27214.7

## Table 28
Annual Funding 3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | TY $M
Total Program
2010 | 1.6
2011 | 2.6
2012 | 8.8
2013 | --
2014 | 215
2015 | 145.4
2016 | 51.7
2017 | 37.2
2018 | 242.3
2019 | 401.5
2020 | 25.1
2021 | 446.5
2022 | 279.4
2023 | 368.2
2024 | 386.3
2025 | 273.4
2026 | 103.7
2027 | 37.3
2028 | 10.9
Subtotal | 3036.9

## Table 29
Annual Funding 3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | BY 2011 $M
Total Program
2010 | 1.6
2011 | 2.5
2012 | 8.4
2013 | --
2014 | 197.8
2015 | 131.6
2016 | 45.9
2017 | 32.4
2018 | 207.1
2019 | 336.4
2020 | 20.6
2021 | 359.6
2022 | 220.6
2023 | 285
2024 | 293.1
2025 | 203.4
2026 | 75.6
2027 | 26.7
2028 | 7.6
Subtotal | 2455.9

## Table 30
Annual Funding 3830 ¦ MILCON ¦ Military Construction, Air National Guard
Fiscal Year | TY $M
Total Program
2015 | 41.9
2016 | 2.8
2017 | 1.5
Subtotal | 46.2

## Table 31
Annual Funding 3830 ¦ MILCON ¦ Military Construction, Air National Guard
Fiscal Year | BY 2011 $M
Total Program
2015 | 38.3
2016 | 2.5
2017 | 1.3
Subtotal | 42.1

## Table 32
Annual Funding 3730 ¦ MILCON ¦ Military Construction, Air Force Reserve
Fiscal Year | TY $M
Total Program
2017 | 98
2018 | 6.4
Subtotal | 104.4

## Table 33
Annual Funding 3730 ¦ MILCON ¦ Military Construction, Air Force Reserve
Fiscal Year | BY 2011 $M
Total Program
2017 | 86.2
2018 | 5.5
Subtotal | 91.7

## Table 34
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2011-02-24 | 2015-04-30
Approved Quantity | 19 | 34
Reference | Milestone B ADM | DAE Brief
Start Year | 2015 | 2015
End Year | 2016 | 2017
The Current Total LRIP Quantity is more than 10% of the total production quantity and has been increased above the Milestone B ADM approved LRIP quantity of 19 aircraft because a greater quantity is now necessary to achieve a smooth production ramp and avoid production breaks/delays on the way to FRP.
The DAE verbally supported the increase of the approved LRIP quantity from 19 to 34 aircraft. This increase is the result of changing Lot 3 (15 aircraft) from an FRP lot to a LRIP lot.

## Table 35
Foreign Military Sales
Notes
Japan: On October 23, 2015, Japan announced its plan to purchase three KC-46A tankers. Japan's FY 2016 program budget of $185M was approved on December 23, 2015. The KC-46A Program Office anticipates the Letter of Request for case manpower and exportable configuration development in March 2016.
Israel: Israel submitted a request for Pricing and Availability (P&A) for four, six, or eight KC-46A aircraft; initial spares; support equipment; technical orders; mission planning system; and training on September 23, 2015. KC-46A Program Office forwarded P&A information to the Air Force Security Assistance and Cooperation Directorate on December 1, 2015. The Office of Deputy Under Secretary of the Air Force for International Affairs forwarded the response to Israel on December 19, 2015.
Korea: Extension of the October 29, 2014 P&A was provided on January 27, 2015 to facilitate continuation of the Republic of Korea Air Force source selection. On June 30, 2015, Korea selected the Airbus 330 Multi-Role Tanker Transport.
Nuclear Costs
None

## Table 36
Unit Cost
Unit Cost Report
Item |  | BY 2011 $M | BY 2011 $M |  | % Change
|  | Current UCR Baseline (Aug 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 43518.2 |  |  | 39940.1
Quantity | 179 |  |  | 179
Unit Cost | 243.118 |  |  | 223.129 |  | -8.22
Average Procurement Unit Cost
Cost | 33040.3 |  |  | 31371
Quantity | 175 |  |  | 175
Unit Cost | 188.802 |  |  | 179.263 |  | -5.05
Item |  | BY 2011 $M | BY 2011 $M |  | % Change
|  | Original UCR Baseline (Aug 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 43518.2 |  |  | 39940.1
Quantity | 179 |  |  | 179
Unit Cost | 243.118 |  |  | 223.129 |  | -8.22
Average Procurement Unit Cost
Cost | 33040.3 |  |  | 31371
Quantity | 175 |  |  | 175
Unit Cost | 188.802 |  |  | 179.263 |  | -5.05

## Table 37
Unit Cost History
Item | [5 empty] | Date |  |  |  |  | BY 2011 $M | [6 empty] | TY $M
[11 empty] | PAUC |  | APUC |  |  |  |  | PAUC |  |  | APUC
Original APB |  |  | Aug 2011 | [7 empty] | 243.118 |  |  | 188.802 |  |  |  |  | 288.828 |  |  | 229.92
APB as of January 2006 |  |  | N/A | [7 empty] | N/A |  |  | N/A |  |  |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A | [7 empty] | N/A |  |  | N/A |  |  |  |  | N/A |  |  | N/A
Prior APB |  |  | N/A | [7 empty] | N/A |  |  | N/A |  |  |  |  | N/A |  |  | N/A
Current APB |  |  | Aug 2011 | [7 empty] | 243.118 |  |  | 188.802 |  |  |  |  | 288.828 |  |  | 229.92
Prior Annual SAR |  |  | Dec 2014 | [7 empty] | 225.075 |  |  | 179.057 |  |  |  |  | 273.237 |  |  | 222.882
Current Estimate |  |  | Dec 2015 | [7 empty] | 223.129 |  |  | 179.263 |  |  |  |  | 269.341 |  |  | 221.514
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [18 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  |  | Eng |  | Est |  |  | Oth |  | Spt |  | Total
288.828 3.866 0.000 -0.009 0.000 -14.838 0.000 -8.506 -19.487 269.341
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [18 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth |  |  | Spt |  | Total
229.920 3.339 0.000 -0.010 0.000 -3.063 0.000 -8.672 -8.406 221.514

## Table 38
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Feb 2011 | N/A | Feb 2011
Milestone C | N/A | Aug 2015 | N/A | Apr 2016
RAA | N/A | Aug 2017 | N/A | Aug 2017
Total Cost (TY $M) | N/A | 51700.2 | N/A | 48212
Total Quantity | N/A | 179 | N/A | 179
PAUC | N/A | 288.828 | N/A | 269.341

## Table 39
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 7149.6 | 40236 | 4314.6 | 51700.2
Previous Changes
Economic | 22.4 | 888.2 | 126 | 1036.6
Quantity | -- | -- | -- | --
Schedule | -- | -1.7 | -- | -1.7
Engineering | -- | -- | -- | --
Estimating | -595.7 | 262.5 | -1105.7 | -1438.9
Other | -- | -- | -- | --
Support | -6.1 | -2380.6 | -- | -2386.7
Subtotal | -579.4 | -1231.6 | -979.7 | -2790.7
Current Changes
Economic | -15.2 | -303.9 | -25.4 | -344.5
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -296.6 | -798.6 | -122 | -1217.2
Other | -- | -- | -- | --
Support | 1.2 | 863 | -- | 864.2
Subtotal | -310.6 | -239.5 | -147.4 | -697.5
Total Changes | -890 | -1471.1 | -1127.1 | -3488.2
CE - Cost Variance | 6259.6 | 38764.9 | 3187.5 | 48212
CE - Cost & Funding | 6259.6 | 38764.9 | 3187.5 | 48212

## Table 40
Summary BY 2011 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 6804.2 | 33040.3 | 3673.7 | 43518.2
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | 0.3 | -- | -53.4 | -53.1
Engineering | -- | -- | -- | --
Estimating | -542.3 | 172 | -920.6 | -1290.9
Other | -- | -- | -- | --
Support | -8.3 | -1877.4 | -- | -1885.7
Subtotal | -550.3 | -1705.4 | -974 | -3229.7
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -275.3 | -647.7 | -110 | -1033
Other | -- | -- | -- | --
Support | 0.8 | 683.8 | -- | 684.6
Subtotal | -274.5 | 36.1 | -110 | -348.4
Total Changes | -824.8 | -1669.3 | -1084 | -3578.1
CE - Cost Variance | 5979.4 | 31371 | 2589.7 | 39940.1
CE - Cost & Funding | 5979.4 | 31371 | 2589.7 | 39940.1
Previous Estimate: December 2014

## Table 41
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -15.2
Decrease in FY 2014 funding due to Above Threshold Reprogramming to KC-46A Procurement. (Estimating)
-8.9 -9.5
Revised Aircrew Training Systems estimate to reflect updated execution plan. (Estimating) -7.6 -8.1
Decrease in FY 2015 and FY 2016 due to Congressional reduction and efficiency cut. (Estimating)
Increase in Government test costs based on updates to the execution strategy. (Estimating)
-210.0 -225.0
+230.3 +252.4
Decrease in FY 2015 funding due to Small Business Innovation Research. (Estimating) -21.7 -23.2 Decrease in FY 2017 - FY 2019 as a result of DoD budgetary adjustments. (Estimating) -2.6 -2.8
Revised FY 2017 estimate as a result of risk reduction given the program's stable execution to date. (Estimating)
Revised estimate for Maintenance Training Systems to reflect latest execution plan. (Estimating)
Revised POE to reflect program realignments resulting from execution changes. (Estimating)
Revised estimate for Program Management Administration to reflect updates to execution plan and program schedule. (Estimating)
-45.2 -50.0
-13.1 -15.2
-227.6 -248.9
+16.9 +18.5
Adjustment for current and prior escalation. (Estimating) Revised estimate to reflect the application of new outyear escalation indices. (Estimating) Revised estimate for Direct Mission Support based on updates to program schedule. | +11.9 +2.3 +0.8 | +12.7 +2.5 +1.2
(Support)
RDT&E Subtotal | -274.5 | -310.6
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -303.9
Decrease in FY 2017 - FY 2021 as a result of DoD budgetary adjustments. (Estimating) | -104.2 | -123.2
Congressional reduction in FY 2015. (Estimating) | -106.9 | -117.1
Revised POE to reflect program realignments resulting from execution changes. | -655.2 | -829.4
(Estimating)
Adjustment for current and prior escalation. (Estimating) | 22.1 | 24.4
Revised estimate to reflect the application of new outyear escalation indices. (Estimating) | 196.5 | 246.7
Adjustment for current and prior escalation. (Support) | 4.1 | 4.7
Increase in Other Support due to increases in Interim Contractor Support, Depot Standup, | 600.4 | 770.9
and decreases in Aircrew Training Systems, Operational Site Activation, Support Equipment, Program Management Administration, and Mission Support Costs. (Support)
Increase in Initial Spares due to DoD budgetary adjustments and an increase in the estimated spares requirement. (Support)
+79.3 +87.4
Procurement Subtotal +36.1 -239.5
MILCON | $M

## Table 42
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | -25.4
Increase in FY 2011 - FY 2012 funding as a result of reprogramming efforts. (Estimating) |  | 2.1 | 2.2
Decrease in FY 2014 funding as a result of reprogramming efforts. (Estimating) |  | -32.2 | -35
Increase in FY 2017 and FY 2021 funding as a result of Main Operating Base #1 and Flight |  | 7.7 | 9.3
Training Unit projects. (Estimating)
Decrease in FY 2017 - FY 2020 funding as a result of selection of Main Operating Base #3 and associated site survey. (Air Force Reserve Command). (Estimating)
-106.1 -123.9
Adjustment for current and prior escalation. (Estimating) | 3 |  |  | 3.2
Revised estimate to reflect the application of new outyear escalation indices. (Estimating) | 120.8 |  |  | 144.3
Revised estimate to reflect the application of new outyear escalation indices. (Estimating) | -105.3 |  |  | -122.1
MILCON Subtotal | -110 |  |  | -147.4

## Table 43
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: KC-46A Engineering and Manufacturing Development
Contractor: The Boeing Company
Contractor Location: 7755 E Marginal Way S
Seattle, WA 98108-4002
Contract Number: FA8625-11-C-6600
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: February 24, 2011
Definitization Date: February 24, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
4327.3 4831.0 4 4321.4 4824.5 4 4824.5 4824.5
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a contractual modification (P00033) signed by the Program Office and the Contractor on March 31, 2014. This contractual modification reduced the target price by $5.9M and reduced the ceiling price by $6.5M, due to the removal of certain Live Fire Test Assets. This contractual modification was updated in the Earned Value data and reduced the ceiling price of the FPIF contract from $4,831M to $4,824.5M.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/28/2016) -23.2 -123.4
Previous Cumulative Variances -320.6 -802.0
Net Change +297.4 +678.6
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to implementation of an Over Target Baseline (OTB) to the program.
The favorable net change in the schedule variance is due to implementation of an Over Target Baseline (OTB) to the program. The 767-2C Boeing Commercial cumulative schedule variance was due to the delayed completion of 4 internal milestones.
Notes
The Contractor's current Estimated Price at Completion reflects the existing contract scope.

## Table 44
Contract Identification
Appropriation: RDT&E
Contract Name: KC-46A Engineering and Manufacturing Development
Contractor: The Boeing Company
Contractor Location: 7755 E Marginal Way S
Seattle, WA 98108-4002
Contract Number: FA8625-11-C-6600/1
Contract Type: Firm Fixed Price (FFP)
Award Date: February 24, 2011
Definitization Date: February 24, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
66.6 N/A N/A 80.3 N/A N/A 80.3 80.3
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to some contract modifications for studies, and support equipment.
On January 14, 2013, a modification (P00022), was issued in the amount of $2.1M for the Cargo Restraint Alternate Location study, increasing the price of this FFP contract from $66.6M to $68.7M.
On October 6, 2014, a modification (P00049) was issued in the amount of $3.1M for the Hi-Strength Pallet Locks and Movable Smoke Barrier Verification / Certification Engineering study, increasing the contract price of this FFP contract from
$68.7M to $71.8M
On February 6, 2015, a modification (P00052) was issued in the amount of $184K for additional support equipment, increasing the contract price of this FFP contract from $71.8M to $72.0M.
On September 18, 2015, a modification (P00066) was issued in the amount of $1.0M for the Characterization of Data Exchange study, increasing the contract price of this FFP contract from $72.0M to $73.0M.
On December 23, 2015, a modification (P00074) was issued in the amount of $7.3M for the Integrated Broadcast Service Common Interactive Broadcast study, increasing the contract price of this FFP contract from $73.0M to $80.3M.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 45
Contract Identification
Appropriation: Procurement
Contract Name: KC-46A Production Contract
Contractor: Boeing
Contractor Location: P.O. Box 3707
Seattle, WA 98214
Contract Number: FA8625-11-C-6600/3
Contract Type: Firm Fixed Price (FFP)
Award Date: February 24, 2011
Definitization Date: December 10, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
119.4 N/A 0 108.8 N/A 0 108.8 108.8
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a reduction in scope when the Undefinitized Contract Action was definitized.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
On December 10, 2014, contract modification P00054 was signed by both the Program Office and the Contractor. This contractual modification in the amount of $84.5M represents the Undefinitized Contract Action (UCA) to purchase Support Equipment and Production Spares in advance of Milestone C as approved in the ADM signed on October 17, 2014.
On December 17, 2014, contract modification P00057 was signed by both the Program Office and the Contractor. This contractual modification in the amount of $34.9M represents the Interim Contractor Support Year 1 option.
On November 9, 2015, contract modification P00067 was signed by both the Program Office and the Contractor. This contractual modification reduced the price of the P00054 UCA by $10.6M due to a reduction in scope.

## Table 46
Contract Identification
Appropriation: RDT&E
Contract Name: KC-46A Aircrew Training Systems - Engineering and Manufacturing Development
Contractor: FlightSafety Services Corporation
Contractor Location: 10770 E. Briarwood Ave. Suite 100
Centennial, CO 80112-3807
Contract Number: FA8621-13-C-6247/0
Contract Type: Fixed Price Incentive(Firm Target) (FPIF), Firm Fixed Price (FFP)
Award Date: May 01, 2013
Definitization Date: May 01, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
78.4 86.6 N/A 78.4 86.6 N/A 86.6 86.6
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) -6.2 -3.1
Previous Cumulative Variances -1.7 -3.1
Net Change -4.5 +0.0
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to a lack of mature aircraft data, primarily for the Weapons System Trainer subsystems such as the cockpit student station, computer systems, and aircraft systems. Additional costs to develop alternative solutions were incurred to maintain schedule. Additionally, the Contractor has elected to include their FFP CLIN efforts for program management in the program baseline and additional cost overruns have been associated with this effort.
The unfavorable net change in the schedule variance is due to a lack of mature aircraft data and defined operational procedures needed for design and engineering efforts. The Boom Operator Training device subsystem development is a significant contributor to this variance. The Weapon System Training sub-systems contribute to this variance as well.
Notes
The Aircrew Training System contract (FA8621-13-C-6247) contains both FPIF and FFP CLINs. While Earned Value data is not required on the FFP efforts, the Contractor has included actual performance in the monthly Earned Value data.

## Table 47
Contract Identification
Appropriation: MILCON
Contract Name: KC-46A MILCON (McConnell AFB)
Contractor: Archer Western Aviation Partners
Contractor Location: 929 W. Adams St.
Chicago, IL 60607-3021
Contract Number: W912DQ-14-C-4006
Contract Type: Firm Fixed Price (FFP)
Award Date: May 22, 2014
Definitization Date: May 22, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
143.7 N/A N/A 147.2 N/A N/A 147.2 147.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract modifications being awarded for additional MILCON projects.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This contract will be a Design-Bid-Build of the 3-Bay General Purpose Hangar, Aircraft Parking Apron, 2-bay Corrosion Control/Fuel Cell Hangar and General Maintenance Hangar located at McConnell AFB Kansas.
As of December 14, 2015, additional contract modifications have been awarded, increasing the original contract price from
$143.7 to $147.2M.

## Table 48
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 4 | 0%
Production | 0 | 0 | 175 | 0%
Total Program Quantity Delivered | 0 | 0 | 179 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
48212
4300.8
8.92%
24
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
12
50%
10311.4
21.39%
The above data is current as of February 09, 2016.

## Table 49
Operating and Support Cost
Cost Estimate Details
Date of Estimate: October 31, 2014
Source of Estimate: POE
Quantity to Sustain: 168
Unit of Measure: Aircraft
Service Life per Unit: 40.00 Years
Fiscal Years in Service: FY 2016 - FY 2069
In support of the Milestone B decision in February 2011, the Air Force developed a SCP. The MDA approved baselining the KC-46A program to this SCP. In October 2014, the KC-46A Division accomplished an update to this SCP in
its third POE. This SAR reflects the POE update. Due to a program schedule rebaseline and an impending MS C estimate, the CY 2015 POE was waived. The MS C POE is currently in work and will be used to reconcile to a Service Cost Position and inform the MS C decision.
The KC-46A Program has 168 Primary Aircraft Authorized (PAA) and 11 back-up aircraft. The O&S estimate is based on the 168 PAA.
Sustainment Strategy
The KC-46A sustainment strategy will use United States Air Force (USAF) Two-Level logistics concepts supported by the USAF maintenance and logistics support structures and Organizational, Maintenance, Installation, and Training data rights. The sustainment strategy will use a Contractor Supported Weapons System concept during EMD, transitioning to an organic/performance-based logistics posture as soon as sustainable organic capabilities are established during production. Organizational-level maintenance will be done by Air Force personnel with assistance of contractor Field Service Representatives and supported by contractor Logistics Support Representatives beginning with Initial Operational Test and Evaluation. The most critical organic capabilities are planned for incremental stand-up during Interim Contractor Support. The Depot-level (C-Check) capability stand-up is targeted not later than two years after first production aircraft delivery. Subsequent depot operations will expand incrementally based upon the Depot Maintenance Activation Working Group developed activation plan. The KC-46A Program Office will closely coordinate with the Air Force Sustainment Center to facilitate planning, execution, and evaluation of the C-Check process and the follow-on stand-up of commodity support capability.
Antecedent Information
KC-135R&T is the antecedent system.
KC-135R&T costs have been normalized to reflect the average of 670 annual flying hours per aircraft in the KC-46A POE. KC-135R&T average annual cost per aircraft reflects actual FY 2014 costs reported in the Air Force Total Ownership Cost system (budget constrained). Most FY 2014 costs reflect the current state of KC-135R&T; however, there are a few exceptions, such as modification costs in Continuing System Improvements, where the FY 2014 KC- 135R&T costs are lower than in previous years.

## Table 50
Annual O&S Costs BY2011 $M
Cost Element |  |  | KC-46A Average Annual Cost Per Aircraft |  |  |  | KC-135R&T (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower |  |  | 4.452 |  |  |  | 3.234
Unit Operations |  |  | 4.069 |  |  |  | 3.969
Maintenance |  |  | 3.045 |  |  |  | 3.793
Sustaining Support |  |  | 0.512 |  |  |  | 0.189
Continuing System Improvements |  |  | 0.894 |  |  |  | 0.072
Indirect Support |  |  | -- |  |  |  | --
Other |  |  | -- |  |  |  | --
Total |  |  | 12.972 |  |  |  | 11.257
KC-46A costs shown in comparison with actual costs for the antecedent system, KC-135 R&T, reflect estimated average annual cost per aircraft.
The "Annual O&S Costs BY2011$M" comparison above excludes "Indirect Support" costs because these costs are not allocated to KC-135 R&T-specific Program Elements in the Air Force Total Ownership Cost system. However, these costs are included in the KC-46A Total O&S costs.
While the comparison is to FY 2014 actual KC-135 R&T costs, the Air Force projects KC-135 R&T O&S costs to increase, surpassing projected KC-46A O&S costs by FY 2020. This projected increase is not reflected in the “Annual O&S Costs BY 2011 $M” table above. This comparison is also not adjusted for the capability differences that exist between the two systems nor does it recognize the cost savings that may be realized due to the commerciality of the KC- 46A aircraft (the KC-46A is derived from a commercial Boeing 767 variant). Because the 767 was designed to be cost competitive in the commercial marketplace, it is anticipated that the aircraft’s commercial efficiencies will facilitate improvement in the military operational costs for the KC-46A. In addition, the KC-46A has significantly more aerial refueling offload capability per aircraft compared to the KC-135 R&T and is a multi-role aircraft with significant secondary missions associated with airlift and aeromedical evacuation. The KC-46A can also provide boom/drogue refueling on the same sortie, and has enhanced net ready and survivability capabilities.
Item | Total O&S Cost $M
| KC-46A | [6 empty] | KC-135R&T (Antecedent)
| Current Development APB Objective/Threshold |  |  |  | Current Estimate
Base Year |  | 92720.6 |  | 101992.7 |  | 104428.41 |  |  | N/A
Then Year 1 APB O&S Cost Breach |  | 182877.7 |  | N/A |  | 184068.6 |  |  | N/A
KC-46A total O&S cost ($M) in the “Total O&S Cost $M” table above reflects the October 2014 POE total O&S costs for FY 2016 - FY 2069. Total KC-46A O&S cost is not a simple extrapolation of the KC-46A average annual cost per aircraft shown in the preceding “Annual O&S Costs BY 2011 $M” table due to the exclusion of "Indirect Costs" associated with the KC-135 R&T. The KC-46A POE reflects the following assumptions: 168 PAA, 40-year service life, steady state beginning in FY 2029, and peacetime operations tempo with average annual flying hours of 489 hours per PAA through FY 2019, and 670 hours per PAA from FY 2020 and beyond. The KC-46A POE is based on legacy fleet history where KC-46A specific data is not available. A comparable total O&S cost for the antecedent system, KC-135 R&T, is not available.

## Table 51
Equation to Translate Annual Cost to Total Cost
Total KC-46A Aircraft O&S (BY 2011$M) = [unitized cost ($12.972M) x 40 operational aircraft years x 168 PAA] + Total O&S Indirect Support costs (excluded from the unitized cost comparison above to allow for a normalized comparison) + phase-in and phase-out costs (as aircraft are fielded and later retired).
O&S Cost Variance
Category | BY 2011 $M | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
104428.4
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 104428.4
Disposal Estimate Details
Date of Estimate: October 31, 2014
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2011 $M): Total costs for disposal of all Aircraft are 14.8
The KC-46A POE assumed that upon retirement at the end of the 40-year service life, each KC-46A aircraft would enter flyable storage at the Aircraft Maintenance and Regeneration Group and will be disposed after a period of five years.