## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-456
Next Generation Operational Control System (OCX)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 15
Cost and Funding 16
Low Rate Initial Production 20
Foreign Military Sales 21
Nuclear Costs 21
Unit Cost 22
Cost Variance 25
Contracts 28
Deliveries and Expenditures 30
Operating and Support Cost 31

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Next Generation Operational Control System (OCX)
DoD Component
Air Force
Joint Participants
Department of Transportation
Responsible Office
Col Steven Whitney 483 N. Aviation Blvd
El Segundo, CA 90245
steven.whitney.1@us.af.mil
Phone: | 310-653-3001
Fax: | 310-653-3005
DSN Phone: | 633-3001
DSN Fax: | 633-3005
Date Assigned: | July 8, 2015
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated November 19, 2012
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 19, 2015

## Table 6
Mission and Description
The Global Positioning System (GPS) is a space-based positioning, navigation, and timing distribution system, which operates through weather and electromagnetic environments (jamming, spoofing, etc.). GPS supports both civil and military users in air, space, sea, and land operations. GPS is a satellite-based radio navigation system that serves military and civil users worldwide. GPS users process satellite signals to determine accurate position, velocity, and time. GPS must comply with section 2281 of title 10, United States Code (USC), which requires that the Secretary of Defense ensures the continued sustainment and operation of GPS for military and civilian purposes and section 50112 of title 51, USC, which requires that GPS complies with certain standards and facilitates international cooperation.
The Next Generation Operational Control System (OCX) program develops and fields a modernized satellite command and control (C2) system which replaces the current ground control system for legacy and new GPS satellites. OCX implements a modern flexible architecture with built-in robust information assurance to address emerging cyber threats. The Air Force is taking a block approach to develop OCX with each block delivering upgrades as they become available.
The OCX program of record consists of two block deliverables: Block 1 and Block 2. OCX Block 0, a subset of Block 1, will allow OCX to support the launch and checkout of GPS III satellites. OCX Block 1 replaces the existing legacy GPS C2 system and fields the operational capability to control legacy satellites (GPS IIR, IIR-M, and IIF) and control existing signals (L1 C/A, L1P(Y), and L2P(Y)). OCX Block 1 also adds the operational capability to command and control the GPS III satellites and the modernized civil signals (L2C and L5). OCX Block 2 adds operational control of the new international open/civil L1C signal in compliance with 2004 European Union-United States agreement and adds control of the modernized Military Code signal.

## Table 7
Executive Summary
Since the December 2014 SAR, the program has completed a new APB, dated October 19, 2015, and held two major Deep Dive reviews with USD(AT&L) to assess program performance and the way-ahead.
The Program Office and Raytheon initially held a Deep Dive with USD(AT&L) in February 2015. As a result of this Deep Dive, the MDA, in a May 23, 2015 ADM, directed the development of a new APB and established five tripwire milestones to measure schedule and cost performance.
An Acquisition Incident Review (AIR) board was conducted in July 2015 to identify root causes associated with OCX program execution challenges and provide recommendations for continuing the procurement of a modernized ground control system. The AIR identified 5 root causes which included an unrealistic program schedule at contract award; appropriate system engineering and system integration practices were not implemented by Raytheon at the start-up of the program; cybersecurity requirements were not clearly understood; a complex incentive structure; and high government personnel turnover. The Program Office and Raytheon have worked to address the root causes identified by the AIR board including applying lessons learned and correct software development practices to Block 1 software iterations; re-writing the incentive structure to simplify the criteria for award; and re-planning the program to a higher fidelity schedule.
A second Deep Dive occurred with USD(AT&L) on December 4, 2015 to re-assess program way-ahead as a result of several tripwire breaches. In support of this Deep Dive, the Deputy Assistant Secretary for Cost and Economics approved the December 1, 2015 SCP based upon a projected 47-month slip to the October 2015 APB. At the Deep Dive, OSD and the Air Force jointly agreed to a 24-month replan beyond the schedule objectives of Milestone C, Block 1 Ready to Transition to Operations (RTO) and Block 2 RTO in the October 2015 APB. On December 23, 2015 the Program Manager signed
a Program Deviation Report declaring a 24-month slip past the current APB objectives of Milestone C, Block 1 RTO, and 2 RTO. The Air Force is in the process of completing an excursion to the December 2015 SCP for the 24-month replan. As part of the replan, the Department of Transportation (DoT) has a commitment to provide the Air Force $25.1M. The DoT funding is not a part of the SCP and is not included in the cost and funding tables.
During this period, Raytheon continued with Block 0 integration and test. Raytheon completed shipment of the Launch and Checkout System hardware on May 7, 2015 and completed installation activities at Schriever Air Force Base in August 2015. Raytheon completed 2 of 3 Configuration Item Qualification Test deficiency report (DR) re-test phases and has reduced the DR backlog from 261 to 138 in preparation for Test Readiness Review in CY 2016.
During this period, Raytheon continued efforts with Block 1 software development. An Iteration 1.6 Critical Design Review (iCDR) was conducted on July 30, 2015, with 11 liens assigned. A closure review was held on September 30, 2015, which resulted in 6 liens being passed and 5 deferred. The Program Office established a Delta iCDR to be held in Spring 2016 to close the remaining 5 liens. Raytheon has continued to make progress towards the Delta iCDR.
Of the 27 watch items reported in the previous SAR, 21 of those items have been closed with the additional 6 on-track to close.
On June 22, 2015, Raytheon notified the Program Office that four of the five tripwires were forecasted to be breached. The primary drivers for the breaches were late discovery of Information Assurance deficiencies, code growth as a result of correcting 635 system engineering gaps and resource contention between multiple critical tasks. On June 26, 2015, the Program Manager submitted notification to the PEO and the PEO submitted notification to the Service Acquisition Executive (SAE). The SAE notified the MDA on June 30, 2015 that Raytheon would breach four of the five tripwires for cost and schedule.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
The schedule breach against the October 19, 2015 APB is a result of lack of appropriate system engineering and configuration management practices, information assurance requirements complexity, and an approximate 40% software code growth. The Air
Force submitted a Program Deviation Report for the schedule breach on December 23, 2015.
The Air Force is currently replanning the OCX program based on a 24
-month slip that was accepted at the December 4, 2015 Deep Dive with USD(AT&L).
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Development Contract Award | Feb 2010 | Feb 2010 | Feb 2010 | Feb 2010
Block 1 and 2 PDR | Aug 2011 | Aug 2011 | Aug 2011 | Aug 2011
Milestone B | Nov 2012 | Nov 2012 | Nov 2012 | Nov 2012
Block 0 (LCS Delivery) | Nov 2014 | Apr 2016 | Oct 2016 | Sep 20171
Milestone C | Oct 2015 | Jul 2018 | Jan 2019 | Jul 20201
Block 1 RTO | Oct 2016 | Jul 2019 | Jul 2020 | Jul 20211
Block 2 RTO | Jun 2017 | Jul 2020 | Jul 2021 | Jul 20221
1 APB Breach
(Ch-1)
(Ch-2)
(Ch-2)
(Ch-2)
Change Explanations
(Ch-1) The current estimate for Block 0 changed from February 2016 to September 2017 as a result of time required to resolve excessive deficiency reports.
(Ch-2) The current estimate for Milestone C changed from July 2018 to July 2020, the current estimate for Block 1 RTO changed from July 2019 to July 2021 and the current estimate for Block 2 RTO changed from July 2020 to July 2022 as a result of poor contractor performance.
Notes
RTO will be achieved when the Control Segment can support GPS III SV01-10 and operational Block II satellites, can monitor broadcast GPS navigation signals, and can support NAVWAR mission planning by JSpOC. At RTO, the system is turned over to the operational community.

## Table 10
Acronyms and Abbreviations
GPS - Global Positioning System JSpOC - Joint Space Operations Center LCS - Launch and Checkout System NAVWAR - Navigation Warfare
PDR - Preliminary Design Review
RTO - Ready to Transition to Operations SV - Space Vehicle

## Table 11
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Backward Compatibility
All modifications made | All modifications made | (T=O) All modifications | TBD | All modifications made
to the existing GPS | to the existing GPS | made to the existing |  | to the existing GPS
Space Segment and | Space Segment and | GPS Space Segment |  | Space Segment and
Control Segment shall | Control Segment shall | and Control Segment |  | Control Segment shall
allow the continued | allow the continued | shall allow the |  | allow the continued
operation of existing IS- | operation of existing IS- | continued operation of |  | operation of existing IS-
GPS-200, IS-GPS-700, | GPS-200, IS-GPS-700, | existing IS-GPS-200, IS |  | GPS-200, IS-GPS-700,
IS-GPS-705 and SS- | IS-GPS-705 and SS- | -GPS-700, IS-GPS-705 |  | IS-GPS-705 and SS-
GPS-001 compliant UE | GPS-001 compliant UE | and SS-GPS-001 |  | GPS-001 compliant UE
and continued operation | and continued | compliant UE and |  | and continued
of legacy receivers (to | operation of legacy | continued operation of |  | operation of legacy
include Federal | receivers (to include | legacy receivers (to |  | receivers (to include
augmentation system | Federal augmentation | include Federal |  | Federal augmentation
receivers) IAW | system receivers) IAW | augmentation system |  | system receivers) IAW
performance meeting | performance meeting | receivers) IAW |  | performance meeting
the APB Precise | the APB Precise | performance meeting |  | the APB Precise
Positioning Service | Positioning Service | the APB Precise |  | Positioning Service
Performance Standard | Performance Standard | Positioning Service |  | Performance Standard
and GPS Positioning | and GPS Positioning | Performance Standard |  | and GPS Positioning
Service Performance | Service Performance | and GPS Positioning |  | Service Performance
Standard, and Federal | Standard, and Federal | Service Performance |  | Standard, and Federal
augmentation system | augmentation system | Standard, and Federal |  | augmentation system
specifica-tions for the | specifica-tions for the | augmentation system |  | specifica-tions for the
Local Area Augmenta- | Local Area Augmenta- | specifica-tions for the |  | Local Area Augmenta-
tion System, Wide Area | tion System, Wide Area | Local Area Augmenta- |  | tion System, Wide Area
Augmenta-tion System, | Augmenta-tion System, | tion System, Wide |  | Augmenta-tion System,
Nationwide Differential | Nationwide Differential | Area Augmenta-tion |  | Nationwide Differential
GPS, and Maritime | GPS, and Maritime | System, Nationwide |  | GPS, and Maritime
Differential GPS. | Differential GPS. | Differential GPS, and |  | Differential GPS.
Maritime Differential
GPS.
Availability of Position Accuracy a. b. Horizontal c.d. Vertical
UEE = 0.8 m rms a. 4.5 | UEE = 0.8 m rms a. | a. 1.2 m (95%) @ 90% | TBD | UEE = 0.8 m rms a.
m (95%) @ 90% | 4.5 m (95%) @ 90% | availability any lat/long |  | 4.5 m (95%) @ 90%
availability any lat/long b. | availability any lat/long | b. 1.2 m (95%) @ |  | availability any lat/long
4.0 m (95%) @ 99.9% | b. 4.0 m (95%) @ | 99.9% availability global |  | b. 4.0 m (95%) @
availability global | 99.9% availability global | average c. 1.9 m (95%) |  | 99.9% availability global
average c. 7.0 m (95%) | average c. 7.0 m (95%) | @ 90% availability any |  | average c. 7.0 m (95%)
@ 90% availability any | @ 90% availability any | lat/long d. 1.9 m (95%) |  | @ 90% availability any
lat/long d. 7.0 m (95%) | lat/long d. 7.0 m (95%) | @ 99.9% availability |  | lat/long d. 7.0 m (95%)
@ 99.9% availability | @ 99.9% availability | global average Note: |  | @ 99.9% availability
global average UEE = | global average UEE = | (a) and (c) values |  | global average UEE =
2.6 m rms a. 11.5 m | 2.6 m rms a. 11.5 m | equal 1 m SEP Note: |  | 2.6 m rms a. 11.5 m

## Table 12
(95%) @ 90% availability any lat/long b. 11.5 m (95%) @ 99.9% availability global average c. 17.7 m (95%) @ 90% availability any lat/long d. 17.7 m (95%) @ 99.9% availability global average. | (95%) @ 90% availability any lat/long b. 11.5 m (95%) @ 99.9% availability global average c. 17.7 m (95%) @ 90% availability any lat/long d. 17.7 m (95%) @ 99.9% availability global average. | no UEE assumed for objective because requirement is stated in FCS ORD. |  | (95%) @ 90% availability any lat/long b. 11.5 m (95%) @ 99.9% availability global average c. 17.7 m (95%) @ 90% availability any lat/long d. 17.7 m (95%) @ 99.9% availability global average.
Position and Time Transfer Integrity
GPS III SV01-08 shall not transmit MSI to the user with a probability greater than 0.0001 per hour. | GPS III SV01-08 shall not transmit MSI to the user with a probability greater than 0.0001 per hour. | GPS III SV01-08 shall not transmit MSI to the user with a probability greater than 0.0000001 per hour. | TBD | GPS III SV01-08 shall not transmit MSI to the user with a probability greater than 0.0001 per hour.
Availability of Dynamic Time Transfer Accuracy
UEE = 0.8 m rms Any lat/long 15 nanoseconds (ns) (95%) @ 90% availability Global Average 15 ns (95%) @ 99.9% availability UEE = 2.6 m rms Any lat/long 40 ns (95%) @ 90% availability Global Average 50 ns (95%) | UEE = 0.8 m rms Any lat/long 15 ns (95%) @ 90% availability Global Average 15 ns (95%) @ 99.9% availability UEE = 2.6 m rms Any lat/long 40 ns (95%) @ 90% availability Global Average 50 ns (95%) | Any lat/long 4.5 ns (95%) @ 90% availability Global Average 4.5 ns (95%) @ 99.9% availability Note: no UEE assumed for objective because requirement is derived from the FCS ORD Objective SEP accuracy requirement | TBD | UEE = 0.8 m rms any lat/long 15 ns (95%) @ 90% availability Global Average 15 ns (95%) @ 99.9% availability UEE = 2.6 m rms any lat/long 40 ns (95%) @ 90% availability Global Average 50 ns (95%).
Availability of Static Time Transfer Accuracy
3.0 ns (95%) @ > 99.9% availability | 3.0 ns (95%) @ > 99.9% availability | 1.0 ns (95%) @ > 99.9% availability | TBD | 3.0 ns (95%) @ > 99.9% availability.
Net-Ready KPP
The system must fully support execution of joint critical operational activities and information exchanges identified in the DoD Enterprise Architecture and solution architectures based on integrated DoD AF content, and must satisfy the technical requirements for transition to Net-Centric military operations to include: 1) Solution architecture products compliant with DoD Enterprise Architecture | The system must fully support execution of joint critical operational activities and information exchanges identified in the DoD Enterprise Architecture and solution architectures based on integrated DoD AF content, and must satisfy the technical requirements for transition to Net-Centric military operations to include: 1) Solution architecture products compliant with DoD | The system must fully support execution of all operational activities and information exchanges identified in DoD Enterprise Architecture and solution architectures based on integrated DoD AF content, and must satisfy the technical requirements for transition to Net- Centric military operations to include 1) Solution architecture products compliant with DoD Enterprise | TBD | The system must fully support execution of joint critical operational activities and information exchanges identified in the DoD Enterprise Architecture and solution architectures based on integrated DoD AF content, and must satisfy the technical requirements for transition to Net-Centric military operations to include: 1) Solution architecture products compliant with DoD

## Table 13
based on integrated | Enterprise Architecture | Architecture based on |  | Enterprise Architecture
DoD AF content, | based on integrated | integrated DoD AF |  | based on integrated
including specified | DoD AF content, | content, including |  | DoD AF content,
operationally effective | including specified | specified operationally |  | including specified
information exchanges | operationally effective | effective information |  | operationally effective
2) Compliant with Net- | information exchanges | exchanges 2) |  | information exchanges
Centric Data Strategy, | 2) Compliant with Net- | Compliant with Net– |  | 2) Compliant with Net-
and Net-centric Services | Centric Data Strategy, | Centric Data Strategy |  | Centric Data Strategy,
Strategy and the | and Net-centric | and Net-Centric |  | and Net-centric
principles and rules | Services Strategy and | Services Strategy, and |  | Services Strategy and
identified in the DoD IEA, | the principles and rules | the principles and rules |  | the principles and rules
excepting tactical and | identified in the DoD | identified in the DoD |  | identified in the DoD
non-IP communic-ations | IEA, excepting tactical | IEA, excepting tactical |  | IEA, excepting tactical
3) Compliant with GIG | and non-IP communic- | and non-IP communic- |  | and non-IP communic-
Technical Guidance to | ations 3) Compliant | ations 3) Compliant |  | ations 3) Compliant
include IT Standards | with GIG Technical | with GIG Technical |  | with GIG Technical
identified in the TV-1 and | Guidance to include IT | Guidance to include IT |  | Guidance to include IT
implementa-tion | Standards identified in | Standards identified in |  | Standards identified in
guidance of GESPs | the TV-1 and | the TV-1 and |  | the TV-1 and
necessary to meet all | implementa-tion | implementa-tion |  | implementa-tion
operational | guidance of GESPs | guidance of GESPs, |  | guidance of GESPs
requirements specified | necessary to meet all | necessary to meet all |  | necessary to meet all
in the DoD Enterprise | operational | operational |  | operational
Architecture and solution | requirements specified | requirements specified |  | requirements specified
architecture views 4) | in the DoD Enterprise | in the DoD Enterprise |  | in the DoD Enterprise
Information assurance | Architecture and | Architecture and |  | Architecture and
requirements including | solution architecture | solution architecture |  | solution architecture
availability, integrity, | views 4) Information | views 4) Information |  | views 4) Information
authentica-tion, | assurance | assurance |  | assurance
confidential-ity, and non- | requirements including | requirements including |  | requirements including
repudiation, and | availability, integrity, | availability, integrity, |  | availability, integrity,
issuance of an IATO or | authentica-tion, | authentica-tion, |  | authentica-tion,
ATO by the DAA, and 5) | confidential-ity, and non | confidential-ity, and non |  | confidential-ity, and non
Support-ability | -repudiation, and | -repudiation, and |  | -repudiation, and
requirements to include | issuance of an IATO or | issuance of an ATO by |  | issuance of an IATO or
SAASM, Spectrum, and | ATO by the DAA, and | the DAA, and 5) |  | ATO by the DAA, and
JTRS require-ments. | 5) Support-ability | Support-ability |  | 5) Support-ability
| requirements to include | requirements to include |  | requirements to include
| SAASM, Spectrum, and | SAASM, Spectrum and |  | SAASM, Spectrum, and
| JTRS require-ments. | JTRS require-ments. |  | JTRS require-ments.
Sustainment--Materiel Availability
The achievement of the | The achievement of the | (T=O) The | TBD | The achievement of the
Availability of Position | Availability of Position | achievement of the |  | Availability of Position
Accuracy KPP and Time | Accuracy KPP and | Availability of Position |  | Accuracy KPP and
Transfer Accuracy KPP | Time Transfer | Accuracy KPP and |  | Time Transfer
Thresholds. | Accuracy KPP | Time Transfer |  | Accuracy KPP
| Thresholds. | Accuracy KPP |  | Thresholds.
Thresholds.

## Table 14
Requirements Reference
GPS III CDD dated September 17, 2009
Change Explanations
None
Notes
This performance baseline is for OCX and was derived from the system-level CDD requirements. The GPS III program will track cost, schedule, and performance separately in its own APB.
Acronyms and Abbreviations
AF - Air Force
ATO - Authority To Operate
DAA - Designated Approval Authority FCS - Future Combat System
GESP - GIG Enterprise Service Profiles GIG - Global Information Grid
GPS - Global Positioning System IATO - Interim Authority to Operate IAW - In Accordance With
IEA - Information Enterprise Architecture IP - Internet Protocol
IS - Interface Specifications IT - Information Technology
JTRS - Joint Tactical Radio System lat - Latitude
long - Longitude m - meter
MSI - Misleading Signal in Space Information ns - nanosecond
rms - root-mean-square
SAASM - Selective Availability/Anti-Spoofing Module SEP - Spherical Error Probable
SS - System Specifications SV - Space Vehicle
TV - Technical View UE - User Equipment
UEE - User Equipment Error

## Table 15
Track to Budget
RDT&E
Appn | BA | PE
Air Force 3600 07 0603421F
Project Name
674993 GPS III (Shared) (Sunk)
Air Force 3600 07 0603423F
Project Name
67A021 Global Positioning System III - Operational Control Segment (OCX)
67A025 GPS Enterprise Integrator

## Table 16
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2012 $M | [5 empty] | BY 2012 $M |  | TY $M
| SAR Baseline Development Estimate |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E | 3347.2 |  |  | 3839.3 | 4112 |  |  | 4056.5 |  | 3413 |  |  | 3964.4 |  | 4189
Procurement | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Flyaway | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Recurring | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Non Recurring | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Other Support | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Initial Spares | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
MILCON | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 3347.2 |  |  | 3839.3 | N/A |  |  | 4056.5 |  | 3413 |  |  | 3964.4 |  | 4189
Current APB Cost Estimate Reference
SCP dated November 10, 2014
Confidence Level
Confidence Level of cost estimate for current APB: 55%
The November 10, 2014 SCP for the OCX Program is at the mean of the cost estimate distribution. It takes into consideration all relevant program risks, providing sufficient resources to execute the program under normal conditions encountering average levels of technical, schedule, and programmatic risk and external interference.
Total Quantity
Quantity |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  | 1 |  |  |  | 1 |  |  |  |  | 1
Procurement |  | 0 |  |  |  | 0 |  |  |  |  | 0
Total |  | 1 |  |  |  | 1 |  |  |  |  | 1

## Table 17
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 2709.2 | 349.2 |  | 393.3 |  | 252.5 |  | 232.8 |  | 124.9 |  | 127.1 |  | 0 |  | 4189
Procurement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
MILCON | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 2709.2 | 349.2 |  | 393.3 |  | 252.5 |  | 232.8 |  | 124.9 |  | 127.1 |  | 0 |  | 4189
PB 2016 Total | 2666.6 | 350.2 |  | 222.3 |  | 136.5 |  | 139 |  | 88 |  | 0 |  | 0 |  | 3602.6
Delta | 42.6 | -1 |  | 171 |  | 116 |  | 93.8 |  | 36.9 |  | 127.1 |  | 0 |  | 586.4
Funding Notes
The current program identified in the FY 2017 PB is for $4.189B. In addition to that, the Department of Transportation (DoT) currently has a commitment to provide $25.1M in support of the program. This additional $25.1M is not part of the SCP and is not included in the cost and funding tables.
An assessment is currently underway which will lead to a formal restructure of the program. The changes to cost and schedule are not definitized at this point in time.
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 1 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1
Production | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 1 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1
PB 2016 Total | 1 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Table 18
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 168.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 249.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 289.6
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 288.4
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 353.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 347
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 316.7
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 361.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 334.6
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 349.2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 393.3
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 252.5
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 232.8
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 124.9
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 127.1
Subtotal |  | 1 | -- |  | -- |  | -- |  | -- |  | -- |  | 4189

## Table 19
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2012 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 181.1
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 263
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 301.2
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 296.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 356.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 343.6
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 308.7
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 347.6
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 318.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 327.5
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 361.9
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 228.1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 206.1
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 108.4
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 108.1
Subtotal |  | 1 | -- |  | -- |  | -- |  | -- |  | -- |  | 4056.5

## Table 20
Low Rate Initial Production
There is no LRIP for this program.

## Table 21
Foreign Military Sales
None
Nuclear Costs
None

## Table 22
Unit Cost
Unit Cost Report
Item |  | BY 2012 $M | BY 2012 $M |  | % Change
|  | Current UCR Baseline (Oct 2015 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 3839.3 |  |  | 4056.5
Quantity | 1 |  |  | 1
Unit Cost | 3839.3 |  |  | 4056.5 |  | 5.66
Average Procurement Unit Cost
Cost | 0 |  |  | 0
Quantity | 0 |  |  | 0
Unit Cost | -- |  |  | -- |  | --
Item |  | BY 2012 $M | BY 2012 $M |  | % Change
|  | Original UCR Baseline (Nov 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 3347.2 |  |  | 4056.5
Quantity | 1 |  |  | 1
Unit Cost | 3347.2 |  |  | 4056.5 |  | 21.19
Average Procurement Unit Cost
Cost | 0 |  |  | 0
Quantity Unit Cost | 0 -- |  |  | 0 -- |  | --
PAUC is based on RDT&E costs and quantities only. There is no APUC for this program because there are no procurement funds or quantities.

## Table 23
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2012 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Nov 2012 |  |  |  |  | 3347.2 |  |  | N/A |  |  | 3413 |  |  | N/A
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | Nov 2012 |  |  |  |  | 3347.2 |  |  | N/A |  |  | 3413 |  |  | N/A
Current APB |  |  | Oct 2015 |  |  |  |  | 3839.3 |  |  | N/A |  |  | 3964.4 |  |  | N/A
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 3521 |  |  | N/A |  |  | 3602.6 |  |  | N/A
Current Estimate |  |  | Dec 2015 |  |  |  |  | 4056.5 |  |  | N/A |  |  | 4189 |  |  | N/A
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
3413.000 -25.800 0.000 0.000 0.000 801.800 0.000 0.000 776.000 4189.000

## Table 24
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [9 empty] | APUC Current Estimate
| Econ | Qty | Sch | Eng |  | Est | Oth | Spt |  | Total
0.000 -- -- -- -- -- -- -- -- 0.000
An APUC Unit Cost History is not available, since no Initial APUC Estimate had been calculated due to a lack of defined quantities.
SAR Baseline History
Item |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone B |  | N/A |  |  | Nov 2012 |  |  |  | N/A |  |  | Nov 2012
Milestone C |  | N/A |  |  | Oct 2015 |  |  |  | N/A |  |  | Jul 2020
IOC |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Total Cost (TY $M) |  | N/A |  |  | 3413 |  |  |  | N/A |  |  | 4189
Total Quantity |  | N/A |  |  | 1 |  |  |  | N/A |  |  | 1
PAUC |  | N/A |  |  | 3413 |  |  |  | N/A |  |  | 4189

## Table 25
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
3413.0 -- -- 3413.0
Economic |  | -14.6 |  | -- |  | -- |  | -14.6
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 204.2 |  | -- |  | -- |  | 204.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 189.6 |  | -- |  | -- |  | 189.6
Current Changes Economic |  | -11.2 |  | -- |  | -- |  | -11.2
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 597.6 |  | -- |  | -- |  | 597.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 586.4 |  | -- |  | -- |  | 586.4
Total Changes |  | 776 |  | -- |  | -- |  | 776
CE - Cost Variance |  | 4189 |  | -- |  | -- |  | 4189
CE - Cost & Funding |  | 4189 |  | -- |  | -- |  | 4189

## Table 26
Summary BY 2012 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
3347.2 -- -- 3347.2
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 173.8 |  | -- |  | -- |  | 173.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 173.8 |  | -- |  | -- |  | 173.8
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 535.5 |  | -- |  | -- |  | 535.5
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 535.5 |  | -- |  | -- |  | 535.5
Total Changes |  | 709.3 |  | -- |  | -- |  | 709.3
CE - Cost Variance |  | 4056.5 |  | -- |  | -- |  | 4056.5
CE - Cost & Funding |  | 4056.5 |  | -- |  | -- |  | 4056.5
Previous Estimate: December 2014

## Table 27
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -11.2
Revised Estimate for Below Threshold Requirement from Space and Missile Systems Center Civilian Pay. (Estimating)
Revised Estimate in support of cost overruns associated with Block 0, 1, and 2 technical issues. (Estimating)
Revised Estimate for Above Threshold Requirement related to the OCX cost overruns for Block 0, 1, and 2 technical issues. (Estimating)
+6.9 +7.1
+488.4 +548.3
+42.7 +44.8
Realignment of funds for Small Business Innovation Research in FY 2015. (Estimating) Adjustment for current and prior escalation. (Estimating) | -8.9 +6.4 |  |  | -9.3 +6.7
RDT&E Subtotal | 535.5 |  |  | 586.4

## Table 28
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: OCX Phase B Contract
Contractor: Raytheon (Intelligence and Information Systems)
Contractor Location: 16800 E Centre Tech Pkwy
Aurora, CO 80011
Contract Number: FA8807-10-C-0001
Contract Type: Cost Plus Award Fee (CPAF)
Award Date: February 25, 2010
Definitization Date: February 25, 2010
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
886.4 N/A 1 1714.3 N/A 1 1956.0 1979.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to recognized cost over-runs as a result of software development and systems engineering challenges. Engineering Change Proposals, Requests for Equitable Adjustments, and engineering studies were also contributors.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (10/20/2015) |  |  |  | -88.2 |  |  |  | -37.3
Previous Cumulative Variances |  |  |  | -25.5 |  |  |  | -15.6
Net Change |  |  |  | -62.7 |  |  |  | -21.7

## Table 29
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to an underestimated decomposition of activities and closure of items required to satisfy entry criteria for Iteration 1.6 Critical Design Review (iCDR) milestone; increased efforts for Technical Interface Meeting support, Peer Reviews, closure of 1.6 Integration Segment Design Walkthrough, Segment Element Freeze Review, 1.6; retention of senior staff to complete Action Items, Technical Requests, Discrepancy Reports, Change Requests as well as government identified issues for 1.6 iCDR; ongoing OCX Monitor Station Receiver Element engineering support for Material Review Board, Failure Review Board, Manufacturing Instructions, Re-Work Orders and Out of Band Interference resolution. Additionally, specific to Block 0, Raytheon continues to discover high defect density reports as well as the need for additional software builds and deployment needed to achieve software maturity.
The unfavorable net change in the schedule variance is due to various delays in the following areas: 1.5 Risk Reduction Integration and Test which caused a 9 month delay to system engineering, iteration 1.6 Software development due to delays in detailed design and risk reduction testing, GPS System Simulator qualification due to 1.6 SW delay and Master Control Station integration blocking discrepancy reports, start of downstream Block 0 factory testing due to software maturity and configuration items readiness, as well as late receipt of Block 1 Monitor Station, Supplier and material quality issues delaying planned assembly and test.
Notes
The OCX current program performance baseline is no longer representative or useful in effective management of the program. The OCX program has authorized the implementation of an Over Target Baseline/Over Target Schedule (OTB/OTS) which will facilitate effective performance management of the GPS OCX program. During this reporting period all earned value reporting was rejected due to forecast realism and new direction provided by OSD. Starting February 2016, the program suspended EVM reporting on the current contractual baseline and tailored their monthly deliveries to report to the proposed current baseline that is being established during the OTB/OTS process. Upon completion of the OTB/OTS the program will establish an approved executable baseline and at that time the program will resume reporting at per the contractual EVM requirements.
For tracking purposes, initial contract price information is based on the initial monthly contractor's performance report ending March 28, 2010.

## Table 30
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 1 | 0%
Production | 0 | 0 | 0 | --
Total Program Quantity Delivered | 0 | 0 | 1 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
4189
2459.2
58.71%
15
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
10
66.67%
3058.4
73.01%
The above data is current as of February 23, 2016.

## Table 31
Operating and Support Cost
Cost Estimate Details
Date of Estimate: November 10, 2014
Source of Estimate: SCP
Quantity to Sustain: 1
Unit of Measure: System
Service Life per Unit: 10.00 Years
Fiscal Years in Service: FY 2019 - FY 2029
Estimated Costs are part of the Service Cost Estimate supported by the Air Force Cost Analysis Agency as part of the SCP completed in November 2014. The current cost estimate was updated and signed by Deputy Assistant Secretary (Cost and Economics) on November 10, 2014.
O&S costs includes operating, maintaining, and supporting the dedicated Master Control Station (MCS) located at Schriever Air Force Base (AFB), CO and the Alternate MCS (AMCS) located at Vandenberg AFB, CA, both of which include connections to the ground antenna and monitoring stations which support the Global Positioning System Ill (GPS Ill) and GPS II legacy spacecraft. Also included are the costs of operating, maintaining, and supporting seventeen monitoring stations, six controlled by the 50th Space Wing and eleven co-located at National Geo-spatial Intelligence Agency sites. Satellite operations at the MCS include mission planning, mission payload operations, and monitoring of satellite state of health. Monitor stations receive mission payload data and transfer this data to the MCS to ensure spacecraft are operating as desired.
The "system" to be supported will consist of the Master Control Station, Alternate Master Control Station, Launch and Checkout System, Transition Support Facility, Data Storage and Archive System, GPS System Simulator, Standard Space Trainer software, four ground antennae elements, and 17 remote sites.
O&S cost estimate assumes OCX Block 1 is Ready To Operate in month end July 2019, a 10 year service life for this one system which starts on August 1, 2019. Manpower assumes a mixture of Air Force personnel performing organic work with assistance from contractor engineers. The estimate assumes organic depot hardware maintenance with 30% organic software maintenance and 70% contractor software maintenance. The cost estimate also includes Software Iteration 2.2 and the O&S requirements to support GPS III Satellite Vehicle (SV) 09 and SV10.
Manpower, operations and maintenance is analogous to the currently operating GPS Operational Control System (OCS) with adjustments modeled to reflect the new OCX footprint.
Sustainment support is based on operator and non-operator training and sustainment engineering support is analogous to GPS OCS.
Continuing system improvements are factored in as hardware modifications and software maintenance and modifications. The OCX hardware and software maintenance cost are based on OCS historical data and adjusted proportionally for the larger hardware profile and Software Lines of Code and Information Assurance differences between OCS and OCX.
Contingency Operations cost is not included in the current OCX SCP O&S estimate.
Sustainment Strategy
Hardware depot maintenance will be 100% supported by Tobyhanna Army Depot while the Organizational Level

## Table 32
maintenance will be Contractor Logistics Support (in alignment with operational unit's maintenance structure).
Antecedent Information
GPS OCS is the current operating control system and is limited to operating GPS II satellites. GPS OCS costs are derived from actual cost collected from the last GPS OCS official Cost Data Summary Report submission in 2011.
Annual O&S Costs BY2012 $M
Cost Element |  | OCX Average Annual Cost Per System |  |  |  | GPS Operational Control System (OCS) (Antecedent) Average Annual Cost Per System
Unit-Level Manpower |  | 16.8 |  |  |  | 12.1
Unit Operations |  | 9.5 |  |  |  | 51.4
Maintenance |  | 46.5 |  |  |  | 5.4
Sustaining Support |  | 2.8 |  |  |  | 4.4
Continuing System Improvements |  | 51.9 |  |  |  | 31.5
Indirect Support |  | 3.3 |  |  |  | 0.5
Other |  | 1.3 |  |  |  | 0
Total |  | 132.1 |  |  |  | 105.3
The estimated GPS OCX average annual cost is higher than the GPS OCS actuals mainly due to the following significant cost drivers; OCX has a significantly more lines-of code (57% larger) to maintain, a significantly more complex and robust Information Assurance (IA) construct, and higher costs for hardware maintenance due to a larger hardware profile (76% larger). Lastly, the Manpower Estimate Report (used estimate unit manning) has been updated with an addendum to more accurately reflect program requirements.
* Other: Costs under this category are linked to Depot Stand-Up.
Item | Total O&S Cost $M
| OCX | [5 empty] | GPS Operational Control System (OCS) (Antecedent)
| Current Development APB Objective/Threshold |  |  | Current Estimate
Base Year | 1321 |  | 1321 |  | 1321 |  | N/A
Then Year | 2066.1 |  | N/A |  | 2065.7 |  | N/A
Equation to Translate Annual Cost to Total Cost
Average Annual Cost per system = Total OCX O&S Cost / number of service years
$132.1M= $1,321.0/10
O&S Cost Variance

## Table 33
Category | BY 2012 $M | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
1597.1
Programmatic/Planning Factors -276.1 Reduction of service life of the program from 12 years to
10
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes -276.1
Current Estimate 1321.0
Disposal Estimate Details
Date of Estimate: Source of Estimate:
Disposal/Demilitarization Total Cost (BY 2012 $M):
OCX disposal costs will be finalized in support of Milestone C.