## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-210
Space Based Infrared System High (SBIRS High)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 6
Mission and Description 7
Executive Summary 8
Threshold Breaches 9
Schedule 10
Performance 14
Track to Budget 16
Cost and Funding 18
Low Rate Initial Production 47
Foreign Military Sales 48
Nuclear Costs 48
Unit Cost 49
Cost Variance 55
Contracts 61
Deliveries and Expenditures 67
Operating and Support Cost 68

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Space Based Infrared System High (SBIRS High)
DoD Component
Air Force
Responsible Office
Col Michael A. Guetlein
Remote Sensing Systems Directorate (SMC/RS) 483 N Aviation Blvd Bldg 271
Los Angeles Air Force Base (LAAFB) El Segundo, CA 90245-2808
michael.guetlein@us.af.mil
Phone: | 310-653-3018
Fax: | 310-653-4414
DSN Phone: | 633-3018
DSN Fax: | 633-4414
Date Assigned: | September 8, 2014

## Table 6
References
Baseline (GEO 1-4, HEO 1-2, and Ground)
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated March 19, 1998
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated February 27, 2013
Block Buy (GEO 5-6)
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated September 4, 2012
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated February 27, 2013

## Table 7
Mission and Description
The Space Based Infrared System High (SBIRS High) program is intended to satisfy key requirements delineated in the SBIRS ORD dated August 15, 1996, with Annex 1 dated July 17, 1998, within the available budget and schedule. SBIRS High is an integrated system consisting of multiple space and ground elements, with incremental deployment phasing, simultaneously satisfying requirements in the following mission areas: Missile Warning, Missile Defense, Technical Intelligence and Battlespace Awareness. The constellation architecture for SBIRS High includes Highly Elliptical Orbit (HEO) sensors and Geosynchronous Earth Orbit (GEO) satellites, in addition to the following ground elements: a Continental United States-based Mission Control Station and Mission Control Station Backup, overseas Relay Ground Stations, Mobile Ground Stations, and associated communication links. The first increment of the SBIRS ground system was certified for operations in December 2001 and supports mission processing of the legacy Defense Support Program system satellites and fusion of HEO monotracks and other data. The SBIRS HEO system was certified for the Integrated Tactical Warning/Attack Assessment (ITW/AA) mission in November 2008 and technical intelligence mission in
August 2009. The SBIRS GEO 1 and 2 systems were ITW/AA mission certified in August 2013 and December 2013, respectively.
The SBIRS High MDAP includes two subprograms: the Baseline subprogram, comprised of GEO satellites 1-4, HEO payloads 1-2 and associated ground elements; and the GEO 5-6 Satellites Replenishment Production "Block Buy" subprogram. HEO payloads 3 and 4 are not part of this MDAP, but are closely related, so programmatic information is included in this SAR.

## Table 8
Executive Summary
SBIRS Baseline (Geosynchronous Earth Orbit (GEO) 1-4, Highly Elliptical Orbit (HEO) 1-2, and Ground)
Pursuant to section 2432 of title 10, United States Code, this is the final SAR submission for the Baseline (GEO 1-4, HEO 1- 2, and Ground) subprogram of the SBIRS High program, because the program is 90% or more expended.
SBIRS Baseline efforts have been focused on obtaining Operational Acceptance (OA) for a launch-capable Block 10.3 ground segment. The Ground Block 10.3 baseline consolidates all SBIRS and Defense Support Program (DSP) operations at the Mission Control Station (MCS-2) at Buckley Air Force Base using a single software and hardware baseline. The contractor completed Capability Integration at MCS-2 on March 12, 2015. Capability Evaluation officially completed on December 23, 2015. A formal test on December 10-18, 2015 proved the Block 10.3 system has the ability to control the full constellation (GEO/HEO and DSP) of satellites. Block 10.3 entered Integrated Test & Evaluation on January 30, 2016. OA of Block 10.3 is projected for November 2016.
On August, 4, 2014, National Geospatial-Intelligence Agency declared the start of Technical Intelligence (TI) Initial Data for Evaluation phase for GEO 1-2 starer sensors, and Initial Data for Operations was declared on August 27, 2015. TI operational acceptance for Ground software Block 10.3 is projected for first Quarter FY 2017.
SBIRS GEO 3-4 Production
The SBIRS GEO 3 satellite completed Thermal Vacuum (TVAC) testing on March 21, 2015 and was placed into storage on July 14, 2015. If necessary, it can be brought out of storage and prepared for launch in six months. GEO 3 initial launch capability is September 30, 2017 as the fourth GEO flight.
SBIRS GEO 4 satellite integration and testing is proceeding as planned. Space Vehicle Baseline Testing was completed on May 15, 2015, acoustic testing and deployments were completed on July 6, 2015, and TVAC testing was completed on October 19, 2015. Final installations, software updates, and testing will be conducted through May 2016 when the satellite will be shipped to Cape Canaveral Air Force Station, FL. GEO 4 is scheduled to launch in July 2016 as the third GEO flight.
The SBIRS HEO 4 payload was successfully delivered by Northrop Grumman to the Host spacecraft manufacturer on May 13, 2015, on schedule and within budget.
SBIRS Survivable and Endurable Evolution (S2E2)
With the contract award of S2E2 Mobile Ground Terminal (SMGT) 4 on November 1, 2015 and a planned March 2016 award of SMGT 5, we will now have all of the main elements (five SMGTs) for the S2E2 Mobile Ground System.
SBIRS Block Buy (GEO 5-6)
The GEO 5-6 Tech Refresh (TR) Engineering Change Proposal was approved on June 10, 2015. This major contract modification converts the SBIRS-unique A2100 satellite bus to a modernized and modular A2100 TR bus. TR was proposed as cost-neutral; however, the contract ceiling was reduced by $85M to offset added government risk. Operations at Lockheed-Martin (LM) Newton, PA shut down on July 31, 2015 and remaining work transitioned to LM Denver, CO. The Independent Research and Development A2100TR bus Critical Design Review (CDR) completed on August 27, 2015.
A delta Preliminary Design Review successfully completed on January 22, 2016, demonstrating that modernization (TR redesign) is making progress towards the next milestone, system CDR planned for early 2017. Additionally, the
delta Integrated Baseline Review was completed on December 15, 2015. SBIRS GEO 5-6 initial Non-Recurring Engineering is 99% complete.
There are no significant software-related issues with this program at this time.

## Table 9
Threshold Breaches
Baseline (GEO 1-4, HEO 1-2, and Ground)
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
Block Buy (GEO 5-6)
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 10
Schedule

## Table 11
Baseline (GEO 1-4, HEO 1-2, and Ground)
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Production Objective/Threshold |  | Current Estimate
High Component Milestone II | Oct 1996 | Oct 1996 | Oct 1996 | Oct 1996
Low Component FDS CDR | Dec 1996 | N/A | N/A | N/A
High Component PDR (Space and Ground Increment 2) | Dec 1997 | Dec 1997 | May 1998 | Dec 1997
Low Component FDS Launch | Sep 1999 | N/A | N/A | N/A
Low Component Pre-EMD Start | Oct 1999 | N/A | N/A | N/A
Low Component Milestone II | Dec 2000 | N/A | N/A | N/A
High Component CDR (Space and Ground Increment 2) | Sep 1999 | Aug 2001 | Aug 2001 | Aug 2001
Ground Segment Increment 1 Certification | Aug 1999 | Dec 2001 | Dec 2001 | Dec 2001
Ground Segment Increment 2 Certification | Jan 2002 | N/A | N/A | N/A
GEO Satellite 2 Launch | Jun 2003 | N/A | N/A | N/A
SBIRS IOC | Dec 2003 | N/A | N/A | N/A
GEO Satellite 3 Launch | Jun 2004 | N/A | N/A | N/A
HEO Sensor 1 Delivery | Sep 2001 | Aug 2004 | Aug 2004 | Aug 2004
GEO Satellite 4 Launch | Jun 2005 | N/A | N/A | N/A
HEO Sensor 2 Delivery | Sep 2003 | Sep 2005 | Sep 2005 | Sep 2005
HEO Message Certification | N/A | Dec 2008 | Dec 2008 | Dec 2008
GEO Satellite 1 Delivery | N/A | Mar 2011 | Mar 2011 | Mar 2011
GEO Satellite 2 Available for Delivery | N/A | Jun 2012 | Dec 2012 | Jun 2012
GEO Message Certification | N/A | Oct 2012 | Oct 2013 | Aug 2013
GEO Satellite 3 Available for Delivery | N/A | Dec 2015 | Jun 2016 | Jul 2015
Initial Increment 2 Ground Architecture | N/A | Jun 2016 | Dec 2016 | Nov 2016
GEO Satellite 4 Available for Delivery | N/A | Dec 2016 | Jun 2017 | Mar 2016
GEO Satellite 4 Ready for PEO Certification | N/A | Feb 2018 | Aug 2018 | May 2018
Final Increment 2 Ground Architecture | N/A | Sep 2018 | Sep 2019 | Jun 2018
Low Component Dem/Val Launch | TBD | N/A | N/A | N/A
(Ch-1)
(Ch-2)

## Table 12
Change Explanations
(Ch-1) The current estimate for GEO Satellite 3 Available for Delivery changed from May 2015 to July 2015 upon GEO Satellite 3 entering storage on July 14, 2015.
(Ch-2) The current estimate for Initial Increment Ground Architecture changed form June 2016 to November 2016 due to additional operator training, operations facility upgrades, and the challenges associated with integrating Defense Satellite Program software Discrepancy Reports into the baseline.
Notes
GEO Satellite "Available for Delivery" is defined as the satellite successfully completing Final Integrated System Test and the satellite is available such that if operational priorities require the satellite to launch at the earliest opportunity, then the satellite will continue final install processing to proceed to a Consent to Ship Review. If operational priorities indicate a later manifest, the satellite will be configured for storage.
Acronyms and Abbreviations
CDR - Critical Design Review Dem/Val - Demonstration/Validation FDS - Flight Demonstration System PDR - Preliminary Design Review

## Table 13
Block Buy (GEO 5-6)
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
GEO Satellite 5 Available for Delivery | Sep 2019 | Sep 2019 | Sep 2020 | Sep 2020
GEO Satellite 6 Available for Delivery | Sep 2020 | Sep 2020 | Sep 2021 | Jul 2021
Change Explanations
None
Notes
GEO Satellite "Available for Delivery" is defined as the GEO satellite successfully completing Final Integrated System Test and the satellite is available such that if operational priorities require the satellite to launch at the earliest opportunity, then the satellite will continue Final Install processing to proceed to a Consent-to-Ship Review. If operational priorities indicate a later manifest, then the satellite will be configured for storage.
GEO 5 and 6 delivery dates reflect the as-negotiated dates.
The one-year period between the objective and threshold values addresses the schedule risk inherent in the first time production under a fixed price contract for a SBIRS satellite.

## Table 14
Performance
Baseline (GEO 1-4, HEO 1-2, and Ground)
Classified Performance information is provided in the classified annex to this submission.
Notes
Performance assessment is based on the full SBIRS constellation and Ground Segment.

## Table 15
Block Buy (GEO 5-6)
No performance characteristics exist for Block Buy (GEO 5-6).
Notes
Performance assessment is based on the full SBIRS constellation and Ground Segment.

## Table 16
Track to Budget
Baseline (GEO 1-4, HEO 1-2, and Ground)
General Notes
RDT&E Program Element (PE) 0604441F and Missile Procurement Air Force PE 0305915F, Line Item MSSBIR and 836720, are shared. PE 0604441F includes funds for the Commercially Hosted Infrared Payload, Space Modernization Initiative and architecture studies that are not part of this MDAP. Line Item MSSBIR and 836720 include funds for Highly Elliptical Orbit payloads 3 and 4 that are not part of this MDAP.
In December 2014, the Office of Management and Budget directed the DoD to establish a new space procurement appropriation as a three-year availability account. Beginning in FY 2016, Air Force major procurement funding formerly under appropriation 3020F (Missile Procurement, Air Force) BA 05 will now be under 3021F (Space Procurement, Air Force) BA 01. The FY 2017 PB justification books reflect the new 3021F appropriation, and the SARs for programs impacted by this new appropriation also reflect this change.
RDT&E
Appn |  | BA | PE
Air Force 3600 05 0604441F
Project | Name
653616 SBIRS High Element EMD/SBIRS High EMD (Shared)
Procurement
Appn BA PE
Air Force 3020 05 0305915F
Line Item Name
MSSBIR SBIRS High Missile Procurement (Shared) (Sunk) Air Force 3021 01 0305915F
Line Item Name
MSSBIR SBIRS High (Space) (Shared) Air Force 3080 03 0305915F
Line Item Name
836720 Space Based IR Sensor Program Space (Shared)
MILCON
Appn BA PE
Air Force 3300 01 0604441F
Project Name
F0300051 SBIRS ARCHI-EMD (SPACE) Military
Construction
(Sunk)
Acq O&M
Appn BA PE
Air Force 3400 01 0305915F

## Table 17
Project | Name
1G01 SBIRS Operation and Maintenance (Sunk)
Block Buy (GEO 5-6)
Procurement
Appn |  | BA | PE
Air Force 3020 05 0305915F
Line Item | Name
MSSBIR SBIRS High Missile Procurement (Shared) (Sunk)
Air Force 3021 01 0305915F
Line Item | Name
MSSBIR SBIRS High (Space) (Shared)

## Table 18
Cost and Funding
Cost Summary - Total Program
Total Acquisition Cost - Total Program
Appropriation | BY 1995 $M |  |  |  | BY 1995 $M |  | TY $M
| SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Development Estimate |  | Current APB Development Objective |  | Current Estimate
RDT&E | 3016.6 |  | 8544.3 | -- |  | 8451.2 |  | 3386.5 |  | 10299.1 |  | 10184.5
Flyaway | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Recurring | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Non Recurring | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Procurement | 3178.3 |  | 5193.6 | -- |  | 4734.1 |  | 4449.9 |  | 7193.2 |  | 6591.5
Flyaway | -- |  | -- | -- |  | 4059.1 |  | -- |  | -- |  | 5644.4
Recurring | -- |  | -- | -- |  | 3296.2 |  | -- |  | -- |  | 4604.8
Non Recurring | -- |  | -- | -- |  | 762.9 |  | -- |  | -- |  | 1039.6
Support | -- |  | -- | -- |  | 675 |  | -- |  | -- |  | 947.1
Other Support | -- |  | -- | -- |  | 675 |  | -- |  | -- |  | 947.1
Initial Spares | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
MILCON | 26 |  | 52 | -- |  | 52 |  | 28.5 |  | 57 |  | 57
Acq O&M | 140.2 |  | 137.5 | -- |  | 112.8 |  | 147.8 |  | 161.1 |  | 161.1
Total | 6361.1 |  | 13927.4 | N/A |  | 13350.1 |  | 8012.7 |  | 17710.4 |  | 16994.1

## Table 19
Cost and Funding
Cost Summary - Baseline (GEO 1-4, HEO 1-2, and Ground)
Total Acquisition Cost - Baseline (GEO 1-4, HEO 1-2, and Ground)
Appropriation | BY 1995 $M | [6 empty] | BY 1995 $M |  | TY $M
| SAR Baseline Development Estimate |  |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E |  | 3016.6 |  |  | 8544.3 | 9398.7 |  |  | 8451.2 |  | 3386.5 |  |  | 10299.1 |  | 10184.5
Procurement |  | 496.7 |  |  | 2512 | 2763.2 |  |  | 2450.6 |  | 584.5 |  |  | 3327.8 |  | 3263.3
Flyaway |  | -- |  |  | -- | -- |  |  | 2029.2 |  | -- |  |  | -- |  | 2698.4
Recurring |  | -- |  |  | -- | -- |  |  | 1635 |  | -- |  |  | -- |  | 2178.7
Non Recurring |  | -- |  |  | -- | -- |  |  | 394.2 |  | -- |  |  | -- |  | 519.7
Support |  | -- |  |  | -- | -- |  |  | 421.4 |  | -- |  |  | -- |  | 564.9
Other Support |  | -- |  |  | -- | -- |  |  | 421.4 |  | -- |  |  | -- |  | 564.9
Initial Spares |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
MILCON |  | 26 |  |  | 52 | 57.2 |  |  | 52 |  | 28.5 |  |  | 57 |  | 57
Acq O&M |  | 140.2 |  |  | 137.5 | 151.3 |  |  | 112.8 |  | 147.8 |  |  | 161.1 |  | 161.1
Total |  | 3679.5 |  |  | 11245.8 | N/A |  |  | 11066.6 |  | 4147.3 |  |  | 13845 |  | 13665.9
Confidence Level
Confidence Level of cost estimate for current APB: 55%
Research, Development, Test and Evaluation cost profile is based on the April 2011 Air Force SCP at a 57% confidence level. The Missile Procurement, Air Force cost profile for Geosynchronous Earth Orbit (GEO) satellites 3 and 4 is based on the April 2011 SCP at a 54% confidence level, with fact-of-life modifications.
Cost Notes
The costs above reflect the FY 2017 PB for the FYDP for GEO satellites 1-4, HEO payloads 1 and 2, and ground modifications to meet the requirements in the SBIRS ORD, plus the cost to complete beyond the FYDP.
Total Quantity - Baseline (GEO 1-4, HEO 1-2, and Ground)
Quantity |  |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  |  | 3 |  |  |  | 2 |  |  |  |  | 2
Procurement |  |  | 2 |  |  |  | 2 |  |  |  |  | 2
Total |  |  | 5 |  |  |  | 4 |  |  |  |  | 4
Quantity Notes
The above quantity represents four GEO satellites.

## Table 20
Cost Summary - Block Buy (GEO 5-6)
Total Acquisition Cost - Block Buy (GEO 5-6)
Appropriation | BY 1995 $M |  |  |  |  | BY 1995 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Flyaway |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Recurring |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Non Recurring |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Procurement |  | 2681.6 |  | 2681.6 | 2949.8 |  | 2283.5 |  | 3865.4 |  | 3865.4 |  | 3328.2
Flyaway |  | -- |  | -- | -- |  | 2029.9 |  | -- |  | -- |  | 2946
Recurring |  | -- |  | -- | -- |  | 1661.2 |  | -- |  | -- |  | 2426.1
Non Recurring |  | -- |  | -- | -- |  | 368.7 |  | -- |  | -- |  | 519.9
Support |  | -- |  | -- | -- |  | 253.6 |  | -- |  | -- |  | 382.2
Other Support |  | -- |  | -- | -- |  | 253.6 |  | -- |  | -- |  | 382.2
Initial Spares |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
MILCON |  | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M |  | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Total |  | 2681.6 |  | 2681.6 | N/A |  | 2283.5 |  | 3865.4 |  | 3865.4 |  | 3328.2
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The ICE to support the SBIRS Geosynchronous Earth Orbit (GEO) 5-6 procurement, like all life-cycle cost estimates previously performed by the CAPE, is built upon a product-oriented work breakdown structure, based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for MDAPs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.
Cost Notes
The Procurement profile above reflects costs for the delivery of the GEO satellites 5 and 6, as documented in the FY 2017 PB.

## Table 21
Total Quantity - Block Buy (GEO 5-6)
Quantity | SAR Baseline Production Estimate | Current APB Production | Current Estimate
RDT&E | 0 | 0 | 0
Procurement | 2 | 2 | 2
Total | 2 | 2 | 2
Quantity Notes
The above quantity represents two GEO satellites.

## Table 22
Cost and Funding
Funding Summary - Total Program
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | To Complete | Total
RDT&E | 9791.8 | 188.3 | 108.9 | 95.5 | 0 | 0 | 0 | 0 | 10184.5
Procurement | 4482.1 | 532.4 | 334.5 | 925.5 | 110.8 | 102.2 | 104 | 0 | 6591.5
MILCON | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57
Acq O&M | 161.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161.1
PB 2017 Total | 14492 | 720.7 | 443.4 | 1021 | 110.8 | 102.2 | 104 | 0 | 16994.1
PB 2016 Total | 14487.3 | 721.4 | 509.7 | 1088.5 | 119.6 | 111 | 118.3 | 0 | 17155.8
Delta | 4.7 | -0.7 | -66.3 | -67.5 | -8.8 | -8.8 | -14.3 | 0 | -161.7

## Table 23
Cost and Funding
Funding Summary - Baseline (GEO 1-4, HEO 1-2, and Ground)
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 9791.8 | 188.3 |  | 108.9 |  | 95.5 | 0 |  | 0 |  | 0 |  | 0 |  | 10184.5
Procurement | 2947.8 | 152.7 |  | 103.5 |  | 35.4 | 7.8 |  | 8 |  | 8.1 |  | 0 |  | 3263.3
MILCON | 57 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 57
Acq O&M | 161.1 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 161.1
PB 2017 Total | 12957.7 | 341 |  | 212.4 |  | 130.9 | 7.8 |  | 8 |  | 8.1 |  | 0 |  | 13665.9
PB 2016 Total | 12953 | 341.6 |  | 214.3 |  | 132 | 7.9 |  | 8 |  | 0 |  | 0 |  | 13656.8
Delta | 4.7 | -0.6 |  | -1.9 |  | -1.1 | -0.1 |  | 0 |  | 8.1 |  | 0 |  | 9.1
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 2 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 2
Production | 0 |  | 2 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 2
PB 2017 Total | 2 |  | 2 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 4
PB 2016 Total | 2 |  | 2 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 4
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0

## Table 24
Funding Summary - Block Buy (GEO 5-6)
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Procurement | 1534.3 | 379.7 |  | 231 |  | 890.1 | 103 |  | 94.2 |  | 95.9 |  | 0 |  | 3328.2
MILCON | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 1534.3 | 379.7 |  | 231 |  | 890.1 | 103 |  | 94.2 |  | 95.9 |  | 0 |  | 3328.2
PB 2016 Total | 1534.3 | 379.8 |  | 295.4 |  | 956.5 | 111.7 |  | 103 |  | 118.3 |  | 0 |  | 3499
Delta | 0 | -0.1 |  | -64.4 |  | -66.4 | -8.7 |  | -8.8 |  | -22.4 |  | 0 |  | -170.8
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Production | 0 |  | 2 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 2
PB 2017 Total | 0 |  | 2 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 2
PB 2016 Total | 0 |  | 2 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 2
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0

## Table 25
Cost and Funding
Annual Funding By Appropriation - Baseline (GEO 1-4, HEO 1-2, and Ground)
Annual Funding - Baseline (GEO 1-4, HEO 1-2, and Ground) 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 113
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 164
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 193
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 337.9
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 502.6
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 400
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 550.1
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 524.5
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 782.9
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 621.8
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 587.1
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 706.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 693
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 583.3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 542.4
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 521.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 501.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 603.9
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 368.3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 264.6
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 229.6
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 188.3
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 108.9
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 95.5
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 10184.5

## Table 26
Annual Funding - Baseline (GEO 1-4, HEO 1-2, and Ground) 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 1995 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 111.3
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 158.7
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 184.4
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 320.3
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 472.1
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 369.9
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 501.3
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 473.1
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 697.3
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 540.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 496.9
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 580.9
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 555
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 457.9
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 420.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 398.9
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 376.8
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 445.7
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 267.3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 189.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 162.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 131.5
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 74.7
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 64.3
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 8451.2

## Table 27
Funds for the Commercially Hosted Infrared Payload (CHIRP), project number A040, were excluded from this report. Those RDT&E funds are not associated with the baseline SBIRS program.
The excluded profile is (TY$): $39.8M
Funds for Space Modernization Initiative efforts, project number 7009, were excluded from this report. Those RDT&E funds are not associated with the baseline SBIRS program.
The excluded profile is (TY$): $831.9M
Funds for Evolved SBIRS, project number 7106, were excluded from this report. Those RDT&E funds are not associated with the baseline SBIRS program.
The excluded profile is (TY$): $2.2543B
PE0604441F is shared with HEO replenishment Payload's ground effort, which is not part of the MDAP. $39.7M in FY 2013 funds and $14.6M in FY 2016 funds associated with that effort are excluded from the report.

## Table 28
Annual Funding - Baseline (GEO 1-4, HEO 1-2, and Ground) 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | 160.3 |  | -- |  | 103.2 |  | 263.5 |  | 5.9 |  | 269.4
2009 |  | 1 | 949 |  | -- |  | 323.7 |  | 1272.7 |  | 21.3 |  | 1294
2010 |  | -- | 144.4 |  | 1.1 |  | 5.4 |  | 150.9 |  | 28.4 |  | 179.3
2011 |  | 1 | 583.5 |  | -- |  | 18.6 |  | 602.1 |  | 33 |  | 635.1
2012 |  | -- | 0.5 |  | 42.7 |  | 0.3 |  | 43.5 |  | 23.3 |  | 66.8
2013 |  | -- | 0.2 |  | 31.8 |  | 1.3 |  | 33.3 |  | 16.8 |  | 50.1
2014 |  | -- | 7.7 |  | 50.3 |  | 2.8 |  | 60.8 |  | 8.9 |  | 69.7
2015 |  | -- | 31.1 |  | 34.6 |  | 19.7 |  | 85.4 |  | 9.8 |  | 95.2
Subtotal |  | 2 | 1876.7 |  | 160.5 |  | 475 |  | 2512.2 |  | 147.4 |  | 2659.6

## Table 29
Annual Funding - Baseline (GEO 1-4, HEO 1-2, and Ground) 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | BY 1995 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | 125 |  | -- |  | 80.5 |  | 205.5 |  | 4.6 |  | 210.1
2009 |  | 1 | 729.9 |  | -- |  | 249 |  | 978.9 |  | 16.4 |  | 995.3
2010 |  | -- | 109.4 |  | 0.8 |  | 4.1 |  | 114.3 |  | 21.6 |  | 135.9
2011 |  | 1 | 433.4 |  | -- |  | 13.8 |  | 447.2 |  | 24.5 |  | 471.7
2012 |  | -- | 0.4 |  | 31.2 |  | 0.2 |  | 31.8 |  | 17 |  | 48.8
2013 |  | -- | 0.1 |  | 22.8 |  | 0.9 |  | 23.8 |  | 12 |  | 35.8
2014 |  | -- | 5.4 |  | 35.4 |  | 2 |  | 42.8 |  | 6.3 |  | 49.1
2015 |  | -- | 21.6 |  | 24.2 |  | 13.7 |  | 59.5 |  | 6.8 |  | 66.3
Subtotal |  | 2 | 1425.2 |  | 114.4 |  | 364.2 |  | 1903.8 |  | 109.2 |  | 2013

## Table 30
The Missile Procurement Air Force (MPAF) funding profile above represents funding for GEO satellites 3 and 4 as displayed in the associated P-5 exhibits in the FY 2017 PB. MPAF funds for HEO 3 and 4 payloads are excluded above, but are reflected in the associated P-5 exhibit in the FY 2017 PB.
The FYDP excluded profile is (TY$): $1.1108B
Cost Quantity Information - Baseline (GEO 1-4, HEO 1-2, and Ground) 3020 ¦ Procurement ¦ Missile Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 1995 $M
2008 | -- | --
2009 | 1 | 922.5
2010 | -- | --
2011 | 1 | 502.7
2012 | -- | --
2013 | -- | --
2014 | -- | --
2015 | -- | --
Subtotal | 2 | 1425.2

## Table 31
Annual Funding - Baseline (GEO 1-4, HEO 1-2, and Ground) 3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | 96.4 |  | 96.4
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | 3.6 |  | 3.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | 6.5 |  | 6.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | 3.8 |  | 3.8
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | 1.9 |  | 1.9
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | 2 |  | 2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | 24.7 |  | 24.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | 49.7 |  | 49.7
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | 39.6 |  | 39.6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | 28.6 |  | 28.6
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | 31.4 |  | 31.4
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | 288.2 |  | 288.2

## Table 32
Annual Funding - Baseline (GEO 1-4, HEO 1-2, and Ground) 3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year | Quantity |  | BY 1995 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | 84.1 |  | 84.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | 3 |  | 3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | 5.2 |  | 5.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | 3 |  | 3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | 1.5 |  | 1.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | 1.5 |  | 1.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | 18.6 |  | 18.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | 36.7 |  | 36.7
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | 28.8 |  | 28.8
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | 20.5 |  | 20.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | 22.3 |  | 22.3
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | 225.2 |  | 225.2

## Table 33
Other Procurement, Air Force funding for FY2016-2021 transferred to Space Procurement, Air Force.

## Table 34
Annual Funding - Baseline (GEO 1-4, HEO 1-2, and Ground) 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | 15.7 |  | 36.8 |  | 10 |  | 62.5 |  | 90.2 |  | 152.7
2017 |  | -- | -- |  | 71.5 |  | 24.5 |  | 96 |  | 7.5 |  | 103.5
2018 |  | -- | -- |  | 17.5 |  | 10.2 |  | 27.7 |  | 7.7 |  | 35.4
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | 7.8 |  | 7.8
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | 8 |  | 8
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | 8.1 |  | 8.1
Subtotal |  | -- | 15.7 |  | 125.8 |  | 44.7 |  | 186.2 |  | 129.3 |  | 315.5

## Table 35
Annual Funding - Baseline (GEO 1-4, HEO 1-2, and Ground) 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | BY 1995 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | 10.7 |  | 25.2 |  | 6.8 |  | 42.7 |  | 61.8 |  | 104.5
2017 |  | -- | -- |  | 48 |  | 16.5 |  | 64.5 |  | 5 |  | 69.5
2018 |  | -- | -- |  | 11.5 |  | 6.7 |  | 18.2 |  | 5.1 |  | 23.3
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | 5 |  | 5
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | 5.1 |  | 5.1
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | 5 |  | 5
Subtotal |  | -- | 10.7 |  | 84.7 |  | 30 |  | 125.4 |  | 87 |  | 212.4

## Table 36
The 3080 appropriation reduction for FY 2016 and beyond is due moving these funds to the new Space Procurement Air Force (SPAF) 3021 appropriation.
The SPAF funding profile above represents funding for GEO satellites 3 and 4 as displayed in the associated P-5 exhibits in the FY 2017 PB. MPAF funds for HEO 3 and 4 payloads are excluded above, but are reflected in the associated P-5 exhibit in the FY 2017 PB.
Total excluded funding over FYDP (TY$): $38.4M
The End Item Recurring Flyaway cost listed below is associated with a 3020 buy.
Cost Quantity Information - Baseline (GEO 1-4, HEO 1-2, and Ground) 3021 ¦ Procurement ¦ Space Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 1995 $M
2009 | -- | 5
2010 | -- | --
2011 | -- | 5.7
2012 | -- | --
2013 | -- | --
2014 | -- | --
2015 | -- | --
2016 | -- | --
2017 | -- | --
2018 | -- | --
2019 | -- | --
2020 | -- | --
2021 | -- | --
Subtotal | -- | 10.7

## Table 37
Annual Funding - Baseline (GEO 1-4, HEO 1-2, and Ground) 3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | TY $M
Total Program
1997 | 14.5
1998 | 14
1999 | --
2000 | --
2001 | 2.8
2002 | 18.8
2003 | 6.9
Subtotal | 57

## Table 38
Annual Funding - Baseline (GEO 1-4, HEO 1-2, and Ground) 3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | BY 1995 $M
Total Program
1997 | 13.7
1998 | 13.1
1999 | --
2000 | --
2001 | 2.5
2002 | 16.7
2003 | 6
Subtotal | 52

## Table 39
Annual Funding - Baseline (GEO 1-4, HEO 1-2, and Ground) 3400 ¦ Acq O&M ¦ Operation and Maintenance, Air Force
Fiscal Year | TY $M
Total Program
1998 | 10.4
1999 | 17
2000 | 15.6
2001 | 17.6
2002 | 18.2
2003 | 0.3
2004 | 6.9
2005 | 7
2006 | 5.4
2007 | 7.6
2008 | 9.7
2009 | 10.2
2010 | 10.2
2011 | 11.5
2012 | 13.5
Subtotal | 161.1

## Table 40
Annual Funding - Baseline (GEO 1-4, HEO 1-2, and Ground) 3400 ¦ Acq O&M ¦ Operation and Maintenance, Air Force
Fiscal Year | BY 1995 $M
Total Program
1998 | 8.1
1999 | 13.1
2000 | 11.9
2001 | 13.2
2002 | 13.5
2003 | 0.2
2004 | 4.9
2005 | 4.8
2006 | 3.6
2007 | 5
2008 | 6.3
2009 | 6.5
2010 | 6.4
2011 | 7.1
2012 | 8.2
Subtotal | 112.8

## Table 41
Annual Funding By Appropriation - Block Buy (GEO 5-6)
Annual Funding - Block Buy (GEO 5-6) 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2011 |  | -- | 103.6 |  | -- |  | 139.7 |  | 243.3 |  | -- |  | 243.3
2012 |  | -- | 192 |  | -- |  | 51.5 |  | 243.5 |  | -- |  | 243.5
2013 |  | 2 | 196.2 |  | -- |  | 89.8 |  | 286 |  | 22.1 |  | 308.1
2014 |  | -- | 311 |  | -- |  | 78.2 |  | 389.2 |  | 36.3 |  | 425.5
2015 |  | -- | 223.7 |  | -- |  | 60.1 |  | 283.8 |  | 30.1 |  | 313.9
Subtotal |  | 2 | 1026.5 |  | -- |  | 419.3 |  | 1445.8 |  | 88.5 |  | 1534.3

## Table 42
Annual Funding - Block Buy (GEO 5-6) 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | BY 1995 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2011 |  | -- | 76.9 |  | -- |  | 103.8 |  | 180.7 |  | -- |  | 180.7
2012 |  | -- | 140.2 |  | -- |  | 37.6 |  | 177.8 |  | -- |  | 177.8
2013 |  | 2 | 140.1 |  | -- |  | 64.1 |  | 204.2 |  | 15.8 |  | 220
2014 |  | -- | 219 |  | -- |  | 55 |  | 274 |  | 25.6 |  | 299.6
2015 |  | -- | 155.7 |  | -- |  | 41.9 |  | 197.6 |  | 20.9 |  | 218.5
Subtotal |  | 2 | 731.9 |  | -- |  | 302.4 |  | 1034.3 |  | 62.3 |  | 1096.6

## Table 43
The procurement profile above reflects procurement costs for the delivery of the GEO satellites 5 and 6, as documented in the FY 2017 PB. The costs above reflect the requirements for GEOs 5 and 6 production, launch, operations, checkout and support.
Cost Quantity Information - Block Buy (GEO 5-6) 3020 ¦ Procurement ¦ Missile Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 1995 $M
2011 | -- | --
2012 | -- | --
2013 | 2 | 731.9
2014 | -- | --
2015 | -- | --
Subtotal | 2 | 731.9

## Table 44
Annual Funding - Block Buy (GEO 5-6) 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | 296.6 |  | -- |  | 25.4 |  | 322 |  | 57.7 |  | 379.7
2017 |  | -- | 158.3 |  | 25.3 |  | 15.4 |  | 199 |  | 32 |  | 231
2018 |  | -- | 456.9 |  | 361.9 |  | 32.5 |  | 851.3 |  | 38.8 |  | 890.1
2019 |  | -- | 35.2 |  | -- |  | 3.6 |  | 38.8 |  | 64.2 |  | 103
2020 |  | -- | 33.6 |  | -- |  | 16.7 |  | 50.3 |  | 43.9 |  | 94.2
2021 |  | -- | 31.8 |  | -- |  | 7 |  | 38.8 |  | 57.1 |  | 95.9
Subtotal |  | -- | 1012.4 |  | 387.2 |  | 100.6 |  | 1500.2 |  | 293.7 |  | 1793.9

## Table 45
Annual Funding - Block Buy (GEO 5-6) 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | BY 1995 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | 202.9 |  | -- |  | 17.4 |  | 220.3 |  | 39.5 |  | 259.8
2017 |  | -- | 106.3 |  | 17 |  | 10.3 |  | 133.6 |  | 21.5 |  | 155.1
2018 |  | -- | 301 |  | 238.4 |  | 21.4 |  | 560.8 |  | 25.6 |  | 586.4
2019 |  | -- | 22.7 |  | -- |  | 2.3 |  | 25 |  | 41.5 |  | 66.5
2020 |  | -- | 21.3 |  | -- |  | 10.6 |  | 31.9 |  | 27.7 |  | 59.6
2021 |  | -- | 19.7 |  | -- |  | 4.3 |  | 24 |  | 35.5 |  | 59.5
Subtotal |  | -- | 673.9 |  | 255.4 |  | 66.3 |  | 995.6 |  | 191.3 |  | 1186.9

## Table 46
The procurement profile above reflects procurement costs for the delivery of the GEO satellites 5 and 6, as documented in the FY 2017 PB. The costs above reflect the requirements for GEOs 5 and 6 production, launch, operations, checkout and support.
The End Item Recurring Flyaway cost listed below is associated with a 3020 quantity buy.
Cost Quantity Information - Block Buy (GEO 5-6) 3021 ¦ Procurement ¦ Space Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 1995 $M
2013 | -- | 673.9
2014 | -- | --
2015 | -- | --
2016 | -- | --
2017 | -- | --
2018 | -- | --
2019 | -- | --
2020 | -- | --
2021 | -- | --
Subtotal | -- | 673.9

## Table 47
Low Rate Initial Production
Baseline (GEO 1-4, HEO 1-2, and Ground)
There is no LRIP for this program.
Block Buy (GEO 5-6)
There is no LRIP for this program.

## Table 48
Foreign Military Sales
Baseline (GEO 1-4, HEO 1-2, and Ground)
Country | Date of Sale | Quantity | Total Cost $M | Description
Australia 3/8/2012 0 18.0 The FMS case with Australia established the agreement for the sale of a SBIRS satellite data processor, satellite data interface system, and contractor logistics support.
Notes
Block Buy (GEO 5-6)
None
Nuclear Costs
Baseline (GEO 1-4, HEO 1-2, and Ground)
None
Block Buy (GEO 5-6)
None

## Table 49
Unit Cost
Baseline (GEO 1-4, HEO 1-2, and Ground)
Unit Cost Report
Item |  | BY 1995 $M | BY 1995 $M |  | % Change
|  | Current UCR Baseline (Feb 2013 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 11245.8 |  |  | 11066.6
Quantity | 4 |  |  | 4
Unit Cost | 2811.45 |  |  | 2766.65 |  | -1.59
Average Procurement Unit Cost
Cost | 2512 |  |  | 2450.6
Quantity | 2 |  |  | 2
Unit Cost | 1256 |  |  | 1225.3 |  | -2.44
Item |  | BY 1995 $M | BY 1995 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Mar 2006 APB)
Program Acquisition Unit Cost
Cost | 8569.3 |  |  | 11066.6
Quantity | 3 |  |  | 4
Unit Cost | 2856.433 |  |  | 2766.65 |  | -3.14
Average Procurement Unit Cost
Cost | 1342.8 |  |  | 2450.6
Quantity | 1 |  |  | 2
Unit Cost | 1342.8 |  |  | 1225.3 |  | -8.75

## Table 50
Baseline (GEO 1-4, HEO 1-2, and Ground)
Unit Cost History
Item |  |  |  | Date |  | BY 1995 $M | [5 empty] | TY $M
[6 empty] | PAUC |  |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Oct 1996 |  |  | 693.98 |  |  |  | N/A |  |  | 732.34 |  |  | N/A
APB as of January 2006 |  |  | Sep 2002 |  |  | 1467.64 |  |  |  | 420.5 |  |  | 1684.18 |  |  | 499.133
Revised Original APB |  |  | Mar 2006 |  |  | 2856.433 |  |  |  | 1342.8 |  |  | 3386.2 |  |  | 1723.2
Prior APB |  |  | Sep 2012 |  |  | 2811.45 |  |  |  | 1256 |  |  | 3461.25 |  |  | 1663.9
Current APB |  |  | Feb 2013 |  |  | 2811.45 |  |  |  | 1256 |  |  | 3461.25 |  |  | 1663.9
Prior Annual SAR |  |  | Dec 2014 |  |  | 2770.3 |  |  |  | 1220.65 |  |  | 3414.2 |  |  | 1625.5
Current Estimate |  |  | Dec 2015 |  |  | 2766.65 |  |  |  | 1225.3 |  |  | 3416.475 |  |  | 1631.65
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [12 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth |  |  | Spt | Total
829.460 29.725 169.190 129.200 126.600 1989.450 0.000 142.850 2587.015 3416.475

## Table 51
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [10 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt |  | Total
292.250 34.100 0.000 0.000 0.000 1019.600 0.000 285.700 1339.400 1631.650
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone I |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone II |  |  | N/A |  |  | Oct 1996 |  |  |  | N/A |  |  | Oct 1996
Milestone III |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
IOC |  |  | N/A |  |  | Dec 2003 |  |  |  | N/A |  |  | N/A
Total Cost (TY $M) |  |  | 2670.3 |  |  | 4147.3 |  |  |  | N/A |  |  | 13665.9
Total Quantity |  |  | N/A |  |  | 5 |  |  |  | N/A |  |  | 4
PAUC |  |  | N/A |  |  | 829.46 |  |  |  | N/A |  |  | 3416.475

## Table 52
Unit Cost Report
Item |  | BY 1995 $M | BY 1995 $M |  | % Change
|  | Current UCR Baseline (Feb 2013 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2681.6 |  |  | 2283.5
Quantity | 2 |  |  | 2
Unit Cost | 1340.8 |  |  | 1141.75 |  | -14.85
Average Procurement Unit Cost
Cost | 2681.6 |  |  | 2283.5
Quantity | 2 |  |  | 2
Unit Cost | 1340.8 |  |  | 1141.75 |  | -14.85
Item |  | BY 1995 $M | BY 1995 $M |  | % Change
|  | Original UCR Baseline (Sep 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2681.6 |  |  | 2283.5
Quantity | 2 |  |  | 2
Unit Cost | 1340.8 |  |  | 1141.75 |  | -14.85
Average Procurement Unit Cost
Cost | 2681.6 |  |  | 2283.5
Quantity | 2 |  |  | 2
Unit Cost | 1340.8 |  |  | 1141.75 |  | -14.85

## Table 53
Unit Cost History
Item |  |  |  | Date |  | BY 1995 $M | [5 empty] | TY $M
[6 empty] | PAUC |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  |  | Sep 2012 |  |  | 1340.8 |  |  | 1340.8 |  |  |  | 1932.7 |  |  | 1932.7
APB as of January 2006 |  |  | N/A |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Prior APB |  |  | Sep 2012 |  |  | 1340.8 |  |  | 1340.8 |  |  |  | 1932.7 |  |  | 1932.7
Current APB |  |  | Feb 2013 |  |  | 1340.8 |  |  | 1340.8 |  |  |  | 1932.7 |  |  | 1932.7
Prior Annual SAR |  |  | Dec 2014 |  |  | 1191.2 |  |  | 1191.2 |  |  |  | 1749.5 |  |  | 1749.5
Current Estimate |  |  | Dec 2015 |  |  | 1141.75 |  |  | 1141.75 |  |  |  | 1664.1 |  |  | 1664.1
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Production Estimate | Changes | [12 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch | Eng | Est | Oth |  |  | Spt | Total
1932.700 26.300 0.000 0.000 0.000 -212.000 0.000 -82.900 -268.600 1664.100

## Table 54
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Production Estimate | Changes | [10 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt |  | Total
1932.700 26.300 0.000 0.000 0.000 -212.000 0.000 -82.900 -268.600 1664.100
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone C |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
IOC |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Total Cost (TY $M) |  |  | N/A |  |  | N/A |  |  |  | 3865.4 |  |  | 3328.2
Total Quantity |  |  | N/A |  |  | N/A |  |  |  | 2 |  |  | 2
PAUC |  |  | N/A |  |  | N/A |  |  |  | 1932.7 |  |  | 1664.1

## Table 55
Cost Variance
Baseline (GEO 1-4, HEO 1-2, and Ground)
Summary TY $M
Item | RDT&E | Procurement |  | MILCON |  | Acq O&M |  | Total
SAR Baseline (Development Estimate)
Previous Changes
3386.5 584.5 28.5 147.8 4147.3
Economic | 19.1 |  | 72.3 |  | -1.4 |  | 1.9 |  | 91.9
Quantity | -152.7 |  | -- |  | -- |  | -- |  | -152.7
Schedule | 516.8 |  | -- |  | -- |  | -- |  | 516.8
Engineering | 514.2 |  | -- |  | 7.8 |  | -15.6 |  | 506.4
Estimating | 5903.8 |  | 2032.9 |  | 22.1 |  | 27 |  | 7985.8
Other | -- |  | -- |  | -- |  | -- |  | --
Support | -- |  | 561.3 |  | -- |  | -- |  | 561.3
Subtotal | 6801.2 |  | 2666.5 |  | 28.5 |  | 13.3 |  | 9509.5
Current Changes Economic | -4 |  | -4.1 |  | -- |  | 35.1 |  | 27
Quantity | -- |  | -- |  | -- |  | -- |  | --
Schedule | -- |  | -- |  | -- |  | -- |  | --
Engineering | -- |  | -- |  | -- |  | -- |  | --
Estimating | 0.8 |  | 6.3 |  | -- |  | -35.1 |  | -28
Other | -- |  | -- |  | -- |  | -- |  | --
Support | -- |  | 10.1 |  | -- |  | -- |  | 10.1
Subtotal | -3.2 |  | 12.3 |  | -- |  | -- |  | 9.1
Total Changes | 6798 |  | 2678.8 |  | 28.5 |  | 13.3 |  | 9518.6
CE - Cost Variance | 10184.5 |  | 3263.3 |  | 57 |  | 161.1 |  | 13665.9
CE - Cost & Funding | 10184.5 |  | 3263.3 |  | 57 |  | 161.1 |  | 13665.9

## Table 56
Summary BY 1995 $M
Item | RDT&E | Procurement | MILCON | Acq O&M | Total
SAR Baseline (Development Estimate) | 3016.6 | 496.7 | 26 | 140.2 | 3679.5
Previous Changes
Economic | -- | -- | -- | -- | --
Quantity | -128.4 | -- | -- | -- | -128.4
Schedule | 384.8 | -- | -- | -- | 384.8
Engineering | 460.5 | -- | 6.8 | -13.5 | 453.8
Estimating | 4717 | 1528.2 | 19.2 | 10.7 | 6275.1
Other | -- | -- | -- | -- | --
Support | -- | 416.4 | -- | -- | 416.4
Subtotal | 5433.9 | 1944.6 | 26 | -2.8 | 7401.7
Current Changes
Economic | -- | -- | -- | -- | --
Quantity | -- | -- | -- | -- | --
Schedule | -- | -- | -- | -- | --
Engineering | -- | -- | -- | -- | --
Estimating | 0.7 | 4.3 | -- | -24.6 | -19.6
Other | -- | -- | -- | -- | --
Support | -- | 5 | -- | -- | 5
Subtotal | 0.7 | 9.3 | -- | -24.6 | -14.6
Total Changes | 5434.6 | 1953.9 | 26 | -27.4 | 7387.1
CE - Cost Variance | 8451.2 | 2450.6 | 52 | 112.8 | 11066.6
CE - Cost & Funding | 8451.2 | 2450.6 | 52 | 112.8 | 11066.6
Previous Estimate: December 2014

## Table 57
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -4
Adjustment for current and prior escalation. (Estimating) | 1.8 | 2.6
Revised estimate to reflect application of Department-wide inflationary adjustments. (Estimating) | -1.1 | -1.8
RDT&E Subtotal | 0.7 | -3.2
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -4.1
Adjustment for current and prior escalation. (Estimating) +1.3 +1.8
Revised estimate for MPAF as a result of realignment of Other Government Costs (OGCs) Missile Procurement, Air Force (MPAF). (Estimating)
Revised estimate due to incorporation of additional funding for OGC (Space Procurement, Air Force (SPAF)). (Estimating)
+2.6 +3.9
+0.3 +0.5
Revised estimate for OPAF as a result of inflation adjustment. (Estimating) +0.1 +0.1
Adjustment for current and prior escalation. (Support) +0.8 +1.0
Increase in Other Support for MPAF due to the realigning of OGC flyaway to support costs (MPAF). (Support)
Decrease in Other Support as a result of reducing reserve funds based on program maturity (Other Procurement, Air force (OPAF)). (Support)
-2.6 -3.9
-79.8 -115.9
Increase in Other Support due to the realignment of funds from OPAF to SPAF. (Support) | 86.6 | 128.9
Procurement Subtotal | 9.3 | 12.3
Acq O&M | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 35.1
Adjustment for current and prior escalation. (Estimating) | -24.6 | -35.1
Acq O&M Subtotal | -24.6 | 0

## Table 58
Cost Variance
Block Buy (GEO 5-6)
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | -- | 3865.4 | -- | 3865.4
Previous Changes
Economic | -- | 72.5 | -- | 72.5
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | -452.9 | -- | -452.9
Other | -- | -- | -- | --
Support | -- | 14 | -- | 14
Subtotal | -- | -366.4 | -- | -366.4
Current Changes
Economic | -- | -19.9 | -- | -19.9
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | 28.9 | -- | 28.9
Other | -- | -- | -- | --
Support | -- | -179.8 | -- | -179.8
Subtotal | -- | -170.8 | -- | -170.8
Total Changes | -- | -537.2 | -- | -537.2
CE - Cost Variance | -- | 3328.2 | -- | 3328.2
CE - Cost & Funding | -- | 3328.2 | -- | 3328.2

## Table 59
Summary BY 1995 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | -- | 2681.6 | -- | 2681.6
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | -305.4 | -- | -305.4
Other | -- | -- | -- | --
Support | -- | 6.2 | -- | 6.2
Subtotal | -- | -299.2 | -- | -299.2
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | 18.5 | -- | 18.5
Other | -- | -- | -- | --
Support | -- | -117.4 | -- | -117.4
Subtotal | -- | -98.9 | -- | -98.9
Total Changes | -- | -398.1 | -- | -398.1
CE - Cost Variance | -- | 2283.5 | -- | 2283.5
CE - Cost & Funding | -- | 2283.5 | -- | 2283.5
Previous Estimate: December 2014

## Table 60
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -19.9
Adjustment for current and prior escalation. (Estimating) +4.6 +6.8
Revised estimate due primarily to realigning the Aerospace Weapon System (WS) and rate update on the overall Aerospace requirement (MPAF). (Estimating)
Revised estimate due primarily to realigning the Aerospace WS and rate update on the overall Aerospace requirement (SPAF). (Estimating)
Revised estimate to reflect application of Department-wide inflationary adjustments. (MPAF) (Estimating)
+8.2 +11.7
+5.7 +10.6
0.0 -0.2
Adjustment for current and prior escalation. (Support) +0.7 +0.8 Decrease in Other Support due to the transfer of FY 2015 funds to SPAF (MPAF). (Support) -8.2 -11.5
Decrease in Other Support due to reduction of reserve funds based on program maturity and transfer of funds from MPAF (SPAF). (Support)
-109.9 -169.1
Procurement Subtotal -98.9 -170.8

## Table 61
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: SBIRS 5-6 Initial Non-Recurring Engineering
Contractor: Lockheed Martin Corporation Contractor Location: Sunnyvale, CA 94089 Contract Number: FA8810-12-C-0001
Contract Type: Cost Plus Incentive Fee (CPIF)
Award Date: September 10, 2012
Definitization Date: September 11, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
81.9 N/A N/A 147.1 N/A N/A 141.2 148.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the GEO 5 and 6 Initial Non-Recurring Engineering (I-NRE) contract being awarded in September 2012, with an Engineering Change Proposal (ECP) to modify the contract to complete all component builds through component qualification added in December 2012. It is a CPIF contract with a Contract Target Price of $148.6M, which includes the I-NRE and the ECP.
There is no contract quantity associated with this I-NRE contract.
The Contractor Estimated Price at Completion is $141.2M compared to $147.3M in the December 2014 SAR. The decrease is due to EAC efficiencies in Payload Systems Engineering, Integration and Test support. The Government’s Estimated Price at Completion remains at $148.6M.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/30/2016) +5.8 -0.1
Previous Cumulative Variances +8.6 +12.8
Net Change -2.8 -12.9
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to the prime contractor using additional resources to closeout the manufacturing Special Test Equipment activity.
The unfavorable net change in the schedule variance is due to pending budget allocations being added into the baseline and delays with Space Bus Communications unit assemblies.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 62
Contract Identification
Appropriation: Procurement
Contract Name: SBIRS Follow-on Production Contractor: Lockheed Martin Corporation Contractor Location: Sunnyvale, CA 94089 Contract Number: FA8810-08-C-0002
Contract Type: Cost Plus Award Fee (CPAF)
Award Date: March 14, 2008
Definitization Date: June 07, 2010
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
370.0 N/A 0 3206.7 N/A 4 3266.3 3341.3
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to additional scope. The Initial Contract Price Target included HEO 3 and GEO 3 long lead effort ($370.0M). Since then the Program Office exercised the HEO 3 and 4 and GEO 3 and 4 production efforts, HEO 3 ground modification effort, Launch Vehicle Integration, launch and Early On-Orbit Support and various special studies, all on separate contract line items. The increased quantity from zero to four is due to the contract award of the HEO 3-4 and GEO 3-4 production efforts.
The contractor Estimated Price at Completion of $3,266.3M, as compared to the December 2014 SAR, is primarily due to additional scope added for the GEO 3-4 Initial Launch Capability (ILC) Modification and the GEO-3 six-month storage extension. The Government’s Estimated Price at Completion is $3,341.3M, derived from the 2015 Single Best Estimate, which assumes GEO-3 entering storage in July 2015 and GEO-4 Ready to Ship in February 2016. The HEO-3 Payload was delivered in June 2013 and the HEO-4 Payload was delivered May 2015.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/31/2016) -21.5 -13.8
Previous Cumulative Variances -7.1 -65.4
Net Change -14.4 +51.6
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to incorporating the ILC modification into the contract baseline.
The favorable net change in the schedule variance is due to baselining and realigning of the GEO 3 4 ILC work scope that was awarded in April 2015.

## Table 63
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 64
Contract Identification
Appropriation: Procurement
Contract Name: SBIRS GEO 5-6 Advance Procurement/Production
Contractor: Lockheed Martin Corporation Contractor Location: Sunnyvale, CA 94089 Contract Number: FA8810-13-C-0001
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: February 19, 2013
Definitization Date: February 19, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
284.4 N/A 0 1955.2 1967.6 2 1950.8 1955.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to added scope. The initial contract price included the GEO 5-6 Advance Procurement (AP) effort on February 19, 2013. The Program Office added an Engineering Change Proposal (ECP) on September 19, 2013. The Production portion of the contract was awarded on June 24, 2014. The entire GEO 5-6 Contract consists of AP (plus the ECP) and Production efforts. This is a Fixed Price Incentive Fee contract with a Contractor Target Price of $1,955.2M. The increase of $7.6M from the last SAR is due to the award of the GEO 5-6 Tech Refresh contract modification.
There is no contract quantity associated with the AP portion of this contract. The change in quantity reflects the award of the GEO 5-6 Production effort. The Contractor Estimated Price at Completion is $1,950.8M, which represents the initial AP (plus ECP) & Production award. The Government Estimated Price at Completion is $1,955.2M.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/31/2016) +24.5 +29.7
Previous Cumulative Variances +17.4 +35.3
Net Change +7.1 -5.6
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to efficiencies with Northrop Grumman payload supplies and level of effort underruns in management.
The unfavorable net change in the schedule variance is due to a Single Point Adjustment (SPA) implemented August 30, 2015, which reduced the majority of the prime contractor's positive variance. This SPA corresponded to the technical and schedule re-baselining for Tech Refresh.

## Table 65
Contract Identification
Appropriation: Acq O&M
Contract Name: SBIRS CLS-CTF
Contractor: Lockheed Martin Corporation Contractor Location: Sunnyvale, CA 94089 Contract Number: FA8810-13-C-0002
Contract Type: Cost Plus Incentive Fee (CPIF)
Award Date: March 15, 2013
Definitization Date: March 15, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
105.9 N/A N/A 746.1 N/A N/A 737.4 746.1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to added scope. The Contractor Logistics Support and Combined Task Force (CLS/CTF) contract was awarded in March 2013 with a negotiated contract cost of $95.7M. The SBIRS Survivable Endurable Evolution (S2E2) ground mobiles added in July 2013 increased the negotiated cost by $67M. An additional FY 2014 CLS effort was awarded in September 2013 for $105M. In September 2014, the following were awarded: FY 2015 option for $84.6M, FY 2015 Factory Support for $39.5M, Sustainment Support Studies and System Modification for $37.1M, Environmental Control Unit (ECU) Request for Equitable Adjustment (REA) for
$1.3M and High Altitude Electromagnetic Pulse hatch door REA for $68K. S2E2 Increment 2 was awarded in November 2014 for $56M, bringing the total negotiated cost to $486.9M. The following contract changes also occurred: June 2015, Interim Mission Control Station Backup de-scope for $1.1M; Block 10 support studies for $737K awarded in July 2015 and FY 2016 Operations crew and Organic Depot Maintenance option exercised for $73.9M in September 2015. October 2015 awards included: FY 2016 Factory support for $42.1M, FY 2015 Sustainment studies and System modification for $37.6M, and CTF Monotrack extension for $39.8M. The total negotiated cost plus target fees equal to the total contractor Target price of $746.1M as of January 31, 2016.
The Contractor Estimated Price at Completion is $737.4M, which represents the initial CLS/CTF portion and its FY 2014 and FY 2015 options, S2E2 Mobile Ground Terminal (SMGT) 1-4, Track Data Relay, GEO capability upgrade, System Test Environment, and Mission Specific Vendor Plug-ins. The Government Estimated Price at Completion is $746.1M.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/31/2016) +27.2 -5.1
Previous Cumulative Variances +12.2 -3.3
Net Change +15.0 -1.8
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to level of effort underruns for sustainment efforts.
The unfavorable net change in the schedule variance is due to late sub-contractor contract award, material delay due to delay in SMGT shelters delivery, and sub-contractor late delivery of Heat Exchanger and ECU.

## Table 66
Notes
The contract consists of CLS (APPN 3400), CTF (APPN 3600), and S2E2 Blocks 1 & 2 (APPN 3080).
Although this contract is designated Acq O&M (APPN 3400) the bulk of the funds are non-Acq O&M APPN 3400 funds. This contract also includes some Procurement and RDT&E funding, but the predominance of non-Acq O&M funding supports a key milestone in the IOC of the SBIRS program and therefore, this contract is included in the SAR.

## Table 67
Deliveries and Expenditures
Baseline (GEO 1-4, HEO 1-2, and Ground)
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 2 | 2 | 2 | 100%
Production | 1 | 1 | 2 | 50%
Total Program Quantity Delivered | 3 | 3 | 4 | 75%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
13665.9
12761.6
93.38%
27
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
22
81.48%
13298.7
97.31%
The above data is current as of February 09, 2016.
Block Buy (GEO 5-6)
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 0 | 0 | 2 | 0%
Total Program Quantity Delivered | 0 | 0 | 2 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
3328.2
404.9
12.17%
11
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
6
54.55%
1914
57.51%
The above data is current as of February 09, 2016.

## Table 68
Operating and Support Cost
Baseline (GEO 1-4, HEO 1-2, and Ground)
Cost Estimate Details
Date of Estimate: October 01, 2014
Source of Estimate: POE
Quantity to Sustain: 1
Unit of Measure: Integrated System
Service Life per Unit: 35.00 Years
Fiscal Years in Service: FY 1999 - FY 2033
O&M funds support the activation of the SBIRS High System, including Component ground operating and training facilities at worldwide sites. The SBIRS Increment 1 ground system was operational in December 2001. These funds purchase temporary facilities, minor construction, office equipment, furniture, travel, supplies, and communication links necessary for the activation of the SBIRS Mission Control Station, the Mission Control Station Backup, Outside Continental United States Relay Ground Stations, Initial Qualification Training facility, and repair and transportation of Government Furnished Equipment and Temporary Duty costs for training of the initial cadre of operators. Also included in this estimate are all manpower and indirect costs required to operate and sustain the SBIRS system.
The Quantity to Sustain of one Integrated System encompasses the four GEO satellites, two HEO payloads and the associated ground infrastructure. The mission and the sustainment costs cannot be assigned to individual satellites. There are two different satellites and one sensor (three constellations) supported by the same Level I and II maintenance/operations and on-orbit sustainment costs. All pieces together are required to meet the mission.
Ground Rules and Assumptions: 35 years service life start date (1999) is based upon increment 1 entry into Development Test/Operational Test and end date (2033) is based upon final GEO 6 satellite and 12 year service life for SBIRS system.
Sustainment Strategy
The current SBIRS sustainment strategy is Contractor Logistics Support (CLS) under one contract with a balanced fee structure of performance and cost incentives with limited organic depot partnership.
The SBIRS High Baseline subprogram profile reflects the first 30 years of the 35 year SBIRS High Life Cycle Cost, from 1999-2028. The average annual costs are based on the entire 35 year life cycle.
Antecedent Information
Comparable O&S cost estimates for the legacy system, Defense Support Program, are not available.

## Table 69
Annual O&S Costs BY1995 $M
Cost Element |  | Baseline (GEO 1-4, HEO 1-2, And Ground) Average Annual Cost Per Integrated System | [5 empty] | Defense Support Program (Antecedent) N/A
Unit-Level Manpower |  | 64.2 | [5 empty] | 0
Unit Operations |  | 2.9 | [5 empty] | 0
Maintenance |  | 34.2 | [5 empty] | 0
Sustaining Support |  | 37.9 | [5 empty] | 0
Continuing System Improvements |  | 6.4 | [5 empty] | 0
Indirect Support |  | 4.4 | [5 empty] | 0
Other |  | 0 | [5 empty] | 0
Total |  | 150 | [5 empty] | --
Unitized costs reflect the Average Annual O&S cost for the SBIRS High system.
Item | Total O&S Cost $M
| Baseline (GEO 1-4, HEO 1-2, And Ground) | [7 empty] | Defense Support Program (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 4203.4 |  |  | 4623.7 |  |  | 4390.2 |  | N/A
Then Year | 6404.5 |  |  | N/A |  |  | 6764.5 |  | N/A
Equation to Translate Annual Cost to Total Cost
Average annual O&S cost of SBIRS High System = (Total O&S cost of SBIRS High Baseline + Total O&S cost of SBIRS High Block Buy)/service life of system = ($4390.2M + $861.8M) / 35Yrs = $150.06M ($0.06M delta from Unitized cost total due to rounding).
O&S Cost Variance
Category |  |  | BY 1995 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
4390.2
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 4390.2
No change from previous year

## Table 70
Disposal Estimate Details
Date of Estimate: Source of Estimate:
Disposal/Demilitarization Total Cost (BY 1995 $M):
Disposal costs have not been estimated at this time.

## Table 71
Block Buy (GEO 5-6)
Cost Estimate Details
Date of Estimate: October 01, 2014
Source of Estimate: POE
Quantity to Sustain: 1
Unit of Measure: Integrated System
Service Life per Unit: 35.00 Years
Fiscal Years in Service: FY 1999 - FY 2033
O&M funds support the activation of the SBIRS High System, including Component ground operating and training facilities at worldwide sites. The SBIRS Increment 1 ground system was operational in December 2001. These funds purchase temporary facilities, minor construction, office equipment, furniture, travel, supplies, and communication links necessary for the activation of the SBIRS Mission Control Station, the Mission Control Station Backup, Outside Continental United States Relay Ground Stations, Initial Qualification Training facility, and repair and transportation of Government Furnished Equipment and Temporary Duty costs for training of the initial cadre of operators. Also included in this estimate are all manpower and indirect costs required to operate and sustain the SBIRS system.
The Quantity to Sustain of one Integrated System encompasses the four GEO satellites, two HEO payloads and the associated ground infrastructure. The mission and the sustainment costs cannot be assigned to individual satellites. There are two different satellites and one sensor (three constellations) supported by the same Level I and II maintenance/operations and on-orbit sustainment costs. All pieces together are required to meet the mission.
Ground Rules and Assumptions: 35 years service life start date (1999) is based upon increment 1 entry into Development Test/Operational Test and end date (2033) is based upon final GEO 6 satellite and 12 year service life for SBIRS system.
Sustainment Strategy
The current SBIRS sustainment strategy is Contractor Logistics Support (CLS) under one contract with a balanced fee structure of performance and cost incentives with limited organic depot partnership.
The SBIRS High Baseline subprogram profile reflects the first 30 years of the 35 year SBIRS High Life Cycle Cost, from 1999-2028. The average annual costs are based on the entire 35 year life cycle.
Antecedent Information
Comparable O&S cost estimates for the legacy system, Defense Support Program, are not available.

## Table 72
Annual O&S Costs BY1995 $M
Cost Element |  | Block Buy (GEO 5-6) Average Annual Cost Per Integrated System | [5 empty] | Defense Support Program (Antecedent) N/A
Unit-Level Manpower |  | 64.2 | [5 empty] | 0
Unit Operations |  | 2.9 | [5 empty] | 0
Maintenance |  | 34.2 | [5 empty] | 0
Sustaining Support |  | 37.9 | [5 empty] | 0
Continuing System Improvements |  | 6.4 | [5 empty] | 0
Indirect Support |  | 4.4 | [5 empty] | 0
Other |  | 0 | [5 empty] | 0
Total |  | 150 | [5 empty] | --
Unitized costs reflect the Average Annual O&S cost for the SBIRS High system.
Item | Total O&S Cost $M
| Block Buy (GEO 5-6) | [7 empty] | Defense Support Program (Antecedent)
| Current Production APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 795.3 |  |  | 874.8 |  |  | 861.8 |  | N/A
Then Year | 1551.1 |  |  | N/A |  |  | 1748.2 |  | N/A
Equation to Translate Annual Cost to Total Cost
Average annual O&S cost of SBIRS High System = (Total O&S cost of SBIRS High Baseline + Total O&S cost of SBIRS High Block Buy)/service life of system = ($4390.2M + $861.8M) / 35Yrs = $150.06M ($0.06M delta from Unitized cost total due to rounding).
O&S Cost Variance
Category |  |  | BY 1995 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
861.8
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 861.8
No change from previous year.

## Table 73
Disposal Estimate Details
Date of Estimate: Source of Estimate:
Disposal/Demilitarization Total Cost (BY 1995 $M):
Disposal costs have not been estimated at this time.