## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-277
Airborne Warning and Control System Block 40/45 Upgrade (AWACS Blk 40/45 Upgrade)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 12
Cost and Funding 13
Low Rate Initial Production 21
Foreign Military Sales 22
Nuclear Costs 22
Unit Cost 23
Cost Variance 26
Contracts 29
Deliveries and Expenditures 31
Operating and Support Cost 32

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Airborne Warning and Control System Block 40/45 Upgrade (AWACS Blk 40/45 Upgrade)
DoD Component
Air Force
Responsible Office
Mr. Thomas Ramsey
3001 Staff Drive, Suite 2AH198C Tinker AFB, OK 73145
thomas.ramsey@us.af.mil
Phone: | 405-736-2370
Fax: | 405-736-5412
DSN Phone: | 336-2370
DSN Fax: | 336-5412
Date Assigned: | February 4, 2015
References
SAR Baseline (Production Estimate)
Air Force Acquisition Executive (AFAE) Approved Acquisition Program Baseline (APB) dated May 1, 2013
Approved APB
Air Force Acquisition Executive (AFAE) Approved Acquisition Program Baseline (APB) dated October 20, 2015

## Table 6
Mission and Description
The Airborne Warning and Control System (AWACS) provides a highly mobile, flexible, survivable theater Battle Management (BM), Wide Area Surveillance, and Command and Control (C2) capability. It is capable of detecting, identifying, and tracking airborne and maritime targets at extended ranges as well as identifying air/ground emitters. AWACS can relay “big picture” information to C2 agencies and friendly aircraft. AWACS provides worldwide response to situations requiring immediate on-scene C2/BM using embedded real-time surveillance for employment of US and allied combat air forces.
AWACS is critical to gaining and maintaining battle-space air superiority. AWACS coordinates with both tactical and C2 assets in theater to execute the air mission.
The AWACS Block 40/45 Upgrade program is the largest modification in U.S. AWACS history and represents the critical foundation and baseline system required for all future AWACS enterprise modifications including net-centric operations. The AWACS Block 40/45 Upgrade provides a single target/single track capability with an improved human-machine interface for time-critical targeting designed to increase combat effectiveness and reduce fratricide. The AWACS Block 40/45 Upgrade program includes an upgrade to Electronic Support Measures sensor data processing; Multi-Source Integration; a Data Link Infrastructure with prioritized data link bandwidth management for Link 16/Link 11; new battle management tools; capability to parse, allow user access to, and integrate Air Control Order/Air Tasking Order data; enhanced mission and console recording capabilities; and an update to a low-bandwidth internet chat capability (Secure Iridium Chat).

## Table 7
Executive Summary
The AWACS Block 40/45 Upgrade program remains funded for a fleet size of 24. In the FY 2016 PB, the Air Force re- phased the E-3 force reduction of seven aircraft to FY 2019. The AWACS Block 40/45 Upgrade program is already positioned in accordance with the planned FY 2019 divestiture; therefore, the program will continue to execute to a baseline of 24 aircraft.
Since submission of the June 2015 SAR, the program office completed the SCP, signed by the Assistant Secretary of the Air Force for Financial Management and Comptroller (SAF/FM) on July 31, 2015. An APB amendment was signed by the Air Force Acquisition Executive on October 20, 2015.
The AWACS Block 40/45 Upgrade program continues to meet all KPPs. During CY 2015, AWACS Block 40/45 installation and deliveries remained on schedule despite several aircraft having experienced delays due to maintenance issues unrelated to Block 40/45 installation. As of December 31, 2015, ten modified aircraft have been delivered.
In FY 2017, we intend to procure the last Commercial Off The Shelf (COTS) necessary to install 40/45 on four aircraft and refresh the six LRIP aircraft to the final configuration. The FY 2017 PB position/FYDP funding profile does not include funding to purchase COTS for any of the seven aircraft the Air Force intends to retire. If these seven aircraft are subsequently retained and modified, significant Non-Recurring Engineering may be necessary to address any COTS no longer available.
There are no significant software-related issues at this time. However, the program office is engaged with Boeing on how to control the cost of emerging cyber security requirements and the integration of urgent operational needs for internet connectivity into 40/45 hardware/software baseline.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B - System Development and Demonstration | Jul 2003 | Jul 2003 | Jul 2003 | Jul 2003
Milestone C - Low-Rate Initial Production | Jan 2009 | Jan 2009 | Jan 2009 | Jan 2009
Initial Operational Test and Evaluation Complete (IOT&E) | Jun 2012 | Jun 2012 | Jun 2012 | Jun 2012
Full Rate Production Decision | Dec 2012 | Dec 2012 | Dec 2012 | Dec 2012
IOC RAA | Apr 2014 | Jan 2014 | Jan 2014 | Jan 2014
FOC RAA | Aug 2020 | Aug 2020 | Feb 2021 | Aug 2020
Change Explanations
Notes
Current estimate dates are based on FY 2017 PB and 24 aircraft fleet size. IOC RAA was declared by the PM on January 7, 2014 and Air Combat Command declared IOC on July 28, 2014.
Acronyms and Abbreviations
FOC RAA - Full Operational Capability - Required Assets Available IOC RAA - Initial Operational Capability - Required Assets Available

## Table 10
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Multi-Source Integration
(Objective = | (Objective = | All target data shall be | The Beyond LRIP | The Beyond
Threshold) All target | Threshold) All target | correlated, fused, and | report confirms the | LRIP report
data shall be | data shall be | integrated into a single | system meets | confirms the
correlated, fused, and | correlated, fused, and | track | required threshold | system meets
integrated into a single | integrated into a single |  | performance. | required
track | track |  |  | threshold
performance.
Net Ready
System must fully | System must fully | System must fully | Per Joint | Each
support execution of all | support execution of all | support execution of joint | Interoperability Test | version/release
activities identified in | activities identified in | critical activities identified | Command letter dated | of Block 40/45
joint and system | joint and system | in joint and system | October 25, 2012, | continues to be
integrated | integrated | integrated architectures. | "The AWACS Block | approved for
architectures. 1) DISR | architectures. 1) DISR | System must satisfy the | 40/45 Upgrade, | use by an IATO
mandated GIG IT | mandated GIG IT | technical requirements | V10.1.20i meets the | or ATO.
standards and profiles | standards and profiles | for future transition to Net | joint critical
identified in the TV-1. | identified in the TV-1. | -Centric operations to | interoperability
2) DISR mandated | 2) DISR mandated | include: 1) DISR | requirements in the
GIG KIPs identified in | GIG KIPs identified in | mandated GIG IT | Joint Staff-certified
the KIP declaration | the KIP declaration | standards and profiles | AWACS Block 40/45
table. 3) Net-Centric | table. 3) Net-Centric | identified in the TV-1; 2) | Upgrade Program ISP,
Operations and | Operations and | DISR mandated GIG | 17 October 2011". Air
Warfare Reference | Warfare Reference | KIPs identified in the KIP | Force C2 Platform
Model Enterprise | Model Enterprise | declaration table; 3) Net- | Information
Services. 4) IA | Services. 4) IA | Centric Operations and | Technology DAA
requirements and | requirements and | Warfare Reference | issued an IATO on
issuance of an ATO by | issuance of an ATO by | Model Enterprise | January 11, 2012.
the DAA. 5) | the DAA. 5) | Services; 4) IA | Subsequent lATOs
Operationally-effective | Operationally-effective | requirements and | and ATOs have been
information exchanges | information exchanges | issuance of an IATO by | introduced for each
and mission critical | and mission critical | the DAA; 5) Operationally | software version
performance specified | performance specified | -effective information | afterwards.
in the applicable joint | in the applicable joint | exchanges and mission
and system integrated | and system integrated | critical performance
architecture views. | architecture views. | specified in the
applicable joint and
system integrated
architecture views.
Classified Performance information is provided in the classified annex to this submission.

## Table 11
Requirements Reference
ORD (Combat Air Forces 010-02-I/II) dated June 16, 2009 (in lieu of CPD)
Change Explanations
None
Acronyms and Abbreviations
AEW&C - Airborne Early Warning and Control ATO - Approval to Operate
DAA - Designated Approving Authority
DISR - Department of Defense Information Technology Standards Registry DOT&E - Director of Operational Test & Evaluation
GIG - Global Information Grid IA - Information Assurance
IATO - Interim Approval to Operate ISP - Information Support Plan
IT - Information Technology KIP - Key Interface Profile TV-1 - Technical View 1

## Table 12
Track to Budget
RDT&E
Appn |  | BA | PE
Air Force 3600 07 0207417F
Project | Name
67411L AWACS (Shared)
Procurement
Appn |  | BA | PE
Air Force 3010 06 0207417F
Line Item Name
000999 Initial Spares (Shared)
Air Force 3010 05 0207417F
Line Item Name
E00300 E-3 (Shared)
E34045 Airborne Warning and Control Systems
Notes
The Procurement funding for the AWACS Block 40/45 Upgrade program is located in modification number 50001T.
Funding for this modification is located in two P-1 Line Item Numbers. AWACS Block 40/45 funding had previously been contained in Weapon System Code (WSC) E00300, but as part of the Major Programs Transparency Initiative and starting in FY 2015, the AWACS Block 40/45 Upgrade was moved to WSC E34045. Prior year funding remains in WSC E00300.

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2012 $M |  |  |  | BY 2012 $M |  | TY $M
| SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E | 1319 |  | 1272.6 | 1415.8 |  | 1273.2 |  | 1192.2 |  | 1145.9 |  | 1145.9
Procurement | 1503.4 |  | 1389.8 | 1527.4 |  | 1382 |  | 1615.4 |  | 1496.5 |  | 1479
Flyaway | -- |  | -- | -- |  | 1344.8 |  | -- |  | -- |  | 1439
Recurring | -- |  | -- | -- |  | 934.7 |  | -- |  | -- |  | 997.3
Non Recurring | -- |  | -- | -- |  | 410.1 |  | -- |  | -- |  | 441.7
Support | -- |  | -- | -- |  | 37.2 |  | -- |  | -- |  | 40
Other Support | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Initial Spares | -- |  | -- | -- |  | 37.2 |  | -- |  | -- |  | 40
MILCON | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 2822.4 |  | 2662.4 | N/A |  | 2655.2 |  | 2807.6 |  | 2642.4 |  | 2624.9
Current APB Cost Estimate Reference
AWACS Block 40/45 FRP SCP Update dated July 28, 2015
Confidence Level
Confidence Level of cost estimate for current APB: 53%
The Life-Cycle Cost Estimate (LCCE) confidence level of 53% reflects the expected value, or mean, of the cost estimate distribution. It takes into consideration relevant risks, including ordinary levels of external and unforeseen events, aiming to provide sufficient resources to execute the program under normal conditions encountering average levels of technical, schedule, and programmatic risk and external influence.

## Table 14
Total Quantity
Quantity | SAR Baseline Production Estimate | Current APB Production | Current Estimate
RDT&E | 0 | 0 | 0
Procurement | 31 | 24 | 24
Total | 31 | 24 | 24
Quantity Notes
Throughout the Cost and Funding section, the quantity of 24 reflects kit procurement and not kit installations. To date, the program has procured and delivered 16 kits, 10 of which have been installed on aircraft.

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 1145.9 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1145.9
Procurement | 866.9 | 183.6 |  |  | 227.9 | 106.6 | 61.4 |  | 32.6 |  | 0 |  | 0 |  | 1479
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 2012.8 | 183.6 |  |  | 227.9 | 106.6 | 61.4 |  | 32.6 |  | 0 |  | 0 |  | 2624.9
PB 2016 Total | 2018.3 | 188.8 |  |  | 230.9 | 106.8 | 61.5 |  | 47.8 |  | 0 |  | 0 |  | 2654.1
Delta | -5.5 | -5.2 |  |  | -3 | -0.2 | -0.1 |  | -15.2 |  | 0 |  | 0 |  | -29.2
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0
Production | 0 |  | 18 |  | 2 | 4 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 24
PB 2017 Total | 0 |  | 18 |  | 2 | 4 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 24
PB 2016 Total | 0 |  | 18 |  | 2 | 4 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 24
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.9
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.2
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.1
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.8
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 116
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 193
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 243.7
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 106.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 127.9
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 90.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 69.9
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 50.1
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 85.1
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.1
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.3
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1145.9

## Table 17
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2012 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.1
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.6
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.4
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.6
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 138.7
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 225
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 276.9
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 117.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 137.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 95.6
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 72.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 51.4
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 85.8
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.7
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.9
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1273.2

## Table 18
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | 0.2 |  | 2.4 |  | 2.6 |  | -- |  | 2.6
2009 |  | 1 | 32.5 |  | 15.3 |  | 13.4 |  | 61.2 |  | 2.9 |  | 64.1
2010 |  | 2 | 45.7 |  | 6.5 |  | 12.1 |  | 64.3 |  | 0.5 |  | 64.8
2011 |  | 3 | 113 |  | 20.7 |  | 28.8 |  | 162.5 |  | 2.8 |  | 165.3
2012 |  | 5 | 106.8 |  | 7.7 |  | 3.8 |  | 118.3 |  | 3.6 |  | 121.9
2013 |  | -- | -- |  | 66 |  | 71.4 |  | 137.4 |  | 5.4 |  | 142.8
2014 |  | 2 | 60.7 |  | 6 |  | 42.1 |  | 108.8 |  | 2.3 |  | 111.1
2015 |  | 5 | 100.2 |  | 38.5 |  | 52.6 |  | 191.3 |  | 3 |  | 194.3
2016 |  | 2 | 64.7 |  | 7.5 |  | 106.1 |  | 178.3 |  | 5.3 |  | 183.6
2017 |  | 4 | 114.4 |  | 58.3 |  | 50.7 |  | 223.4 |  | 4.5 |  | 227.9
2018 |  | -- | 59.3 |  | 6.6 |  | 37.5 |  | 103.4 |  | 3.2 |  | 106.6
2019 |  | -- | 31.4 |  | 6.2 |  | 20.6 |  | 58.2 |  | 3.2 |  | 61.4
2020 |  | -- | 23.5 |  | 5.6 |  | 0.2 |  | 29.3 |  | 3.3 |  | 32.6
Subtotal |  | 24 | 752.2 |  | 245.1 |  | 441.7 |  | 1439 |  | 40 |  | 1479

## Table 19
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | BY 2012 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | 0.2 |  | 2.5 |  | 2.7 |  | -- |  | 2.7
2009 |  | 1 | 33.3 |  | 15.6 |  | 13.7 |  | 62.6 |  | 3 |  | 65.6
2010 |  | 2 | 45.9 |  | 6.5 |  | 12.2 |  | 64.6 |  | 0.5 |  | 65.1
2011 |  | 3 | 111.7 |  | 20.5 |  | 28.4 |  | 160.6 |  | 2.8 |  | 163.4
2012 |  | 5 | 104 |  | 7.5 |  | 3.7 |  | 115.2 |  | 3.5 |  | 118.7
2013 |  | -- | -- |  | 63 |  | 68.1 |  | 131.1 |  | 5.2 |  | 136.3
2014 |  | 2 | 57.1 |  | 5.6 |  | 39.7 |  | 102.4 |  | 2.2 |  | 104.6
2015 |  | 5 | 93.1 |  | 35.8 |  | 48.8 |  | 177.7 |  | 2.8 |  | 180.5
2016 |  | 2 | 59 |  | 6.8 |  | 96.8 |  | 162.6 |  | 4.8 |  | 167.4
2017 |  | 4 | 102.3 |  | 52.2 |  | 45.4 |  | 199.9 |  | 4 |  | 203.9
2018 |  | -- | 52 |  | 5.8 |  | 32.9 |  | 90.7 |  | 2.8 |  | 93.5
2019 |  | -- | 27 |  | 5.3 |  | 17.7 |  | 50 |  | 2.8 |  | 52.8
2020 |  | -- | 19.8 |  | 4.7 |  | 0.2 |  | 24.7 |  | 2.8 |  | 27.5
Subtotal |  | 24 | 705.2 |  | 229.5 |  | 410.1 |  | 1344.8 |  | 37.2 |  | 1382

## Table 20
Cost Quantity Information 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2012 $M
2008 | -- | --
2009 | 1 | 33.3
2010 | 2 | 45.9
2011 | 3 | 111.4
2012 | 5 | 103
2013 | -- | --
2014 | 2 | 62.4
2015 | 5 | 110
2016 | 2 | 103.3
2017 | 4 | 135.9
2018 | -- | --
2019 | -- | --
2020 | -- | --
Subtotal | 24 | 705.2

## Table 21
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2008-11-24 | 2008-11-24
Approved Quantity | 6 | 6
Reference | Milestone C ADM | Milestone C ADM
Start Year | 2009 | 2009
End Year | 2014 | 2015
The Current Total LRIP Quantity is more than 10% of the total production quantity due to operational requirements.
Air Combat Command identified a requirement for five AWACS Block 40/45 Upgrade aircraft for IOC declaration. The program office requested an LRIP quantity of six to utilize the first modified aircraft as a risk reduction asset to streamline the process of combining a major upgrade with Programmed Depot Maintenance. In addition, the first aircraft was required to support production qualification testing.
The Start Year indicated specifies the year that the LRIP contract (Delivery Order 23) was awarded. The program procured one 40/45 shipset in FY 2009, two 40/45 shipsets in FY 2010 and three 40/45 shipsets in FY 2011. The Current End Year indicated above specifies the completion of the contract Period of Performance (PoP).
The PoP was extended to July 2015 to complete the provisioning effort.

## Table 22
Foreign Military Sales
None
Nuclear Costs
None

## Table 23
Unit Cost
Unit Cost Report
Item |  |  | BY 2012 $M | BY 2012 $M |  | % Change
|  |  | Current UCR Baseline (Oct 2015 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2662.4 |  |  |  | 2655.2
Quantity | 24 |  |  |  | 24
Unit Cost | 110.933 |  |  |  | 110.633 |  |  | -0.27
Average Procurement Unit Cost
Cost | 1389.8 |  |  |  | 1382
Quantity | 24 |  |  |  | 24
Unit Cost | 57.908 |  |  |  | 57.583 |  |  | -0.56
Item |  |  | BY 2012 $M | BY 2012 $M |  | % Change
|  |  | Original UCR Baseline (May 2013 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost |  | 2822.4 |  |  | 2655.2
Quantity |  | 31 |  |  | 24
Unit Cost |  | 91.045 |  |  | 110.633 |  | 21.51
Average Procurement Unit Cost
Cost |  | 1503.4 |  |  | 1382
Quantity |  | 31 |  |  | 24
Unit Cost |  | 48.497 |  |  | 57.583 |  | 18.74
.

## Table 24
Unit Cost History
Item | [5 empty] | Date |  |  | BY 2012 $M | [6 empty] | TY $M
[9 empty] | PAUC |  | APUC |  |  |  |  | PAUC |  |  | APUC
Original APB |  |  | May 2013 | [5 empty] | 91.045 |  |  |  | 48.497 |  |  |  | 90.568 |  |  | 52.11
APB as of January 2006 |  |  | N/A | [5 empty] | N/A |  |  |  | N/A |  |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A | [5 empty] | N/A |  |  |  | N/A |  |  |  | N/A |  |  | N/A
Prior APB |  |  | May 2013 | [5 empty] | 91.045 |  |  |  | 48.497 |  |  |  | 90.568 |  |  | 52.11
Current APB |  |  | Oct 2015 | [5 empty] | 110.933 |  |  |  | 57.908 |  |  |  | 110.1 |  |  | 62.354
Prior Annual SAR |  |  | Dec 2014 | [5 empty] | 111.383 |  |  |  | 57.821 |  |  |  | 110.588 |  |  | 62.217
Current Estimate |  |  | Dec 2015 | [5 empty] | 110.633 |  |  |  | 57.583 |  |  |  | 109.371 |  |  | 61.625
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Production Estimate | Changes | [16 empty] | PAUC Current Estimate
| Econ | Qty |  |  | Sch |  | Eng | Est |  | Oth | Spt |  |  | Total
90.568 -0.308 15.623 -0.912 0.000 4.562 0.000 -0.162 18.803 109.371
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Production Estimate | Changes | [16 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  |  | Eng | Est |  | Oth |  | Spt |  |  | Total
52.110 -0.317 4.407 -0.217 0.000 5.804 0.000 -0.162 9.515 61.625

## Table 25
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | N/A | Jul 2003 | Jul 2003
Milestone C | N/A | N/A | Jan 2009 | Jan 2009
IOC | N/A | N/A | Apr 2014 | Jan 2014
Total Cost (TY $M) | N/A | N/A | 2807.6 | 2624.9
Total Quantity | N/A | N/A | 31 | 24
PAUC | N/A | N/A | 90.568 | 109.371

## Table 26
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 1192.2 | 1615.4 | -- | 2807.6
Previous Changes
Economic | 0.9 | 0.5 | -- | 1.4
Quantity | -- | -259 | -- | -259
Schedule | -16.7 | -5.2 | -- | -21.9
Engineering | -- | -- | -- | --
Estimating | -15.5 | 145.3 | -- | 129.8
Other | -- | -- | -- | --
Support | -- | -3.8 | -- | -3.8
Subtotal | -31.3 | -122.2 | -- | -153.5
Current Changes
Economic | -0.7 | -8.1 | -- | -8.8
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -14.3 | -6 | -- | -20.3
Other | -- | -- | -- | --
Support | -- | -0.1 | -- | -0.1
Subtotal | -15 | -14.2 | -- | -29.2
Adjustments | -- | -- | -- | --
Total Changes | -46.3 | -136.4 | -- | -182.7
CE - Cost Variance | 1145.9 | 1479 | -- | 2624.9
CE - Cost & Funding | 1145.9 | 1479 | -- | 2624.9

## Table 27
Summary BY 2012 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 1319 | 1503.4 | -- | 2822.4
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -227.1 | -- | -227.1
Schedule | -17.9 | -6.4 | -- | -24.3
Engineering | -- | -- | -- | --
Estimating | -15.6 | 122.2 | -- | 106.6
Other | -- | -- | -- | --
Support | -- | -4.4 | -- | -4.4
Subtotal | -33.5 | -115.7 | -- | -149.2
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -12.3 | -5.7 | -- | -18
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -12.3 | -5.7 | -- | -18
Adjustments | -- | -- | -- | --
Total Changes | -45.8 | -121.4 | -- | -167.2
CE - Cost Variance | 1273.2 | 1382 | -- | 2655.2
CE - Cost & Funding | 1273.2 | 1382 | -- | 2655.2
Previous Estimate: June 2015

## Table 28
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | -0.7
Adjustment for current and prior escalation. (Estimating) |  | 0.6 | 0.6
Realignment of funds from AWACS Blk 40/45 to support Combat Identification program. (Estimating) |  | -12.9 | -14.9
RDT&E Subtotal |  | -12.3 | -15
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -8.1
Adjustment for current and prior escalation. (Estimating) +4.1 +4.2
Realignment of funding from AWACS Blk 40/45 to source the Next-Generation Identification Friend or Foe and Training Support Infrastructure requirements. (Estimating)
-9.8 -10.2
Adjustment for current and prior escalation. (Support) Decrease in Initial Spares. (Support) | +0.1 -0.1 |  |  | +0.2 -0.3
Procurement Subtotal | -5.7 |  |  | -14.2

## Table 29
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: AWACS 40/45 Upgrade Program Full Rate Production
Contractor: The Boeing Company
Contractor Location: P.O. Box 3707
Seattle, WA 98124-2207
Contract Number: F19628-01-D-0016/26
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 27, 2012
Definitization Date: December 27, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
137.3 142.5 N/A 205.3 249.1 N/A 182.1 175.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the award of Next Generation Identification Friend or Foe Integration and FRP Shipsets #12 and 13.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/28/2016) +10.8 -3.2
Previous Cumulative Variances +1.7 -7.7
Net Change +9.1 +4.5
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to improvements in cost performance of CLINs 3606, 3610, and 3613. The government-contractor team has been effective in controlling Shipset costs over the period July 2015 to December 2015.
The favorable net change in the schedule variance is due to strong recovery in the schedule variances for CLINs 3606 and 3613, over the period July 2015 to January 2016.

## Table 30
Notes
Earned Value Management Data is received only for specific CLINs listed below representing $178.2M, 61% of the total contract value.
CLIN 3300 Engineering Support to Diminishing Manufacturing Sources Upgrade CLIN 3606 FRP #1 Shipsets for aircraft P7 - P11
CLIN 3608 Life of Type Buy
CLIN 3613 FRP Shipsets # P12 and P13
CLIN 3302 Next Generation Identification Friend or Foe Integration CLIN 3610 FRP Shipsets for aircraft P14 - P18

## Table 31
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 10 | 10 | 24 | 41.67%
Total Program Quantity Delivered | 10 | 10 | 24 | 41.67%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
2624.9
1523.7
58.05%
22
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
18
81.82%
2196.4
83.68%
The above data is current as of February 09, 2016.

## Table 32
Operating and Support Cost
Cost Estimate Details
Date of Estimate: July 31, 2015
Source of Estimate: SCP
Quantity to Sustain: 24
Unit of Measure: Aircraft
Service Life per Unit: 25.00 Years
Fiscal Years in Service: FY 2011 - FY 2035
O&S cost estimate reflects revised SCP dated July 31, 2015.
Sustainment Strategy
- Production will leave the AWACS fleet with two COTS Diminishing Manufacturing Sources (DMS) versions (DMS 3.0 and DMS 4.0) going into the O&S phase
- DMS tech refresh every 5 years starting in FY 2019 through life of program
- O&S COTS procured with AF O&M funding
- O&S COTS installed by Air Logistics Complex (ALC) during Programmed Depot Maintenance or a dedicated modification installation line
- Software maintained organically with contractor support/partnership
- COTS, active DMS and DMS refreshes done with contractor partnership
- No modifications or capability upgrades included other than planned DMS tech refresh
- Product Support Business Case Analysis (PSBCA) initiated in November 2015
Antecedent Information
AWACS Block 30/35 O&S cost is based on historical Block 30/35 O&S cost projected through FY 2035. These costs are used for comparison to Block 40/45 O&S costs. This comparison assumes Block 30/35 can be maintained through FY 2035 and assumes no major DMS issues (Status Quo). Block 30/35 cost was obtained from the Air Force Total Ownership Cost (AFTOC) database for a period of FY 2007-2011. The data was normalized to BY2012 and projected out through FY 2035.

## Table 33
Annual O&S Costs BY2012 $M
Cost Element |  | AWACS Blk 40/45 Upgrade Average Annual Cost Per Aircraft | [5 empty] | AWACS Blk 30/35 (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower |  | 0 | [5 empty] | 11.733
Unit Operations |  | 0 | [5 empty] | 6.162
Maintenance |  | 0.52 | [5 empty] | 8.318
Sustaining Support |  | 0.299 | [5 empty] | 1.203
Continuing System Improvements |  | 0.098 | [5 empty] | 0.737
Indirect Support |  | 0 | [5 empty] | 3.583
Other |  | 0 | [5 empty] | 0
Total |  | 0.917 | [5 empty] | 31.736
AWACS Block 40/45 Upgrade program Yearly Average per Aircraft costs represent the additional funding required per aircraft when compared to the antecedent AWACS Block 30/35 yearly average per Aircraft O&S costs. Thus, these costs are due solely to the AWACS Block 40/45 Upgrade.
Item | Total O&S Cost $M
| AWACS Blk 40/45 Upgrade | [7 empty] | AWACS Blk 30/35 (Antecedent)
| Current Production APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 550 |  |  | 605 |  |  | 550 |  | 19041.1
Then Year | 731.3 |  |  | N/A |  |  | 731 |  | N/A
The AWACS Block 40/45 Upgrade program Current Estimate is the delta cost from the AWACS Block 30/35 (Antecedent) Current Estimate, reflecting the total O&S cost of the AWACS Enterprise.
Equation to Translate Annual Cost to Total Cost
Average annual cost per AWACS aircraft (24) (entire fleet) is calculated by taking the total AWACS 40/45 system cost ($550.0M) and dividing by the life of the platform (FY 2011-2035, 25 years) and then dividing by the total quantity of aircraft (24). $550.0M / 25 / 24 = $0.917M.
O&S Cost Variance
Category |  |  | BY 2012 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Jun 2015 SAR
1020.8
Programmatic/Planning Factors 0.0
Cost Estimating Methodology -470.8 Cost model revised and new basis from AFTOC updated from 2012 to 2015 data
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0

## Table 34
Other 0.0
Total Changes -470.8
Current Estimate 550.0
Disposal Estimate Details
Date of Estimate: Source of Estimate:
Disposal/Demilitarization Total Cost (BY 2012 $M):
There are no disposal costs associated specifically with the AWACS Block 40/45 Upgrade.