## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-185
AIM-120 Advanced Medium Range Air-to-Air Missile (AMRAAM)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 9
Schedule 10
Performance 13
Track to Budget 15
Cost and Funding 17
Low Rate Initial Production 32
Foreign Military Sales 33
Nuclear Costs 33
Unit Cost 34
Cost Variance 37
Contracts 41
Deliveries and Expenditures 47
Operating and Support Cost 48

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
AIM-120 Advanced Medium Range Air-to-Air Missile (AMRAAM)
DoD Component
Air Force
Joint Participants
Navy
Responsible Office
Col Jeffrey Sobel
Chief, Air Dominance Division AFLCMC/EBA
207 West D Ave, STE 214 Eglin AFB, FL 32542-6892
jeffrey.sobel@eglin.af.mil
Phone: | 850-883-0343
Fax: | 850-883-0559
DSN Phone: | 875-0343
DSN Fax: | 875-0559
Date Assigned: | June 17, 2013
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated January 17, 1992
Approved APB
Component Acquisition Executive (CAE) Approved Acquisition Program Baseline (APB) dated October 28, 2015

## Table 6
Mission and Description
The Advanced Medium Range Air-to-Air Missile (AMRAAM) AIM-120 program provides for the acquisition and upgrade of the most advanced all-weather, all-environment medium range air-to-air missile system in response to United States Air Force, United States Navy, North Atlantic Treaty Organization, and other Allied operational requirements through 2024. Designed to replace the AIM-7 Sparrow, the system is an active radar guided intercept missile with inherent Electronic Protection capabilities for air-to-air applications against massed penetration aircraft. The AIM-120D, currently in production, provides improved accuracy via Global Positioning System aided navigation, improved network compatibility, and enhanced aircrew survivability via a two-way datalink capability. The AIM-120D reached IOC for the United States Air Force and Navy in 2015.

## Table 7
Executive Summary
AIM-120D IOC: AIM-120D reached IOC for the US Navy on January 5, 2015 and the US Air Force on July 9, 2015.
AIM-120 Basic Electronic Protection Improvement Program (EPIP): Basic EPIP is a missile software upgrade to
provide AIM-120C3/4/5/6 and C7 missiles with improved capability against electronic attack (EA). The EPIP program has separate software configurations for both the AIM-120C7 and AIM-120C-3/4/5/6 missiles. The US Air Force approved fielding for the AIM-120C7 in February 2015 and the US Navy approved fielding in April 2015. The AIM-120C3/4/5/6 dedicated Operational Test (OT) program is completed, and fielding authorization is anticipated in 2nd Quarter FY 2016.
AIM-120C7 Advanced Electronic Protection Improvement Program (AEPIP): AEPIP is structured to deliver combat capability for the AIM-120C7 via two incremental and complimentary software tapes, Tape 1 and Tape 2. Tape 1 provides enhanced capability to fielded systems. Tape 2 builds on the capabilities of Tape 1 and expands the system’s envelope. Tape 1 and 2 development is on track, and performance Probability of weapons effectiveness (Pwe) meets or exceeds requirements. Tape 1 completed two of three Integrated Test (IT) live fires in November 2015, with the third shot projected for 3rd Quarter FY 2016. Tape 2 Developmental Testing (DT) completed three of seven captive carry missions and Critical Design Review (CDR) in 2015. The planned fielding dates for Tape 1 and Tape 2 are 4th Quarter FY 2017 and 4th Quarter FY 2018 respectively.
AIM-120D System Improvement Program (SIP): SIP is a software upgrade program structured to deliver increased combat capability and counter advanced threats and EA techniques on planned intervals to the AIM-120D. Three efforts are now in development, SIP 1, SIP 2, and SIP 3. SIP 1 successfully passed the Operational Test Readiness Review on September 11, 2015. The Air Force Operational Test and Evaluation Center conducted two live OT shots on February 4 and 9, 2016. SIP 2 kicked off Engineering & Manufacturing Development with an Integrated Baseline Review (IBR) in September 2015. The next milestone, CDR, is planned for 4th Quarter FY 2016. The SIP 3 effort began with Technology Maturation and Risk Reduction (TMRR) kick off in November 2015 followed by an IBR conducted in January 2016. SIP 1 fielding is projected for 4th Quarter FY 2016 followed by SIP 2 fielding in 1st Quarter FY 2019 and SIP 3 fielding in
1st Quarter FY 2021.
Processor Replacement Program (PRP): PRP is a Diminishing Manufacturing Sources and Material Shortages (DMSMS) project to provide a form-fit-function replacement for the obsolete Data Processor and Input / Output cards onto a
single Circuit Card Assembly. Delivery of the final AIM-120D PRP software was completed in January 2015. In May 2015, PRP successfully completed qualification and the final Engineering Change Proposal (ECP) was approved to support
missile deliveries to the warfighter. PRP missiles are now in production.
VCAS (Value Control Actuation System): VCAS is a DMSMS replacement for the Shortened Control Actuation System in PRP configured AIM-120D and AIM-120C7 tactical missiles. VCAS production cut in was planned to begin with Lot 27 deliveries in July 2015, however, tactical missile deliveries were delayed due to VCAS qualification issues. Raytheon released the VCAS qualification report on December 18, 2015 and successfully passed the Functional Configuration Audit on January 15, 2016, enabling the completion of safe separation flight testing targeted for 3rd Quarter FY 2016. ECP approval, planned for 4th Quarter FY 2016, is the final step for deliveries of Lot 27 units.
Safe and Arming Fuze (SAF) for F-35 / AMRAAM Flight Test: The SAF is a component used for both the warhead in AMRAAM tactical missiles and the Flight Termination System (FTS) in instrumented flight test missiles. The SAF FTS allows range safety the ability to terminate the flight of a test missile. In August 2015, Range Safety and the Program Office determined that production SAFs for flight test missiles have not been lot acceptance tested (LAT) to required specification levels. LAT has been conducted at the tactical level instead of the harsher FTS level for all SAFs. Range Safety has provided a variance for use of SAFs for legacy fighter testing due to the exceptional SAFs safety record in past testing.
However, due to the more rigorous F-35 test environment, Range Safety clears the SAFs for F-35 testing on a case by case basis. The Program Office has worked closely with Range Safety and the F-35 Program Office to develop and execute a short and long term plan for AIM-120 testing.

## Table 8
Form, Fit, Function Refresh (F3R): F3R is a comprehensive AMRAAM DMSMS project to mitigate obsolescence issues in the AMRAAM guidance section and enable missile production beyond Lot 31. Currently in Phase 3 for Detailed Design, Raytheon has experienced technical difficulties with the Application Specific Integrated Circuit design, hardware integration, and guidance section performance demonstration in preparation for CDR. CDR is delayed from November 2015 to
April 2016 to ensure technical maturity and completion of design verification prior to proceeding to the next phase. F3R production is planned to cut in the latter part of Lot 31 in FY 2019.
AIM-120 Lot 28-30 Production Contract: The Lot 28 contract, with priced options for Lots 29 and 30, was awarded on December 22, 2014 for $492M. Lot 29 contract option was awarded on March 24, 2015 for $529M. Lot 30 contract option award is planned for 2nd Quarter FY 2016.
AIM-120 Program Support and Annual Sustainment (PSAS) 2015 Contract: PSAS is an Indefinite-Delivery-Indefinite- Quantity (IDIQ) contract for program support, contractor logistics support (CLS), the Service Life Prediction Program (SLPP), and non-warranty depot repair. The basic PSAS 2015 contract was awarded on September 21, 2015 with a ceiling price of $180M. The first task order for program support, CLS, and SLPP was awarded on September 21, 2015, for $18M.
AIM-120D Production: As of December 31, 2015, Raytheon has delivered 1,498 of 2,074 AIM-120D missiles on contract and has delivered 1,548 of 2,400 AIM-120C7 FMS missiles on contract (through Lot 29).
AIM-120 Sustainment: Joint missile availability as of December 31, 2015 is 91.6% against an APB threshold of 82%. There are no significant software-related issues with this program at this time.

## Table 9
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 10
Schedule

## Table 11
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone I (DSARC) | Nov 1978 | Nov 1978 | Nov 1978 | Nov 1978
Milestone II (DSARC) | Sep 1982 | Sep 1982 | Sep 1982 | Sep 1982
Start DT&E/IOT&E | Oct 1983 | N/A | N/A | Oct 1983
Certification | Feb 1986 | Feb 1986 | Feb 1986 | Feb 1986
Milestone IIIA (DAB) | Jun 1987 | Jun 1987 | Jun 1987 | Jun 1987
DAE Program Review | May 1988 | May 1988 | May 1988 | May 1988
Start Production Deliveries | Sep 1988 | Sep 1988 | Sep 1988 | Sep 1988
Complete D/IOT&E (Air Force) | Jan 1989 | Jan 1989 | Jan 1989 | Jan 1989
Complete IOT&E/Captive Carry Reliability Program w/Lot 1 Assets (Air Force) | Jun 1990 | Jun 1990 | Jun 1990 | Jun 1990
Initial Equipage | Dec 1990 | Dec 1990 | Dec 1990 | Dec 1990
Milestone IIIB (DAB) (Lot IV Full Go-Ahead Rate Production) | Apr 1991 | Apr 1991 | Apr 1991 | Apr 1991
IOC Air Force | Mar 1991 | Sep 1991 | Sep 1991 | Sep 1991
DAB Program Review Full Rate Production Approval | Mar 1992 | Mar 1992 | Mar 1992 | Mar 1992
Full Operational Capability (FOC) 1st F-16 Unit Fully Operational w/AMRAAMs | Mar 1992 | Mar 1992 | Mar 1992 | Mar 1992
P3I Phase 1 CDR Complete | Oct 1992 | Oct 1992 | Oct 1992 | Oct 1992
Complete AF FOT&E Phase I | Mar 1992 | Feb 1993 | Feb 1993 | Feb 1993
IOC (Navy) | Sep 1992 | Sep 1993 | Sep 1993 | Sep 1993
Complete FOT&E (OPEVAL) (Navy) | Mar 1992 | Jan 1994 | Jan 1994 | Jan 1994
P3I Phase 1 Flight Test Completed | Dec 1994 | Dec 1994 | Dec 1994 | Dec 1994
Joint Depot Activated | Sep 1994 | Jul 1999 | Jul 1999 | Jul 1999
Phase 4 (AIM-120D) Contract Award | N/A | Jan 2004 | Jan 2004 | Jan 2004
Phase 4 (AIM-120D) CDR | N/A | Nov 2005 | Nov 2005 | Nov 2005
Phase 4 (AIM-120D) Functional Configuration Audit (FCA) | N/A | Sep 2009 | Sep 2009 | Sep 2009
Phase 4 (AIM-120D) Missile Deliveries to Meet F/A-18 RAA | N/A | May 2012 | May 2012 | May 2012
Phase 4 (AIM-120D) Missile Deliveries to Meet F- 15C/D RAA | N/A | May 2012 | May 2012 | May 2012
Phase 4 (AIM-120D) Full Production Go-ahead | N/A | Jan 2015 | Jan 2015 | Jan 2015
Last Delivery | Sep 2001 | N/A | N/A | Jan 2027
(Ch-1)

## Table 12
Change Explanations
(Ch-1) Current estimate changed from Oct 2014 to Jan 2015 to update to actuals.
Acronyms and Abbreviations
AF - Air Force
CDR - Critical Design Review
D/IOT&E - Development / Initial Operational Test & Evaluation DSARC - Defense Systems Acquisition Review Council DT&E - Development Test and Evaluation
FOT&E - Follow-on Test and Evaluation IOT&E - Initial Operational Test and Evaluation OPEVAL - Operational Evaluation
P3I - Pre-Planned Product Improvement RAA - Required Assets Available

## Table 13
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Weight (lbs)
327 | 327 | 350 | 344 | 345
Reliability
Ready Storage (hrs) (mature msl - 90K operational flight hours)
60000 | 60000 | 45000 | 45000 | 45000
Availability (%)
86 | 86 | 82 | 91.6 | 90.7
Captive-Carry (MTBM-Type I) (hrs)
600 | 600 | 450 | 1313 | 1270
On Alert Storage MTBM
30000 | 30000 | 22500 | N/A | 30000
Aircraft Configure/ Load - 3 Man Load Crew
Install 4 Rail Launchers (mins)
20 | 20 | 25 | 21 | 21
Load 4 Missiles from trailer (mins)
15 | 15 | 20 | 18 | 18
Load 4 Missiles from container (mins)
20 | 20 | 30 | 22 | 22
Missile checks (mins)
1 | 1 | 5 | 1 | 1
All Weather Capability
Day, Night, Rain, Clouds | Day, Night, Rain, Clouds | Day, Night, Rain, Clouds | Day, Night, Rain, Clouds | Day, Night, Rain, Clouds
Aircraft Compatibility
F-15, F-16, F- 14, F/A-18 | F-15, F-16, F/A-18, F- 35 | F-15, F-16, F/A 18, F- 22 | F-15, F-16, F-14, F/A-18 | F-15, F-16, F/A-18, F- 22
All-Up Round
Control Surfaces field installed | Control Surfaces field installed | Control Surfaces field installed | Control Surfaces field installed | Control Surfaces field installed
Net Ready
N/A | Satisfies NCOW-RM and GIG Information | Satisfies 100% of enterprise level or | Satisfies NCOW-RM and GIG Information | Satisfies 100% of enterprise level or
(Ch-1)
(Ch-2)

## Table 14
| assurance reqmts | critical information reqmts | assurance reqmts | critical information reqmts
Shipboard Survivability
N/A | Compatible in aircraft carrier electro- magnetic environment | Compatible in aircraft carrier electro- magnetic environment | Compatible in aircraft carrier electro-magnetic environment | Compatible in aircraft carrier electro- magnetic environment
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Joint Service Operational Requirement (JSOR) dated May 22, 1991, Operational Requirements Document (ORD) (Combat Air Forces (CAF) 009-76-I/II/III-A) dated March 10, 1997 (revised January 21, 2004), and Capability Production Document (CPD) Phase 4 (AIM-120D) dated June 16, 2005
Change Explanations
(Ch-1) Current estimate changed from 90 to 90.7 due to current actuals as of December 31, 2015. (Ch-2) Current estimate changed from 1200 to 1270 due to current actuals as of December 31, 2015.
Acronyms and Abbreviations
GIG - Global Information Grid hrs - Hours
K - Thousands lbs - Pounds mins - Minutes msl - Missile
MTBM - Mean Time Between Maintenance
NCOW-RM - Net Centric Operations Warfare - Reference Model

## Table 15
Track to Budget
RDT&E
Appn |  | BA | PE
Navy 1319 07 0207163N
Project Name
0981 AMRAAM
Navy 1319 07 0603370N
Project Name
UNK Beyond Visual Range, Air-to-Air Missile (BVRAAM), FY 1978-1981.
Navy 1319 07 0604314N
(Sunk)
Project | Name
W0981 (AMRAAM), FY 1982-1992 (Shared) (Sunk) Air Force 3600 07 0207163F
Project Name
673777 AMRAAM (Shared)
Air Force 3600 07 0603370F
Project Name
2437 (AMRAAM), FY 1978-1982 (Sunk)
Air Force 3600 07 0604314F
Project Name
3096 (AMRAAM), FY 1982-1992 (Sunk)
Procurement
Appn BA PE
Navy 1507 02 0206138M
Line Item Name
2206 AMRAAM
Navy 1507 02 0204162N
Line Item Name
2206 AMRAAM
Navy 1507 06 0204162N
Line Item Name
6120 Spares and Repair Parts (Shared) Air Force 3020 04 0207163F
Line Item Name
000999 Initial Spares / Repair Parts (Shared)
00099A Initial Spares / Repair Parts (Sunk)
00099K Initial Spares / Repair Parts (Sunk)
Air Force 3020 01 0207163F

## Table 16
Line Item | Name
00099L Missile Replacement Equipment - Ballistic (Shared) (Sunk)
Air Force 3020 02 0207163F
Line Item | Name
MAMRAO AMRAAM

## Table 17
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 1992 $M | [5 empty] | BY 1992 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E | 1725.7 |  |  | 2419.5 | 2661.5 |  |  | 2413.1 |  | 1350.6 |  |  | 2247.2 |  | 2236.7
Procurement | 10552.5 |  |  | 13574.7 | 14932.2 |  |  | 13729.6 |  | 11761.8 |  |  | 17499.8 |  | 17665.3
Flyaway | -- |  |  | -- | -- |  |  | 12888 |  | -- |  |  | -- |  | 16540.7
Recurring | -- |  |  | -- | -- |  |  | 11016.5 |  | -- |  |  | -- |  | 14654.3
Non Recurring | -- |  |  | -- | -- |  |  | 1871.5 |  | -- |  |  | -- |  | 1886.4
Support | -- |  |  | -- | -- |  |  | 841.6 |  | -- |  |  | -- |  | 1124.6
Other Support | -- |  |  | -- | -- |  |  | 720.9 |  | -- |  |  | -- |  | 979.4
Initial Spares | -- |  |  | -- | -- |  |  | 120.7 |  | -- |  |  | -- |  | 145.2
MILCON | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 12278.2 |  |  | 15994.2 | N/A |  |  | 16142.7 |  | 13112.4 |  |  | 19747 |  | 19902
Current APB Cost Estimate Reference
AMRAAM Program Office Estimate validated by the Air Force Cost Analysis Agency as part of the Non-Advocate Cost Assessment dated May 12, 2014
Confidence Level
Confidence Level of cost estimate for current APB: 54%
The life-cycle cost estimate represents the expected value, or mean, of the cost estimate distribution, and for this estimate, the confidence level is 54%. It takes into consideration relevant risks, including ordinary levels of external and unforeseen events. It aims to provide sufficient resources to execute the program under normal conditions encountering average levels of technical, schedule, and programmatic risk and external influence.
Total Quantity
Quantity |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  | 15450 |  |  |  | 16427 |  |  |  |  | 17312
Total |  | 15450 |  |  |  | 16427 |  |  |  |  | 17312

## Table 18
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 2219.5 | 1.9 |  |  | 1.8 | 1.8 | 1.8 |  | 2 |  | 1.9 |  |  | 6 |  | 2236.7
Procurement | 10944.6 | 586.2 |  |  | 558 | 710.8 | 746.9 |  | 745.5 |  | 746.3 |  |  | 2627 |  | 17665.3
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 13164.1 | 588.1 |  |  | 559.8 | 712.6 | 748.7 |  | 747.5 |  | 748.2 |  |  | 2633 |  | 19902
PB 2016 Total | 13373.4 | 664.4 |  |  | 683.7 | 827.8 | 864.2 |  | 850.8 |  | 786.7 |  |  | 2549.9 |  | 20600.9
Delta | -209.3 | -76.3 |  |  | -123.9 | -115.2 | -115.5 |  | -103.3 |  | -38.5 |  |  | 83.1 |  | -698.9
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Production | 0 |  | 11559 |  | 441 | 419 | 635 |  | 664 |  | 666 | 651 |  | 2277 |  | 17312
PB 2017 Total | 0 |  | 11559 |  | 441 | 419 | 635 |  | 664 |  | 666 | 651 |  | 2277 |  | 17312
PB 2016 Total | 0 |  | 11467 |  | 429 | 407 | 595 |  | 634 |  | 608 | 571 |  | 1829 |  | 16540
Delta | 0 |  | 92 |  | 12 | 12 | 40 |  | 30 |  | 58 | 80 |  | 448 |  | 772

## Table 19
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1977 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.8
1978 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.7
1979 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.1
1980 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.2
1981 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.9
1982 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 137.9
1983 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 212.9
1984 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 197.3
1985 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 206.6
1986 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 91.1
1987 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.7
1988 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.7
1989 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.9
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.9
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.3
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.9
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 64.8
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 63.8
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44.2
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.7
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.2
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.5
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49.4
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 50.4
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 53.5
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.3
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.9
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.1
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.7

## Table 20
2012 | -- | -- | -- | -- | -- | -- | 58.2
2013 | -- | -- | -- | -- | -- | -- | 43.1
2014 | -- | -- | -- | -- | -- | -- | 40.2
Subtotal | -- | -- | -- | -- | -- | -- | 1956.7

## Table 21
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 1992 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1977 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.3
1978 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.2
1979 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.5
1980 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.2
1981 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.1
1982 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 191.7
1983 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 283.4
1984 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 252.6
1985 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 255.9
1986 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 110.1
1987 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.6
1988 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.1
1989 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.4
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.6
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.2
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 60.9
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 58.9
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40.1
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.7
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.8
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.5
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42.8
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 45.2
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.8
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.2
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.8
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.8
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.1
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2097.9

## Table 22
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1978 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6
1979 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.3
1980 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.3
1981 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.2
1982 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.3
1983 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.3
1984 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.3
1985 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.8
1986 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.2
1987 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5
1988 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.3
1989 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.4
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.9
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.5
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.5
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.1
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.8
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.3
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.1
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.5
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.5
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.8
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.3
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.7
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.7
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.7
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.5
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.4
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.1
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.2
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.1
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.1
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8

## Table 23
2018 | -- | -- | -- | -- | -- | -- | 1.8
2019 | -- | -- | -- | -- | -- | -- | 1.8
2020 | -- | -- | -- | -- | -- | -- | 2
2021 | -- | -- | -- | -- | -- | -- | 1.9
2022 | -- | -- | -- | -- | -- | -- | 2
2023 | -- | -- | -- | -- | -- | -- | 2
2024 | -- | -- | -- | -- | -- | -- | 2
Subtotal | -- | -- | -- | -- | -- | -- | 280

## Table 24
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 1992 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1978 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.7
1979 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.3
1980 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.5
1981 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.4
1982 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.6
1983 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.7
1984 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.4
1985 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.7
1986 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.1
1987 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.9
1988 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.3
1989 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.5
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.2
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.5
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.5
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.2
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.9
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.9
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.1
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.7
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.2
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.4
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.7
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.6
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.8
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.6
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.8
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.8
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.7
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.2

## Table 25
2018 | -- | -- | -- | -- | -- | -- | 1.1
2019 | -- | -- | -- | -- | -- | -- | 1.1
2020 | -- | -- | -- | -- | -- | -- | 1.2
2021 | -- | -- | -- | -- | -- | -- | 1.1
2022 | -- | -- | -- | -- | -- | -- | 1.2
2023 | -- | -- | -- | -- | -- | -- | 1.1
2024 | -- | -- | -- | -- | -- | -- | 1.1
Subtotal | -- | -- | -- | -- | -- | -- | 315.2

## Table 26
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1989 |  | 26 | 26 |  | -- |  | 2.7 |  | 28.7 |  | 2.5 |  | 31.2
1990 |  | 85 | 61.5 |  | -- |  | 18.7 |  | 80.2 |  | 4.9 |  | 85.1
1991 |  | 300 | 191.5 |  | -- |  | 52.9 |  | 244.4 |  | 17.5 |  | 261.9
1992 |  | 191 | 115.3 |  | -- |  | 38 |  | 153.3 |  | 41.2 |  | 194.5
1993 |  | 165 | 72.5 |  | -- |  | 20.3 |  | 92.8 |  | 12.4 |  | 105.2
1994 |  | 75 | 26.7 |  | -- |  | 21.5 |  | 48.2 |  | 8.6 |  | 56.8
1995 |  | 106 | 40.5 |  | -- |  | 24.6 |  | 65.1 |  | 9.9 |  | 75
1996 |  | 115 | 35.2 |  | -- |  | 28.5 |  | 63.7 |  | 10 |  | 73.7
1997 |  | 100 | 30.4 |  | -- |  | 16.3 |  | 46.7 |  | 6 |  | 52.7
1998 |  | 120 | 38.1 |  | -- |  | 10.1 |  | 48.2 |  | 6.3 |  | 54.5
1999 |  | 100 | 36.5 |  | -- |  | 9 |  | 45.5 |  | 5.4 |  | 50.9
2000 |  | 91 | 33.5 |  | -- |  | 10 |  | 43.5 |  | 2.5 |  | 46
2001 |  | 63 | 25.3 |  | -- |  | 9.1 |  | 34.4 |  | 3.4 |  | 37.8
2002 |  | 55 | 20.4 |  | -- |  | 12.9 |  | 33.3 |  | 3.5 |  | 36.8
2003 |  | 76 | 34.4 |  | -- |  | 12.5 |  | 46.9 |  | 3.5 |  | 50.4
2004 |  | 42 | 18.5 |  | -- |  | 15 |  | 33.5 |  | 3.8 |  | 37.3
2005 |  | 37 | 16.4 |  | -- |  | 9.4 |  | 25.8 |  | 3 |  | 28.8
2006 |  | 48 | 40.4 |  | -- |  | 30.2 |  | 70.6 |  | 3.2 |  | 73.8
2007 |  | 42 | 60.4 |  | -- |  | 25 |  | 85.4 |  | 3.4 |  | 88.8
2008 |  | 52 | 75.8 |  | -- |  | 7.5 |  | 83.3 |  | 2.7 |  | 86
2009 |  | 57 | 80.3 |  | -- |  | 2.4 |  | 82.7 |  | 2.6 |  | 85.3
2010 |  | 71 | 135.3 |  | -- |  | -- |  | 135.3 |  | 3.3 |  | 138.6
2011 |  | 101 | 134.2 |  | -- |  | -- |  | 134.2 |  | 5 |  | 139.2
2012 |  | 67 | 93.3 |  | -- |  | -- |  | 93.3 |  | 5.5 |  | 98.8
2013 |  | 67 | 81.1 |  | -- |  | -- |  | 81.1 |  | 6.4 |  | 87.5
2014 |  | 61 | 69.7 |  | -- |  | 1.5 |  | 71.2 |  | 11.8 |  | 83
2015 |  | -- | -- |  | 1.9 |  | -- |  | 1.9 |  | 0.3 |  | 2.2
2016 |  | 179 | 198.4 |  | -- |  | -- |  | 198.4 |  | 5.8 |  | 204.2
2017 |  | 163 | 204.1 |  | -- |  | -- |  | 204.1 |  | 1.7 |  | 205.8
2018 |  | 247 | 259.3 |  | -- |  | 2 |  | 261.3 |  | 1.9 |  | 263.2
2019 |  | 260 | 271.8 |  | -- |  | -- |  | 271.8 |  | 3 |  | 274.8
2020 |  | 252 | 264.8 |  | -- |  | -- |  | 264.8 |  | 5.7 |  | 270.5
2021 |  | 248 | 266.5 |  | -- |  | -- |  | 266.5 |  | 9.2 |  | 275.7
2022 |  | 267 | 286.9 |  | -- |  | -- |  | 286.9 |  | 7.1 |  | 294
2023 |  | 266 | 281.9 |  | -- |  | -- |  | 281.9 |  | 7.3 |  | 289.2
2024 |  | 266 | 305.5 |  | -- |  | -- |  | 305.5 |  | 22.3 |  | 327.8
Subtotal |  | 4461 | 3932.4 |  | 1.9 |  | 380.1 |  | 4314.4 |  | 252.6 |  | 4567

## Table 27
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | BY 1992 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1989 |  | 26 | 27.1 |  | -- |  | 2.9 |  | 30 |  | 2.6 |  | 32.6
1990 |  | 85 | 62 |  | -- |  | 18.9 |  | 80.9 |  | 4.9 |  | 85.8
1991 |  | 300 | 188.4 |  | -- |  | 52 |  | 240.4 |  | 17.2 |  | 257.6
1992 |  | 191 | 110.6 |  | -- |  | 36.5 |  | 147.1 |  | 39.5 |  | 186.6
1993 |  | 165 | 68.3 |  | -- |  | 19.1 |  | 87.4 |  | 11.7 |  | 99.1
1994 |  | 75 | 24.7 |  | -- |  | 19.9 |  | 44.6 |  | 7.9 |  | 52.5
1995 |  | 106 | 36.8 |  | -- |  | 22.4 |  | 59.2 |  | 9 |  | 68.2
1996 |  | 115 | 31.6 |  | -- |  | 25.6 |  | 57.2 |  | 9 |  | 66.2
1997 |  | 100 | 27 |  | -- |  | 14.6 |  | 41.6 |  | 5.3 |  | 46.9
1998 |  | 120 | 33.5 |  | -- |  | 8.9 |  | 42.4 |  | 5.5 |  | 47.9
1999 |  | 100 | 31.7 |  | -- |  | 7.8 |  | 39.5 |  | 4.7 |  | 44.2
2000 |  | 91 | 28.7 |  | -- |  | 8.5 |  | 37.2 |  | 2.2 |  | 39.4
2001 |  | 63 | 21.4 |  | -- |  | 7.7 |  | 29.1 |  | 2.9 |  | 32
2002 |  | 55 | 17.1 |  | -- |  | 10.7 |  | 27.8 |  | 3 |  | 30.8
2003 |  | 76 | 28.2 |  | -- |  | 10.3 |  | 38.5 |  | 2.8 |  | 41.3
2004 |  | 42 | 14.7 |  | -- |  | 12 |  | 26.7 |  | 3 |  | 29.7
2005 |  | 37 | 12.7 |  | -- |  | 7.3 |  | 20 |  | 2.3 |  | 22.3
2006 |  | 48 | 30.6 |  | -- |  | 22.8 |  | 53.4 |  | 2.4 |  | 55.8
2007 |  | 42 | 44.7 |  | -- |  | 18.5 |  | 63.2 |  | 2.5 |  | 65.7
2008 |  | 52 | 55.2 |  | -- |  | 5.6 |  | 60.8 |  | 1.9 |  | 62.7
2009 |  | 57 | 57.7 |  | -- |  | 1.7 |  | 59.4 |  | 1.9 |  | 61.3
2010 |  | 71 | 95.5 |  | -- |  | -- |  | 95.5 |  | 2.4 |  | 97.9
2011 |  | 101 | 93 |  | -- |  | -- |  | 93 |  | 3.5 |  | 96.5
2012 |  | 67 | 63.7 |  | -- |  | -- |  | 63.7 |  | 3.7 |  | 67.4
2013 |  | 67 | 54.6 |  | -- |  | -- |  | 54.6 |  | 4.3 |  | 58.9
2014 |  | 61 | 46.3 |  | -- |  | 1 |  | 47.3 |  | 7.8 |  | 55.1
2015 |  | -- | -- |  | 1.2 |  | -- |  | 1.2 |  | 0.2 |  | 1.4
2016 |  | 179 | 127.5 |  | -- |  | -- |  | 127.5 |  | 3.8 |  | 131.3
2017 |  | 163 | 128.8 |  | -- |  | -- |  | 128.8 |  | 1 |  | 129.8
2018 |  | 247 | 160.4 |  | -- |  | 1.3 |  | 161.7 |  | 1.2 |  | 162.9
2019 |  | 260 | 164.9 |  | -- |  | -- |  | 164.9 |  | 1.8 |  | 166.7
2020 |  | 252 | 157.5 |  | -- |  | -- |  | 157.5 |  | 3.4 |  | 160.9
2021 |  | 248 | 155.4 |  | -- |  | -- |  | 155.4 |  | 5.3 |  | 160.7
2022 |  | 267 | 164 |  | -- |  | -- |  | 164 |  | 4.1 |  | 168.1
2023 |  | 266 | 158 |  | -- |  | -- |  | 158 |  | 4.1 |  | 162.1
2024 |  | 266 | 167.8 |  | -- |  | -- |  | 167.8 |  | 12.3 |  | 180.1
Subtotal |  | 4461 | 2690.1 |  | 1.2 |  | 336 |  | 3027.3 |  | 201.1 |  | 3228.4

## Table 28
Annual Funding 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1984 |  | -- | -- |  | -- |  | 29.2 |  | 29.2 |  | -- |  | 29.2
1985 |  | -- | -- |  | -- |  | 74.1 |  | 74.1 |  | -- |  | 74.1
1986 |  | -- | -- |  | -- |  | 193.8 |  | 193.8 |  | 4.1 |  | 197.9
1987 |  | 180 | 405.2 |  | -- |  | 170.4 |  | 575.6 |  | 20.5 |  | 596.1
1988 |  | 400 | 535.5 |  | -- |  | 160.6 |  | 696.1 |  | 15.2 |  | 711.3
1989 |  | 874 | 667.3 |  | -- |  | 102.6 |  | 769.9 |  | 16.3 |  | 786.2
1990 |  | 803 | 576.3 |  | -- |  | 88.4 |  | 664.7 |  | 17.9 |  | 682.6
1991 |  | 600 | 397.5 |  | -- |  | 190.2 |  | 587.7 |  | 24.2 |  | 611.9
1992 |  | 700 | 438.5 |  | -- |  | 73.2 |  | 511.7 |  | 18.1 |  | 529.8
1993 |  | 1000 | 422.2 |  | -- |  | 140.5 |  | 562.7 |  | 30.6 |  | 593.3
1994 |  | 983 | 347.1 |  | -- |  | 81.5 |  | 428.6 |  | 18.4 |  | 447
1995 |  | 412 | 123.3 |  | -- |  | 75.5 |  | 198.8 |  | 31.7 |  | 230.5
1996 |  | 291 | 146.2 |  | -- |  | 21.7 |  | 167.9 |  | 11.9 |  | 179.8
1997 |  | 133 | 93.6 |  | -- |  | 10.8 |  | 104.4 |  | 8.2 |  | 112.6
1998 |  | 173 | 53.6 |  | -- |  | 44.6 |  | 98.2 |  | 4.8 |  | 103
1999 |  | 180 | 67 |  | -- |  | 22.4 |  | 89.4 |  | 1 |  | 90.4
2000 |  | 163 | 68.4 |  | -- |  | 6.2 |  | 74.6 |  | 9.2 |  | 83.8
2001 |  | 170 | 75.3 |  | -- |  | 9.4 |  | 84.7 |  | 10.6 |  | 95.3
2002 |  | 190 | 80.5 |  | -- |  | 7.1 |  | 87.6 |  | 12.6 |  | 100.2
2003 |  | 124 | 69.9 |  | -- |  | 4.1 |  | 74 |  | 11 |  | 85
2004 |  | 159 | 84.6 |  | -- |  | -- |  | 84.6 |  | 13.8 |  | 98.4
2005 |  | 159 | 87.7 |  | -- |  | -- |  | 87.7 |  | 19.2 |  | 106.9
2006 |  | 84 | 99.9 |  | -- |  | -- |  | 99.9 |  | 2.2 |  | 102.1
2007 |  | 59 | 103.9 |  | -- |  | -- |  | 103.9 |  | 11.6 |  | 115.5
2008 |  | 133 | 167.2 |  | -- |  | -- |  | 167.2 |  | 27.2 |  | 194.4
2009 |  | 133 | 161.3 |  | -- |  | -- |  | 161.3 |  | 45.8 |  | 207.1
2010 |  | 170 | 248.4 |  | -- |  | -- |  | 248.4 |  | 29.1 |  | 277.5
2011 |  | 246 | 311.9 |  | -- |  | -- |  | 311.9 |  | 28.2 |  | 340.1
2012 |  | 112 | 146.7 |  | -- |  | -- |  | 146.7 |  | 20.9 |  | 167.6
2013 |  | 113 | 176.5 |  | -- |  | -- |  | 176.5 |  | 24.9 |  | 201.4
2014 |  | 279 | 303.6 |  | -- |  | -- |  | 303.6 |  | 8.5 |  | 312.1
2015 |  | 223 | 305 |  | -- |  | -- |  | 305 |  | 14.7 |  | 319.7
2016 |  | 262 | 352.2 |  | -- |  | -- |  | 352.2 |  | 29.8 |  | 382
2017 |  | 256 | 317.3 |  | -- |  | -- |  | 317.3 |  | 34.9 |  | 352.2
2018 |  | 388 | 409.8 |  | -- |  | -- |  | 409.8 |  | 37.8 |  | 447.6
2019 |  | 404 | 429.2 |  | -- |  | -- |  | 429.2 |  | 42.9 |  | 472.1
2020 |  | 414 | 435.4 |  | -- |  | -- |  | 435.4 |  | 39.6 |  | 475
2021 |  | 403 | 430.1 |  | -- |  | -- |  | 430.1 |  | 40.5 |  | 470.6
2022 |  | 415 | 448.7 |  | -- |  | -- |  | 448.7 |  | 43.2 |  | 491.9
2023 |  | 532 | 563.8 |  | -- |  | -- |  | 563.8 |  | 44 |  | 607.8

## Table 29
2024 | 531 | 569.4 | -- | -- | 569.4 | 46.9 | 616.3
Subtotal | 12851 | 10720 | -- | 1506.3 | 12226.3 | 872 | 13098.3

## Table 30
Annual Funding 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | BY 1992 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1984 |  | -- | -- |  | -- |  | 36 |  | 36 |  | -- |  | 36
1985 |  | -- | -- |  | -- |  | 88.8 |  | 88.8 |  | -- |  | 88.8
1986 |  | -- | -- |  | -- |  | 221.8 |  | 221.8 |  | 4.7 |  | 226.5
1987 |  | 180 | 445 |  | -- |  | 187.1 |  | 632.1 |  | 22.6 |  | 654.7
1988 |  | 400 | 567.5 |  | -- |  | 170.1 |  | 737.6 |  | 16.1 |  | 753.7
1989 |  | 874 | 676.7 |  | -- |  | 104 |  | 780.7 |  | 16.6 |  | 797.3
1990 |  | 803 | 573.7 |  | -- |  | 88.1 |  | 661.8 |  | 17.8 |  | 679.6
1991 |  | 600 | 384.8 |  | -- |  | 184.1 |  | 568.9 |  | 23.4 |  | 592.3
1992 |  | 700 | 419.6 |  | -- |  | 70.1 |  | 489.7 |  | 17.3 |  | 507
1993 |  | 1000 | 396 |  | -- |  | 131.7 |  | 527.7 |  | 28.7 |  | 556.4
1994 |  | 983 | 319 |  | -- |  | 74.9 |  | 393.9 |  | 16.9 |  | 410.8
1995 |  | 412 | 112.2 |  | -- |  | 68.6 |  | 180.8 |  | 28.9 |  | 209.7
1996 |  | 291 | 131.3 |  | -- |  | 19.5 |  | 150.8 |  | 10.7 |  | 161.5
1997 |  | 133 | 82.9 |  | -- |  | 9.6 |  | 92.5 |  | 7.3 |  | 99.8
1998 |  | 173 | 47 |  | -- |  | 39.1 |  | 86.1 |  | 4.2 |  | 90.3
1999 |  | 180 | 58.1 |  | -- |  | 19.4 |  | 77.5 |  | 0.9 |  | 78.4
2000 |  | 163 | 58.6 |  | -- |  | 5.3 |  | 63.9 |  | 7.9 |  | 71.8
2001 |  | 170 | 63.8 |  | -- |  | 8 |  | 71.8 |  | 9 |  | 80.8
2002 |  | 190 | 67.1 |  | -- |  | 5.9 |  | 73 |  | 10.5 |  | 83.5
2003 |  | 124 | 57.6 |  | -- |  | 3.4 |  | 61 |  | 9.1 |  | 70.1
2004 |  | 159 | 68.2 |  | -- |  | -- |  | 68.2 |  | 11.1 |  | 79.3
2005 |  | 159 | 68.7 |  | -- |  | -- |  | 68.7 |  | 15.1 |  | 83.8
2006 |  | 84 | 76.1 |  | -- |  | -- |  | 76.1 |  | 1.7 |  | 77.8
2007 |  | 59 | 77.3 |  | -- |  | -- |  | 77.3 |  | 8.6 |  | 85.9
2008 |  | 133 | 122.1 |  | -- |  | -- |  | 122.1 |  | 19.9 |  | 142
2009 |  | 133 | 116.1 |  | -- |  | -- |  | 116.1 |  | 33 |  | 149.1
2010 |  | 170 | 176.2 |  | -- |  | -- |  | 176.2 |  | 20.7 |  | 196.9
2011 |  | 246 | 217 |  | -- |  | -- |  | 217 |  | 19.6 |  | 236.6
2012 |  | 112 | 100.3 |  | -- |  | -- |  | 100.3 |  | 14.3 |  | 114.6
2013 |  | 113 | 118 |  | -- |  | -- |  | 118 |  | 16.7 |  | 134.7
2014 |  | 279 | 200.1 |  | -- |  | -- |  | 200.1 |  | 5.6 |  | 205.7
2015 |  | 223 | 198.8 |  | -- |  | -- |  | 198.8 |  | 9.6 |  | 208.4
2016 |  | 262 | 225.5 |  | -- |  | -- |  | 225.5 |  | 19.1 |  | 244.6
2017 |  | 256 | 199.4 |  | -- |  | -- |  | 199.4 |  | 21.9 |  | 221.3
2018 |  | 388 | 252.5 |  | -- |  | -- |  | 252.5 |  | 23.3 |  | 275.8
2019 |  | 404 | 259.2 |  | -- |  | -- |  | 259.2 |  | 25.9 |  | 285.1
2020 |  | 414 | 257.8 |  | -- |  | -- |  | 257.8 |  | 23.5 |  | 281.3
2021 |  | 403 | 249.6 |  | -- |  | -- |  | 249.6 |  | 23.5 |  | 273.1
2022 |  | 415 | 255.3 |  | -- |  | -- |  | 255.3 |  | 24.6 |  | 279.9
2023 |  | 532 | 314.6 |  | -- |  | -- |  | 314.6 |  | 24.6 |  | 339.2

## Table 31
2024 | 531 | 311.5 | -- | -- | 311.5 | 25.6 | 337.1
Subtotal | 12851 | 8325.2 | -- | 1535.5 | 9860.7 | 640.5 | 10501.2

## Table 32
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 1987-06-04 | 1991-05-23
Approved Quantity | 810 | 4159
Reference | Milestone IIIA ADM | Milestone IIIB ADM
Start Year | 1987 | 1987
End Year | 1989 | 1992
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the LRIP extension to include 6 lots, FY 1987 through FY 1992. The follow-on DAB Program Review, held on April 23, 1992, approved FRP for Lot VII (FY 1993) procurement. The original LRIP decision during the Milestone IIIA review by the DAB in June 1987 to procure 810 LRIP missiles which covered 2 lots. On May 23, 1991, the DAB for Milestone IIIB approved a procurement quantity of 4,159 missiles.

## Table 33
Foreign Military Sales
Classified FMS information is provided in the classified annex to this submission.
Nuclear Costs
None

## Table 34
Unit Cost
Unit Cost Report
Item |  | BY 1992 $M | BY 1992 $M |  | % Change
|  | Current UCR Baseline (Oct 2015 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 15994.2 |  |  | 16142.7
Quantity | 16427 |  |  | 17312
Unit Cost | 0.974 |  |  | 0.932 |  | -4.31
Average Procurement Unit Cost
Cost | 13574.7 |  |  | 13729.6
Quantity | 16427 |  |  | 17312
Unit Cost | 0.826 |  |  | 0.793 |  | -4
Item |  | BY 1992 $M | BY 1992 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Sep 1996 APB)
Program Acquisition Unit Cost
Cost | 12302.9 |  |  | 16142.7
Quantity | 13038 |  |  | 17312
Unit Cost | 0.944 |  |  | 0.932 |  | -1.27
Average Procurement Unit Cost
Cost | 10205.7 |  |  | 13729.6
Quantity | 13038 |  |  | 17312
Unit Cost | 0.783 |  |  | 0.793 |  | 1.28

## Table 35
Unit Cost History
Item | [5 empty] | Date |  |  | BY 1992 $M |  |  |  |  | TY $M
[9 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Dec 1988 | [5 empty] | 0.471 |  |  | 0.409 |  |  | 0.46 |  |  | 0.413
APB as of January 2006 |  |  | Sep 1996 | [5 empty] | 0.944 |  |  | 0.783 |  |  | 1.022 |  |  | 0.883
Revised Original APB |  |  | Sep 1996 | [5 empty] | 0.944 |  |  | 0.783 |  |  | 1.022 |  |  | 0.883
Prior APB |  |  | Mar 2015 | [5 empty] | 0.974 |  |  | 0.826 |  |  | 1.202 |  |  | 1.065
Current APB |  |  | Oct 2015 | [5 empty] | 0.974 |  |  | 0.826 |  |  | 1.202 |  |  | 1.065
Prior Annual SAR |  |  | Dec 2014 | [5 empty] | 1.002 |  |  | 0.822 |  |  | 1.246 |  |  | 1.057
Current Estimate |  |  | Dec 2015 | [5 empty] | 0.932 |  |  | 0.793 |  |  | 1.15 |  |  | 1.02
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Production Estimate | Changes | [14 empty] | PAUC Current Estimate
| Econ | Qty |  |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
0.849 -0.017 -0.007 0.145 0.068 0.079 0.000 0.033 0.301 1.150
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Production Estimate | Changes | [14 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  |  | Eng | Est |  | Oth | Spt |  | Total
0.761 -0.015 0.002 0.144 0.031 0.064 0.000 0.033 0.259 1.020

## Table 36
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone I | N/A | Nov 1978 | Nov 1978 | Nov 1978
Milestone II | N/A | Nov 1982 | Sep 1982 | Sep 1982
Milestone III | N/A | Dec 1984 | Apr 1991 | Apr 1991
IOC | N/A | Sep 1986 | Sep 1992 | Sep 1993
Total Cost (TY $M) | N/A | 11591.6 | 13112.4 | 19902
Total Quantity | N/A | 24335 | 15450 | 17312
PAUC | N/A | 0.476 | 0.849 | 1.15

## Table 37
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
1350.6 11761.8 -- 13112.4
Economic |  | -45.1 |  | -205.8 |  | -- |  | -250.9
Quantity |  | -- |  | 925.2 |  | -- |  | 925.2
Schedule |  | 26.5 |  | 2575.2 |  | -- |  | 2601.7
Engineering |  | 643.8 |  | 512.1 |  | -- |  | 1155.9
Estimating |  | 1148.7 |  | 1316.9 |  | -- |  | 2465.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 591 |  | -- |  | 591
Subtotal |  | 1773.9 |  | 5714.6 |  | -- |  | 7488.5
Current Changes Economic |  | -5.2 |  | -46 |  | -- |  | -51.2
Quantity |  | -- |  | 511.9 |  | -- |  | 511.9
Schedule |  | -- |  | -83.2 |  | -- |  | -83.2
Engineering |  | -- |  | 29.8 |  | -- |  | 29.8
Estimating |  | -882.6 |  | -207.2 |  | -- |  | -1089.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -16.4 |  | -- |  | -16.4
Subtotal |  | -887.8 |  | 188.9 |  | -- |  | -698.9
Total Changes |  | 886.1 |  | 5903.5 |  | -- |  | 6789.6
CE - Cost Variance |  | 2236.7 |  | 17665.3 |  | -- |  | 19902
CE - Cost & Funding |  | 2236.7 |  | 17665.3 |  | -- |  | 19902

## Table 38
Summary BY 1992 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
1725.7 10552.5 -- 12278.2
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 597.2 |  | -- |  | 597.2
Schedule |  | 13.6 |  | 1126 |  | -- |  | 1139.6
Engineering |  | 510.9 |  | 377.2 |  | -- |  | 888.1
Estimating |  | 716.5 |  | 612.7 |  | -- |  | 1329.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 338.5 |  | -- |  | 338.5
Subtotal |  | 1241 |  | 3051.6 |  | -- |  | 4292.6
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 281.8 |  | -- |  | 281.8
Schedule |  | -- |  | -31.1 |  | -- |  | -31.1
Engineering |  | -- |  | 16.4 |  | -- |  | 16.4
Estimating |  | -553.6 |  | -130.5 |  | -- |  | -684.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -11.1 |  | -- |  | -11.1
Subtotal |  | -553.6 |  | 125.5 |  | -- |  | -428.1
Total Changes |  | 687.4 |  | 3177.1 |  | -- |  | 3864.5
CE - Cost Variance |  | 2413.1 |  | 13729.6 |  | -- |  | 16142.7
CE - Cost & Funding |  | 2413.1 |  | 13729.6 |  | -- |  | 16142.7
Previous Estimate: December 2014

## Table 39
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | -5.2
Realignment of RDT&E funds to O&S (Air Force). (Estimating) |  | -353.9 | -556.8
Realignment of RDT&E funds to O&S (Navy). (Estimating) |  | -202.4 | -331
Adjustment for current and prior escalation. (Estimating) |  | 0.3 | 0.9
Revised estimate to reflect application of escalation indices (Air Force). (Estimating) |  | 1.5 | 2.6
Revised estimate to reflect application of escalation indices (Navy). (Estimating) |  | 0.9 | 1.7
RDT&E Subtotal |  | -553.6 | -887.8
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -46.0
Quantity variance resulting from an increase of 772 missiles from 12,079 to 12,851 (Air Force). (Subtotal)
Quantity variance resulting from an increase of 772 missiles from 12,079 to 12,851 (Air Force). (Quantity)
+422.9 +768.3
(+281.8) (+511.9)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) (+82.5) (+149.9) Allocation to Engineering resulting from Quantity change. (Engineering) (QR) (+16.4) (+29.8) Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (+42.2) (+76.7)
Additional Schedule variance resulting from realignment of missile buy profile from FY 2014 through FY 2024 (Air Force). (Schedule)
Additional Schedule variance resulting from realignment of missile buy profile from FY 2014 through FY 2024 (Navy). (Schedule)
Acceleration of procurement buy profile to meet total Air Force procurement objective of 12,851 missiles (Air Force). (Schedule)
Acceleration of procurement buy profile within FYDP to meet total Navy procurement objective of 4,461 missiles (Navy). (Schedule)
Increase in Diminishing Manufacturing Sources (DMS) costs due to updated estimate and realization of actual costs (Air Force). (Estimating)
Increase in DMS costs due to updated estimate and realization of actual costs (Navy). (Estimating)
Increase in Production test and technical support requirements due to updated estimate and realization of actual costs (Air Force). (Estimating)
Decrease in Production test and technical support requirements due to updated estimate and realization of actual costs (Navy). (Estimating)
Revised estimate methodology for missile hardware by using negotiated values instead of proposal data (Navy). (Estimating)
Revised estimate methodology for missile hardware by using negotiated values instead of proposal data (Air Force). (Estimating)
-79.9 -138.8
-33.7 -56.9
0.0 -30.6
0.0 -6.8
+17.1 +34.3
+11.8 +18.7
+15.1 +26.6
-15.1 -25.5
-93.8 -160.5
-134.8 -225.3
Adjustment for current and prior escalation. (Estimating) | 1.6 |  |  | 4.5
Revised estimate to reflect application of escalation indices (Navy). (Estimating) | 11.1 |  |  | 19.1
Revised estimate to reflect application of escalation indices (Air Force). (Estimating) | 14.3 |  |  | 24.2
Adjustment for current and prior escalation. (Support) | 0.7 |  |  | 0.7

## Table 40
Decrease in Other Support due to decrease of training equipment requirements (Air Force). (Support)
Decrease in Other Support due to decrease of training equipment requirements (Navy). (Support)
Decrease in Initial Spares due to decrease in initial spares requirements (Air Force). (Support)
-9.0 -11.5
-2.9 -5.4
0.0 -0.2
Increase in Initial Spares due to application of escalation indices (Navy). (Support) +0.1 0.0
Procurement Subtotal +125.5 +188.9
(QR) Quantity Related

## Table 41
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: Raytheon Lot 25
Contractor: Raytheon Company
Contractor Location: 1151 East Hermans Road
Tucson, AZ 85706
Contract Number: FA8675-11-C-0030
Contract Type: Firm Fixed Price (FFP)
Award Date: August 31, 2011
Definitization Date: August 31, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
569.0 N/A 469 666.1 N/A 550 666.1 666.1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to additional telemetry devices and the addition of AIM-120C7 missiles for FMS. Additionally, other contract modifications were performed as needed and were within scope. AIM-120D production is anticipated to complete in first quarter FY 2016.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 42
Contract Identification
Appropriation: Procurement
Contract Name: Raytheon Lot 26
Contractor: Raytheon Company
Contractor Location: 1151 East Hermans Road
Tuscon, AZ 85706
Contract Number: FA8675-12-C-0011
Contract Type: Firm Fixed Price (FFP)
Award Date: March 30, 2012
Definitization Date: March 30, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
497.1 N/A 404 528.0 N/A 404 528.0 528.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to addition of a Lean Cost Reduction Initiative, Life-of-Type buys for the Shortened Control Actuation System and a Final Assembly Test Station in CY 2012. Additionally, other contract modifications were performed as needed and were within scope. Lot 26 was completed in September 2015.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 43
Contract Identification
Appropriation: Procurement
Contract Name: Raytheon Lot 27
Contractor: Raytheon Company
Contractor Location: 1151 East Hermans Road
Tucson, AZ 85706
Contract Number: FA8675-13-C-0003
Contract Type: Firm Fixed Price (FFP)
Award Date: June 17, 2013
Definitization Date: June 17, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
534.7 N/A 464 578.7 N/A 464 578.7 578.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to FMS offsets, second source warhead and Life of Type Buys. Additionally, other contract modifications were performed as needed and were within scope. AIM-120D production is anticipated to complete in July 2016.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 44
Contract Identification
Appropriation: Procurement
Contract Name: Program Support and Sustainment (PSAS)
Contractor: Raytheon Company
Contractor Location: 1151 East Hermans Road
Tucson, AZ 85706
Contract Number: FA8675-14-C-0026
Contract Type: Firm Fixed Price (FFP)
Award Date: June 27, 2014
Definitization Date: June 27, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
63.3 N/A N/A 68.0 N/A N/A 68.0 68.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to extending services for system engineering and support (SEPM) and service life prediction program (SLPP). Additionally, other contract modifications were performed as needed and were within scope.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
The initial contract price was changed from $166.4M to $63.3M because the DMS refresh Ph 3 F3R is broken out as a separate contract.

## Table 45
Contract Identification
Appropriation: Procurement
Contract Name: AMRAAM Production LOTS 28, 29, 30
Contractor: Raytheon Company
Contractor Location: 1151 E Hermans Road
Tucson, AZ 85756
Contract Number: FA8675-15-C-0022
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 22, 2014
Definitization Date: December 22, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
1020.3 1020.3 1133 1071.5 1071.5 1133 1071.5 1071.5
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to additional Life of Type Buys, special tooling and equipment and PRP guidance sections. Additionally, other contract modifications were performed as needed and were within scope.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because an earned value management (EVM) waiver was granted by Assistant Secretary of the Air Force for Acquisition on September 19, 2014. Under the Better Buying Power (BBP) goal to “Employ appropriate contract types,” the AMRAAM production lot contract transitioned from a Firm Fixed Price (FFP) contract type to a Fixed Price Incentive (Firm Target) (FPIF) contract type. This approach allows the government to share expected cost savings with the contractor and does not require EVM information in order to properly execute this strategy.
Notes
Production Lot 28: The following missiles were purchased on the Lot 28 contract: 190 USAF AIM-120D Air Vehicles (AAVs), 9 USAF AIM-120D AMRAAM Air Vehicles Instrumented (AAVIs), 18 USAF and 54 USN AIM-120D Captive Air Training Missiles (CATMs) and 300 AIM-120C7 AMRAAM missiles for FMS customers. Lot 28 missile deliveries begin in July 2016 and are projected to be complete by July 2017.
Production Lot 29: The following missiles were purchased on the Lot 29 contract: 285 USAF and 7 AIM-120D Air Vehicles (AAVs) and 270 AIM-120C7 AMRAAM missiles for FMS customers. Lot 29 missile deliveries begin in July 2017 and are projected to be complete by April 2018.
The initial contract price was updated from $491.5M to $1020.3M due to the award of Lot 29 contract option.

## Table 46
Contract Identification
Appropriation: Procurement
Contract Name: DMSMS Refresh Phase 3 F3R
Contractor: Raytheon Company
Contractor Location: 1151 East Hermans Road
Tuscon, AZ 85706
Contract Number: FA8675-14-C-0026/881 Contract Type: Cost Plus Incentive Fee (CPIF) Award Date: June 27, 2014
Definitization Date: May 27, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
99.9 N/A N/A 99.9 N/A N/A 116.7 114.6
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) -18.5 -4.4
Previous Cumulative Variances -- --
Net Change -18.5 -4.4
Cost and Schedule Variance Explanations
The unfavorable cumulative cost variance is due to additional resources required to accommodate the delays in schedule in the areas of guidance section hardware, system on a chip (SOC) and integration.
The unfavorable cumulative schedule variance is due to issues with guidance section hardware, SOC, and integration and verification. The guidance section hardware team experienced challenges with several of the circuit card assemblies. Due to delays in development of engineering test fixtures, the team had to build test interface boards that drove additional cost in unplanned work. Issues associated with SOC include schedule delays due to design complexity. Issues associated with integration and verification include late hardware delivery and troubleshooting multiple issues.
Notes
This is the first time this contract is being reported.
DMSMS Refresh Phase 3 F3R: This contract includes Form-Fit-Function-Refresh (F3R). This effort supports USAF, USN and Foreign Military Sales (FMS) customers.
This contract was part of the Program Support and Sustainment (PSAS) contract and is now listed separately.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 47
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 11584 | 10998 | 17312 | 63.53%
Total Program Quantity Delivered | 11584 | 10998 | 17312 | 63.53%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
19902
13044.4
65.54%
48
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
40
83.33%
13752.2
69.1%
The above data is current as of February 09, 2016.

## Table 48
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 05, 2016
Source of Estimate: POE
Quantity to Sustain: 17312
Unit of Measure: Total Quantity
Service Life per Unit: 25.00 Years
Fiscal Years in Service: FY 1991 - FY 2050
The O&S costs are the direct costs for the tactical missile and the Captive Carry Missile (CCM) associated with operating, supporting, and maintaining the AMRAAM missile over a 60-year deployment phase starting in FY 1991 for the Air Force and FY 1992 for the Navy. The Air Force estimate covers base operations including CCM, All-Up-Round (AUR) fault verification, operational firings, depot repairs (seven year Interim Contractor Support (ICS)), supply/item management, transportation, replenishment spares, and field software updates. The Navy estimate includes AMRAAM
fleet operations and support, depot rework (five years ICS), technical support (fleet support, engineering services, quality surveillance, program management), supply support, replenishment spares, and contractor augmented support.
Sustainment Strategy
The AUR maintenance concept calls for aircraft loading/unloading, removal/replacement of wings and fins and missile Built-In-Test (BIT). A missile failing BIT will be sent to the Intermediate-Level Shop for test verification on the Missile Bit Test Set (Air Force only), Common Field-Level Memory Reprogramming Equipment, or Common Munitions BIT Reprogramming Equipment Plus. Failed missiles will be returned to the contractor AMRAAM depot for repair.
Antecedent Information
The antecedent system is the AIM-7. The AIM-7 is the last semi-active air-to-air missile while the AIM-120 provides the first fully active and autonomous launch and leave medium range capability. The AIM-7 cost data was obtained from the Naval Visibility and Management of Operating and Support Cost (VAMOSC) database (FY 1990 - FY 2013) and is historical in nature.
Annual O&S Costs BY1992 $M
Cost Element | AMRAAM Average Annual Cost Per Total Quantity | AIM-7 (Antecedent) Average Annual Cost For All Missiles
Unit-Level Manpower | 0.175 | 0
Unit Operations | 0.311 | 0.627
Maintenance | 7.867 | 4.29
Sustaining Support | 16.61 | 4.615
Continuing System Improvements | 12.333 | 1.192
Indirect Support | 1.314 | 0
Other | 0 | 0
Total | 38.61 | 10.724
Cost Element Continuing System Improvements was revised to include O&S RDT&E for both Navy and Air Force.

## Table 49
Item | Total O&S Cost $M
| AMRAAM | [6 empty] | AIM-7 (Antecedent)
| Current Production APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year |  | 2210 |  | 2431 |  |  | 2316.6 |  | N/A
Then Year |  | 3928.3 |  | N/A |  |  | 4070 |  | N/A
.
Equation to Translate Annual Cost to Total Cost
Total O&S Cost = Average Annual O&S Cost per Total Quantity *total O&S years = $38.610M * 60 years = $2316.6M
O&S Cost Variance
Category |  |  | BY 1992 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
892.4
Programmatic/Planning Factors 582.8 Realignment of RDT&E funds to O&S Cost Estimating Methodology 0.0
Cost Data Update 540.2 Update to actual costs Labor Rate 0.2 Update to 2015 labor rates
Energy Rate 0.0
Technical Input 301.0 Added new requirement for Program Office Manpower Other 0.0
Total Changes 1424.2
Current Estimate 2316.6
Program office completed a new O&S cost model. The O&S model includes adding 25 years to the program life, increasing the service life from 20 to 25 years, and realigning the RDT&E funds into O&S. Although there are quantity changes as well, the variances based on each of these changes cannot be defined individually.
Disposal Estimate Details
Date of Estimate: January 05, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 1992 $M): Total costs for disposal of all Total Quantity are 3.6
Letterkenny Munitions Center is utilized to demilitarize AMRAAM. The decision to demilitarize individual missiles or entire lots in lieu of refurbishment or retrofit will be made by Air Combat Command (ACC) for the Air Force and Navy Resource Sponsor for the Navy.

## Table 50
The disposal total cost was changed from 10.8 to 3.6 due to an increase in total inventory and a decrease in demil cost per missile.