## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-224
B-2 Extremely High Frequency SATCOM and Computer Increment 1 (B-2 EHF Inc 1)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 11
Cost and Funding 13
Low Rate Initial Production 19
Foreign Military Sales 20
Nuclear Costs 20
Unit Cost 21
Cost Variance 24
Contracts 27
Deliveries and Expenditures 28
Operating and Support Cost 29

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
B-2 Extremely High Frequency SATCOM and Computer Increment 1 (B-2 EHF Inc 1)
DoD Component
Air Force
Responsible Office
Col Robert Strasser B-2 SPM
2690 Loop Road West Area B, Bldg. 556
Wright-Patterson Air Force Base, OH 45433-7148
robert.strasser@us.af.mil
Phone: | 937-713-6450
Fax: | 937-656-7207
DSN Phone: | 716-6450
DSN Fax: | 986-7207
Date Assigned: | May 6, 2013
References
SAR Baseline (Production Estimate)
Air Force Acquisition Executive (AFAE) Approved Acquisition Program Baseline (APB) dated September 20, 2012
Approved APB
Air Force Acquisition Executive (AFAE) Approved Acquisition Program Baseline (APB) dated September 20, 2012

## Table 6
Mission and Description
The aging Ultra High Frequency (UHF) Military Satellite Communications (MILSATCOM) system is being phased out and replaced by the Advanced Extremely High Frequency (AEHF) Satellite Communications (SATCOM) system.
B-2 Extremely High Frequency SATCOM and Computer Increment 1 program (B-2 EHF Inc 1) supports the replacement of the present B-2 UHF Terminal Set with an EHF SATCOM system that will be compatible with the legacy EHF Satellite (MILSTAR I/II) constellation and the future AEHF satellite constellation. The B-2 EHF Inc 1 system is one element of a system-of-systems that includes the AEHF satellites, multiple platforms, and the Family of Advanced Beyond-Line-of-Site Terminals. The B-2 EHF upgrade is a three-increment program. Increment 1 will provide upgraded flight management computer processors, increased data storage, a re-hosted Flight Management Operational Flight Program, and a high bandwidth data bus in order to prevent degradation of existing capabilities resulting from EHF SATCOM installation.
Additionally, the Increment 1 Integrated Processing Unit and Disk Drive Unit architectures establish a high speed fiber optic structure network as well as maintain connectivity to legacy interfaces. Increment 1 provides a processing growth path to future B-2 upgrades. B-2 EHF Inc 2 would ensure continuing secure, survivable communication capability; and B-2 EHF Inc 3 would enable the B-2 to interface with the Global Information Grid and provide Net Ready capability. This SAR addresses B-2 EHF Inc 1 only.
Note: EHF SATCOM Increment 2 was terminated on December 31, 2013 and Increment 3 was never started. Both Increments 2 and 3 were replaced with the EHF SATCOM program which is planned to begin development in FY 2016.

## Table 7
Executive Summary
Pursuant to section 2432 of title 10, United States Code, this is the final SAR submission for B-2 EHF Inc 1, because the program is 90% or more expended and 90% or more delivered.
B-2 EHF Inc 1 consists of upgraded flight management processors, increased data storage and a high-bandwidth data bus which provide a processing growth path for future B-2 upgrades. On April 26, 2013, Air Force Global Strike Command authorized fielding and full-up (conventional and nuclear) use of EHF modified aircraft.
The program realized several significant accomplishments during this period. Six production installations occurred at Whiteman Air Force Base, MO and an additional three aircraft completed modification during programmed depot maintenance in Palmdale, CA. The remaining two aircraft are currently in modification.
The EMD contract is complete and is progressing through financial closeout.
The Air Force Acquisition Executive (AFAE) certified that the B-2 EHF Inc 1 Program was in compliance with the requirements of Section 2366a of title 10, United States Code on May 30, 2007; the certification waived the requirement for an analysis of alternatives.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B | May 2007 | May 2007 | May 2007 | May 2007
Milestone C | Feb 2012 | Feb 2012 | Feb 2012 | Feb 2012
Final DIOT&E flight | Jul 2012 | Jul 2012 | Jul 2012 | Jul 2012
RAA | Mar 2015 | Mar 2015 | Mar 2016 | Dec 2014
Change Explanations
Notes
RAA is defined as eight assigned aircraft modified, sufficient aircrews and maintenance personnel trained, sufficient aircrew and maintenance trainers upgraded, formal aircrew and maintenance technical orders delivered and adequate spares available to support 509th Bombardment Wing operational tasking. IOC is declared by the Commander, Air Force Global Strike Command when the B-2 operational squadrons have completed the upgrade.
Acronyms and Abbreviations
DIOT&E - Dedicated Initial Operational Test and Evaluation RAA - Required Assets Available

## Table 10
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Information Assurance (IA)
Protection consistent w/the classification of data being stored, processed, or transferred in compliance with Senior Jersey Security Classification Guide and JAFAN 6/3 Manual, Protection Special Access Program Information Within Information Systems | Protection consistent w/the classification of data being stored, processed, or transferred in compliance with Senior Jersey Security Classification Guide and JAFAN 6/3 Manual, Protection Special Access Program Information Within Information Systems | Protection consistent w/the classification of data being stored, processed, or transferred in compliance with Senior Jersey Security Classification Guide and JAFAN 6/3 Manual, Protection Special Access Program Information Within Information Systems | Protection consistent w/the classification of data being stored, processed, or transferred in compliance with Senior Jersey Security Classification Guide and JAFAN 6/3 Manual, Protection Special Access Program Information Within Information Systems | Protection consistent w/the classification of data being stored, processed, or transferred in compliance with Senior Jersey Security Classification Guide and JAFAN 6/3 Manual, Protection Special Access Program Information Within Information Systems
Flight Management Functionality
IFC-P5 functionality shall be maintained | IFC-P5 functionality shall be maintained | IFC-P5 functionality shall be maintained | IFC-P5 functionality maintained | IFC-P5 functionality shall be maintained
Requirements Reference
CPD dated July 19, 2011
Change Explanations
None
Notes
IFC-P5 is the fifth major block software release for the B-2 Weapon System and is specifically tied to the Radar Modernization Program.
Acronyms and Abbreviations
IFC - Integrated Functional Capability JAFAN - Joint Air Force, Army, Navy

## Table 11
Track to Budget
General Notes
This SAR includes funding only for Increment 1 of the B-2 EHF Program.
RDT&E
Appn |  | BA | PE
Air Force | 3600 07 |  | 0101127F
| Project |  | Name
| 675345 |  | B-2 EHF Inc 1 SATCOM and Computer Upgrade | (Shared) | (Sunk)
| Notes: |  | Complete FY 2011
| 676022 |  | B-2 EHF Inc 1 SATCOM and Computer Upgrade | (Shared) | (Sunk)
| Notes: |  | Complete FY 2013
Air Force | 3600 05 |  | 0604240F
| Project |  | Name
| 653843 |  | B-2 EHF Inc 1 SATCOM and Computer Upgrade | (Shared) | (Sunk)
| Notes: |  | Complete FY 2009
Notes
Prior to FY 2013, PE 0101127F project 6022 also funded B-2 EHF Increment 2.
Procurement
Appn |  | BA | PE
Air Force | 3010 07 |  | 0101127F
| Line Item |  | Name
| 75 |  | B-2 EHF Inc 1 SATCOM and Computer Upgrade Product Support / Depot Activation |  |  | (Shared)
Air Force | 3010 06 |  | 0101127F
| Line Item |  | Name
| 999 |  | B-2 EHF Inc 1 SATCOM and Computer Upgrade Initial Spares |  |  | (Shared)
Air Force | 3010 05 |  | 0101127F
| Line Item |  | Name
| B00200 |  | B-2 EHF Inc 1 SATCOM and Computer Upgrade Modifications |  |  | (Shared)
Air Force | 3010 07 |  | 0101127F
| Line Item |  | Name
| B00200 |  | B-2 EHF Inc 1 SATCOM and Computer Upgrade Interim Contractor Support |  |  | (Shared) (Sunk)

## Table 12
B002B0 B-2 EHF Inc 1 SATCOM and Computer Upgrade Interim Contractor Support
(Shared) (Sunk)
Notes
Aircraft Procurement, Air Force BA 05 line is shared for all B-2 Modifications (EHF SATCOM is modification number 110026 on the Exhibit P-40, Budget Item Justification). Funding for Initial Spares is in the shared BA 06 line; funding for Post Production Support is provided in BA 07 (Line Item 000075), and funding for Other Production is provided in BA 07 (Line Item B00200 and Line Item B002B0). The BA 07 line is shared for all B-2 Modifications.

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2012 $M | [6 empty] | BY 2012 $M |  | TY $M
| SAR Baseline Production Estimate |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 450.2 |  |  | 450.2 | 495.2 |  |  | 430.5 |  | 431.5 |  |  | 431.5 |  | 411.6
Procurement |  | 129 |  |  | 129 | 141.9 |  |  | 123.4 |  | 135.2 |  |  | 135.2 |  | 128.8
Flyaway |  | -- |  |  | -- | -- |  |  | 112.9 |  | -- |  |  | -- |  | 117.8
Recurring |  | -- |  |  | -- | -- |  |  | 112.9 |  | -- |  |  | -- |  | 117.8
Non Recurring |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support |  | -- |  |  | -- | -- |  |  | 10.5 |  | -- |  |  | -- |  | 11
Other Support |  | -- |  |  | -- | -- |  |  | 1.8 |  | -- |  |  | -- |  | 1.8
Initial Spares |  | -- |  |  | -- | -- |  |  | 8.7 |  | -- |  |  | -- |  | 9.2
MILCON |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 579.2 |  |  | 579.2 | N/A |  |  | 553.9 |  | 566.7 |  |  | 566.7 |  | 540.4
Confidence Level
Confidence Level of cost estimate for current APB: 55%
This APB reflects cost and funding data based on the B-2 EHF Increment I SCP. This cost estimate was quantified at the Mean (~55%) confidence level.
Total Quantity
Quantity |  |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  |  | 4 |  |  |  | 4 |  |  |  |  | 4
Procurement |  |  | 16 |  |  |  | 16 |  |  |  |  | 16
Total |  |  | 20 |  |  |  | 20 |  |  |  |  | 20

## Table 14
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 411.6 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 411.6
Procurement | 127.9 | 0.7 |  |  | 0.2 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 128.8
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 539.5 | 0.7 |  |  | 0.2 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 540.4
PB 2016 Total | 539.9 | 1.4 |  |  | 0.2 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 541.5
Delta | -0.4 | -0.7 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | -1.1
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 4 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 4
Production | 0 |  | 16 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 16
PB 2017 Total | 4 |  | 16 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 20
PB 2016 Total | 4 |  | 16 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 20
Delta | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Table 15
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.4
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 75.7
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 71.6
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 85
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
Subtotal |  | 4 | -- |  | -- |  | -- |  | -- |  | -- |  | 411.6

## Table 16
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2012 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 81.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 75.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 88.4
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 50.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.9
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
Subtotal |  | 4 | -- |  | -- |  | -- |  | -- |  | -- |  | 430.5

## Table 17
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | 5 | 47.8 |  | 3.5 |  | -- |  | 51.3 |  | 0.2 |  | 51.5
2013 |  | 11 | 45.1 |  | 5.8 |  | -- |  | 50.9 |  | 5.4 |  | 56.3
2014 |  | -- | -- |  | 9.4 |  | -- |  | 9.4 |  | 1.2 |  | 10.6
2015 |  | -- | -- |  | 6.2 |  | -- |  | 6.2 |  | 3.3 |  | 9.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.7 |  | 0.7
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.2 |  | 0.2
Subtotal |  | 16 | 92.9 |  | 24.9 |  | -- |  | 117.8 |  | 11 |  | 128.8

## Table 18
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | BY 2012 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | 5 | 46.5 |  | 3.4 |  | -- |  | 49.9 |  | 0.2 |  | 50.1
2013 |  | 11 | 43 |  | 5.5 |  | -- |  | 48.5 |  | 5.2 |  | 53.7
2014 |  | -- | -- |  | 8.8 |  | -- |  | 8.8 |  | 1.2 |  | 10
2015 |  | -- | -- |  | 5.7 |  | -- |  | 5.7 |  | 3.1 |  | 8.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.6 |  | 0.6
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.2 |  | 0.2
Subtotal |  | 16 | 89.5 |  | 23.4 |  | -- |  | 112.9 |  | 10.5 |  | 123.4

## Table 19
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2007-02-22 | 2011-01-14
Approved Quantity | 2 | 5
Reference | Milestone B ADM | Milestone C Acquisition Strategy Panel ADM
Start Year | 2012 | 2012
End Year | 2012 | 2012
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the need to achieve cost efficiencies within the small B-2 fleet and to deliver this capability in a timely manner.

## Table 20
Foreign Military Sales
None
Nuclear Costs
None

## Table 21
Unit Cost
Unit Cost Report
Item |  | BY 2012 $M | BY 2012 $M |  | % Change
|  | Current UCR Baseline (Sep 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 579.2 |  |  | 553.9
Quantity | 20 |  |  | 20
Unit Cost | 28.96 |  |  | 27.695 |  | -4.37
Average Procurement Unit Cost
Cost | 129 |  |  | 123.4
Quantity | 16 |  |  | 16
Unit Cost | 8.062 |  |  | 7.712 |  | -4.34
Item |  | BY 2012 $M | BY 2012 $M |  | % Change
|  | Original UCR Baseline (May 2007 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 718.4 |  |  | 553.9
Quantity | 21 |  |  | 20
Unit Cost | 34.21 |  |  | 27.695 |  | -19.04
Average Procurement Unit Cost
Cost | 125 |  |  | 123.4
Quantity | 17 |  |  | 16
Unit Cost | 7.353 |  |  | 7.712 |  | 4.88

## Table 22
Unit Cost History
Item | [7 empty] | Date |  |  |  | BY 2012 $M | [6 empty] | TY $M
[12 empty] | PAUC |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | May 2007 | [6 empty] | 34.21 |  |  |  | 7.353 |  |  |  | 33.624 |  |  |  | 7.747
APB as of January 2006 |  |  |  |  | N/A | [6 empty] | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Revised Original APB |  |  |  |  | N/A | [6 empty] | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | May 2007 | [6 empty] | 34.21 |  |  |  | 7.353 |  |  |  | 33.624 |  |  |  | 7.747
Current APB |  |  |  |  | Sep 2012 | [6 empty] | 28.96 |  |  |  | 8.062 |  |  |  | 28.335 |  |  |  | 8.45
Prior Annual SAR |  |  |  |  | Dec 2014 | [6 empty] | 27.725 |  |  |  | 7.762 |  |  |  | 27.075 |  |  |  | 8.119
Current Estimate |  |  |  |  | Dec 2015 | [6 empty] | 27.695 |  |  |  | 7.712 |  |  |  | 27.02 |  |  |  | 8.05
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [20 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth |  | Spt |  |  | Total
33.624 -0.350 1.381 0.375 0.000 -6.075 0.000 -0.620 -5.289 28.335
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [18 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng | Est |  | Oth | Spt |  |  | Total
28.335 -0.010 0.000 0.000 0.000 -1.395 0.000 0.090 -1.315 27.020

## Table 23
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [12 empty] | APUC Production Estimate
| Econ | Qty |  | Sch |  | Eng |  | Est | Oth | Spt |  |  | Total
7.747 -0.150 0.109 0.469 0.000 1.050 0.000 -0.775 0.703 8.450
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [12 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  |  | Est | Oth | Spt |  | Total
8.450 -0.019 0.000 0.000 0.000 -0.494 0.000 0.112 -0.401 8.050
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  |  | Current Estimate
Milestone I |  |  | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Milestone B |  |  | N/A |  |  |  | Feb 2007 |  |  |  | May 2007 |  |  |  | May 2007
Milestone C |  |  | N/A |  |  |  | Jul 2011 |  |  |  | Feb 2012 |  |  |  | Feb 2012
IOC |  |  | N/A |  |  |  | Mar 2014 |  |  |  | Mar 2015 |  |  |  | Dec 2014
Total Cost (TY $M) |  |  | N/A |  |  |  | 706.1 |  |  |  | 566.7 |  |  |  | 540.4
Total Quantity |  |  | N/A |  |  |  | 21 |  |  |  | 20 |  |  |  | 20
PAUC |  |  | N/A |  |  |  | 33.624 |  |  |  | 28.335 |  |  |  | 27.02
Required Assets Available is used in place of IOC.

## Table 24
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 431.5 | 135.2 | -- | 566.7
Previous Changes
Economic | 0.3 | 0.1 | -- | 0.4
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -20.2 | -7.5 | -- | -27.7
Other | -- | -- | -- | --
Support | -- | 2.1 | -- | 2.1
Subtotal | -19.9 | -5.3 | -- | -25.2
Current Changes
Economic | -0.2 | -0.4 | -- | -0.6
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 0.2 | -0.4 | -- | -0.2
Other | -- | -- | -- | --
Support | -- | -0.3 | -- | -0.3
Subtotal | -- | -1.1 | -- | -1.1
Adjustments | -- | -- | -- | --
Total Changes | -19.9 | -6.4 | -- | -26.3
CE - Cost Variance | 411.6 | 128.8 | -- | 540.4
CE - Cost & Funding | 411.6 | 128.8 | -- | 540.4

## Table 25
Summary BY 2012 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 450.2 | 129 | -- | 579.2
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -19.9 | -6.9 | -- | -26.8
Other | -- | -- | -- | --
Support | -- | 2.1 | -- | 2.1
Subtotal | -19.9 | -4.8 | -- | -24.7
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 0.2 | -0.4 | -- | -0.2
Other | -- | -- | -- | --
Support | -- | -0.4 | -- | -0.4
Subtotal | 0.2 | -0.8 | -- | -0.6
Adjustments | -- | -- | -- | --
Total Changes | -19.7 | -5.6 | -- | -25.3
CE - Cost Variance | 430.5 | 123.4 | -- | 553.9
CE - Cost & Funding | 430.5 | 123.4 | -- | 553.9
Previous Estimate: December 2014

## Table 26
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.2
Adjustment for current and prior escalation. (Estimating) | 0.2 | 0.2
RDT&E Subtotal | 0.2 | 0
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -0.4
Revised estimate due to fact-of-life changes and reallocation to other B-2 efforts in FY 2013 and FY 2014. (Estimating)
-0.9 -0.8
Adjustment for current and prior escalation. (Estimating) +0.5 +0.4
Adjustment for current and prior escalation. (Support) -0.1 0.0
Decrease in Initial Spares due to removal of program funding that is not required for contracted deliveries. (Support)
-0.3 -0.3
Procurement Subtotal -0.8 -1.1

## Table 27
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: EHF Inc 1 SatCom Production
Contractor: Northrop Grumman Corp. Contractor Location: Palmdale, CA 93550 Contract Number: F33657-99-D-0028/62 Contract Type: Firm Fixed Price (FFP)
Award Date: September 27, 2012
Definitization Date: September 27, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
108.1 N/A 16 108.1 N/A 16 108.1 108.1
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
Contract awarded September 27, 2012, for LRIP, with three options, one for FRP, and two for installs.

## Table 28
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 4 | 4 | 4 | 100%
Production | 14 | 14 | 16 | 87.5%
Total Program Quantity Delivered | 18 | 18 | 20 | 90%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
540.4
512.4
94.82%
13
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
12
92.31%
540.2
99.96%
The above data is current as of February 09, 2016.

## Table 29
Operating and Support Cost
Cost Estimate Details
Date of Estimate: August 22, 2012
Source of Estimate: SCP
Quantity to Sustain: 20
Unit of Measure: Aircraft
Service Life per Unit: 35.00 Years
Fiscal Years in Service: FY 2013 - FY 2048
Sustainment Strategy
The maintenance concept for the B-2 EHF Inc 1 is two level (organizational and depot). Organizational maintenance will consist of Air Force maintenance personnel removing and replacing failed items, performing preventative maintenance, and conducting fault isolation actions. All repairs of the Line Replaceable Units (LRUs) removed from the B-2 aircraft will be accomplished at the depot level. The source of repair for depot maintenance for Increment 1 was initially projected to be Warner Robins Air Logistics Complex (WR-ALC) for the two LRUs, the Integrated Processing Unit and the Disk Drive Unit. An Office Under Secretary Defense/Acquisition, Technology & Logistics action item out of July 2011 Defense Acquisition Executive Summary briefing directed reassessment of the organic depot strategy based on LRU reliability projections. In response, a Workload Shift package (from organic repair at WR-ALC to Contractor Depot Repair) was submitted and approved. The System Development and Demonstration (SDD) contract requires delivery of repair data and associated training. The planning for establishing this repair capability will be accomplished during the SDD contract. There are no increased O&S costs associated with B-2 EHF Inc 1, because improved reliability and maintainability provided by this modification are projected to reduce O&S costs incurred for B-2 legacy computers. The B-2 EHF Inc 1 modification is replacing two legacy LRUs with two high reliability LRUs, per Mean Time Between Failure estimates, in each of the 20 aircraft.
Antecedent Information
No Antecedent
Annual O&S Costs BY2012 $K
Cost Element | B-2 EHF Inc 1 Average Annual Cost Per Aircraft | None (Antecedent) N/A
Unit-Level Manpower | 22.851 | 0
Unit Operations | 0.235 | 0
Maintenance | 46.634 | 0
Sustaining Support | 55.031 | 0
Continuing System Improvements | 17.873 | 0
Indirect Support | 7.983 | 0
Other | 0 | 0
Total | 150.607 | --

## Table 30
Item | Total O&S Cost $M
| B-2 EHF Inc 1 | [5 empty] | None (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 105.4 |  | 115.9 |  |  | 105.4 | N/A
Then Year | 151 |  | N/A |  |  | 151 | 0
Equation to Translate Annual Cost to Total Cost
Total O&S Cost/number of aircraft/years of service = Unitized O&S Cost. $105.4M/20/35=$0.15M
O&S Cost Variance
Category |  | BY 2012 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
105.4
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 105.4
Disposal Estimate Details
Date of Estimate: Source of Estimate:
Disposal/Demilitarization Total Cost (BY 2012 $M):
Disposal costs for this modification are included in the B-2 platform.