## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-327
C-5 Reliability Enhancement and Re-engining Program (C-5 RERP)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 13
Cost and Funding 14
Low Rate Initial Production 23
Foreign Military Sales 24
Nuclear Costs 24
Unit Cost 25
Cost Variance 28
Contracts 31
Deliveries and Expenditures 34
Operating and Support Cost 35

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
C-5 Reliability Enhancement and Re-engining Program (C-5 RERP)
DoD Component
Air Force
Responsible Office
Mr. Brian Townsend C-5 Division Mobility Directorate
2275 D Street, Bldg 16, Room 127
Wright Patterson Air Force Base, OH 45433-7222
brian.townsend@us.af.mil
Phone: | 937-656-9568
Fax: | 937-656-7026
DSN Phone: | 986-9568
DSN Fax: | 986-7026
Date Assigned: | October 2, 2012
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated June 24, 2008
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 7, 2010

## Table 6
Mission and Description
The C-5 Reliability Enhancement and Re-engining Program (C-5 RERP) is the second phase of a two-phase modernization program for the C-5. The Avionics Modernization Program was Phase I and is the baseline for C-5 RERP. Following completion of Phase II, C-5 RERP, the aircraft is designated a C-5M. C-5 RERP is a comprehensive modernization effort that will improve aircraft reliability, maintainability, and availability. C-5 RERP will enable the C-5M to achieve wartime mission requirements by increasing fleet availability (mission capable rates and departure reliability), reducing total ownership costs, and improving aircraft performance. This effort centers on replacing the current TF39 engine with a more reliable, commercial off-the-shelf General Electric (GE) CF6-80C2 (F138-GE-100 military designation) turbofan engine with increased takeoff thrust, stage-3 noise compliance, and Federal Aviation Regulation pollution compliance. In addition to new engines/pylons, C-5 RERP will provide upgrades to wing attachment fittings; new thrust reversers and auxiliary power units; upgrades to the electrical, hydraulic, fuel, fire suppression, landing gear, and pressurization/air conditioning systems; and airframe structural modifications. These aircraft improvements increase payload capability and access to communication, navigation, surveillance/air traffic management airspace. C-5 RERP also decreases aircraft time-to-climb, increases engine
-out climb gradient for takeoff, improves transportation system throughput, and decreases engine removals.
The procurement tempo to deliver a C-5 RERP aircraft is a three-year process. The first year is advance procurement of material with longer than 12 months duration to buy and deliver, the second year involves material procurement and fabrication, while the third and final year is installation on the aircraft.

## Table 7
Executive Summary
Lockheed Martin Aeronautics (LMA) delivered nine C-5M aircraft to the Air Force in 2015. The total complement of aircraft for Dover Air Force Base (AFB) was completed in 2014. Travis AFB received 9 aircraft, bringing their complement of aircraft to 14 as of December 31, 2015. The 9 deliveries in CY 2015 brought the total number of C-5Ms delivered to 32 aircraft. In addition, LMA delivered 2 aircraft in CY 2016 bringing the total C-5M fleet to 34 aircraft as of February 22, 2016.
Aircraft 68-0213, the first C-5C model to undergo the RERP modification, was delivered on April 24, 2015 and was ferried to Stewart Air National Guard Base (ANGB) for refurbishment before final delivery to Travis AFB.
A “handshake” agreement was reached during negotiations for the FY 2015 Lot 7 Production (Install) contract on the first day of “face-to-face” negotiations on July 6, 2015. The contract was awarded on August 13, 2015 and is the final lot buy for RERP.
Since the introduction of a government advisory team and an onsight representative in CY 2013, an improved LMA production feedback process and streamlined LMA/Defense Contract Management Agency flight operations process have stablized the RERP modification line. Significant savings have been achieved in several modification phases: aircraft induction timelines have been reduced 32 percent; aircraft modification timelines have been reduced 15 percent; quality assurance steps have been reduced 16 percent and functional testing has been reduced 8 percent. Together these reductions have reduced the delivery time from 678 calendar days in CY 2013 to 479 calendar days in CY 2015, a reduction of 199 calendar days (29 percent). LMA delivered nine of nine aircraft scheduled for delivery in CY 2015 and two of eight aircraft planned for delivery in CY 2016. Thirty-four of fifty-two aircraft have been modified to the C-5M configuration as
of February 22, 2016.
A C-5 Safety Investigation Board (SIB) convened January 5, 2015 in response to multiple gear strikes causing a Class B mishap during acceptance testing at LMA. The number one main landing gear malfunctioned twice on two separate acceptance test flights while conducting hydraulic pressure tests during landing gear retraction. The SIB completed its investigation January 29, 2015 and the formal outbrief to the Air Force Life Cycle Management Center commander was held February 20, 2015. All recommendations were implemented. The aircraft completed acceptance testing March 31, 2015 and was delivered on April 6, 2015. The aircraft was ferried to Stewart ANGB for refurbishment on April 8, 2015 prior to delivery to Travis AFB.
At Air Mobility Command's request, the C-5 team successfully expedited delivery and fielding of updated C-5 software (Operational Flight Program version 3.5.2) and associated logistics support to include training, technical orders and the Time Compliance Technical Order (TCTO). The new software fixed a number of nuisance errors and also eliminated a safety risk during takeoff and landing. The contract was awarded January 29, 2015; aircrew training was completed March 31, 2015; and the TCTO was completed on all fielded aircraft (total of 30) in November 2015. The first Lot 6 production aircraft to be delivered with the new software occurred October 21, 2015.
On April 2, 2015, C-5M 85-0010, from Travis AFB, set 46 world records in the time to climb category with a 264,000 pound payload. Gross takeoff weight was 735,222 pounds. The records have been validated and certified by the National Aeronautics Association and the Federation Aeronautique Internationale. The C-5M Super Galaxy is now the top aviation record holder with a total of 89 world records; beating the AN-225 (73 records) and the B-1B (83 records).
The C-5 RERP CPD requires the C-5M to achieve a wartime Mission Capability Rate (MCR) of 75 percent. Since the start of production in October 2010, the C-5M has demonstrated that capability during several events. The latest event was three C-5Ms supporting real-world movement of helicopters and other equipment from Rota Air Base Portugal to Afganistan from December 6, 2015 to January 2, 2016. During this period, the aircraft flew 41 sorties and achieved an impressive 90.5 percent MCR.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Program Initiation | Feb 2000 | Feb 2000 | Feb 2000 | Feb 2000
Milestone B | Nov 2001 | Nov 2001 | Nov 2001 | Nov 2001
Contract Award | Dec 2001 | Dec 2001 | Dec 2001 | Dec 2001
Hardware/Software CDR | Apr 2004 | Apr 2004 | Apr 2004 | Apr 2004
First Flight | Jun 2006 | Jun 2006 | Jun 2006 | Jun 2006
Start Combined QT&E/QOT&E | Jun 2006 | Jun 2006 | Jun 2006 | Jun 2006
Milestone C | Mar 2008 | Mar 2008 | Sep 2008 | Mar 2008
Complete Dedicated QOT&E (AFOTEC Report complete) | Apr 2010 | Apr 2010 | Oct 2010 | Mar 2010
FRP For B Models | Dec 2010 | Dec 2010 | Dec 2011 | Oct 2010
IOC | Jun 2013 | Jun 2013 | Jun 2014 | Feb 2014
Change Explanations

## Table 10
Acronyms and Abbreviations
AFOTEC - Air Force Operational Test and Evaluation Center CDR - Critical Design Review
QOT&E - Qualification Operational Test and Evaluation QT&E - Qualification Test and Evaluation

## Table 11
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Time To Climb/Initial Level Off
837,000 lbs take-off gross weight; RCR 23; climb condition: 77 deg F; SL to 31,000 ft in less than 25 min | 837,000 lbs take-off gross weight; RCR 23; climb condition: 77 deg F; SL to 31,000 ft in less than 25 min | 769,000 lbs take-off gross weight; RCR 23; climb condition: 77 deg F; SL to 31,000 ft in less than 25 min | 837,000 lbs take-off gross weight; RCR 23; climb condition: 77 deg F; SL to 31,000 ft in less than 25 min | Will meet or exceed Current APB Threshold. 769,000 lbs take-off gross weight; RCR 23; climb condition: 77 deg F; SL to 31,000 ft in less than 25 min
Aircraft Take-off Climb Gradient
One engine out climb gradient >=3.3% beginning at departure end of runway / 837,000 lbs take-off weight / hot day (103 deg F) / 10,000 ft runway / SL / RCR 23 | One engine out climb gradient >=3.3% beginning at departure end of runway / 837,000 lbs take-off weight / hot day (103 deg F) / 10,000 ft runway / SL / RCR 23 | One engine out climb gradient >=2.5% beginning at departure end of runway / 837,000 lbs take-off weight / hot day (103 deg F) / 10,000 ft runway / SL / RCR 23 | One engine out climb gradient >= 3.3% beginning at departure end of runway/ 837,000 lbs takeoff weight; hot day (103 deg F)/ 10,000 ft runway/ SL/ RCR 23 | Will meet or exceed Current APB Threshold. One engine out climb gradient >=2.5% beginning at departure end of runway / 837,000 lbs take-off weight / hot day (103 deg F) / 10,000 ft runway / SL / RCR 23
Mission Capable Rate (MCR)
Wartime >= 82% and Peacetime >= 75% | Wartime >= 82% and Peacetime >= 75% | Wartime >= 75% | SDD (81.6%)/ QOT&E (66% & 76%)/ CONOPS I Surge (78%) & CONOPS II Surge (89%)/ AMC/ AFTRANS Surge (90%); Wartime >= 75% & Peace time >= 82% | Will meet or exceed Current APB Threshold. Wartime >= 75%
Noise Compliance
Certifiable under FAR Part 36 Stage 4 noise standards | Certifiable under FAR Part 36 Stage 4 noise standards | Certifiable under FAR part 36 Stage 3 noise standards | Certifiable under FAR Part 36 Stage 4 noise standards | Will meet or exceed Current APB Threshold. Certifiable under FAR part 36 Stage 3 noise standards
Emission Compliance
Certifiable under FAR Part 34 emission | Certifiable under FAR Part 34 emission | Certifiable under FAR Part 34 emission | Certifiable under FAR Part 34 emission requirements | Will meet or exceed Current APB Threshold. Certifiable

## Table 12
requirements | requirements | requirements | under FAR Part 34 emission requirements
Requirements Reference
Capability Production Document (CPD) Change 1 dated December 1, 2009
Change Explanations
None
Notes
Demonstrated performance reflects the outcome of Flight Test completed during SDD on August 18, 2008; QOT&E completed on March 8, 2010; and Post-QOT&E Real-World Surge Exercises.
Acronyms and Abbreviations
AFTRANS - Air Forces Transportation AMC - Air Mobility Command CONOPS - Concept of Operations deg - degrees
F - Fahrenheit
FAR - Federal Aviation Regulation ft - feet
lbs - pounds min - minutes
QOT&E - Qualification Operational Test and Evaluation RCR - Runway Condition Reading
SDD - System Design and Development SL - Sea Level

## Table 13
Track to Budget
RDT&E
Appn |  |  | BA | PE
Air Force 3600 07 0401119F
Project | Name
674835 C-5 Airlift Squadrons/C-5 Reliability Enhancement & Reengining Program (RERP)
(Sunk)
Procurement
Appn |  |  | BA | PE
Air Force |  | 3010 07 |  | 0401119F
|  | Line Item |  | Name
|  | 75 |  | C-5 Reliability Enhancement and Reengining Program (RERP) | (Shared) | (Sunk)
Air Force |  | 3010 06 |  | 0401119F
|  | Line Item |  | Name
|  | 999 |  | Initial spares and repair parts | (Shared) | (Sunk)
Air Force |  | 3010 05 |  | 0401119F
|  | Line Item |  | Name
|  | C00500 |  | C-5 Reliability Enhancement and Reengining Program (RERP) |  | (Sunk)
|  | C005M0 |  | C-5M |  | (Sunk)
MILCON
Appn |  |  | BA | PE
Air Force 3300 01 0401896F
Project | Name
103003 C-5 Reliability Enhancement
and Reengining Program (RERP)
Notes: Training facility at Dover Air Force Base
(Sunk)

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2008 $M | [6 empty] | BY 2008 $M |  | TY $M
| SAR Baseline Production Estimate |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 1722.9 |  |  | 1734.3 | 1907.7 |  |  | 1691.4 |  | 1643.5 |  |  | 1645 |  | 1601.2
Procurement |  | 5415.9 |  |  | 5396.3 | 5935.9 |  |  | 5001.6 |  | 6042.1 |  |  | 5860.4 |  | 5460.1
Flyaway |  | -- |  |  | -- | -- |  |  | 4170.6 |  | -- |  |  | -- |  | 4560.3
Recurring |  | -- |  |  | -- | -- |  |  | 4170.6 |  | -- |  |  | -- |  | 4560.3
Non Recurring |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support |  | -- |  |  | -- | -- |  |  | 831 |  | -- |  |  | -- |  | 899.8
Other Support |  | -- |  |  | -- | -- |  |  | 291.1 |  | -- |  |  | -- |  | 316.4
Initial Spares |  | -- |  |  | -- | -- |  |  | 539.9 |  | -- |  |  | -- |  | 583.4
MILCON |  | 7.8 |  |  | 5.1 | 5.6 |  |  | 5 |  | 8.5 |  |  | 5.3 |  | 5.3
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 7146.6 |  |  | 7135.7 | N/A |  |  | 6698 |  | 7694.1 |  |  | 7510.7 |  | 7066.6
Confidence Level
Confidence Level of cost estimate for current APB: 50%
Confidence Level for current Acquisition Program Baseline (APB) cost is 50%. The Independent Cost Estimate (ICE) to support C-5 RERP Full Rate Production decision, like all life-cycle cost estimates previously performed by the Cost Assessment and Program Evaluation (CAPE), is built upon a product-oriented work breakdown structure, based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for Major Defense Acquisition Program (MDAPs) programs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.
Total Quantity
Quantity |  |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  |  | 3 |  |  |  | 3 |  |  |  |  | 3
Procurement |  |  | 49 |  |  |  | 49 |  |  |  |  | 49
Total |  |  | 52 |  |  |  | 52 |  |  |  |  | 52

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 1601.2 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1601.2
Procurement | 5460.1 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 5460.1
MILCON | 5.3 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 5.3
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 7066.6 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 7066.6
PB 2016 Total | 7090.6 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 7090.6
Delta | -24 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | -24
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 3 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 3
Production | 0 |  | 49 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 49
PB 2017 Total | 3 |  | 49 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 52
PB 2016 Total | 3 |  | 49 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 52
Delta | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.3
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.6
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83.7
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 191.4
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 260.2
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 278.2
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 222.9
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 137.6
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 161.6
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 80.9
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.4
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.4
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12
Subtotal |  | 3 | -- |  | -- |  | -- |  | -- |  | -- |  | 1601.2

## Table 17
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 45.6
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 95.4
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 215.4
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 285.5
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 297.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 231.4
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 139.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 160.3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 79.2
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 60.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 51.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.2
Subtotal |  | 3 | -- |  | -- |  | -- |  | -- |  | -- |  | 1691.4

## Table 18
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | 52.5 |  | -- |  | -- |  | 52.5 |  | 9 |  | 61.5
2008 |  | 1 | 132.6 |  | -- |  | -- |  | 132.6 |  | 61.3 |  | 193.9
2009 |  | 3 | 289.9 |  | -- |  | -- |  | 289.9 |  | 46.7 |  | 336.6
2010 |  | 5 | 482.9 |  | -- |  | -- |  | 482.9 |  | 72.3 |  | 555.2
2011 |  | 7 | 636.5 |  | -- |  | -- |  | 636.5 |  | 187.1 |  | 823.6
2012 |  | 11 | 823.3 |  | -- |  | -- |  | 823.3 |  | 329.1 |  | 1152.4
2013 |  | 11 | 1002.7 |  | -- |  | -- |  | 1002.7 |  | 120.1 |  | 1122.8
2014 |  | 11 | 853.2 |  | -- |  | -- |  | 853.2 |  | 43.5 |  | 896.7
2015 |  | -- | 286.7 |  | -- |  | -- |  | 286.7 |  | 30.7 |  | 317.4
Subtotal |  | 49 | 4560.3 |  | -- |  | -- |  | 4560.3 |  | 899.8 |  | 5460.1

## Table 19
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | 52.2 |  | -- |  | -- |  | 52.2 |  | 9 |  | 61.2
2008 |  | 1 | 129.9 |  | -- |  | -- |  | 129.9 |  | 60 |  | 189.9
2009 |  | 3 | 279.3 |  | -- |  | -- |  | 279.3 |  | 45 |  | 324.3
2010 |  | 5 | 456.3 |  | -- |  | -- |  | 456.3 |  | 68.3 |  | 524.6
2011 |  | 7 | 592.1 |  | -- |  | -- |  | 592.1 |  | 174.1 |  | 766.2
2012 |  | 11 | 754.4 |  | -- |  | -- |  | 754.4 |  | 301.5 |  | 1055.9
2013 |  | 11 | 900.1 |  | -- |  | -- |  | 900.1 |  | 107.8 |  | 1007.9
2014 |  | 11 | 755.7 |  | -- |  | -- |  | 755.7 |  | 38.5 |  | 794.2
2015 |  | -- | 250.6 |  | -- |  | -- |  | 250.6 |  | 26.8 |  | 277.4
Subtotal |  | 49 | 4170.6 |  | -- |  | -- |  | 4170.6 |  | 831 |  | 5001.6

## Table 20
Cost Quantity Information 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2008 $M
2007 | -- | --
2008 | 1 | 176.2
2009 | 3 | 294.5
2010 | 5 | 468.7
2011 | 7 | 639.4
2012 | 11 | 914.8
2013 | 11 | 808.1
2014 | 11 | 868.9
2015 | -- | --
Subtotal | 49 | 4170.6

## Table 21
Annual Funding 3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | TY $M
Total Program
2010 5.3
Subtotal 5.3

## Table 22
Annual Funding 3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | BY 2008 $M
Total Program
2010 5.0
Subtotal 5.0

## Table 23
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2001-11-05 | 2008-03-25
Approved Quantity | 12 | 16
Reference | Milestone B ADM | Milestone C ADM
Start Year | 2006 | 2007
End Year | 2010 | 2012
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the C-5 RERP Milestone C ADM approving an LRIP quantity of 16 systems as being necessary to maintain a steady ramp to FRP. The start year changed from the Initial LRIP Decision to the Current Total LRIP during the Nunn-McCurdy restructure.
The procurement tempo to deliver a C-5 RERP aircraft is a three-year process. The first year is advance procurement of material with longer than 12 months duration to buy and deliver. The second year involves material procurement and fabrication, while the third and final year is installation on the aircraft.

## Table 24
Foreign Military Sales
None
Nuclear Costs
None

## Table 25
Unit Cost
Unit Cost Report
Item |  | BY 2008 $M | BY 2008 $M |  | % Change
|  | Current UCR Baseline (Oct 2010 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 7135.7 |  |  | 6698
Quantity | 52 |  |  | 52
Unit Cost | 137.225 |  |  | 128.808 |  | -6.13
Average Procurement Unit Cost
Cost | 5396.3 |  |  | 5001.6
Quantity | 49 |  |  | 49
Unit Cost | 110.129 |  |  | 102.073 |  | -7.32
Item |  | BY 2008 $M | BY 2008 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Jun 2008 APB)
Program Acquisition Unit Cost
Cost | 7146.6 |  |  | 6698
Quantity | 52 |  |  | 52
Unit Cost | 137.435 |  |  | 128.808 |  | -6.28
Average Procurement Unit Cost
Cost | 5415.9 |  |  | 5001.6
Quantity | 49 |  |  | 49
Unit Cost | 110.529 |  |  | 102.073 |  | -7.65

## Table 26
Unit Cost History
Item | [7 empty] | Date |  |  |  | BY 2008 $M | [8 empty] | TY $M
[12 empty] | PAUC |  |  |  | APUC |  |  |  |  | PAUC |  |  |  |  | APUC
Original APB |  |  |  |  | Nov 2001 | [6 empty] | 81.955 | [5 empty] | 71.01 |  |  |  |  | 88.047 |  |  |  | 78.293
APB as of January 2006 |  |  |  |  | Feb 2005 | [6 empty] | 92.829 | [5 empty] | 81.564 |  |  |  |  | 98.252 |  |  |  | 88.355
Revised Original APB |  |  |  |  | Jun 2008 | [6 empty] | 137.435 | [5 empty] | 110.529 |  |  |  |  | 147.963 |  |  |  | 123.308
Prior APB |  |  |  |  | Jun 2008 | [6 empty] | 137.435 | [5 empty] | 110.529 |  |  |  |  | 147.963 |  |  |  | 123.308
Current APB |  |  |  |  | Oct 2010 | [6 empty] | 137.225 | [5 empty] | 110.129 |  |  |  |  | 144.437 |  |  |  | 119.6
Prior Annual SAR |  |  |  |  | Dec 2014 | [6 empty] | 128.998 | [5 empty] | 102.28 |  |  |  |  | 136.358 |  |  |  | 111.92
Current Estimate |  |  |  |  | Dec 2015 | [6 empty] | 128.808 | [5 empty] | 102.073 |  |  |  |  | 135.896 |  |  |  | 111.431
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [23 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  |  | Eng |  |  | Est |  | Oth |  |  |  | Spt |  |  | Total
88.047 0.635 55.435 10.863 -1.056 -6.673 0.000 0.712 59.916 147.963
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [21 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  | Eng |  | Est |  |  | Oth |  |  | Spt |  |  | Total
147.963 -2.469 0.000 0.000 0.000 -6.554 0.000 -3.044 -12.067 135.896

## Table 27
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [14 empty] | APUC Production Estimate
| Econ | Qty |  |  |  | Sch |  | Eng |  | Est | Oth | Spt |  |  | Total
78.293 0.640 32.062 7.029 0.000 -4.756 0.000 10.040 45.015 123.308
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [14 empty] | APUC Current Estimate
| Econ |  | Qty |  | Sch |  | Eng |  |  | Est | Oth | Spt |  | Total
123.308 -2.420 0.000 0.000 0.000 -6.227 0.000 -3.231 -11.878 111.431
SAR Baseline History
Item |  |  |  | SAR Planning Estimate |  |  |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  |  | Current Estimate
Milestone I |  |  |  | N/A |  |  |  |  | Feb 2000 |  |  |  | Feb 2000 |  |  |  | Feb 2000
Milestone B |  |  |  | N/A |  |  |  |  | Nov 2001 |  |  |  | Nov 2001 |  |  |  | Nov 2001
Milestone C |  |  |  | N/A |  |  |  |  | Dec 2006 |  |  |  | Mar 2008 |  |  |  | Mar 2008
IOC |  |  |  | N/A |  |  |  |  | Mar 2010 |  |  |  | Jun 2013 |  |  |  | Feb 2014
Total Cost (TY $M) |  |  |  | N/A |  |  |  |  | 11093.9 |  |  |  | 7694.1 |  |  |  | 7066.6
Total Quantity |  |  |  | N/A |  |  |  |  | 126 |  |  |  | 52 |  |  |  | 52
PAUC |  |  |  | N/A |  |  |  |  | 88.047 |  |  |  | 147.963 |  |  |  | 135.896

## Table 28
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 1643.5 | 6042.1 | 8.5 | 7694.1
Previous Changes
Economic | -9.4 | -105.7 | -0.2 | -115.3
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -32.9 | -316.1 | -3 | -352
Other | -- | -- | -- | --
Support | -- | -136.2 | -- | -136.2
Subtotal | -42.3 | -558 | -3.2 | -603.5
Current Changes
Economic | -0.2 | -12.9 | -- | -13.1
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 0.2 | 11 | -- | 11.2
Other | -- | -- | -- | --
Support | -- | -22.1 | -- | -22.1
Subtotal | -- | -24 | -- | -24
Total Changes | -42.3 | -582 | -3.2 | -627.5
CE - Cost Variance | 1601.2 | 5460.1 | 5.3 | 7066.6
CE - Cost & Funding | 1601.2 | 5460.1 | 5.3 | 7066.6

## Table 29
Summary BY 2008 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 1722.9 | 5415.9 | 7.8 | 7146.6
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -31.7 | -280.9 | -2.8 | -315.4
Other | -- | -- | -- | --
Support | -- | -123.3 | -- | -123.3
Subtotal | -31.7 | -404.2 | -2.8 | -438.7
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 0.2 | 9.8 | -- | 10
Other | -- | -- | -- | --
Support | -- | -19.9 | -- | -19.9
Subtotal | 0.2 | -10.1 | -- | -9.9
Total Changes | -31.5 | -414.3 | -2.8 | -448.6
CE - Cost Variance | 1691.4 | 5001.6 | 5 | 6698
CE - Cost & Funding | 1691.4 | 5001.6 | 5 | 6698
Previous Estimate: December 2014

## Table 30
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.2
Adjustment for current and prior escalation. (Estimating) | 0.2 | 0.2
RDT&E Subtotal | 0.2 | 0
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -12.9
Revised estimate to reflect actuals. (Estimating) | -0.5 | -0.7
Adjustment for current and prior escalation. (Estimating) | 10.3 | 11.7
Adjustment for current and prior escalation. (Support) | 1.2 | 1.2
Decrease in Other Support related to Depot Activation. (Support) | -1.5 | -1.6
Decrease in Initial Spares to reflect actuals and refined estimating assumptions. (Support) | -19.6 | -21.7
Procurement Subtotal | -10.1 | -24

## Table 31
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: C-5 RERP FRP Lot 5
Contractor: Lockheed Martin
Contractor Location: 86 South Cobb Drive
Marietta, GA 39963-0290
Contract Number: FA8625-07-C-6471/5
Contract Type: Fixed Price with Economic Price Adjustment (FPEPA)
Award Date: October 20, 2010
Definitization Date: October 20, 2010
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
162.9 N/A 11 1099.1 N/A 11 1099.1 1099.1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract modification adding the following to Lot 5: Long lead, material/fabrication, installation, initial spares, readiness spares package, rapid repair and response, and support equipment.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPEPA) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because an EVM waiver was granted in an ADM, dated October 07, 2010, due to fixed price production contract.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 32
Contract Identification
Appropriation: Procurement
Contract Name: C-5 RERP FRP Lot 6
Contractor: Lockheed Martin
Contractor Location: 86 South Cobb Drive
Marietta, GA 39963-0290
Contract Number: FA8625-07-C-6471/6
Contract Type: Fixed Price with Economic Price Adjustment (FPEPA)
Award Date: October 21, 2011
Definitization Date: October 21, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
160.0 N/A 11 1014.6 N/A 11 1014.6 1014.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract modification adding the following to Lot 6: Long lead, material/fabrication, installation, initial spares, readiness spares package, rapid repair and response, and support equipment.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPEPA) contract.

## Table 33
Contract Identification
Appropriation: Procurement
Contract Name: C-5 RERP FRP Lot 7
Contractor: Lockheed Martin
Contractor Location: 86 Cobb Drive
Marietta, GA 39963-0290
Contract Number: FA8625-07-C-6471/7
Contract Type: Fixed Price with Economic Price Adjustment (FPEPA)
Award Date: October 19, 2012
Definitization Date: October 19, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
155.5 N/A 11 1088.0 N/A 11 1088.0 1088.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract modification adding the following to Lot 7: Long lead, material/fabrication, installation, and rapid repair and response.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPEPA) contract.

## Table 34
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 3 | 3 | 3 | 100%
Production | 30 | 31 | 49 | 63.27%
Total Program Quantity Delivered | 33 | 34 | 52 | 65.38%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
7066.6
5450.4
77.13%
16
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
16
100%
7066.6
100%
The above data is current as of February 09, 2016.
RERP 3010/3600 expenditures as of February 9, 2016.
Scheduled deliveries are based on the award of the Production Contract Schedule Re-Baseline modification, dated November 6, 2012.

## Table 35
Operating and Support Cost
Cost Estimate Details
Date of Estimate: Source of Estimate: Quantity to Sustain: Unit of Measure: Service Life per Unit:
Fiscal Years in Service:
O&S costs are not tracked separately for C-5 RERP. O&S costs are included in the overall operational costs for the existing C-5 fleet managed by the program office at Robins Air Force Base.
Sustainment Strategy
.
Antecedent Information
No Antecedent
Annual O&S Costs BY2008 $M
Cost Element |  | C-5 RERP N/A |  |  |  | N/A (Antecedent) N/A
Unit-Level Manpower |  | 0 |  |  |  | 0
Unit Operations |  | 0 |  |  |  | 0
Maintenance |  | 0 |  |  |  | 0
Sustaining Support |  | 0 |  |  |  | 0
Continuing System Improvements |  | 0 |  |  |  | 0
Indirect Support |  | 0 |  |  |  | 0
Other |  | 0 |  |  |  | 0
Total |  | -- |  |  |  | --
Item | Total O&S Cost $M
| C-5 RERP | [5 empty] | N/A (Antecedent)
| Current Production APB Objective/Threshold |  |  | Current Estimate
Base Year | N/A |  | N/A |  | N/A |  | N/A
Then Year | N/A |  | N/A |  | N/A |  | 0
O&S Cost Variance

## Table 36
Category | BY 2008 $M | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
0
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 0.0
Disposal Estimate Details
Date of Estimate: Source of Estimate:
Disposal/Demilitarization Total Cost (BY 2008 $M):