## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-121
Enhanced Polar System (EPS)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 13
Cost and Funding 14
Low Rate Initial Production 18
Foreign Military Sales 19
Nuclear Costs 19
Unit Cost 20
Cost Variance 23
Contracts 26
Deliveries and Expenditures 28
Operating and Support Cost 29

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Enhanced Polar System (EPS)
DoD Component
Air Force
Responsible Office
Mr. Robert Tarleton
MILSATCOM Systems Directorate 483 N. Aviation Blvd.
El Segundo, CA 90245
robert.tarleton@us.af.mil
Phone: | 310-653-9001
Fax: | 310-653-9636
DSN Phone: | 633-9001
DSN Fax: | 633-9636
Date Assigned: | February 10, 2014
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 30, 2014
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 30, 2014

## Table 6
Mission and Description
The Enhanced Polar System (EPS) provides continuous protected communication (low probability of interception and detection) over the north polar region using two communications payloads on classified host satellites in highly elliptical Molniya orbits.
EPS is composed of four segments: the eXtended Data Rate (XDR) Payload (integrated onto a classified host), the User Terminals (acquired separately by the users), the Gateway (a fixed installation), and the Control and Planning Segment (CAPS) (another fixed installation). The Payload segment provides protected Extremely High Frequency communications in the north polar region. The Terminal segment provides the communication link to the EPS users. The Gateway segment provides connectivity between the north polar users and the mid-latitude users via the Defense Information System
Network / Global Information Grid. CAPS acts as the Satellite Operations Center with command and control, mission and crypto planning, test and sustainment, training, ephemeris, and key distribution workload.

## Table 7
Executive Summary
The Air Force program manager is responsible for fielding three (Control and Planning Segment (CAPS), Payload Segment, and Gateway Segment) of the four EPS segments as well as an integrated EPS capability.
CAPS:
CAPS completed all software development and test activities for Increment 1 (of 2) in September 2015, verifying ~50% of the CAPS software requirements. All Increment 2 software development activities completed in September 2015. Increment 2 Software Item Qualification Test (SIQT) began in October 2015 and will continue through 2nd Quarter FY 2016. Upon completion of Increment 2 SIQT events, CAPS will proceed with factory segment test verification, followed by Site Acceptance Test (SAT) at Schriever Air Force Base, Colorado by 3rd Quarter CY 2016. In addition, the EPS program office fielded a Telemetry & Command - Terminal (T&C-T), as part of CAPS, in December 2015 at the Clear Air Force Station (AFS), Alaska Gateway site. This terminal transmits telemetry and command for CAPS-to-payload interactions.
Payload Segment:
Two payloads were acquired with a classified host per the EPS ADM dated December 8, 2007. Both flight payloads are developed, tested, declared acceptable, and shipped to the host facility. The first payload completed satellite integration and test and became operationally available in March 2015. The second payload was removed from storage in October 2014 to begin integration and test on the host platform.
Gateway Segment:
The Gateway Segment completed hardware installation at Clear AFS, Alaska, and Camp Roberts, California; Installation Qualification Test was successfully conducted for both sites in November 2015. During the test, the Gateway
team transmitted simulated two-way user traffic from the Gateway Terminal interface (polar users) to the Teleport interface (mid-latitude users) utilizing the Defense Information System Network fiber optics transport infrastructure. The T&C-T hardware was installed at Clear AFS, Alaska and its interface with the resident CAPS equipment successfully tested. The Gateway Segment and the T&C-T are now ready to support System Tests.
The Payload and Gateway segments are nearly complete and no significant acquisition decisions remain.
Terminal Segment:
The Navy Multiband Terminal is the only EPS-compatible terminal which is funded and fielded by the Navy. The Navy has successfully contacted the EPS payload from a shore test facility, ship test facility, and submarine test facility, as directed by the Naval Undersea Warfare Center in November 2015. The Time Division Multiple Access Interface Processor, which is the Navy internet protocol network baseband equipment, demonstrated that it is compatible and inter-operable with the EPS payload.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | Apr 2014 | Apr 2014 | Apr 2014 | Apr 2014
CDR | Aug 2014 | Aug 2014 | Feb 2015 | Jul 2014
DT&E Completion for Single String | May 2017 | May 2017 | Nov 2017 | May 2017
RAA | Jun 2018 | Jun 2018 | Jun 2019 | Jun 2018
Change Explanations
Notes
DT&E Completion for Single String will include one Hosted Payload, T&C-T, CAPS, and the Gateway system with the one NMT as defined by Section 12.0 of the EPS CDD dated September 15, 2011 in support of IOC.
RAA is the date two hosted payloads, T&C-T, CAPS, and the Gateway system with the three NMTs are available for operational use per Section 12.3 of the EPS CDD dated September 15, 2011, in support of FOC. The RAA date follows the completion of MOT&E including the required reporting following the test. The threshold date margin of one year is due to the uncertainty of availability of operational U.S. Naval assets in the north polar region to support MOT&E, and the availability of payload #2 by the host satellite.

## Table 10
Acronyms and Abbreviations
CAPS - Control and Planning Segment CDR - Critical Design Review
DT&E - Developmental Test and Evaluation IC2 - Interim Command and Control
MOT&E - Multiservice Operational Test and Evaluation NMT - Navy Multiband Terminal
RAA - Required Assets Available
T&C-T - Telemetry & Command - Terminal

## Table 11
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Coverage
Provide continuous 24- hour coverage anywhere from 65° North latitude to 90° North latitude and CONUS. | Provide continuous 24 -hour coverage anywhere from 65° North latitude to 90° North latitude and CONUS. | Provide continuous 24- hour coverage anywhere from 65° North latitude to 90° North latitude. | TBD | Provide continuous 24- hour coverage anywhere from 65° North latitude to 90° North latitude and CONUS.
Capacity
EPS shall have an 18 Mbps capacity to support the CCDR’s mission capabilities in the North Polar Region. | EPS shall have an 18 Mbps capacity to support the CCDR’s mission capabilities in the North Polar Region. | Provide the capacity to support the CCDR’s minimum mission capabilities in the North Polar Region. | TBD | EPS shall have an 18 Mbps capacity to support the CCDR’s mission capabilities in the North Polar Region.
Protection - AJ
Provide anti-jam protection against the medium probability far- term fixed and transportable jammers. | Provide anti-jam protection against the medium probability far -term fixed and transportable jammers. | (T=O) Provide anti-jam protection against the medium probability far- term fixed and transportable jammers. | TBD | Provide AJ protection against the medium probability far-term fixed and transportable jammers.
Protection - LPI/LPD
LPI/LPD - Satisfy CEVR require-ments. | LPI/LPD - Satisfy CEVR require-ments. | (T=O) LPI/LPD - Satisfy CEVR require- ments. | TBD | LPI/LPD - Satisfy CEVR requirements.
Operational Management - Users
Provide users a capability to plan, control, and reconfigure their assigned resources. | Provide users a capability to plan, control, and reconfigure their assigned resources. | (T=O) Provide users a capability to plan, control, and reconfigure their assigned resources. | TBD | Provide users a capability to plan, control, and reconfigure their assigned resources.
Operational Management - System
Plan, configure, monitor, manage and control the payload, network and terminal resources. | Plan, configure, monitor, manage and control the payload, network and terminal resources. | (T=O) Plan, configure, monitor, manage and control the payload, network and terminal resources. | TBD | Plan, configure, monitor, manage and control the payload, network and terminal resources.
Net Readiness
100 percent of | 100 percent of | 100 percent of | TBD | 100 percent of interfaces;

## Table 12
interfaces; services; | interfaces; services; | interfaces; services; |  | services; policy-
policy-enforcement | policy-enforcement | policy-enforcement |  | enforcement controls;
controls; and data | controls; and data | controls; and data |  | and data correctness,
correctness, availability | correctness, | correctness, |  | availability and
and processing | availability and | availability and |  | processing requirements
requirements in the | processing | processing |  | in the Joint integrated
Joint integrated | requirements in the | requirements |  | architecture.
architecture. | Joint integrated | designated as
| architecture. | enterprise-level or
critical in the Joint
integrated architecture.
Interconnectivity
The EPS system | The EPS system | (T=O) The EPS | TBD | The EPS system
Gateway(s) shall | Gateway(s) shall | system Gateway(s) |  | Gateway(s) shall
simultan-eously provide | simultan-eously | shall simultan-eously |  | simultaneously provide
continuous access to | provide continuous | provide continuous |  | continuous access to the
the rising and | access to the rising | access to the rising |  | rising and descending
descending EPS | and descending EPS | and descending EPS |  | EPS payloads during
payloads during | payloads during | payloads during |  | communications payload
communi-cations | communi-cations | communi-cations |  | availability and
payload availability and | payload availability and | payload availability and |  | simultaneous access to a
simultaneous access to | simultaneous access | simultaneous access |  | GIG point of presence.
a GIG point of | to a GIG point of | to a GIG point of
presence. | presence. | presence.
Requirements Reference
Capability Development Document (CDD) dated September 15, 2011
Change Explanations
None
Acronyms and Abbreviations
AJ - Anti-Jamming
CCDR - Combatant Commander
CEVR - Circular Equivalent Vulnerability Radius CONUS - Continental United States
EPS - Enhanced Polar System GIG - Global Information Grid
LPD - Low Probability of Detection LPI - Low Probability of Intercept Mbps - Megabits per second
O - Objective T - Threshold

## Table 13
Track to Budget
RDT&E
Appn | BA | PE
Air Force 3600 04 0603432F
Project Name
644052 Polar Satellite Communications (Sunk) Air Force 3600 05 0605432F
Project Name
657105 Polar Satellite Communications

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2014 $M | [5 empty] | BY 2014 $M |  | TY $M
| SAR Baseline Development Estimate |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E | 1389.1 |  |  | 1389.1 | 1528 |  |  | 1380.3 |  | 1338.5 |  |  | 1338.5 |  | 1334.2
Procurement | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Flyaway | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Recurring | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Non Recurring | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Other Support | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Initial Spares | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
MILCON | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 1389.1 |  |  | 1389.1 | N/A |  |  | 1380.3 |  | 1338.5 |  |  | 1338.5 |  | 1334.2
Current APB Cost Estimate Reference
Service Cost Position dated January 28, 2014
Confidence Level
Confidence Level of cost estimate for current APB: 59%
The Life-Cycle Cost Estimate confidence level of 59% Research, Development, Test, and Evaluation and Operations and Support reflects the expected value, or mean, of the cost estimate distribution. It takes into consideration relevant risks, including ordinary levels of external and unforeseen events, aiming to provide sufficient resources to execute the program under normal conditions encountering average levels of technical, schedule, and programmatic risk and external influence.
Total Quantity
Quantity |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  | 2 |  |  |  | 2 |  |  |  |  | 2
Procurement |  | 0 |  |  |  | 0 |  |  |  |  | 0
Total |  | 2 |  |  |  | 2 |  |  |  |  | 2
Quantity Notes
The two EPS payloads are funded by RDT&E. EPS has no procurement funding or quantities.

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 1187 | 71.9 |  | 50.8 |  | 24.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1334.2
Procurement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
MILCON | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 1187 | 71.9 |  | 50.8 |  | 24.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1334.2
PB 2016 Total | 1190.4 | 72.1 |  | 51.3 |  | 24.7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1338.5
Delta | -3.4 | -0.2 |  | -0.5 |  | -0.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | -4.3
Funding Notes
The prior year funding does not include the Interim Polar System, consistent with the approved scope of the EPS program.
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 2 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2
Production | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 2 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2
PB 2016 Total | 2 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 171.8
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 220.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 246.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 131.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 97.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 77.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 101.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 99.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 71.9
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 50.8
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.5
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 1334.2

## Table 17
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2014 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.8
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.6
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 186.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 236.4
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 260.6
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 136.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 99.7
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 77.5
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 100.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 97.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 69.4
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.1
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.8
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 1380.3

## Table 18
Low Rate Initial Production
There is no LRIP for this program.

## Table 19
Foreign Military Sales
None
Nuclear Costs
None

## Table 20
Unit Cost
Unit Cost Report
Item |  | BY 2014 $M | BY 2014 $M |  | % Change
|  | Current UCR Baseline (Apr 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1389.1 |  |  | 1380.3
Quantity | 2 |  |  | 2
Unit Cost | 694.55 |  |  | 690.15 |  | -0.63
Average Procurement Unit Cost
Cost | 0 |  |  | 0
Quantity | 0 |  |  | 0
Unit Cost | -- |  |  | -- |  | --
Item |  | BY 2014 $M | BY 2014 $M |  | % Change
|  | Original UCR Baseline (Apr 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1389.1 |  |  | 1380.3
Quantity | 2 |  |  | 2
Unit Cost | 694.55 |  |  | 690.15 |  | -0.63
Average Procurement Unit Cost
Cost | 0 |  |  | 0
Quantity Unit Cost | 0 -- |  |  | 0 -- |  | --
The PAUC is based on RDT&E cost and quantities only. There is no APUC for this program because there are no procurement funds or quantities.

## Table 21
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2014 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Apr 2014 |  |  |  |  | 694.55 |  |  | N/A |  |  | 669.25 |  |  | N/A
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Current APB |  |  | Apr 2014 |  |  |  |  | 694.55 |  |  | N/A |  |  | 669.25 |  |  | N/A
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 691.5 |  |  | N/A |  |  | 669.25 |  |  | N/A
Current Estimate |  |  | Dec 2015 |  |  |  |  | 690.15 |  |  | N/A |  |  | 667.1 |  |  | N/A
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
669.250 2.150 0.000 0.000 0.000 -4.300 0.000 0.000 -2.150 667.100

## Table 22
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [9 empty] | APUC Current Estimate
| Econ | Qty | Sch | Eng |  | Est | Oth | Spt |  | Total
0.000 -- -- -- -- -- -- -- -- 0.000
An APUC Unit Cost History is not available, since no Initial APUC Estimate had been calculated due to a lack of defined quantities.
SAR Baseline History
Item |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone B |  | N/A |  |  | Apr 2014 |  |  |  | N/A |  |  | Apr 2014
Milestone C |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
RAA |  | N/A |  |  | Jun 2018 |  |  |  | N/A |  |  | Jun 2018
Total Cost (TY $M) |  | N/A |  |  | 1338.5 |  |  |  | N/A |  |  | 1334.2
Total Quantity |  | N/A |  |  | 2 |  |  |  | N/A |  |  | 2
PAUC |  | N/A |  |  | 669.25 |  |  |  | N/A |  |  | 667.1

## Table 23
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 1338.5 | -- | -- | 1338.5
Previous Changes
Economic | 5.8 | -- | -- | 5.8
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -5.8 | -- | -- | -5.8
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -- | -- | -- | --
Current Changes
Economic | -1.5 | -- | -- | -1.5
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -2.8 | -- | -- | -2.8
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -4.3 | -- | -- | -4.3
Total Changes | -4.3 | -- | -- | -4.3
CE - Cost Variance | 1334.2 | -- | -- | 1334.2
CE - Cost & Funding | 1334.2 | -- | -- | 1334.2

## Table 24
Summary BY 2014 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 1389.1 | -- | -- | 1389.1
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -6.1 | -- | -- | -6.1
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -6.1 | -- | -- | -6.1
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -2.7 | -- | -- | -2.7
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -2.7 | -- | -- | -2.7
Total Changes | -8.8 | -- | -- | -8.8
CE - Cost Variance | 1380.3 | -- | -- | 1380.3
CE - Cost & Funding | 1380.3 | -- | -- | 1380.3
Previous Estimate: December 2014

## Table 25
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -1.5
Revised estimate for transfer of funds to Small Business Innovative Research/Small Business Technology Transfer. (Estimating)
-3.3 -3.4
Revised estimate due to Congressional General Reductions in FY 2016. (Estimating) | -0.2 |  |  | -0.2
Revised estimate due to inflation adjustment (Estimating) | -0.2 |  |  | -0.2
Adjustment for current and prior escalation. (Estimating) | 1 |  |  | 1
RDT&E Subtotal | -2.7 |  |  | -4.3

## Table 26
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: EPS CAPS
Contractor: Northrop Grumman Information Systems (NGIS) Corporation
Contractor Location: One Space Park
Redondo Beach, CA 90278
Contract Number: FA8808-13-C-0001
Contract Type: Cost Plus Incentive Fee (CPIF), Cost Plus Fixed Fee (CPFF)
Award Date: November 30, 2012
Definitization Date: November 30, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
66.8 N/A 1 157.6 N/A 1 144.9 156.9
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to exercise of CLIN 0002 for software development and delivery, CLIN 0003 for initial spares and support equipment, CLIN 0010 for special studies, and CLIN 0011 for Key Management System to Protected Key Management Architecture upgrade.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) |  |  |  | -6.4 |  |  |  | -1.7
Previous Cumulative Variances |  |  |  | 1.4 |  |  |  | -0.4
Net Change |  |  |  | -7.8 |  |  |  | -1.3

## Table 27
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to the application of unplanned resources to several software and System Engineering, Integration and Test efforts: Software Installation Qualification Test readiness activities for both Increment 1 and 2 testing; additional software integration testing recommended by a joint Government/NGIS Tiger Team; unplanned CAPS/Payload interface integration activities; added effort for test environment configuration; updates to the test tools needed for requirements verification; and unplanned Information Assurance and Security Technical Implementation Guide effort in the database and software environment. Based on performance trends, the NGIS cost variance (-$7.8M) is unrecoverable. However, the Program Office will evaluate options to modify remaining scope and limit the potential for future cost growth. NGIS sacrificed cost to maintain schedule and meet the contractual schedule incentive fee requirement of Site Acceptance Test (SAT) at Schriever Air Force Base (AFB), Colorado in April 2016.
The unfavorable net change in the schedule variance is due to software development and testing delays relative to the baseline in Increment 1, causing ripple effects to initial Increment 2 activities. NGIS sacrificed cost to maintain schedule and meet the contractual schedule incentive fee requirement of SAT at Schriever AFB, Colorado in April 2016. To date, no critical path schedule impacts have been realized. However, parallel segment and system level tests from 1st Quarter to 4th Quarter FY 2016 increase the risk of critical path impact and further cost growth on CAPS. Any delay will also impact system level test events and could result in additional cost increases to other EPS segments.

## Table 28
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 2 | 0%
Production | 0 | 0 | 0 | --
Total Program Quantity Delivered | 0 | 0 | 2 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
1334.2
1174.1
88%
13
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
11
84.62%
1258.9
94.36%
The above data is current as of February 25, 2016.

## Table 29
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 28, 2014
Source of Estimate: SCP
Quantity to Sustain: 1
Unit of Measure: System
Service Life per Unit: 10.00 Years
Fiscal Years in Service: FY 2018 - FY 2028
The EPS system is defined as two payloads plus ground components. The Quantity to Sustain is one EPS system.
Sustainment Strategy
The EPS sustainment strategy follows a path that is consistent with the product acquisition strategy. Current sustainment approach is to have Contractor Logistics Support (CLS) for each segment with planned Performance Based Logistics / Public Private Partnership contract for the Gateway and the Control and Planning Segment (CAPS). The Gateway segment is acquired through the Space and Naval Warfare Systems Command (SPAWAR) Systems Center- Pacific (SC-PAC). The Gateway also includes the Telemetry & Command - Terminal (T&C-T) designed by Massachusetts Institute of Technology / Lincoln Lab (MIT/LL). Northrop Grumman Information Systems Corporation was selected through a competitive process to design and develop CAPS. The Payload segment is a subset of Advanced Extremely High Frequency (AEHF) payload capabilities, provided by the AEHF payload contractor, Northrop Grumman.
The Terminal segment employs the Navy Multiband Terminal (NMT) by the user community as the only EPS-compatible terminal. Support for each of these segments maps back to the applicable Government or contractor agencies.
The support concept for the T&C-T, CAPS and Gateway employs both organizational and depot maintenance. The operators and maintainers for the T&C-T, CAPS and Gateway will be contractors. Depot support for the T&C-T is the responsibility of MIT/LL, and depot support for the Gateway is the responsibility of SSC-PAC. For CAPS, the EPS depots are as follows:
• Ogden Air Logistics Center, Hill Air Force Base (AFB), Utah for software maintenance or public private partnership
• Tobyhanna Army Depot, Pennsylvania for hardware maintenance
• Cryptologic and Cyber Systems Division, Lackland AFB, Texas, for cryptologic items
Interim Contractor Support will be employed for all maintenance and operations until system IOC expected in 2018. Post IOC, operations and organizational level-maintenance will be provided by the operational unit through CLS, and depot- level maintenance support will be provided in accordance with the final Depot Source Of Repair.
Antecedent Information
Interim Polar System (IPS) consists of three Low Data Rate Milstar packages on three classified host satellites as an expedited, interim solution for protected connectivity requirements in the north polar region. Two satellites with hosted packages are required to provide the necessary 24-hour coverage. Since the first IPS was no longer operational, the third package went into operations in November 2008 to sustain the 24-hour coverage.
Comparable O&S cost estimates for the antecedent system, IPS, are not available. The requirements of IPS vary significantly from EPS, making a cost-only comparison between the systems very misleading. The technical differences between the fielded capabilities will be vast. EPS supports an eXtended Data Rate terminal fleet consisting of NMTs,

## Table 30
which can utilize both EPS and AEHF. This reduces the Navy platform footprint and support tail, providing a corresponding reduction in Navy O&S costs. EPS will support a current cryptographic architecture and the accompanying key planning, management, and distribution infrastructure. EPS is therefore positioned to address a modern and evolving cyber threat.
Annual O&S Costs BY2014 $M
Cost Element |  | EPS Average Annual Cost Per System | [5 empty] | IPS (Antecedent) Average Annual Cost Per System
Unit-Level Manpower |  | 5.3 | [5 empty] | --
Unit Operations |  | 0 | [5 empty] | --
Maintenance |  | 1.8 | [5 empty] | --
Sustaining Support |  | 2.2 | [5 empty] | --
Continuing System Improvements |  | 6.1 | [5 empty] | --
Indirect Support |  | 0.3 | [5 empty] | --
Other |  | 0 | [5 empty] | --
Total |  | 15.7 | [5 empty] | --
Item | Total O&S Cost $M
| EPS | [7 empty] | IPS (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 157.4 |  |  | 173.1 |  |  | 157.4 |  | N/A
Then Year | 189.4 |  |  | N/A |  |  | 189.4 |  | 0
Equation to Translate Annual Cost to Total Cost
Total O&S Costs = service life per system * number of systems * unitized cost
Total O&S Costs = 10 year design life * 1 EPS System * $15.7M
O&S Cost Variance
Category |  |  | BY 2014 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
157.4
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 157.4

## Table 31
Disposal Estimate Details
Date of Estimate: Source of Estimate:
Disposal/Demilitarization Total Cost (BY 2014 $M): Total costs for disposal of all System are 0.0