## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-474
F-22 Increment 3.2B Modernization (F-22 Inc 3.2B Mod)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 12
Cost and Funding 13
Low Rate Initial Production 20
Foreign Military Sales 21
Nuclear Costs 21
Unit Cost 22
Cost Variance 25
Contracts 28
Deliveries and Expenditures 31
Operating and Support Cost 32

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
F-22 Increment 3.2B Modernization (F-22 Inc 3.2B Mod)
DoD Component
Air Force
Responsible Office
Col Anthony Genatempo 2725 C Street
Building 553
Wright-Patterson Air Force Base, OH 45433
anthony.genatempo@us.af.mil
Phone: | 937-713-7001
Fax: | 937-656-7511
DSN Phone: | 713-7001
DSN Fax: | 986-7511
Date Assigned: | July 19, 2014
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated June 24, 2013
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated June 24, 2013

## Table 6
Mission and Description
The F-22’s combination of stealth, supercruise, maneuverability, Intra-Flight Data Link (IFDL), sensor fusion coupled with improved supportability provides an exponential leap in warfighting capabilities and allows full realization of operational concepts vital to the 21st Century Air Force and joint warfighting anti-access area denial environment. As a critical component of the Global Strike Concept of Operations, the F-22 provides unmatched air-to-air and air-to-ground capabilities.
F-22 Increment 3.2B Modernization (F-22 Inc 3.2B Mod) integrates the Air Intercept Missiles AIM-9X and AIM-120D into the F
-22, adds Electronic Protection techniques, incorporates new hardware, enhances Geolocate capability, and expands IFDL functionality.

## Table 7
Executive Summary
The F-22 Inc 3.2B Mod is on-track to meet APB parameters, and the EMD effort is progressing as planned. Full hardware qualification is complete. Final software Critical Design Review completed on October 29, 2015. Developmental software coding is on-going and five Developmental Test aircraft are modified. Laboratory and flight tests are proceeding on production representative hardware.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Materiel Development Decision | Dec 2011 | Dec 2011 | Jun 2012 | Dec 2011
Milestone B | Mar 2013 | Mar 2013 | Sep 2013 | Jun 2013
Milestone C | Mar 2016 | Mar 2016 | Sep 2016 | Jun 2016
Full Rate Production | Jan 2018 | Jan 2018 | Jul 2018 | Jul 2018
Required Assets Available (RAA) | Mar 2019 | Mar 2019 | Sep 2019 | Sep 2019
Change Explanations
Notes
RAA is defined as six aircraft and associated support equipment.

## Table 10
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Materiel Availability (Am)
Do not degrade aircraft | Do not degrade aircraft | (Threshold = Objective) | TBD | Do not degrade aircraft
Am below current | Am below current | Do not degrade aircraft |  | Am below current
baseline performance. | baseline performance. | Am below current |  | baseline performance.
Baseline performance | Baseline performance | baseline performance. |  | Baseline performance
KPP: By the end of: FY | KPP: By the end of: FY | Baseline performance |  | KPP: By the end of: FY
2011: 61.2% FY 2012: | 2011: 61.2% FY 2012: | KPP: By the end of: FY |  | 2011: 61.2% FY 2012:
62.6% FY 2013: 65.8% | 62.6% FY 2013: 65.8% | 2011: 61.2% FY 2012: |  | 62.6% FY 2013: 65.8%
FY 2014: 67.6% FY | FY 2014: 67.6% FY | 62.6% FY 2013: 65.8% |  | FY 2014: 67.6% FY
2015: 70.6% | 2015: 70.6% | FY 2014: 67.6% FY |  | 2015: 70.6%
2015: 70.6%
Reliability, MTBCF
Do not degrade aircraft | Do not degrade aircraft | (Threshold = Objective) | TBD | Do not degrade aircraft
MTBCF below current | MTBCF below current | Do not degrade aircraft |  | MTBCF below current
baseline performance. | baseline performance. | MTBCF below current |  | baseline performance.
baseline performance.
Weapons Integration
The F-22A shall be | The F-22A shall be | (Threshold = Objective) | TBD | The F-22A shall be
modified as required to | modified as required to | The F-22A shall be |  | modified as required to
enable employment of | enable employment of | modified as required to |  | enable employment of
the AIM-120D and the | the AIM-120D and the | enable employment of |  | the AIM-120D and the
AIM-9X Block II. | AIM-9X Block II. | the AIM-120D and the |  | AIM-9X Block II.
AIM-9X Block II.
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Capability Production Document (CPD) dated January 4, 2007, as clarified by Joint Requirements Oversight Council Memorandum (JROCM) 052-11 dated April 19, 2011 and JROCM 134-12 dated September 4, 2012 (weapons integration performance criteria are contained in F-22A Increment 3.2B Operational Capabilities Development Document Revision A dated November 15, 2011; availability and reliability performance criteria are contained in Air Force Requirements Oversight Council Memorandum (AFROCM) 11-10-02 dated November 19, 2010 and JROCM 052-11)
Change Explanations
None

## Table 11
Acronyms and Abbreviations
AIM - Air Intercept Missile
MTBCF - Mean Time Between Critical Failure

## Table 12
Track to Budget
RDT&E
Appn |  | BA | PE
Air Force | 3600 07 |  | 0207138F
| Project |  |  | Name
| 674785 |  | F-22 |  | (S | hared) (Sunk)
Air Force | 3600 07 |  | 0207163F
| Project |  |  | Name
| 673777 |  | AIM-120D |  | (S | hared)
Air Force | 3600 05 |  | 0605213F
| Project |  |  | Name
| 654785 |  | F-22 Increment 3.2B |  | (S | hared)
Procurement
Air Force | 3010 06 |  | 0207138F
| Line Item |  |  | Name
| 999 |  | Initial Spares/Repair | Parts |  | (Shared)
Air Force | 3010 05 |  | 0207138F
| Line Item |  |  | Name
Appn |  | BA | PE
F2232B Increment 3.2B F2232BC Advanced Procurement

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2013 $M | [6 empty] | BY 2013 $M |  | TY $M
| SAR Baseline Development Estimate |  |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E |  | 1199.4 |  |  | 1199.4 | 1319.3 |  |  | 1156.2 |  | 1207.3 |  |  | 1207.3 |  | 1158.6
Procurement |  | 338.2 |  |  | 338.2 | 372 |  |  | 345.3 |  | 376.8 |  |  | 376.8 |  | 384
Flyaway |  | -- |  |  | -- | -- |  |  | 325.1 |  | -- |  |  | -- |  | 361.8
Recurring |  | -- |  |  | -- | -- |  |  | 325.1 |  | -- |  |  | -- |  | 361.8
Non Recurring |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support |  | -- |  |  | -- | -- |  |  | 20.2 |  | -- |  |  | -- |  | 22.2
Other Support |  | -- |  |  | -- | -- |  |  | 6.7 |  | -- |  |  | -- |  | 7.3
Initial Spares |  | -- |  |  | -- | -- |  |  | 13.5 |  | -- |  |  | -- |  | 14.9
MILCON |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 1537.6 |  |  | 1537.6 | N/A |  |  | 1501.5 |  | 1584.1 |  |  | 1584.1 |  | 1542.6
Confidence Level
Confidence Level of cost estimate for current APB: 53%
The Life-Cycle Cost Estimate (LCCE) reflects the expected value, or mean, of the cost estimate distribution. It takes into consideration relevant risks, including ordinary levels of external and unforeseen events, aiming to provide sufficient resources to execute the program under normal conditions encountering average levels of technical, schedule, and programmatic risk and external influence.
Total Quantity
Quantity |  |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  |  | 9 |  |  |  | 9 |  |  |  |  | 9
Procurement |  |  | 143 |  |  |  | 143 |  |  |  |  | 143
Total |  |  | 152 |  |  |  | 152 |  |  |  |  | 152
Quantity Notes
The unit of measure is modified aircraft.

## Table 14
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 941.9 | 146.4 |  | 70.3 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1158.6
Procurement | 28.5 | 67.1 |  | 82.8 |  | 151.4 | 13.1 |  | 20.4 |  | 20.7 |  | 0 |  | 384
MILCON | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 970.4 | 213.5 |  | 153.1 |  | 151.4 | 13.1 |  | 20.4 |  | 20.7 |  | 0 |  | 1542.6
PB 2016 Total | 980.2 | 218.6 |  | 156.1 |  | 152.6 | 13.1 |  | 20.6 |  | 0 |  | 0 |  | 1541.2
Delta | -9.8 | -5.1 |  | -3 |  | -1.2 | 0 |  | -0.2 |  | 20.7 |  | 0 |  | 1.4
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 9 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 9
Production | 0 |  | 0 |  | 35 | 36 | 72 |  | 0 | 0 |  | 0 |  | 0 |  | 143
PB 2017 Total | 9 |  | 0 |  | 35 | 36 | 72 |  | 0 | 0 |  | 0 |  | 0 |  | 152
PB 2016 Total | 9 |  | 0 |  | 35 | 36 | 72 |  | 0 | 0 |  | 0 |  | 0 |  | 152
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0

## Table 15
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.4
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.4
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 131
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 129.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 127.5
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 129
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 109.1
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 187.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 146.4
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 70.3
Subtotal |  | 9 | -- |  | -- |  | -- |  | -- |  | -- |  | 1158.6

## Table 16
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2013 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.6
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.6
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 136.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 132.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 128.1
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 127.6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 106.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 181.3
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 139.3
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.6
Subtotal |  | 9 | -- |  | -- |  | -- |  | -- |  | -- |  | 1156.2

## Table 17
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2015 |  | -- | 28.5 |  | -- |  | -- |  | 28.5 |  | -- |  | 28.5
2016 |  | 35 | 62.1 |  | -- |  | -- |  | 62.1 |  | 5 |  | 67.1
2017 |  | 36 | 76.8 |  | -- |  | -- |  | 76.8 |  | 6 |  | 82.8
2018 |  | 72 | 140.7 |  | -- |  | -- |  | 140.7 |  | 10.7 |  | 151.4
2019 |  | -- | 13 |  | -- |  | -- |  | 13 |  | 0.1 |  | 13.1
2020 |  | -- | 20 |  | -- |  | -- |  | 20 |  | 0.4 |  | 20.4
2021 |  | -- | 20.7 |  | -- |  | -- |  | 20.7 |  | -- |  | 20.7
Subtotal |  | 143 | 361.8 |  | -- |  | -- |  | 361.8 |  | 22.2 |  | 384

## Table 18
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | BY 2013 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2015 |  | -- | 26.9 |  | -- |  | -- |  | 26.9 |  | -- |  | 26.9
2016 |  | 35 | 57.4 |  | -- |  | -- |  | 57.4 |  | 4.7 |  | 62.1
2017 |  | 36 | 69.7 |  | -- |  | -- |  | 69.7 |  | 5.5 |  | 75.2
2018 |  | 72 | 125.3 |  | -- |  | -- |  | 125.3 |  | 9.5 |  | 134.8
2019 |  | -- | 11.3 |  | -- |  | -- |  | 11.3 |  | 0.1 |  | 11.4
2020 |  | -- | 17.1 |  | -- |  | -- |  | 17.1 |  | 0.4 |  | 17.5
2021 |  | -- | 17.4 |  | -- |  | -- |  | 17.4 |  | -- |  | 17.4
Subtotal |  | 143 | 325.1 |  | -- |  | -- |  | 325.1 |  | 20.2 |  | 345.3

## Table 19
Cost Quantity Information 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2013 $M
2015 | -- | --
2016 | 35 | 79.6
2017 | 36 | 81.8
2018 | 72 | 163.7
2019 | -- | --
2020 | -- | --
2021 | -- | --
Subtotal | 143 | 325.1

## Table 20
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2013-06-26 | 2013-06-26
Approved Quantity | 71 | 71
Reference | Milestone B ADM | Milestone B ADM
Start Year | 2016 | 2016
End Year | 2017 | 2017
The Current Total LRIP Quantity is more than 10% of the total production quantity due to an opportunity to capture economic order quantity efficiencies. This strategy was approved as part of the Milestone B review.

## Table 21
Foreign Military Sales
None
Nuclear Costs
None

## Table 22
Unit Cost
Unit Cost Report
Item |  | BY 2013 $M | BY 2013 $M |  | % Change
|  | Current UCR Baseline (Jun 2013 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1537.6 |  |  | 1501.5
Quantity | 152 |  |  | 152
Unit Cost | 10.116 |  |  | 9.878 |  | -2.35
Average Procurement Unit Cost
Cost | 338.2 |  |  | 345.3
Quantity | 143 |  |  | 143
Unit Cost | 2.365 |  |  | 2.415 |  | 2.11
Item |  | BY 2013 $M | BY 2013 $M |  | % Change
|  | Original UCR Baseline (Jun 2013 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1537.6 |  |  | 1501.5
Quantity | 152 |  |  | 152
Unit Cost | 10.116 |  |  | 9.878 |  | -2.35
Average Procurement Unit Cost
Cost | 338.2 |  |  | 345.3
Quantity | 143 |  |  | 143
Unit Cost | 2.365 |  |  | 2.415 |  | 2.11

## Table 23
Unit Cost History
Item |  |  |  |  | Date |  |  |  |  | BY 2013 $M | [5 empty] | TY $M
[10 empty] | PAUC |  |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Jun 2013 | [6 empty] | 10.116 |  |  |  | 2.365 |  |  | 10.422 |  |  | 2.635
APB as of January 2006 |  |  | N/A | [6 empty] | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A | [6 empty] | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | N/A | [6 empty] | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Current APB |  |  | Jun 2013 | [6 empty] | 10.116 |  |  |  | 2.365 |  |  | 10.422 |  |  | 2.635
Prior Annual SAR |  |  | Dec 2014 | [6 empty] | 9.848 |  |  |  | 2.321 |  |  | 10.139 |  |  | 2.592
Current Estimate |  |  | Dec 2015 | [6 empty] | 9.878 |  |  |  | 2.415 |  |  | 10.149 |  |  | 2.685
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [16 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng |  | Est |  |  | Oth | Spt |  |  | Total
10.422 -0.036 0.000 0.000 0.000 -0.232 0.000 -0.005 -0.273 10.149
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [16 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  |  | Eng |  | Est |  | Oth | Spt |  |  | Total
2.635 -0.010 0.000 0.000 0.000 0.066 0.000 -0.005 0.051 2.685

## Table 24
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Mar 2013 | N/A | Jun 2013
Milestone C | N/A | Mar 2016 | N/A | Jun 2016
RAA | N/A | Mar 2019 | N/A | Sep 2019
Total Cost (TY $M) | N/A | 1584.1 | N/A | 1542.6
Total Quantity | N/A | 152 | N/A | 152
PAUC | N/A | 10.422 | N/A | 10.149

## Table 25
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 1207.3 | 376.8 | -- | 1584.1
Previous Changes
Economic | -1.1 | 1.3 | -- | 0.2
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -35.6 | -7.1 | -- | -42.7
Other | -- | -- | -- | --
Support | -- | -0.4 | -- | -0.4
Subtotal | -36.7 | -6.2 | -- | -42.9
Current Changes
Economic | -2.9 | -2.8 | -- | -5.7
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -9.1 | 16.5 | -- | 7.4
Other | -- | -- | -- | --
Support | -- | -0.3 | -- | -0.3
Subtotal | -12 | 13.4 | -- | 1.4
Total Changes | -48.7 | 7.2 | -- | -41.5
CE - Cost Variance | 1158.6 | 384 | -- | 1542.6
CE - Cost & Funding | 1158.6 | 384 | -- | 1542.6

## Table 26
Summary BY 2013 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 1199.4 | 338.2 | -- | 1537.6
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -34.4 | -6.1 | -- | -40.5
Other | -- | -- | -- | --
Support | -- | -0.2 | -- | -0.2
Subtotal | -34.4 | -6.3 | -- | -40.7
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -8.8 | 13.4 | -- | 4.6
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -8.8 | 13.4 | -- | 4.6
Total Changes | -43.2 | 7.1 | -- | -36.1
CE - Cost Variance | 1156.2 | 345.3 | -- | 1501.5
CE - Cost & Funding | 1156.2 | 345.3 | -- | 1501.5
Previous Estimate: December 2014

## Table 27
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -2.9
Revised estimate to reflect Air Force reprogramming of funds. (Estimating) | -11.1 | -11.5
Adjustment for current and prior escalation. (Estimating) | 2.3 | 2.4
RDT&E Subtotal | -8.8 | -12
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -2.8
Revised estimate to reflect Congressional reductions in FY 2016. (Estimating) | -4.6 | -4.9
Revised estimate to reflect baseline extension. (Estimating) | 17.4 | 20.7
Adjustment for current and prior escalation. (Estimating) | 0.6 | 0.7
Adjustment for current and prior escalation. (Support) | 0.1 | 0
Decrease in Initial Spares (Support) | -0.3 | -0.3
Increase in Other Support. (Support) | 0.2 | 0
Procurement Subtotal | 13.4 | 13.4

## Table 28
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: F-22 Mod, DO 0004 REDI II, Incr 3.2B Ph C&D
Contractor: Lockheed Martin Aeronautics
Contractor Location: 1 Lockheed Blvd
Ft. Worth, TX 76108-3619
Contract Number: FA8611-13-D-2850/3
Contract Type: Cost Plus Incentive Fee (CPIF), Cost Plus Fixed Fee (CPFF)
Award Date: June 26, 2013
Definitization Date: June 26, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
328.8 N/A 9 329.8 N/A 9 290.3 295.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the addition of one Engineering Change Proposal (ECP) and two Contract Change Proposals (CCPs) in CY 2015:
Contract Modification 000412 added ECP 0661 - Addition of 7th Dual Computing Engine (DuCE) and Global Inertial Navigation System (GINS) 09 to Increment 3.2B; as a result, the Delivery Order (DO) 0004 price increased by $.9M.
Contract Modification 000417 added CCP 438 - Credit for stop work of maintenance training courseware activities; as a result, the DO 0004 price decreased by $.3M.
Contract Modification 000419 added CCP 0452 - Partial stop work and addition of new work due to Air Force Operational Test and Evaluation Center (AFOTEC) providing new threat model requirements beyond the scope of DO 0004 and deleted threat model requirements previously identified; as a result, the DO 0004 price increased by $3.1M.
The total net value of DO 0004 contract changes in CY 2015 amount to $3.7M.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/27/2015) |  |  |  | -3.6 |  |  |  | -4.3
Previous Cumulative Variances |  |  |  | 3.8 |  |  |  | -4.2
Net Change |  |  |  | -7.4 |  |  |  | -0.1

## Table 29
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to additional unplanned efforts due to delays of predecessor F-22 software programs.
The unfavorable net change in the schedule variance is due to schedule delays of predecessor F-22 software programs.
Notes
Delivery Order (DO) 0004 was issued under the overarching F-22 Raptor, Enhancement, Development, and Integration II Indefinite Delivery Indefinite Quantity Contract (FA8611-13-D-2850). Definitization date is same as award date and does not indicate this DO was issued as a letter contract or Undefinitized Contractual Action.

## Table 30
Contract Identification
Appropriation: RDT&E
Contract Name: D.O. 009 Test Execution CLIN 0301
Contractor: Lockheed Martin (Aeronautics)
Contractor Location: 1 Lockheed Blvd
Ft. Worth, TX 76108-3619
Contract Number: FA8611-13-D-2850/4
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: January 01, 2015
Definitization Date: January 01, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
54.6 N/A N/A 54.6 N/A N/A 54.6 54.6
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/27/2015) +2.2 -0.5
Previous Cumulative Variances -- --
Net Change +2.2 -0.5
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to less effort required due to delays in predecessor F-22 software programs.
The unfavorable cumulative schedule variance is due to delayed start of flight testing due to delays in predecessor F-22 software programs.
Notes
This is the first time this contract is being reported.
This effort is for 3.2B System Integration and Test efforts only; deliveries, as such, are not anticipated.

## Table 31
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 5 | 5 | 9 | 55.56%
Production | 0 | 0 | 143 | 0%
Total Program Quantity Delivered | 5 | 5 | 152 | 3.29%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
1542.6
894.8
58.01%
18
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
13
72.22%
1183.9
76.75%
The above data is current as of February 09, 2016.
Total funding years reflect development executed in support of the F-22 Inc 3.2B Mod program. Beginning in FY 2011 the program was rescoped into smaller increments of capability (e.g. 3.2A, 3.2B) to adjust to financial constraints, facilitate improved baseline control/management, and meet capability delivery needs. F-22 Inc 3.2B Mod officially started in FY 2013 with approval of Milestone B.

## Table 32
Operating and Support Cost
Cost Estimate Details
Date of Estimate: May 31, 2013
Source of Estimate: SCP
Quantity to Sustain: 149
Unit of Measure: Modified Aircraft
Service Life per Unit: 15.00 Years
Fiscal Years in Service: FY 2018 - FY 2033
The F-22 Inc 3.2B Mod is a capability upgrade modification program. The program will modify 152 F-22A aircraft (9 RDT&E and 143 Procurement). Of the 152 aircraft, 3 are development test assets, and 149 will be sustained with O&S funds.
Sustainment Strategy
Given the low hardware risk of the F-22 Inc 3.2B Mod upgrade, sustainment requirements will be managed within the baseline F-22 sustainment concept with minimal impact on O&S cost estimates or achievement of materiel availability goals. The F-22 sustainment strategy is to sustain F-22 readiness and availability at the lowest cost over the life of the weapon system. The F-22 sustainment strategy employs Performance-Based Logistics contracts with Public/Private Partnering for depot repair capabilities to meet Air Force Core requirements.
Antecedent Information
No Antecedent
Annual O&S Costs BY2013 $K
Cost Element | F-22 Inc 3.2B Mod Average Annual Cost Per Modified Aircraft | No Antecedent (Antecedent)
Unit-Level Manpower | 0 | 0
Unit Operations | 0 | 0
Maintenance | 33 | 0
Sustaining Support | 0 | 0
Continuing System Improvements | 0 | 0
Indirect Support | 0 | 0
Other | 0 | 0
Total | 33 | --
Average Primary Aircraft Assigned (PAA): 163 (entire F-22 fleet)

## Table 33
Item | Total O&S Cost $M
| F-22 Inc 3.2B Mod | [5 empty] | No Antecedent (Antecedent)
| Current Development APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 80.9 |  | 89 |  |  | 80.9 | N/A
Then Year | 104.5 |  | N/A |  |  | 104.5 | N/A
The F-22 Inc 3.2B Mod O&S costs will not be tracked separately as directed by the June 26, 2013 ADM. The total Inc 3.2B Mod O&S costs, estimated to be $80.9M (BY 2013), will be reported as part of the estimated $67.1B overall F-22 baseline program O&S costs.
The Air Force expects F-22 Incr 3.2B Mod O&S costs to be budgeted in the baseline F-22 PE (27138F) and expended along with baseline program O&S funds, so the PAA value used in the calculation includes all F-22s, not just the aircraft receiving the Increment 3.2B modification.
Total O&S costs were estimated for initial "steady state" year, 2022.
- Cost were then applied for the years 2018 (1st modified aircraft is fielded) through 2033 (15 years)
Equation to Translate Annual Cost to Total Cost
Unitized cost estimate is calculated:
Total O&S / estimated service life / Average PAA; ($80.9M/15/163) = $.033M
The average annual cost per modified aircraft represents the additional O&S cost of the 149 modified aircraft spread over the entire fleet of F-22 aircraft (163 PAA). This is necessary since the modified aircraft will be reported as part of the overall F-22 baseline program.
O&S Cost Variance
Category |  | BY 2013 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
80.9
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 80.9
Disposal Estimate Details
Date of Estimate:

## Table 34
Source of Estimate:
Disposal/Demilitarization Total Cost (BY 2013 $M):
Disposal costs for this modification are included in the F-22 platform.