## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-237
Global Broadcast Service (GBS)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 13
Cost and Funding 14
Low Rate Initial Production 32
Foreign Military Sales 33
Nuclear Costs 33
Unit Cost 34
Cost Variance 37
Contracts 41
Deliveries and Expenditures 42
Operating and Support Cost 43

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Global Broadcast Service (GBS)
DoD Component
Air Force
Joint Participants
Army; Navy; Marine Corps
Responsible Office
Mr. Robert Tarleton
MILSATCOM Systems Directorate 483 N. Aviation Blvd.
El Segundo, CA 90245-2802
Robert.Tarleton@us.af.mil
Phone: | 310-653-9001
Fax: | 310-653-9636
DSN Phone: | 633-9001
DSN Fax: | 633-9636
Date Assigned: | February 10, 2014
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated November 14, 1997
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated September 15, 2006

## Table 6
Mission and Description
The Global Broadcast Service (GBS) is an extension of the Global Information Grid that provides worldwide, high capacity, one-way transmission of video (especially from Unmanned Aerial Vehicles), imagery and geospatial intelligence products, and other high-bandwidth information supporting the nation's command centers and joint combat forces in garrison, in transit, and deployed within global combat zones. It employs readily available satellite-based commercial technologies that are relatively inexpensive and easily integrated into existing systems and processes, yet are not so unwieldy as to be unusable by smaller and more mobile units. To this end, GBS currently uses broadcast payloads on two Ultra-High Frequency Follow-On satellites and the Wideband Global Satellite Communications constellation.
Information sources deliver products for daily broadcast via Defense Enterprise Computing Centers operated by the Defense Information Systems Agency. Content is based on defined mission profiles approved by the Combatant Commander's Theater Information Managers. The GBS Operations Center provides broadcast planning and coordinates beam movement as well as 24/7/365 support to users worldwide.

## Table 7
Executive Summary
The GBS program office is proceeding with its non-transmission security (TRANSEC) solution to address obsolescence issues and vulnerabilities and enable fielding of new receive suite products. Activities include testing new versions of GBS specific software with new hardware components, coordinating test resources, and executing path check-outs through teleport gateways and the Defense Enterprise Computing Center Satellite Broadcast Manager. Government Qualification Testing was successfully held in October 2015 as planned. Forty-nine deficiencies were identified of which 16 have been closed; courses of action have been identified for those remaining. The program office continues to plan and coordinate resources for regression testing starting in February 2016 followed by Operational Testing in May/June 2016. Operational Acceptance (OA) is projected for November 2016.
The program office continues to support the DoD effort to develop a replacement TRANSEC solution. Defense Information Systems Agency (DISA), the lead agency for this effort, has a program entitled Enterprise Satellite Communications (SATCOM) Gateway Modem. DISA issued a Request for Information in May 2015 to support Commercial Product Analysis. From that, DISA down-selected potential modems to undergo demonstration and performance testing at the Joint SATCOM Engineering Center December 2015 – March 2016. GBS technical staff participates in stakeholder meetings to ensure GBS requirements will be met.
On April 24, 2015, the Army announced it no longer has a requirement for the Theater Injection Point (TIP), which is GBS’s transportable broadcast capability. The five TIPs (three Army, one Air Force, and one for testing) were being upgraded for obsolescence issues and vulnerabilities and were to be part of the OA process. The Air Force later determined that the cost of operating and maintaining its TIP outweighed the operational requirement. On June 25, 2015, Headquarters Air Force Space Command removed the TIP from the Digital Video Broadcast – SATCOM Generation 2 non-TRANSEC architecture test requirements.
On September 24, 2015, an Indefinite Delivery/Indefinite Quantity production contract was awarded to AQYR Technologies for Portable Receive Suites (PRS). This is Phase III of a Small Business Innovative Research effort. The contract has a
$100M ceiling and pricing tables through CY 2020. The first Delivery Order (DO) was placed on September 28, 2015, for 150 Rucksack PRSs and associated spares for the Air Force. The DO totals $13.95M. Details of this contract are
not included in the Contracts section of this SAR since the value is currently below the $40M threshold for SAR reporting.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
The schedule and the total procurement cost breaches were previously reported in the December 2010 SAR.
A Program Deviation Report (PDR) was issued for the schedule breach on January 30, 2008.
Throughout the budgeting process the Services have increased procurement funding to buy additional receive suites. These increases led to a procurement breach in the FY 2011 PB. A PDR for the procurement cost breach was submitted to the Secretary of the Air Force on April 23, 2010 and to USD(AT&L) August 31, 2010.
The program office was not directed to update the APB.
Nunn-McCurdy Breaches

## Table 9
Schedule
1 APB Breach
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone II (DAE) | Dec 1997 | Dec 1997 | Jun 1998 | Nov 1997
System Available for Operational Use | Jun 1999 | Oct 2001 | Apr 2002 | Oct 2001
IOC | Dec 1999 | Sep 2003 | Mar 2004 | Dec 2003
Beyond LRIP Review | N/A | Dec 2006 | Jun 2007 | Apr 2007
IOC 2&3 | N/A | Jun 2007 | Dec 2007 | Oct 20081
Milestone III | Dec 1999 | N/A | N/A | N/A
Change Explanations
None
Notes
All Schedule Events have been fulfilled.
An incremental IOC approach was approved by the JROC memo 111-00, dated June 27, 2000. GBS Phase II requirements are grouped into IOC 1, 2 and 3. The following summarizes the threshold requirements associated with each IOC:
IOC 1:
- PIPs operational on UFO satellites 8, 9, 10.
- Full Satellite Broadcast Manager capability.
- Field 20% of JPO Receive Suites (19 units).
- Personnel training in operations and maintenance of fielded equipment.
- Logistically support the system to effectively sustain GBS.
- Independently assess system capabilities.
- Augment UFO GBS with leased commercial satellite services to cover gaps over CONUS.

## Table 10
- Demonstrate smart push and user pull capability.
(Note: IOC 1 is based on the performance of the then-fielded ATM based system.)
IOC 2:
- Field 90% of JPO Receive Suites (86 units).
- Provide classified video capability.
- Remote Receive Suite enable/disable.
IOC 3:
- Tactically suitable Ground Receive Suite (two-person lift).
- Protect all information from exploitation.
Acronyms and Abbreviations
ATM - Asynchronous Transfer Mode CONUS - Continental United States JPO - Joint Program Office
PIP - Primary Injection Point
UFO - Ultra High Frequency Follow-On

## Table 11
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
System Coverage
65 deg South to 65 deg North | 65 deg South to 65 deg North | 65 deg South to 65 deg North | 65 deg South to 65 deg North | 65 deg South to 65 deg North
Space Segment Resources
N/A | WGS with UFO GBS | WGS with UFO GBS | WGS with UFO GBS | WGS with UFO GBS
Spot Beams
Two 500nm steerable, one 2000 nm steerable | Two 500nm steerable, one 2000 nm steerable | Two 500nm steerable, One 2000 nm steerable | Two 500nm steerable, One 2000 nm steerable | Two 500nm steerable, One 2000 nm steerable
Simultaneous Uplinks
One PIP and up to 3 TIPs simultan-eously | One PIP and up to 3 TIPs simultan-eously | One PIP and one TIP | One PIP and one TIP | One PIP and one TIP
Security
Pass unclassified to TS/SCI traffic | Pass unclassified toTS/SCI traffic | Pass unclassified toTS/SCI traffic | Pass unclassified to TS/SCI traffic | Pass unclassified to TS/SCI traffic
Receive Frequency Band
20.2-21. 2 GHz UFO GBS, one or more commercial satellite frequency bands | N/A | N/A | N/A | N/A
Support operations with multiple satellite beams and terminal types (i.e., Receive Variable Data Rates)
2000nm: add SSRS and ART 500nm: add ART | 2000nm: add SSRS and ART 500nm: Add ART | 2000nm: FGRS, TGRS and SRS 500nm: FGRS, TGRS, SRS and SSRS | 2000nm: FGRS, TGRS and SRS 500nm: FGRS, TGRS, SRS and SSRS | 2000nm: FGRS, TGRS and SRS 500nm: FGRS, TGRS, SRS and SSRS
Pointing of Steerable Spot Beam Antenna
Frequent | Frequent | Frequent | Frequent | Frequent
Steerable Antenna Tasking
SBM Primary means | SBM Primary Means | SBM Primary Means | SBM Primary Means | SBM Primary Means
Interoperability
N/A | 100% IERs | 100% critical IERs | 100% IERs satisfied | 100% IERs satisfied

## Table 12
| satisfied | satisfied
Network Ready
N/A | TBD | TBD | Certification granted May 16, 2013 | Certification granted May 16, 2013
Requirements Reference
Operational Requirements Document (ORD) dated January 12, 2005
Change Explanations
None
Notes
The Demonstrated Performance and Current Estimate for Network Ready was updated to acknowledge a Joint Staff Memorandum for United States Air Force, dated May 16, 2013, that granted full Net-Ready KPP certification of the GBS program. With this certification, all Performance Characteristics have been fulfilled.
Acronyms and Abbreviations
ART - Airborne Receive Terminal deg - Degrees
FGRS - Fixed Ground Receive Suite/Terminal GHz - Gigahertz
IERs - Information Exchange Requirements nm - Nautical Miles
PIP - Primary Injection Point
SBM - Satellite Broadcast Manager
SRS - Shipboard Receive Suite/Terminal
SSRS - SubSurface (submarine) Receive Suite/Terminal TGRS - Transportable Ground Receive Suite/Terminal TIP - Theater Injection Point
TS/SCI - Top Secret/Sensitive Compartmented Information UFO - Ultra High Frequency Follow-on Satellite
WGS - Wideband Global SATCOM

## Table 13
Track to Budget
RDT&E
Appn |  |  | BA | PE
Navy |  | 1319 07 |  | 0303109N
|  | Project |  | Name
|  | 3398 |  | Enterprise SATCOM Gateway Modems (ESGM) | (Shared)
Air Force |  | 3600 07 |  | 0303601F
|  | Project |  | Name
|  | 2487 |  | MILSATCOM Space | (Shared) | (Sunk)
Air Force |  | 3600 05 |  | 0603840F
|  | Project |  | Name
|  | 4887 |  | Global Broadcast Service | (Shared) | (Sunk)
Air Force |  | 3600 04 |  | 0603854F
|  | Project |  | Name
|  | 2679 |  | Global Broadcast Service 1 & 2 |  | (Sunk)
Air Force |  | 3600 04 |  | 0604775F
|  | Project |  | Name
|  | 6004 |  | Defense Rapid Innovation Program | (Shared) | (Sunk)
Procurement
Appn |  |  | BA | PE
Navy 1109 04 0206313M
Line Item | Name
4633 Radio Systems (Shared)
Navy 1810 02 0303109N
Line Item | Name
3215 Satellite Communications Systems (Shared)
Army 2035 02 0310703A
Line Item | Name
BC4120 GBS (Shared)
Air Force 3021 05 0303601F
Line Item | Name
199 AF - Space Equipment (Shared)
Air Force 3080 03 0303601F
Line Item | Name
836780 MILSATCOM Space (Shared) (Sunk)
Defense-Wide 0350 02 0505001D
Line Item | Name
21005 Misc Equipment - Army National Guard (Shared) (Sunk)

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 1997 $M | [5 empty] | BY 1997 $M |  | TY $M
| SAR Baseline Development Estimate |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E | 397.5 |  |  | 423.5 | 465.9 |  |  | 399.7 |  | 439.2 |  |  | 450.5 |  | 424.2
Procurement | 53.9 |  |  | 361.3 | 397.4 |  |  | 569.01 |  | 57.9 |  |  | 412.3 |  | 707.7
Flyaway | -- |  |  | -- | -- |  |  | 545.4 |  | -- |  |  | -- |  | 679.5
Recurring | -- |  |  | -- | -- |  |  | 360.6 |  | -- |  |  | -- |  | 443.2
Non Recurring | -- |  |  | -- | -- |  |  | 184.8 |  | -- |  |  | -- |  | 236.3
Support | -- |  |  | -- | -- |  |  | 23.6 |  | -- |  |  | -- |  | 28.2
Other Support | -- |  |  | -- | -- |  |  | 5.3 |  | -- |  |  | -- |  | 5.6
Initial Spares | -- |  |  | -- | -- |  |  | 18.3 |  | -- |  |  | -- |  | 22.6
MILCON | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 451.4 |  |  | 784.8 | N/A |  |  | 968.7 |  | 497.1 |  |  | 862.8 |  | 1131.9
1 APB Breach
Total Quantity
Quantity |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  | 221 |  |  |  | 136 |  |  |  |  | 136
Procurement |  | 125 |  |  |  | 1085 |  |  |  |  | 1903
Total |  | 346 |  |  |  | 1221 |  |  |  |  | 2039
Quantity Notes
The RDT&E quantity of 136 is comprised of 10 First Generation Increment One (I1E) Air Force Receive Suites (RS), 27 I1E Shipboard RS, 96 Joint Program Office funded Air Force RS, and 3 Primary Injection Points (PIPs).
The Procurement quantity includes 3 Army Theater Injection Points (TIPs) and 2 Air Force TIPs; all others are RS. The quantity increase of 25 receive suites on the following page breaks out as follows:
3 - increase in Air Force (APPN 3080) receive suites FY 2014 - 2015
11 - increase and redistribution in Navy (APPN 1810) receive suites FY 2016 - 2021
11 - increase and redistribution in Marine Corps (APPN 1109) receive suites FY 2014 - 2017 25 - total increase from prior SAR

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 419.4 | 0 |  |  | 2.4 | 1.5 | 0.9 |  | 0 |  | 0 |  |  | 0 | 424.2
Procurement | 631.5 | 22.3 |  |  | 26.2 | 8.5 | 7.2 |  | 5 |  | 5.1 |  |  | 1.9 | 707.7
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 | 0
PB 2017 Total | 1050.9 | 22.3 |  |  | 28.6 | 10 | 8.1 |  | 5 |  | 5.1 |  |  | 1.9 | 1131.9
PB 2016 Total | 1045.4 | 24.9 |  |  | 11.8 | 5 | 5 |  | 3.3 |  | 0 |  |  | 0 | 1095.4
Delta | 5.5 | -2.6 |  |  | 16.8 | 5 | 3.1 |  | 1.7 |  | 5.1 |  |  | 1.9 | 36.5
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 136 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 136
Production | 0 |  | 1803 |  | 19 | 38 | 6 | 12 |  | 12 |  | 13 |  | 0 |  | 1903
PB 2017 Total | 136 |  | 1803 |  | 19 | 38 | 6 | 12 |  | 12 |  | 13 |  | 0 |  | 2039
PB 2016 Total | 136 |  | 1807 |  | 25 | 15 | 7 | 12 |  | 12 |  | 0 |  | 0 |  | 2014
Delta | 0 |  | -4 |  | -6 | 23 | -1 | 0 |  | 0 |  | 13 |  | 0 |  | 25

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.9
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 70.2
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 64.3
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.1
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.6
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.8
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.8
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.9
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.1
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.6
Subtotal |  | 136 | -- |  | -- |  | -- |  | -- |  | -- |  | 419.4

## Table 17
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 1997 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.1
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.7
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 69.3
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.9
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.6
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.9
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.3
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.4
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.2
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.3
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.4
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.6
Subtotal |  | 136 | -- |  | -- |  | -- |  | -- |  | -- |  | 396.4

## Table 18
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.4
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.9
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.8

## Table 19
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 1997 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.6
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.3

## Table 20
Annual Funding 2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1998 |  | 1 | 3 |  | -- |  | 2.2 |  | 5.2 |  | 2.1 |  | 7.3
1999 |  | 8 | 4.3 |  | -- |  | -- |  | 4.3 |  | 1.5 |  | 5.8
2000 |  | 17 | 9.4 |  | -- |  | 4 |  | 13.4 |  | 1.5 |  | 14.9
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.2 |  | 0.2
2002 |  | 27 | 7.6 |  | -- |  | -- |  | 7.6 |  | 0.8 |  | 8.4
2003 |  | 13 | 4.9 |  | -- |  | -- |  | 4.9 |  | 1 |  | 5.9
2004 |  | 24 | 13.6 |  | -- |  | 0.3 |  | 13.9 |  | 0.1 |  | 14
2005 |  | 1 | 12.2 |  | -- |  | -- |  | 12.2 |  | 1.2 |  | 13.4
2006 |  | 59 | 12.1 |  | -- |  | -- |  | 12.1 |  | 1 |  | 13.1
2007 |  | 62 | 16.7 |  | -- |  | -- |  | 16.7 |  | 1.2 |  | 17.9
2008 |  | 332 | 46.6 |  | -- |  | -- |  | 46.6 |  | 3.5 |  | 50.1
2009 |  | 188 | 34.4 |  | -- |  | -- |  | 34.4 |  | 3.3 |  | 37.7
2010 |  | 4 | 0.5 |  | -- |  | 6.3 |  | 6.8 |  | -- |  | 6.8
2011 |  | -- | -- |  | -- |  | 4.6 |  | 4.6 |  | -- |  | 4.6
2012 |  | 177 | 51.3 |  | -- |  | -- |  | 51.3 |  | 0.5 |  | 51.8
2013 |  | 89 | 17.6 |  | -- |  | -- |  | 17.6 |  | 3 |  | 20.6
2014 |  | -- | -- |  | -- |  | 9.1 |  | 9.1 |  | -- |  | 9.1
2015 |  | -- | -- |  | -- |  | 15.9 |  | 15.9 |  | -- |  | 15.9
2016 |  | -- | -- |  | -- |  | 6.3 |  | 6.3 |  | -- |  | 6.3
Subtotal |  | 1002 | 234.2 |  | -- |  | 48.7 |  | 282.9 |  | 20.9 |  | 303.8

## Table 21
Annual Funding 2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity |  | BY 1997 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1998 |  | 1 | 2.9 |  | -- |  | 2.1 |  | 5 |  | 2.1 |  | 7.1
1999 |  | 8 | 4.1 |  | -- |  | -- |  | 4.1 |  | 1.5 |  | 5.6
2000 |  | 17 | 9 |  | -- |  | 3.7 |  | 12.7 |  | 1.5 |  | 14.2
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.2 |  | 0.2
2002 |  | 27 | 7.1 |  | -- |  | -- |  | 7.1 |  | 0.7 |  | 7.8
2003 |  | 13 | 4.5 |  | -- |  | -- |  | 4.5 |  | 0.9 |  | 5.4
2004 |  | 24 | 12.1 |  | -- |  | 0.3 |  | 12.4 |  | 0.1 |  | 12.5
2005 |  | 1 | 10.6 |  | -- |  | -- |  | 10.6 |  | 1 |  | 11.6
2006 |  | 59 | 10.2 |  | -- |  | -- |  | 10.2 |  | 0.9 |  | 11.1
2007 |  | 62 | 13.8 |  | -- |  | -- |  | 13.8 |  | 1 |  | 14.8
2008 |  | 332 | 37.8 |  | -- |  | -- |  | 37.8 |  | 2.9 |  | 40.7
2009 |  | 188 | 27.5 |  | -- |  | -- |  | 27.5 |  | 2.7 |  | 30.2
2010 |  | 4 | 0.4 |  | -- |  | 4.9 |  | 5.3 |  | -- |  | 5.3
2011 |  | -- | -- |  | -- |  | 3.6 |  | 3.6 |  | -- |  | 3.6
2012 |  | 177 | 39 |  | -- |  | -- |  | 39 |  | 0.4 |  | 39.4
2013 |  | 89 | 13.1 |  | -- |  | -- |  | 13.1 |  | 2.3 |  | 15.4
2014 |  | -- | -- |  | -- |  | 6.7 |  | 6.7 |  | -- |  | 6.7
2015 |  | -- | -- |  | -- |  | 11.5 |  | 11.5 |  | -- |  | 11.5
2016 |  | -- | -- |  | -- |  | 4.5 |  | 4.5 |  | -- |  | 4.5
Subtotal |  | 1002 | 192.1 |  | -- |  | 37.3 |  | 229.4 |  | 18.2 |  | 247.6

## Table 22
Annual Funding 1109 ¦ Procurement ¦ Procurement, Marine Corps
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | 2.4 |  | 2.4 |  | -- |  | 2.4
2005 |  | 48 | 5.7 |  | -- |  | -- |  | 5.7 |  | -- |  | 5.7
2006 |  | 20 | 3.1 |  | -- |  | 3.4 |  | 6.5 |  | -- |  | 6.5
2007 |  | -- | -- |  | -- |  | 0.1 |  | 0.1 |  | -- |  | 0.1
2008 |  | -- | -- |  | -- |  | 2.4 |  | 2.4 |  | -- |  | 2.4
2009 |  | -- | -- |  | -- |  | 0.7 |  | 0.7 |  | -- |  | 0.7
2010 |  | 16 | 2.4 |  | -- |  | -- |  | 2.4 |  | -- |  | 2.4
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | 0.1 |  | 0.1 |  | -- |  | 0.1
2013 |  | 3 | 0.3 |  | -- |  | 1 |  | 1.3 |  | -- |  | 1.3
2014 |  | -- | -- |  | -- |  | 0.3 |  | 0.3 |  | -- |  | 0.3
2015 |  | -- | -- |  | -- |  | 1.3 |  | 1.3 |  | -- |  | 1.3
2016 |  | -- | -- |  | -- |  | 0.6 |  | 0.6 |  | -- |  | 0.6
2017 |  | 18 | 2 |  | -- |  | 6.3 |  | 8.3 |  | 0.2 |  | 8.5
2018 |  | -- | -- |  | -- |  | 1.7 |  | 1.7 |  | -- |  | 1.7
2019 |  | -- | -- |  | -- |  | 1.7 |  | 1.7 |  | -- |  | 1.7
2020 |  | -- | -- |  | -- |  | 1.8 |  | 1.8 |  | -- |  | 1.8
2021 |  | -- | -- |  | -- |  | 1.8 |  | 1.8 |  | -- |  | 1.8
2022 |  | -- | -- |  | -- |  | 1.9 |  | 1.9 |  | -- |  | 1.9
Subtotal |  | 105 | 13.5 |  | -- |  | 27.5 |  | 41 |  | 0.2 |  | 41.2

## Table 23
Annual Funding 1109 ¦ Procurement ¦ Procurement, Marine Corps
Fiscal Year | Quantity |  | BY 1997 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | 2.1 |  | 2.1 |  | -- |  | 2.1
2005 |  | 48 | 4.9 |  | -- |  | -- |  | 4.9 |  | -- |  | 4.9
2006 |  | 20 | 2.6 |  | -- |  | 2.8 |  | 5.4 |  | -- |  | 5.4
2007 |  | -- | -- |  | -- |  | 0.1 |  | 0.1 |  | -- |  | 0.1
2008 |  | -- | -- |  | -- |  | 1.9 |  | 1.9 |  | -- |  | 1.9
2009 |  | -- | -- |  | -- |  | 0.6 |  | 0.6 |  | -- |  | 0.6
2010 |  | 16 | 1.9 |  | -- |  | -- |  | 1.9 |  | -- |  | 1.9
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | 0.1 |  | 0.1 |  | -- |  | 0.1
2013 |  | 3 | 0.2 |  | -- |  | 0.8 |  | 1 |  | -- |  | 1
2014 |  | -- | -- |  | -- |  | 0.2 |  | 0.2 |  | -- |  | 0.2
2015 |  | -- | -- |  | -- |  | 0.9 |  | 0.9 |  | -- |  | 0.9
2016 |  | -- | -- |  | -- |  | 0.4 |  | 0.4 |  | -- |  | 0.4
2017 |  | 18 | 1.4 |  | -- |  | 4.5 |  | 5.9 |  | 0.1 |  | 6
2018 |  | -- | -- |  | -- |  | 1.2 |  | 1.2 |  | -- |  | 1.2
2019 |  | -- | -- |  | -- |  | 1.1 |  | 1.1 |  | -- |  | 1.1
2020 |  | -- | -- |  | -- |  | 1.2 |  | 1.2 |  | -- |  | 1.2
2021 |  | -- | -- |  | -- |  | 1.2 |  | 1.2 |  | -- |  | 1.2
2022 |  | -- | -- |  | -- |  | 1.2 |  | 1.2 |  | -- |  | 1.2
Subtotal |  | 105 | 11 |  | -- |  | 20.3 |  | 31.3 |  | 0.1 |  | 31.4

## Table 24
Annual Funding 3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | 5 | 2.9 |  | -- |  | -- |  | 2.9 |  | -- |  | 2.9
2001 |  | 16 | 4.5 |  | -- |  | -- |  | 4.5 |  | -- |  | 4.5
2002 |  | 28 | 6.7 |  | -- |  | -- |  | 6.7 |  | -- |  | 6.7
2003 |  | 6 | 1 |  | -- |  | 13.8 |  | 14.8 |  | -- |  | 14.8
2004 |  | 88 | 19.1 |  | -- |  | -- |  | 19.1 |  | 0.1 |  | 19.2
2005 |  | 2 | 12.1 |  | -- |  | -- |  | 12.1 |  | 0.1 |  | 12.2
2006 |  | 65 | 13.1 |  | -- |  | -- |  | 13.1 |  | 0.1 |  | 13.2
2007 |  | -- | -- |  | -- |  | 0.7 |  | 0.7 |  | -- |  | 0.7
2008 |  | -- | -- |  | -- |  | 1.1 |  | 1.1 |  | -- |  | 1.1
2009 |  | 2 | 1.7 |  | -- |  | -- |  | 1.7 |  | -- |  | 1.7
2010 |  | 10 | 1.4 |  | -- |  | 4.9 |  | 6.3 |  | 0.5 |  | 6.8
2011 |  | 22 | 10.1 |  | -- |  | 9.9 |  | 20 |  | 0.7 |  | 20.7
2012 |  | 2 | 0.4 |  | -- |  | 11.1 |  | 11.5 |  | 0.1 |  | 11.6
2013 |  | -- | -- |  | -- |  | 10.8 |  | 10.8 |  | -- |  | 10.8
2014 |  | 59 | 5.3 |  | -- |  | 6.9 |  | 12.2 |  | 0.4 |  | 12.6
2015 |  | 91 | 10.7 |  | -- |  | 19.4 |  | 30.1 |  | 0.8 |  | 30.9
Subtotal |  | 396 | 89 |  | -- |  | 78.6 |  | 167.6 |  | 2.8 |  | 170.4

## Table 25
Annual Funding 3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year | Quantity |  | BY 1997 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | 5 | 2.7 |  | -- |  | -- |  | 2.7 |  | -- |  | 2.7
2001 |  | 16 | 4.2 |  | -- |  | -- |  | 4.2 |  | -- |  | 4.2
2002 |  | 28 | 6.1 |  | -- |  | -- |  | 6.1 |  | -- |  | 6.1
2003 |  | 6 | 0.9 |  | -- |  | 12.8 |  | 13.7 |  | -- |  | 13.7
2004 |  | 88 | 17.3 |  | -- |  | -- |  | 17.3 |  | 0.1 |  | 17.4
2005 |  | 2 | 10.7 |  | -- |  | -- |  | 10.7 |  | -- |  | 10.7
2006 |  | 65 | 11.2 |  | -- |  | -- |  | 11.2 |  | 0.1 |  | 11.3
2007 |  | -- | -- |  | -- |  | 0.6 |  | 0.6 |  | -- |  | 0.6
2008 |  | -- | -- |  | -- |  | 0.9 |  | 0.9 |  | -- |  | 0.9
2009 |  | 2 | 1.4 |  | -- |  | -- |  | 1.4 |  | -- |  | 1.4
2010 |  | 10 | 1.1 |  | -- |  | 3.9 |  | 5 |  | 0.4 |  | 5.4
2011 |  | 22 | 7.9 |  | -- |  | 7.8 |  | 15.7 |  | 0.5 |  | 16.2
2012 |  | 2 | 0.3 |  | -- |  | 8.5 |  | 8.8 |  | 0.1 |  | 8.9
2013 |  | -- | -- |  | -- |  | 8.2 |  | 8.2 |  | -- |  | 8.2
2014 |  | 59 | 4 |  | -- |  | 5.1 |  | 9.1 |  | 0.3 |  | 9.4
2015 |  | 91 | 7.9 |  | -- |  | 14.3 |  | 22.2 |  | 0.6 |  | 22.8
Subtotal |  | 396 | 75.7 |  | -- |  | 62.1 |  | 137.8 |  | 2.1 |  | 139.9

## Table 26
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1997 |  | 11 | 0.6 |  | -- |  | -- |  | 0.6 |  | -- |  | 0.6
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1999 |  | 20 | 4.2 |  | -- |  | -- |  | 4.2 |  | -- |  | 4.2
2000 |  | 8 | 0.8 |  | -- |  | -- |  | 0.8 |  | -- |  | 0.8
2001 |  | 13 | 1.1 |  | -- |  | -- |  | 1.1 |  | -- |  | 1.1
2002 |  | 16 | 2.1 |  | -- |  | -- |  | 2.1 |  | -- |  | 2.1
2003 |  | -- | -- |  | -- |  | 5.5 |  | 5.5 |  | -- |  | 5.5
2004 |  | -- | -- |  | -- |  | 19.3 |  | 19.3 |  | -- |  | 19.3
2005 |  | -- | -- |  | -- |  | 7.9 |  | 7.9 |  | -- |  | 7.9
2006 |  | -- | -- |  | -- |  | 2.7 |  | 2.7 |  | -- |  | 2.7
2007 |  | 2 | 0.9 |  | -- |  | -- |  | 0.9 |  | -- |  | 0.9
2008 |  | 1 | 1.8 |  | -- |  | -- |  | 1.8 |  | -- |  | 1.8
2009 |  | 10 | 13.9 |  | -- |  | 11.8 |  | 25.7 |  | 0.4 |  | 26.1
2010 |  | 13 | 4.3 |  | -- |  | 2.7 |  | 7 |  | -- |  | 7
2011 |  | 20 | 7.7 |  | -- |  | 2.8 |  | 10.5 |  | 0.3 |  | 10.8
2012 |  | 10 | 3.9 |  | -- |  | 0.5 |  | 4.4 |  | 0.1 |  | 4.5
2013 |  | 10 | 13 |  | -- |  | -- |  | 13 |  | -- |  | 13
2014 |  | 10 | 5.4 |  | -- |  | 0.2 |  | 5.6 |  | 0.3 |  | 5.9
2015 |  | 2 | 0.7 |  | -- |  | 3.1 |  | 3.8 |  | 0.1 |  | 3.9
2016 |  | 19 | 7.2 |  | -- |  | 6.2 |  | 13.4 |  | 0.3 |  | 13.7
2017 |  | 20 | 7.6 |  | -- |  | 1.8 |  | 9.4 |  | 0.3 |  | 9.7
2018 |  | 6 | 1.7 |  | -- |  | 1 |  | 2.7 |  | 0.2 |  | 2.9
2019 |  | 12 | 3 |  | -- |  | -- |  | 3 |  | 0.1 |  | 3.1
2020 |  | 12 | 3 |  | -- |  | -- |  | 3 |  | 0.2 |  | 3.2
2021 |  | 13 | 3.3 |  | -- |  | -- |  | 3.3 |  | -- |  | 3.3
Subtotal |  | 228 | 86.2 |  | -- |  | 65.5 |  | 151.7 |  | 2.3 |  | 154

## Table 27
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | BY 1997 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1997 |  | 11 | 0.6 |  | -- |  | -- |  | 0.6 |  | -- |  | 0.6
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1999 |  | 20 | 4.1 |  | -- |  | -- |  | 4.1 |  | -- |  | 4.1
2000 |  | 8 | 0.8 |  | -- |  | -- |  | 0.8 |  | -- |  | 0.8
2001 |  | 13 | 1 |  | -- |  | -- |  | 1 |  | -- |  | 1
2002 |  | 16 | 2 |  | -- |  | -- |  | 2 |  | -- |  | 2
2003 |  | -- | -- |  | -- |  | 5 |  | 5 |  | -- |  | 5
2004 |  | -- | -- |  | -- |  | 17.2 |  | 17.2 |  | -- |  | 17.2
2005 |  | -- | -- |  | -- |  | 6.8 |  | 6.8 |  | -- |  | 6.8
2006 |  | -- | -- |  | -- |  | 2.3 |  | 2.3 |  | -- |  | 2.3
2007 |  | 2 | 0.7 |  | -- |  | -- |  | 0.7 |  | -- |  | 0.7
2008 |  | 1 | 1.5 |  | -- |  | -- |  | 1.5 |  | -- |  | 1.5
2009 |  | 10 | 11.1 |  | -- |  | 9.4 |  | 20.5 |  | 0.3 |  | 20.8
2010 |  | 13 | 3.4 |  | -- |  | 2.1 |  | 5.5 |  | -- |  | 5.5
2011 |  | 20 | 5.9 |  | -- |  | 2.2 |  | 8.1 |  | 0.2 |  | 8.3
2012 |  | 10 | 3 |  | -- |  | 0.3 |  | 3.3 |  | 0.1 |  | 3.4
2013 |  | 10 | 9.7 |  | -- |  | -- |  | 9.7 |  | -- |  | 9.7
2014 |  | 10 | 4 |  | -- |  | 0.1 |  | 4.1 |  | 0.3 |  | 4.4
2015 |  | 2 | 0.5 |  | -- |  | 2.2 |  | 2.7 |  | 0.1 |  | 2.8
2016 |  | 19 | 5.2 |  | -- |  | 4.4 |  | 9.6 |  | 0.2 |  | 9.8
2017 |  | 20 | 5.3 |  | -- |  | 1.3 |  | 6.6 |  | 0.2 |  | 6.8
2018 |  | 6 | 1.2 |  | -- |  | 0.7 |  | 1.9 |  | 0.1 |  | 2
2019 |  | 12 | 2 |  | -- |  | -- |  | 2 |  | 0.1 |  | 2.1
2020 |  | 12 | 2 |  | -- |  | -- |  | 2 |  | 0.1 |  | 2.1
2021 |  | 13 | 2.1 |  | -- |  | -- |  | 2.1 |  | -- |  | 2.1
Subtotal |  | 228 | 66.1 |  | -- |  | 54 |  | 120.1 |  | 1.7 |  | 121.8

## Table 28
Annual Funding 0350 ¦ Procurement ¦ National Guard and Reserve Equipment ,Defense
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2011 |  | 172 | 20.3 |  | -- |  | -- |  | 20.3 |  | 2 |  | 22.3
Subtotal |  | 172 | 20.3 |  | -- |  | -- |  | 20.3 |  | 2 |  | 22.3

## Table 29
Annual Funding 0350 ¦ Procurement ¦ National Guard and Reserve Equipment ,Defense
Fiscal Year | Quantity |  | BY 1997 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2011 |  | 172 | 15.7 |  | -- |  | -- |  | 15.7 |  | 1.5 |  | 17.2
Subtotal |  | 172 | 15.7 |  | -- |  | -- |  | 15.7 |  | 1.5 |  | 17.2

## Table 30
Annual Funding 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | -- | -- |  | -- |  | 1.7 |  | 1.7 |  | -- |  | 1.7
2017 |  | -- | -- |  | -- |  | 8 |  | 8 |  | -- |  | 8
2018 |  | -- | -- |  | -- |  | 3.9 |  | 3.9 |  | -- |  | 3.9
2019 |  | -- | -- |  | -- |  | 2.4 |  | 2.4 |  | -- |  | 2.4
Subtotal |  | -- | -- |  | -- |  | 16 |  | 16 |  | -- |  | 16

## Table 31
Annual Funding 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | BY 1997 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | -- | -- |  | -- |  | 1.2 |  | 1.2 |  | -- |  | 1.2
2017 |  | -- | -- |  | -- |  | 5.6 |  | 5.6 |  | -- |  | 5.6
2018 |  | -- | -- |  | -- |  | 2.7 |  | 2.7 |  | -- |  | 2.7
2019 |  | -- | -- |  | -- |  | 1.6 |  | 1.6 |  | -- |  | 1.6
Subtotal |  | -- | -- |  | -- |  | 11.1 |  | 11.1 |  | -- |  | 11.1

## Table 32
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 1997-11-14 | 2006-06-21
Approved Quantity | 500 | 628
Reference | Milestone II ADM | LRIP ADM
Start Year | 1997 | 1997
End Year | 1999 | 2007
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the following:
Milestone II ADM, dated November 11, 1997, approved the GBS Phase II entry into EMD and an LRIP of up to 500 Receive Suites (RS) and 140 shipboard antennas.
A USD(AT&L) ADM, dated June 2006, authorized an LRIP increase of 128 RS to an approved quantity of 628.
On April 13, 2007, the USD(AT&L) signed an ADM that authorized the Joint Program Office to procure Beyond LRIP quantities of RS.

## Table 33
Foreign Military Sales
None
Nuclear Costs
None

## Table 34
Unit Cost
Unit Cost Report
Item |  | BY 1997 $M | BY 1997 $M |  | % Change
|  | Current UCR Baseline (Sep 2006 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 784.8 |  |  | 968.7
Quantity | 1221 |  |  | 2039
Unit Cost | 0.643 |  |  | 0.475 |  | -26.13
Average Procurement Unit Cost
Cost | 361.3 |  |  | 569
Quantity | 1085 |  |  | 1903
Unit Cost | 0.333 |  |  | 0.299 |  | -10.21
Item |  | BY 1997 $M | BY 1997 $M |  | % Change
|  | Original UCR Baseline (Nov 1997 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 451.4 |  |  | 968.7
Quantity | 346 |  |  | 2039
Unit Cost | 1.305 |  |  | 0.475 |  | -63.6
Average Procurement Unit Cost
Cost | 53.9 |  |  | 569
Quantity | 125 |  |  | 1903
Unit Cost | 0.431 |  |  | 0.299 |  | -30.63

## Table 35
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 1997 $M | [5 empty] | TY $M
[8 empty] | PAUC |  |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Nov 1997 |  |  |  |  | 1.305 |  |  |  | 0.431 |  |  | 1.437 |  |  | 0.463
APB as of January 2006 |  |  | Feb 2003 |  |  |  |  | 0.614 |  |  |  | 0.333 |  |  | 0.673 |  |  | 0.38
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | Feb 2003 |  |  |  |  | 0.614 |  |  |  | 0.333 |  |  | 0.673 |  |  | 0.38
Current APB |  |  | Sep 2006 |  |  |  |  | 0.643 |  |  |  | 0.333 |  |  | 0.707 |  |  | 0.38
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 0.468 |  |  |  | 0.291 |  |  | 0.544 |  |  | 0.36
Current Estimate |  |  | Dec 2015 |  |  |  |  | 0.475 |  |  |  | 0.299 |  |  | 0.555 |  |  | 0.372
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [14 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  |  | Oth | Spt |  | Total
1.437 -0.004 -0.974 0.042 0.070 -0.027 0.000 0.011 -0.882 0.555
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [14 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth |  | Spt |  | Total
0.463 0.003 -0.195 0.045 0.040 0.004 0.000 0.012 -0.091 0.372

## Table 36
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone I | N/A | N/A | N/A | N/A
Milestone II | N/A | Dec 1997 | N/A | Nov 1997
Milestone III | N/A | Dec 1999 | N/A | N/A
IOC | N/A | Dec 1999 | N/A | Dec 2003
Total Cost (TY $M) | N/A | 497.1 | N/A | 1131.9
Total Quantity | N/A | 346 | N/A | 2039
PAUC | N/A | 1.437 | N/A | 0.555

## Table 37
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 439.2 | 57.9 | -- | 497.1
Previous Changes
Economic | -14.5 | 6.7 | -- | -7.8
Quantity | -2.7 | 447.1 | -- | 444.4
Schedule | -- | 83.3 | -- | 83.3
Engineering | 65.6 | 83.1 | -- | 148.7
Estimating | -68.2 | -23.6 | -- | -91.8
Other | -- | -- | -- | --
Support | -- | 21.5 | -- | 21.5
Subtotal | -19.8 | 618.1 | -- | 598.3
Current Changes
Economic | 0.2 | -0.4 | -- | -0.2
Quantity | -- | 3.7 | -- | 3.7
Schedule | -- | 2.2 | -- | 2.2
Engineering | -- | -6.1 | -- | -6.1
Estimating | 4.6 | 31.2 | -- | 35.8
Other | -- | -- | -- | --
Support | -- | 1.1 | -- | 1.1
Subtotal | 4.8 | 31.7 | -- | 36.5
Total Changes | -15 | 649.8 | -- | 634.8
CE - Cost Variance | 424.2 | 707.7 | -- | 1131.9
CE - Cost & Funding | 424.2 | 707.7 | -- | 1131.9

## Table 38
Summary BY 1997 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
397.5 53.9 -- 451.4
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -2.6 |  | 370.2 |  | -- |  | 367.6
Schedule |  | -- |  | 64.4 |  | -- |  | 64.4
Engineering |  | 57 |  | 65.9 |  | -- |  | 122.9
Estimating |  | -55.3 |  | -24.8 |  | -- |  | -80.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 17.3 |  | -- |  | 17.3
Subtotal |  | -0.9 |  | 493 |  | -- |  | 492.1
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 2.5 |  | -- |  | 2.5
Schedule |  | -- |  | 1.4 |  | -- |  | 1.4
Engineering |  | -- |  | -4.5 |  | -- |  | -4.5
Estimating |  | 3.1 |  | 21.8 |  | -- |  | 24.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 0.9 |  | -- |  | 0.9
Subtotal |  | 3.1 |  | 22.1 |  | -- |  | 25.2
Total Changes |  | 2.2 |  | 515.1 |  | -- |  | 517.3
CE - Cost Variance |  | 399.7 |  | 569 |  | -- |  | 968.7
CE - Cost & Funding |  | 399.7 |  | 569 |  | -- |  | 968.7
Previous Estimate: December 2014

## Table 39
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A +0.2
Additional funding for Transmission Security upgrades in FY 2017 to FY 2019 (Navy). (Estimating)
+3.3 +4.8
Adjustment for current and prior escalation. (Estimating) -0.2 -0.2
RDT&E Subtotal +3.1 +4.8
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -0.4
Stretch-out of procurement buy profile (FY 2016 - FY 2021) (Navy). (Schedule) 0.0 +0.1
Quantity variance resulting from an increase of 11 receive suites from 217 to 228 (Navy). (Subtotal)
Quantity variance resulting from an increase of 11 receive suites from 217 to 228 (Navy). (Quantity)
+2.1 +3.2
(+1.1) (+1.7)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) (+0.6) (+0.9) Allocation to Engineering resulting from Quantity change. (Engineering) (QR) (+0.6) (+0.9) Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (-0.2) (-0.3)
Quantity variance resulting from an increase of 3 receive suites from 393 to 396 (Air Force). (Subtotal)
Quantity variance resulting from an increase of 3 receive suites from 393 to 396 (Air Force). (Quantity)
+0.6 +0.8
(+0.3) (+0.4)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) (+0.2) (+0.3) Allocation to Engineering resulting from Quantity change. (Engineering) (QR) (+0.2) (+0.3) Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (-0.1) (-0.2)
Quantity variance resulting from an increase of 11 receive suites from 94 to 105 (Marine Corps). (Subtotal)
Quantity variance resulting from an increase of 11 receive suites from 94 to 104 (Marine Corps). (Quantity)
+2.1 +3.0
(+1.1) (+1.6)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) (+0.6) (+0.9) Allocation to Engineering resulting from Quantity change. (Engineering) (QR) (+0.6) (+0.9) Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (-0.2) (-0.4)
Decrease related to removal of the Theatre Injection Point (TIP) (FY2013 - FY2015) (Army). (Engineering)
Decrease in Operational Acceptance activities because of TIP removal (FY 2017) (Army). (Estimating)
Increase for activities leading to Operational Acceptance (FY 2013 - FY 2017) (Air Force). (Estimating)
-5.9 -8.2
-1.7 -2.4
+11.5 +15.7
Funding received for Flyaway costs (FY 2020 - FY 2022) (Marine Corps). (Estimating) +4.8 +7.3
Realignment of appropriation funding in FY 2015 to FY 2021 to align with FY 2017 PB (Navy). (Estimating)
Revised estimating due to lower unit cost per receive suite (FY 2014 - FY 2015) (Air Force). (Estimating)
+1.1 +1.4
-1.4 -1.8

## Table 40
Funds allocated to incorporate hardware and software changes into the production baseline (FY 2017) (Marine Corps). (Estimating)
Re-alignment of funds from Other Procurement Air Force to Space Procurement Air Force in FY 2016 to FY 2017 (Air Force). (Estimating)
Re-alignment of funds from Other Procurement Air Force to Space Procurement Air Force in FY 2016 to FY 2017 (Air Force). (Estimating)
Additional funding for Transmission Security upgrades in FY 2017 to FY 2019 (Air Force). (Estimating)
+1.1 +1.6
-4.3 -6.0
+4.2 +6.0
+6.8 +10.0
Adjustment for current and prior escalation. (Estimating) | 0.2 | 0.3
Adjustment for current and prior escalation. (Support) | 0.1 | 0
Increase in Initial Spares (Marine Corps). (Support) | 0.1 | 0.2
Increase in Initial Spares (Air Force). (Support) | 0.7 | 1
Decrease in Initial Spares (Navy). (Support) | 0 | -0.1
Procurement Subtotal (QR) Quantity Related | 22.1 | 31.7

## Table 41
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: Transportable Ground Receive Suite Production
Contractor: General Dynamics C4 Systems, Inc.
Contractor Location: 400 John Quincy Adams Rd
Taunton, MA 02780-1036
Contract Number: FA8307-11-D-0005
Contract Type: Firm Fixed Price (FFP)
Award Date: August 22, 2011
Definitization Date: August 22, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
8.7 N/A 4 45.7 N/A 283 45.7 45.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to orders placed by all services.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This contract has a $900M ceiling. Current orders total $45.7M. The contract includes pre-negotiated pricing tables that extend through FY 2016. Future contract modifications will extend the pricing tables through FY 2020. The Estimated Price at Completion depends on the future orders placed by all services.

## Table 42
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 136 | 136 | 136 | 100%
Production | 1651 | 1651 | 1903 | 86.76%
Total Program Quantity Delivered | 1787 | 1787 | 2039 | 87.64%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
1131.9
960.1
84.82%
27
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
21
77.78%
1073.2
94.81%
The above data is current as of February 09, 2016.
Total Program Quantity breaks out as follows:
RDT&E:
10 First Generation Units
96 Ground Receive Suites (RS)
27 Shipboard RS
3 Primary Injection Points, two of which included Satellite Broadcast Manager (SBM) Facilities
136 Total RDT&E Quantities
Procurement:
5 Theatre Injection Points 1,898 RS - all variants
1,903 Total Procurement Quantities
2,039 Total Program Quantity (136 RDT&E + 1,903 Procurement)
2,021 = total RSs (96 Ground + 27 Shipboard + 1,898 Procurement)
Quantity to Sustain:
2,039 Total Program Quantity
-10 First Generation Units not used
+2 Original SBMs replaced by Defense Enterprise Computer Center Facilities
-1 Primary Injection Point site decommissioned
-5 Theatre Injection Points no longer used
2,025 Total Quantity to Sustain

## Table 43
Operating and Support Cost
Cost Estimate Details
Date of Estimate: September 25, 2015
Source of Estimate: POE
Quantity to Sustain: 2025
Unit of Measure: Total Quantity
Service Life per Unit: 17.00 Years
Fiscal Years in Service: FY 2014 - FY 2031
Assets include: Broadcast facilities, Receive Suites (RSs), and Primary Injection Points (PIPs). The costs include all the operating, logistics and personnel costs associated with operating the transmit sites.
The September 25, 2015 O&S cost estimate assumes one primary and one secondary broadcast facility located at two Defense Enterprise Computing Centers (DECCs), two PIPs, and a total of 2,021 RSs for all configurations and all services. Sustained assets total 2,025. This varies from the total quantity of the December 2014 SAR for the following reason: decommissioning of five Theatre Injection Points (TIPs) (Army and Air Force Assets), and increase of 25 RS procurements across the services.
The POE costs include the sustainment of the GBS DECCs starting in FY 2014 and were updated to reflect the GBS September 2015 Published Centralized Access for Data Exchange and associated Element of Expense Identification Code/ OSD Cost Element Structure mapping. Significant updates include GBS contractor software maintenance transitioning to Ogden organic support as recommended in the December 2014 Product Support Business Case Analysis, planned PIPs decommissioning in FY 2018, and initiating decommissioning of five TIPs.
Sustainment Strategy
The GBS employs a two-level maintenance concept employing Operational level maintenance by the individual GBS RSs users and normalized organic supply support and Depot repair for stock listed parts for the RS, while the DECC Satellite Broadcast Management (SBM) user equipment is currently fully supported through Contractor Logistics Support (CLS).
Ogden - Air Logistics Center is designated as the software depot, including license renewal, for GBS RS and DECC SBM software. While other major stakeholders for GBS sustainment include: System-level Product Support Management, 50th Space Communications Squadron, and Tobyhanna Army Depot.
Antecedent Information
No Antecedent

## Table 44
Annual O&S Costs BY1997 $M
Cost Element |  | GBS Average Annual Cost Per Total Quantity | [5 empty] | None (Antecedent) N/A
Unit-Level Manpower |  | 5.606 | [5 empty] | 0
Unit Operations |  | 0 | [5 empty] | 0
Maintenance |  | 0.051 | [5 empty] | 0
Sustaining Support |  | 0.847 | [5 empty] | 0
Continuing System Improvements |  | 8.039 | [5 empty] | 0
Indirect Support |  | 0 | [5 empty] | 0
Other |  | 0 | [5 empty] | 0
Total |  | 14.543 | [5 empty] | --
Unit Operations encompasses all operations of the broadcast facilities.
Maintenance includes Depot hardware maintenance activities.
Sustaining Support encompasses sustaining engineering support costs for all GBS assets.
Continuing System Improvements includes organic software maintenance, software license renewals and other support as required.
Item | Total O&S Cost $M
| GBS | [7 empty] | None (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 308.1 |  |  | 338.9 |  |  | 247.2 |  | N/A
Then Year | 382.5 |  |  | N/A |  |  | 393.9 |  | N/A
The current APB dates from February 2003. The APB O&S estimate assumed O&S through FY 2015. The latest OSD inflation indices used for the current estimate indicate a higher rate of inflation than those used for the APB. The current estimate assumes O&S through FY 2031 but also assumes a lower annual cost than the APB. These
factors explain the apparent discongruence between BY$ and TY$ for the O&S costs.
Equation to Translate Annual Cost to Total Cost
Total O&S Costs = average annual cost x assumed life in years = $14.543M x 17 = $247.2M (BY$)
O&S Cost Variance
Category |  |  | BY 1997 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
301.3
Programmatic/Planning Factors -54.1 Transition to Organic Software, PIPs Decommissioning
and TIPs Decommissioning
Cost Estimating Methodology 0.0
Cost Data Update 0.0

## Table 45
Labor Rate | 0
Energy Rate | 0
Technical Input | 0
Other | 0
Total Changes | -54.1
Current Estimate | 247.2
Disposal Estimate Details
Date of Estimate: Source of Estimate:
Disposal/Demilitarization Total Cost (BY 1997 $M):
No disposal estimate at this time.