## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-424
MQ-9 Reaper Unmanned Aircraft System (MQ-9 Reaper)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 9
Schedule 10
Performance 12
Track to Budget 14
Cost and Funding 16
Low Rate Initial Production 27
Foreign Military Sales 28
Nuclear Costs 29
Unit Cost 30
Cost Variance 33
Contracts 37
Deliveries and Expenditures 43
Operating and Support Cost 44

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
MQ-9 Reaper Unmanned Aircraft System (MQ-9 Reaper)
DoD Component
Air Force
Responsible Office
Col William Leister 2640 Loop Road West
Wright-Patterson Air Force Base, OH 45433-7106
william.leister@us.af.mil
Phone: | 937-904-6008
Fax: | 937-904-7099
DSN Phone: | 674-6008
DSN Fax: | 674-7099
Date Assigned: | September 1, 2013
References
SAR Baseline (Production Estimate)
FY 2011 President's Budget dated February 1, 2010
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated December 12, 2012

## Table 6
Mission and Description
Mission:
The MQ-9 Reaper Unmanned Aircraft System (MQ-9 Reaper) is a multi-mission Hunter-Killer and Intelligence, Surveillance and Reconnaissance (ISR) system, which provides the combat commander with a persistent capability to find, fix, track, target, engage and assess Time Sensitive Targets. In the Hunter-Killer mission, the MQ-9 Reaper offers the commander a choice of weapons including the Hellfire Air-to-Ground Missile, Laser Guided Bombs and Joint Direct Attack Munitions. In the ISR role, the MQ-9 Reaper's ability to fly for up to 14 hours at altitudes up to 50,000 feet while carrying up to 3,000 pounds on the wings make it the platform of choice for a number of ISR and strike missions. This ability to support a wide variety of operations results in a steady stream of requirements to develop new capabilities to support an expanding array of missions. As a result of the combat deployment of the developmental system, the MQ-9 Reaper is supported and maintained by Contractor Logistics Support personnel and organic Air Force personnel.
Description:
A MQ-9 Reaper system consists of aircraft, a Ground Control Station (GCS), a Satellite Communications terminal, support equipment, and maintenance and operations personnel deployed for 24-hour operations. The aircraft is controlled by a pilot who is located in a GCS. Control commands are transmitted from the GCS to the aircraft by a ground based datalink terminal. The GCS incorporates workstations that allow operators to plan missions, control and monitor the aircraft, accomplish reconnaissance missions, control weapons and exploit received images. The MQ-9 Reaper carries the Multi- spectral Targeting System which integrates electro-optical, infrared, laser designator, and laser illuminator into a single sensor package. The system is composed of four major components which can be deployed for worldwide operations. The MQ-9 Reaper aircraft can be disassembled and loaded into a container for travel. The GCS is transportable in a C-130 Hercules (or larger) transport aircraft or installed in a fixed facility. The ground data terminal antenna provides line-of-sight communications for takeoff and landing. The satellite communication system provides over-the-horizon control of the aircraft. An alternate method of employment, Remote Split Operations, employs a mobile version of the GCS for launch and recovery efforts. This system conducts takeoff and landing operations at the forward deployed location while the Continental United States based GCS conducts the mission via extended communication links.
In March 2006, the Commander of Air Combat Command directed early fielding to meet operational needs. To meet the early fielding date, the program was broken into two blocks with Block 1 providing initial capability to meet the early fielding date and Block 5 completing the program to the Increment I requirements as described in the CPD. Consequently, the MQ-9 Reaper Increment I program is comprised of Block 1 and Block 5 aircraft. This SAR only includes Increment I
requirements. An MQ-9 Reaper Modernization program is being established in the future to incorporate additional capabilities. The MQ-9 Reaper Modernization program will have separate requirement documents.
The MQ-9 Reaper's combat potential and demonstrated combat performance fueled the rapid growth of the program. The MQ-9 Reaper program was initially managed as a Quick Reaction Capability program, a separate Program Office was established in 2006 to restructure the program to support the Air Combat Command urgent request to field the system. The MQ-9 Reaper has been actively flying combat missions in overseas contingency operations since September 2007.
The program is in concurrent capability development, procurement, combat operations and support. This situation resulted from the MQ-9 Reaper's urgent beginnings in the weeks after September 11, 2001, its growth as a Hunter-Killer to support overseas contingency operations, and the MQ-9 Reaper's evolution into the platform of choice for both ISR and Hunter-Killer missions.

## Table 7
Executive Summary
As of February 2016, the Air Force contracted with General Atomics Aeronautical Systems, Incorporated (GA-ASI) for a total of 263 MQ-9 Reaper Unmanned Aircraft Systems (MQ-9 Reapers). There have been 207 aircraft delivered, which include test and continuation training assets. Additionally, the MQ-9 Reaper has flown over 980,000 cumulative flight hours. This SAR is based on the FY 2017 PB for the MDAP only, which set the total number of MQ-9 Reaper aircraft to 350.
Air Combat Command (ACC) declared IOC for the MQ-9 Reaper on December 21, 2015. The signed memorandum stated the MQ-9 Reaper has met all required IOC capabilities as outlined in the MQ-9 Increment I, CPD.
In 2015, the Program Office (PO) successfully completed the execution of the Extended Range (ER) MQ-9 Reaper. ER provides an extension of range and/or endurance over the current MQ-9 Reaper configuration, which allows for increased time on station and/or mission radius. Air Force Special Operations Command is already using the ER aircraft operationally and has amassed approximately 25,000 flight hours. ACC completed ER Operational Test in September 2015 and approved fielding in November 2015. Based on warfighter requirements, the PO plans to retrofit the entire MQ-9 Reaper fleet with ER capability.
As a result of the April 9, 2014 ACC Acquisition and Sustainment Review, the Air Force Service Acquisition Executive (AFSAE), the Commander of Air Force Materiel Command, and the Commander of ACC directed the PO to develop an acquisition strategy that blends the rigor of a traditional acquisition program with the agility of a Quick Reaction Capability program. The intent of this direction is to enable the team to be even more responsive to rapidly-emerging warfighter requirements. The AFSAE approved the MQ-9 Reaper Hybrid Acquisition Strategy Annex to the MQ-9 Acquisition Strategy on April 6, 2015. The first hybrid procurement (e.g., Release 1) is already underway with the initial Request for Proposal released December 10, 2015, and expected contract award is March 2016.
The Block 50 Ground Control Station (GCS) development program conducted an Integrated Baseline Review (IBR) in August 2015. All actions were successfully completed, and the IBR was closed out in November 2015. The PO is on track to conduct the Preliminary Design Review in June 2016.
The original design of the MQ-9 Reaper Block 1 aircraft electrical system contained a Starter-Generator (S-G) which serves as the primary source of electrical power and a battery power backup system. During the timeframe from April 29, 2013 through December 31, 2015, there have been 96 recorded MQ-9 Reaper S-G failures which have resulted in the loss of 13 aircraft. The MQ-9 Reaper PO, through a Crisis Action Team, completed a root cause investigation. Initial results of the investigation suggested several areas of concern to include manufacturing quality, brushes and brush box alignment, commutator roundness, rotor balance, and Technical Order procedures, all of which have been addressed through changes or procedures to the system. However, to date, no root cause has been found.
The PO has implemented a series of mitigation steps to address the S-G issue. First, to prevent loss of aircraft due to S-G failure, the MQ-9 PO established the Electrical Safety Improvement Program (ESIP) to deliver a kit containing a Direct Drive Brushless Alternator which is a back-up alternator that provides up to 10 hours of MQ-9 Reaper flight time should the S-G fail. To date, 72 ESIP kits have been delivered to the Air Force and 41 have been installed on aircraft. The ESIP kit has successfully provided return-to-base power for 17 aircraft S-G failures. Second, to address manufacturing quality issues, the aircraft Original Equipment Manufacturer (OEM) is in the process of moving the S-G overhaul process to a new maintenance, repair and overhaul facility. Third, GA-ASI has also identified a potential alternate generator and is in the process of adding a second repair source. The PO is in the process of determining if this alternate S-G meets MQ-9 requirements and whether or not it would be a suitable replacement for the legacy OEM’s S-G.
In the December 2014 SAR, the PO had slipped the Follow-on Operational Test and Evaluation (FOT&E) completion date by three months to April 2016 in order to address a High Outside Air Temperature (OAT) issue. The final phase of 904.6 software release completed Developmental Test on February 26, 2015, where the procedural changes addressing the overheating issue were successfully exercised. The final Thermal Management hardware solution, consisting of an internal plenum in the avionics bay, was verified during testing that completed in August 2015. Integrated testing indicated adequate

## Table 8
performance of the key subsystems required for successful Block 5 flight operations in High OAT conditions. Final verified and approved Flight Manual and Checklist documentation was delivered to Operational Test on November 2, 2015. FOT&E start was delayed until January 27, 2016 based on the thermal management mitigations, overlapping test priorities, and limited aircrew availability. A successful Block 5 Operational Test Readiness Review was held on December 3, 2015 where the MQ-9 Block 5 weapon system was certified as ready for FOT&E by the PEO for Intelligence, Surveillance, & Reconnaissance & Special Operations Forces. The PO continues to monitor the schedule closely to ensure it is tracking to complete within the schedule thresholds approved at the December 2013 MQ-9 Configuration Steering Board.
Five FMS Letters of Offer and Acceptance (LOAs) were signed since the 2014 SAR totaling approximately $560M. The French signed an LOA for three MQ-9 Reaper Block 5 aircraft and two Dual Control Mobile Ground Control System GCSs. This will be the third system the French have acquired but the first MQ-9 Reaper Block 5. They also signed an LOA for continued Air Worthiness documentation to support the MQ-9 platform. Spain signed an LOA for four MQ-9 Reaper Block 5 aircraft and two Mobile GCSs. This will be the first MQ-9 Reaper Block 5 acquisition for Spain. Spain also signed an LOA providing funding for Air Worthiness documentation, which was signed, to support the Air Worthiness Certification Spain must provide to their Air Worthiness Authority to fly aircraft in their airspace. Lastly, the United Kingdom signed an LOA to continue CLS support for the MQ-9 Reaper Block 1 platform.
There are no significant software-related issues with this program at this time.

## Table 9
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
The MILCON APPN breach was previously reported in the December 2012 SAR.
The Follow-On Test and Evaluation and FRP schedule breaches were previously reported in the December 2013 SAR.
The Program Office is working to update the APB to clear these breaches.
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 10
Schedule
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B ACAT II | Feb 2004 | Feb 2004 | Feb 2004 | Feb 2004
Milestone C ACAT II Block 1 | Feb 2008 | Feb 2008 | Feb 2008 | Feb 2008
IOT&E for Block 1 | May 2008 | May 2008 | May 2008 | May 2008
RAA | Sep 2010 | Jun 2012 | Jun 2012 | Jun 2012
Milestone C ACAT ID Increment 1, Block 5 | Mar 2011 | Nov 2012 | Nov 2012 | Nov 2012
FOT&E for Increment I Block 5 | Nov 2012 | Nov 2013 | Oct 2014 | Sep 20161
FRP Decision for Increment I Block 1 and 5 | Mar 2013 | Jul 2014 | Jun 2015 | N/A1
1 APB Breach
(Ch-1)
(Ch-2)
Change Explanations
(Ch-1) The current estimate for FOT&E for Increment I Block 5 changed from April 2016 to September 2016 based on thermal management mitigations in work, overlapping test priorities, and limited aircrew availability. The Program Office worked with the test community and the user to address all three of these issues resulting in successful IOC. The Program Office held an Operational Test Readiness Review on December 3, 2015 and received approval from the PEO Intelligence, Surveillance, & Reconnaissance & Special Operations Forces to enter FOT&E. The last test event is projected to be completed in August 2016 with the final test report being delivered by September 30, 2016 which is within the schedule threshold approved at the December 2013 MQ-9 Configuration Steering Board.
(Ch-2) The FRP event changed from TBD to N/A as a result of the August 2013 Air Force Review Board approving the removal of the FRP milestone. The FRP milestone was removed because the program reached maximum production rate in FY 2011; It will be replaced by an In Progress Review. In addition, the program will already have delivered and contracted for the majority of production aircraft at the time of the baselined FRP date.
Notes

## Table 11
RAA includes two fixed GCSs, two mobile GCSs, six PMAI Block 1 aircraft, technical orders, support equipment, initial and readiness spares packages, and logistics support.
The August 2013 Air Force Review Board approved the removal of the FRP milestone and it will be replaced by an In Progress Review. The FRP milestone was removed because the program reached maximum production rate in FY 2011. In addition, the program will already have delivered and contracted for the majority of production aircraft at the time of the baselined FRP date.
Acronyms and Abbreviations
FOT&E - Follow-On Test and Evaluation GCS - Ground Control Station
IOT&E - Initial Operational Test and Evaluation PMAI - Primary Mission Aircraft Inventory
RAA - Required Assets Available

## Table 12
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Hunter
The system’s | The system’s | The system’s | DT ongoing for | The system's capability
capability must allow a | capability must allow a | capability must allow a | KPP; AFOTEC | must allow a targeting
targeting solution at the | targeting solution at a | targeting solution at a | IOT&E did not | solution at a direct
weapon’s maximum | direct attack weapon’s | direct attack weapon’s | evaluate KPP | attack weapon's
range. | maximum range | maximum range | due to system | maximum range.
availability; Full
KPP evaluation
deferred to
future FOT&E
Killer
System must be | System must be | System must be | AFOTEC IOT&E | System must be
capable of computing a | capable of computing | capable of computing a | found KPP | capable of computing a
weapon’s release | a weapon’s release | weapon’s release | operationally | weapon’s release point,
point, passing required | point, passing required | point, passing required | effective and | passing required
information, at the | information, at the | information, at the | suitable | information, at the
required accuracy, to | required accuracy, to | required accuracy, to |  | required accuracy, to
the weapon and | the weapon and | the weapon and |  | the weapon and reliably
reliably releasing the | reliably releasing the | reliably releasing the |  | releasing the weapon
weapon upon | weapon upon | weapon upon |  | upon command.
command. | command. | command.
Net Ready: The system must support Net-Centric military operations. The system must be able to enter and be managed in the network, and exchange data in a secure manner to enhance mission effectiveness. The system must continuously provide survivable, interoperable, secure, and operationally effective information exchanges to enable a Net-Centric military capability.
The System must fully | The System must fully | The System must fully | JITC certified | The System must fully
support execution of all | support execution of all | support execution of | KPP; JITC | support execution of all
operational activities | operational activities | joint critical operational | certification is | operational activities
identified in the | identified in the | activities identified in | renewed for | identified in the
applicable joint and | applicable joint and | the applicable joint and | each software | applicable joint and
system integrated | system integrated | system integrated | update | system integrated
architectures and the | architectures and the | architectures and the |  | architectures and the
system must satisfy | system must satisfy | system must satisfy |  | system must satisfy the
the technical | the technical | the technical |  | technical requirements
requirements for Net- | requirements for Net- | requirements for |  | for Net-Centric military
Centric military | Centric military | transition to Net- |  | operations to include 1)
operations to include 1) | operations to include | Centric military |  | DISR mandated GIG IT
DISR mandated GIG IT | 1) DISR mandated | operations to include 1) |  | standards and profiles
standards and profiles | GIG IT standards and | DISR mandated GIG IT |  | identified in the TV-1, 2)
identified in the TV-1, | profiles identified in the | standards and profiles |  | DISR mandated GIG
2) DISR mandated GIG | TV-1, 2) DISR | identified in the TV-1, |  | KIPs identified in the
KIPs identified in the | mandated GIG KIPs | 2) DISR mandated GIG |  | KIP declaration table, 3)
KIP declaration table, | identified in the KIP | KIPs identified in the |  | NCOW-RM Enterprise

## Table 13
3) NCOW-RM | declaration table, 3) | KIP declaration table, | Services 4) IA
Enterprise Services 4) | NCOW-RM Enterprise | 3) NCOW-RM | requirements including
IA requirements | Services 4) IA | Enterprise Services 4) | availability, integrity,
including availability, | requirements including | IA requirements | authentication, confiden
integrity, authenticat- | availability, integrity, | including availability, | -tiality, and nonrepu-
ion, confidential-ity, and | authenticat-ion, | integrity, authenticat- | diation, and issuance of
nonrepudiat-ion, and | confidential-ity, and | ion, confidential-ity, and | an ATO by the DAA,
issuance of an ATO by | nonrepudiat-ion, and | nonrepudiat-ion, and | and 5) Operationally
the DAA, and 5) | issuance of an ATO by | issuance of an IATO by | effective information
Operationally effective | the DAA, and 5) | the DAA, and 5) | exchanges; and
information exchanges; | Operationally effective | Operationally effective | mission critical
and mission critical | information | information exchanges; | performance and IA
performance and | exchanges; and | and mission critical | attributes, data
information assurance | mission critical | performance and IA | correctness, data
attributes, data | performance and IA | attributes, data | availability, and
correctness, data | attributes, data | correctness, data | consistent data
availability, and | correctness, data | availability, and | processing specified in
consistent data | availability, and | consistent data | the applicable joint and
processing specified in | consistent data | processing specified in | system integrated
the applicable joint and | processing specified in | the applicable joint and | architecture views.
system integrated | the applicable joint and | system integrated
architecture views. | system integrated | architecture views.
architecture views.
Requirements Reference
Capability Production Document (CPD) dated January 29, 2007
Change Explanations
None
Acronyms and Abbreviations
AFOTEC - Air Force Operational Test and Evaluation Center ATO - Approval to Operate
DAA - Designated Approval Authority
DISR - Department of Defense Information Technology Standards Registry DT - Developmental Testing
FOT&E - Follow-On Operational Test and Evaluation GIG - Global Information Grid
IA - Information Assurance
IATO - Interim Approval to Operate
IOT&E - Initial Operational Test and Evaluation IT - Information Technology
JITC - Joint Interoperability Test Command KIP - Key Interface Profile
NCOW-RM - Net-Centric Operations and Warfare Reference Model TV-1 - Technical Standards Profile

## Table 14
Track to Budget
General Notes
Program Element 0205219F includes funds not associated with the MDAP. This report only reflects funds associated with the MDAP.
RDT&E
Appn |  |  | BA | PE
Air Force 3600 07 0205219F
Project | Name
675246 MQ-9 Development and Fielding
675249 (Shared)
Air Force 3600 07 0305205F
Project | Name
674755 (Shared) (Sunk)
Air Force 3600 07 0305219F
Project | Name
675143 PREDATOR (Shared) (Sunk)
Procurement
Appn |  |  | BA | PE
Air Force |  | 3010 07 |  | 0205219F
|  | Line Item |  | Name
|  | 75 |  | Other Production Charges |  | (Shared)
Air Force |  | 3010 06 |  | 0205219F
|  | Line Item |  | Name
|  | 999 |  | Initial Spares |  | (Shared)
Air Force |  | 3010 05 |  | 0305205F
|  | Line Item |  | Name
|  | PRDT01 |  | MQ-1 Mods |  | (Shared) (Sunk)
Air Force |  | 3010 04 |  | 0305205F
|  | Line Item |  |  | Name
|  | PRDTA1 |  | Aircraft Procurement |  | (Shared) (Sunk)
Air Force |  | 3010 04 |  | 0205219F
|  | Line Item |  |  | Name
|  | PRDTB1 |  | MQ-9
Air Force |  | 3010 05 |  | 0205219F
|  | Line Item |  |  | Name
|  | PRDTB2 |  | MQ-9 Mods
MILCON
Appn |  |  | BA | PE

## Table 15
Air Force 3300 01 | 0205219F
Project | Name
BHD000 KWRD143 RKMF113 | MQ-9 Operations RPA Fixed Ground Control Station Facility Add RPA Weapons School Facility | (Sunk) (Sunk)

## Table 16
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2008 $M |  |  |  | BY 2008 $M |  | TY $M
| SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E | 778.8 |  | 1365.1 | 1501.6 |  | 1248.3 |  | 809.9 |  | 1488.8 |  | 1346.8
Procurement | 9824 |  | 10175.3 | 11192.8 |  | 9221.7 |  | 10866 |  | 11765.5 |  | 10591.4
Flyaway | -- |  | -- | -- |  | 6831.6 |  | -- |  | -- |  | 7863.5
Recurring | -- |  | -- | -- |  | 6831.6 |  | -- |  | -- |  | 7863.5
Non Recurring | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support | -- |  | -- | -- |  | 2390.1 |  | -- |  | -- |  | 2727.9
Other Support | -- |  | -- | -- |  | 976.5 |  | -- |  | -- |  | 1129.8
Initial Spares | -- |  | -- | -- |  | 1413.6 |  | -- |  | -- |  | 1598.1
MILCON | 148.5 |  | 53.3 | 58.6 |  | 72.31 |  | 158.9 |  | 55.6 |  | 77.3
Acq O&M | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Total | 10751.3 |  | 11593.7 | N/A |  | 10542.3 |  | 11834.8 |  | 13309.9 |  | 12015.5
1 APB Breach
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The Service Cost Position, signed September 10, 2012, to support the MQ-9 Reaper program Milestone C decision is built upon a product-oriented work breakdown structure, based on historical actual cost information to the maximum extent possible, and based on assumptions that are consistent with actual demonstrated contractor and government performance.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for Major Defense Acquisition Programs (MDAPs). Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.

## Table 17
Total Quantity
Quantity | SAR Baseline Production Estimate | Current APB Production | Current Estimate
RDT&E | 3 | 3 | 3
Procurement | 388 | 401 | 347
Total | 391 | 404 | 350
Quantity Notes
Procurement quantity is the number of MQ-9 Reaper aircraft. Ground Control Stations (GCS) and other equipment costs are included, but not used as a unit of measure.

## Table 18
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 958.7 | 122.7 |  | 115.1 |  | 95.7 |  | 54.6 |  | 0 |  | 0 |  | 0 |  | 1346.8
Procurement | 5710.1 | 945.8 |  | 744.7 |  | 457.5 |  | 509.3 |  | 359.5 |  | 314.8 |  | 1549.7 |  | 10591.4
MILCON | 74.1 | 0 |  | 0 |  | 3.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 77.3
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 6742.9 | 1068.5 |  | 859.8 |  | 556.4 |  | 563.9 |  | 359.5 |  | 314.8 |  | 1549.7 |  | 12015.5
PB 2016 Total | 6817.4 | 1013.1 |  | 1033.3 |  | 1000 |  | 694.6 |  | 387.6 |  | 315.7 |  | 1044.5 |  | 12306.2
Delta | -74.5 | 55.4 |  | -173.5 |  | -443.6 |  | -130.7 |  | -28.1 |  | -0.9 |  | 505.2 |  | -290.7
Funding Notes
"To Complete" procurement costs in the table above primarily include retrofit costs and GCS Block 50 costs.
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 3 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3
Production | 0 |  | 290 |  | 33 | 24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 347
PB 2017 Total | 3 |  | 290 |  | 33 | 24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 350
PB 2016 Total | 3 |  | 284 |  | 29 | 24 | 21 |  | 3 |  | 0 |  | 0 |  | 0 |  | 364
Delta | 0 |  | 6 |  | 4 | 0 | -21 |  | -3 |  | 0 |  | 0 |  | 0 |  | -14

## Table 19
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.8
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.8
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.9
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 56.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.1
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 55.9
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.6
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 102.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 136.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 106.7
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 130.9
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 103.3
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 141.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 122.7
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 115.1
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 95.7
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.6
Subtotal |  | 3 | -- |  | -- |  | -- |  | -- |  | -- |  | 1346.8

## Table 20
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.9
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.4
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.9
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 60.7
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 55.4
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 99.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 129.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 99.5
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 120
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 93.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 126.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 108.2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 99.7
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 81.4
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 45.5
Subtotal |  | 3 | -- |  | -- |  | -- |  | -- |  | -- |  | 1248.3

## Table 21
FY 2002 RDT&E includes $7.8M (TY$) of Defense Emergency Response Funds.

## Table 22
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | 4 | 60.4 |  | -- |  | -- |  | 60.4 |  | -- |  | 60.4
2003 |  | 4 | 36.8 |  | -- |  | -- |  | 36.8 |  | -- |  | 36.8
2004 |  | 5 | 67.7 |  | -- |  | -- |  | 67.7 |  | 2.8 |  | 70.5
2005 |  | 5 | 85.8 |  | 2.2 |  | -- |  | 88 |  | 5.3 |  | 93.3
2006 |  | 2 | 32.2 |  | 33 |  | -- |  | 65.2 |  | 44.7 |  | 109.9
2007 |  | 12 | 109.4 |  | 50.6 |  | -- |  | 160 |  | 151.6 |  | 311.6
2008 |  | 28 | 214.2 |  | 51.7 |  | -- |  | 265.9 |  | 80.5 |  | 346.4
2009 |  | 24 | 212.3 |  | 138.4 |  | -- |  | 350.7 |  | 186.4 |  | 537.1
2010 |  | 24 | 263.8 |  | 24.1 |  | -- |  | 287.9 |  | 245.6 |  | 533.5
2011 |  | 48 | 429.8 |  | 51.9 |  | -- |  | 481.7 |  | 140.3 |  | 622
2012 |  | 48 | 515.4 |  | 177.8 |  | -- |  | 693.2 |  | 211.6 |  | 904.8
2013 |  | 39 | 583.2 |  | 145.4 |  | -- |  | 728.6 |  | 150.5 |  | 879.1
2014 |  | 23 | 292 |  | 68.5 |  | -- |  | 360.5 |  | 143.4 |  | 503.9
2015 |  | 24 | 416.1 |  | 130 |  | -- |  | 546.1 |  | 154.7 |  | 700.8
2016 |  | 33 | 595.9 |  | 134.6 |  | -- |  | 730.5 |  | 215.3 |  | 945.8
2017 |  | 24 | 375.7 |  | 152.8 |  | -- |  | 528.5 |  | 216.2 |  | 744.7
2018 |  | -- | 99.2 |  | 217.4 |  | -- |  | 316.6 |  | 140.9 |  | 457.5
2019 |  | -- | 112.3 |  | 260.8 |  | -- |  | 373.1 |  | 136.2 |  | 509.3
2020 |  | -- | 103.8 |  | 126.3 |  | -- |  | 230.1 |  | 129.4 |  | 359.5
2021 |  | -- | 88.7 |  | 163.5 |  | -- |  | 252.2 |  | 62.6 |  | 314.8
2022 |  | -- | 143.5 |  | 218.2 |  | -- |  | 361.7 |  | 77.4 |  | 439.1
2023 |  | -- | 127.6 |  | 149 |  | -- |  | 276.6 |  | 76.3 |  | 352.9
2024 |  | -- | 160.2 |  | 34.7 |  | -- |  | 194.9 |  | 52.1 |  | 247
2025 |  | -- | 164.9 |  | 8.7 |  | -- |  | 173.6 |  | 45.3 |  | 218.9
2026 |  | -- | 154.2 |  | 8.5 |  | -- |  | 162.7 |  | 42.4 |  | 205.1
2027 |  | -- | 31.5 |  | 5.2 |  | -- |  | 36.7 |  | 6.7 |  | 43.4
2028 |  | -- | 28.8 |  | 4.8 |  | -- |  | 33.6 |  | 9.7 |  | 43.3
Subtotal |  | 347 | 5505.4 |  | 2358.1 |  | -- |  | 7863.5 |  | 2727.9 |  | 10591.4

## Table 23
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | 4 | 68 |  | -- |  | -- |  | 68 |  | -- |  | 68
2003 |  | 4 | 40.8 |  | -- |  | -- |  | 40.8 |  | -- |  | 40.8
2004 |  | 5 | 73.1 |  | -- |  | -- |  | 73.1 |  | 3 |  | 76.1
2005 |  | 5 | 90 |  | 2.3 |  | -- |  | 92.3 |  | 5.5 |  | 97.8
2006 |  | 2 | 32.9 |  | 33.7 |  | -- |  | 66.6 |  | 45.7 |  | 112.3
2007 |  | 12 | 108.9 |  | 50.4 |  | -- |  | 159.3 |  | 150.9 |  | 310.2
2008 |  | 28 | 209.8 |  | 50.6 |  | -- |  | 260.4 |  | 79 |  | 339.4
2009 |  | 24 | 204.6 |  | 133.4 |  | -- |  | 338 |  | 179.6 |  | 517.6
2010 |  | 24 | 249.2 |  | 22.8 |  | -- |  | 272 |  | 232.1 |  | 504.1
2011 |  | 48 | 399.8 |  | 48.3 |  | -- |  | 448.1 |  | 130.5 |  | 578.6
2012 |  | 48 | 472.1 |  | 162.9 |  | -- |  | 635 |  | 193.9 |  | 828.9
2013 |  | 39 | 523.7 |  | 130.7 |  | -- |  | 654.4 |  | 135.1 |  | 789.5
2014 |  | 23 | 258.6 |  | 60.7 |  | -- |  | 319.3 |  | 127 |  | 446.3
2015 |  | 24 | 363.7 |  | 113.6 |  | -- |  | 477.3 |  | 135.2 |  | 612.5
2016 |  | 33 | 511.4 |  | 115.4 |  | -- |  | 626.8 |  | 184.8 |  | 811.6
2017 |  | 24 | 316.3 |  | 128.6 |  | -- |  | 444.9 |  | 182 |  | 626.9
2018 |  | -- | 81.9 |  | 179.5 |  | -- |  | 261.4 |  | 116.4 |  | 377.8
2019 |  | -- | 90.9 |  | 211.1 |  | -- |  | 302 |  | 110.2 |  | 412.2
2020 |  | -- | 82.4 |  | 100.2 |  | -- |  | 182.6 |  | 102.7 |  | 285.3
2021 |  | -- | 69 |  | 127.2 |  | -- |  | 196.2 |  | 48.6 |  | 244.8
2022 |  | -- | 109.4 |  | 166.4 |  | -- |  | 275.8 |  | 59 |  | 334.8
2023 |  | -- | 95.4 |  | 111.5 |  | -- |  | 206.9 |  | 57 |  | 263.9
2024 |  | -- | 117.4 |  | 25.4 |  | -- |  | 142.8 |  | 38.3 |  | 181.1
2025 |  | -- | 118.5 |  | 6.3 |  | -- |  | 124.8 |  | 32.6 |  | 157.4
2026 |  | -- | 108.7 |  | 6 |  | -- |  | 114.7 |  | 29.8 |  | 144.5
2027 |  | -- | 21.7 |  | 3.6 |  | -- |  | 25.3 |  | 4.7 |  | 30
2028 |  | -- | 19.5 |  | 3.3 |  | -- |  | 22.8 |  | 6.5 |  | 29.3
Subtotal |  | 347 | 4837.7 |  | 1993.9 |  | -- |  | 6831.6 |  | 2390.1 |  | 9221.7

## Table 24
FY 2002 Procurement includes $29.1M (TY$) of Defense Emergency Response Funds.
End Item Recurring Flyaway related costs include aircraft, Multi-spectral Targeting System-B (MTS-B) and government furnished equipment, as well as retrofit costs associated with aircraft and MTS-B.
Non End Item Recurring Flyaway costs include retrofit, GCS and communications. Retrofits include GCS and other miscellaneous communications and sensor retrofits.
Cost Quantity Information 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2008 $M
2002 | 4 | 81.1
2003 | 4 | 44.6
2004 | 5 | 90.1
2005 | 5 | 106.8
2006 | 2 | 39.7
2007 | 12 | 163.5
2008 | 28 | 315.8
2009 | 24 | 281
2010 | 24 | 299.8
2011 | 48 | 558.5
2012 | 48 | 589
2013 | 39 | 636.7
2014 | 23 | 363.1
2015 | 24 | 385.8
2016 | 33 | 543.7
2017 | 24 | 338.5
2018 | -- | --
2019 | -- | --
2020 | -- | --
2021 | -- | --
2022 | -- | --
2023 | -- | --
2024 | -- | --
2025 | -- | --
2026 | -- | --
2027 | -- | --
2028 | -- | --
Subtotal | 347 | 4837.7

## Table 25
Annual Funding 3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | TY $M
Total Program
2009 44.5
2010 2.7
2011 8.4
2012 --
2013 --
2014 18.5
2015 --
2016 --
2017 --
2018 3.2
Subtotal 77.3

## Table 26
Annual Funding 3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | BY 2008 $M
Total Program
2009 43.0
2010 2.6
2011 7.8
2012 --
2013 --
2014 16.3
2015 --
2016 --
2017 --
2018 2.6
Subtotal 72.3

## Table 27
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2012-11-21 | 2012-11-21
Approved Quantity | 48 | 62
Reference | Milestone C ADM | Milestone C ADM
Start Year | 2013 | 2013
End Year | 2014 | 2014
The Current Total LRIP Quantity is more than 10% of the total production quantity due to Congressional approval to procure 39 Block 5 aircraft in FY 2013 and 23 in FY 2014. The change from the initial LRIP quantity to current LRIP quantity is due to 14 aircraft added to the FY 2013 and FY 2014 profile; eight aircraft added by Congress in FY 2014 and approval to purchase six additional aircraft based on budget.
The MQ-9 Reaper program was broken into two blocks; Block 1 aircraft, providing initial capability to meet the early fielding directed by Congress, and Block 5 aircraft which provides additional power, a redesigned avionics bay, and encrypted communications. The program procured 195 Block 1 aircraft prior to the planned procurement of 155 Block 5 aircraft starting in FY 2013. The LRIP quantities reported in the table above reflect the procurement of Block 5 aircraft only.

## Table 28
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Spain | 2015-12-21 | 4 | 168.3 | FMS case SP-D-SAA provides funding for four MQ- 9 Reaper Block 5 aircraft, two Mobile Ground Control Stations (MGCS), various support equipment, and Contractor Logistics Support (CLS).
Spain | 2015-12-21 | 0 | 5.8 | FMS case SP-D-GAI provides funding for studies and site surveys for airworthiness certifications.
France | 2015-12-07 | 3 | 116.6 | FMS case FR-D-SAC provides funding for three MQ-9 Block 5 aircraft, two MGCS, and assorted support equipment.
France | 2015-12-07 | 0 | 5.7 | FMS case FR-D-GAI provides funding for technical assistance support of the MQ-9 Reaper Block 5 aircraft, for Tech Assistance support, and for airworthiness certifications.
United Kingdom | 2015-11-12 | 0 | 63.5 | FMS case UK-D-QBQ provides funding for CLS.
United Kingdom | 2014-12-10 | 0 | 64.1 | FMS case UK-D-GAY provides funding for CLS.
Netherlands | 2014-09-30 | 0 | 3.1 | FMS case NE-D-GAO provides funding for airworthiness certification as well as a site survey.
Germany | 2013-12-26 | 0 | 1 | FMS case GY-D-GAX provides funding for airworthiness documents, manpower, and travel.
France | 2013-08-09 | 3 | 340.5 | FMS case FR-D-STE provides funding for the purchase of three aircraft, one MGCS, CLS, and support equipment.
United Kingdom | 2011-11-10 | 5 | 70.1 | FMS case UK-D-SMK provides funding for the purchase of five aircraft, four MGCSs, and assorted sensors and support equipment.
Italy | 2008-11-20 | 6 | 181.5 | FMS case IT-D-SAG provides funding for the purchase of six aircraft, three MGCSs, CLS, and assorted support equipment.
United Kingdom | 2007-10-04 | 4 | 69.1 | FMS case UK-D-SMJ provides funding for the purchase of four aircraft, one MGCS, and spares.
United Kingdom | 2007-02-14 | 2 | 374.9 | FMS case UK-D-SMI provides funding for the purchase of two aircraft, two MGCSs, CLS, and assorted support equipment.
Notes

## Table 29
Nuclear Costs
None

## Table 30
Unit Cost
Unit Cost Report
Item |  | BY 2008 $M | BY 2008 $M |  | % Change
|  | Current UCR Baseline (Dec 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 11593.7 |  |  | 10542.3
Quantity | 404 |  |  | 350
Unit Cost | 28.697 |  |  | 30.121 |  | 4.96
Average Procurement Unit Cost
Cost | 10175.3 |  |  | 9221.7
Quantity | 401 |  |  | 347
Unit Cost | 25.375 |  |  | 26.576 |  | 4.73
Item |  | BY 2008 $M | BY 2008 $M |  | % Change
|  | Original UCR Baseline (Feb 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 11541.3 |  |  | 10542.3
Quantity | 404 |  |  | 350
Unit Cost | 28.568 |  |  | 30.121 |  | 5.44
Average Procurement Unit Cost
Cost | 10402.1 |  |  | 9221.7
Quantity | 401 |  |  | 347
Unit Cost | 25.94 |  |  | 26.576 |  | 2.45
The FY 2017 PB reduced the number of aircraft from the baselined 404 to 350. The aircraft reduction was the primary driver of unit cost growth in both the PAUC and APUC.

## Table 31
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2008 $M | [5 empty] | TY $M
[8 empty] | PAUC |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  |  | Feb 2012 |  |  |  |  | 28.568 |  |  |  | 25.94 |  |  | 32.396 |  |  | 29.604
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | Feb 2012 |  |  |  |  | 28.568 |  |  |  | 25.94 |  |  | 32.396 |  |  | 29.604
Current APB |  |  | Dec 2012 |  |  |  |  | 28.697 |  |  |  | 25.375 |  |  | 32.945 |  |  | 29.34
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 29.614 |  |  |  | 26.225 |  |  | 33.808 |  |  | 30.163
Current Estimate |  |  | Dec 2015 |  |  |  |  | 30.121 |  |  |  | 26.576 |  |  | 34.33 |  |  | 30.523
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Production Estimate | Changes | [14 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth |  | Spt |  | Total
30.268 0.279 1.517 0.225 3.024 -3.155 0.000 2.172 4.062 34.330
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Production Estimate | Changes | [14 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth |  | Spt |  | Total
28.005 0.302 1.263 0.199 1.514 -3.041 0.000 2.281 2.518 30.523

## Table 32
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | N/A | Feb 2004 | Feb 2004
Milestone C | N/A | N/A | Feb 2008 | Feb 2008
IOC | N/A | N/A | Sep 2010 | Jun 2012
Total Cost (TY $M) | N/A | N/A | 11834.8 | 12015.5
Total Quantity | N/A | N/A | 391 | 350
PAUC | N/A | N/A | 30.268 | 34.33
The Milestone C schedule event above reflects the ACAT II Block 1 Milestone C decision. On November 21, 2012 the USD (AT&L) signed an ADM approving the ACAT ID Increment 1, Block 5 Milestone C and delegating MDA to the Air Force.
Milestone Required Assets Available is used in lieu of IOC and was completed on June 30, 2012.

## Table 33
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 809.9 | 10866 | 158.9 | 11834.8
Previous Changes
Economic | -7.4 | 156.9 | 4.3 | 153.8
Quantity | -- | -474.3 | -- | -474.3
Schedule | -- | 60.6 | -- | 60.6
Engineering | 530.1 | 414.3 | 3.2 | 947.6
Estimating | 38.9 | -1049.4 | -89.1 | -1099.6
Other | -- | -- | -- | --
Support | -31.3 | 914.6 | -- | 883.3
Subtotal | 530.3 | 22.7 | -81.6 | 471.4
Current Changes
Economic | -4 | -52 | -0.1 | -56.1
Quantity | -- | -235.6 | -- | -235.6
Schedule | 9.5 | 8.5 | -- | 18
Engineering | -- | 110.9 | -- | 110.9
Estimating | 1.1 | -6 | 0.1 | -4.8
Other | -- | -- | -- | --
Support | -- | -123.1 | -- | -123.1
Subtotal | 6.6 | -297.3 | -- | -290.7
Total Changes | 536.9 | -274.6 | -81.6 | 180.7
CE - Cost Variance | 1346.8 | 10591.4 | 77.3 | 12015.5
CE - Cost & Funding | 1346.8 | 10591.4 | 77.3 | 12015.5

## Table 34
Summary BY 2008 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 778.8 | 9824 | 148.5 | 10751.3
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -347.7 | -- | -347.7
Schedule | -- | -6.4 | -- | -6.4
Engineering | 457.5 | 289.4 | 2.7 | 749.6
Estimating | 31.1 | -1022.9 | -78.9 | -1070.7
Other | -- | -- | -- | --
Support | -27.3 | 730.8 | -- | 703.5
Subtotal | 461.3 | -356.8 | -76.2 | 28.3
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -193.7 | -- | -193.7
Schedule | 7.4 | 15.2 | -0.1 | 22.5
Engineering | -- | 49.6 | -- | 49.6
Estimating | 0.8 | 9.4 | 0.1 | 10.3
Other | -- | -- | -- | --
Support | -- | -126 | -- | -126
Subtotal | 8.2 | -245.5 | -- | -237.3
Total Changes | 469.5 | -602.3 | -76.2 | -209
CE - Cost Variance | 1248.3 | 9221.7 | 72.3 | 10542.3
CE - Cost & Funding | 1248.3 | 9221.7 | 72.3 | 10542.3
Previous Estimate: December 2014

## Table 35
RDT&E | $M
Current Change Explanations | Base Year |  | Then Year
Revised escalation indices. (Economic) N/A -4.0
Adjustment for current and prior escalation. (Estimating) +1.8 +2.0
Schedule delays due to Air Force funding adjustments in FY 2014 and FY 2015 which resulted in the inability to begin Multi-Transit Operations development and delayed initial design reviews of Ground Control Station (GCS) Block 50 Development. (Schedule)
Schedule adjustment due to Air Force funding adjustments which will enable the ramp up of Technology Maturity efforts for Hybrid Release 1. (Schedule)
-7.0 -7.8
+14.4 +17.3
Revised estimate due to OSD levied funding adjustment in FY 2016. (Estimating) |  | -0.7 |  | -0.7
Revised estimate due to the removal of funds for the MQ-9 Reaper Modernization Program. (Estimating) |  | -0.3 |  | -0.2
RDT&E Subtotal |  | 8.2 |  | 6.6
Procurement | $M
Current Change Explanations | Base Year |  | Then Year
Revised escalation indices. (Economic) N/A -52.0
Adjustment for current and prior escalation. (Estimating) +12.5 +14.4
Quantity variance resulting from a decrease of 14 MQ-9 Reapers from 361 to 347. (Quantity)
Acceleration of procurement buy profile from FY 2018 and FY 2019 to FY 2013 and FY 2014; primarily due to the movement of six aircraft (three in each affected year) . (Schedule)
Additional schedule variance due to delays in the Block 50 GCS production program from FY 2016 to FY 2018. (Schedule)
Revised estimate due to the removal of funds for the MQ-9 Reaper Modernization Program. (Estimating)
-193.7 -235.6
0.0 -9.9
+15.2 +18.4
-31.9 -53.4
Revised estimate due to addition of Overseas Contingency Operations for six additional GCSs in support of Government Owned Contractor Operated stand-up. (Estimating) | 28.8 |  | 33
Additional funding for 21 Block 50 GCSs requirements. (Engineering) | 49.6 |  | 110.9
Adjustment for current and prior escalation. (Support) | 4.5 |  | 4.9
Decrease in Other Support due to decrease in production line shut down estimated cost. | -46.6 |  | -42.4
(Support)
Decrease Initial Spares resulting from a decrease of 14 aircraft. (Support) (QR) | -83.9 |  | -85.6
Procurement Subtotal | -245.5 |  | -297.3
(QR) Quantity Related
MILCON | $M
Current Change Explanations | Base Year |  | Then Year
Revised escalation indices. (Economic) | N/A |  | -0.1
Adjustment for current and prior escalation. (Estimating) | 0.1 |  | 0.1
Revised estimate as a result of a delay in required storage facility for Block 50 GCS. | -0.1 |  | 0

## Table 36
(Schedule)
MILCON Subtotal 0.0 0.0

## Table 37
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: MQ-9 System Development and Demonstration Bridge DO 49
Contractor: General Atomics Aeronautical Systems, INC.
Contractor Location: 14200 Kirkham Way
Poway, CA 92064
Contract Number: FA8620-05-G-3028/49 Contract Type: Cost Plus Incentive Fee (CPIF) Award Date: July 17, 2009
Definitization Date: July 17, 2009
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
39.3 N/A N/A 107.5 N/A N/A 157.5 157.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract overruns, rebaselining and contract modifications.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/29/2016) -42.2 -0.9
Previous Cumulative Variances -34.6 -4.4
Net Change -7.6 +3.5
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to unplanned/unscheduled on-wing certification events and test and evaluation support to incorporate software change requests. Unrecoverable cost variances have been captured in three overrun modifications totaling $46.8M. They were awarded in November 2011 for $5.9M, February 2014 for $12.1M, and October 2014 for $28.8M. Total contract variance to date is $-42.2M.
The favorable net change in the schedule variance is due to completion of contract events. Development testing has completed and Follow-On Test & Evaluation (FOT&E) began January 27, 2016.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 38
Contract Identification
Appropriation: Procurement
Contract Name: MQ-9 CY11 Spares & Support Equipment
Contractor: General Atomics Aeronautical Systems, INC.
Contractor Location: 14200 Kirkham Way
Poway, CA 92064
Contract Number: FA8620-10-G-3038/1
Contract Type: Firm Fixed Price (FFP)
Award Date: July 12, 2012
Definitization Date: July 12, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
120.6 N/A N/A 138.6 N/A N/A 138.6 138.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to engineering change orders and contract modifications.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 39
Contract Identification
Appropriation: Procurement
Contract Name: Block 30 GCS Retrofit
Contractor: General Atomics Aeronautical Systems, INC.
Contractor Location: 14200 Kirkham Way
Poway, CA 92064
Contract Number: FA8620-10-G-3038/14 Contract Type: Cost Plus Incentive Fee (CPIF) Award Date: September 29, 2011
Definitization Date: September 29, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
65.0 N/A N/A 65.7 N/A N/A 64.7 64.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to engineering change orders and contract modifications.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/29/2016) +1.5 -1.5
Previous Cumulative Variances +4.7 -0.5
Net Change -3.2 -1.0
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to a quality configuration issue with the sizing of the display monitor; a corrective action plan was implemented and closed in October 2015. Contract is expected to complete with an underrun.
The unfavorable net change in the schedule variance is due to a quality configuration issue with sizing of the display monitor which is preventing the production orders from closing. A contract modification is expected to extend the period of performance to September 2016.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 40
Contract Identification
Appropriation: Procurement
Contract Name: FY13 MQ-9 Reaper Production
Contractor: General Atomics Aeronautical Systems, INC.
Contractor Location: 14200 Kirkham Way
Poway, CA 92064
Contract Number: FA8620-10-G-3038/50
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: October 15, 2013
Definitization Date: December 12, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
213.8 233.4 24 213.8 233.4 24 214.4 215.6
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/29/2016) -4.7 -1.1
Previous Cumulative Variances +4.5 +8.9
Net Change -9.2 -10.0
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to material dollars that have come in for partial bomb racks but credit will not be claimed until the entire unit is received. No impact expected to delivery schedule.
The unfavorable net change in the schedule variance is due to Government directed reprioritization of labor to accelerate the Electrical Safety Improvement Program kit production ahead of the MQ-9 Reaper Block 5 aircraft production.

## Table 41
Contract Identification
Appropriation: Procurement
Contract Name: FY14 MQ-9 Reaper Production
Contractor: General Atomics Aeronautical Systems, INC.
Contractor Location: 14200 Kirkham Way
Poway, CA 92064
Contract Number: FA8620-10-G-3038/77
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: February 04, 2015
Definitization Date: February 04, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
221.0 237.1 24 292.9 313.4 32 293.1 292.9
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to an additional eight aircraft being added to the contract in May 2015.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/29/2016) +2.3 +10.5
Previous Cumulative Variances 0.0 0.0
Net Change +2.3 +10.5
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to savings in program management due to a slower ramp up in staffing than anticipated.
The favorable cumulative schedule variance is due to the early distribution of seven engines. There is no expected impact to the overall delivery schedule.

## Table 42
Contract Identification
Appropriation: RDT&E
Contract Name: BLK 50 GCS Development (DO 89)
Contractor: General Atomics Aeronautical Systems, INC.
Contractor Location: 14200 Kirkham Way
Poway, CA 92064
Contract Number: FA8620-10-G-3038/89
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: April 10, 2014
Definitization Date: April 10, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
141.4 N/A 7 141.4 N/A 7 206.2 209.2
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/29/2016) -0.1 +1.0
Previous Cumulative Variances -- --
Net Change -0.1 +1.0
Cost and Schedule Variance Explanations
The unfavorable cumulative cost variance is due to the delayed start in program execution. The replanned discrete tasks commenced in November 2015 and no additional overrun is projected at this time.
The favorable cumulative schedule variance is due to the program being ahead of schedule on several key tasks to complete Preliminary Design Review (PDR) two months early.
General Contract Variance Explanation
Block 50 Ground Control Station development program conducted an Integrated Baseline Review (IBR) of the program in August 2015. All actions related to the IBR have been successfully closed and the program is executing to an approved baseline. As part of the IBR closure the contractor submitted an Over Target Baseline of $65M and a Period of Performance extension of approximately 38 months.
Notes
This is the first time this contract is being reported.

## Table 43
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 3 | 3 | 3 | 100%
Production | 214 | 204 | 347 | 58.79%
Total Program Quantity Delivered | 217 | 207 | 350 | 59.14%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
12015.5
4727.3
39.34%
27
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
15
55.56%
7811.4
65.01%
The above data is current as of February 10, 2016.
Ten aircraft have been conditionally accepted. Actual aircraft deliveries are less than planned due to contractor manpower issues for aircraft integration, as well as Secure Triple-Link Modem Assembly (STMA) diminishing manufacturing sources & material shortages (DMSMS). In order to facilitate these deliveries, the Government supplied STMAs via Government Furnished Equipment (GFE). This GFE solution is a temporary fix until a new Generation 3 STMA is fully qualified which is anticipated for February 2016. Further aircraft deliveries are pending fielding of operational flight program software and the qualification of the Generation 3 STMA.

## Table 44
Operating and Support Cost
Cost Estimate Details
Date of Estimate: November 24, 2015
Source of Estimate: POE
Quantity to Sustain: 350
Unit of Measure: Aircraft
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2002 - FY 2044
The O&S costs are from the current POE which is based on historical costs and estimated future costs through 2044. The O&S estimate includes all CAPE elements as detailed in the table on the following page. The MQ-9 Reaper has been flying operations since 2006.
Historical costs are obtained from monthly Contractor Logistics Support (CLS) cost reports, Air Force Total Ownership Cost (AFTOC) actuals, and other data sources. Future costs are based on flying hour projections, manpower projections, number of operating locations, and applicable rates and factors. Flying hours are based on the number of anticipated Combat Air Patrols (CAPs). The total MQ-9 Reaper life cycle flying hours are based on the Air Combat Command (ACC) MQ-9 Reaper standup plan, ACC projected flight hours per CAP, and the defined MQ-9 Reaper life cycle. The attrition rate is based upon the official Air Force Studies and Analysis MQ-9 Reaper attrition model. Quantity of aircraft per CAP will continue to vary based on mission requirements and future operations.
Unit-Level Manpower costs are estimated using manpower projections. Unit Operations cost factors include fuel, training munitions, and temporary duty costs. Maintenance costs include Operational-level, Depot-level (D-level), and Government Furnished Equipment repair. Sustaining support includes D-level sustaining engineering and program management and system specific training derived from actual costs from the AFTOC database, and converted to a cost per flying hour. Continuing System Improvements costs include Reliability & Maintainability Enhancements and Software Maintenance supported via the CLS contract. Indirect Support costs are based on factors from Air Force Instruction 65- 503 table A56-1, which were applied against manpower projections.
Sustainment Strategy
Sustainment of the MQ-9 Reaper systems is currently provided through CLS contracts with General Atomics, Aeronautical Systems Incorporated (GA-ASI), and Raytheon. The CLS contracts include program management, logistics support, configuration management, technical manuals, software maintenance, engineering technical services, contractor field service representative support, contractor inventory control point, spares management, depot repair, flight operations support, reliability and maintainability studies, maintenance data collection/entry and depot field maintenance. Supported organizations include ACC, Air National Guard, Air Force Special Operations Command, Air Education and Training Command. The Program Office (PO) is working to transition portions of CLS to a Public Private Partnership that leverages original equipment manufacturer and organic capabilities. Currently, the Air Force Sustainment Center has entered into a Public Private Partnership Agreement with GA-ASI and the Fleet Readiness Center-Southeast has entered into a Public Private Partnership Agreement with Raytheon for depot repair on certain components for the MQ-9
Reapers and Multi-Spectral Targeting System, respectively.
Antecedent Information
The antecedent program for the MQ-9 Reaper is the MQ-1 Predator. The MQ-1 Predator O&S costs are based on the current POE which utilizes the same methodology as the MQ-9 Reaper O&S estimate. The MQ-1 Predator O&S costs

## Table 45
are based on 268 aircraft and a service life of 21 years, with a planned divestiture of the program within the FYDP.
The MQ-1 Predator total BY 2008 O&S figure may be computed by multiplying the average cost per flying hour for each cost element category (totaling $3.523K) by the total flying hours of the MQ-1 Predator program (2,025,397). The total MQ
-1 Predator O&S figure increased from the figure reported in the December 2014 SAR due to the extension of the planned divestiture of the MQ-1 Predator to within the current FYDP. From a cost per flying hour perspective the MQ-9 Reaper's costs vary slightly from its antecedent program, the MQ-1 Predator.
Annual O&S Costs BY2008 $M
Cost Element |  | MQ-9 Reaper Average Annual Cost Per Aircraft | [5 empty] | MQ-1 Predator (Antecedent) Avg Annual Cost Per Aircraft
Unit-Level Manpower |  | 1.588 | [5 empty] | 0.409
Unit Operations |  | 0.325 | [5 empty] | 0.291
Maintenance |  | 1.262 | [5 empty] | 0.413
Sustaining Support |  | 1.398 | [5 empty] | 0.027
Continuing System Improvements |  | 0.161 | [5 empty] | 0.119
Indirect Support |  | 0.696 | [5 empty] | 0.071
Other |  | 0 | [5 empty] | 0
Total |  | 5.43 | [5 empty] | 1.33
The average cost per flying hour for a MQ-9 Reaper is $3.538K. The flying hour projection is based on the updated flying hour profile received from ACC. The PO utilized a bottoms-up cost estimating approach to estimate the MQ-9 Reaper life cycle cost.
Item | Total O&S Cost $M
| MQ-9 Reaper | [7 empty] | MQ-1 Predator (Antecedent)
| Current Production APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 47215.4 |  |  | 51936.9 |  |  | 38011 |  | 7135.5
Then Year | 65058.9 |  |  | N/A |  |  | 54763.5 |  | N/A
The total O&S cost was derived through: i) analysis of manpower projections, and ii) actual historical data and estimated out year data. The total O&S costs do not include disposal costs.
Equation to Translate Annual Cost to Total Cost
The average annual cost per aircraft is derived by dividing the total life cycle cost by the number of aircraft and number of years the program is in operation. $38,011.0M (BY life cycle cost) / 350 (total aircraft) / 20 (years in operation) = $5.43M
O&S Cost Variance
Category |  |  | BY 2008 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
41626
Programmatic/Planning Factors 0.0
Cost Estimating Methodology -3615.0 Revised flying hour calculation methodology, resulting in a
decrease of projected flying hours.

## Table 46
Cost Data Update | 0
Labor Rate | 0
Energy Rate | 0
Technical Input | 0
Other | 0
Total Changes | -3615
Current Estimate | 38011
Disposal Estimate Details
Date of Estimate: November 24, 2015
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2008 $M): Total costs for disposal of all Aircraft are 19.2
The MQ-9 Reaper disposal cost estimate is based on the current POE and assumes cold storage. The estimate utilizes various factors such as aircraft quantity and weights to calculate shipping costs, demolition costs, and disposal of hazardous materials.