## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-439
Small Diameter Bomb Increment II (SDB II)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 9
Schedule 10
Performance 12
Track to Budget 18
Cost and Funding 19
Low Rate Initial Production 31
Foreign Military Sales 32
Nuclear Costs 32
Unit Cost 33
Cost Variance 36
Contracts 39
Deliveries and Expenditures 40
Operating and Support Cost 41

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Small Diameter Bomb Increment II (SDB II)
DoD Component
Air Force
Joint Participants
Department of the Navy
Responsible Office
Col Kevin Hickman 102 West D Ave
Eglin Air Force Base, FL 32542
kevin.hickman@us.af.mil
Phone: | 850-883-2881
Fax: | 850-882-2438
DSN Phone: | 875-2881
DSN Fax: | 872-2438
Date Assigned: | June 16, 2014
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated September 23, 2015
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated September 23, 2015

## Table 6
Mission and Description
Small Diameter Bomb Increment II (SDB II) is a joint interest United States Air Force (USAF) and Department of the Navy (DoN) ACAT ID program, with the USAF as the lead service. SDB II provides the warfighter the capability to attack mobile targets from stand-off, through weather. The threshold aircraft for the USAF is the F-15E and the threshold aircraft for the DoN are the F-35B and F-35C. Objective aircraft include the F-16, F/A-18E/F, F-22A, F-35A, B-1B, B-2, B-52, A-10, MQ-9, and AC-130. SDB II will be compatible with the Bomb Rack Unit (BRU-61/A) and the Joint Miniature Munitions BRU (BRU- 61A/A) miniature munitions carriages, the CNU-660/E carriage system, the Common Munitions Bit and Reprogramming Equipment and the Joint Mission Planning System. The SDB II Program will develop and field a single-weapon USAF storage container and a dual DoN weapon storage container.

## Table 7
Executive Summary
Since the last exception SAR, the program completed Captive Flight Test “Hybrid” and all return-to-flight activities following the Live Fire (LF)-5 failure investigation. On September 15, 2015, the program office executed the LF-5 flight test. The weapon experienced an anomaly immediately prior to weapon release and failed to arm. The weapon directly impacted the target but did not detonate. Due to a lack of telemetry data, because live fire test assets are not equipped with telemetry, the failure investigation did not identify a root cause. However, the investigation identified potential failure modes. Corrective actions were developed, verified and implemented prior to returning to flight.
On November 16, 2015, the latest version of SDB II Operational Flight Profile software was released. This software supports the Normal Attack and Coordinate Attack (CA) test events required to occur prior to the start of the 28-shot Government Confidence Test effort. The next release of software will support the first Laser Illuminated Attack (LIA) test event which is currently projected to occur the 3rd Quarter FY 2016. SDB II remains an events-based program.
In January 12, 2016 the SDB II program executed Guided Test Vehicle (GTV)-11 Flight Test. The weapon released nominally but did not impact the intended target. This was the first use of the new Build 6 Software. The Failure Review Board has identified the most likely root cause and was able to replicate the failure in the Computer in the Loop lab. Corrective actions are in work. The next drop of Build 6 software is projected for March 2016. This will support a return to flight with GTV-11a, CA, and LIA GTV shots currently projected for April 2016.
Implementation of high temperature sulfuric acid corrosive atmosphere corrective actions is on-going. Full qualification test is expected to complete by the 3rd Quarter FY 2016. The Lot 2 contract option award is dependent on completion of the full qualification test.
There are no significant software-related issues with this program at this time.
History of Significant Developments since Program Initiation
July 28, 2009: The JROC approved the SDB II CDD.
August 6, 2010: The DAE signed an ADM authorizing the program to enter the EMD phase and certified the program pursuant to section 2366b of title 10, U.S. Code.
October 8, 2010: The DAE signed the Milestone (MS) B APB.
January 20, 2011: Conducted the Critical Design Review (CDR). The Office of the Deputy Assistant Secretary of Defense for Systems Engineering concluded that the CDR is complete and the SDB II Program is “well situated to continue into the System Capability and Manufacturing Process Demonstration Phase.”
January 2011: Delays in the F-35 development program extended SDB II F-35 integration beyond the dates identified in the MS B APB.
July 17, 2012: First GTV-1 flight test.
July 2013: System Environmental Qualification testing began. September 24, 2014: First LF test.
November 7, 2014: All dynamic environmental qualification testing complete.
December 8, 2014: Test, Analyze and Fix (TAAF) testing complete, culminating over 18 months of testing that totaled 2,190 hours. TAAF demonstrated a reliability of 253 hours Mean Time Between Failure which surpassed the 250 hour

## Table 8
requirement.
January 13, 2015: JROC approved use of SDB II CDD in lieu of CPD for production MS C. They also formally added the AC-130 as an objective aircraft.
April 1-2, 2015: Systems Verification Review.
June 3, 2015: DAE signed the MS C ADM authorizing entrance into LRIP.
June 12, 2015: Lot 1 Production contract award for the first 144 weapons.
September 23, 2015: DAE signed the MS C APB. The APB included updated F-15E Required Asset Available dates to account for previous program delays and to allow sufficient time for the remaining Developmental Testing and the upcoming Operational Testing.

## Table 9
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 10
Schedule
(Ch-1)
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B Approval | Aug 2010 | Aug 2010 | Aug 2010 | Jul 2010
Milestone C Approval | May 2015 | May 2015 | May 2015 | May 2015
RAA for SDB II-Threshold Aircraft F-15E | Jan 2018 | Jan 2018 | Jan 2019 | Jul 2018
F-35B Initial Fielding | Jan 2022 | Jan 2022 | Jan 2023 | Jan 2022
F-35C Initial Fielding | Jan 2022 | Jan 2022 | Jan 2023 | Jan 2022
Full Rate Production | Apr 2022 | Apr 2022 | Apr 2023 | Apr 2022
Change Explanations
(Ch-1) The RAA for SDB II-Threshold Aircraft F-15E current estimate changed from March 2018 to July 2018 to account for Live Fire-5 failure investigation and to allow sufficient time for the remaining Developmental Testing, Government Confidence Testing, and OT.
Notes
SDB II RAA is defined as the capability to arm twelve F-15Es with two fully-loaded Bomb Rack Units (BRU-61) carriage systems for 1.5 sorties, which equates to 144 weapons. RAA includes associated spares, support equipment (including load crew trainers), initial training, mission planning capability, and verified technical orders. The ACC Commander, or applicable Major Command Commander (if first operational unit is not within ACC) will declare IOC for the Air Force at the first designated SDB II capable wing based on the wing or group commander's recommendations. The weapon configuration delivered to meet the F-15E RAA will include fully qualified hardware functionality for all required employment modes.
The threshold date for RAA is one year beyond the objective date due to the fluidity of the Government Confidence Test schedule and the magnitude of OT which remains to be completed.
The threshold dates for FRP, F-35B Initial Fielding, and F-35C Initial Fielding are one year beyond the objective dates due to

## Table 11
the fluidity of the F-35 program schedule.
In FY 2013, the DoN adjusted the platform integration strategy by inclusion of F/A-18 E/F to deliver the mult-mode moving target capability to the warfighter ahead of the F-35. This strategy was approved and supported by OSD. The first DoN unit equipped will be an F/A-18E/F squadron aircraft. The quantity of SDB II weapons required for DoN Initial Fielding is 90 weapons.
Acronyms and Abbreviations
ACC - Air Combat Command DoN - Department of Navy OT - Operational Testing
RAA - Required Assets Available

## Table 12
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Scenario Weapon Effectiveness (WE)
Given SDB II weapon delivery from an objective platform employing self targeting or an SDB II weapon delivery from a threshold or objective aircraft with third party targeting via an objective airborne platform (Paragraph 6.2.3.1.2 of CDD for SDB II dated July 28, 2009), the SDB II weapon will achieve a minimum PSSK of (OB -1) when averaged over all the target types contained in Table 6-1 of CDD for SDB II dated July 28, 2009. The Joint JROC reviewed the CDD in lieu of the CPD on November 18, 2014; the JROC subsequently signed the memorandum on January 13, 2015. | Given SDB II weapon delivery from an objective platform employing self targeting or an SDB II weapon delivery from a threshold or objective aircraft with third party targeting via an objective airborne platform (Paragraph 6.2.3.1.2 of CDD for SDB II dated July 28, 2009), the SDB II weapon will achieve a minimum PSSK of (OB -1) when averaged over all the target types contained in Table 6-1 of CDD for SDB II dated July 28, 2009. The Joint JROC reviewed the CDD in lieu of the CPD on November 18, 2014; the JROC subsequently signed the memorandum on January 13, 2015. | Given SDB II weapon delivery from a threshold aircraft employing self targeting or a threshold aircraft delivering SDB II with third party targeting via a JTAC, the SDB II weapon will achieve a minimum PSSK of (T- 1) when averaged over all the target types contained in Table 6-1 of CDD for SDB II dated July 28, 2009. The JROC reviewed the CDD in lieu of the CPD on November 18, 2014; the JROC subsequently signed the memorandum on January 13, 2015. | Demonstrated Performance data will be collected and displayed when SDB II enters OT. | Given SDB II weapon delivery from a threshold aircraft employing self- targeting or a threshold aircraft delivering SDB II with third party targeting via a JTAC, the SDB II weapon will achieve a minimum PSSK of (T-1) when averaged over all the target types contained in Table 6-1 of CDD for SDB II dated July 28, 2009. 1. The JROC reviewed the CDD in lieu of the CPD on November 18, 2014; the JROC subsequently signed the memorandum on January 13, 2015.
Weapon Loadout
Four SDB II weapons integrated onto the BRU -61/A. Aircraft will be able to carry and employ both SDB I and II weapons loaded on separate BRU-61/As during the same mission. | Four SDB II weapons integrated onto the BRU -61/A. Aircraft will be able to carry and employ both SDB I and II weapons loaded on separate BRU-61/As during the same mission. | (T=O) Four SDB II weapons integrated onto the BRU-61/A. Aircraft will be able to carry and employ both SDB I and II weapons loaded on separate BRU-61/As during the same mission. | Demonstrated performance data will be collected and displayed when SDB II enters OT. | Four SDB II weapons integrated onto the BRU-61/A. Aircraft will be able to carry and employ both SDB I and SDB II weapons loaded on separate BRU- 61/As during the same mission.
Carrier Operability (Navy Unique Requirement)
SDB II will be compatible with carrier operations without | SDB II will be compatible with carrier operations without | (T=O) SDB II will be compatible with carrier operations without | Demonstrated Performance data will be | SDB II will be compatible with carrier operations without

## Table 13
degrading other naval | degrading other naval | degrading other naval | collected and | degrading other naval
operations. | operations. | operations. | displayed when | operations.
Compatibility includes | Compatibility includes | Compatibility includes | SDB II enters F | Compatibility includes
being capable of at | being capable of at | being capable of at | -35C OT. | being capable of at
least fifty catapult | least fifty catapult | least fifty catapult |  | least fifty catapult
launches and forty-nine | launches and forty-nine | launches and forty-nine |  | launches and forty-nine
arrested landings; able | arrested landings; able | arrested landings; able |  | arrested landings; able
to be transported, | to be transported, | to be transported, |  | to be transported,
handled, stored, | handled, stored, | handled, stored, |  | handled, stored,
prepared, uploaded, | prepared, uploaded, | prepared, uploaded, |  | prepared, uploaded,
and downloaded; and | and downloaded; and | and downloaded; and |  | and downloaded; and
capable of operating in | capable of operating in | capable of operating in |  | capable of operating in
EMI, EMC, container | EMI, EMC, container | EMI, EMC, container |  | EMI, EMC, container
immersion/washdown, | immersion/washdown, | immersion/washdown, |  | immersion/ washdown,
salt fog/salt spray, | salt fog/salt spray, | salt fog/salt spray, |  | salt fog/salt spray,
explosive atmosphere, | explosive atmosphere, | explosive atmosphere, |  | explosive atmosphere,
mechanical shock (i.e., | mechanical shock (i.e., | mechanical shock (i.e., |  | mechanical shock (i.e.,
near-miss, catapult | near-miss, catapult | near-miss, catapult |  | near-miss, catapult
launches/arrested | launches/arrested | launches/arrested |  | launches/ arrested
landings, and handling | landings, and handling | landings, and handling |  | landings, and handling
shock), acoustic noise, | shock), acoustic noise, | shock), acoustic noise, |  | shock), acoustic noise,
vibration, fluid | vibration, fluid | vibration, fluid |  | vibration, fluid
contamination, | contamination, | contamination, |  | contamination,
corrosive atmosphere, | corrosive atmosphere, | corrosive atmosphere, |  | corrosive atmosphere,
fungus, humidity, ice, | fungus, humidity, ice, | fungus, humidity, ice, |  | fungus, humidity, ice,
and rain environments | and rain environments | and rain environments |  | and rain environments
of aircraft carrier and | of aircraft carrier and | of aircraft carrier and |  | of aircraft carrier and
replenishment ship | replenishment ship | replenishment ship |  | replenishment ship
operations. | operations. | operations. |  | operations.
Materiel Availability
Once 3,000 SDB II | Once 3,000 SDB II | The Materiel Availability | Demonstrated | The Materiel Availability
weapons are in the | weapons are in the | for SDB II will follow this | performance | for SDB II will follow
inventory, the Materiel | inventory, the Materiel | graduated scale: | data will be | this graduated scale:
Availability for SDB II will | Availability for SDB II will | Greater than 500 | collected and | Greater than 500
be no less than .95. | be no less than .95. | weapons in inventory - | displayed when | weapons in inventory -
|  | no less than .75 Greater | 500 weapons | no less than .75
|  | than 1,000 weapons in | are placed in | Greater than 1000
|  | inventory - no less | inventory. | weapons in inventory -
|  | than .80 Greater than |  | no less than .80
|  | 3,000 weapons in |  | Greater than 3000
|  | inventory - no less |  | weapons in inventory -
|  | than .90. |  | no less than .90.
Net Ready
I) Support net-centric | I) Support net-centric | (T=O) I) Support net- | Demonstrated | I) Support net-centric
military operations: A) | military operations: A) | centric military | performance | military operations: A)
Mission: Positive | Mission: Positive | operations: A) Mission: | data will be | Mission: Positive
weapon control during | weapon control during | Positive weapon control | collected and | weapon control during
engagement of mobile | engagement of mobile | during engagement of | displayed when | engagement of mobile
(moving and stationary) | (moving and stationary) | mobile (moving and | SDB II enters | (moving and
targets enabled by | targets enabled by | stationary) targets | OT. | stationary) targets
digital communications | digital communications | enabled by digital |  | enabled by digital
as planned and/or event | as planned and/or event | communications as |  | communications as

## Table 14
-driven. 1) Measure: Receipt of weapon control directives = less than or equal to 12 seconds (Link 16); Transmission of situation awareness messages = less than or equal to 30 seconds UHF. 2) Conditions: Secure and available communications (DoD Chief Information Officer net-centric attribute). B) Mission Activities: Enable target acquisition; Target tracking. 1) Measure: Link 16 Target location accuracy** = 60 meters TLE90 and UHF** = 100 meters TLE90. 2) Conditions: SWE and WE conditions. II) Enter and be managed in the network: A) Link 16 tactical data link network. 1) Measure: Time to fine synchronization = less than or equal to 60 seconds; Terminal performance = 99%
-driven. 1) Measure: Receipt of weapon control directives = less than or equal to 12 seconds (Link 16); Transmission of situation awareness messages = less than or equal to 30 seconds UHF. 2) Conditions: Secure and available communications (DoD Chief Information Officer net-centric attribute). B) Mission Activities: Enable target acquisition; Target tracking. 1) Measure: Link 16 Target location accuracy** = 60 meters TLE90 and UHF** = 100 meters TLE90. 2) Conditions: SWE and WE conditions. II) Enter and be managed in the network: A) Link 16 tactical data link network. 1) Measure: Time to fine synchronization = less than or equal to 60 seconds; Terminal performance = 99%
planned and/or event- driven. 1) Measure: Receipt of weapon control directives = less than or equal to 12 seconds (Link 16); Transmission of situation awareness messages = less than or equal to 30 seconds UHF. 2) Conditions: Secure and available communications (DoD Chief Information Officer net-centric attribute). B) Mission Activities: Enable target acquisition; Target tracking. 1) Measure: Link 16 Target location accuracy** = 60 meters TLE90 and UHF** = 100 meters TLE90. 2) Conditions: SWE and WE conditions. II) Enter and be managed in the network: A) Link 16 tactical data link network. 1) Measure: Time to fine synchronization = less than or equal to 60 seconds; Terminal
planned and/or event- driven. 1) Measure: Receipt of weapon control directives = less than or equal to 12 seconds (Link 16); Transmission of situation awareness messages = less than or equal to 30 seconds UHF. 2) Conditions: Secure and available communications (DoD Chief Information Officer net-centric attribute). B) Mission Activities: Enable target acquisition; Target tracking. 1) Measure: Link 16 Target location accuracy** = 60 meters TLE90 and UHF** = 100 meters TLE90. 2) Conditions: SWE and WE conditions. II) Enter and be managed in the network: A) Link 16 tactical data link network. 1) Measure: Time to fine synchronization = less than or equal to 60
availability; Messaging = availability; Messaging = performance = 99% seconds; Terminal
MER of less than or equal to 1%. 2) Conditions: Operational network; Type 1 encryption; Spectrum availability. B) Line-of- sight UHF tactical data link network. 1) Measure: Time to fine synchronization = less than or equal to 60 seconds; Terminal Performance = 99%
MER of less than or equal to 1%. 2) Conditions: Operational network; Type 1 encryption; Spectrum availability. B) Line-of- sight UHF tactical data link network. 1) Measure: Time to fine synchronization = less than or equal to 60 seconds; Terminal Performance = 99%
availability; Messaging = MER of less than or equal to 1%. 2) Conditions: Operational network; Type 1 encryption; Spectrum availability. B) Line-of- sight UHF tactical data link network. 1) Measure: Time to fine synchronization = less than or equal to 60 seconds; Terminal
performance = 99% availability; Messaging
= MER of less than or equal to 1%. 2) Conditions: Operational network; Type 1 encryption; Spectrum availability.
B) Line-of-sight UHF tactical data link network. 1) Measure: Time to fine 2) Conditions:
availability; Messaging = availability; Messaging = Performance = 99% Operational network;
MER less than or equal to 1%. 2) Conditions: Operational network; Type 1 encryption; spectrum availability. III) Exchange Information:
MER less than or equal to 1%. 2) Conditions: Operational network; Type 1 encryption; spectrum availability. III) Exchange Information:
availability; Messaging = MER less than or equal to 1%. 2) Conditions: Operational network; Type 1 encryption; spectrum availability. III)
Type 1 encryption; spectrum availability.
III) Exchange Information: A) Link 16 weapon control: 1) Measure: Periodicity***

## Table 15
A) Link 16 weapon | A) Link 16 weapon | Exchange Information: | = less than or equal to
control: 1) Measure: | control: 1) Measure: | A) Link 16 weapon | 12 seconds;
Periodicity*** = less | Periodicity*** = less | control: 1) Measure: | Timeliness**** = less
than or equal to 12 | than or equal to 12 | Periodicity*** = less | than or equal to 3
seconds; | seconds; | than or equal to 12 | seconds;
Timeliness**** = less | Timeliness**** = less | seconds; | Throughput***** =
than or equal to 3 | than or equal to 3 | Timeliness**** = less | 53.76 kilobits per
seconds; | seconds; | than or equal to 3 | second; Size****** =
Throughput***** = | Throughput***** = | seconds; | 0.56 kilobits. 2)
53.76 kilobits per | 53.76 kilobits per | Throughput***** = | Conditions:
second; Size****** = | second; Size****** = | 53.76 kilobits per | Operational network;
0.56 kilobits. 2) | 0.56 kilobits. 2) | second; Size****** = | Type I encryption;
Conditions: Operational | Conditions: Operational | 0.56 kilobits. 2) | Required spectrum is
network; Type I | network; Type I | Conditions: Operational | available. B) UHF
encryption; Required | encryption; Required | network; Type I | weapon control JTAC2:
spectrum is available. | spectrum is available. | encryption; Required | 1) Measure
B) UHF weapon control | B) UHF weapon control | spectrum is available. | Periodicity******* =
JTAC2: 1) Measure: | JTAC2: 1) Measure: | B) UHF weapon control | less than or equal to 30
Periodicity******* = less | Periodicity******* = less | JTAC2: 1) Measure: | seconds;
than or equal to 30 | than or equal to 30 | Periodicity******* = less | Timeliness******** =
seconds; | seconds; | than or equal to 30 | less than or equal to 6
Timeliness******** = | Timeliness******** = | seconds; | seconds;
less than or equal to 6 | less than or equal to 6 | Timeliness******** = | Throughput********* =
seconds; | seconds; | less than or equal to 6 | 16 kilobits per second;
Throughput********* = | Throughput********* = | seconds; | Size********** = 1.12
16 kilobits per second; | 16 kilobits per second; | Throughput********* = | kilobits. 2) Conditions:
Size********** = 1.12 | Size********** = 1.12 | 16 kilobits per second; | Operational network;
kilobits. 2) Conditions: | kilobits. 2) Conditions: | Size********** = 1.12 | Type 1 encryption;
Operational network; | Operational network; | kilobits. 2) Conditions: | Required spectrum is
Type I encryption; | Type I encryption; | Operational network; | available. C) Link 16
Required spectrum is | Required spectrum is | Type I encryption; | precise participant
available. C) Link 16 | available. C) Link 16 | Required spectrum is | location and
precise participant | precise participant | available. C) Link 16 | identification TDL 1: 1)
location and | location and | precise participant | Measure:
identification TDL 1: 1) | identification TDL 1: 1) | location and | Periodicity*********** =
Measure: | Measure: | identification (TDL 1): 1) | less than or equal to 12
Periodicity*********** = | Periodicity*********** = | Measure: | seconds;
less than or equal to 12 | less than or equal to 12 | Periodicity*********** = | Timeliness************
seconds; | seconds; | less than or equal to 12 | = less than or equal to
Timeliness************ = | Timeliness************ = | seconds; | 3 seconds;
less than or equal to 3 | less than or equal to 3 | Timeliness************ = | Throughput***** =
seconds; | seconds; | less than or equal to 3 | 53.76 kilobits per
Throughput***** = | Throughput***** = | seconds; | second;
53.76 kilobits per | 53.76 kilobits per | Throughput***** = | Size************* =
second; | second; | 53.76 kilobits per | 0.315 kilobits. 2)
Size************* = | Size************* = | second; | Conditions:
0.315 kilobits. 2) | 0.315 kilobits. 2) | Size************* = | Operational network;
Conditions: Operational | Conditions: Operational | 0.315 kilobits. 2) | Type 1 encryption;
network; Type I | network; Type I | Conditions: Operational | Required spectrum is
encryption; Required | encryption; Required | network; Type I | available.
spectrum is available. | spectrum is available. | encryption; Required
spectrum is available.
Weapon Effectiveness

## Table 16
Given meeting the | Given meeting the | SDB II will achieve a | Demonstrated | SDB II will achieve a
threshold of WE the | threshold of WE the | minimum PSSK of (T- | performance | minimum PSSK of (T-
SDB II will achieve a | SDB II will achieve a | 3) for each target type | data will be | 3) for each target type
minimum PSSK of (O- | minimum PSSK of (O- | (Table 6-1 of CDD for | collected and | (Table 6-1 of CDD for
3), when averaged over | 3), when averaged over | SDB II dated July 28, | displayed when | SDB II dated July 28,
various | various | 2009) in each | SDB II enters | 2009) in each
environmental/threat | environmental/threat | environmental/threat | OT. | environmental/ threat
condition cases listed in | condition cases listed in | condition case listed in |  | condition case listed in
Appendix F of CDD for | Appendix F of CDD for | Appendix F of CDD for |  | Appendix F of CDD for
SDB II dated July 28, | SDB II dated July 28, | SDB II dated July 28, |  | SDB II dated July 28,
2009. The JROC | 2009. The JROC | 2009. The JROC |  | 2009. The JROC
reviewed the CDD in | reviewed the CDD in | reviewed the CDD in |  | reviewed the CDD in
lieu of the CPD on | lieu of the CPD on | lieu of the CPD on |  | lieu of the CPD on
November 18, 2014, the | November 18, 2014, the | November 18, 2014, the |  | November 18, 2014;
JROC subsequently | JROC subsequently | JROC subsequently |  | the JROC
signed the | signed the | signed the |  | subsequently signed
memorandum on | memorandum on | memorandum on |  | the memorandum on
January 13, 2015. | January 13, 2015. | January 13, 2015. |  | January 13, 2015.
Requirements Reference
Miniature Munitions Capability ORD dated April 8, 2005, CDD dated July 28, 2009, and JROC Memorandum dated January 13, 2015
Change Explanations
None
Notes
Threshold aircraft is defined as F-15E for the Air Force and F-35B and F-35C for the Navy. Program schedule for the Air Force will not be delayed due to availability of the F-35B and F-35C. Both targeting methods (threshold aircraft or JTAC) must be employed in any combination to achieve an average over the target set.
1/ Net Ready KPP was updated in the CDD in lieu of a CPD and approved by the JROC:
**Probability (90%) that target can be found within a 60 meter or 100 meter location error ellipse.
*** Maximum interval for Link 16 IFTU message (CDD: Aircraft Controller Requirement).
****Nominal Link 16 network access delay due to host buffering, contention access randomness, and minimum NPG time slot assignment.
*****Link 16 Packed-2 Double Pulse maximum tactical throughput rate.
******7-word Re-Target message sent in two time slots with associated headers.
*******Maximum interval for UHF IFTU message (CDD: JTAC Controller Requirement).
********Nominal UHF CNR deterministic adaptable priority network access delay and nominal 7-node network.

## Table 17
*********CNR modem and the VINSON crypto algorithm maximum tactical throughput rate.
**********7-word Re-Target message sent with IP version 4 and CNR overhead and Mil-Std-2045-47001 header.
***********Nominal NPG 6 weapon assignment.
************Nominal Link 16 network access delay due to host buffering and contention access randomness.
*************4-word PPLI message sent in one time slot with associated header.
Acronyms and Abbreviations
BRU - Bomb Rack Unit CNR - Combat-Net Radio
EMC - Electromagnetic Compatibility EMI - Electromagnetic Interference
IEA - Information Enterprise Architecture IFTU - In Flight Target Update
IP - Internet Protocol
JTAC - Joint Terminal Attack Controller MER - Message Error Rate
NPG - Network Participation Group O - Objective
PPLI - Precise Participant Location Information PSSK - Probability of Single Shot Kill
SWE - Scenario Weapon Effectiveness T - Threshold
TDL - Tactical Data Link TLE - Target Location Error UHF - Ultra High Frequency WE - Weapon Effectiveness

## Table 18
Track to Budget
RDT&E
Appn |  | BA | PE
Navy | 1319 05 |  | 0604329N
| Project |  | Name
| 3072 |  | Small Diameter Bomb | (Shared)
Air Force | 3600 05 |  | 0604329F
| Project |  | Name
| 655191 |  | Small Diameter Bomb Increment II
Procurement
Appn |  | BA | PE
Navy | 1507 02 |  | 0204162N
| Line Item |  | Name
| 223800 |  | Small Diameter Bomb II
Air Force | 3020 02 |  | 0207327F
| Line Item |  | Name
| SDB000 |  | Small Diameter Bomb (Shared)

## Table 19
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2015 $M |  |  |  | BY 2015 $M |  | TY $M
| SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E | 1678.1 |  | 1678.1 | 1845.9 |  | 1777.9 |  | 1648.9 |  | 1648.9 |  | 1757.5
Procurement | 2376.8 |  | 2376.8 | 2614.5 |  | 2392.5 |  | 2792 |  | 2792 |  | 2797.4
Flyaway | -- |  | -- | -- |  | 2122.5 |  | -- |  | -- |  | 2490.4
Recurring | -- |  | -- | -- |  | 2122.5 |  | -- |  | -- |  | 2490.4
Non Recurring | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support | -- |  | -- | -- |  | 270 |  | -- |  | -- |  | 307
Other Support | -- |  | -- | -- |  | 270 |  | -- |  | -- |  | 307
Initial Spares | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
MILCON | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 4054.9 |  | 4054.9 | N/A |  | 4170.4 |  | 4440.9 |  | 4440.9 |  | 4554.9
Current APB Cost Estimate Reference
Joint Air Force / Navy Service Cost Position dated April 29, 2015
Confidence Level
Confidence Level of cost estimate for current APB: 50%
A mathematically derived confidence level was not computed for this Life-Cycle Cost Estimate (LCCE). This LCCE represents the expected value, taking into consideration relevant risks, including ordinary levels of external and unforeseen events. It aims to provide sufficient resources to execute the program under normal conditions encountering average levels of technical, schedule, and programmatic risk and external influence.
Cost Notes
The APB covers the SDB II weapon system which consists of the Guided Bomb Unit (GBU)-53/B munition, mission planning and logistics system, and associated containers.

## Table 20
Total Quantity
Quantity | SAR Baseline Production Estimate | Current APB Production | Current Estimate
RDT&E | 163 | 163 | 163
Procurement | 17000 | 17000 | 17000
Total | 17163 | 17163 | 17163

## Table 21
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 1171.6 | 58.4 |  | 92.4 |  | 105.3 |  | 142.9 |  | 102.4 |  | 62.7 |  | 21.8 |  | 1757.5
Procurement | 40.6 | 66 |  | 92.4 |  | 99.9 |  | 161.3 |  | 291 |  | 452.2 |  | 1594 |  | 2797.4
MILCON | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 1212.2 | 124.4 |  | 184.8 |  | 205.2 |  | 304.2 |  | 393.4 |  | 514.9 |  | 1615.8 |  | 4554.9
PB 2016 Total | 1216.7 | 127.9 |  | 176.4 |  | 187.4 |  | 267.5 |  | 361.9 |  | 439.9 |  | 1481.8 |  | 4259.5
Delta | -4.5 | -3.5 |  | 8.4 |  | 17.8 |  | 36.7 |  | 31.5 |  | 75 |  | 134 |  | 295.4
Funding Notes
The cost estimate between the FY 2016 PB and the FY 2017 PB is a result of updated cost estimating methodologies for the Milestone C SCP, the addition of M-code, a reduction, Small Business Innovation Research, and inflation adjustments.
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 163 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 163
Production | 0 |  | 144 |  | 250 | 312 | 550 |  | 1050 |  | 1650 |  | 2910 |  | 10134 |  | 17000
PB 2017 Total | 163 |  | 144 |  | 250 | 312 | 550 |  | 1050 |  | 1650 |  | 2910 |  | 10134 |  | 17163
PB 2016 Total | 163 |  | 144 |  | 250 | 312 | 550 |  | 1050 |  | 1650 |  | 2718 |  | 10326 |  | 17163
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 192 |  | -192 |  | 0

## Table 22
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 92
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 139.6
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 107.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 126.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 100
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 138.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 125.1
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 109.6
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66.4
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.8
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.4
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 70.1
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.5
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.4
Subtotal |  | 136 | -- |  | -- |  | -- |  | -- |  | -- |  | 1269.1

## Table 23
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.4
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 103
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 153.2
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 116
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 135.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 105
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 143.1
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 127
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 109.7
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.4
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 52.5
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44.6
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 64.6
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.5
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.7
Subtotal |  | 136 | -- |  | -- |  | -- |  | -- |  | -- |  | 1310.8

## Table 24
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.7
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.1
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.6
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.4
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.9
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.2
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.3
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.6
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57.9
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 72.8
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 70.9
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 56.3
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.4
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.4
Subtotal |  | 27 | -- |  | -- |  | -- |  | -- |  | -- |  | 488.4

## Table 25
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.4
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.4
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.8
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.2
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.1
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.9
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.8
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.4
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.8
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66.7
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 63.7
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49.6
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.9
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.9
Subtotal |  | 27 | -- |  | -- |  | -- |  | -- |  | -- |  | 467.1

## Table 26
Includes weapon development only; does not include rack development.

## Table 27
Annual Funding 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2015 |  | 144 | 39.4 |  | 0.5 |  | -- |  | 39.9 |  | 0.7 |  | 40.6
2016 |  | 250 | 44.9 |  | 1 |  | -- |  | 45.9 |  | 20.1 |  | 66
2017 |  | 312 | 56 |  | 1.1 |  | -- |  | 57.1 |  | 35.3 |  | 92.4
2018 |  | 460 | 56 |  | 1.2 |  | -- |  | 57.2 |  | 21.8 |  | 79
2019 |  | 300 | 32.5 |  | 0.9 |  | -- |  | 33.4 |  | 35.8 |  | 69.2
2020 |  | 900 | 143.7 |  | 2.9 |  | -- |  | 146.6 |  | 22.8 |  | 169.4
2021 |  | 2160 | 297 |  | 7 |  | -- |  | 304 |  | 30.5 |  | 334.5
2022 |  | 1968 | 280.4 |  | 6.6 |  | -- |  | 287 |  | 15.5 |  | 302.5
2023 |  | 1968 | 275.7 |  | 6.8 |  | -- |  | 282.5 |  | 23.9 |  | 306.4
2024 |  | 1968 | 277.1 |  | 6.9 |  | -- |  | 284 |  | 12.8 |  | 296.8
2025 |  | 1570 | 241 |  | 5.8 |  | -- |  | 246.8 |  | 25.2 |  | 272
Subtotal |  | 12000 | 1743.7 |  | 40.7 |  | -- |  | 1784.4 |  | 244.4 |  | 2028.8

## Table 28
Annual Funding 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2015 |  | 144 | 38.3 |  | 0.5 |  | -- |  | 38.8 |  | 0.7 |  | 39.5
2016 |  | 250 | 42.9 |  | 1 |  | -- |  | 43.9 |  | 19.2 |  | 63.1
2017 |  | 312 | 52.5 |  | 1 |  | -- |  | 53.5 |  | 33.1 |  | 86.6
2018 |  | 460 | 51.5 |  | 1.1 |  | -- |  | 52.6 |  | 20.1 |  | 72.7
2019 |  | 300 | 29.3 |  | 0.8 |  | -- |  | 30.1 |  | 32.3 |  | 62.4
2020 |  | 900 | 127 |  | 2.6 |  | -- |  | 129.6 |  | 20.1 |  | 149.7
2021 |  | 2160 | 257.2 |  | 6.1 |  | -- |  | 263.3 |  | 26.4 |  | 289.7
2022 |  | 1968 | 238.1 |  | 5.6 |  | -- |  | 243.7 |  | 13.2 |  | 256.9
2023 |  | 1968 | 229.6 |  | 5.7 |  | -- |  | 235.3 |  | 19.9 |  | 255.2
2024 |  | 1968 | 226.2 |  | 5.6 |  | -- |  | 231.8 |  | 10.5 |  | 242.3
2025 |  | 1570 | 193 |  | 4.6 |  | -- |  | 197.6 |  | 20.2 |  | 217.8
Subtotal |  | 12000 | 1485.6 |  | 34.6 |  | -- |  | 1520.2 |  | 215.7 |  | 1735.9

## Table 29
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2018 |  | 90 | 10.8 |  | 0.4 |  | -- |  | 11.2 |  | 9.7 |  | 20.9
2019 |  | 750 | 79.5 |  | 2.7 |  | -- |  | 82.2 |  | 9.9 |  | 92.1
2020 |  | 750 | 109 |  | 3.3 |  | -- |  | 112.3 |  | 9.3 |  | 121.6
2021 |  | 750 | 105.2 |  | 3.2 |  | -- |  | 108.4 |  | 9.3 |  | 117.7
2022 |  | 750 | 105.4 |  | 3.4 |  | -- |  | 108.8 |  | 5.6 |  | 114.4
2023 |  | 750 | 103.6 |  | 3.3 |  | -- |  | 106.9 |  | 6.6 |  | 113.5
2024 |  | 750 | 104.1 |  | 3.4 |  | -- |  | 107.5 |  | 5.5 |  | 113
2025 |  | 410 | 66.7 |  | 2 |  | -- |  | 68.7 |  | 6.7 |  | 75.4
Subtotal |  | 5000 | 684.3 |  | 21.7 |  | -- |  | 706 |  | 62.6 |  | 768.6

## Table 30
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2018 |  | 90 | 9.9 |  | 0.4 |  | -- |  | 10.3 |  | 8.9 |  | 19.2
2019 |  | 750 | 71.7 |  | 2.4 |  | -- |  | 74.1 |  | 9 |  | 83.1
2020 |  | 750 | 96.4 |  | 2.9 |  | -- |  | 99.3 |  | 8.3 |  | 107.6
2021 |  | 750 | 91.2 |  | 2.8 |  | -- |  | 94 |  | 8.1 |  | 102.1
2022 |  | 750 | 89.6 |  | 2.9 |  | -- |  | 92.5 |  | 4.8 |  | 97.3
2023 |  | 750 | 86.4 |  | 2.8 |  | -- |  | 89.2 |  | 5.4 |  | 94.6
2024 |  | 750 | 85.1 |  | 2.8 |  | -- |  | 87.9 |  | 4.4 |  | 92.3
2025 |  | 410 | 53.4 |  | 1.6 |  | -- |  | 55 |  | 5.4 |  | 60.4
Subtotal |  | 5000 | 583.7 |  | 18.6 |  | -- |  | 602.3 |  | 54.3 |  | 656.6

## Table 31
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2010-08-06 | 2015-06-04
Approved Quantity | 4034 | 9947
Reference | Milestone B ADM | Milestone C ADM
Start Year | 2013 | 2015
End Year | 2018 | 2022
The Current Total LRIP Quantity is more than 10% of the total production quantity due to a delay in the completion of Operational Test and Evaluation caused by schedule revisions to the F-35 program, a threshold aircraft. Since the SDB II EMD contract award, the F-35 schedule has been further delayed, which requires an additional increase in the LRIP quantities to 9,947; this change was approved by the Milestone C ADM and accounts for max quantities in Lots 1-5 and most probable quantities in Lots 6-8. These quantities are necessary to provide production-configured or representative articles for Operational Testing (OT), to establish an initial production base for the system, and to permit an orderly increase in the production rate for the system sufficient to lead to FRP upon the successful completion of OT.

## Table 32
Foreign Military Sales
Notes
SDB II participated in OSD's Defense Exportability Features (DEF) program for FY 2014 and FY 2015. SDB II has been approved for FY 2016 DEF pending available funding.
Nuclear Costs
None

## Table 33
Unit Cost
Unit Cost Report
Item |  | BY 2015 $M | BY 2015 $M |  | % Change
|  | Current UCR Baseline (Sep 2015 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 4054.9 |  |  | 4170.4
Quantity | 17163 |  |  | 17163
Unit Cost | 0.236 |  |  | 0.243 |  | 2.97
Average Procurement Unit Cost
Cost | 2376.8 |  |  | 2392.5
Quantity | 17000 |  |  | 17000
Unit Cost | 0.14 |  |  | 0.141 |  | 0.71
Item |  | BY 2015 $M | BY 2015 $M |  | % Change
|  | Original UCR Baseline (Oct 2010 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 4979.8 |  |  | 4170.4
Quantity | 17163 |  |  | 17163
Unit Cost | 0.29 |  |  | 0.243 |  | -16.21
Average Procurement Unit Cost
Cost | 3237.9 |  |  | 2392.5
Quantity | 17000 |  |  | 17000
Unit Cost | 0.19 |  |  | 0.141 |  | -25.79

## Table 34
Unit Cost History
Item | [7 empty] | Date |  |  |  |  | BY 2015 $M | [5 empty] | TY $M
[13 empty] | PAUC |  | APUC |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Oct 2010 | [7 empty] | 0.29 |  |  | 0.19 |  |  |  | 0.304 |  |  |  | 0.209
APB as of January 2006 |  |  |  |  | N/A | [7 empty] | N/A |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Revised Original APB |  |  |  |  | N/A | [7 empty] | N/A |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | Oct 2010 | [7 empty] | 0.29 |  |  | 0.19 |  |  |  | 0.304 |  |  |  | 0.209
Current APB |  |  |  |  | Sep 2015 | [7 empty] | 0.236 |  |  | 0.14 |  |  |  | 0.259 |  |  |  | 0.164
Prior Annual SAR |  |  |  |  | Dec 2014 | [7 empty] | 0.228 |  |  | 0.129 |  |  |  | 0.248 |  |  |  | 0.151
Current Estimate |  |  |  |  | Dec 2015 | [7 empty] | 0.243 |  |  | 0.141 |  |  |  | 0.265 |  |  |  | 0.165
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [20 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  |  | Oth | Spt |  |  | Total
0.304 0.006 0.000 0.001 0.000 -0.049 0.000 -0.003 -0.045 0.259
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [18 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth | Spt |  | Total
0.259 -0.001 0.000 0.000 0.006 0.001 0.000 0.000 0.006 0.265

## Table 35
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [15 empty] | APUC Production Estimate
| Econ | Qty |  |  | Sch |  | Eng |  |  | Est |  | Oth |  | Spt |  | Total
0.209 0.005 0.000 0.001 0.000 -0.048 0.000 -0.003 -0.045 0.164
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [15 empty] | APUC Current Estimate
| Econ |  | Qty |  |  | Sch |  | Eng |  |  | Est |  | Oth |  | Spt | Total
0.164 -0.001 0.000 0.000 0.000 0.001 0.000 0.000 0.000 0.165
SAR Baseline History
Item |  |  |  | SAR Planning Estimate |  |  |  |  | SAR Development Estimate | [5 empty] | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  |  | N/A |  |  |  |  | N/A | [5 empty] | N/A |  |  | N/A
Milestone B |  |  |  | N/A |  |  |  |  | Jul 2010 | [5 empty] | Aug 2010 |  |  | Jul 2010
Milestone C |  |  |  | N/A |  |  |  |  | Jan 2013 | [5 empty] | May 2015 |  |  | May 2015
IOC |  |  |  | N/A |  |  |  |  | Jul 2016 | [5 empty] | Jan 2018 |  |  | Jul 2018
Total Cost (TY $M) |  |  |  | N/A |  |  |  |  | 5210.4 | [5 empty] | 4440.9 |  |  | 4554.9
Total Quantity |  |  |  | N/A |  |  |  |  | 17163 | [5 empty] | 17163 |  |  | 17163
PAUC |  |  |  | N/A |  |  |  |  | 0.304 | [5 empty] | 0.259 |  |  | 0.265
The IOC event above uses the F-15E Required Assets Available (RAA) milestone which is a surrogate for IOC, The F-15E is the initial aircraft with SDB II capability. There are three additional IOCs for this program, F/A-18E/F, F-35B and F-35C Initial Fielding, all occurring after the F-15E RAA milestone.

## Table 36
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
1648.9 2792.0 -- 4440.9
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 51.5 |  | -301.4 |  | -- |  | -249.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 68.5 |  | -- |  | 68.5
Subtotal |  | 51.5 |  | -232.9 |  | -- |  | -181.4
Current Changes Economic |  | 0.8 |  | -10.4 |  | -- |  | -9.6
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -1.7 |  | -- |  | -1.7
Engineering |  | 115.8 |  | -- |  | -- |  | 115.8
Estimating |  | -59.5 |  | 318 |  | -- |  | 258.5
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -67.6 |  | -- |  | -67.6
Subtotal |  | 57.1 |  | 238.3 |  | -- |  | 295.4
Adjustments |  | -- |  | -- |  | -- |  | --
Total Changes |  | 108.6 |  | 5.4 |  | -- |  | 114
CE - Cost Variance |  | 1757.5 |  | 2797.4 |  | -- |  | 4554.9
CE - Cost & Funding |  | 1757.5 |  | 2797.4 |  | -- |  | 4554.9

## Table 37
Summary BY 2015 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
1678.1 2376.8 -- 4054.9
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 46.6 |  | -251.7 |  | -- |  | -205.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 58.1 |  | -- |  | 58.1
Subtotal |  | 46.6 |  | -193.6 |  | -- |  | -147
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | 107.9 |  | -- |  | -- |  | 107.9
Estimating |  | -54.7 |  | 266.2 |  | -- |  | 211.5
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -56.9 |  | -- |  | -56.9
Subtotal |  | 53.2 |  | 209.3 |  | -- |  | 262.5
Adjustments |  | -- |  | -- |  | -- |  | --
Total Changes |  | 99.8 |  | 15.7 |  | -- |  | 115.5
CE - Cost Variance |  | 1777.9 |  | 2392.5 |  | -- |  | 4170.4
CE - Cost & Funding |  | 1777.9 |  | 2392.5 |  | -- |  | 4170.4
Previous Estimate: September 2015

## Table 38
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 0.8
Adjustment for current and prior escalation. (Estimating) | -2.5 | -2.5
Revised estimate for Small Business Innovation Research (Air Force). (Estimating) | -2.3 | -2.3
Congressional reduction in FY 2016 (Air Force). (Estimating) | -3.3 | -3.4
Revised estimate to reflect updated cost estimating methodologies in support of Milestone | 8 | 9.7
C (Air Force). (Estimating)
Revised estimate to reflect updated cost estimating methodologies in support of Milestone C (Navy). (Estimating)
-54.6 -61.0
Additional funding in FY 2017 - 2019 for M-Code requirement (Air Force). (Engineering) +107.9 +115.8
RDT&E Subtotal +53.2 +57.1
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -10.4
Acceleration of procurement buy profile from FY 2025 to FY 2021 (Air Force). (Schedule) 0.0 -1.7
Revised estimate to reflect updated cost estimating methodologies in support of Milestone C (Air Force). (Estimating)
Revised estimate to reflect updated cost estimating methodologies in support of Milestone C (Navy). (Estimating)
+182.4 +219.0
+83.5 +98.7
Adjustment for current and prior escalation. (Estimating) +0.3 +0.3
Adjustment for current and prior escalation. (Support) +0.1 +0.1
Decrease in Other Support to reflect updated cost estimating methodologies in support of Milestone C (Air Force). (Support)
Decrease in Other Support to reflect updated cost estimating methodologies in support of Milestone C (Navy). (Support)
-55.8 -65.3
-1.2 -2.4
Procurement Subtotal +209.3 +238.3

## Table 39
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: Low Rate Initial Production Lot 1
Contractor: Raytheon Company
Contractor Location: 1151 E. Hermans Rd
Tucson, AZ 85756
Contract Number: FA8672-15-C-0136
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: June 12, 2015
Definitization Date: June 12, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
30.9 35.1 144 30.9 35.1 144 34.6 35.1
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF) contract.
General Contract Variance Explanation
Cost variance is not reported for this contract, because contract performance has not yet begun.
Notes
The SDB II LRIP contract was awarded for 144 Munitions, 156 Single Weapon Containers, eight Weapon Load Crew Trainers/Conventional Munitions Maintenance Trainers, four Practical EOD System Trainers, and Data. This contract provides for the exercise of an option (awarded as a separate contract for administrative convenience) for SDB II LRIP Lot
1. The work is expected to be completed by May 30, 2017.
The SDB II Production Lot 1 Integrated Baseline Review occurred November 17, 2015.

## Table 40
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 163 | 0%
Production | 0 | 0 | 17000 | 0%
Total Program Quantity Delivered | 0 | 0 | 17163 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
4554.9
992.4
21.79%
21
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
12
57.14%
1336.6
29.34%
The above data is current as of March 01, 2016.
The Government does not take delivery of the 163 Developmental Test (DT) assets. The DT assets will not go to inventory. The 17,000 sustainment quantity will be delivered to inventory.

## Table 41
Operating and Support Cost
Cost Estimate Details
Date of Estimate: April 29, 2015
Source of Estimate: SCP
Quantity to Sustain: 17000
Unit of Measure: Total Quantity
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2014 - FY 2046
Development units will not be sustained.
Sustainment Strategy
The SDB II O&S strategy is to use Contractor Logistics Support (CLS) to cover sustainment activities for 17,000 weapons. A CLS Product Support Agreement (PSA) will be developed and put on contract with Raytheon for initial support. That PSA will be reviewed and updated at the end of each contractual period of performance. A 20-year warranty is assumed with a 20-year shelf-life and the subsequent demilitarization of the weapon.
Antecedent Information
No Antecedent. The SDB II weapon is a new acquisition program that provides Joint fighter/bomber aircraft the capability to engage mobile targets in adverse weather from stand-off ranges by utilizing a multi-mode seeker and a post-release communications weapon data link. SDB II will not replace SDB I.
Annual O&S Costs BY2015 $M
Cost Element | SDB II Average Annual Cost Per Total Quantity | No Antecedent (Antecedent) N/A
Unit-Level Manpower | 0.6 | 0
Unit Operations | 0 | 0
Maintenance | 2.9 | 0
Sustaining Support | 17.9 | 0
Continuing System Improvements | 5.3 | 0
Indirect Support | 0.5 | 0
Other | 0 | 0
Total | 27.2 | --

## Table 42
Item | Total O&S Cost $M
| SDB II | [5 empty] | No Antecedent (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 897.5 |  | 987.3 |  |  | 897.5 | 0
Then Year | 1327.5 |  | N/A |  |  | 1327.5 | N/A
Equation to Translate Annual Cost to Total Cost
Total O&S cost is equal to the average annual total inventory cost per year times the total number of years in the O&S phase, $27.2M * 33 years = $897M (BY 2015).
O&S Cost Variance
Category |  | BY 2015 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Sep 2015 SAR
897.5
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 897.5
Disposal Estimate Details
Date of Estimate: April 29, 2015
Source of Estimate: SCP
Disposal/Demilitarization Total Cost (BY 2015 $M): Total costs for disposal of all Total Quantity are 41.7