## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-326
Wideband Global SATCOM (WGS)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 12
Cost and Funding 13
Low Rate Initial Production 26
Foreign Military Sales 27
Nuclear Costs 27
Unit Cost 28
Cost Variance 31
Contracts 34
Deliveries and Expenditures 35
Operating and Support Cost 36

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Wideband Global SATCOM (WGS)
DoD Component
Air Force
Responsible Office
Mr. Robert Tarleton
MILSATCOM Systems Directorate 483 N. Aviation Blvd.
El Segundo, CA 90245-2802
robert.tarleton@us.af.mil
Phone: | 310-653-9001
Fax: | 310-653-9636
DSN Phone: | 633-9001
DSN Fax: | 633-9636
Date Assigned: | February 10, 2014
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated August 11, 2010
Approved APB
Air Force Acquisition Executive (AFAE) Approved Acquisition Program Baseline (APB) dated March 12, 2014

## Table 6
Mission and Description
Wideband Global SATCOM (WGS), previously reported as Wideband Gapfiller Satellites, is a constellation of the Department of Defense's highest capacity communication satellites. WGS augments the Defense Satellite Communications System III and the Global Broadcast Service Phase II. WGS is a fully duplexed communications platform offering warfighters a significant increase in capacity, connectivity and interoperability. It provides high capacity and digitally channelized service at both X and Ka frequency bands, opening up a new 2-way Ka communication capability. This highly flexible communications satellite design leverages commercial processes, practices and technology to provide a wideband payload compatible with existing and future terminals. WGS provides an order of magnitude increase in communications bandwidth to our infrastructure users, Soldiers, Sailors, Airmen and Marines.
The WGS program has two International Partnerships. In exchange for access to a portion of the WGS constellation, Australia is providing funds for WGS-6 while Canada, Denmark, Luxembourg, the Netherlands, New Zealand and the United States are providing funds for WGS-9.

## Table 7
Executive Summary
Wideband Global SATCOM (WGS), previously reported as Wideband Gapfiller Satellites, is a constellation of the Department of Defense's highest capacity communication satellites. WGS Block I satellites became operational with WGS- 1 in April 2008 (IOC was declared in January 2009), WGS-2 in August 2009, and WGS-3 in June 2010. WGS Block II satellites became operational with WGS-4 in August 2012, WGS-5 in December 2013 (FOC declared in May 2014) and WGS-6 in February 2014. WGS-7 launched on July 23, 2015 and achieved operational acceptance on January 5, 2016.
The Wideband Digital Channelizer upgrade, to be implemented on WGS 8-10, completed the engineering model
qualification unit build and is starting system level testing.
The WGS-6 financial data is not reported in this SAR because funding is provided by Australia in exchange for access to a
portion of the WGS constellation bandwidth.
The WGS-9 financial data is not reported in this SAR because funding is provided by Canada, Denmark, Luxembourg, the Netherlands, and New Zealand in exchange for access to a portion of the WGS constellation bandwidth.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone II/Procurement (DAB) | Oct 2000 | Oct 2000 | Apr 2001 | Nov 2000
Contract Award EMD/Production | Dec 2000 | Dec 2000 | Jun 2001 | Jan 2001
Critical Design Review | Mar 2002 | Mar 2002 | Sep 2002 | Jul 2002
IOC | Aug 2008 | Aug 2008 | Feb 2009 | Jan 2009
FOC | Jun 2013 | Feb 2014 | Aug 2014 | May 2014
Change Explanations
Notes
WGS met the following conditions for a successful FOC:
a) Satellites 1-5 must be operating in their assigned orbital locations.
b) Satellites 1-5 must be capable of supporting deployed military forces in each coverage area and have the ability to focus those coverage areas anywhere within the satellite Field of View.
c) Satellites 1-5 must be fully capable of providing intra and inter-coverage connectivity and frequency cross-banding.
d) Satellites 1-5 and the control system must be fully capable of providing S-band platform and payload control.
e) Satellites 1-5 and the control system must be fully capable of providing X and Ka in-band satellite control in each satellite's operations region.
f) Satellites 1-5 must be fully interoperable with existing DoD X-band and Global Broadcast Service Ka-band terminals.
g) All program support needed to operate and maintain satellites 1-5 and associated mission control must be in place, to include: All operator, maintenance and software training completed, all training equipment and software delivered, all provisioning data delivered, all spares delivered, all depot support equipment delivered, all software maintenance documentation and maintenance support equipment delivered, payload equipment string delivered, and contractor anomaly resolution and software maintenance capability in place.

## Table 10
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Coverage
Capable of providing | Capable of providing | Capable of providing | Confirmed by | Capable of providing
communicat-ions | communicat-ions | communicat-ions | analysis using | communications
connec-tivity | connec-tivity | connec-tivity | industry-standard | connectivity anywhere
anywhere between 70 | anywhere between 70 | anywhere between 65 | Satellite Tool Kit. | between 65º N and 65º S
deg N and 65 deg S | deg N and 65 deg S | deg N and 65 deg S | Operationally | latitude and at all
latitude and at all | latitude and at all | latitude and at all | verified at 64º N | longitudes within each
longitudes within each | longitudes within each | longitudes within each | latitude. | satellites field of view, 24
satellites field of view, | satellites field of view, | satellites field of view, |  | hrs a day.
24 hrs a day | 24 hrs a day | 24 hrs a day
Capacity
Each satellite should | Each satellite should | Each satellite should | Calculated simplex | Each satellite should
provide a min | provide a min | provide a min | throughput of | provide a minimum
throughput of 3.6 | throughput of 3.6 | throughput of 1.2 | 4.186 Gbps*. | throughput of ~2.14
Gbps | Gbps | Gbps | Current average | Gbps.
throughput is 2.1
Gbps.
Access and Control
Provide platform and | Provide platform and | Provide platform and | Positive platform | Provide platform and
payload controlled | payload controlled | payload controlled | and payload | payload controlled
capabilities to perform | capabilities to perform | capabilities to perform | operator ratings. | capabilities to perform
Launch and Early | Launch and Early | Launch and Early |  | Launch and Early Orbit,
Orbit, On-Orbit | Orbit, On-Orbit | Orbit, On-Orbit |  | On-Orbit Operations,
Operations, Station- | Operations, Station- | Operations, Station- |  | Station-keeping, Satellite
keeping, Satellite | keeping, Satellite | keeping, Satellite |  | Repositioning, Platform
Reposition-ing, | Reposition-ing, | Reposition-ing, |  | and Payload
Platform and Payload | Platform and Payload | Platform and Payload |  | Maintenance, and
Maintenance, and | Maintenance, and | Maintenance, and |  | Anomaly Identification
Anomaly Identification | Anomaly Identification | Anomaly Identification |  | and Resolution.
and Resolution | and Resolution | and Resolution
Interoperability
Satellites must be | Satellites must be | Satellites must be | Confirmed | Satellites must be fully
fully inter-operable | fully inter-operable | fully inter-operable | interoperability with | interoperable with
with existing and | with existing and | with existing and | 40 terminal types, | existing and programmed
programmed DSCS | programmed DSCS | programmed DSCS | including DSCS & | DSCS and GBS
and GBS terminals | and GBS terminals | and GBS terminals | GBS. | terminals.
Requirements Reference
ORD 004-99 dated May 3, 2000

## Table 11
Change Explanations
None
Notes
* Capacity demonstrated performance of 4.186 Gbps is based on a scenario of optimized ground terminal power/antenna aperture function. Interoperability demonstrated performance is based on testing with 40 terminals.
Acronyms and Abbreviations
deg - degrees
DSCS - Defense Satellite Communications System Gbps - Gigabits per second
GBS - Global Broadcast Service hrs - hours
min - minimum N - North
S - South

## Table 12
Track to Budget
General Notes
Budget documentations (i.e. P/R Docs) for program name remained unchanged; program began as "Wideband Gapfiller Satellites," but is now known as "Wideband Global SATCOM."
RDT&E
Appn |  | BA | PE
Air Force 3600 04 0603854F
Project | Name
644811 Wideband Gapfiller Satellites (Shared) (Sunk)
Procurement
Appn |  | BA | PE
Air Force 3020 05 0303600F
Line Item Name
GAP000 Wideband Gapfiller Satellites (Sunk) Air Force 3021 01 0303600F
Line Item Name
GAP000 Wideband Gapfiller Satellites Air Force 3080 03 0303600F
Line Item Name
836780 Wideband Gapfiller Satellites (Shared) (Sunk)
Notes
In December 2014, the Office of Management and Budget directed the DoD to establish a new space procurement appropriation as a five-year availability account. Beginning in FY 2016, Air Force major procurement funding formerly under appropriation 3020F (Missile Procurement, Air Force) BA 05 will now be under 3021F (Space Procurement, Air Force) BA 01.

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2010 $M |  |  |  |  | BY 2010 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 417.2 |  | 417.2 | 458.9 |  | 444.4 |  | 380.7 |  | 380.7 |  | 409.6
Procurement |  | 3193.4 |  | 3193.4 | 3512.6 |  | 3386.9 |  | 3159 |  | 3159 |  | 3392.3
Flyaway |  | -- |  | -- | -- |  | 3354.1 |  | -- |  | -- |  | 3363.2
Recurring |  | -- |  | -- | -- |  | 3354.1 |  | -- |  | -- |  | 3363.2
Non Recurring |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support |  | -- |  | -- | -- |  | 32.8 |  | -- |  | -- |  | 29.1
Other Support |  | -- |  | -- | -- |  | 32.8 |  | -- |  | -- |  | 29.1
Initial Spares |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
MILCON |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total |  | 3610.6 |  | 3610.6 | N/A |  | 3831.3 |  | 3539.7 |  | 3539.7 |  | 3801.9
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The ICE to support WGS Milestone C decision, like all life-cycle cost estimates previously performed by the CAPE office, is built upon a product-oriented work breakdown structure, based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for MDAPs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.
Confidence Level for Current APB O&S Estimate Exceeds 50% -
A mathematically derived confidence level was not computed for the Operations and Support (O&S) estimate used in the Current Baseline. The O&S estimate does however represent the expected value, or mean, of the distribution, and it exceeds the 50% confidence level. This estimate takes into consideration relevant risks, including ordinary levels of external and unforeseen events. It aims to provide sufficient resources to execute the O&S program under normal conditions encountering average levels of technical, schedule, and programmatic risk and external influence.

## Table 14
Total Quantity
Quantity | SAR Baseline Production Estimate | Current APB Production | Current Estimate
RDT&E | 0 | 0 | 0
Procurement | 7 | 7 | 8
Total | 7 | 7 | 8
Quantity Notes
The WGS APB was amended with an administrative note only on May 8, 2012 increasing the total quantities from seven to eight satellites. These eight satellites include three satellites (WGS 1-3) on the Block I contract, two satellites (WGS 4-5) on the Block II contract and three additional satellites (WGS 7-8 and WGS 10) on the WGS 7-10 contract.

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 409.6 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 409.6
Procurement | 3078.7 | 74.5 |  | 86.3 |  | 90.7 | 62.1 |  | 0 |  | 0 |  | 0 |  | 3392.3
MILCON | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 3488.3 | 74.5 |  | 86.3 |  | 90.7 | 62.1 |  | 0 |  | 0 |  | 0 |  | 3801.9
PB 2016 Total | 3505.5 | 53.5 |  | 65.4 |  | 48.3 | 11.2 |  | 0 |  | 0 |  | 0 |  | 3683.9
Delta | -17.2 | 21 |  | 20.9 |  | 42.4 | 50.9 |  | 0 |  | 0 |  | 0 |  | 118
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0
Production | 0 |  | 8 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 8
PB 2017 Total | 0 |  | 8 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 8
PB 2016 Total | 0 |  | 8 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 8
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.7
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.5
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 77.7
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 79
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.7
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 78.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 56.7
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 409.6

## Table 17
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.8
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.4
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 91.5
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 92.2
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.7
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83.4
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 55.1
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 444.4

## Table 18
Annual Funding 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | 24.6 |  | -- |  | -- |  | 24.6 |  | -- |  | 24.6
2002 |  | 2 | 372.9 |  | -- |  | -- |  | 372.9 |  | -- |  | 372.9
2003 |  | 1 | 184.1 |  | -- |  | -- |  | 184.1 |  | -- |  | 184.1
2004 |  | -- | 21.8 |  | -- |  | -- |  | 21.8 |  | -- |  | 21.8
2005 |  | -- | 35.4 |  | -- |  | -- |  | 35.4 |  | -- |  | 35.4
2006 |  | -- | 76.1 |  | -- |  | -- |  | 76.1 |  | -- |  | 76.1
2007 |  | 1 | 428.7 |  | -- |  | -- |  | 428.7 |  | -- |  | 428.7
2008 |  | 1 | 304.8 |  | -- |  | -- |  | 304.8 |  | -- |  | 304.8
2009 |  | -- | 50.4 |  | -- |  | -- |  | 50.4 |  | -- |  | 50.4
2010 |  | -- | 197 |  | -- |  | -- |  | 197 |  | -- |  | 197
2011 |  | 1 | 517 |  | -- |  | -- |  | 517 |  | -- |  | 517
2012 |  | 2 | 748.7 |  | -- |  | -- |  | 748.7 |  | -- |  | 748.7
2013 |  | -- | 25.1 |  | -- |  | -- |  | 25.1 |  | -- |  | 25.1
2014 |  | -- | 26.9 |  | -- |  | -- |  | 26.9 |  | -- |  | 26.9
2015 |  | -- | 36.1 |  | -- |  | -- |  | 36.1 |  | -- |  | 36.1
Subtotal |  | 8 | 3049.6 |  | -- |  | -- |  | 3049.6 |  | -- |  | 3049.6

## Table 19
Annual Funding 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | 28.8 |  | -- |  | -- |  | 28.8 |  | -- |  | 28.8
2002 |  | 2 | 429.1 |  | -- |  | -- |  | 429.1 |  | -- |  | 429.1
2003 |  | 1 | 209.5 |  | -- |  | -- |  | 209.5 |  | -- |  | 209.5
2004 |  | -- | 24.3 |  | -- |  | -- |  | 24.3 |  | -- |  | 24.3
2005 |  | -- | 38.3 |  | -- |  | -- |  | 38.3 |  | -- |  | 38.3
2006 |  | -- | 80.1 |  | -- |  | -- |  | 80.1 |  | -- |  | 80.1
2007 |  | 1 | 440.1 |  | -- |  | -- |  | 440.1 |  | -- |  | 440.1
2008 |  | 1 | 307.4 |  | -- |  | -- |  | 307.4 |  | -- |  | 307.4
2009 |  | -- | 50.1 |  | -- |  | -- |  | 50.1 |  | -- |  | 50.1
2010 |  | -- | 192.9 |  | -- |  | -- |  | 192.9 |  | -- |  | 192.9
2011 |  | 1 | 496.6 |  | -- |  | -- |  | 496.6 |  | -- |  | 496.6
2012 |  | 2 | 706.9 |  | -- |  | -- |  | 706.9 |  | -- |  | 706.9
2013 |  | -- | 23.2 |  | -- |  | -- |  | 23.2 |  | -- |  | 23.2
2014 |  | -- | 24.5 |  | -- |  | -- |  | 24.5 |  | -- |  | 24.5
2015 |  | -- | 32.5 |  | -- |  | -- |  | 32.5 |  | -- |  | 32.5
Subtotal |  | 8 | 3084.3 |  | -- |  | -- |  | 3084.3 |  | -- |  | 3084.3

## Table 20
Cost Quantity Information 3020 ¦ Procurement ¦ Missile Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2010 $M
2001 | -- | --
2002 | 2 | 643.1
2003 | 1 | 299.9
2004 | -- | --
2005 | -- | --
2006 | -- | --
2007 | 1 | 504.8
2008 | 1 | 435.8
2009 | -- | --
2010 | -- | --
2011 | 1 | 542.1
2012 | 2 | 658.6
2013 | -- | --
2014 | -- | --
2015 | -- | --
Subtotal | 8 | 3084.3

## Table 21
Annual Funding 3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | 15.1 |  | 15.1
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | 10.8 |  | 10.8
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | 1.6 |  | 1.6
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | 1.6 |  | 1.6
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | 29.1 |  | 29.1

## Table 22
Annual Funding 3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | 17.4 |  | 17.4
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | 12.2 |  | 12.2
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | 1.6 |  | 1.6
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | 1.6 |  | 1.6
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | 32.8 |  | 32.8

## Table 23
Annual Funding 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | 74.5 |  | -- |  | -- |  | 74.5 |  | -- |  | 74.5
2017 |  | -- | 86.3 |  | -- |  | -- |  | 86.3 |  | -- |  | 86.3
2018 |  | -- | 90.7 |  | -- |  | -- |  | 90.7 |  | -- |  | 90.7
2019 |  | -- | 62.1 |  | -- |  | -- |  | 62.1 |  | -- |  | 62.1
Subtotal |  | -- | 313.6 |  | -- |  | -- |  | 313.6 |  | -- |  | 313.6

## Table 24
Annual Funding 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | 65.9 |  | -- |  | -- |  | 65.9 |  | -- |  | 65.9
2017 |  | -- | 74.9 |  | -- |  | -- |  | 74.9 |  | -- |  | 74.9
2018 |  | -- | 77.2 |  | -- |  | -- |  | 77.2 |  | -- |  | 77.2
2019 |  | -- | 51.8 |  | -- |  | -- |  | 51.8 |  | -- |  | 51.8
Subtotal |  | -- | 269.8 |  | -- |  | -- |  | 269.8 |  | -- |  | 269.8

## Table 25
Cost Quantity Information 3021 ¦ Procurement ¦ Space Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2010 $M
2012 | -- | 269.8
2013 | -- | --
2014 | -- | --
2015 | -- | --
2016 | -- | --
2017 | -- | --
2018 | -- | --
2019 | -- | --
Subtotal | -- | 269.8

## Table 26
Low Rate Initial Production
There is no LRIP for this program.

## Table 27
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Multilateral | 2012-01-12 | 1 | 387.6 | A Memorandum of Understanding (MOU) with Canada, Denmark, Luxembourg, the Netherlands and New Zealand was signed on January 12, 2012 for the procurement of WGS-9 in exchange for access to the WGS constellation.
Australia | 2007-11-14 | 1 | 297 | MOU between the DoD of the United States of America and the DoD of Australia concerning production, operations, and support of WGS was signed on November 14, 2007. Australia is providing funds for WGS-6 in exchange for access to the WGS constellation.
Notes
The WGS program has no FMS; all sales in the table are International Cooperations.
Multilateral numbers include WGS-9 Channelizer upgrade.
Australia numbers reflect the final Boeing negotiated/settled cost for WGS-6.
Nuclear Costs
None

## Table 28
Unit Cost
Unit Cost Report
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
|  | Current UCR Baseline (Mar 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 3610.6 |  |  | 3831.3
Quantity | 7 |  |  | 8
Unit Cost | 515.8 |  |  | 478.912 |  | -7.15
Average Procurement Unit Cost
Cost | 3193.4 |  |  | 3386.9
Quantity | 7 |  |  | 8
Unit Cost | 456.2 |  |  | 423.362 |  | -7.2
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Aug 2010 APB)
Program Acquisition Unit Cost
Cost | 3610.6 |  |  | 3831.3
Quantity | 7 |  |  | 8
Unit Cost | 515.8 |  |  | 478.912 |  | -7.15
Average Procurement Unit Cost
Cost | 3193.4 |  |  | 3386.9
Quantity | 7 |  |  | 8
Unit Cost | 456.2 |  |  | 423.362 |  | -7.2

## Table 29
Unit Cost History
Item | [7 empty] | Date |  |  |  | BY 2010 $M | [5 empty] | TY $M
[12 empty] | PAUC |  | APUC |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Dec 2000 | [6 empty] | 387.4 |  |  | 317.933 |  |  |  | 347.5 |  |  |  | 287.9
APB as of January 2006 |  |  |  |  | Feb 2004 | [6 empty] | 390.6 |  |  | 314.3 |  |  |  | 353.42 |  |  |  | 286.48
Revised Original APB |  |  |  |  | Aug 2010 | [6 empty] | 515.8 |  |  | 456.2 |  |  |  | 505.671 |  |  |  | 451.286
Prior APB |  |  |  |  | Aug 2010 | [6 empty] | 515.8 |  |  | 456.2 |  |  |  | 505.671 |  |  |  | 451.286
Current APB |  |  |  |  | Mar 2014 | [6 empty] | 515.8 |  |  | 456.2 |  |  |  | 505.671 |  |  |  | 451.286
Prior Annual SAR |  |  |  |  | Dec 2014 | [6 empty] | 466.062 |  |  | 410.525 |  |  |  | 460.488 |  |  |  | 409.288
Current Estimate |  |  |  |  | Dec 2015 | [6 empty] | 478.912 |  |  | 423.362 |  |  |  | 475.238 |  |  |  | 424.038
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [19 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth |  |  | Spt |  | Total
347.500 3.214 74.201 0.000 19.057 64.585 0.000 -2.886 158.171 505.671
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [17 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng | Est |  | Oth |  | Spt |  | Total
505.671 2.688 -12.370 0.000 18.262 -38.975 0.000 -0.038 -30.433 475.238

## Table 30
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [12 empty] | APUC Production Estimate
| Econ | Qty |  |  | Sch |  | Eng |  | Est | Oth | Spt |  | Total
287.900 2.786 108.257 0.000 0.000 55.229 0.000 -2.886 163.386 451.286
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [12 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng |  |  | Est | Oth | Spt |  | Total
451.286 2.612 -5.572 0.000 18.262 -42.512 0.000 -0.038 -27.248 424.038
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone I |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone II |  |  | N/A |  |  |  |  | Oct 2000 |  |  |  | Oct 2000 |  |  | Nov 2000
Milestone III |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A
IOC |  |  | N/A |  |  |  |  | Dec 2004 |  |  |  | Aug 2008 |  |  | Jan 2009
Total Cost (TY $M) |  |  | N/A |  |  |  |  | 1042.5 |  |  |  | 3539.7 |  |  | 3801.9
Total Quantity |  |  | N/A |  |  |  |  | 3 |  |  |  | 7 |  |  | 8
PAUC |  |  | N/A |  |  |  |  | 347.5 |  |  |  | 505.671 |  |  | 475.238

## Table 31
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
380.7 3159.0 -- 3539.7
Economic |  | 0.7 |  | 24.1 |  | -- |  | 24.8
Quantity |  | -- |  | 406.7 |  | -- |  | 406.7
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 28.2 |  | -315.2 |  | -- |  | -287
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -0.3 |  | -- |  | -0.3
Subtotal |  | 28.9 |  | 115.3 |  | -- |  | 144.2
Current Changes Economic |  | -0.1 |  | -3.2 |  | -- |  | -3.3
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | 146.1 |  | -- |  | 146.1
Estimating |  | 0.1 |  | -24.9 |  | -- |  | -24.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -- |  | 118 |  | -- |  | 118
Total Changes |  | 28.9 |  | 233.3 |  | -- |  | 262.2
CE - Cost Variance |  | 409.6 |  | 3392.3 |  | -- |  | 3801.9
CE - Cost & Funding |  | 409.6 |  | 3392.3 |  | -- |  | 3801.9

## Table 32
Summary BY 2010 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
417.2 3193.4 -- 3610.6
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 383 |  | -- |  | 383
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 27.1 |  | -292 |  | -- |  | -264.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -0.2 |  | -- |  | -0.2
Subtotal |  | 27.1 |  | 90.8 |  | -- |  | 117.9
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | 124.8 |  | -- |  | 124.8
Estimating |  | 0.1 |  | -22.1 |  | -- |  | -22
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 0.1 |  | 102.7 |  | -- |  | 102.8
Total Changes |  | 27.2 |  | 193.5 |  | -- |  | 220.7
CE - Cost Variance |  | 444.4 |  | 3386.9 |  | -- |  | 3831.3
CE - Cost & Funding |  | 444.4 |  | 3386.9 |  | -- |  | 3831.3
Previous Estimate: December 2014

## Table 33
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | -0.1
Adjustment for current and prior escalation. (Estimating) |  | 0.1 | 0.1
RDT&E Subtotal |  | 0.1 | 0
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -3.2
Reallocation of funding to higher Department priorities (Missile Procurement, Air Force (AF)). (Estimating)
Reallocation of funding to higher Department priorities (Space Procurement, AF). (Estimating)
Additional funding for pathfinder 2-5 to expand the Commercial SATCOM pooled and portable bandwidth. (Engineering)
-15.7 -17.2
-4.3 -5.0
+124.8 +146.1
Congressional reduction in FY 2016. (Estimating) Adjustment for current and prior escalation. (Estimating) | -4.4 +2.3 |  |  | -5.0 +2.3
Procurement Subtotal | 102.7 |  |  | 118

## Table 34
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: WGS-Block II Follow-On (SVs 7-10)
Contractor: Boeing Satellite Systems, Inc.
Contractor Location: 2260 Imperial Hwy.
El Segundo, CA 90245
Contract Number: FA8808-10-C-0001/3
Contract Type: Firm Fixed Price (FFP)
Award Date: August 31, 2011
Definitization Date: August 31, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
442.6 N/A 1 1157.3 N/A 3 1157.3 1157.3
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the exercise of production options for satellites WGS-8 and WGS-10.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 35
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 6 | 6 | 8 | 75%
Total Program Quantity Delivered | 6 | 6 | 8 | 75%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
3801.9
3183.8
83.74%
21
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
18
85.71%
3562.8
93.71%
The above data is current as of February 29, 2016.
The WGS APB was amended with an administrative note only on May 8, 2012 increasing the total quantities from seven to eight satellites without updating the APB cost parameters. The eight satellites in the approved APB include: three satellites (WGS 1-3) on the Block I contract, two satellites (WGS 4-5) on the Block II contract and three additional satellites (WGS 7-8 and WGS-10) on the WGS 7-10 contract.
A third satellite (WGS-6) on the Block II contract is funded by Australia and thus is not included in the APB costs, budgets or quantities. Similar to WGS-6, WGS-9 is being funded by international partners (Canada, Denmark, Luxembourg, The Netherlands, New Zealand and the United States) and is also not included in the APB costs, budgets or quantities.
Three satellites (WGS 1-3) on the Block I contract, two satellites (WGS 4-5) on the Block II contract and one satellite (WGS-
7) on the Block II follow-on have been delivered to date.

## Table 36
Operating and Support Cost
Cost Estimate Details
Date of Estimate: December 13, 2013
Source of Estimate: SCP
Quantity to Sustain: 8
Unit of Measure: Total Quantity
Service Life per Unit: 14.00 Years
Fiscal Years in Service: FY 2009 - FY 2030
Sustainment Strategy
Contract Logistics Support (CLS) has been provided by Boeing covering the whole system, via a Time and Material (T&M) CLIN option exercised every calendar year as necessary. On December 31, 2014 a separate CLS sustainment contract was established and started on January 1, 2015.
Antecedent Information
The antecedent system is Defense Satellite Communication System (DSCS) III. The first DSCS III satellite was launched in October 1982 and the last DSCS III satellite was launched in August 2003. O&S effort for DSCS transitioned to Air Force O&M funding in FY 2005. Prior to this transition, on-going O&S for on-orbit DSCS satellites were part of missile procurement costs. O&S costs include all costs for operating, maintaining and supporting the DSCS assets (14 satellites and ground segment) for an assumed designed life of ten years.
O&S costs for DSCS are based on validated requirements from Air Force Space Command Logistics Support Requirements Brochures for the FY 2004 President's Budget.
The antecedent DSCS program office estimate is from April 2002 finalized in Air Force Space Command's budget request to Headquaters Air Force.
Annual O&S Costs BY2010 $M
Cost Element | WGS Average Annual Cost Per Total Quantity | DSCS (Antecedent) Average Annual Cost Per Total Quantity
Unit-Level Manpower | 9.381 | 0
Unit Operations | 0.249 | 0.83
Maintenance | 1.863 | 0
Sustaining Support | 6.525 | 12.802
Continuing System Improvements | 2.76 | 0
Indirect Support | 4.073 | 1.304
Other | 0 | 2.371
Total | 24.851 | 17.307

## Table 37
Item | Total O&S Cost $M
| WGS | [5 empty] | DSCS (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 546.7 |  | 601.4 |  |  | 546.7 | 173.1
Then Year | 662 |  | N/A |  |  | 662 | 0
Equation to Translate Annual Cost to Total Cost
Total O&S Costs = Average annual cost x years to sustain = $24.851M x 22 = $546.7M
O&S Cost Variance
Category |  | BY 2010 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
546.7
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 546.7
Disposal Estimate Details
Date of Estimate: Source of Estimate:
Disposal/Demilitarization Total Cost (BY 2010 $M):
The disposal estimate is to be determined.