## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-202
AH-64E Apache Remanufacture (AH-64E Remanufacture)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 9
Schedule 10
Performance 12
Track to Budget 14
Cost and Funding 15
Low Rate Initial Production 22
Foreign Military Sales 23
Nuclear Costs 23
Unit Cost 24
Cost Variance 27
Contracts 30
Deliveries and Expenditures 36
Operating and Support Cost 37

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
AH-64E Apache Remanufacture (AH-64E Remanufacture)
DoD Component
Army
Responsible Office
COL Jeffrey Hager Project Manager Builidng 5307
Redstone Arsenal, AL 35898-5000
jeffrey.hager@peoavn.army.mil
Phone: | 256-313-4200
Fax: | 256-313-4147
DSN Phone: | 897-4200
DSN Fax: Date Assigned: | August 9, 2012
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated December 16, 2010
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated November 26, 2012

## Table 6
Mission and Description
The AH-64E Apache Remanufacture (AH-64E Remanufacture), hereinafter referred to as AH-64E, is the heavy attack helicopter of the current and future force. It is a twin engine, four-bladed, tandem seat, attack helicopter with 30-millimeter ammunition, 2.75-inch rockets, laser and radio frequency Hellfire missiles. The AH-64E is the Army's network-centric, multi- role weapon system within the Future Modular Force (FMF). It provides the capability to simultaneously conduct (or quickly transition between) close combat, mobile strike, armed reconnaissance, Manned-Unmanned Teaming, security and vertical maneuver missions across the full spectrum of warfare from Stability and Support Operations to Major Combat Operations, when required, in day, night, obscured battlefield and adverse weather conditions. The AH-64E enables the Joint Air/Ground Maneuver Team to dominate the battle space by providing air-ground synergy through real-time Intelligence, Surveillance, and Reconnaissance (ISR) information and responsive precision fires. The AH-64E is linked to Joint and Combined Arms Air/Ground Maneuver Teams via Enhanced Digital Communications, Unmanned Aircraft Systems Data Links and Joint networking waveforms.
The AH-64E is an Apache attack helicopter modified as required to effectively and efficiently integrate the Longbow Apache well into the 21st century by providing improvements to make it relevant in FMF operations. It provides a significantly enhanced warfighting capability over the AH-64A and AH-64D. It is capable of being employed day or night in adverse weather and obscurants, and can effectively engage and destroy advanced threat weapon systems on the air-land battlefield. Tactically, the AH-64E provides significant war fighting advantages over the original AH-64D and multiplies the combat effectiveness of the entire fleet. It will be fully capable of employing the Longbow Fire Control Radar mission kit, the Modernized Target Acquisition Designation System/Modernized Pilot Night Vision System, the Longbow Hellfire missiles, and future improved munitions in addition to the normal complement of AH-64D munitions. Additionally, the AH-64E includes upgraded engines, debuts evolutionary transmission technology and incorporates significant improvements to its main rotor system which increases power and provides substantial performance gains.
The AH-64E is fully network-centric capable with current digitized forces and FMF-equipped forces. This enables interoperability with current and future Tactical Operations Center and Army Battle Command System forces. In addition, this reduces the logistics footprint, enhances its deployability, reduces O&S costs, improves AH-64D flight performance and provides a means to effectively utilize already funded technology insertions. The AH-64E has a fully compatible and rapidly re-configurable open system architecture mission processor design, enabling rapid integration of future communication systems, and minimizing obsolescence.
The AH-64E operates within the future force system-of-systems environment where maximum combat power is delivered to units only in coherent packages of systems with synergistic interdependence. The FMF concept drives the demand for network-centric interdependence and Joint integration across the force to new levels. The AH-64E meets these challenges by providing and integrating Command and Control, ISR, and communications connectivity for attack/reconnaissance aviation within Brigade Combat Teams, Divisions, and Corps.

## Table 7
Executive Summary
Program Highlights Since Last Report:
On August 3, 2015, the Secretary of the Army approved the AH-64E Multi-Year (MY) procurement, which is on schedule to meet a Spring 2017 award. Also, in August 2015, Manned/Unmanned Teaming Expanded capabilities competition was completed and the contract awarded. Meanwhile, Fire Control Radar Maritime Mode Testing occurred from August through September 2015 at Joint Base Little Creek, Virginia.
On September 2015, PM Apache completed fielding to the 2-17 Calvary (3-101 Attack Reconnaissance Battalion (ARB)), the Army’s 4th Unit Equipped with the E-model Apaches. PM Apache also assisted and managed transfer of 20 AH-64D aircraft from Germany and Forces Command to a new AH-64 unit, the 1-25 ARB in Fort Wainwright, Alaska. PM Apache identified and provided a materiel solution to support Apache AH-64D and AH-64E helicopters for first time stationing in an arctic environment.
On September 21, 2015, the Joint Staff and USD(AT&L) concurred on the MY procurement request for approval. In October 2015, PM Apache received FY 2015 funding in an Omnibus Reprogramming Action to support procurement of 13 additional AH-64E Remanufacture aircraft. OSD CAPE then visited Boeing Mesa to support MY Independent Government Estimate analysis.
History of Significant Developments Since Program Initiation:
Note: Before its establishment as a stand-alone ACAT IC program, the AH-64E Remanufacture Program was derived from the ACAT ID program, known as Apache Block III.
June 28, 2006: The Apache Block III Program completed a successful Milestone B review with the DAE.
July 10, 2006: The DAE signed an ADM approving Milestone B, authorizing the Apache Block III program to enter System Development and Demonstration (SDD), and designating it as an ACAT ID program.
July 14, 2006: The Apache PM awarded an SDD contract to the Boeing Company to begin the development effort for Apache Block III.
March 7, 2007: A follow-on ADM authorized an LRIP quantity of 59 aircraft and granted the Army authority to procure long- lead items beginning in FY 2009. The APB schedule milestones were established for both the Preliminary Design Review (PDR) and the Critical Design Review (CDR).
April 19, 2007: Milestones for PDR were successfully completed. January 30, 2008: Milestones for CDR were successfully completed. November 2009: The Limited User Test was executed successfully.
December 2009: Resource Management Decision (RMD) 802 and RMD 700 directed the PM to increase the total procurement quantity by 56 Apache Block III aircraft as New Build airframes and was included in the FY 2011 PB at a total of
$2.6B. This change was implemented to support an increase in the training base capacity and to establish a new heavy combat aviation brigade in the active component. This change was significant due to the fact that the baseline program was fundamentally a Remanufacture production program by design. These additional aircraft procurements would be New Build aircraft at a unit cost significantly higher than the remanufacture unit cost. The increased unit cost, compounded with minor fact-of-life changes throughout the program, caused a Nunn-McCurdy unit cost breach to the APUC, reflected in the December 2009 SAR. The DAE supported a rapid Nunn-McCurdy process in response.

## Table 8
June 1, 2010: Nunn-McCurdy reporting was completed, resulting in an ADM certifying the program progress to Milestone C, and formally separating it into two MDAPs for cost and reporting purposes: the Apache Block IIIA (AB3A) and Apache Block IIIB (AB3B) programs.
September 27, 2010: A successful Milestone C DAB was completed, authorizing LRIP and advance procurement actions for FRP.
October 22, 2010: An LRIP contract was awarded procuring a total of 51 AH-64E Remanufacture aircraft.
October - November 2011: The first Apache AH-64E Remanufacture production delivery occurred on October 24, 2011, with a formal roll-out ceremony held on November 2, 2011.
April 2012: The Initial Operational Test and Evaluation for the AH-64E Remanufacture production aircraft was completed.
June 2012: The Apache Project Management Office (PMO) requested and received approval for the Mission Design Series change for Apache Block III and was formally designated AH-64E Remanufacture. The AB3A and AB3B programs were subsequently renamed the AH-64E Apache Remanufacture and the AH-64E Apache New Build programs, respectively.
August 16, 2012: Another DAB was held, which approved FRP for the AH-64E Apache Remanufacture program and authorized up to 12 LRIP aircraft for the AH-64E Apache New Build program in FY 2013. The DAE issued an ADM approving the designation of the Apache AH-64E Remanufacture and Apache AH-64E New Build programs as ACAT IC after approval of the AH-64E Remanufacture APB.
November 26, 2012: The DAE approved the AH-64E Remanufacture APB.
December 31, 2014: The Apache PMO delivered 83 AH-64E Remanufacture Attack Helicopters of the 690 Approved Acquisition Objective.
June 30, 2014: The United States Government/Boeing Company FRP contract for Lot 3 and Lot 4 was definitized and awarded. This contract supports the remanufacture of 72 AH-64E Apache Helicopters. This production activity supported completion of fielding the second and third units equipped, as well as augmentation of the training fleet.
May 14, 2014: The Army Acquisition Executive (AAE) approved a Justification and Approval (J&A) for sole source procurement for Lot 5 and Lot 6 production contract. A proposal was received September 15, 2014.
August 14, 2014 : AH-64E Remanufacture Capability Version 4 Follow-on Operational Test & Evaluation was successfully concluded on time on at Eglin Air Force Base, Florida. This capability is scheduled to be delivered in 2016.
November 2014: The First Unit Equipped, 1-229 ARB, successfully completed the first operational combat deployment of the AH-64E Remanufacture.
December 23, 2014: The AAE approved the J&A to enter a MY procurement to support production from FY 2017 to FY 2021.
Note: It is important to understand that the Remanufacture and New Build aircraft are procured using the same contracts, built on the same production line, and delivered in the same configuration with the same capabilities.

## Table 9
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 10
Schedule
None
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B | Jun 2006 | Jun 2006 | Dec 2006 | Jul 2006
Preliminary Design Review | Apr 2007 | Apr 2007 | Oct 2007 | Apr 2007
Critical Design Review | Jan 2008 | Jan 2008 | Jul 2008 | Jan 2008
LUT | Nov 2009 | Nov 2009 | May 2010 | Nov 2009
Milestone C | Jul 2010 | Jul 2010 | Jan 2011 | Sep 2010
IOT&E | Mar 2012 | Mar 2012 | Sep 2012 | Mar 2012
FRP | Jul 2012 | Jul 2012 | Jan 2013 | Sep 2012
First Unit Equipped | Nov 2012 | Nov 2012 | May 2013 | May 2013
IOC | May 2013 | May 2013 | Nov 2013 | Nov 2013
Change Explanations
Notes
AH-64E Remanufacture (formerly known as Apache Block IIIA) schedule encompasses a 12-year EMD phase which began with a risk reduction effort from May 2005 to July 2006. This effort was followed by the current development effort which began in July 2006 and continues through September 2019. Production started in FY 2010 and continues through FY 2024.

## Table 11
Acronyms and Abbreviations
IOT&E - Initial Operational Test and Evaluation LUT - Limited User Test

## Table 12
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Net Ready
Fully support execution of all operational activities. | Fully support execution of all operational activities. | Fully support execution of joint critical operational activities. | Met Threshold | Support execution of all critical operational activities
Performance
6000' PA, 95 F OGE Hover (lbs/payload)
4100 | 4100 | 3400 | Met Threshold | 3400
Mission Reliability
MTBF(M) hrs.
Lot 1
22 | 22 | 15.3 | Met Objective | 15.3
Lot 4
22 | 22 | 17 | Met Objective | 17
MR for 3.5 hr. flight (%)
85 | 85 | 80 | Met Objective | 80
Survivability
Safe operation (minutes)
30 | 30 | 30 | Met Objective | 30
Survive Band IV MANPADS IR Missile Engagement
IAW JROCM 086-10 | IAW JROCM 086-10 | IAW JROCM 086-10 | Met Objective | IAW JROCM 086-10
Force Protection
Crewstation armor survivability (mm)
IAW JROCM 086-10 | IAW JROCM 086-10 | IAW JROCM 086-10 | Met Objective | IAW JROCM 086-10
Crewstation armor barrier survivability (mm)
IAW JROCM 086-10 | IAW JROCM 086-10 | IAW JROCM 086-10 | Met Objective | IAW JROCM 086-10
Requirements Reference
CPD dated June 1, 2010
Change Explanations
None

## Table 13
Notes
Net Ready KPP compliance is achieved by meeting the information exchange capabilities required by the Integrated Architectures Operational View-1 and is demonstrated by achieving Joint Interoperability Certification, Army Interoperability Certification, and DoD Information Assurance and Accreditation Process accreditation.
Demonstrated Performance is based upon Director, Operational Test and Evaluation assessment of AH-64E Initial Operational Test and Evaluation.
Acronyms and Abbreviations
% - Percent ' - feet
F - Fahrenheit hr - hour
hrs - hours
IAW - In Accordance With IR - Infrared
JROCM - Joint Requirements Oversight Council Memorandum lbs - Pounds
MANPADS - Man Portable Air Defense System mm - Millimeters
MR - Mission Reliability
MTBF (M) - Mean Time Between Failure (Mission) OGE - Out of Ground Effect
PA - Pressure Altitude

## Table 14
Track to Budget
RDT&E
Appn |  |  | BA | PE
Army |  | 2040 07 |  | 0203744A
|  | Project |  | Name
|  | D17 |  | Aircraft Modifications/Product Improvement Programs
Army |  | 2040 07 |  | 0607135A
|  | Project |  | Name
|  | ES2 |  | Apache Product Improvement Program
Procurement
Army |  | 2031 01 |  | 0210100A
|  | Line Item |  | Name
Appn |  |  | BA | PE
A05111 AH-64 Apache Block IIIA
Reman
Army 2031 02 0210102A
Line Item | Name
AA6606 AH-64 Mods (Shared) (Sunk)
Notes: Prior to FY 2009 and creation of the AH-64E program, this line was shared to reflect AH-64E advance procurement.

## Table 15
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2010 $M | [6 empty] | BY 2010 $M |  | TY $M
| SAR Baseline Production Estimate |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 1611.8 |  |  | 1504.2 | 1654.6 |  |  | 1565 |  | 1664.7 |  |  | 1557.8 |  | 1628.9
Procurement |  | 8856.9 |  |  | 10088.1 | 11096.9 |  |  | 11093.6 |  | 10231.9 |  |  | 12041.7 |  | 12968.2
Flyaway |  | -- |  |  | -- | -- |  |  | 10356.8 |  | -- |  |  | -- |  | 12087.6
Recurring |  | -- |  |  | -- | -- |  |  | 10318.9 |  | -- |  |  | -- |  | 12043.5
Non Recurring |  | -- |  |  | -- | -- |  |  | 37.9 |  | -- |  |  | -- |  | 44.1
Support |  | -- |  |  | -- | -- |  |  | 736.8 |  | -- |  |  | -- |  | 880.6
Other Support |  | -- |  |  | -- | -- |  |  | 582.3 |  | -- |  |  | -- |  | 696.2
Initial Spares |  | -- |  |  | -- | -- |  |  | 154.5 |  | -- |  |  | -- |  | 184.4
MILCON |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 10468.7 |  |  | 11592.3 | N/A |  |  | 12658.6 |  | 11896.6 |  |  | 13599.5 |  | 14597.1
Confidence Level
Confidence Level of cost estimate for current APB: 50%
This estimate, like all previous Cost Analysis Improvement Group (CAIG) and CAPE estimates, is built upon a product- oriented work breakdown structure; is based on historical actual cost information to the maximum extent possible; and, most importantly, is based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for MDAPs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.
Total Quantity
Quantity |  |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  |  | 5 |  |  |  | 5 |  |  |  |  | 5
Procurement |  |  | 634 |  |  |  | 634 |  |  |  |  | 634
Total |  |  | 639 |  |  |  | 639 |  |  |  |  | 639

## Table 16
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 1335.7 | 65.6 |  |  | 66.4 | 59.8 | 31.2 |  | 32.7 |  | 37.5 |  |  | 0 |  | 1628.9
Procurement | 3825.6 | 1353.4 |  |  | 1066.2 | 1082 | 1179.3 |  | 1123.3 |  | 998.7 |  |  | 2339.7 |  | 12968.2
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 5161.3 | 1419 |  |  | 1132.6 | 1141.8 | 1210.5 |  | 1156 |  | 1036.2 |  |  | 2339.7 |  | 14597.1
PB 2016 Total | 4922.2 | 1448.3 |  |  | 1140.3 | 1319 | 1169.6 |  | 1165.1 |  | 950.9 |  |  | 2652 |  | 14767.4
Delta | 239.1 | -29.3 |  |  | -7.7 | -177.2 | 40.9 |  | -9.1 |  | 85.3 |  |  | -312.3 |  | -170.3
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 5 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 5
Production | 0 |  | 171 |  | 64 | 52 | 58 |  | 59 |  | 57 | 49 |  | 124 |  | 634
PB 2017 Total | 5 |  | 171 |  | 64 | 52 | 58 |  | 59 |  | 57 | 49 |  | 124 |  | 639
PB 2016 Total | 5 |  | 158 |  | 64 | 52 | 68 |  | 57 |  | 57 | 46 |  | 132 |  | 639
Delta | 0 |  | 13 |  | 0 | 0 | -10 |  | 2 |  | 0 | 3 |  | -8 |  | 0

## Table 17
Cost and Funding
Annual Funding By Appropriation
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 107.1
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 119.9
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 184.8
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 218.2
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 149
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 90.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 89.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 120.7
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 112.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 86.1
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.6
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66.4
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.8
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.2
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.7
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.5
Subtotal |  | 5 | -- |  | -- |  | -- |  | -- |  | -- |  | 1628.9

## Table 18
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 61.7
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 112.8
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 123.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 186.6
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 217.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 146.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 87.4
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 85.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 112.5
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 102.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 77.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 58.4
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 58.1
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 51.3
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.2
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.3
Subtotal |  | 5 | -- |  | -- |  | -- |  | -- |  | -- |  | 1565

## Table 19
Annual Funding 2031 ¦ Procurement ¦ Aircraft Procurement, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2009 |  | -- | 28.4 |  | -- |  | -- |  | 28.4 |  | -- |  | 28.4
2010 |  | 8 | 230 |  | -- |  | -- |  | 230 |  | -- |  | 230
2011 |  | 16 | 488.4 |  | -- |  | -- |  | 488.4 |  | -- |  | 488.4
2012 |  | 27 | 609.3 |  | -- |  | -- |  | 609.3 |  | -- |  | 609.3
2013 |  | 37 | 593.6 |  | -- |  | -- |  | 593.6 |  | -- |  | 593.6
2014 |  | 35 | 671.6 |  | -- |  | 18 |  | 689.6 |  | 62.9 |  | 752.5
2015 |  | 48 | 1034.9 |  | -- |  | 2.6 |  | 1037.5 |  | 85.9 |  | 1123.4
2016 |  | 64 | 1256.9 |  | -- |  | 2.7 |  | 1259.6 |  | 93.8 |  | 1353.4
2017 |  | 52 | 977.9 |  | -- |  | 2.4 |  | 980.3 |  | 85.9 |  | 1066.2
2018 |  | 58 | 1010.9 |  | -- |  | 2.5 |  | 1013.4 |  | 68.6 |  | 1082
2019 |  | 59 | 1084.6 |  | -- |  | 2.5 |  | 1087.1 |  | 92.2 |  | 1179.3
2020 |  | 57 | 1031.4 |  | -- |  | 2.6 |  | 1034 |  | 89.3 |  | 1123.3
2021 |  | 49 | 903.9 |  | -- |  | 2.6 |  | 906.5 |  | 92.2 |  | 998.7
2022 |  | 46 | 821.6 |  | -- |  | 2.7 |  | 824.3 |  | 85.3 |  | 909.6
2023 |  | 47 | 811.1 |  | -- |  | 2.7 |  | 813.8 |  | 75.4 |  | 889.2
2024 |  | 31 | 489 |  | -- |  | 2.8 |  | 491.8 |  | 49.1 |  | 540.9
Subtotal |  | 634 | 12043.5 |  | -- |  | 44.1 |  | 12087.6 |  | 880.6 |  | 12968.2

## Table 20
Annual Funding 2031 ¦ Procurement ¦ Aircraft Procurement, Army
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2009 |  | -- | 28.1 |  | -- |  | -- |  | 28.1 |  | -- |  | 28.1
2010 |  | 8 | 224 |  | -- |  | -- |  | 224 |  | -- |  | 224
2011 |  | 16 | 467.2 |  | -- |  | -- |  | 467.2 |  | -- |  | 467.2
2012 |  | 27 | 573.1 |  | -- |  | -- |  | 573.1 |  | -- |  | 573.1
2013 |  | 37 | 548.5 |  | -- |  | -- |  | 548.5 |  | -- |  | 548.5
2014 |  | 35 | 611.3 |  | -- |  | 16.4 |  | 627.7 |  | 57.2 |  | 684.9
2015 |  | 48 | 927.7 |  | -- |  | 2.3 |  | 930 |  | 77.1 |  | 1007.1
2016 |  | 64 | 1112.3 |  | -- |  | 2.4 |  | 1114.7 |  | 83 |  | 1197.7
2017 |  | 52 | 849.2 |  | -- |  | 2.1 |  | 851.3 |  | 74.6 |  | 925.9
2018 |  | 58 | 860.8 |  | -- |  | 2.1 |  | 862.9 |  | 58.5 |  | 921.4
2019 |  | 59 | 905.5 |  | -- |  | 2.1 |  | 907.6 |  | 76.9 |  | 984.5
2020 |  | 57 | 844.2 |  | -- |  | 2.1 |  | 846.3 |  | 73.1 |  | 919.4
2021 |  | 49 | 725.3 |  | -- |  | 2.1 |  | 727.4 |  | 74 |  | 801.4
2022 |  | 46 | 646.3 |  | -- |  | 2.1 |  | 648.4 |  | 67.2 |  | 715.6
2023 |  | 47 | 625.6 |  | -- |  | 2.1 |  | 627.7 |  | 58.1 |  | 685.8
2024 |  | 31 | 369.8 |  | -- |  | 2.1 |  | 371.9 |  | 37.1 |  | 409
Subtotal |  | 634 | 10318.9 |  | -- |  | 37.9 |  | 10356.8 |  | 736.8 |  | 11093.6

## Table 21
Cost Quantity Information 2031 ¦ Procurement ¦ Aircraft Procurement, Army
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2010 $M
2009 | -- | --
2010 | 8 | 184.2
2011 | 16 | 382.6
2012 | 27 | 531.6
2013 | 37 | 641.4
2014 | 35 | 556.3
2015 | 48 | 707.1
2016 | 64 | 1078.3
2017 | 52 | 819.3
2018 | 58 | 965.2
2019 | 59 | 851.4
2020 | 57 | 859
2021 | 49 | 680.5
2022 | 46 | 750.7
2023 | 47 | 714.3
2024 | 31 | 597
Subtotal | 634 | 10318.9

## Table 22
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2010-10-07 | 2010-10-07
Approved Quantity | 51 | 51
Reference | Milestone C ADM | Milestone C ADM
Start Year | 2010 | 2010
End Year | 2013 | 2013

## Table 23
Foreign Military Sales
None
Nuclear Costs
None

## Table 24
Unit Cost
Unit Cost Report
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
|  | Current UCR Baseline (Nov 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 11592.3 |  |  | 12658.6
Quantity | 639 |  |  | 639
Unit Cost | 18.141 |  |  | 19.81 |  | 9.2
Average Procurement Unit Cost
Cost | 10088.1 |  |  | 11093.6
Quantity | 634 |  |  | 634
Unit Cost | 15.912 |  |  | 17.498 |  | 9.97
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Dec 2010 APB)
Program Acquisition Unit Cost
Cost | 10468.7 |  |  | 12658.6
Quantity | 639 |  |  | 639
Unit Cost | 16.383 |  |  | 19.81 |  | 20.92
Average Procurement Unit Cost
Cost | 8856.9 |  |  | 11093.6
Quantity | 634 |  |  | 634
Unit Cost | 13.97 |  |  | 17.498 |  | 25.25
The Apache program made great strides to reduce the cost of the Remanufacture program from the FY 2016 PB to FY 2017 PB. The incorporation of actuals that depict a downward cost trend allowed an update to the Apache POE cost estimating methodology pulling the program back within the APB threshold for the APUC and total procurement dollars. The Apache program will continue to review and analyze all cost elements and drive efficiency and Better Buying Power Initiatives into the program in order to control costs.

## Table 25
Unit Cost History
Item | [6 empty] | Date |  |  |  | BY 2010 $M | [5 empty] | TY $M
[11 empty] | PAUC |  |  | APUC |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Aug 2006 | [5 empty] | 11.735 |  |  |  | 9.945 |  |  | 13.445 |  |  |  | 11.649
APB as of January 2006 |  |  |  |  | N/A | [5 empty] | N/A |  |  |  | N/A |  |  | N/A |  |  |  | N/A
Revised Original APB |  |  |  |  | Dec 2010 | [5 empty] | 16.383 |  |  |  | 13.97 |  |  | 18.618 |  |  |  | 16.139
Prior APB |  |  |  |  | Dec 2010 | [5 empty] | 16.383 |  |  |  | 13.97 |  |  | 18.618 |  |  |  | 16.139
Current APB |  |  |  |  | Nov 2012 | [5 empty] | 18.141 |  |  |  | 15.912 |  |  | 21.282 |  |  |  | 18.993
Prior Annual SAR |  |  |  |  | Dec 2014 | [5 empty] | 19.869 |  |  |  | 17.6 |  |  | 23.11 |  |  |  | 20.771
Current Estimate |  |  |  |  | Dec 2015 | [5 empty] | 19.81 |  |  |  | 17.498 |  |  | 22.844 |  |  |  | 20.455
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [18 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  | Eng |  | Est |  |  | Oth |  | Spt |  | Total
13.445 -0.626 -0.159 0.231 0.000 3.961 0.000 1.766 5.173 18.618
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [16 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  | Sch |  | Eng | Est |  |  | Oth |  | Spt |  | Total
18.618 0.111 0.000 -0.150 0.000 5.560 0.000 -1.295 4.226 22.844

## Table 26
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [14 empty] | APUC Production Estimate
| Econ |  | Qty |  |  | Sch |  | Eng |  | Est |  | Oth |  | Spt | Total
11.649 -0.614 -0.056 0.233 0.000 3.147 0.000 1.780 4.490 16.139
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [14 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch |  | Eng |  | Est |  | Oth |  | Spt |  | Total
16.139 0.094 0.000 -0.151 0.000 5.678 0.000 -1.305 4.316 20.455
SAR Baseline History
Item |  |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate | [5 empty] | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  |  | N/A |  |  |  | N/A | [5 empty] | N/A |  |  | N/A
Milestone B |  |  |  | N/A |  |  |  | Jun 2006 | [5 empty] | Jun 2006 |  |  | Jul 2006
Milestone C |  |  |  | N/A |  |  |  | Apr 2010 | [5 empty] | Jul 2010 |  |  | Sep 2010
IOC |  |  |  | N/A |  |  |  | Jan 2013 | [5 empty] | May 2013 |  |  | Nov 2013
Total Cost (TY $M) |  |  |  | N/A |  |  |  | 8093.9 | [5 empty] | 11896.6 |  |  | 14597.1
Total Quantity |  |  |  | N/A |  |  |  | 602 | [5 empty] | 639 |  |  | 639
PAUC |  |  |  | N/A |  |  |  | 13.445 | [5 empty] | 18.618 |  |  | 22.844

## Table 27
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 1664.7 | 10231.9 | -- | 11896.6
Previous Changes
Economic | 14.8 | 146.2 | -- | 161
Quantity | -- | -- | -- | --
Schedule | -- | -69.6 | -- | -69.6
Engineering | -- | -- | -- | --
Estimating | -80.7 | 3617.6 | -- | 3536.9
Other | -- | -- | -- | --
Support | -- | -757.5 | -- | -757.5
Subtotal | -65.9 | 2936.7 | -- | 2870.8
Current Changes
Economic | -3.4 | -86.7 | -- | -90.1
Quantity | -- | -- | -- | --
Schedule | -- | -26.2 | -- | -26.2
Engineering | -- | -- | -- | --
Estimating | 33.5 | -17.7 | -- | 15.8
Other | -- | -- | -- | --
Support | -- | -69.8 | -- | -69.8
Subtotal | 30.1 | -200.4 | -- | -170.3
Total Changes | -35.8 | 2736.3 | -- | 2700.5
CE - Cost Variance | 1628.9 | 12968.2 | -- | 14597.1
CE - Cost & Funding | 1628.9 | 12968.2 | -- | 14597.1

## Table 28
Summary BY 2010 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 1611.8 | 8856.9 | -- | 10468.7
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -8.9 | -- | -8.9
Engineering | -- | -- | -- | --
Estimating | -73.4 | 2987.8 | -- | 2914.4
Other | -- | -- | -- | --
Support | -- | -677.6 | -- | -677.6
Subtotal | -73.4 | 2301.3 | -- | 2227.9
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 26.6 | -5.3 | -- | 21.3
Other | -- | -- | -- | --
Support | -- | -59.3 | -- | -59.3
Subtotal | 26.6 | -64.6 | -- | -38
Total Changes | -46.8 | 2236.7 | -- | 2189.9
CE - Cost Variance | 1565 | 11093.6 | -- | 12658.6
CE - Cost & Funding | 1565 | 11093.6 | -- | 12658.6
Previous Estimate: December 2014

## Table 29
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -3.4
Adjustment for current and prior escalation. (Estimating) | 1.8 | 1.9
Revised estimate to align with the FY 2017 PB. (Estimating) | 31 | 38.3
Revised estimate to reflect actuals. (Estimating) | -7.5 | -8.2
Revised estimate to reflect application of new outyear inflation indices. (Estimating) | 1.3 | 1.5
RDT&E Subtotal | 26.6 | 30.1
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -86.7
Adjustment for current and prior escalation. (Estimating) +18.4 +20.2
Acceleration of procurement buy profile from FY 2018 to FY 2015 due to receipt of Omnibus funding. (Schedule)
0.0 -26.2
Revised estimate to reflect actuals. (Estimating) -13.1 -14.5
Revised estimate to align with FY 2017 PB. (Estimating) -56.9 -75.7
Realignment of previously marked flyaway dollars to support. (Estimating) +25.6 +28.3 Revised estimate to reflect application of new outyear inflation indices. (Estimating) +20.7 +24.0 Adjustment for current and prior escalation. (Support) +1.3 +1.7
Decrease in Other Support due to a revision of the training requirements estimate. (Support)
Increase in Initial Spares due to realignment of previously marked flyaway dollars to support. (Support)
-86.0 -101.3
+25.4 +29.8
Procurement Subtotal -64.6 -200.4

## Table 30
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: AB3 System Development and Demonstration (SDD) and Risk and Reduction
Contractor: The Boeing Company
Contractor Location: 5000 E McDowell Road
Mesa, AZ 85215
Contract Number: W58RGZ-05-C-0001
Contract Type: Cost Plus Incentive Fee (CPIF)
Award Date: July 14, 2006
Definitization Date: July 14, 2006
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
619.3 N/A 5 920.6 N/A 5 959.2 959.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to Government directed changes.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/30/2016) -6.5 -0.6
Previous Cumulative Variances -3.4 -4.1
Net Change -3.1 +3.5
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to this contract having a no-cost Period of Performance (POP) extension to finish First Article Test (FAT) efforts and work on the transmission design.
The favorable net change in the schedule variance is due to this contract having a no-cost POP extension to finish FAT efforts and work on the transmission design.
Notes
The initial revised contract target price represented initial award of Apache Block 3 Risk Reduction and SDD in June 2005. The current contract name, contract type, award, definitization, and current contract target price reflect status with the award of the Apache Block 3 SDD through production Lot 4/6 configuration and associated directed changes to that contract. The contract is now 98% complete.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 31
Contract Identification
Appropriation: Procurement
Contract Name: FRP REU/UTA Lot 3
Contractor: Longbow LLC
Contractor Location: 5600 W Sand Lake Road
Orlando, FL 32819-8907
Contract Number: W58RGZ-12-C-0049
Contract Type: Firm Fixed Price (FFP)
Award Date: August 30, 2012
Definitization Date: March 31, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
39.0 N/A 34 72.9 N/A 34 72.9 72.9
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to new requirements being identified and placed on contract.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 32
Contract Identification
Appropriation: Procurement
Contract Name: FRP Lots 3/4
Contractor: The Boeing Company
Contractor Location: 5000 E McDowell Road
Mesa, AZ 85215-9707
Contract Number: W58RGZ-12-C-0055
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: June 29, 2012
Definitization Date: June 27, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
N/A 246.6 72 1027.9 1043.7 72 1027.9 1027.9
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract award as an Undefinitized Contract Action; the contract is now definitized.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because an EVM waiver was granted by the Army Acquisition Executive on December 6, 2015 due to the program being a mature production or non-developmental services program.

## Table 33
Contract Identification
Appropriation: Procurement
Contract Name: REU Lots 5/6
Contractor: Longbow LLC
Contractor Location: 5600 W Sand Lake Road
Orlando, FL 32819-8907
Contract Number: W58RGZ-15-C-0078
Contract Type: Firm Fixed Price (FFP)
Award Date: September 03, 2015
Definitization Date:
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
61.8 N/A 67 61.8 N/A 67 61.8 61.8
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
General Contract Variance Explanation
Cost variance is not reported for this contract, because an EVM reporting waiver was granted by the Army Acquisition Executive on December 6, 2015 due to the program being a mature production or non-developmental services program.
Notes
This is the first time this contract is being reported.
This is an Undefinitized Contract Action; definitization is planned for 3rd Quarter FY 2016.
The Radar Electronic Unit (REU) Lot 5/6 is an Advance Procurement contract.

## Table 34
Contract Identification
Appropriation: RDT&E
Contract Name: AH 64E, Version 6 (V6) System Development and Demonstration (SDD)
Contractor: The Boeing Company
Contractor Location: 5000 E. McDowell Road
Mesa, AZ 85215
Contract Number: W58RGZ-15-C-0043
Contract Type: Cost Plus Incentive Fee (CPIF)
Award Date: April 15, 2015
Definitization Date:
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
321.8 N/A 0 321.8 N/A 0 321.8 321.8
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date 0.0 --
Previous Cumulative Variances -- --
Net Change +0.0 --
Cost and Schedule Variance Explanations
None
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because EVM reporting has not commenced due to the current contract being an Undefinitized Contract Action (UCA) with a planned definitization in 2nd Quarter FY 2016. Target Cost and Target Fee are undefinitized estimates. Upon definitization, a negotiated fee will be recognized on allowable and allocable costs under this UCA.
Notes
This is the first time this contract is being reported.

## Table 35
Contract Identification
Appropriation: Procurement
Contract Name: FRP Lots 5/6
Contractor: The Boeing Company
Contractor Location: 5000 E McDowell Road
Mesa, AZ 85215-9707
Contract Number: W58RGZ-14-C-0018
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: February 19, 2015
Definitization Date:
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
591.2 N/A 35 591.2 N/A 35 591.2 591.2
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because an EVM was granted by the Army Acquisition Executive on December 6, 2015 due to the program being a mature production or non-developmental services program.
Notes
This is the first time this contract is being reported.
This is an Undefinitized Contract Action; definitization is planned for 3rd Quarter FY 2016.
The Quantity includes six Overseas Contingency Operations-funded AH-64E Remanufacture aircraft.

## Table 36
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 5 | 5 | 5 | 100%
Production | 126 | 126 | 634 | 19.87%
Total Program Quantity Delivered | 131 | 131 | 639 | 20.5%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
14597.1
3521.5
24.12%
20
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
12
60%
6580.3
45.08%
The above data is current as of March 01, 2016.

## Table 37
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 14, 2016
Source of Estimate: POE
Quantity to Sustain: 634
Unit of Measure: Aircraft
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2012 - FY 2047
The O&S cost estimate is based upon the OSD CAPE ICE dated August 15, 2012. The estimate was updated on September 17, 2013; February 24, 2014; January 16, 2015; and January 14, 2016 for fact-of-life changes.
The sustainment quantity of 634 aircraft differs from the acquisition quantity of 639 aircraft by five aircraft. Those five aircraft were procured as limited test articles only and do not become part of the operational inventory.
Sustainment Strategy
The AH-64E Apache is maintained by a mix of soldier and civilian maintainers. Assumes the fielding of 634 Remanufactured aircraft, each flying 203.4 hours per year. The Mean Time Between Failure goal for the aircraft system is 22 hours at maturity once the total program reaches 50,000 operational hours.
Antecedent Information
The antecedent to the AH-64E Apache is the AH-64D Longbow. The AH-64D Longbow will be in service until 2046. There are currently 633 AH-64D Longbow aircraft in operation. The AH-64D Longbow will have a total of 14,847 Fleet Years of Operational Tempo. Longbow antecedent data is derived from the Milestone C estimate, updated January 15, 2013.
14,847 Fleet Years x $3,420K per operation hour = $50,776.7M (BY 2010 $M); $58,146.7M (TY)
Annual O&S Costs BY2010 $K
Cost Element | AH-64E Remanufacture Average Annual Cost Per Aircraft | Longbow Apache (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower | 1538 | 1538
Unit Operations | 206 | 205
Maintenance | 938 | 1148
Sustaining Support | 358 | 355
Continuing System Improvements | 73 | 73
Indirect Support | 102 | 101
Other | 0 | 0
Total | 3215 | 3420

## Table 38
Item | Total O&S Cost $M
| AH-64E Remanufacture | [5 empty] | Longbow Apache (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 38506 |  | 42356.6 |  |  | 40774.9 | 50776.7
Then Year | 53639 |  | N/A |  |  | 58170 | N/A
The AH-64E Remanufacture estimate updated to reflect an Extensive Overhaul Program that was added to the Depot Support Plan as of January 14, 2016.
Equation to Translate Annual Cost to Total Cost
634 Helicopters * 20 Years Operational Life * $3,215K Unitized Cost = $40,774.9 (BY 2010 $M)
The discrepancy between the reported cost and the equation is due to rounding.
O&S Cost Variance
Category |  | BY 2010 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
40106.7
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 617.5 Depot Level Overhaul and Depot Level Spares re- estimated.
Cost Data Update 0.0
Labor Rate 35.5 Increase in labor rates from Prior Year.
Energy Rate 15.2 Updated Cost of Petroleum, Oil, and Lubricants.
Technical Input 0.0
Other 0.0
Total Changes 668.2
Current Estimate 40774.9
Disposal Estimate Details
Date of Estimate: August 15, 2012
Source of Estimate: CAPE ICE
Disposal/Demilitarization Total Cost (BY 2010 $M): Total costs for disposal of all Aircraft are 46.0
Total Disposal Costs for both the AH-64E Remanufacture and AH-64E New Build aircraft is $46.03M (BY 2010 $M) in accordance with the OSD CAPE ICE dated August 15, 2012.