## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-421
Airborne & Maritime/Fixed Station Joint Tactical Radio System (AMF JTRS)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 12
Cost and Funding 13
Low Rate Initial Production 24
Foreign Military Sales 25
Nuclear Costs 25
Unit Cost 26
Cost Variance 29
Contracts 32
Deliveries and Expenditures 33
Operating and Support Cost 34

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Airborne & Maritime/Fixed Station Joint Tactical Radio System (AMF JTRS)
DoD Component
Army
Responsible Office
COL James Ross 6007 Combat Drive
Aberdeen Proving Ground, MD 21005
james.p.ross2.mil@mail.mil
Phone: 443-395-2669
Fax: 443-395-2921
DSN Phone: 648-2669
DSN Fax:
Date Assigned: August 19, 2014
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 17, 2008
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated May 1, 2014

## Table 6
Mission and Description
Airborne & Maritime/Fixed Station Joint Tactical Radio System (AMF JTRS) products are software programmable, multi- band, multi-mode, mobile ad hoc networking radios, providing simultaneous voice and data communications for Army aviation platforms. The radios will operate in networks supporting the Common Operational Picture, situational awareness, and interoperability of Mission Command systems throughout the battlefield. AMF must ensure the soldier’s ability to communicate both horizontally and vertically via voice and data within all mission areas and Combat Operational Environments. AMF helps close capability gaps by extending data networking to company echelons and below, enabling network services to the platform, and connecting Army aviation platforms to Army ground and Joint air network domains.
AMF will procure the Small Airborne Networking Radio (SANR) as a Non-Developmental Item. The SANR is a two-channel, software-defined, National Security Agency Type 1 certified networking radio providing seamless real-time information for operation in mobile and dynamic combat environments that will meet tactical communications requirements as validated by the Army aviation community. SANR will provide increased data throughput to Army aviation platforms via the Soldier Radio Waveform (SRW) and Wideband Networking Waveform (WNW) capabilities, and maintain Single Channel Ground and Airborne Radio System (SINCGARS) capability. SANR will replace the current SINCGARS radios on Army aviation platforms. SANR is planned for implementation on the following platforms: Apache (AH-64E), Black Hawk (UH-60V, UH-60M, HH-60M, and MH-60M), Chinook (CH-47F and MH-47G), Gray Eagle Unmanned Aircraft System (MQ-1C), and Little Bird (MH-6) aircraft. SANR will enhance and further enable the ability of the maneuver commander to integrate and synchronize aviation forces with land based operational forces. SANR, employed on Army aviation platforms, will enable aviation combat elements (Combat Aviation Brigades, Theater Aviation Brigades, and Special Operations Aviation Regiment ) to better utilize the inherent versatility of airborne communications as a complement to the unique capabilities of the other combat arms.
SANR will give commanders enhanced situational awareness and mission command in a package that provides a more responsive means of directing aircraft to match changing maneuver forces situations and missions.
The fielding of SANR will follow the deployment of ground network capabilities. The SANR radio will provide SRW, SINCGARS and the WNW capability to all Army tactical aircraft (reconnaissance, attack, cargo, and utility).

## Table 7
Executive Summary
General:
The objective of the AMF JTRS program is to purchase Non-Developmental Item production-ready radios capable of operating network and legacy waveforms for Army aviation platforms. The acquisition approach will leverage prior industry and Government investment in software-defined radios to meet stated user requirements.
The Small Airborne Networking Radio (SANR) will be a two-channel radio that will run the Single Channel Ground and Airborne Radio System waveform, Soldier Radio Waveform, and Wideband Networking Waveform to interoperate with ground forces and maintain connectivity for combat operations. The SANR subprogram is designated an ACAT ID.
SANR:
As reported in the September 2015 Exception SAR, the addition of sunk RDT&E costs to the SANR subprogram, as a result of the August 2015 ADM that directed close out of the Small Airborne Link 16 Terminal subprogram, triggered a threshold breach of the APB SANR RDT&E objective. A Program Deviation Report was submitted in January 2016 as formal notification that a threshold breach to the APB occurred.
SANR acquisition activities resumed in FY 2016. These activities include market research, development and release of the request for proposal, along with preparation for, and start of, source selection activities in support of contract award.
An update to the AMF JTRS APB is under review. The APB will be finalized upon approval of the SANR CPD. There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
The RDT&E APB breach was previously reported in the September 2015 SAR. A Program Deviation Report was submitted in January 2016.
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B Decision | Dec 2007 | Mar 2008 | Mar 2008 | Mar 2008
Contract Award | Feb 2008 | Nov 2021 | May 2022 | Oct 2017
Milestone C Decision | Nov 2011 | Oct 2022 | Apr 2023 | May 2019
FRP | Jul 2014 | Jun 2023 | Dec 2023 | Aug 2020
IOC | Aug 2014 | Apr 2026 | Oct 2026 | Oct 2022
Change Explanations

## Table 10
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Have an internal growth capability
Open system architecture IAW DISR; Modular, Scaleable, Flexible Form Factors | Open system architecture IAW DISR; Modular, Scaleable, Flexible Form Factors | Open system architecture IAW DISR; Modular, Scaleable, Flexible Form Factors | TBD | N/A
JTR set modes / capabilities configuration and reconfiguration via software
By operators in their operational environment | By operators in their operational environment | By operators in their operational environment | TBD | N/A
Multi-channel routing and retransmission
Objective waveforms that are same in mode (voice, data, or video) and use like data rates and operate at permissible security classification levels | Objective waveforms that are same in mode (voice, data, or video) and use like data rates and operate at permissible security classification levels | KPP waveforms that are same in mode (voice, data, or video) and use like data rates and operate at permissible security classification levels | TBD | N/A
Support waveforms.
Maritime / Fixed: Same as Threshold. Small Airborne: Threshold plus UHF SATCOM, SINCGARS, Havequick II, EPLRS | Maritime / Fixed: Same as Threshold. Small Airborne: Threshold plus UHF SATCOM, SINCGARS, Havequick II, EPLRS | Maritime / Fixed: UHF SATCOM, MUOS. Small Airborne: MUOS, SRW, WNW, Link 16 | TBD | N/A
To operate on designated number of channels at the same time.
Small Airborne: 10 channels. Maritime / Fixed (full duplex): 10 channels | Small Airborne: 10 channels. Maritime / Fixed (full duplex): 10 channels | Small Airborne: 2 channels. Maritime / Fixed (full duplex): 4 channels | TBD | N/A
Scaleable networking services
All domains | All domains | All domains | TBD | N/A
Network extension / coverage
Across organizational boundaries | Across organizational boundaries | Across organizational boundaries | TBD | N/A
JTR system network interoperability
Interoperate with Allied / Coalition and commercial networks; satisfy 100% of top -level IER | Interoperate with Allied / Coalition and commercial networks; satisfy 100% of top-level IER | Interoperate with Service and Joint networks; satisfy 100% of critical top-level IERs | TBD | N/A
Sustainment - Operational Availability (Ao)
0.99 (channel) | 0.99 (channel) | 0.96 (channel) | TBD | N/A

## Table 11
Requirements Reference
JTRS ORD Increment 1 Version 3.2 dated April 9, 2003 / v.3.2.1 errata dated August 28, 2006 and as modified by JROC Memorandum 063-11 dated April 29, 2011
Change Explanations
None
Notes
The current APB represents the Milestone B Acquisition Strategy. A revised CPD is currently in staffing with the Army Capabilities Integration Center of the Training & Doctrine Command. The program office anticipates a subset of the approved KPPs will apply to the approved CPD.
Acronyms and Abbreviations
DISR - Defense Information Standards Registry
EPLRS - Enhanced Position Location Reporting System IAW - In Accordance With
IER - Information Exchange Requirement JTR - Joint Tactical Radio
MUOS - Mobile User Objective System SATCOM - Satellite Communications
SINCGARS - Single Channel Ground and Airborne Radio System SRW - Soldier Radio Waveform
UHF - Ultra High Frequency
WNW - Wideband Networking Waveform

## Table 12
Track to Budget
RDT&E
Appn |  |  |  | BA | PE
Navy 1319 05 0604280N
Project | Name
3073 AMF JTRS (Sunk)
Army 2040 05 0604280A
Project | Name
162 Joint Tactical Radio / Network Enterprise Domain
(Sunk)
Army 2040 |  |  | 5 |  | 0605380A
Proj |  |  | ect |  | Name
EA9 |  |  |  |  | Airborne Maritime Fixed Small Airborne (AMF- SA)
EG6 |  |  |  |  | Small Airborne Networking Radio (SANR)
Air Force 3600 |  |  | 5 |  | 0604280F
Proj |  |  | ect |  | Name
655068 |  |  |  |  | Joint Tactical Radio System (JTRS)
(Sunk)
(Sunk)
Procurement
Appn |  |  |  | BA | PE
Army |  | 2035 02 |  |  | 0204380A
|  | Line Item |  |  | Name
|  | B90902 B90904 |  |  | AMF JTRS AMF JTRS | (Sunk)
Notes
B90900 is the parent Line Item number to B90902 and B90904.

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2008 $M |  |  |  | BY 2008 $M |  | TY $M
| SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Development Estimate |  | Current APB Development Objective |  | Current Estimate
RDT&E | 1681.6 |  | 1256.2 | 1381.8 |  | 1463.31 |  | 1764.2 |  | 1279.1 |  | 1502.8
Procurement | 5459.7 |  | 1387.1 | 1525.8 |  | 1443.8 |  | 6569.8 |  | 2092.1 |  | 1990.6
Flyaway | -- |  | -- | -- |  | 1201 |  | -- |  | -- |  | 1655.2
Recurring | -- |  | -- | -- |  | 1201 |  | -- |  | -- |  | 1655.2
Non Recurring | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support | -- |  | -- | -- |  | 242.8 |  | -- |  | -- |  | 335.4
Other Support | -- |  | -- | -- |  | 129.6 |  | -- |  | -- |  | 179.5
Initial Spares | -- |  | -- | -- |  | 113.2 |  | -- |  | -- |  | 155.9
MILCON | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 7141.3 |  | 2643.3 | N/A |  | 2907.1 |  | 8334 |  | 3371.2 |  | 3493.4
1 APB Breach
Current APB Cost Estimate Reference
Program Office Estimate aligned with FY 2015 President's Budget dated March 04, 2014
Confidence Level
Confidence Level of cost estimate for current APB: 50%
Original APB cost estimate was established by OSD decision at 50% confidence level.
Cost Notes
Costs do not reflect funding for platform integration and installation. Army requirements by platform and year, including integration and installation of Small Airborne Networking Radios (SANR) on host platforms, are documented separately.

## Table 14
Total Quantity
Quantity | SAR Baseline Development Estimate | Current APB Development | Current Estimate
RDT&E | 204 | 192 | 162
Procurement | 24920 | 14060 | 14060
Total | 25124 | 14252 | 14222
Quantity Notes
The fielding plan and procurement funding are based on current Army requirements of 7,030 SANR (14,060 channels).
RDT&E quantity of 81 units (162 channels) reflect planned deliveries to the Army for integration onto platforms. This quantity does not include 19 units (38 channels) required for testing.
AMF PAUC and APUC units of measure are per channel. Quantities are channels with the assumption of two channels per radio.

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 1419.8 | 6.2 |  | 5 |  | 35.9 |  | 6.8 |  | 10.8 |  | 9.4 |  | 8.9 |  | 1502.8
Procurement | 0 | 0 |  | 0 |  | 0 |  | 41 |  | 64.2 |  | 82.9 |  | 1802.5 |  | 1990.6
MILCON | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 1419.8 | 6.2 |  | 5 |  | 35.9 |  | 47.8 |  | 75 |  | 92.3 |  | 1811.4 |  | 3493.4
PB 2016 Total | 1293.6 | 6.2 |  | 10.4 |  | 35.4 |  | 48.5 |  | 86.9 |  | 163.2 |  | 1735.3 |  | 3379.5
Delta | 126.2 | 0 |  | -5.4 |  | 0.5 |  | -0.7 |  | -11.9 |  | -70.9 |  | 76.1 |  | 113.9
Funding Notes
Starting in FY 2014, all AMF RDT&E funding resides in Army PE 0605380A.
The Prior delta of +$126.2M between PB 2016 Total and the PB 2017 Total is comprised of +$129.9M and -$3.7M
where $129.9M is due to the movement of sunk cost associated with AMF acquisition program from SALT to SANR. This amount is offset by a prior year adjustment -$3.7M in the Navy account.
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 162 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 162
Production | 0 |  | 0 |  | 0 | 0 | 0 |  | 296 |  | 340 |  | 524 |  | 12900 |  | 14060
PB 2017 Total | 162 |  | 0 |  | 0 | 0 | 0 |  | 296 |  | 340 |  | 524 |  | 12900 |  | 14222
PB 2016 Total | 162 |  | 0 |  | 0 | 0 | 0 |  | 296 |  | 340 |  | 1188 |  | 12236 |  | 14222
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | -664 |  | 664 |  | 0

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.4
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 55.9
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 53.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 99.3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 212.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 306.9
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 303.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 119.5
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.1
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1265.7

## Table 17
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.4
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57.7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 53.9
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 98.3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 207.4
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 295.4
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 285.3
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 110.5
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.3
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1231

## Table 18
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.9
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.8
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.8
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.4
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.9
Subtotal |  | 162 | -- |  | -- |  | -- |  | -- |  | -- |  | 83

## Table 19
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.4
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.3
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.6
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.7
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.4
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.9
Subtotal |  | 162 | -- |  | -- |  | -- |  | -- |  | -- |  | 68.4

## Table 20
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.8
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36.1
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 77.1
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 154.1

## Table 21
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.4
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.8
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.6
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 80.1
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 163.9

## Table 22
Annual Funding 2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2019 |  | 296 | 34 |  | -- |  | -- |  | 34 |  | 7 |  | 41
2020 |  | 340 | 39.1 |  | -- |  | -- |  | 39.1 |  | 25.1 |  | 64.2
2021 |  | 524 | 60.3 |  | -- |  | -- |  | 60.3 |  | 22.6 |  | 82.9
2022 |  | 2264 | 249 |  | -- |  | -- |  | 249 |  | 47.3 |  | 296.3
2023 |  | 1844 | 201.6 |  | -- |  | -- |  | 201.6 |  | 29.7 |  | 231.3
2024 |  | 1800 | 201 |  | -- |  | -- |  | 201 |  | 30.1 |  | 231.1
2025 |  | 1444 | 166.2 |  | -- |  | -- |  | 166.2 |  | 26.8 |  | 193
2026 |  | 1368 | 161.1 |  | -- |  | -- |  | 161.1 |  | 25.6 |  | 186.7
2027 |  | 1304 | 157.1 |  | -- |  | -- |  | 157.1 |  | 25.4 |  | 182.5
2028 |  | 920 | 115.9 |  | -- |  | -- |  | 115.9 |  | 21.4 |  | 137.3
2029 |  | 832 | 106.9 |  | -- |  | -- |  | 106.9 |  | 19.8 |  | 126.7
2030 |  | 692 | 92.3 |  | -- |  | -- |  | 92.3 |  | 18.5 |  | 110.8
2031 |  | 296 | 44.9 |  | -- |  | -- |  | 44.9 |  | 13.9 |  | 58.8
2032 |  | 136 | 25.8 |  | -- |  | -- |  | 25.8 |  | 11.1 |  | 36.9
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | 11.1 |  | 11.1
Subtotal |  | 14060 | 1655.2 |  | -- |  | -- |  | 1655.2 |  | 335.4 |  | 1990.6

## Table 23
Annual Funding 2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2019 |  | 296 | 27.8 |  | -- |  | -- |  | 27.8 |  | 5.7 |  | 33.5
2020 |  | 340 | 31.3 |  | -- |  | -- |  | 31.3 |  | 20.1 |  | 51.4
2021 |  | 524 | 47.4 |  | -- |  | -- |  | 47.4 |  | 17.7 |  | 65.1
2022 |  | 2264 | 191.8 |  | -- |  | -- |  | 191.8 |  | 36.4 |  | 228.2
2023 |  | 1844 | 152.2 |  | -- |  | -- |  | 152.2 |  | 22.4 |  | 174.6
2024 |  | 1800 | 148.8 |  | -- |  | -- |  | 148.8 |  | 22.3 |  | 171.1
2025 |  | 1444 | 120.6 |  | -- |  | -- |  | 120.6 |  | 19.5 |  | 140.1
2026 |  | 1368 | 114.6 |  | -- |  | -- |  | 114.6 |  | 18.2 |  | 132.8
2027 |  | 1304 | 109.6 |  | -- |  | -- |  | 109.6 |  | 17.7 |  | 127.3
2028 |  | 920 | 79.3 |  | -- |  | -- |  | 79.3 |  | 14.6 |  | 93.9
2029 |  | 832 | 71.7 |  | -- |  | -- |  | 71.7 |  | 13.2 |  | 84.9
2030 |  | 692 | 60.7 |  | -- |  | -- |  | 60.7 |  | 12.1 |  | 72.8
2031 |  | 296 | 28.9 |  | -- |  | -- |  | 28.9 |  | 9 |  | 37.9
2032 |  | 136 | 16.3 |  | -- |  | -- |  | 16.3 |  | 7 |  | 23.3
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | 6.9 |  | 6.9
Subtotal |  | 14060 | 1201 |  | -- |  | -- |  | 1201 |  | 242.8 |  | 1443.8

## Table 24
Low Rate Initial Production
An LRIP request is anticipated at Milestone C.

## Table 25
Foreign Military Sales
None
Nuclear Costs
None

## Table 26
Unit Cost
Unit Cost Report
Item |  | BY 2008 $M | BY 2008 $M |  | % Change
|  | Current UCR Baseline (May 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2643.3 |  |  | 2907.1
Quantity | 14252 |  |  | 14222
Unit Cost | 0.185 |  |  | 0.204 |  | 10.27
Average Procurement Unit Cost
Cost | 1387.1 |  |  | 1443.8
Quantity | 14060 |  |  | 14060
Unit Cost | 0.099 |  |  | 0.103 |  | 4.04
Item |  | BY 2008 $M | BY 2008 $M |  | % Change
|  | Original UCR Baseline (Oct 2008 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 7141.3 |  |  | 2907.1
Quantity | 25124 |  |  | 14222
Unit Cost | 0.284 |  |  | 0.204 |  | -28.17
Average Procurement Unit Cost
Cost | 5459.7 |  |  | 1443.8
Quantity | 24920 |  |  | 14060
Unit Cost | 0.219 |  |  | 0.103 |  | -52.97
.

## Table 27
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2008 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Oct 2008 |  |  |  |  | 0.284 |  |  | 0.219 |  |  | 0.332 |  |  | 0.264
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | Oct 2008 |  |  |  |  | 0.284 |  |  | 0.219 |  |  | 0.332 |  |  | 0.264
Current APB |  |  | May 2014 |  |  |  |  | 0.185 |  |  | 0.099 |  |  | 0.237 |  |  | 0.149
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 0.196 |  |  | 0.103 |  |  | 0.238 |  |  | 0.142
Current Estimate |  |  | Dec 2015 |  |  |  |  | 0.204 |  |  | 0.103 |  |  | 0.246 |  |  | 0.142
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
0.332 -0.005 0.066 0.013 0.001 -0.185 0.000 0.024 -0.086 0.246
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
0.264 -0.004 0.016 0.023 0.000 -0.182 0.000 0.025 -0.122 0.142

## Table 28
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Dec 2007 | N/A | Mar 2008
Milestone C | N/A | Nov 2011 | N/A | May 2019
IOC | N/A | Aug 2014 | N/A | Oct 2022
Total Cost (TY $M) | N/A | 8334 | N/A | 3493.4
Total Quantity | N/A | 25124 | N/A | 14222
PAUC | N/A | 0.332 | N/A | 0.246

## Table 29
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 1764.2 | 6569.8 | -- | 8334
Previous Changes
Economic | -23.5 | -36.4 | -- | -59.9
Quantity | -29.9 | -2646.8 | -- | -2676.7
Schedule | -139.9 | 326.1 | -- | 186.2
Engineering | 12.3 | -- | -- | 12.3
Estimating | -80.4 | -2549.8 | -- | -2630.2
Other | -- | -- | -- | --
Support | -- | 340 | -- | 340
Subtotal | -261.4 | -4566.9 | -- | -4828.3
Current Changes
Economic | -1 | -15.8 | -- | -16.8
Quantity | -- | -- | -- | --
Schedule | -- | 1.4 | -- | 1.4
Engineering | -- | -- | -- | --
Estimating | 1 | -5.4 | -- | -4.4
Other | -- | -- | -- | --
Support | -- | 7.5 | -- | 7.5
Subtotal | -- | -12.3 | -- | -12.3
Total Changes | -261.4 | -4579.2 | -- | -4840.6
CE - Cost Variance | 1502.8 | 1990.6 | -- | 3493.4
CE - Cost & Funding | 1502.8 | 1990.6 | -- | 3493.4

## Table 30
Summary BY 2008 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 1681.6 | 5459.7 | -- | 7141.3
Previous Changes
Economic | -- | -- | -- | --
Quantity | -27.4 | -2250.6 | -- | -2278
Schedule | -140.4 | 23.5 | -- | -116.9
Engineering | 11 | -- | -- | 11
Estimating | -61.4 | -2027.3 | -- | -2088.7
Other | -- | -- | -- | --
Support | -- | 236.2 | -- | 236.2
Subtotal | -218.2 | -4018.2 | -- | -4236.4
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -0.1 | -4.3 | -- | -4.4
Other | -- | -- | -- | --
Support | -- | 6.6 | -- | 6.6
Subtotal | -0.1 | 2.3 | -- | 2.2
Total Changes | -218.3 | -4015.9 | -- | -4234.2
CE - Cost Variance | 1463.3 | 1443.8 | -- | 2907.1
CE - Cost & Funding | 1463.3 | 1443.8 | -- | 2907.1
Previous Estimate: September 2015

## Table 31
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -1.0
Adjustment to FY 2022 to account for previously funded requirements within the FYDP. (Estimating)
+6.9 +8.9
Revised estimate to align with adjustments in FY 2017 PB. (Estimating) Adjustment for current and prior escalation. (Estimating) | -7.3 +0.3 |  |  | -8.2 +0.3
RDT&E Subtotal | -0.1 |  |  | 0
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -15.8
Additional schedule variance due to procurement buy profile shifting quantity from FY 2021 to FY2022 to align with FY 2017 PB. (Schedule)
Revised estimate to align with FY 2017 PB which resulted in program fielding schedule adjustment. (Estimating)
Increase in Other Support as a result of fact-of-life changes related to manpower and overhead. (Support)
0.0 +1.4
-4.3 -5.4
+5.0 +5.4
Increase in Initial Spares due to adjustments in buy profile and fielding schedule. (Support) +1.6 +2.1
Procurement Subtotal +2.3 -12.3

## Table 32
Contracts
There are no Contracts data to display.

## Table 33
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 162 | 0%
Production | 0 | 0 | 14060 | 0%
Total Program Quantity Delivered | 0 | 0 | 14222 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
3493.4
1422.1
40.71%
31
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
14
45.16%
1426
40.82%
The above data is current as of February 09, 2016.
The decrease of $0.3M from $1,422.4M to $1,422.1M since the September 2015 SAR is associated with the Navy Account (RDT&E Account 1319); the adjustment is for returned funds no longer needed by the activity.

## Table 34
Operating and Support Cost
Cost Estimate Details
Date of Estimate: December 30, 2015
Source of Estimate: POE
Quantity to Sustain: 14060
Unit of Measure: Channels
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2020 - FY 2052
O&S costs are based on the procurement of 7,030 two-channel radios (7,030 x 2 = 14,060), each with a 20-year estimated service life. RDT&E quantities are not sustained.
Sustainment Strategy
The project is currently in the pre-solicitation stage. The program office will conduct an in-depth assessment of risks to logistics and training as information on the product becomes available. The program office will execute a step approach to contracting for a Performance Based Logistics (PBL) solution to be initiated after the FRP decision. Initial procurement of test/integration units is planned to come with a one-year warranty and Interim Contractor Logistics Support at contract award. The program office plans to conduct a business case analysis using actual cost, usage, and turn-around times before FRP. This approach will facilitate transition to full PBL implementation with greater understanding of requirements, more effective metrics, and greater cost fidelity. Depot Source of Repair Analysis will also be conducted prior to Milestone
C. The training concept is being jointly developed by the PEO for Command, Control, and Communications - Tactical, PM Tactical Radios, PM AMF, the Army Training and Doctrine Command Training Directorate and the U.S. Army Aviation Center of Excellence, and will include a System Training Plan to accompany the validated requirements document.
Antecedent Information
No Antecedent. AMF radios are software programmable, multi-band, multi-mode, mobile ad hoc networking radios, providing simultaneous voice, data, and video communications, and which may be employed in new and innovative ways as compared to any currently fielded legacy radio.
Annual O&S Costs BY2008 $K
Cost Element | Small Airborne Networking Radio (SANR) Average Annual Cost Per Channels | No Antecedent (Antecedent)
Unit-Level Manpower | 0.305 | --
Unit Operations | 0 | --
Maintenance | 3.561 | --
Sustaining Support | 1.773 | --
Continuing System Improvements | 0.209 | --
Indirect Support | 0 | --
Other | -- | --
Total | 5.848 | --

## Table 35
Item | Total O&S Cost $M
| Small Airborne Networking Radio (SANR) | [5 empty] | No Antecedent (Antecedent)
| Current Development APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 2887.4 |  | 3176.1 |  |  | 1644.5 | 0
Then Year | 5311.8 |  | N/A |  |  | 2837.3 | N/A
Equation to Translate Annual Cost to Total Cost
14,060 channels * 20 years * $5.848K = $1,644,457.60K = $1,644.5M (BY 2008 $M)
O&S Cost Variance
Category |  | BY 2008 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Sep 2015 SAR
1651.2
Programmatic/Planning Factors 30.1 Revised estimate due to shift in buy profile to align with FY
2017 PB.
Cost Estimating Methodology -36.8 Removal of unit operations costs. Army requirements for fuel, oil and lubricants for SANR will be incurred by the host platform.
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes -6.7
Current Estimate 1644.5
Disposal Estimate Details
Date of Estimate: December 30, 2015
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2008 $M): Total costs for disposal of all Channels are 1.6