## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-471
Armored Multi-Purpose Vehicle (AMPV)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 9
Schedule 10
Performance 12
Track to Budget 18
Cost and Funding 19
Low Rate Initial Production 26
Foreign Military Sales 27
Nuclear Costs 27
Unit Cost 28
Cost Variance 31
Contracts 34
Deliveries and Expenditures 35
Operating and Support Cost 36

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Armored Multi-Purpose Vehicle (AMPV)
DoD Component
Army
Responsible Office
COL Michael Milner
6501 E. 11 Mile Road/Mail Stop 563
Warren, MI 48397-5000
michael.w.milner.mil@mail.mil
Phone: | 586-282-0968
Fax: | 586-282-7797
DSN Phone: | 786-0968
DSN Fax: | 786-7797
Date Assigned: | September 5, 2014
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated May 12, 2015
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated May 12, 2015

## Table 6
Mission and Description
The Armored Multi-Purpose Vehicle (AMPV) is the materiel solution for replacement of the Army's M113 Armored Personnel Carrier Family of Vehicles (FoV) within the Armored Brigade Combat Team (ABCT). It will mitigate current and future capability gaps in force protection, mobility, reliability, and interoperability across the Spectrum of Conflict. The AMPV will replace five mission roles currently performed by the M113 FoV by transferring the current M113 Mission Equipment Packages to a new Military Vehicle Derivative platform. In total, the AMPV FoV will account for approximately 30% of the ABCT’s tracked fleet and consists of the following five variants:
1. Mission Command Vehicle: This platform enables effective mission command planning and execution for both the Command Post and Tactical Command Vehicle versions. It will host current Battle Command Systems, communications equipment future replacements, and upgrades of hardware and software.
2. Medical Treatment Vehicle: This platform will provide a protected surgical environment, with adequate lighting and accessible medical equipment. It will provide a capability for immediate medical care for one patient by a medical crew of four.
3. Medical Evacuation Vehicle: This platform will conduct combat medical evacuation activities and provide evacuation for up to four litter or six ambulatory patients, with a crew of three medical attendants.
4. General Purpose Vehicle: This platform will operate throughout the battle space by conducting re-supply, maintenance, casualty evacuation, and other tasks within the formation.
5. Mortar Carrier Vehicle: This platform will provide immediate responsive fire support to conduct fast-paced offensive operations.

## Table 7
Executive Summary
Program Highlights since Last Report:
Since the initial June 2015 SAR for AMPV, a successful Integrated Baseline Review (IBR) occurred at BAE’s facility on August 8-10, 2015. The IBR verified that the contractor has a baseline in place to accomplish the EMD scope of work on time and within budget.
A Configuration Steering Board (CSB) was held on September 23, 2015 that approved modifications to Key System Attribute (KSA) 5 (Power/Power Management) and KSA 16 (Transportability). These modifications made minor adjustments to align requirements with emerging design. The CSB decision memorandum was signed by the Army Acquisition Executive on December 6, 2015. The program intends to conduct a trigger CSB prior to Critical Design Review (CDR) to resolve any remaining requirements compliance issues.
On May 26, 2015, PM AMPV modified the contract with BAE to update the Mission Command (MCmd) vehicle to meet the Army’s latest network requirements. To assess BAE’s progress towards meeting these changes the Government and BAE completed an Artifact Review (AR) October 20-21, 2015. During the AR, BAE presented the additional MCmd equipment in the Materials and Equipment Matrix that will support all the mission roles, and demonstrated the MCmd variant’s readiness to continue with detailed design for CDR.
A joint Government and BAE Technical Review (TR) was held on December 8-9, 2015 to close out Preliminary Design Review (PDR) exit criteria. This successful review included key stakeholders from OSD, Maneuver Center of Excellence, Armaments Research, Development and Engineering Center, and Army Test and Evaluation Command. The Procurement Contracting Officer (PCO) notified BAE of PDR completion on January 21, 2016.
The FY 2016 Omnibus Appropriations Bill decremented FY 2016 RDT&E funding by $4M assigned to Program Management Growth. While this decrement will cause a slight re-prioritization of selected efforts in FY 2016, there is sufficient funding to execute critical planned FY 2016 work. In accordance with standard practices, the program’s EVM baseline reflects a combination of detailed work packages and higher level planning packages. Since the detailed work packages encompass all FY 2016 effort, and since these work packages were generated with the knowledge of the $4M funding decrement, the impact of the decrement has been mitigated by the program’s planning process.
As required by section 2366b, title 10, U.S.C., the USD(AT&L) certified the program on December 22, 2014 with three waivers. Two of the waivers are no longer relevant as the actions that necessitated the waivers are now complete. The remaining waiver and status is as follows:
Provision (2), Preliminary Design Review (PDR): The DAE waived this requirement because a Technology Maturation and Risk Reduction Phase was not required based on the maturity of the technology. The DAE determined that delaying the start of EMD until completion of the PDR and post-PDR assessment would create unnecessarily delays and increased costs. The strategy to procure a Military Vehicle Derivative and to integrate Government defined, mature subsystems supported this waiver.
There are no significant software-related issues with this program at this time.
History of Significant Developments since Program Initiation:
June 21, 2013: The AMPV CDD was approved.
December 9, 2014: The AMPV Milestone B DAB was held.
December 22, 2014: The ADM was signed by the DAE authorizing AMPV to enter at Milestone B. The ADM directed the Army to fund the AMPV program to the OSD CAPE ICE.

## Table 8
December 23, 2014: A Cost Plus Incentive Fee EMD contract was awarded to BAE Systems Land & Armaments.
March 24, 2015: The System Requirements Review (SRR) was completed. The SRR deemed the program ready to proceed into preliminary design.
May 12, 2015: APB approved.
June 18, 2015: The PDR was held and ensured that the allocated baseline was: properly documented, assessed to be consistent with CDD requirements and under configuration control. All PDR items were closed by the PCO on January 21, 2016.

## Table 9
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 10
Schedule
None
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | Dec 2014 | Dec 2014 | Dec 2014 | Dec 2014
Preliminary Design Review | Jun 2015 | Jun 2015 | Dec 2015 | Jun 2015
Critical Design Review | Jun 2016 | Jun 2016 | Dec 2016 | Jun 2016
Developmental Test Start | Jun 2017 | Jun 2017 | Dec 2017 | Jun 2017
Limited User Test Start | Aug 2018 | Aug 2018 | Feb 2019 | Aug 2018
Milestone C | Feb 2019 | Feb 2019 | Aug 2019 | Feb 2019
LRIP LFT&E Start | Mar 2020 | Mar 2020 | Sep 2020 | Mar 2020
IOT&E Start | Feb 2021 | Feb 2021 | Aug 2021 | Feb 2021
First Unit Equipped | Sep 2021 | Sep 2021 | Mar 2022 | Sep 2021
Full Rate Production | Oct 2021 | Oct 2021 | Apr 2022 | Oct 2021
Initial Operational Capability | Mar 2022 | Mar 2022 | Sep 2022 | Mar 2022
Full Operational Capability | Dec 2023 | Dec 2023 | Jun 2024 | Dec 2023
Change Explanations

## Table 11
Acronyms and Abbreviations
IOT&E - Initial Operational Test & Evaluation LFT&E - Live Fire Test & Evaluation

## Table 12
Performance
Performance |  | Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
KPP 1 Net Ready
The capability, system, | The capability, system, | The capability, system, | TBD | AMPV
and/or service must fully | and/or service must fully | and/or service must fully |  | Management
support execution of all | support execution of all | support execution of Joint |  | estimates
operational activities and | operational activities and | critical operational activities |  | that the
information exchanges | information exchanges | and information exchanges |  | program will
identified in DoD Enterprise | identified in DoD Enterprise | identified in the DoD |  | achieve the
Architecture and solution | Architecture and solution | Enterprise Architecture and |  | Threshold
architectures based on | architectures based on | solution architectures |  | requirement.
integrated DoDAF content, | integrated DoDAF content, | based on integrated
and must satisfy the | and must satisfy the | DoDAF content, and must
technical requirements for | technical requirements for | satisfy the technical
transition to Net-Centric | transition to Net-Centric | requirements for transition
military operations to | military operations to | to Net-Centric military
include: 1) Solution | include: 1) Solution | operations to include: 1)
architecture products | architecture products | Solution architecture
compliant with DoD | compliant with DoD | products compliant with
Enterprise Architecture | Enterprise Architecture | DoD Enterprise
based on integrated | based on integrated | Architecture based on
DoDAF content, including | DoDAF content, including | integrated DoDAF content,
specified operationally | specified operationally | including specified
effective information | effective information | operationally effective
exchanges 2) Compliant | exchanges 2) Compliant | information exchanges 2)
with Net-Centric Data | with Net-Centric Data | Compliant with Net-Centric
Strategy and Net-Centric | Strategy and Net-Centric | Data Strategy and Net-
Services Strategy, and the | Services Strategy, and the | Centric Services Strategy,
principles and rules | principles and rules | and the principles and rules
identified in the DoD IEA, | identified in the DoD IEA, | identified in the DoD IEA,
excepting tactical and non- | excepting tactical and non- | excepting tactical and non-
IP communications 3) | IP communications 3) | IP Communications 3)
Compliant with GIG | Compliant with GIG | Compliant with GIG
Technical Guidance to | Technical Guidance to | Technical Guidance to
include IT standards | include IT standards | include IT standards
identified in the TV-1 and | identified in the TV-1 and | identified in the TV-1 and
implementation guidance of | implementation guidance of | implementation guidance of
GESPs, necessary to meet | GESPs, necessary to meet | GESPs necessary to meet
all operational | all operational | all operational
requirements specified in | requirements specified in | requirements specified in
the DoD Enterprise | the DoD Enterprise | the DoD Enterprise
Architecture and solution | Architecture and solution | Architecture and solution
architecture views 4) IA | architecture views 4) IA | architecture views 4) IA
requirements including | requirements including | requirements including
availability, integrity, | availability, integrity, | availability, integrity,
authentication, | authentication, | authentication,
confidentiality, and non- | confidentiality, and non- | confidentiality, non-

## Table 13
repudiation, and issuance of an ATO by the DAA, and 5) Supportability requirements to include SAASM, spectrum, and JTRS requirements. | repudiation, and issuance of an ATO by the DAA, and 5) Supportability requirements to include SAASM, spectrum, and JTRS requirements. | repudiation, and issuance of an IATO or ATO by the DAA, and 5) supportability requirements to include SAASM, spectrum, and JTRS requirements.
KPP 3 Force Protection
Objective values listed in | Objective values listed in | The AMPV will provide | TBD | AMPV
Table 6.1 and shall provide | Table 6.1 and shall provide | protection for crew and |  | Management
for spall reducing floor | for spall reducing floor | occupant compartments to |  | estimates
material or spall blanket. | material or spall blanket. | meet mission |  | that the
|  | requirements. A kitting |  | program will
|  | strategy can be used for |  | achieve the
|  | selected threats as detailed |  | Threshold
|  | in Table 6.1. The protection |  | requirement.
level from ballistic
engagements shall be
based on the most recent
injury criteria thresholds
provided by the ARL SLAD.
At a minimum, the AMPV
will provide integral
protection for the crew and
occupants from serious or
greater injuries due to on-
board fires, various blast,
shock, overpressure,
fragments and accelerative
effects of attack by the
threshold threats listed in
the Table 6.1 for threat
weapons systems. The
AMPV shall prevent a
sustained fuel fire when
fuel container(s) are
exposed to the RPG, IED,
and EFP threats and
conditions specified in
Table 6.1. The AMPV shall
minimize spall from
overmatching threats.
KPP 4 Sustainment
The AMPV, at full combat | The AMPV, at full combat | The AMPV, at full combat | TBD | AMPV
configuration (excluding | configuration (excluding | configuration (excluding |  | Management
failures and maintenance | failures and maintenance | failures and maintenance |  | estimates
of the Government directed | of the Government directed | of the Government directed |  | that the
GFE/GFM MEP), shall | GFE/GFM MEP), shall | GFE/GFM MEP), shall |  | program will
achieve an Ao of at least | achieve an Ao of at least | achieve an Ao of at least |  | achieve the
93.3% when measured | 93.3% when measured | 91.8% when measured |  | Threshold
continuously over a three- | continuously over a three- | continuously over a three- |  | requirement.
day mission (consistent | day mission (consistent | day mission (consistent
with the General Purpose | with the General Purpose | with the General Purpose

## Table 14
M113A3 Mission Profile | M113A3 Mission Profile | M113A3 Mission Profile
defined in the HBCT | defined in the HBCT | defined in the HBCT
OMS/MP) with only SA | OMS/MP) with only SA | OMS/MP) with only SA
failures factored into the Ao | failures factored into the Ao | failures factored into the Ao
assessment. The AMPV | assessment. The AMPV | assessment. The AMPV
FDSC shall include all | FDSC shall include all | FDSC shall include all
provisions necessary to | provisions necessary to | provisions necessary to
fully address each vehicle | fully address each vehicle | fully address each vehicle
variant with GFE/GFM MEP | variant with GFE/GFM MEP | variant with GFE/GFM MEP
integrated therein, to | integrated therein, to | integrated therein, to
support the supplementary | support the supplementary | support the supplementary
assessment/evaluation of | assessment/evaluation of | assessment/evaluation of
total vehicle system | total vehicle system | total vehicle system
availability and hold | availability and hold | availability and hold
accountable vehicle | accountable vehicle | accountable vehicle
development for proper | development for proper | development for proper
functional integration of the | functional integration of the | functional integration of the
MEP (MEP failures caused | MEP (MEP failures caused | MEP (MEP failures caused
by integration issues are | by integration issues are | by integration issues are
chargeable to the host | chargeable to the host | chargeable to the host
vehicle). Accordingly, | vehicle). Accordingly, | vehicle). Accordingly,
availability of the MEP is | availability of the MEP is | availability of the MEP is
not reduced (degraded or | not reduced (degraded or | not reduced (degraded or
lessened) beyond that of its | lessened) beyond that of its | lessened) beyond that of its
current performance as a | current performance as a | current performance as a
result of integration into the | result of integration into the | result of integration into the
host AMPV chassis. The | host AMPV chassis. The | host AMPV chassis. The
AMPV at full combat | AMPV at full combat | AMPV at full combat
configuration (excluding | configuration (excluding | configuration (excluding
Department of the Army | Department of the Army | Department of the Army
directed GFE/GFM MEP | directed GFE/GFM MEP | directed GFE/GFM MEP)
will achieve an Am of not | will achieve an Am of not | will achieve an Am of not
less than 86.5% when | less than 86.5% when | less than 81.5% when
assessed at the Army fleet | assessed at the Army fleet | assessed at the Army fleet
level. | level. | level.
KPP 5 Energy
Energy objective values are | Energy objective values are | Energy threshold values | TBD | AMPV
developed at a vehicle | developed at a vehicle | are developed at a vehicle |  | Management
weight meeting the | weight meeting the | weight meeting the |  | estimates
Survivability KPP and | Survivability KPP and | Survivability KPP and |  | that the
Force Protection KPP | Force Protection KPP | Force Protection KPP |  | program will
objectives and other | objectives and other | thresholds and other |  | achieve the
performance KPP | performance KPP | performance KPP |  | Threshold
objectives while ensuring | objectives while ensuring | thresholds while ensuring |  | requirement.
the vehicle can operate | the vehicle can operate | the vehicle can operate
within fuel apportioned for | within fuel apportioned for | within fuel apportioned for
the AMPV during the 72- | the AMPV during the 72- | the AMPV during the 72-
hour mission cycle of | hour mission cycle of | hour mission cycle of
HBCT OMS/MP (for each | HBCT OMS/MP (for each | HBCT OMS/MP (for each
individual mission role). | individual mission role). | individual mission role).
The AMPV, using standard | The AMPV, using standard | The AMPV, using standard
(JP8) fuel, will consume | (JP8) fuel, will consume | (JP8) fuel, will consume
fuel at, or better than, the | fuel at, or better than, the | fuel at, or better than, the

## Table 15
level identified in Table 6.2 | level identified in Table 6.2 | level identified in Table 6.2
(O) at full combat | (O) at full combat | (T) at full combat
configuration, when | configuration, when | configuration, when
evaluated at sustained | evaluated at sustained | evaluated at sustained
speeds of 30-MPH on | speeds of 30-MPH on | speeds of 30-MPH on
primary roads, | primary roads, | primary roads,
maneuvering the distance | maneuvering the distance | maneuvering the distance
outlined in the HBCT | outlined in the HBCT | outlined in the HBCT
OMS/MP for the 72-hour | OMS/MP for the 72-hour | OMS/MP for the 72-hour
mission cycle without | mission cycle without | mission cycle without
refueling, and while | refueling, and while | refueling, and while
providing power sustained | providing power sustained | providing power at
loads to support all | loads to support all | sustained loads to support
electronic equipment with a | electronic equipment with a | all electronic equipment
50% spare electrical | 50% spare electrical | with a 20% spare electrical
capacity for all variants. | capacity for all variants. | capacity for all variants.
The AMPV will consume | The AMPV will consume | The AMPV will consume
fuel at, or better than, the | fuel at, or better than, the | fuel at, or better than, the
level identified in Table 6.2 | level identified in Table 6.2 | level identified in Table 6.2
for stationary operations | for stationary operations | for stationary operations
(Idle/GPH) when evaluated | (Idle/GPH) when evaluated | (Idle/GPH) when evaluated
at providing power at | at providing power at | at providing power at
sustained loads to support | sustained loads to support | sustained loads to support
all electronic equipment | all electronic equipment | all electronic equipment
with a 50% spare electrical | with a 50% spare electrical | with a 20% spare electrical
capacity for all variants. | capacity for all variants. | capacity for all variants.
KPP 6 Mobility
The AMPV mobility is | The AMPV mobility is | (T=O) The AMPV mobility | TBD | AMPV
aligned with Survivability | aligned with Survivability | is aligned with Survivability |  | Management
and Force Protection KPP | and Force Protection KPP | and Force Protection KPP |  | estimates
requirements. The vehicle | requirements. The vehicle | requirements. The vehicle |  | that the
must be capable of | must be capable of | must be capable of |  | program will
traversing steep hills, | traversing steep hills, | traversing steep hills, |  | achieve the
valleys, and man-made | valleys, and man-made | valleys, and man-made |  | Threshold
objects typical in cross- | objects typical in cross- | objects typical in cross- |  | requirement.
country and urban terrain. | country and urban terrain. | country and urban terrain.
The AMPV must be able to | The AMPV must be able to | The AMPV must be able to
maintain mobility threshold | maintain mobility threshold | maintain mobility threshold
as outlined in the HBCT | as outlined in the HBCT | as outlined in the HBCT
OMS/MP. The platform | OMS/MP. The platform | OMS/MP. The platform
must have the speed and | must have the speed and | must have the speed and
mobility to successfully | mobility to successfully | mobility to successfully
fulfill its role in the BCT and | fulfill its role in the BCT and | fulfill its role in the BCT and
maintain its doctrinal | maintain its doctrinal | maintain its doctrinal
positioning within the ABCT | positioning within the ABCT | positioning within the ABCT
formation. | formation. | formation.
KPP 7 Training
Upon completion of FUE | Upon completion of FUE | Upon completion of FUE | TBD | AMPV
NET the soldier, both | NET the soldier, both | NET the soldier, both |  | Management
operator and maintainer, | operator and maintainer, | operator and maintainer, |  | estimates
will successfully | will successfully | will successfully |  | that the
accomplish >99% (O) of | accomplish >99% (O) of | accomplish >80% (T) of |  | program will

## Table 16
the critical tasks and >80% (O) of the non-critical tasks required to operate and maintain the AMPV. Further, institutional and sustainment training will be IAW AR 71-70 and AR 350- 1. | the critical tasks and >80% (O) of the non-critical tasks required to operate and maintain the AMPV. Further, institutional and sustainment training will be IAW AR 71-70 and AR 350- 1. | the critical tasks and >70% (T) of the non-critical tasks required to operate and maintain the AMPV. Further, institutional and sustainment training will be IAW AR 71-70 and AR 350- 1. |  | achieve the Threshold requirement.
KPP 8 Lethality
The Lethality KPP | The Lethality KPP | (T=O) The Lethality KPP | TBD | AMPV
addresses the GCV ICD | addresses the GCV ICD | addresses the GCV ICD |  | Management
Capability 3, Lethality. The | Capability 3, Lethality. The | Capability 3, Lethality. The |  | estimates
AMPV MC will host and | AMPV MC will host and | AMPV MC will host and |  | that the
integrate the current M121 | integrate the current M121 | integrate the current M121 |  | program will
120-mm mortar system to | 120-mm mortar system to | 120-mm mortar system to |  | achieve the
provide indirect fires in | provide indirect fires in | provide indirect fires in |  | Threshold
support of maneuver units. | support of maneuver units. | support of maneuver units. |  | requirement.
The mortar system must | The mortar system must | The mortar system must
accommodate a | accommodate a | accommodate a
smoothbore 120-mm | smoothbore 120-mm | smoothbore 120-mm
mortar system, which must | mortar system, which must | mortar system, which must
be capable of firing the full | be capable of firing the full | be capable of firing the full
family of mortar | family of mortar | family of mortar
ammunition: HE, | ammunition: HE, | ammunition: HE,
illumination, IR illumination, | illumination, IR illumination, | illumination, IR illumination,
smoke, precision | smoke, precision | smoke, precision
munitions, and future | munitions, and future | munitions, and future
extended range munitions. | extended range munitions. | extended range munitions.
The system will integrate | The system will integrate | The system will integrate
the current M95 Mortar Fire | the current M95 Mortar Fire | the current M95 Mortar Fire
Control System-Mounted | Control System-Mounted | Control System-Mounted
and carry current ground | and carry current ground | and carry current ground
mounting and firing | mounting and firing | mounting and firing
equipment as utilized on | equipment as utilized on | equipment as utilized on
the M1064 MC. The AMPV | the M1064 MC. The AMPV | the M1064 MC. The AMPV
MC’s lethality, | MC’s lethality, | MC’s lethality,
responsiveness and | responsiveness and | responsiveness and
accuracy will be equal to or | accuracy will be equal to or | accuracy will be equal to or
greater than the M1064 | greater than the M1064 | greater than the M1064
MC. | MC. | MC.
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Capability Development Document (CDD) dated June 21, 2013
Change Explanations
None

## Table 17
Notes
Detailed KPP information is available in the approved AMPV CDD, dated June 21, 2013, including Table 6.1 and Table 6.2 referenced in the Performance Characteristics above.
The AMPV program conducted a Preliminary Design Review and is now executing detailed design activities to re-assess compliance at the Critical Design Review.
Acronyms and Abbreviations
% - percent
ABCT - Armor Brigade Combat Team Am - Materiel Availability
Ao - Operational Availability AR - Army Regulation
ARL - Army Research Laboratory ATO - Authorization To Operate BCT - Brigade Combat Team
DAA - Designated Accrediting Authority
DoDAF - Department of Defense Architecture Framework EFP - Explosively Formed Penetrator
FDSC - Failure Definition and Scoring Criteria FUE - First Unit Equipped
GCV - Ground Combat Vehicle
GESP - GIG Enterprise Service Profile GFE - Government Furnished Equipment GFM - Government Furnished Material GIG - Global Information Grid
GPH - Gallons Per Hour
HBCT - Heavy Brigade Combat Team HE - High Explosive
IA - Information Assurance
IATO - Interim Authority To Operate IAW - In Accordance With
ICD - Initial Capability Document
IEA - Information Enterprise Architecture IED - Improvised Explosive Device
IP - Internet Protocol IR - InfraRed
IT - Information Technology
JTRS - Joint Tactical Radio System MC - Mortar Carrier
MEP - Mission Equipment Package mm - millimeter
MPH - Miles Per Hour
NET - New Equipment Training O - Objective
OMS/MP - Operational Mode Summary/Mission Profile RPG - Rocket Propelled Grenade
SA - System Abort
SAASM - Selective Availability Anti-Spoofing Module SLAD - Survivability/Lethality Analysis Directorate
T - Threshold
TV - Technical View

## Table 18
Track to Budget
RDT&E
Appn |  | BA | PE
Army 2040 05 0605028A
Project | Name
EB5 Armored Multi-Purpose Vehicle (AMPV)
Procurement
Appn |  | BA | PE
Army 2033 01 0211708A
Line Item | Name
2944G80819 Armored Multi Purpose Vehicle (AMPV)

## Table 19
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2015 $M |  |  |  | BY 2015 $M |  | TY $M
| SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Development Estimate |  | Current APB Development Objective |  | Current Estimate
RDT&E | 988.2 |  | 988.2 | 1087 |  | 1013 |  | 1073.8 |  | 1073.8 |  | 1081.8
Procurement | 9736.6 |  | 9736.6 | 10710.3 |  | 9736.8 |  | 12871 |  | 12871 |  | 12760.6
Flyaway | -- |  | -- | -- |  | 9183.8 |  | -- |  | -- |  | 12042.6
Recurring | -- |  | -- | -- |  | 9145.4 |  | -- |  | -- |  | 11999.8
Non Recurring | -- |  | -- | -- |  | 38.4 |  | -- |  | -- |  | 42.8
Support | -- |  | -- | -- |  | 553 |  | -- |  | -- |  | 718
Other Support | -- |  | -- | -- |  | 370.9 |  | -- |  | -- |  | 479.1
Initial Spares | -- |  | -- | -- |  | 182.1 |  | -- |  | -- |  | 238.9
MILCON | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 10724.8 |  | 10724.8 | N/A |  | 10749.8 |  | 13944.8 |  | 13944.8 |  | 13842.4
Current APB Cost Estimate Reference
CAPE ICE dated December 08, 2014
Confidence Level
Confidence Level of cost estimate for current APB: 50%
This estimate, like all previous OSD CAPE estimates, is built upon a product-oriented work breakdown structure; is based on historical actual cost information to the maximum extent possible; and, most importantly, is based on conservative assumptions that are consistent with actual demonstrated contractor and Government performance for a series of acquisition programs in which the Department was successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for Major Defense Acquisition Programs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.

## Table 20
Total Quantity
Quantity | SAR Baseline Development Estimate | Current APB Development | Current Estimate
RDT&E | 39 | 39 | 39
Procurement | 2897 | 2897 | 2897
Total | 2936 | 2936 | 2936
Quantity Notes
To support the development phase 39 AMPVs are required: 29 AMPV prototype vehicles for EMD and ten production representative AMPVs for Full Up System Level live fire tests; the live fire test assets are RDT&E-funded in LRIP.

## Table 21
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 155.2 | 226.2 |  | 184.2 |  | 200.8 |  | 124.3 |  | 95.9 |  | 95.2 |  | 0 |  | 1081.8
Procurement | 0 | 0 |  | 0 |  | 193.7 |  | 397.3 |  | 495.7 |  | 691.2 |  | 10982.7 |  | 12760.6
MILCON | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 155.2 | 226.2 |  | 184.2 |  | 394.5 |  | 521.6 |  | 591.6 |  | 786.4 |  | 10982.7 |  | 13842.4
| -- | -- |  | -- |  | -- |  | -- |  | -- |  | -- |  | -- |  | --
Funding Notes
The ADM directed the Army to fund the AMPV program to the OSD CAPE ICE in the FY 2016 PB. The FY 2016 Omnibus Appropriations Bill decremented FY 2016 RDT&E funding by $4M assigned to Program Management Growth. While this decrement will cause a slight re-prioritization of selected efforts in FY 2016, there is sufficient funding to execute critical planned FY 2016 work.
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 39 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 39
Production | 0 |  | 0 |  | 0 | 0 | 42 |  | 107 |  | 130 |  | 180 |  | 2438 |  | 2897
PB 2017 Total | 39 |  | 0 |  | 0 | 0 | 42 |  | 107 |  | 130 |  | 180 |  | 2438 |  | 2936
| -- |  | -- |  | -- | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --

## Table 22
Cost and Funding
Annual Funding By Appropriation
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.8
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.3
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 88.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 226.2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 184.2
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 200.8
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 124.3
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 95.9
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 95.2
Subtotal |  | 39 | -- |  | -- |  | -- |  | -- |  | -- |  | 1081.8

## Table 23
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.6
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 86.4
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 217.9
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 174.2
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 186.2
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 113
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 85.5
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83.2
Subtotal |  | 39 | -- |  | -- |  | -- |  | -- |  | -- |  | 1013

## Table 24
Annual Funding 2033 ¦ Procurement ¦ Procurement of Weapons and Tracked Combat Vehicles, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2018 |  | 42 | 166.2 |  | 3.5 |  | 18.1 |  | 187.8 |  | 5.9 |  | 193.7
2019 |  | 107 | 349 |  | 7.3 |  | 14.5 |  | 370.8 |  | 26.5 |  | 397.3
2020 |  | 130 | 411.2 |  | 38.1 |  | 6.6 |  | 455.9 |  | 39.8 |  | 495.7
2021 |  | 180 | 591.9 |  | 46.7 |  | 3.6 |  | 642.2 |  | 49 |  | 691.2
2022 |  | 180 | 569.6 |  | 67.6 |  | -- |  | 637.2 |  | 55.1 |  | 692.3
2023 |  | 180 | 573.6 |  | 69.6 |  | -- |  | 643.2 |  | 50.6 |  | 693.8
2024 |  | 180 | 580.2 |  | 71.7 |  | -- |  | 651.9 |  | 35.9 |  | 687.8
2025 |  | 180 | 650.7 |  | 73.8 |  | -- |  | 724.5 |  | 38.1 |  | 762.6
2026 |  | 180 | 662.8 |  | 76 |  | -- |  | 738.8 |  | 39.4 |  | 778.2
2027 |  | 180 | 675.8 |  | 78.2 |  | -- |  | 754 |  | 39.4 |  | 793.4
2028 |  | 180 | 689.6 |  | 80.5 |  | -- |  | 770.1 |  | 40.4 |  | 810.5
2029 |  | 180 | 704.2 |  | 82.9 |  | -- |  | 787.1 |  | 41.1 |  | 828.2
2030 |  | 180 | 719.4 |  | 85.4 |  | -- |  | 804.8 |  | 41.9 |  | 846.7
2031 |  | 180 | 735.2 |  | 87.9 |  | -- |  | 823.1 |  | 42.8 |  | 865.9
2032 |  | 180 | 751.7 |  | 90.5 |  | -- |  | 842.2 |  | 43.8 |  | 886
2033 |  | 180 | 768.7 |  | 79.2 |  | -- |  | 847.9 |  | 44.8 |  | 892.7
2034 |  | 180 | 786.4 |  | 61.2 |  | -- |  | 847.6 |  | 45.8 |  | 893.4
2035 |  | 98 | 466.1 |  | 27 |  | -- |  | 493.1 |  | 37.7 |  | 530.8
2036 |  | -- | -- |  | 20.4 |  | -- |  | 20.4 |  | -- |  | 20.4
Subtotal |  | 2897 | 10852.3 |  | 1147.5 |  | 42.8 |  | 12042.6 |  | 718 |  | 12760.6

## Table 25
Annual Funding 2033 ¦ Procurement ¦ Procurement of Weapons and Tracked Combat Vehicles, Army
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2018 |  | 42 | 152.3 |  | 3.2 |  | 16.5 |  | 172 |  | 5.4 |  | 177.4
2019 |  | 107 | 313.5 |  | 6.6 |  | 13 |  | 333.1 |  | 23.7 |  | 356.8
2020 |  | 130 | 362.1 |  | 33.6 |  | 5.8 |  | 401.5 |  | 35 |  | 436.5
2021 |  | 180 | 511 |  | 40.3 |  | 3.1 |  | 554.4 |  | 42.3 |  | 596.7
2022 |  | 180 | 482.1 |  | 57.2 |  | -- |  | 539.3 |  | 46.6 |  | 585.9
2023 |  | 180 | 475.9 |  | 57.8 |  | -- |  | 533.7 |  | 42 |  | 575.7
2024 |  | 180 | 472 |  | 58.3 |  | -- |  | 530.3 |  | 29.2 |  | 559.5
2025 |  | 180 | 518.9 |  | 58.9 |  | -- |  | 577.8 |  | 30.4 |  | 608.2
2026 |  | 180 | 518.2 |  | 59.5 |  | -- |  | 577.7 |  | 30.8 |  | 608.5
2027 |  | 180 | 518 |  | 60 |  | -- |  | 578 |  | 30.2 |  | 608.2
2028 |  | 180 | 518.3 |  | 60.5 |  | -- |  | 578.8 |  | 30.3 |  | 609.1
2029 |  | 180 | 518.8 |  | 61.1 |  | -- |  | 579.9 |  | 30.3 |  | 610.2
2030 |  | 180 | 519.7 |  | 61.6 |  | -- |  | 581.3 |  | 30.3 |  | 611.6
2031 |  | 180 | 520.7 |  | 62.2 |  | -- |  | 582.9 |  | 30.3 |  | 613.2
2032 |  | 180 | 521.9 |  | 62.8 |  | -- |  | 584.7 |  | 30.4 |  | 615.1
2033 |  | 180 | 523.2 |  | 53.9 |  | -- |  | 577.1 |  | 30.5 |  | 607.6
2034 |  | 180 | 524.8 |  | 40.8 |  | -- |  | 565.6 |  | 30.6 |  | 596.2
2035 |  | 98 | 304.9 |  | 17.7 |  | -- |  | 322.6 |  | 24.7 |  | 347.3
2036 |  | -- | -- |  | 13.1 |  | -- |  | 13.1 |  | -- |  | 13.1
Subtotal |  | 2897 | 8276.3 |  | 869.1 |  | 38.4 |  | 9183.8 |  | 553 |  | 9736.8

## Table 26
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2014-12-23 | 2014-12-23
Approved Quantity | 289 | 289
Reference | Milestone B ADM | Milestone B ADM
Start Year | 2018 | 2018
End Year | 2022 | 2022

## Table 27
Foreign Military Sales
None
Nuclear Costs
None

## Table 28
Unit Cost
Unit Cost Report
Item |  | BY 2015 $M | BY 2015 $M |  | % Change
|  | Current UCR Baseline (May 2015 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 10724.8 |  |  | 10749.8
Quantity | 2936 |  |  | 2936
Unit Cost | 3.653 |  |  | 3.661 |  | 0.22
Average Procurement Unit Cost
Cost | 9736.6 |  |  | 9736.8
Quantity | 2897 |  |  | 2897
Unit Cost | 3.361 |  |  | 3.361 |  | 0
Item |  | BY 2015 $M | BY 2015 $M |  | % Change
|  | Original UCR Baseline (May 2015 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 10724.8 |  |  | 10749.8
Quantity | 2936 |  |  | 2936
Unit Cost | 3.653 |  |  | 3.661 |  | 0.22
Average Procurement Unit Cost
Cost | 9736.6 |  |  | 9736.8
Quantity | 2897 |  |  | 2897
Unit Cost | 3.361 |  |  | 3.361 |  | 0

## Table 29
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2015 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | May 2015 |  |  |  |  | 3.653 |  |  | 3.361 |  |  | 4.75 |  |  | 4.443
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Current APB |  |  | May 2015 |  |  |  |  | 3.653 |  |  | 3.361 |  |  | 4.75 |  |  | 4.443
Prior Annual SAR |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Current Estimate |  |  | Dec 2015 |  |  |  |  | 3.661 |  |  | 3.361 |  |  | 4.715 |  |  | 4.405
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
4.750 -0.044 0.000 0.000 0.000 0.009 0.000 0.000 -0.035 4.715
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
4.443 -0.038 0.000 0.000 0.000 0.000 0.000 0.000 -0.038 4.405

## Table 30
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Dec 2014 | N/A | Dec 2014
Milestone C | N/A | Feb 2019 | N/A | Feb 2019
IOC | N/A | Mar 2022 | N/A | Mar 2022
Total Cost (TY $M) | N/A | 13944.8 | N/A | 13842.4
Total Quantity | N/A | 2936 | N/A | 2936
PAUC | N/A | 4.75 | N/A | 4.715

## Table 31
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 1073.8 | 12871 | -- | 13944.8
Previous Changes
Economic | -13.4 | -47.1 | -- | -60.5
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 27.8 | -1.2 | -- | 26.6
Other | -- | -- | -- | --
Support | -- | -4.4 | -- | -4.4
Subtotal | 14.4 | -52.7 | -- | -38.3
Current Changes
Economic | -4.9 | -63 | -- | -67.9
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -1.5 | 0.9 | -- | -0.6
Other | -- | -- | -- | --
Support | -- | 4.4 | -- | 4.4
Subtotal | -6.4 | -57.7 | -- | -64.1
Total Changes | 8 | -110.4 | -- | -102.4
CE - Cost Variance | 1081.8 | 12760.6 | -- | 13842.4
CE - Cost & Funding | 1081.8 | 12760.6 | -- | 13842.4

## Table 32
Summary BY 2015 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
988.2 9736.6 -- 10724.8
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 26.5 |  | -1.9 |  | -- |  | 24.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -3.1 |  | -- |  | -3.1
Subtotal |  | 26.5 |  | -5 |  | -- |  | 21.5
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -1.7 |  | 0.7 |  | -- |  | -1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 4.5 |  | -- |  | 4.5
Subtotal |  | -1.7 |  | 5.2 |  | -- |  | 3.5
Total Changes |  | 24.8 |  | 0.2 |  | -- |  | 25
CE - Cost Variance |  | 1013 |  | 9736.8 |  | -- |  | 10749.8
CE - Cost & Funding |  | 1013 |  | 9736.8 |  | -- |  | 10749.8
Previous Estimate: June 2015

## Table 33
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -4.9
Revised Estimate to align with FY 2017 PB. (Estimating) | -2.9 | -2.7
Adjustment for current and prior escalation. (Estimating) | 1.2 | 1.2
RDT&E Subtotal | -1.7 | -6.4
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -63
Revised Estimate to align with FY 2017 PB. (Estimating) | 0.7 | 0.9
Increase in Other Support to align Procurement estimate with the FY 2017 PB (Support) | 0.3 | -0.2
Increase in Initial Spares to align Procurement estimate with the FY 2017 PB. (Support) | 4.2 | 4.6
Procurement Subtotal | 5.2 | -57.7

## Table 34
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: AMPV EMD Contract with LRIP Options
Contractor: BAE Systems Land & Armaments, L.P.
Contractor Location: 34201 Van Dyke Avenue
Sterling Heights, MI 48312-4648
Contract Number: W56HZV-15-C-A001
Contract Type: Cost Plus Incentive Fee (CPIF)
Award Date: December 23, 2014
Definitization Date: December 23, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
383.0 N/A 29 383.0 N/A 29 397.4 397.4
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/31/2016) -2.5 -5.1
Previous Cumulative Variances -1.0 -0.4
Net Change -1.5 -4.7
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to unplanned analysis related to requirement compliance (Human Factors Engineering, Reliability, Availability, and Maintainability Assessments, and Mobility Analyses) as well as under- budgeting and re-work associated with Preliminary Design Review deliverables (System Engineering, Software, Production Support).
The unfavorable net change in the schedule variance is due to subcontractor delays linked to extensions in the Smart Power Management Unit Test Readiness Review and delays in completion of drawings necessary for procurement of prototype hardware and Critical Design Review.
Notes
The change in Estimated Price at Completion is due to clarification and update to the contract Scope of Work, specifically tailoring language to articulate the Government's requirement for the contractor to produce designs for the hardware integration for all vehicle mission equipment within the AMPV Family of Vehicles.
The variant baseline concept change issued under modification P00004 to this contract is undefinitized. The negotiated value of this modification is $11,448,341.

## Table 35
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 39 | 0%
Production | 0 | 0 | 2897 | 0%
Total Program Quantity Delivered | 0 | 0 | 2936 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
13842.4
136.4
0.99%
25
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
5
20%
381.4
2.76%
The above data is current as of February 09, 2016.

## Table 36
Operating and Support Cost
Cost Estimate Details
Date of Estimate: December 08, 2014
Source of Estimate: CAPE ICE
Quantity to Sustain: 2897
Unit of Measure: Vehicle
Service Life per Unit: 26.00 Years
Fiscal Years in Service: FY 2021 - FY 2062
The 39 development vehicles will not be sustained.
Sustainment Strategy
The AMPV sustainment concept leverages existing organic structures for maintenance and supply support to maximize commonality and minimize the logistics footprint. By using an existing base platform materiel solution, the common and unique Line Replaceable Units (LRU) will be sustained with the Two Level Maintenance and sustainment repair concepts. Field-level maintenance will maintain, handle, and support the LRUs with the same concept as the existing Armor Brigade Combat Team (ABCT) structure. Sustainment-level maintenance will use common repair programs, facilities, and depots wherever economical and feasible. Newly developed maintenance tasks and support will be determined and supported by results from the Logistic Support Analysis, Level of Repair Analysis, Source of Repair Analysis, and Business Case Analysis and/or Management Analysis, as required.
Any new operator and maintainer training requirements will be determined by task analysis and results from the Logistics Demonstration, Limited User Test, and other vehicle tests. AMPV will provide Operator New Equipment Training and Field Maintenance New Equipment Training to each gaining unit. Mission equipment training will be provided by the corresponding equipment representatives.
PEO Ground Combat Systems performed the analysis required by section 2464, title 10 U.S.C. and determined that AMPV is a core system. PM AMPV is committed to developing the detailed requirements for core depot-level maintenance and repair capabilities as well as the associated sustaining workloads required to support such requirements when the vehicle configuration is solidified. A preliminary estimate of core depot hours, using an existing tracked vehicle as the baseline, was included in the section 2366b, title 10 U.S.C. certification. The LRIP option scope of work contains the development of a National Maintenance Work Requirement, which will be in place within four years of IOC.
The O&S estimate assumes that the AMPV will support the 20 ABCT, Active and National Guard Units, across the range of military operations and will train in environments typical in cross-country and urban terrain. It replaces the M113 Family of Vehicles (FoV), which comprise 30% of the ABCT vehicle fleet.
Antecedent Information
The Antecedent system is the M113 FoV. Antecedent estimate is based on data from O&S Management Information System and Army Manpower Cost System.

## Table 37
Annual O&S Costs BY2015 $M
Cost Element |  | AMPV Average Annual Cost Per Vehicle | [5 empty] | M113 (Antecedent) Vehicle
Unit-Level Manpower |  | 0.262 | [5 empty] | 0.263
Unit Operations |  | 0.033 | [5 empty] | 0.03
Maintenance |  | 0.074 | [5 empty] | 0.058
Sustaining Support |  | 0.023 | [5 empty] | 0.027
Continuing System Improvements |  | 0.012 | [5 empty] | 0.003
Indirect Support |  | 0.055 | [5 empty] | 0.055
Other |  | -- | [5 empty] | --
Total |  | 0.459 | [5 empty] | 0.436
Item | Total O&S Cost $M
| AMPV | [7 empty] | M113 (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 34540.1 |  |  | 37994.1 |  |  | 34540.1 |  | 32823.9
Then Year | 55313.8 |  |  | N/A |  |  | 55313.8 |  | N/A
Equation to Translate Annual Cost to Total Cost
Total Cost = # of systems * service life per system * average annual cost (BY 2015 $M)
$34,540.1 = 2897 * 26 * $0.458565 (BY 2015 $M)
O&S Cost Variance
Category |  |  | BY 2015 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Jun 2015 SAR
34540.1
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 34540.1
Disposal Estimate Details
Date of Estimate: December 08, 2014
Source of Estimate: CAPE ICE

## Table 38
Disposal/Demilitarization Total Cost (BY 2015 $M): Total costs for disposal of all Vehicle are 128.0