## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-278
CH-47F Improved Cargo Helicopter (CH-47F)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 13
Cost and Funding 14
Low Rate Initial Production 21
Foreign Military Sales 22
Nuclear Costs 22
Unit Cost 23
Cost Variance 26
Contracts 29
Deliveries and Expenditures 30
Operating and Support Cost 31

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
CH-47F Improved Cargo Helicopter (CH-47F)
DoD Component
Army
Responsible Office
LTC Richard Bratt
Office of the Project Manager Cargo Helicopters Building 5678
Redstone Arsenal, AL 35898-5280
richard.m.bratt.mil@mail.mil
Phone: | 256-313-3396
Fax: | 256-313-3604
DSN Phone: | 897-3396
DSN Fax: Date Assigned: | July 31, 2015
References
SAR Baseline (Production Estimate)
Army Acquisition Executive (AAE) Approved Acquisition Program Baseline (APB) dated November 22, 2004
Approved APB
Army Acquisition Executive (AAE) Approved Acquisition Program Baseline (APB) dated April 22, 2010

## Table 6
Mission and Description
The CH-47F Improved Cargo Helicopter (CH-47F) supports the Army's requirement to be strategically responsive across the full spectrum of operations. It will provide continued support, coverage, and sustainment of Maneuver, Fire Support, Air Defense, and Survivability mission areas. Its mission is transportation of ground forces, Class III/Class V supplies, and other battle critical cargo in support of all future contingencies. The CH-47F enables the Army to support the rapid response capability necessary for forcible and early entry contingency missions, as well as tactical and operational nonlinear, noncontiguous, simultaneous, or sequential operations, which will be characteristic of future operations.
The CH-47F is a future force system that supports the Army Vision. The CH-47F is a twin-turbine, tandem-rotor, heavy-lift transport helicopter with a useful payload of up to 25,000 pounds. The CH-47F's lift capability is invaluable as the Army transforms from a heavy-division dominated force to a more deployable medium weight force focused toward 21st Century Army requirements. The CH-47F, with its upgraded engines, the Common Avionics Architecture System (CAAS) with advanced avionics, monolithic machined frame components and airframe modifications, will reduce operating costs and continue to be a National asset providing peacetime disaster relief and wartime service to this country for another 20 years.
The CH-47F program fills the Army's Aviation Transformation Chinook requirement for upgraded aircraft and is comprised of both remanufactured and new aircraft. The total remanufactured aircraft will consist of CH-47Fs and MH-47Gs. The MH-47G configuration replaces the current MH-47E/Ds for Special Operations Forces. The CH-47F program installs a new digital cockpit, incorporates all new airframe components, and modifies the aircraft to reduce vibration. The CAAS digital cockpit will provide future growth potential. It includes a digital data bus that permits installation of enhanced communications and navigation equipment for improved situational awareness, mission performance, and survivability. New airframe structural components and modifications will reduce harmful vibrations, improving O&S efficiency and crew endurance. Other airframe modifications reduce the time required for aircraft tear down and build-up during C-5/C-17 deployment by 60 percent. These modifications significantly enhance the CH-47F's strategic deployment capability.

## Table 7
Executive Summary
The CH-47F program is in FRP and remains on schedule with 406 CH-47F aircraft on contract (234 New Build and 172 ReNew). The first lot of the Multiyear II contract (Lot 11) was awarded on June 10, 2013, the second lot (Lot 12) was awarded on December 26, 2013, and the third lot (Lot 14) was awarded on March 13, 2015. The first Multiyear II delivery occurred ahead of schedule on January 29, 2015. A total of 409 aircraft have been delivered as of January 31, 2016 (two RDT&E aircraft, 340 CH47F and 67 MH-47G). The FY 2013 Overseas Contingency Operations (OCO) funds of $231.3M were received in June 2013 for six CH-47F aircraft. The FY 2014 OCO funds of $386.0M were received in March 2014 for ten CH-47F aircraft. On December 23, 2014, an ADM resulting from a Configuration Steering Board increased the CH- 47F Army Acquisition Objective from 533 to 542. In January 2015, $347.4M in FY 2014 OCO funds for nine aircraft was rescinded.
The CH-47F Product Manager’s Office (PMO) is tasked by the Department of the Army to continue CH-47F training of Active Component (AC), Army National Guard (ARNG), and U.S. Army Reserve (USAR) Combat Aviation Brigades (CAB) via New Equipment Training (NET) through FY 2017. The CH-47F NET teams have completed fielding and training of all 13 AC CABs, the Honduras detachment, ten of 13 ARNG CABs and the USAR CABs. The PMO supports multiple contractor NET teams who provide concurrent training at separate locations.
The NET for the Washington/Oregon ARNG CAB was completed on September 30, 2015. The NET for the Illinois/South Carolina ARNG CAB was completed on November 20, 2015. The NET for the Mississippi/Florida ARNG CAB was completed on November 20, 2015. All ARNG NET was conducted in Savannah, Georgia.
The NET for the 2nd USAR CAB was completed on April 27, 2015. The NET for the 3rd USAR CAB was completed on July 1, 2015. This completed fielding and NET to the USAR CABs.
Additionally, the NET completed training and fielding of the first Multiyear II configured aircraft to the 1st Armored Division in July 2015, the 1-214th Aviation Regiment (Germany) in August 2015, and is currently fielding the 3rd Infantry Division with fielding scheduled to be completed in 3rd Quarter FY 2016.
Two CH-47F units are currently deployed to Operation Freedom Sentinel and Operation Inherent Resolve.
The CH-47F PMO has completed installation of Infrared Suppression System, Advanced Threat Infared Counter Measures, and other Army-directed modifications at the Millville, New Jersey modification center.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
ORD Approval | Nov 1997 | Nov 1997 | May 1998 | Nov 1997
Milestone II ASARC | Nov 1997 | Nov 1997 | May 1998 | Dec 1997
EMD Contract Award | Mar 1998 | Mar 1998 | Sep 1998 | May 1998
CDR | Sep 1999 | Sep 1999 | Mar 2000 | Sep 1999
LRIP (#1) Contract Award | Dec 2002 | Dec 2002 | Jun 2003 | Dec 2002
LRIP (#2) Contract Award | Dec 2003 | Dec 2003 | Jun 2004 | Dec 2003
IOT&E
Start | Mar 2004 | Mar 2004 | Sep 2004 | Apr 2004
Finish | May 2004 | May 2004 | Nov 2004 | May 2004
LRIP (#1) First Delivery | Oct 2004 | Oct 2004 | Apr 2005 | Oct 2004
Milestone III ASARC | Nov 2004 | Nov 2004 | May 2005 | Nov 2004
Full Rate Production Contract Award | Dec 2004 | Dec 2004 | Jun 2005 | May 2005
First Unit Equipped | May 2007 | May 2007 | Nov 2007 | Jul 2007

## Table 10
Change Explanations
None
Notes
The IOT&E is a single effort divided into two phases. Phase I, completed in May 2004, supported FRP. Phase II, completed in June 2007, supported First Unit Equipped.
Acronyms and Abbreviations
ASARC - Army Systems Acquisition Review Council CDR - Critical Design Review
IOT&E - Initial Operational Test and Evaluation

## Table 11
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Self-deploy w/30 min fuel reserve (nm)
1260 | 1260 | 1056 | 1130 | 1130
Transport 16,000 lbs of internal/external cargo (nm)
100 | 100 | 50 | 56 | 56
Transport combat equipped troops:
Number of Troops
44 | 44 | 31 | 31 | 31
Range (nm)
150 | 150 | 100 | 150 | 150
Reliability:
MTBEMA (flt hrs)
3.5 | 3.5 | 3.3 | 4.13 | 3.3
Maintenance:
Total Maintenance Ratio (mmh/flt hr)
9.2 | 9.2 | 9.8 | 4.9 | 9.8
Requirements Reference
ORD Revision 4 dated January 26, 2006
Change Explanations
None
Notes
Per new guidance from DoD Acquisition Visibilty, O&S/Sustainment Reporting Functional Description Document Version 3.0, the definitions of Demonstrated Performance and Current Estimate are:
Demonstrated Performance: The Demonstrated Performance section of Reliability and Maintenance is actual data derived from the current Aviation and Missile Research Development and Engineering Center CH-47 RAM Report.
Current Estimate: The Current Estimate represents anticipated performance when all units are fielded. The Current Estimates for Reliability and Maintenance correspond to the CH-47F ORD values.
CH-47F Operational Test was completed on June 4, 2007; RAM data final scoring conference completed on June 5, 2007.

## Table 12
Acronyms and Abbreviations
flt - flight
hr(s) - hour(s) lbs - pounds min - minute
mmh - maintenance man hour
MTBEMA - Mean Time Between Essential Maintenance Actions nm - nautical miles
RAM - Reliability, Availability, Maintainability w/ - with

## Table 13
Track to Budget
RDT&E
Appn |  |  | BA | PE
Army 2040 07 0203744A
Project | Name
D430 Aircraft Modifications/Product Improvement Program/Improved Cargo Helicopter
(Shared) (Sunk)
Procurement
Appn |  |  | BA | PE
Army 2031 01 0210104A
|  | Line Item |  | Name
|  | A05008 |  | CH-47 NEW BUILD
Army |  | 2031 01
|  | Line Item |  |  | Name
|  | A05105 |  | CH-47 SLEP
Army |  | 2031 02
|  | Line Item |  |  | Name
(Shared)
(Shared)
AA0252 CH-47 CARGO HELICOPTER MODS (Shared) (Sunk)
Notes
Line Item AA0252 is shared with CH-47D Modifications applied to currently fielded CH-47D aircraft. The CH-47F funding lines changed starting in FY 2010 to CH-47 Helicopter (A05101) - a parent (roll-up) of New Build and Service Life Extension Program (SLEP), CH-47 SLEP (A05105), and CH-47 New Build (A05008). CH-47F funding for FY 2009 and prior resides on the previously combined AA0252 line. A05008 and A05105 fund the CH-47F aircraft and post-production modification efforts.

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2005 $M | [6 empty] | BY 2005 $M |  | TY $M
| SAR Baseline Production Estimate |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 179.7 |  |  | 183.3 | 201.6 |  |  | 183.3 |  | 171 |  |  | 171.6 |  | 171.6
Procurement |  | 10435.1 |  |  | 11869 | 13055.9 |  |  | 12826.9 |  | 11976.4 |  |  | 13464.6 |  | 14702.6
Flyaway |  | -- |  |  | -- | -- |  |  | 12072 |  | -- |  |  | -- |  | 13841.4
Recurring |  | -- |  |  | -- | -- |  |  | 11732.8 |  | -- |  |  | -- |  | 13509
Non Recurring |  | -- |  |  | -- | -- |  |  | 339.2 |  | -- |  |  | -- |  | 332.4
Support |  | -- |  |  | -- | -- |  |  | 754.9 |  | -- |  |  | -- |  | 861.2
Other Support |  | -- |  |  | -- | -- |  |  | 703 |  | -- |  |  | -- |  | 800.7
Initial Spares |  | -- |  |  | -- | -- |  |  | 51.9 |  | -- |  |  | -- |  | 60.5
MILCON |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 10614.8 |  |  | 12052.3 | N/A |  |  | 13010.2 |  | 12147.4 |  |  | 13636.2 |  | 14874.2
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The Confidence Level of the CH-47F APB cost estimate, which was approved on April 22, 2010, is 50% in accordance with Army SCP policy.
Total Quantity
Quantity |  |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  |  | 2 |  |  |  | 2 |  |  |  |  | 2
Procurement |  |  | 510 |  |  |  | 523 |  |  |  |  | 543
Total |  |  | 512 |  |  |  | 525 |  |  |  |  | 545

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 171.6 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 171.6
Procurement | 12691.7 | 1103.1 |  |  | 565 | 342.8 | 0 |  | 0 |  | 0 |  | 0 |  | 14702.6
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 12863.3 | 1103.1 |  |  | 565 | 342.8 | 0 |  | 0 |  | 0 |  | 0 |  | 14874.2
PB 2016 Total | 12863.3 | 1123.1 |  |  | 710.7 | 342.8 | 0 |  | 0 |  | 0 |  | 0 |  | 15039.9
Delta | 0 | -20 |  |  | -145.7 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | -165.7
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 2 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 2
Production | 0 |  | 473 |  | 39 | 22 | 9 | 0 |  | 0 |  | 0 |  | 0 |  | 543
PB 2017 Total | 2 |  | 473 |  | 39 | 22 | 9 | 0 |  | 0 |  | 0 |  | 0 |  | 545
PB 2016 Total | 2 |  | 473 |  | 39 | 27 | 9 | 0 |  | 0 |  | 0 |  | 0 |  | 550
Delta | 0 |  | 0 |  | 0 | -5 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | -5

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.7
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.3
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.6
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.6
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.8
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.1
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.7
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.7
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.3
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.3
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 171.6

## Table 17
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2005 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.1
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.8
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.4
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.9
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.9
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.1
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.9
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.5
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.4
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.3
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.4
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 183.3

## Table 18
Annual Funding 2031 ¦ Procurement ¦ Aircraft Procurement, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | 41.6 |  | 41.6 |  | 17.7 |  | 59.3
2002 |  | -- | -- |  | -- |  | 45.5 |  | 45.5 |  | 14.9 |  | 60.4
2003 |  | 14 | 353.8 |  | -- |  | 224.8 |  | 578.6 |  | 18.6 |  | 597.2
2004 |  | 16 | 227.8 |  | -- |  | -- |  | 227.8 |  | 23.2 |  | 251
2005 |  | 30 | 700.3 |  | -- |  | 4.6 |  | 704.9 |  | 15 |  | 719.9
2006 |  | 24 | 461.4 |  | -- |  | 2.6 |  | 464 |  | 40.6 |  | 504.6
2007 |  | 43 | 1121.7 |  | -- |  | 13.3 |  | 1135 |  | 88.3 |  | 1223.3
2008 |  | 53 | 1253.8 |  | -- |  | -- |  | 1253.8 |  | 60.4 |  | 1314.2
2009 |  | 52 | 1216.3 |  | -- |  | -- |  | 1216.3 |  | 57.3 |  | 1273.6
2010 |  | 39 | 852.2 |  | -- |  | -- |  | 852.2 |  | 76.1 |  | 928.3
2011 |  | 49 | 1198.9 |  | -- |  | -- |  | 1198.9 |  | 113.7 |  | 1312.6
2012 |  | 48 | 1352.5 |  | -- |  | -- |  | 1352.5 |  | 20 |  | 1372.5
2013 |  | 44 | 1104 |  | -- |  | -- |  | 1104 |  | 98.9 |  | 1202.9
2014 |  | 29 | 824.2 |  | -- |  | -- |  | 824.2 |  | 87.7 |  | 911.9
2015 |  | 32 | 896.7 |  | -- |  | -- |  | 896.7 |  | 63.3 |  | 960
2016 |  | 39 | 1073.8 |  | -- |  | -- |  | 1073.8 |  | 29.3 |  | 1103.1
2017 |  | 22 | 530.6 |  | -- |  | -- |  | 530.6 |  | 34.4 |  | 565
2018 |  | 9 | 341 |  | -- |  | -- |  | 341 |  | 1.8 |  | 342.8
Subtotal |  | 543 | 13509 |  | -- |  | 332.4 |  | 13841.4 |  | 861.2 |  | 14702.6

## Table 19
Annual Funding 2031 ¦ Procurement ¦ Aircraft Procurement, Army
Fiscal Year | Quantity |  | BY 2005 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | 43.9 |  | 43.9 |  | 18.7 |  | 62.6
2002 |  | -- | -- |  | -- |  | 47.4 |  | 47.4 |  | 15.5 |  | 62.9
2003 |  | 14 | 360.5 |  | -- |  | 228.9 |  | 589.4 |  | 19 |  | 608.4
2004 |  | 16 | 225.8 |  | -- |  | -- |  | 225.8 |  | 22.9 |  | 248.7
2005 |  | 30 | 675.4 |  | -- |  | 4.4 |  | 679.8 |  | 14.5 |  | 694.3
2006 |  | 24 | 433.2 |  | -- |  | 2.4 |  | 435.6 |  | 38.2 |  | 473.8
2007 |  | 43 | 1032.4 |  | -- |  | 12.2 |  | 1044.6 |  | 81.4 |  | 1126
2008 |  | 53 | 1136 |  | -- |  | -- |  | 1136 |  | 54.7 |  | 1190.7
2009 |  | 52 | 1086.4 |  | -- |  | -- |  | 1086.4 |  | 51.2 |  | 1137.6
2010 |  | 39 | 748.2 |  | -- |  | -- |  | 748.2 |  | 66.8 |  | 815
2011 |  | 49 | 1033.8 |  | -- |  | -- |  | 1033.8 |  | 98 |  | 1131.8
2012 |  | 48 | 1146.8 |  | -- |  | -- |  | 1146.8 |  | 16.9 |  | 1163.7
2013 |  | 44 | 919.7 |  | -- |  | -- |  | 919.7 |  | 82.3 |  | 1002
2014 |  | 29 | 676.2 |  | -- |  | -- |  | 676.2 |  | 72 |  | 748.2
2015 |  | 32 | 724.6 |  | -- |  | -- |  | 724.6 |  | 51.2 |  | 775.8
2016 |  | 39 | 856.6 |  | -- |  | -- |  | 856.6 |  | 23.4 |  | 880
2017 |  | 22 | 415.4 |  | -- |  | -- |  | 415.4 |  | 26.9 |  | 442.3
2018 |  | 9 | 261.8 |  | -- |  | -- |  | 261.8 |  | 1.3 |  | 263.1
Subtotal |  | 543 | 11732.8 |  | -- |  | 339.2 |  | 12072 |  | 754.9 |  | 12826.9

## Table 20
Cost Quantity Information 2031 ¦ Procurement ¦ Aircraft Procurement, Army
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2005 $M
2001 | -- | --
2002 | -- | --
2003 | 14 | 348.3
2004 | 16 | 224.9
2005 | 30 | 672.1
2006 | 24 | 415.6
2007 | 43 | 1037.8
2008 | 53 | 1133.7
2009 | 52 | 1077
2010 | 39 | 746.7
2011 | 49 | 1016.7
2012 | 48 | 1092.3
2013 | 44 | 948.9
2014 | 29 | 653.3
2015 | 32 | 715.3
2016 | 39 | 874.8
2017 | 22 | 513.6
2018 | 9 | 261.8
Subtotal | 543 | 11732.8

## Table 21
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 1998-05-19 | 2002-08-19
Approved Quantity | 30 | 30
Reference | Milestone II ADM | LRIP ADM
Start Year | 2003 | 2003
End Year | 2004 | 2004
Milestone II and LRIP ADMs specified LRIP quantity as "up to 30 aircraft."
The FY 2003 PB funded 23 LRIP aircraft (7 in FY 2003 and 16 in FY 2004). Of these, 1 aircraft in FY 2003 was a CH-47F and the remaining 22 were MH-47G.

## Table 22
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Netherlands | 2015-11-12 | 14 | 492.5
United Arab Emirates | 2011-06-28 | 16 | 598.7
Turkey | 2010-07-09 | 11 | 403.3 An additional five aircraft, with a value of $151.3M,
were added to this case in September 2015.
Australia | 2010-03-19 | 7 | 249
Notes
The sale dates above are Letter Of Acceptance signature dates. The costs are for the aircraft only.
The CH-47F aircraft capabilities and operational successes in Operation Iraqi Freedom and Operation Enduring Freedom generated interest and inquiries from foreign CH-47D customers. The Common Avionics Architecture System (CAAS) cockpit provides pilot workload reductions and enhanced flight capabilities through flight control coupling. Foreign customers requesting configuration modifications to the aircraft which change the CAAS software, aircraft handling qualities, mission equipment or performance will incur non-recurring and recurring costs to develop, test, qualify, certify,
field, and maintain the software and related hardware as well as increase the lead time to deliver the modified CH-47F. The FMS helps ensure a robust supply chain and industrial base.
Nuclear Costs
None

## Table 23
Unit Cost
Unit Cost Report
Item |  | BY 2005 $M | BY 2005 $M |  | % Change
|  | Current UCR Baseline (Apr 2010 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 12052.3 |  |  | 13010.2
Quantity | 525 |  |  | 545
Unit Cost | 22.957 |  |  | 23.872 |  | 3.99
Average Procurement Unit Cost
Cost | 11869 |  |  | 12826.9
Quantity | 523 |  |  | 543
Unit Cost | 22.694 |  |  | 23.622 |  | 4.09
Item |  | BY 2005 $M | BY 2005 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Nov 2004 APB)
Program Acquisition Unit Cost
Cost | 10614.8 |  |  | 13010.2
Quantity | 512 |  |  | 545
Unit Cost | 20.732 |  |  | 23.872 |  | 15.15
Average Procurement Unit Cost
Cost | 10435.1 |  |  | 12826.9
Quantity | 510 |  |  | 543
Unit Cost | 20.461 |  |  | 23.622 |  | 15.45

## Table 24
Unit Cost History
Item | [7 empty] | Date |  |  |  |  | BY 2005 $M | [6 empty] | TY $M
[13 empty] | PAUC |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | May 1998 | [7 empty] | 9.283 |  |  |  | 8.84 |  |  |  | 10.316 |  |  |  | 9.909
APB as of January 2006 |  |  |  |  | Nov 2004 | [7 empty] | 20.732 |  |  |  | 20.461 |  |  |  | 23.725 |  |  |  | 23.483
Revised Original APB |  |  |  |  | Nov 2004 | [7 empty] | 20.732 |  |  |  | 20.461 |  |  |  | 23.725 |  |  |  | 23.483
Prior APB |  |  |  |  | Nov 2004 | [7 empty] | 20.732 |  |  |  | 20.461 |  |  |  | 23.725 |  |  |  | 23.483
Current APB |  |  |  |  | Apr 2010 | [7 empty] | 22.957 |  |  |  | 22.694 |  |  |  | 25.974 |  |  |  | 25.745
Prior Annual SAR |  |  |  |  | Dec 2014 | [7 empty] | 23.844 |  |  |  | 23.597 |  |  |  | 27.345 |  |  |  | 27.132
Current Estimate |  |  |  |  | Dec 2015 | [7 empty] | 23.872 |  |  |  | 23.622 |  |  |  | 27.292 |  |  |  | 27.077
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [21 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  |  | Oth |  | Spt |  |  | Total
10.316 -0.491 3.003 -0.164 2.273 7.378 0.000 1.410 13.409 23.725
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [19 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth |  | Spt |  | Total
23.725 -0.173 0.285 -0.678 0.416 3.381 0.000 0.336 3.567 27.292

## Table 25
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [13 empty] | APUC Production Estimate
| Econ | Qty |  | Sch | Eng |  | Est |  | Oth |  | Spt |  | Total
9.909 -0.487 3.180 -0.171 2.282 7.354 0.000 1.416 13.574 23.483
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  |  | Est |  | Oth |  | Spt |  | Total
23.483 -0.172 0.300 -0.680 0.417 3.392 0.000 0.337 3.594 27.077
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  | SAR Development Estimate | [5 empty] | SAR Production Estimate |  |  |  | Current Estimate
Milestone I |  |  | N/A |  |  | N/A | [5 empty] | N/A |  |  |  | N/A
Milestone II |  |  | N/A |  |  | Nov 1997 | [5 empty] | Nov 1997 |  |  |  | Dec 1997
Milestone III |  |  | N/A |  |  | Jan 2004 | [5 empty] | Nov 2004 |  |  |  | Nov 2004
FUE |  |  | N/A |  |  | Sep 2004 | [5 empty] | May 2007 |  |  |  | Jul 2007
Total Cost (TY $M) |  |  | N/A |  |  | 3115.4 | [5 empty] | 12147.4 |  |  |  | 14874.2
Total Quantity |  |  | N/A |  |  | 302 | [5 empty] | 512 |  |  |  | 545
PAUC |  |  | N/A |  |  | 10.316 | [5 empty] | 23.725 |  |  |  | 27.292

## Table 26
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
171.0 11976.4 -- 12147.4
Economic |  | -0.9 |  | -61.6 |  | -- |  | -62.5
Quantity |  | -- |  | 1050.2 |  | -- |  | 1050.2
Schedule |  | -- |  | -379.7 |  | -- |  | -379.7
Engineering |  | 0.5 |  | 231.1 |  | -- |  | 231.6
Estimating |  | 1 |  | 1857.3 |  | -- |  | 1858.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 194.6 |  | -- |  | 194.6
Subtotal |  | 0.6 |  | 2891.9 |  | -- |  | 2892.5
Current Changes Economic |  | -- |  | -32 |  | -- |  | -32
Quantity |  | -- |  | -112.2 |  | -- |  | -112.2
Schedule |  | -- |  | 10.4 |  | -- |  | 10.4
Engineering |  | -- |  | -4.7 |  | -- |  | -4.7
Estimating |  | -- |  | -15.7 |  | -- |  | -15.7
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -11.5 |  | -- |  | -11.5
Subtotal |  | -- |  | -165.7 |  | -- |  | -165.7
Total Changes |  | 0.6 |  | 2726.2 |  | -- |  | 2726.8
CE - Cost Variance |  | 171.6 |  | 14702.6 |  | -- |  | 14874.2
CE - Cost & Funding |  | 171.6 |  | 14702.6 |  | -- |  | 14874.2

## Table 27
Summary BY 2005 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
179.7 10435.1 -- 10614.8
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 844.2 |  | -- |  | 844.2
Schedule |  | -- |  | -58.5 |  | -- |  | -58.5
Engineering |  | 0.5 |  | 187.3 |  | -- |  | 187.8
Estimating |  | 3.1 |  | 1353.1 |  | -- |  | 1356.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 169.9 |  | -- |  | 169.9
Subtotal |  | 3.6 |  | 2496 |  | -- |  | 2499.6
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -86.1 |  | -- |  | -86.1
Schedule |  | -- |  | 5.8 |  | -- |  | 5.8
Engineering |  | -- |  | -3.6 |  | -- |  | -3.6
Estimating |  | -- |  | -11.1 |  | -- |  | -11.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -9.2 |  | -- |  | -9.2
Subtotal |  | -- |  | -104.2 |  | -- |  | -104.2
Total Changes |  | 3.6 |  | 2391.8 |  | -- |  | 2395.4
CE - Cost Variance |  | 183.3 |  | 12826.9 |  | -- |  | 13010.2
CE - Cost & Funding |  | 183.3 |  | 12826.9 |  | -- |  | 13010.2
Previous Estimate: December 2014

## Table 28
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -32
Adjustment for current and prior escalation. (Estimating) | 18.4 | 22.4
Quantity variance resulting from a decrease of five CH-47Fs from 548 to 543. (Subtotal) | -112.4 | -146.4
Quantity variance resulting from a decrease of five CH-47Fs from 548 to 543. | -86.1 | -112.2
(Quantity)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) | -5.8 | -7.6
Allocation to Engineering resulting from Quantity change. (Engineering) (QR) | -3.6 | -4.7
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) | -28.5 | -37.1
Stretch-out of five CH-47Fs from FY 2017 to FY 2018. (Schedule) | 0 | 2.8
Adjustment to Engineering Change Orders due to funding reduction. (Estimating) | -1 | -1
Adjustment for current and prior escalation. (Support) | 1 | 1.4
Increase in Other Support to reflect actuals. (Support) | 0.2 | 0.3
Decrease in Initial Spares to reflect actuals. (Support) | -10.4 | -13.2
Procurement Subtotal | -104.2 | -165.7
(QR) Quantity Related

## Table 29
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: Multiyear II
Contractor: Boeing Helicopter Contractor Location: Philadelphia, PA 19142 Contract Number: W58RGZ-13-C-0002 Contract Type: Firm Fixed Price (FFP)
Award Date: June 10, 2013
Definitization Date: June 10, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
916.5 N/A 37 2840.8 N/A 105 2840.8 2840.8
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the increase in number of aircraft on contract and the application of Engineering Change Proposals.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 30
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 2 | 2 | 2 | 100%
Production | 407 | 407 | 543 | 74.95%
Total Program Quantity Delivered | 409 | 409 | 545 | 75.05%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
14874.2
11385.2
76.54%
24
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
22
91.67%
13966.4
93.9%
The above data is current as of February 09, 2016.

## Table 31
Operating and Support Cost
Cost Estimate Details
Date of Estimate: February 08, 2016
Source of Estimate: POE
Quantity to Sustain: 449
Unit of Measure: Aircraft
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2007 - FY 2040
The O&S costs are taken from the the February 2016 Program Office Estimate (POE) which is based on methodology from the 2004 CH-47F Army Cost Position. It assumes an end state of 449 CH-47F operational aircraft when fully fielded flying 180 peacetime hours per aircraft per year. While the common production costs of 66 MH-47Gs are included in the procurement costs, they are excluded from the O&S costs as they are managed by the Special Operations Aviation Regiment. The remaining 30 CH-47F aircraft are RDT&E aircraft and peacetime attrition aircraft that incur no O&S costs due to no flying hours; or are wartime replacement aircraft whose flying hours are already accounted.
Sustainment Strategy
The sustainment approach for the CH-47F is a blend of Government and Contractor Logistics Support in conjunction with the Supportability Strategy. There is a continued focus on reducing maintenance burden and O&S costs including the use of Performance Based Logistics when appropriate.
The CH-47D and CH-47F costs are based on CH-47D actuals extracted from the O&S Management Information System (OSMIS). To calculate the CH-47F costs, the CH-47D actuals were augmented by an improvement factor to account for the increased reliability of recapitalized parts, new airframe, and vibration engineering.
Antecedent Information
The antecedent to the CH-47F is the CH-47D, for which the O&S costs are from the CH-47D model POE. The total O&S cost is based on 306 systems with an operating span of 20 years peacetime operating tempo spanning FY 1997 to FY 2018. The O&S costs are based on actuals extracted from OSMIS.
Annual O&S Costs BY2005 $K
Cost Element | CH-47F Average Annual Cost Per Aircraft | CH-47D (Antecedent) Average Annual Per Aircraft
Unit-Level Manpower | 401.3 | 658.828
Unit Operations | 69.5 | 76.408
Maintenance | 1160.8 | 1208.797
Sustaining Support | 19.7 | 470.291
Continuing System Improvements | 208.9 | 11.359
Indirect Support | 99.3 | 652.265
Other | 0 | 0
Total | 1959.5 | 3077.948

## Table 32
Item | Total O&S Cost $M
| CH-47F | [5 empty] | CH-47D (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 16379.4 |  | 18017.3 |  |  | 17596.3 | 18837
Then Year | 22285.6 |  | N/A |  |  | 25068.3 | N/A
Disposal Cost is included in the Operating and Support Cost of the current APB objective and threshold for this program.
Equation to Translate Annual Cost to Total Cost
Total cost = Average annual cost per aircraft * quantity * service life = $1959.5K * 449 * 20 = $17596.3M.
O&S Cost Variance
Category |  | BY 2005 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
17659.2
Programmatic/Planning Factors 0.0
Cost Estimating Methodology -62.9 Post Production Modifications methodology change.
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes -62.9
Current Estimate 17596.3
Disposal Estimate Details
Date of Estimate: February 08, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2005 $M): Total costs for disposal of all Aircraft are 6.5