## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-366
Excalibur Precision 155mm Projectiles (Excalibur)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 13
Cost and Funding 14
Low Rate Initial Production 26
Foreign Military Sales 27
Nuclear Costs 27
Unit Cost 28
Cost Variance 31
Contracts 34
Deliveries and Expenditures 36
Operating and Support Cost 37

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Excalibur Precision 155mm Projectiles (Excalibur)
DoD Component
Army
Responsible Office
Mr. Peter DeMasi Building 172
Picatinny Arsenal, NJ 07806-5000
peter.g.demasi2.civ@mail.mil
Phone: | 973-724-9066
Fax: | 973-724-8786
DSN Phone: | 880-9066
DSN Fax: | 880-8786
Date Assigned: | June 21, 2015
References
SAR Baseline (Production Estimate)
Army Acquisition Executive (AAE) Approved Acquisition Program Baseline (APB) dated March 14, 2011
Approved APB
Army Acquisition Executive (AAE) Approved Acquisition Program Baseline (APB) dated June 25, 2014

## Table 6
Mission and Description
Excalibur Precision 155-mm Projectiles (Excalibur) provide Brigade Combat Teams an organic precision fires capability. Additionally, it provides improved fire support capability due to its increased range of 40.5-kilometers (km) and demonstrated accuracy of less than three meters radial miss distances, which enables a first round effect on target reducing the number of rounds required and reducing collateral damage. Excalibur is compatible with the M777A2 Lightweight 155-mm Howitzer, the M109A6 Paladin Howitzer, the M109A7 Paladin Integrated Management Howitzer, and the Swedish Archer Howitzer.
Excalibur provides a 35 percent range increase over current Rocket Assisted Projectiles with less than ten-meter circular error probable requirement at all ranges. Excalibur is also highly resistant to Global Positioning System jamming.
Excalibur Inc Ia-1 and Inc Ia-2 are currently fielded and in use by units throughout Afghanistan and deployed globally to support other military contingency operations. Excalibur is an International Cooperative Development Program, teamed with the Kingdom of Sweden (KoS) which contributed resources towards development in accordance with an established Project Agreement. Excalibur Inc Ia-1 was initially fielded to units in Iraq and Afghanistan in response to urgent need requests in support of Operation Iraqi Freedom, Operation New Dawn, and Operation Enduring Freedom. Excalibur Inc Ia-2 was fielded in early FY 2012 and greatly increased range from 25.2-km to 37.5-km. The Excalibur guided projectile program is using an incremental development approach to provide a combat capability to the soldier as quickly as possible while delivering advanced capabilities at lower costs. Excalibur Inc Ib provides further performance improvements while significantly lowering unit costs.
Excalibur completed FMS to Canada, United Kingdom, Australia, Germany, and the KoS. The program is actively executing current FMS cases with Spain, The Netherlands, and the Kingdom of Jordan. The program also received interest for future sales from numerous other countries.

## Table 7
Executive Summary
Pursuant to section 2432 of title 10, U.S. Code, this is the final SAR submission for Excalibur because the program is 90 percent or more expended.
Excalibur Inc Ia-1 and Inc Ia-2
The final Excalibur Inc Ia-2 projectile was delivered to inventory in April 2014. In total, PM Excalibur procured and delivered 2,132 Excalibur Inc Ia-1 (Department of the Army (DA) 39) and 4,316 Excalibur Inc Ia-2 (DA45) projectiles to U.S. and foreign customers. The Army and U.S. Marine Corps fired a total of 832 projectiles since the first production deliveries were made available to troops in 2007 with a proven field reliability of 88 percent. Excalibur is highly successful and proves the value of precision munitions in dense urban environments by virtually eliminating collateral damage while providing effects on the intended target.
Excalibur Inc Ib
Excalibur Inc Ib is an integral part of the strategy to field Excalibur capability to the DoD and the Kingdom of Sweden (KoS). It delivers a lower cost, higher reliability precision munition to the warfighter. As of December 31, 2015, PM Excalibur contracted for 2,894 Excalibur Inc Ib projectiles for the Army, with 2,469 delivered to inventory. The KoS procured an additional 297 projectiles.
On September 14, 2015, the Excalibur Product Lead briefed the Army Acquisition Executive (AAE) to address the M-Code, Global Positioning System (GPS) Degraded, and GPS Denied retrofit options to the Excalibur Ib inventory. The
PM presented the benefits to retrofitting the inventory for the M982A1 Excalibur Inc Ib variant along with the associated costs in both RDT&E and Procurement starting in FY 2018. The Excalibur program continues to execute within all APB parameters. No current issues exist that impact cost, schedule, or performance.
On October 8, 2015, the Configuration Steering Board was held during which the Product Lead for Excalibur provided a briefing to the AAE and other principals on the status and plans of the Excalibur program. Participants included PM Combat Ammunition Systems, PEO Ammunition and the Army Training and Doctrine Command Capability Manager Brigade Combat Team Fires. No de-scoping of program efforts was recommended or directed. Two topics of particular emphasis were discussed. The first was the conclusion of the Excalibur Army-funded production program with the FY 2017 purchase. There is considerable interest to ensure sufficient stockpile exists before production ends or maintaining production at the minimum sustaining rate to enable reaction to urgent needs. The second key topic regarded the robustness of the Excalibur design to the GPS threats. Several options for development of improved resistance to GPS threats were presented. A decision regarding continued production relies heavily on the results of the Army G-3 Munitions Requirements Process and funding availability from FY 2018 to FY 2022. Excalibur's GPS Degraded path forward will be considered along with other Army systems in the overall review of GPS Position, Navigation and Timing.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone I/II | May 1997 | May 1997 | May 1997 | May 1997
Milestone C (Block Ia-1) | May 2005 | May 2005 | May 2005 | May 2005
Milestone C (Block Ia-2) | Sep 2007 | Sep 2007 | Sep 2007 | Jul 2007
IOT&E
IOT&E Start | Jan 2010 | Jan 2010 | Jan 2010 | Jan 2010
IOT&E End | May 2010 | May 2010 | May 2010 | Apr 2010
FRP IPR | Mar 2011 | Mar 2011 | Mar 2011 | Mar 2011
IOC | Oct 2011 | Dec 2011 | Dec 2011 | Dec 2011
Milestone C (Block Ib) | Jun 2012 | Dec 2012 | Dec 2012 | Dec 2012
Increment Ib IOC | Mar 2014 | Jul 2014 | Jan 2015 | Jun 2014
Increment Ib FRP | Mar 2014 | Jul 2014 | Jan 2015 | Jun 2014
Change Explanations

## Table 10
Acronyms and Abbreviations
IOT&E - Initial Operational Test and Evaluation IPR - In-Process Review

## Table 11
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Accuracy (CEP)(m) (Increment Ia)
<= 10 CEP | <= 10 CEP | <= 20 CEP | <4-m CEP | <4-m CEP
Reliability (percent) (Increment Ia)
>= 96 | >= 96 | >= 85 | 88 | 88
Effectiveness (Increment Ia)
>=M107 HE | >=M107 HE | >=M107 HE | >=M107 HE | >=M107 HE
Net Ready (Increment Ia)
ATO | ATO | IATO | ATO | ATO
Accuracy (CEP)(m) (Increment Ib)
<= 10m CEP | <= 10m CEP | <= 10m CEP | 2-m CEP | 2-m CEP
Range (Increment Ib)
>=40 km | >=40 km | >= 35 km | 37.5-km | >=37.5-km
Effectiveness (Increment Ib)
>=M107 HE | >=M107 HE | >=M107 HE | >=M107 HE | >=M107 HE
Reliability (percent)(Increment Ib)
>=96% | >=96% | >=90% | 93% | >=90%
Net Ready (Increment Ib)
ATO | ATO | IATO | ATO | ATO
Requirements Reference
CPD dated October 24, 2012
Change Explanations
None
Notes
The first four performance characteristics listed above (Accuracy, Reliability, Effectiveness, and Net Ready) pertain to Excalibur Inc Ia projectiles.
The current assessment of the overall Excalbur Inc Ia-2 Reliability, based on combined results from both test results and in- theater firing, is approximately 88 percent; when considered independently, the point estimate for reliability in the production contract acceptance testing is currently at 93 percent.
Current Army Test and Evaluation Command assessment of Excalbur Inc Ib Reliability is 93 percent.

## Table 12
Acronyms and Abbreviations
ATO - Approval to Operate CEP - Circular Error Probable HE - High Explosives
IATO - Interim Authority to Operate km - kilometer
m - meter

## Table 13
Track to Budget
RDT&E
Appn |  | BA | PE
Army 2040 05 0604814A
Project | Name
708 M982 Projectile (Shared) (Sunk)
Notes: Completed in FY 2014
Defense-Wide 9999 05 0604814A
Project | Name
708 M982 Projectile (Shared) (Sunk)
Notes: Completed in FY 2012
Notes
The Excalibur RDT&E funding line supports the Excalibur Unitary variant. This funding line is shared with all Excalibur increments and was shared in prior years with the Spin Stabilized Sensor Fuzed Munition and the Enhanced Portable Inductive Artillery Fuze Setter.
Excalibur is an International Program with a Memorandum of Agreement for the cooperative development with the Kingdom of Sweden which contributed $69M to the development program ($57M contributed to Excalibur Inc Ia and $12M to Excalibur Inc Ib). These funds are included in this report as Non-Treasury RDT&E (9999).
Procurement
Appn |  | BA | PE
Army 2034 01 0210600A
Line Item | Name
E80103 Excalibur Unitary
Defense-Wide 0300 01 0210600A
Line Item | Name
E80103 Excalibur
Notes: Parent Line for is E80100 (Projectile 155 MM Expended Range M982).
Notes
Excalibur procured additional projectiles in FY 2007 - FY 2009 and again in FY 2015 as FMS Buy Back rounds. The funds are included in this SAR as Other Procurement, Defense Agency (0300).

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2007 $M | [5 empty] | BY 2007 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E | 993.4 |  |  | 1002.6 | 1102.9 |  |  | 1006.5 |  | 972.7 |  |  | 984 |  | 988.3
Procurement | 661.2 |  |  | 688.2 | 757 |  |  | 745.6 |  | 706.3 |  |  | 746.3 |  | 812.2
Flyaway | -- |  |  | -- | -- |  |  | 742.8 |  | -- |  |  | -- |  | 809.2
Recurring | -- |  |  | -- | -- |  |  | 708.1 |  | -- |  |  | -- |  | 770.4
Non Recurring | -- |  |  | -- | -- |  |  | 34.7 |  | -- |  |  | -- |  | 38.8
Support | -- |  |  | -- | -- |  |  | 2.8 |  | -- |  |  | -- |  | 3
Other Support | -- |  |  | -- | -- |  |  | 2.8 |  | -- |  |  | -- |  | 3
Initial Spares | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
MILCON | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 1654.6 |  |  | 1690.8 | N/A |  |  | 1752.1 |  | 1679 |  |  | 1730.3 |  | 1800.5
Current APB Cost Estimate Reference
Army Cost Position (ACP) dated May 22, 2014
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The Excalibur ACP approved by the Assistant Secretary of the Army for Financial Management and Comptroller is based on a negotiated price that was definitized prior to the FRP decision. The ICE methodology used the most recent pricing data received from the prime contractor.
Total Quantity
Quantity |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  | 544 |  |  |  | 544 |  |  |  |  | 544
Procurement |  | 6930 |  |  |  | 6930 |  |  |  |  | 7496
Total |  | 7474 |  |  |  | 7474 |  |  |  |  | 8040
Quantity Notes
Excalibur's total planned procurement quantity of 7,496 includes 6,830 projectiles to be delivered to inventory (566 of which are replacing expended or damaged projectiles) and 666 projectiles for contract acceptance and reliability growth testing. Excalibur's war stock requirement is 6,264 projectiles.

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 988.3 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 988.3
Procurement | 707.5 | 65.5 |  |  | 39.2 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 812.2
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 1695.8 | 65.5 |  |  | 39.2 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1800.5
PB 2016 Total | 1692.5 | 45.5 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1738
Delta | 3.3 | 20 |  |  | 39.2 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 62.5
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 544 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 544
Production | 0 |  | 6578 |  | 546 | 372 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 7496
PB 2017 Total | 544 |  | 6578 |  | 546 | 372 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 8040
PB 2016 Total | 544 |  | 6563 |  | 476 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 7583
Delta | 0 |  | 15 |  | 70 | 372 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 457

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.7
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.9
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.5
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.8
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.6
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.3
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 102.1
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 112.5
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 129
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 102
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 95.1
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 60.9
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 68.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 45.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.2
Subtotal |  | 544 | -- |  | -- |  | -- |  | -- |  | -- |  | 919.3

## Table 17
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2007 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.5
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.4
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.7
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.1
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.1
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.8
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 111.2
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 119.6
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 133.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 102.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 93.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 58.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.4
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.5
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8
Subtotal |  | 544 | -- |  | -- |  | -- |  | -- |  | -- |  | 937

## Table 18
Annual Funding 9999 ¦ RDT&E ¦ Non Treasury Funds
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.5
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.5
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.5
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 69

## Table 19
Annual Funding 9999 ¦ RDT&E ¦ Non Treasury Funds
Fiscal Year | Quantity |  | BY 2007 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.3
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.3
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.2
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.9
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 69.5

## Table 20
This appropriation accounts for $69M provided by the Kingdom of Sweden for the Excalibur development program.

## Table 21
Annual Funding 2034 ¦ Procurement ¦ Procurement of Ammunition, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | 127 | 35.1 |  | -- |  | 1.8 |  | 36.9 |  | -- |  | 36.9
2006 |  | 321 | 48.3 |  | -- |  | 1 |  | 49.3 |  | -- |  | 49.3
2007 |  | 793 | 84.5 |  | -- |  | 1.7 |  | 86.2 |  | -- |  | 86.2
2008 |  | 400 | 47.5 |  | -- |  | -- |  | 47.5 |  | -- |  | 47.5
2009 |  | 435 | 57.9 |  | -- |  | 10.1 |  | 68 |  | 0.8 |  | 68.8
2010 |  | 900 | 103.2 |  | -- |  | -- |  | 103.2 |  | 2.2 |  | 105.4
2011 |  | 100 | 30.5 |  | -- |  | -- |  | 30.5 |  | -- |  | 30.5
2012 |  | 744 | 56.1 |  | -- |  | 2 |  | 58.1 |  | -- |  | 58.1
2013 |  | 928 | 72 |  | -- |  | 2.6 |  | 74.6 |  | -- |  | 74.6
2014 |  | 996 | 75.8 |  | -- |  | 1.5 |  | 77.3 |  | -- |  | 77.3
2015 |  | 428 | 34.6 |  | -- |  | 1.1 |  | 35.7 |  | -- |  | 35.7
2016 |  | 546 | 49.5 |  | -- |  | 16 |  | 65.5 |  | -- |  | 65.5
2017 |  | 372 | 38.2 |  | -- |  | 1 |  | 39.2 |  | -- |  | 39.2
Subtotal |  | 7090 | 733.2 |  | -- |  | 38.8 |  | 772 |  | 3 |  | 775

## Table 22
Annual Funding 2034 ¦ Procurement ¦ Procurement of Ammunition, Army
Fiscal Year | Quantity |  | BY 2007 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | 127 | 35.9 |  | -- |  | 1.9 |  | 37.8 |  | -- |  | 37.8
2006 |  | 321 | 48 |  | -- |  | 1 |  | 49 |  | -- |  | 49
2007 |  | 793 | 82 |  | -- |  | 1.7 |  | 83.7 |  | -- |  | 83.7
2008 |  | 400 | 45.4 |  | -- |  | -- |  | 45.4 |  | -- |  | 45.4
2009 |  | 435 | 54.8 |  | -- |  | 9.5 |  | 64.3 |  | 0.8 |  | 65.1
2010 |  | 900 | 95.9 |  | -- |  | -- |  | 95.9 |  | 2 |  | 97.9
2011 |  | 100 | 27.8 |  | -- |  | -- |  | 27.8 |  | -- |  | 27.8
2012 |  | 744 | 50.4 |  | -- |  | 1.8 |  | 52.2 |  | -- |  | 52.2
2013 |  | 928 | 63.3 |  | -- |  | 2.3 |  | 65.6 |  | -- |  | 65.6
2014 |  | 996 | 65.9 |  | -- |  | 1.3 |  | 67.2 |  | -- |  | 67.2
2015 |  | 428 | 29.6 |  | -- |  | 1 |  | 30.6 |  | -- |  | 30.6
2016 |  | 546 | 41.7 |  | -- |  | 13.4 |  | 55.1 |  | -- |  | 55.1
2017 |  | 372 | 31.5 |  | -- |  | 0.8 |  | 32.3 |  | -- |  | 32.3
Subtotal |  | 7090 | 672.2 |  | -- |  | 34.7 |  | 706.9 |  | 2.8 |  | 709.7

## Table 23
Annual Funding 0300 ¦ Procurement ¦ Procurement, Defense-Wide
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | 295 | 25.1 |  | -- |  | -- |  | 25.1 |  | -- |  | 25.1
2008 |  | 75 | 6.2 |  | -- |  | -- |  | 6.2 |  | -- |  | 6.2
2009 |  | 29 | 5.4 |  | -- |  | -- |  | 5.4 |  | -- |  | 5.4
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | 7 | 0.5 |  | -- |  | -- |  | 0.5 |  | -- |  | 0.5
Subtotal |  | 406 | 37.2 |  | -- |  | -- |  | 37.2 |  | -- |  | 37.2

## Table 24
Annual Funding 0300 ¦ Procurement ¦ Procurement, Defense-Wide
Fiscal Year | Quantity |  | BY 2007 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | 295 | 24.5 |  | -- |  | -- |  | 24.5 |  | -- |  | 24.5
2008 |  | 75 | 5.9 |  | -- |  | -- |  | 5.9 |  | -- |  | 5.9
2009 |  | 29 | 5.1 |  | -- |  | -- |  | 5.1 |  | -- |  | 5.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | 7 | 0.4 |  | -- |  | -- |  | 0.4 |  | -- |  | 0.4
Subtotal |  | 406 | 35.9 |  | -- |  | -- |  | 35.9 |  | -- |  | 35.9

## Table 25
This appropriation captures the procurement of FMS Buy Back projectiles.

## Table 26
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2005-05-23 | 2012-12-13
Approved Quantity | 500 | 1800
Reference | Inc Ia Milestone C ADM | Inc Ib Milestone C ADM
Start Year | 2005 | 2012
End Year | 2006 | 2014
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the significant decrease in Army Procurement Objective from 30,000 projectiles to 6,264.
The program received an Army Acquisition Executive (AAE) ADM on May 23, 2005 to authorize entry into LRIP and procurement of up to 500 Exalibur Inc Ia-1 projectiles in FY 2005 to FY 2006.
The AAE provided a revised ADM on March 26, 2007 to increase the authorized LRIP procurement quantity up to 1,500 Excalibur Inc Ia-1 projectiles.
A revised ADM dated July 31, 2007 authorized entry into Excalibur Inc Ia-2 LRIP with procurement authorization of up to 2,500 Exclibur Inc Ia projectiles in FY 2005 to FY 2009.
An ADM dated December 13, 2012 authorized entry into Excalibur Inc Ib LRIP with procurement authorization of up to 1,800 Excalibur Inc Ib projectiles in FY 2013 to FY 2014.

## Table 27
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Jordan | 2015-12-27 | 91 | 12 | Letter of Offer and Acceptance (LOA) with Kingdom of Jordan was signed on December 27, 2015 to procure 91 Excalibur Inc Ib projectiles.
Netherlands | 2015-05-12 | 100 | 16.5 | LOA with the Netherlands was signed on May 12, 2015 to procure a total of 100 Excalibur Inc Ib projectiles.
Spain | 2014-11-07 | 0 | 0.7 | LOA with Spain was signed on November 7, 2014 to procure initial qualification test effort.
Germany | 2013-05-02 | 8 | 2 | LOA and Project Agreement with Germany was signed on May 2, 2013 for eight Excalibur Inc Ia-2 projectiles for compatibility testing with their gun system.
Sweden | 2013-04-25 | 297 | 21.7 | 297 Excalibur Inc Ib projectiles were procured by the Kingdom of Sweden (KoS) under the Excalibur Production Project Agreement.
Canada | 2011-01-10 | 75 | 8.8 | LOA with Canada signed on January 10, 2011 to procure 75 M982 Excalibur Inc Ia-2 projectiles.
Sweden | 2009-09-23 | 114 | 12 | 114 Excalibur Inc Ia-2 projectiles sold to the KoS under the Excalibur Production Project Agreement.
United Kingdom | 2009-03-06 | 6 | 1.1 | The United Kingdom purchased six projectiles.
Australia | 2008-05-08 | 250 | 26.9 | Australia purchased 250 Excalibur Inc Ia-1 projectiles.
Sweden | 2007-10-15 | 18 | 2.3 | KoS LOA FMS case signed October 15, 2007.
Canada | 2007-10-07 | 30 | 4.1 | Canadian Defense Forces FMS contract for FY 2007 projectiles.
Notes
Nuclear Costs
None

## Table 28
Unit Cost
Unit Cost Report
Item |  | BY 2007 $M | BY 2007 $M |  | % Change
|  | Current UCR Baseline (Jun 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1690.8 |  |  | 1752.1
Quantity | 7474 |  |  | 8040
Unit Cost | 0.226 |  |  | 0.218 |  | -3.54
Average Procurement Unit Cost
Cost | 688.2 |  |  | 745.6
Quantity | 6930 |  |  | 7496
Unit Cost | 0.099 |  |  | 0.099 |  | 0
Item |  | BY 2007 $M | BY 2007 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Mar 2011 APB)
Program Acquisition Unit Cost
Cost | 1654.6 |  |  | 1752.1
Quantity | 7474 |  |  | 8040
Unit Cost | 0.221 |  |  | 0.218 |  | -1.36
Average Procurement Unit Cost
Cost | 661.2 |  |  | 745.6
Quantity | 6930 |  |  | 7496
Unit Cost | 0.095 |  |  | 0.099 |  | 4.21

## Table 29
Unit Cost History
Item | [7 empty] | Date |  |  |  | BY 2007 $M | [7 empty] | TY $M
[12 empty] | PAUC |  |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Oct 2004 | [6 empty] | 0.072 |  |  |  |  | 0.039 |  |  |  | 0.076 |  |  |  | 0.045
APB as of January 2006 |  |  |  |  | Oct 2004 | [6 empty] | 0.072 |  |  |  |  | 0.039 |  |  |  | 0.076 |  |  |  | 0.045
Revised Original APB |  |  |  |  | Mar 2011 | [6 empty] | 0.221 |  |  |  |  | 0.095 |  |  |  | 0.225 |  |  |  | 0.102
Prior APB |  |  |  |  | Dec 2012 | [6 empty] | 0.228 |  |  |  |  | 0.101 |  |  |  | 0.233 |  |  |  | 0.109
Current APB |  |  |  |  | Jun 2014 | [6 empty] | 0.226 |  |  |  |  | 0.099 |  |  |  | 0.232 |  |  |  | 0.108
Prior Annual SAR |  |  |  |  | Dec 2014 | [6 empty] | 0.224 |  |  |  |  | 0.099 |  |  |  | 0.229 |  |  |  | 0.107
Current Estimate |  |  |  |  | Dec 2015 | [6 empty] | 0.218 |  |  |  |  | 0.099 |  |  |  | 0.224 |  |  |  | 0.108
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [21 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  |  | Oth |  | Spt |  |  | Total
0.063 -0.005 0.142 0.011 0.006 0.006 0.000 0.000 0.160 0.225
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [19 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng | Est |  | Oth |  | Spt |  |  | Total
0.225 0.000 -0.006 0.000 0.004 0.001 0.000 0.000 -0.001 0.224

## Table 30
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [13 empty] | APUC Production Estimate
| Econ |  | Qty |  |  | Sch |  | Eng |  |  | Est | Oth | Spt | Total
0.054 -0.005 0.040 0.010 0.000 0.003 0.000 0.000 0.048 0.102
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch |  | Eng |  |  | Est |  | Oth | Spt | Total
0.102 0.000 0.003 0.000 0.004 -0.001 0.000 0.000 0.006 0.108
SAR Baseline History
Item |  |  |  | SAR Planning Estimate |  |  |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone I |  |  |  | N/A |  |  |  |  | May 1997 |  |  |  | N/A |  |  | N/A
Milestone II |  |  |  | N/A |  |  |  |  | May 1997 |  |  |  | May 1997 |  |  | May 1997
Milestone C |  |  |  | N/A |  |  |  |  | Jun 2006 |  |  |  | May 2005 |  |  | May 2005
IOC |  |  |  | N/A |  |  |  |  | Sep 2008 |  |  |  | Oct 2011 |  |  | Dec 2011
Total Cost (TY $M) |  |  |  | N/A |  |  |  |  | 4798.7 |  |  |  | 1679 |  |  | 1800.5
Total Quantity |  |  |  | N/A |  |  |  |  | 76677 |  |  |  | 7474 |  |  | 8040
PAUC |  |  |  | N/A |  |  |  |  | 0.063 |  |  |  | 0.225 |  |  | 0.224

## Table 31
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
972.7 706.3 -- 1679.0
Economic |  | 1 |  | 4.1 |  | -- |  | 5.1
Quantity |  | -- |  | 37.3 |  | -- |  | 37.3
Schedule |  | -- |  | 2.5 |  | -- |  | 2.5
Engineering |  | -- |  | 12.7 |  | -- |  | 12.7
Estimating |  | 11.8 |  | -8.4 |  | -- |  | 3.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -2 |  | -- |  | -2
Subtotal |  | 12.8 |  | 46.2 |  | -- |  | 59
Current Changes Economic |  | -0.1 |  | -1.3 |  | -- |  | -1.4
Quantity |  | -- |  | 39.5 |  | -- |  | 39.5
Schedule |  | -- |  | 0.2 |  | -- |  | 0.2
Engineering |  | 2.8 |  | 20 |  | -- |  | 22.8
Estimating |  | 0.1 |  | 1.3 |  | -- |  | 1.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 2.8 |  | 59.7 |  | -- |  | 62.5
Total Changes |  | 15.6 |  | 105.9 |  | -- |  | 121.5
CE - Cost Variance |  | 988.3 |  | 812.2 |  | -- |  | 1800.5
CE - Cost & Funding |  | 988.3 |  | 812.2 |  | -- |  | 1800.5

## Table 32
Summary BY 2007 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
993.4 661.2 -- 1654.6
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 36.6 |  | -- |  | 36.6
Schedule |  | -- |  | -3.8 |  | -- |  | -3.8
Engineering |  | -- |  | 11 |  | -- |  | 11
Estimating |  | 10.6 |  | -8.1 |  | -- |  | 2.5
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -1.9 |  | -- |  | -1.9
Subtotal |  | 10.6 |  | 33.8 |  | -- |  | 44.4
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 32.7 |  | -- |  | 32.7
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | 2.4 |  | 16.8 |  | -- |  | 19.2
Estimating |  | 0.1 |  | 1.1 |  | -- |  | 1.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 2.5 |  | 50.6 |  | -- |  | 53.1
Total Changes |  | 13.1 |  | 84.4 |  | -- |  | 97.5
CE - Cost Variance |  | 1006.5 |  | 745.6 |  | -- |  | 1752.1
CE - Cost & Funding |  | 1006.5 |  | 745.6 |  | -- |  | 1752.1
Previous Estimate: December 2014

## Table 33
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.1
Adjustment for current and prior escalation. (Estimating) | 0.1 | 0.1
Analysis of Global Positioning System interface redesign to attain M-Code compliance. (Engineering) | 2.4 | 2.8
RDT&E Subtotal | 2.5 | 2.8
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -1.3
Adjustment for current and prior escalation. (Estimating) +1.1 +1.3
Quantity variance resulting from an increase of 450 projectiles from 6,640 to 7,090 (Army). (Quantity)
Quantity variance resulting from an increase of 7 projectiles from 399 to 406 (DoD). (Quantity)
+35.7 +43.1
+0.4 +0.5
Additional quantity variance as a result of an increase of 457 projectiles. (Quantity) -3.4 -4.1
Contract close out costs shifted from FY 2016 to FY 2017 due to extension of production contract. (Schedule)
0.0 +0.2
Software upgrade based on updated System Threat Assessment Report. (Engineering) +16.8 +20.0
Procurement Subtotal +50.6 +59.7

## Table 34
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: XM982 ER Projectile-Incr Ib Production
Contractor: Raytheon Missile Systems
Contractor Location: 1151 E Hermans Rd.
Tucson, AZ 85706
Contract Number: W15QKN-08-C-0530/3
Contract Type: Firm Fixed Price (FFP)
Award Date: December 21, 2012
Definitization Date: December 21, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
56.6 N/A 819 129.3 N/A 1800 129.3 129.3
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to subsequent awards of contract options for additional projectiles.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This is the contract for Production of the Excalibur Inc Ib projectile. The total price includes:
An initial award of $58.9M for 819 projectiles. An option award of $54.1M for 765 projectiles. An option award of $16.3M for 216 projectiles.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 35
Contract Identification
Appropriation: Procurement
Contract Name: Excalibur Ib Production
Contractor: Raytheon Missile Systems
Contractor Location: 1151 E Hermans Road
Tucson, AZ 85706
Contract Number: W15QKN-08-C-0530/4
Contract Type: Firm Fixed Price (FFP)
Award Date: December 21, 2012
Definitization Date: July 27, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
52.5 N/A 744 132.4 N/A 1854 132.4 132.4
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract modifications awarded for additional quantities.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
The current target price reflects the Army portion of the contract ($123.5M for 1,749 projectiles) as well as the FMS portion ($8.9M for 105 projectiles).

## Table 36
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 544 | 544 | 544 | 100%
Production | 6563 | 5944 | 7496 | 79.3%
Total Program Quantity Delivered | 7107 | 6488 | 8040 | 80.7%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
1800.5
1632.2
90.65%
21
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
20
95.24%
1761.3
97.82%
The above data is current as of February 09, 2016.
Planned and actual projectile quantities refer to projectiles delivered to the Army. FMS and U.S. Marine Corps sales are not included.
Production deliveries include 3,475 Excalibur Inc Ia projectiles and 2,469 Excalibur Inc Ib projectiles.

## Table 37
Operating and Support Cost
Cost Estimate Details
Date of Estimate: June 25, 2014
Source of Estimate: SCP
Quantity to Sustain: 6264
Unit of Measure: Total Quantity
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2007 - FY 2038
A total of 7,496 projectiles will be procured, 6,830 will be delivered to inventory (566 replace expended or damaged projectiles, leaving 6,264 to be sustained) and 666 will be consumed in testing. The 544 RDT&E-funded projectiles were consumed in test.
Sustainment Strategy
Excalibur is a one shot use item. There is no scheduled maintenance over the 20-year shelf life. There is a defined stockpile surveillance program which will be used to calculate stockpile reliability and detect/measure adverse trends of critical parameters. The surveillance program began in FY 2015.
Antecedent Information
No Antecedent
Annual O&S Costs BY2007 $K
Cost Element | EXCALIBUR Average Annual Cost Per Total Quantity | No Antecedent Program (Antecedent)
Unit-Level Manpower | 0 | --
Unit Operations | 0 | --
Maintenance | 142.75 | --
Sustaining Support | 251.344 | --
Continuing System Improvements | 0 | --
Indirect Support | 0 | --
Other | 0 | --
Total | 394.094 | --
Costs are calculated as the average annual cost for all projectiles for each category over the 32-years Excalibur is planned to be in the field (FY 2007 - FY 2038).
Maintenance costs include stockpile surveillance, laboratory teardown testing, and Depot Inventory Management.
Sustaining Support includes the storage cost of projectiles and Systems Engineering/Program Management.

## Table 38
Item | Total O&S Cost $M
| EXCALIBUR | [5 empty] | No Antecedent Program (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 20.8 |  | 22.9 |  |  | 12.6 | N/A
Then Year | 31.6 |  | N/A |  |  | 18.1 | N/A
Disposal Cost is included in the Operating and Support Cost of the current APB objective and threshold for this program.
Equation to Translate Annual Cost to Total Cost
Total Cost = average annual cost per all fielded Excalibur projectiles * planned life = $394.1K * 32 years = $12.6M
O&S Cost Variance
Category |  | BY 2007 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
12.5
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.1 Increased cost for storage of additional projectiles being procured to replenish the stockpile.
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.1
Current Estimate 12.6
The minor increase in O&S costs is due to the increased storage costs estimated due to the additional projectiles being procured in FY 2016 and FY 2017 to replenish the stockpile.
Disposal Estimate Details
Date of Estimate: June 25, 2015
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2007 $M): Total costs for disposal of all Total Quantity are 8.9
Demilitarization/Disposal costs of $8.9M (BY 2007) are included in the Excalibur Inc Ib FRP Army Cost Position. This is a
$0.5M increase from the December 2014 estimate due to an increased quantity of projectiles to be disposed.