## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-205
Integrated Air and Missile Defense (IAMD)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 15
Cost and Funding 16
Low Rate Initial Production 24
Foreign Military Sales 25
Nuclear Costs 25
Unit Cost 26
Cost Variance 29
Contracts 32
Deliveries and Expenditures 34
Operating and Support Cost 35

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Integrated Air and Missile Defense (IAMD)
DoD Component
Army
Responsible Office
Mr. Michael Chandler - IAMD Project Office 5250 Martin Road
Redstone Arsenal, AL 35898-8000
michael.r.chandler10.civ@mail.mil
Phone: | 256-313-3576
Fax: | 256-313-3460
DSN Phone: | 897-3576
DSN Fax: | 897-3460
Date Assigned: | October 19, 2014
References
SAR Baseline (Development Estimate)
FY 2011 President's Budget dated February 1, 2010
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 8, 2014

## Table 6
Mission and Description
The mission of the Army Integrated Air and Missile Defense (IAMD) Project Office (PO) is to define, develop, acquire, field and sustain the Army’s portion of the Joint IAMD System of Systems capability to be deployed as integrated components in Army, Joint, Interagency, Inter-Governmental and Multi-National net-centric architectures. Additionally, the IAMD PO will develop, acquire, field and sustain the IAMD Battle Command System (IBCS) component of the architecture and integrate externally developed sensors and shooters to provide an effective IAMD capability.
The IAMD program will allow transformation to a network-centric system of systems capability, also referred to as "Plug and Fight", that integrates all Air and Missile Defense (AMD) sensors, weapons, and mission control. The IAMD program will integrate the Patriot and Improved Sentinel components to support the engagement of air breathing targets, cruise missiles, unmanned aerial vehicles, and the tactical ballistic missiles threat. Each sensor and weapon platform will have a "Plug and Fight" interface module, which supplies distributed battle management functionality to enable network-centric operations.
Additionally, the IBCS functionality will be incorporated into Air Defense Airspace Management Cells, Air Defense Artillery Brigade Headquarters, and Army Air and Missile Defense Command Headquarters.
The common IBCS provides the functional capabilities to control and manage the IAMD sensors and weapons via the Integrated Fire Control Network capability for fire control connectivity and enabling distributed operations. Central to the IAMD program is the IBCS Development Program consisting of the IBCS Major End Items (MEI): the Engagement Operations Center and "Plug and Fight" modules. The development of these MEIs is essential to achieving Army transformation imperatives, connectivity to the Global Interface Grid for Joint operations, obtaining a Joint Single Integrated Air Picture, establishing Engage on Network capabilities, enabling Net-Ready operations for Army AMD components, and providing a common IAMD mission command capability. This innovative approach at modernization will reduce O&S costs and will enhance training.

## Table 7
Executive Summary
The Army IAMD program conducted its first successful intercept test against a Tactical Ballistic Missile (TBM) surrogate target utilizing a Patriot Guidance Enhanced Missile-Tactical (GEM-T) missile on May 28, 2015. The Patriot-As-A-Target TBM surrogate flew a TBM trajectory against an asset defended by an AIAMD task force comprised of a Battalion Engagement Operations Center (EOC), a non-collocated Battery EOC with a Patriot radar, and a remote Integrated Fire Control Network (IFCN) Relay connected to two adapted Patriot Launchers operating on an IFCN. The two adapted Patriot Launchers were equipped with GEM-T missiles to intercept the threatening TBM surrogate. This test demonstrated a dramatic change in how current air and missile defense systems will operate in the future in a netted system of systems architecture. This test also demonstrated the ability to conduct an engagement over an IFCN utilizing the IAMD Battle Command System (IBCS).
The Army IAMD program conducted its first successful intercept test against a Cruise Missile surrogate target utilizing a Patriot Advanced Capability Three (PAC-3) interceptor and composite track data from Sentinel and Patriot radars on November 12, 2015. This test demonstrated the Army’s capability to identify, track, engage and kill targets using an interceptor from one legacy air defense system and remote sensors to another legacy air defense system operating on the IFCN under the control of the IBCS. The cruise missile surrogate, an MQM-107 Drone Target, flew a low altitude trajectory against an asset defended by an Army IAMD task force comprised of a Battalion EOC, a non-collocated Battery EOC with a Patriot radar, a remote IFCN Relay connected to two Patriot PAC-3 launchers, two remote Sentinel radars connected to IFCN Relays, all operating on the IFCN. The low altitude trajectory of the target obscured it from the Patriot radar’s field of view. As designed, the IBCS system correctly utilized the Sentinel composite tracking data to calculate the necessary engagement solution resulting in the PAC-3 missile successfully engaging and killing the target.
The IAMD Project Office Logistics Directorate published the results of the IBCS Early Abbreviated Demonstration (EAD) on November 12, 2015. The IAMD EAD was conducted at the Tobin Wells Training Facility at Fort Bliss, Texas
from September 17 to October 8, 2015 to gain preliminary data points for Mean Time to Repair and Product Support Package validation to support the forthcoming IBCS Initial Operational Test & Evaluation Logistics Demonstration tentatively scheduled for 4th Quarter FY 2017.
An IBCS Army Acquisition Objective (AAO) adjustment memo was approved by Headquarters, Department of the Army on December 23, 2015. This memo adjusted the AAO from 431 to 454 EOCs. A revised program baseline will be established at Milestone C to reflect these quantities.
On February 23, 2016 the DAE hosted an IAMD status review presented by the PM. Army IAMD is preparing for a Limited User Test from March through May 2016 as the program proceeds to a Milestone C decision in August 2016. The areas of concerns were software maturity, system reliability and operator training/readiness. The program remains on track to execute per the current schedule.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
MS B | Dec 2009 | Dec 2009 | Dec 2009 | Dec 2009
CDR | Aug 2011 | May 2012 | May 2012 | May 2012
MS C | Dec 2014 | Aug 2016 | Aug 2017 | Aug 2016
IOT&E
Start | Jan 2016 | Oct 2017 | Oct 2018 | Oct 2017
Complete | Jul 2016 | Apr 2018 | Apr 2019 | Apr 2018
IOC | Aug 2016 | Jun 2018 | Jun 2019 | Jun 2018
FRP | May 2017 | Oct 2018 | Oct 2019 | Oct 2018
Change Explanations
Acronyms and Abbreviations
CDR - Critical Design Review
IOT&E - Initial Operational Test and Evaluation MS - Milestone

## Table 10
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Net Ready
The Army IAMD SoS | The Army IAMD SoS | The Army IAMD SoS | TBD | The Army IAMD SoS
must fully support | must fully support | must fully support |  | must fully support
execution of joint critical | execution of all | execution of joint critical |  | execution of joint
operational activities | operational activities | operational activities |  | critical operational
identified in the applicable | identified in the | identified in the |  | activities identified in
joint- and system- | applicable joint and | applicable joint- and |  | the applicable Joint-
integrated architectures, | system integrated | system-integrated |  | and system-
and the system must | architectures and the | architectures, and the |  | integrated
satisfy the technical | system must satisfy the | system must satisfy the |  | architectures, and
requirements for | technical requirements | technical requirements |  | the system must
transition to Net-Centric | for Net-Centric military | for transition to Net- |  | satisfy the technical
military operations to | operations to include | Centric military |  | requirements for
include the following: | the following: DISR | operations to include |  | transition to Net-
DISR mandated GIG IT | mandated GIG IT | the following: DISR |  | Centric military
standards and profiles | standards and profiles | mandated GIG IT |  | operations to include
identified in the TV- | identified in the TV-1 | standards and profiles |  | the following: DISR
1 •DISR mandated GIG | DISR mandated GIG | identified in the TV-1 |  | mandated GIG IT
KIPs identified in the KIP | KIPs identified in the | DISR mandated GIG |  | standards and
declaration table NCOW | KIP declaration table | KIPs identified in the |  | profiles identified in
RM Enterprise | NCOW RM Enterprise | KIP declaration table |  | the TV-1. DISR
Services •Information | Services IA | NCOW RM Enterprise |  | mandated GIG KIPs
assurance requirements | requirements including | Services IA |  | identified in the KIP
including availability, | availability, integrity, | requirements including |  | declaration table.
integrity, authenticat-ion, | authentication, | availability, integrity, |  | NCOW RM
confidential-ity, and non- | confidentiality, and non- | authentication, |  | Enterprise Services.
repudiation, and issuance | repudiation, and | confidentiality, and non- |  | Information
of an ATO by the | issuance of an ATO by | repudiation, and |  | assurance
DAA •Operationally | the DAA Operationally | issuance of an ATO by |  | requirements
effective information | effective information | the DAA Operationally |  | including availability,
exchanges •Mission | exchanges Mission | effective information |  | integrity,
critical performance and | critical performance | exchanges Mission |  | authentication,
information assurance | and IA attributes, data | critical performance |  | confidentiality, and
attributes, data | correctness, data | and IA attributes, data |  | non-repudiation, and
correctness, data | availability, and | correctness, data |  | issuance of an ATO
availability, and | consistent data | availability, and |  | by the DAA.
consistent data | processing specified in | consistent data |  | Operationally
processing specified in | the applicable joint and | processing specified in |  | effective information
the applicable joint- and | system integrated | the applicable joint- and |  | exchanges. Mission
system-integrated | architecture views. | system-integrated |  | critical performance
architecture views. |  | architecture views. |  | and information
assurance attributes,
data correctness,
data availability, and
consistent data

## Table 11
processing specified in the applicable Joint - and system- integrated architecture views.
Integrated Defense Effectiveness
To support attainment of | To support attainment | To support attainment | TBD | To support
a command-er’s defense | of a commander’s | of a commander’s |  | attainment of a
effectiveness objectives, | defense effectiveness | defense effectiveness |  | commander’s
which would normally | objectives, which would | objectives, which would |  | defense
range from 0.50% to | normally range from 0.5 | normally range from 0.5 |  | effectiveness
0.99%, the Army IAMD | to 0.99, the Army IAMD | to 0.99, the Army IAMD |  | objectives, which
SoS shall provide flexible | SoS shall provide | SoS shall provide |  | would normally range
interceptor selection and | flexible interceptor | flexible interceptor |  | from 0.50% to 0.99%,
firing doctrine within the | selection and firing | selection and firing |  | the Army IAMD SoS
Task Force. The Army | doctrine within the Task | doctrine within the Task |  | shall provide flexible
IAMD SoS-integrated | Force. The Army IAMD | Force. The Army IAMD |  | interceptor selection
defenses shall enable | SoS-integrated | SoS-integrated |  | and firing doctrine
defeat of non-ballistic and | defenses shall enable | defenses shall enable |  | within the Task
ballistic platforms at | defeat of non-ballistic | defeat of non-ballistic |  | Force. The Army
times and locations not | and ballistic platforms | and ballistic platforms |  | IAMD SoS-integrated
otherwise available to the | at times and locations | at times and locations |  | defenses shall
commander without an | not otherwise available | not otherwise available |  | enable defeat of non-
integrated operations | to the commander | to the commander |  | ballistic and ballistic
capability by exploiting | without an integrated | without an integrated |  | platforms at times
fused organic and non- | operations capability by | operations capability by |  | and locations not
organic sensor data to | exploiting fused organic | exploiting fused organic |  | otherwise available to
execute engage-ments | and non-organic sensor | and non-organic sensor |  | the commander
up to the operationally | data to execute | data to execute |  | without an integrated
effective range of | engagements up to the | engagements up to the |  | operations capability
selected missile | operationally effective | operationally effective |  | by exploiting fused
kinematics. The Army | range of selected | range of selected |  | organic and non-
IAMD SoS shall be | missile kinematics. The | missile kinematics. The |  | organic sensor data
capable of allowing | Army IAMD SoS shall | Army IAMD SoS shall |  | to execute
greater defense | be capable of allowing | be capable of allowing |  | engagements up to
effectiveness for high- | greater defense | greater defense |  | the operationally
priority assets while | effectiveness for high- | effectiveness for high- |  | effective range of
increasing defense | priority assets while | priority assets while |  | selected missile
effectiveness to full 360- | increasing defense | increasing defense |  | kinematics. The
degree coverage against | effectiveness to full 360 | effectiveness to full 360 |  | Army IAMD SoS shall
attacking non-ballistic | -degree coverage | -degree coverage |  | be capable of
threats. The Army IAMD | against attacking non- | against attacking non- |  | allowing greater
SoS defense | ballistic threats. The | ballistic threats. The |  | defense
effectiveness levels shall | Army IAMD SoS | Army IAMD SoS |  | effectiveness for high
not degrade and be equal | defense effectiveness | defense effectiveness |  | -priority assets while
to or greater than the | levels shall not degrade | levels shall not degrade |  | increasing defense
effectiveness levels of | and be equal to or | and be equal to or |  | effectiveness to full
fielded TBM and CM/ABT | greater than the | greater than the |  | 360-degree coverage
defense systems. | effectiveness levels of | effectiveness levels of |  | against attacking non
| fielded TBM and | fielded TBM and |  | -ballistic threats. The
| CM/ABT defense | CM/ABT defense |  | Army IAMD SoS
| systems. | systems. |  | defense
effectiveness levels

## Table 12
shall not degrade and be equal to or greater than the effectiveness levels of fielded TBM and CM/ABT defense systems.
Common Command and Control
The Army IAMD SoS common C2 components (Battalion and below) shall incorporate common functionality that includes: defense planning, defense design, warfighter-machine interface, battle monitor and control, network interface and manage- ment, track manage- ment, engagement planning, engagement decision, engagement monitoring, and staff functions. The Army IAMD SoS shall provide backward compatibility to enable integration and common functionality (as defined above) of a current force Patriot Battery/SLAMRAAM Platoon with the Increment 2 equipped Task Force. | The Army IAMD SoS common C2 components (Battalion and below) shall incorporate common functionality that includes: defense planning, defense design, warfighter- machine interface, battle monitor and control, network interface and management, track management, engagement planning, engagement decision, engagement monitoring, and staff functions. The Army IAMD SoS shall provide backward compatibility to enable integration and common functionality (as defined above) of a current force Patriot Battery/SLAMRAAM Platoon with the Increment 2 equipped Task Force. | The Army IAMD SoS common C2 components (Battalion and below) shall incorporate common functionality that includes: defense planning, defense design, warfighter- machine interface, battle monitor and control, network interface and management, track management, engagement planning, engagement decision, engagement monitoring, and staff functions. The Army IAMD SoS shall provide backward compatibility to enable integration and common functionality (as defined above) of a current force Patriot Battery/SLAMRAAM Platoon with the Increment 2 equipped Task Force. | TBD | The Army IAMD SoS common C2 components (Battalion and below) shall incorporate common functionality that includes: defense planning, defense design, warfighter-machine interface, battle monitor and control, network interface and management, track management, engagement planning, engagement decision, engagement monitoring, and staff functions. The Army IAMD SoS shall provide backward compatibility to enable integration and common functionality (as defined above) of a current force PATRIOT Battery/ SLAMRAAM Platoon with the Increment 2 equipped Task Force.
Material Availability
The Army IAMD SoS C2 shall achieve an Operational Availability (Ao) of at least 95%. | The Army IAMD SoS common C2 shall achieve an Ao 99%. | The Army IAMD SoS common C2 shall achieve an Ao of at least 95%. | TBD | The Army IAMD SoS C2 shall achieve an Ao of at least 95%.
Force Protection and Survivability
The Army IAMD SoS common C2 equipment shall be designed to be | All Army IAMD SoS common C2 vehicle cabs and manned | The Army IAMD SoS common C2 equipment shall be designed to be | TBD | The Army IAMD SoS common C2 equipment shall be

## Table 13
operated by Soldiers | shelters shall be | operated by Soldiers | designed to be
wearing body armor and | capable of adding up- | wearing body armor | operated by soldiers
equipped with appropriate | armor protection | and equipped with | wearing body armor
weapons; shall have | sufficient to repel | appropriate weapons; | and equipped with
situational awareness | enemy small arms as | shall have situational | appropriate weapons;
and under-standing | developed by the PM, | awareness and | shall have situational
commens-urate with the | FMTV. All equipment | understanding | awareness and
supported force; will | manned during | commensurate with the | understanding
report the position and ID | transport or operations | supported force; will | commensurate with
of all Army IAMD SoS | shall mitigate the | report the position and | the supported force;
system into the COP and | effects of 7.62mm | ID of all Army IAMD SoS | will report the position
BFT nets; shall be | rounds and below. | system into the COP | and ID of all Army
operable by Soldiers in |  | and BFT nets; shall be | IAMD SoS system
MOPP 4; and shall |  | operable by Soldiers in | into the COP and
survive decontami-nation |  | MOPP 4; and shall | BFT nets; shall be
procedures in such a |  | survive | operable by soldiers
manner that it can quickly |  | decontamination | in MOPP 4; and shall
return (within 30 minutes) |  | procedures in such a | survive
to full operational |  | manner that it can | decontamination
capability. All Army IAMD |  | quickly return (within 30 | procedures in such a
SoS common C2 vehicle |  | min) to full operational | manner that it can
cabs shall be capable of |  | capability. All Army | quickly return (within
adding up-armor |  | IAMD SoS common C2 | 30 min) to full
protection sufficient to |  | vehicle cabs shall be | operational capability.
repel enemy small arms |  | capable of adding up- | All Army IAMD SoS
as developed by the PM, |  | armor protection | common C2 vehicle
FMTV. Manned rigid wall |  | sufficient to repel | cabs shall be
shelters incorporated into |  | enemy small arms as | capable of adding up-
the Army IAMD SoS shall |  | developed by the PM, | armor protection
provide an active |  | FMTV. Manned rigid | sufficient to repel
overpressure system to |  | wall shelters | enemy small arms
prevent contaminat-ion |  | incorporated into the | as developed by PM
during a CBRNE event |  | Army IAMD SoS shall | FMTV. Manned rigid
that is sustainable |  | provide an active | wall shelters
through decontami- |  | overpressure system to | incorporated into the
nation. |  | prevent contamination | Army IAMD SoS shall
|  | during a CBRNE event | provide an active
|  | that is sustainable | overpressure system
|  | through | to prevent
|  | decontamination. | contamination during
a CBRNE event that
is sustainable
through
decontamination.
Requirements Reference
CDD dated May 17, 2010
Change Explanations
None

## Table 14
Notes
The Common Command and Control KPP no longer includes SLAMRAAM backward compatibility. This change will be reflected in the approved CPD supporting Milestone C.
Acronyms and Abbreviations
ABT - Air Breathing Threat Ao - Operational Availability ATO - Approval to Operate BFT - Blue Force Tracking C2 - Command and Control
CBRNE - Chemical, Biological, Radiological, Nuclear and High Yield Explosives CM - Cruise Missile
COP - Common Operating Picture DAA - Designated Approval Authority
DISR - DoD Information Technology Standards Registry FMTV - Family of Medium Tactical Vehicles
GIG - Global Information Grid IA - Information Assurance ID - Identification
IT - Information Technology KIP - Key Information Profile min - minute
mm - millimeter
MOPP - Mission Oriented Protective Posture
NCOW RM - Net-Centric Operations and Warfare Reference Model SLAMRAAM - Surface-Launched Advanced Medium Range Air-to-Air Missile SoS - System of Systems
TBM - Tactical Ballistic Missile
TV - Technical View, Standards Profile

## Table 15
Track to Budget
RDT&E
Appn |  | BA | PE
Army 2040 04 0603327A
Project Name
S34 AMD System of Systems Engineering and Integration
Army 2040 05 0605457A
Project Name
DU4 Advanced Electronic Protection Enhancements
S40 Army Integrated Air and Missile Defense
(Sunk)
(Sunk)
Notes: Army IAMD Project Office Engineering and Manufacturing Development program funding began in FY 2011.
Procurement
Appn |  | BA | PE
Army 2035 02 0214400A
Line Item | Name
BZ5075 IAMD Battle Command System

## Table 16
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2009 $M |  |  |  | BY 2009 $M |  | TY $M
| SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Development Estimate |  | Current APB Development Objective |  | Current Estimate
RDT&E | 1540.6 |  | 2199.5 | 2419.5 |  | 2385 |  | 1627.5 |  | 2402.6 |  | 2632.9
Procurement | 3316 |  | 3174.8 | 3492.3 |  | 3403.7 |  | 4164.1 |  | 3939.2 |  | 4379.4
Flyaway | -- |  | -- | -- |  | 3248 |  | -- |  | -- |  | 4178.5
Recurring | -- |  | -- | -- |  | 3243.9 |  | -- |  | -- |  | 4173.9
Non Recurring | -- |  | -- | -- |  | 4.1 |  | -- |  | -- |  | 4.6
Support | -- |  | -- | -- |  | 155.7 |  | -- |  | -- |  | 200.9
Other Support | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Initial Spares | -- |  | -- | -- |  | 155.7 |  | -- |  | -- |  | 200.9
MILCON | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 4856.6 |  | 5374.3 | N/A |  | 5788.7 |  | 5791.6 |  | 6341.8 |  | 7012.3
Current APB Cost Estimate Reference
CAPE ICE dated June 07, 2012
Confidence Level
Confidence Level of cost estimate for current APB: 50%
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for MDAPs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.

## Table 17
Total Quantity
Quantity | SAR Baseline Development Estimate | Current APB Development | Current Estimate
RDT&E | 11 | 16 | 16
Procurement | 285 | 431 | 427
Total | 296 | 447 | 443
Quantity Notes
The IAMD Unit of Measure - 16 Fully Configured RDT&E units and 431 IAMD Battle Command Systems Procurement Quantities which enable System of Systems operation of Air and Missile Defense Units as defined in the IAMD CDD.

## Table 18
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 1649 | 222.1 |  | 252.8 |  | 169.1 | 152.9 |  | 32.9 |  | 34.4 |  |  | 119.7 |  | 2632.9
Procurement | 0 | 20.9 |  | 205 |  | 287.2 | 372.9 |  | 440.6 |  | 439.8 |  |  | 2613 |  | 4379.4
MILCON | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 1649 | 243 |  | 457.8 |  | 456.3 | 525.8 |  | 473.5 |  | 474.2 |  |  | 2732.7 |  | 7012.3
PB 2016 Total | 1654.2 | 235 |  | 431.6 |  | 465.9 | 529.2 |  | 477 |  | 466.3 |  |  | 2732.7 |  | 6991.9
Delta | -5.2 | 8 |  | 26.2 |  | -9.6 | -3.4 |  | -3.5 |  | 7.9 |  |  | 0 |  | 20.4
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 16 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 16
Production | 0 |  | 0 |  | 0 | 12 | 16 |  | 25 |  | 39 | 65 |  | 270 |  | 427
PB 2017 Total | 16 |  | 0 |  | 0 | 12 | 16 |  | 25 |  | 39 | 65 |  | 270 |  | 443
PB 2016 Total | 16 |  | 0 |  | 0 | 18 | 24 |  | 44 |  | 47 | 53 |  | 241 |  | 443
Delta | 0 |  | 0 |  | 0 | -6 | -8 |  | -19 |  | -8 | 12 |  | 29 |  | 0

## Table 19
Cost and Funding
Annual Funding By Appropriation
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36.3
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 114.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 164.7
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 246.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 262
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 247.4
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 358.2
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 147.3
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 222.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 252.8
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 169.1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 152.9
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.9
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.4
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.5
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.7
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.5
Subtotal |  | 16 | -- |  | -- |  | -- |  | -- |  | -- |  | 2632.9

## Table 20
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2009 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.8
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.1
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.1
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 113.4
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 160.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 235.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 246.5
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 228.9
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 325
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 131.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 196.2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 219.3
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 143.9
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 127.5
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.9
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.6
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36.8
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.3
Subtotal |  | 16 | -- |  | -- |  | -- |  | -- |  | -- |  | 2385

## Table 21
Annual Funding 2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | -- | 16.3 |  | -- |  | 4.6 |  | 20.9 |  | -- |  | 20.9
2017 |  | 12 | 205 |  | -- |  | -- |  | 205 |  | -- |  | 205
2018 |  | 16 | 281.3 |  | -- |  | -- |  | 281.3 |  | 5.9 |  | 287.2
2019 |  | 25 | 356.5 |  | -- |  | -- |  | 356.5 |  | 16.4 |  | 372.9
2020 |  | 39 | 416.6 |  | -- |  | -- |  | 416.6 |  | 24 |  | 440.6
2021 |  | 65 | 412.1 |  | -- |  | -- |  | 412.1 |  | 27.7 |  | 439.8
2022 |  | 53 | 488.6 |  | -- |  | -- |  | 488.6 |  | 29.2 |  | 517.8
2023 |  | 45 | 476.2 |  | -- |  | -- |  | 476.2 |  | 30.6 |  | 506.8
2024 |  | 43 | 391 |  | -- |  | -- |  | 391 |  | 24.8 |  | 415.8
2025 |  | 42 | 394.1 |  | -- |  | -- |  | 394.1 |  | 22.8 |  | 416.9
2026 |  | 48 | 279.9 |  | -- |  | -- |  | 279.9 |  | 9.3 |  | 289.2
2027 |  | 34 | 217 |  | -- |  | -- |  | 217 |  | 6.2 |  | 223.2
2028 |  | 5 | 161.7 |  | -- |  | -- |  | 161.7 |  | 4 |  | 165.7
2029 |  | -- | 77.6 |  | -- |  | -- |  | 77.6 |  | -- |  | 77.6
Subtotal |  | 427 | 4173.9 |  | -- |  | 4.6 |  | 4178.5 |  | 200.9 |  | 4379.4

## Table 22
Annual Funding 2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity |  | BY 2009 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | -- | 14.3 |  | -- |  | 4.1 |  | 18.4 |  | -- |  | 18.4
2017 |  | 12 | 176.9 |  | -- |  | -- |  | 176.9 |  | -- |  | 176.9
2018 |  | 16 | 238 |  | -- |  | -- |  | 238 |  | 5 |  | 243
2019 |  | 25 | 295.7 |  | -- |  | -- |  | 295.7 |  | 13.6 |  | 309.3
2020 |  | 39 | 338.8 |  | -- |  | -- |  | 338.8 |  | 19.5 |  | 358.3
2021 |  | 65 | 328.6 |  | -- |  | -- |  | 328.6 |  | 22 |  | 350.6
2022 |  | 53 | 381.9 |  | -- |  | -- |  | 381.9 |  | 22.8 |  | 404.7
2023 |  | 45 | 364.9 |  | -- |  | -- |  | 364.9 |  | 23.5 |  | 388.4
2024 |  | 43 | 293.8 |  | -- |  | -- |  | 293.8 |  | 18.6 |  | 312.4
2025 |  | 42 | 290.3 |  | -- |  | -- |  | 290.3 |  | 16.8 |  | 307.1
2026 |  | 48 | 202.1 |  | -- |  | -- |  | 202.1 |  | 6.7 |  | 208.8
2027 |  | 34 | 153.6 |  | -- |  | -- |  | 153.6 |  | 4.4 |  | 158
2028 |  | 5 | 112.2 |  | -- |  | -- |  | 112.2 |  | 2.8 |  | 115
2029 |  | -- | 52.8 |  | -- |  | -- |  | 52.8 |  | -- |  | 52.8
Subtotal |  | 427 | 3243.9 |  | -- |  | 4.1 |  | 3248 |  | 155.7 |  | 3403.7

## Table 23
Cost Quantity Information 2035 ¦ Procurement ¦ Other Procurement, Army
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2009 $M
2016 | -- | --
2017 | 12 | 191.2
2018 | 16 | 238
2019 | 25 | 295.7
2020 | 39 | 338.8
2021 | 65 | 328.6
2022 | 53 | 381.9
2023 | 45 | 364.9
2024 | 43 | 293.8
2025 | 42 | 290.3
2026 | 48 | 202.1
2027 | 34 | 153.6
2028 | 5 | 165
2029 | -- | --
Subtotal | 427 | 3243.9

## Table 24
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2009-12-23 | 2009-12-23
Approved Quantity | 27 | 27
Reference | Milestone B ADM | MS B ADM
Start Year | 2015 | 2017
End Year | 2016 | 2018

## Table 25
Foreign Military Sales
Notes
The IAMD program continues to refine the program protection techniques and incorporate them into the baseline program design. Interest in the system has been expressed by the Netherlands, Germany, Poland, Saudi Arabia and the United Kingdom.
Nuclear Costs
None

## Table 26
Unit Cost
Unit Cost Report
Item |  | BY 2009 $M | BY 2009 $M |  | % Change
|  | Current UCR Baseline (Oct 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 5374.3 |  |  | 5788.7
Quantity | 447 |  |  | 443
Unit Cost | 12.023 |  |  | 13.067 |  | 8.68
Average Procurement Unit Cost
Cost | 3174.8 |  |  | 3403.7
Quantity | 431 |  |  | 427
Unit Cost | 7.366 |  |  | 7.971 |  | 8.21
Item |  | BY 2009 $M | BY 2009 $M |  | % Change
|  | Original UCR Baseline (Jun 2010 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 4806.8 |  |  | 5788.7
Quantity | 296 |  |  | 443
Unit Cost | 16.239 |  |  | 13.067 |  | -19.53
Average Procurement Unit Cost
Cost | 3316 |  |  | 3403.7
Quantity | 285 |  |  | 427
Unit Cost | 11.635 |  |  | 7.971 |  | -31.49

## Table 27
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2009 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Jun 2010 |  |  |  |  | 16.239 |  |  | 11.635 |  |  | 19.382 |  |  | 14.611
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | Nov 2012 |  |  |  |  | 12.023 |  |  | 7.366 |  |  | 14.187 |  |  | 9.14
Current APB |  |  | Oct 2014 |  |  |  |  | 12.023 |  |  | 7.366 |  |  | 14.187 |  |  | 9.14
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 12.947 |  |  | 7.948 |  |  | 15.783 |  |  | 10.305
Current Estimate |  |  | Dec 2015 |  |  |  |  | 13.067 |  |  | 7.971 |  |  | 15.829 |  |  | 10.256
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
19.566 0.184 -1.980 -0.122 0.385 -0.040 0.000 -2.164 -3.737 15.829
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
14.611 0.187 -0.152 -0.127 0.000 -2.018 0.000 -2.245 -4.355 10.256

## Table 28
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Dec 2009 | N/A | Dec 2009
Milestone C | N/A | Dec 2014 | N/A | Aug 2016
IOC | N/A | Aug 2016 | N/A | Jun 2018
Total Cost (TY $M) | N/A | 5791.6 | N/A | 7012.3
Total Quantity | N/A | 296 | N/A | 443
PAUC | N/A | 19.566 | N/A | 15.829

## Table 29
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
1627.5 4164.1 -- 5791.6
Economic |  | 12.1 |  | 114.2 |  | -- |  | 126.3
Quantity |  | -10.8 |  | 2009.9 |  | -- |  | 1999.1
Schedule |  | -- |  | -95.2 |  | -- |  | -95.2
Engineering |  | 170.6 |  | -- |  | -- |  | 170.6
Estimating |  | 792.4 |  | -832.9 |  | -- |  | -40.5
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -960 |  | -- |  | -960
Subtotal |  | 964.3 |  | 236 |  | -- |  | 1200.3
Current Changes Economic |  | -10.1 |  | -34.5 |  | -- |  | -44.6
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 41.1 |  | -- |  | 41.1
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 51.2 |  | -28.6 |  | -- |  | 22.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 1.3 |  | -- |  | 1.3
Subtotal |  | 41.1 |  | -20.7 |  | -- |  | 20.4
Total Changes |  | 1005.4 |  | 215.3 |  | -- |  | 1220.7
CE - Cost Variance |  | 2632.9 |  | 4379.4 |  | -- |  | 7012.3
CE - Cost & Funding |  | 2632.9 |  | 4379.4 |  | -- |  | 7012.3

## Table 30
Summary BY 2009 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
1540.6 3316.0 -- 4856.6
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -9.2 |  | 1436.6 |  | -- |  | 1427.4
Schedule |  | -- |  | 3 |  | -- |  | 3
Engineering |  | 148.7 |  | -- |  | -- |  | 148.7
Estimating |  | 661.2 |  | -620.4 |  | -- |  | 40.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -741.2 |  | -- |  | -741.2
Subtotal |  | 800.7 |  | 78 |  | -- |  | 878.7
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 43.7 |  | 8.4 |  | -- |  | 52.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 1.3 |  | -- |  | 1.3
Subtotal |  | 43.7 |  | 9.7 |  | -- |  | 53.4
Total Changes |  | 844.4 |  | 87.7 |  | -- |  | 932.1
CE - Cost Variance |  | 2385 |  | 3403.7 |  | -- |  | 5788.7
CE - Cost & Funding |  | 2385 |  | 3403.7 |  | -- |  | 5788.7
Previous Estimate: December 2014

## Table 31
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -10.1
Revised estimate for test equipment and test and integration efforts resulting from test plan changes. (Estimating)
+39.7 +46.8
Adjustment for current and prior escalation. (Estimating) +4.0 +4.4
RDT&E Subtotal +43.7 +41.1
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -34.5
Accelerated procurement buy profile from FY 2017 to FY 2028 to align with fielding synchronization efforts. (Schedule)
Revised estimate for IAMD Battle Command System components resulting from design maturation. (Estimating)
0.0 +41.1
+8.2 -28.8
Adjustment for current and prior escalation. (Estimating) Increase in Initial Spares resulting from design maturation. (Support) | +0.2 +1.3 |  |  | +0.2 +1.3
Procurement Subtotal | 9.7 |  |  | -20.7

## Table 32
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: IAMD Battle Command System (IBCS) Development Program
Contractor: Northrop Grumman Space & Mission Systems Corporpation
Contractor Location: 213 Wynn Drive
Huntsville, AL 35805
Contract Number: W31P4Q-08-C-0418
Contract Type: Cost Plus Incentive Fee (CPIF)
Award Date: December 30, 2009
Definitization Date: December 30, 2009
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
420.0 N/A 11 819.8 N/A 11 814.4 814.4
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to an increase in contract cost since original contract value. Several modifications have been issued to adjust the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) -9.0 -0.6
Previous Cumulative Variances -4.3 -4.5
Net Change -4.7 +3.9
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to the discovery of software issues during software integration at the system of systems level which required unplanned additional effort. No impact to the Estimate at Completion is anticipated.
The favorable net change in the schedule variance is due to the award of modification #20 (P00118) which extended the contract to November 30, 2016.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 33
Contract Identification
Appropriation: RDT&E
Contract Name: A-Kit Development
Contractor: Raytheon Company
Contractor Location: 401 Jan Davis Dr
Huntsville, AL 35806
Contract Number: W31P4Q-12-C-0120
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: February 14, 2012
Definitization Date: September 19, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
126.0 N/A 1 152.8 N/A 1 152.4 152.4
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to an increase in contract cost. Contract modification P00039 was received on April 28, 2015 which extended the period of performance to November 30, 2015 and added scope for the continuation of IAMD support requirements, described as Phase 2 Extension.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) -0.2 0.0
Previous Cumulative Variances -1.0 -0.1
Net Change +0.8 +0.1
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to completion of the most challenging phase of the program. As a result, the effort going forward became less complex.
The favorable net change in the schedule variance is due to
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 34
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 12 | 12 | 16 | 75%
Production | 0 | 0 | 427 | 0%
Total Program Quantity Delivered | 12 | 12 | 443 | 2.71%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
7012.3
1385.3
19.76%
24
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
11
45.83%
1892
26.98%
The above data is current as of February 09, 2016.
Expenditures to Date decreased from the FY 2016 PB due to miscalculation; the correct Expenditures to Date are included in this report.

## Table 35
Operating and Support Cost
Cost Estimate Details
Date of Estimate: February 20, 2014
Source of Estimate: POE
Quantity to Sustain: 427
Unit of Measure: Engagement Operations Center (EOC)
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2018 - FY 2048
The difference in the acquisition quantity of 443 and the sustainment quantity of 427 is due to 16 RDT&E prototypes that are not to be sustained.
An IAMD Engagement Operations Center provides common mission command through an IAMD Battle Command System with full Engagement Operations/Force Operations capability.
Sustainment Strategy
The IAMD Program will be supported by a combination of Army organic and contractor-provided resources through a Performance Based Logistics (PBL) Product Support Strategy (PSS). Under PBL sustainment constructs, the IAMD Project Office will utilize performance based sustainment methods and performance metrics which will include a public- private partnership. The sustainment decision will be the result of a Product Support Business Case Analysis. The IAMD PBL PSS provides a sustainment level product support decision that will provide the human interface, tools, and resources needed to sustain the IAMD equipment throughout its life cycle.
Antecedent Information
No Antecedent
Annual O&S Costs BY2009 $K
Cost Element | IAMD Average Annual Cost Per Engagement Operations Center (EOC) | No Antecedent System (Antecedent)
Unit-Level Manpower | 0 | --
Unit Operations | 0.8 | --
Maintenance | 124.5 | --
Sustaining Support | 91.4 | --
Continuing System Improvements | 62.4 | --
Indirect Support | 0 | --
Other | 0 | --
Total | 279.1 | --
.

## Table 36
Item | Total O&S Cost $M
| IAMD | [5 empty] | No Antecedent System (Antecedent)
| Current Development APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 2235.9 |  | 2459.5 |  |  | 2383.5 | N/A
Then Year | 3333.3 |  | N/A |  |  | 3454.2 | N/A
Equation to Translate Annual Cost to Total Cost
Average annual cost per unit is based on 427 units x 20-years of O&S. (Total Cost = Average Annual Cost per unit ($279.1) x number of units (427) x life per unit (20-years) = $2,383.5M (BY$ 2009)
O&S Cost Variance
Category |  | BY 2009 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
2383.5
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 2383.5
Disposal Estimate Details
Date of Estimate: February 20, 2014
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2009 $M): Total costs for disposal of all Engagement Operations Center
(EOC) are 22.3