## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-341
UH-60M Black Hawk Helicopter (UH-60M Black Hawk)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 13
Cost and Funding 14
Low Rate Initial Production 22
Foreign Military Sales 23
Nuclear Costs 23
Unit Cost 24
Cost Variance 27
Contracts 30
Deliveries and Expenditures 31
Operating and Support Cost 32

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
UH-60M Black Hawk Helicopter (UH-60M Black Hawk)
DoD Component
Army
Responsible Office
COL William D. Jackson
Utility Helicopters Project Office Program Executive Office Aviation Redstone Arsenal, AL 35898-5000
william.d.jackson15.mil@mail.mil
Phone: | 256-955-8938
Fax: | 256-955-8109
DSN Phone: | 645-8938
DSN Fax: | 645-8109
Date Assigned: | June 18, 2015
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated March 31, 2005
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated June 20, 2011

## Table 6
Mission and Description
The UH-60M Black Hawk Helicopter (UH-60M Black Hawk) serves as the Army's utility helicopter for the current and Future Force and is in line with the Army's Modernization Strategy, the National Military Strategy, and the National Defense Strategy. The UH-60M Black Hawk is a digital networked platform with greater range and lift to support maneuver commanders through air assault, general support, command and control, and aeromedical evacuation. FRP for this new-build helicopter began in 2007. The UH-60M Black Hawk, with the integrated Medical Evacuation (MEDEVAC) Mission Equipment Package (MEP) kit, provides day/night and adverse weather emergency evacuation of casualties. The integration of the MEDEVAC MEP onto the UH-60M changes the nomenclature to HH-60M.

## Table 7
Executive Summary
A FY 2016 Congressional plus-up provided funding to procure ten additional UH-60M aircraft for the Army National Guard.
The FY 2017 PB funding position accelerated production by 14 aircraft, bringing total aircraft acceleration quantity to 24 aircraft, and reducing total procurement cost by $242.5M compared to FY 2016 PB.
Defense Contract Management Agency Plant Representative Evaluation as of December 31, 2015 indicates that the eighth Multi-Year (MY)/Multi-Service contract, (MY VIII) covering the years FY 2012 to FY 2016 was awarded on July 6, 2012. The requirement of this FRP contract is for a total of 566 H-60M aircraft (304 UH-60M and 120 HH-60M for the Army,18 UH-60M for the U.S. Air Force, 24 UH-60M for the Saudi Arabia National Guard, three UH-60Ms for Thailand, 56 UH-60Ms for Taiwan, 25 UH-60Ms for Mexico, and three UH-60Ms for the Federal Bureau of Investigations, eight UH-60Ms for Tunisia, one UH- 60M for Jordan and nine UH-60Ms for Slovakia).
In FY 2015, two additional aircraft were procured as a result of the Blackhawk Exchange and Sales Team program which avoids the divestment (demilitarization) cost and applies H-60 proceeds toward H-60M aircraft via the reimbursable transfer credit to the MY contract.
As of December 31, 2015, a total of 318 MY VIII aircraft (217 UH-60M and 83 HH-60M for the U.S. Army; and 18 UH-60M for the U.S. Air Force) were accepted.
Sikorsky Aircraft Corporation is currently six aircraft behind on the contract delivery schedule.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
The O&S Cost Breach was previously reported in the December 2013 SAR.
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B | Mar 2001 | Mar 2001 | Mar 2001 | Mar 2001
SDD Contract Award | May 2001 | May 2001 | May 2001 | May 2001
System PDR | Nov 2002 | Nov 2002 | Nov 2002 | Nov 2002
System CDR | Jun 2003 | Jun 2003 | Jun 2003 | Jun 2003
First Flight | Sep 2003 | Sep 2003 | Sep 2003 | Sep 2003
Milestone C | Feb 2005 | Mar 2005 | Nov 2005 | Mar 2005
LRIP Contract Award | Mar 2005 | Jun 2005 | Dec 2005 | Jun 2005
OT Start | Sep 2006 | Sep 2006 | Sep 2007 | Oct 2006
OT Complete | Nov 2006 | Nov 2006 | Nov 2007 | Nov 2006
Full Rate Production IPR | May 2007 | May 2007 | May 2008 | May 2007
FUE | Jan 2008 | Jan 2008 | Jan 2009 | Feb 2008
Change Explanations

## Table 10
Acronyms and Abbreviations
CDR - Critical Design Review FUE - First Unit Equipped IPR - In-Process Review
OT - Operational Test
PDR - Preliminary Design Review SDD - System Design & Development

## Table 11
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Key Performance Parameters (KPPs)
Interoperability (meet IERs)
All | N/A | N/A | N/A | N/A
Net-Ready
All | All | All Critical | All | All
Survivability IR Signature
N/A | Existing | Existing | Existing | Existing
Aircraft Survivability Equipment
N/A | Existing | Existing | Existing | Existing
Survivability Fuel Cells
N/A | 14.5mm | 7.62mm | 7.62mm | 7.62mm
Force Protection Armor Plating
N/A | 14.5mm | 7.62mm | 7.62mm | 7.62mm
External Lift
Payload
10000 | 10000 | 4500 | 4888 | 4888
Non-KPPs
Troop Movement
Airspeed (Sustained Cruise) (KTAS)
175 | 175 | 145 | 142 | 145
One Engine Inoperative (KTAS)
100 | 100 | 100 | TBD | 100
Combat Radius (w/20 min reserve) (KM)
500 | 500 | 225 | 225 | 225.6
Vertical Rate of Climb (fpm)
750 | 750 | 500 | 725 | 725
Vertical Rate of Climb w/ One Engine Inoperative (fpm)
200 | 200 | 100 | TBD | 100
Internal Lift Capability (290 lbs each)
11 | 11 | 11 | 11 | 11
Self-Deploy Range (nautical miles)

## Table 12
1260 | 1260 | 1056 | TBD | 1071
Ballistic Protection (ground fired armor piercing (mm))
14.5 | 14.5 | 7.62 | 14.5 | 14.5
Maintainability (mhrs per flight hr)
4.6 | 4.6 | 5.4 | 2.3 | 4.1
Unscheduled mhrs per flight hr
1.3 | 1.3 | 2.1 | 0.4 | 1.1
External Lift
Vertical Rate of Climb (fpm)
500 | 500 | 200 | 200 | 200
Combat Radius (w/20 min reserve) (KM)
275 | 275 | 135 | 135 | 135
Requirements Reference
ORD dated January 29, 2007
Change Explanations
None
Acronyms and Abbreviations
fpm - feet per minute hr - hour
IER - Information Exchange Requirement IR - infrared
KM - kilometer
KTAS - Knots True Air Speed lbs - pounds
mhrs - man-hours min - minutes
mm - millimeter w/ - with

## Table 13
Track to Budget
RDT&E
Appn |  |  | BA | PE
Army |  | 2040 07 |  | 0203744A
|  | Project |  | Name
|  | 504 |  | UH-60M Recapitalization/Modifications (Shared) (Sunk)
Notes
Only UH-60M Black Hawk and UH-60M Upgrade Technologies (RDT&E only) funds are included in this SAR.
Procurement
Appn |  |  | BA | PE
Army 2031 01 0210101A
Line Item | Name
A05002 Black Hawk UH-60M (MYP)
Army 2031 02 0210101A
Line Item | Name
AA0492 Black Hawk UH-60M Upgrade/Recap (Shared) (Sunk)
Notes
The Aircraft Procurement, Army (APA) Line Item AA0492 is shared with other UH-60M Black Hawk modifications such as Crashworthy External Fuel System, Medical Equipment Package, and other safety modifications. No funds from the AA0492 line are included in this report.
The APA Line Item AA0005 is the parent to the APA Line Item A05002.

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2005 $M | [6 empty] | BY 2005 $M |  | TY $M
| SAR Baseline Production Estimate |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 717.5 |  |  | 761.3 | 837.4 |  |  | 761.3 |  | 739.3 |  |  | 780.4 |  | 780.4
Procurement |  | 16084.2 |  |  | 21873.7 | 24061.1 |  |  | 20670.1 |  | 20107.8 |  |  | 27314.2 |  | 25880.4
Flyaway |  | -- |  |  | -- | -- |  |  | 19500.9 |  | -- |  |  | -- |  | 24438.1
Recurring |  | -- |  |  | -- | -- |  |  | 19280.6 |  | -- |  |  | -- |  | 24184.4
Non Recurring |  | -- |  |  | -- | -- |  |  | 220.3 |  | -- |  |  | -- |  | 253.7
Support |  | -- |  |  | -- | -- |  |  | 1169.2 |  | -- |  |  | -- |  | 1442.3
Other Support |  | -- |  |  | -- | -- |  |  | 975.5 |  | -- |  |  | -- |  | 1197.9
Initial Spares |  | -- |  |  | -- | -- |  |  | 193.7 |  | -- |  |  | -- |  | 244.4
MILCON |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 16801.7 |  |  | 22635 | N/A |  |  | 21431.4 |  | 20847.1 |  |  | 28094.6 |  | 26660.8
Confidence Level
Confidence Level of cost estimate for current APB: 50%
In March, 2011 the Program Office and the Deputy Assistant Secretary of the Army for Cost and Economics (DASA-CE) agreed on an Army Cost Position which was used to establish the APB, dated June 20, 2011. Costs are reflected at the 50% Confidence Level in accordance with the Army Cost and Economic Analysis Program, Army Regulation 11-18.
It is difficult to calculate mathematically the precise confidence levels associated with life cycle cost estimates prepared for MDAPs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.
Total Quantity
Quantity |  |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  |  | 8 |  |  |  | 8 |  |  |  |  | 8
Procurement |  |  | 1227 |  |  |  | 1367 |  |  |  |  | 1367
Total |  |  | 1235 |  |  |  | 1375 |  |  |  |  | 1375

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 780.4 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 780.4
Procurement | 13361.8 | 1701.8 |  |  | 929.3 | 1129.7 | 1226.4 |  | 1012.3 |  | 1235.2 |  |  | 5283.9 |  | 25880.4
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 14142.2 | 1701.8 |  |  | 929.3 | 1129.7 | 1226.4 |  | 1012.3 |  | 1235.2 |  |  | 5283.9 |  | 26660.8
PB 2016 Total | 14146.9 | 1563 |  |  | 1263.1 | 1182.4 | 943.1 |  | 960.5 |  | 1104.8 |  |  | 5739.5 |  | 26903.3
Delta | -4.7 | 138.8 |  |  | -333.8 | -52.7 | 283.3 |  | 51.8 |  | 130.4 |  |  | -455.6 |  | -242.5
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 8 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 8
Production | 0 |  | 766 |  | 107 | 36 | 60 |  | 69 |  | 38 | 65 |  | 226 |  | 1367
PB 2017 Total | 8 |  | 766 |  | 107 | 36 | 60 |  | 69 |  | 38 | 65 |  | 226 |  | 1375
PB 2016 Total | 8 |  | 766 |  | 94 | 60 | 72 |  | 37 |  | 38 | 47 |  | 253 |  | 1375
Delta | 0 |  | 0 |  | 13 | -24 | -12 |  | 32 |  | 0 | 18 |  | -27 |  | 0

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.5
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.8
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 55.9
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 96.8
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 144.8
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 99.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 106.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 117.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 84.9
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5
Subtotal |  | 8 | -- |  | -- |  | -- |  | -- |  | -- |  | 780.4

## Table 17
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2005 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.2
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.5
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 58.6
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 99.5
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 145.4
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 97.4
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 101.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 109
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 77.3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.4
Subtotal |  | 8 | -- |  | -- |  | -- |  | -- |  | -- |  | 761.3

## Table 18
FY 2010 - FY 2011 RDT&E includes funding for the Fly-By-Wire flight test program which is no longer a part of the acquisition program as directed in the February 18, 2010 ADM; subsequent reports reflect the direction of the ADM.

## Table 19
Annual Funding 2031 ¦ Procurement ¦ Aircraft Procurement, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | 13.5 |  | -- |  | 13.5 |  | -- |  | 13.5
2005 |  | 5 | 82.5 |  | 6.1 |  | 5.6 |  | 94.2 |  | 2.8 |  | 97
2006 |  | 17 | 241.3 |  | 7.5 |  | 4.5 |  | 253.3 |  | 15.2 |  | 268.5
2007 |  | 72 | 1086.3 |  | 85.8 |  | 45.4 |  | 1217.5 |  | 54.4 |  | 1271.9
2008 |  | 77 | 1144.4 |  | 85.3 |  | 63.3 |  | 1293 |  | 61.6 |  | 1354.6
2009 |  | 66 | 962.3 |  | 92 |  | 9 |  | 1063.3 |  | 48.2 |  | 1111.5
2010 |  | 84 | 1182.5 |  | 172 |  | 4.5 |  | 1359 |  | 124.2 |  | 1483.2
2011 |  | 99 | 1512.5 |  | 131.4 |  | 36.2 |  | 1680.1 |  | 108.8 |  | 1788.9
2012 |  | 89 | 1298 |  | 174.5 |  | 35.9 |  | 1508.4 |  | 189.1 |  | 1697.5
2013 |  | 100 | 1263.9 |  | 179.6 |  | 3.7 |  | 1447.2 |  | 130.3 |  | 1577.5
2014 |  | 70 | 980.7 |  | 171.1 |  | 1.2 |  | 1153 |  | 76 |  | 1229
2015 |  | 87 | 1211.3 |  | 181.1 |  | 3.4 |  | 1395.8 |  | 72.9 |  | 1468.7
2016 |  | 107 | 1425.5 |  | 186.3 |  | 4.2 |  | 1616 |  | 85.8 |  | 1701.8
2017 |  | 36 | 675.5 |  | 192.4 |  | 10.6 |  | 878.5 |  | 50.8 |  | 929.3
2018 |  | 60 | 839.5 |  | 202.7 |  | 14 |  | 1056.2 |  | 73.5 |  | 1129.7
2019 |  | 69 | 953 |  | 211.9 |  | 2.4 |  | 1167.3 |  | 59.1 |  | 1226.4
2020 |  | 38 | 749.6 |  | 209.9 |  | 0.7 |  | 960.2 |  | 52.1 |  | 1012.3
2021 |  | 65 | 973.8 |  | 223.6 |  | 4.7 |  | 1202.1 |  | 33.1 |  | 1235.2
2022 |  | 50 | 918.4 |  | 227.4 |  | 0.9 |  | 1146.7 |  | 44 |  | 1190.7
2023 |  | 50 | 752 |  | 228.3 |  | 1 |  | 981.3 |  | 33.7 |  | 1015
2024 |  | 50 | 881.6 |  | 238.3 |  | 1 |  | 1120.9 |  | 37.9 |  | 1158.8
2025 |  | 50 | 827.5 |  | 242.9 |  | 1 |  | 1071.4 |  | 34.9 |  | 1106.3
2026 |  | 26 | 477.3 |  | 237.2 |  | 0.5 |  | 715 |  | 39.3 |  | 754.3
2027 |  | -- | -- |  | 44.2 |  | -- |  | 44.2 |  | 14.6 |  | 58.8
Subtotal |  | 1367 | 20439.4 |  | 3745 |  | 253.7 |  | 24438.1 |  | 1442.3 |  | 25880.4

## Table 20
Annual Funding 2031 ¦ Procurement ¦ Aircraft Procurement, Army
Fiscal Year | Quantity |  | BY 2005 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | 13.4 |  | -- |  | 13.4 |  | -- |  | 13.4
2005 |  | 5 | 79.6 |  | 5.8 |  | 5.4 |  | 90.8 |  | 2.7 |  | 93.5
2006 |  | 17 | 226.6 |  | 7 |  | 4.2 |  | 237.8 |  | 14.3 |  | 252.1
2007 |  | 72 | 999.9 |  | 78.9 |  | 41.8 |  | 1120.6 |  | 50.1 |  | 1170.7
2008 |  | 77 | 1036.9 |  | 77.2 |  | 57.4 |  | 1171.5 |  | 55.8 |  | 1227.3
2009 |  | 66 | 859.5 |  | 82.2 |  | 8 |  | 949.7 |  | 43.1 |  | 992.8
2010 |  | 84 | 1038.2 |  | 150.9 |  | 4 |  | 1193.1 |  | 109.1 |  | 1302.2
2011 |  | 99 | 1304.2 |  | 113.3 |  | 31.2 |  | 1448.7 |  | 93.8 |  | 1542.5
2012 |  | 89 | 1100.6 |  | 148 |  | 30.4 |  | 1279 |  | 160.3 |  | 1439.3
2013 |  | 100 | 1052.9 |  | 149.6 |  | 3.1 |  | 1205.6 |  | 108.5 |  | 1314.1
2014 |  | 70 | 804.6 |  | 140.3 |  | 1 |  | 945.9 |  | 62.4 |  | 1008.3
2015 |  | 87 | 978.9 |  | 146.4 |  | 2.7 |  | 1128 |  | 58.9 |  | 1186.9
2016 |  | 107 | 1137.2 |  | 148.6 |  | 3.4 |  | 1289.2 |  | 68.4 |  | 1357.6
2017 |  | 36 | 528.8 |  | 150.6 |  | 8.3 |  | 687.7 |  | 39.8 |  | 727.5
2018 |  | 60 | 644.4 |  | 155.7 |  | 10.7 |  | 810.8 |  | 56.4 |  | 867.2
2019 |  | 69 | 717.2 |  | 159.5 |  | 1.8 |  | 878.5 |  | 44.5 |  | 923
2020 |  | 38 | 553.1 |  | 154.9 |  | 0.5 |  | 708.5 |  | 38.4 |  | 746.9
2021 |  | 65 | 704.4 |  | 161.8 |  | 3.4 |  | 869.6 |  | 23.9 |  | 893.5
2022 |  | 50 | 651.3 |  | 161.3 |  | 0.6 |  | 813.2 |  | 31.2 |  | 844.4
2023 |  | 50 | 522.8 |  | 158.8 |  | 0.7 |  | 682.3 |  | 23.4 |  | 705.7
2024 |  | 50 | 600.9 |  | 162.5 |  | 0.7 |  | 764.1 |  | 25.8 |  | 789.9
2025 |  | 50 | 553 |  | 162.3 |  | 0.7 |  | 716 |  | 23.3 |  | 739.3
2026 |  | 26 | 312.7 |  | 155.5 |  | 0.3 |  | 468.5 |  | 25.7 |  | 494.2
2027 |  | -- | -- |  | 28.4 |  | -- |  | 28.4 |  | 9.4 |  | 37.8
Subtotal |  | 1367 | 16407.7 |  | 2872.9 |  | 220.3 |  | 19500.9 |  | 1169.2 |  | 20670.1

## Table 21
On May 18, 2010, the Aviation Synchronization Conference Council of Colonels recommended the Army Acquisition Objective increase from 1,227 to 1,365. Two additional aircraft were procured in the upgrade configuration. These two aircraft will not be fielded.

## Table 22
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2005-03-31 | 2005-03-31
Approved Quantity | 40 | 40
Reference | Milestone C ADM | Milestone C ADM
Start Year | 2005 | 2005
End Year | 2007 | 2007
The Milestone C ADM, dated March 31, 2005, contained approval for production of up to 40 LRIP aircraft and approval to award an Advance Procurement contract for the first lot of FRP aircraft.

## Table 23
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Jordan | 2015-06-19 | 1 | 17.2 | Case Number JO-N-YAT
Slovakia | 2015-04-21 | 9 | 170.1 | Case Number LO-B-UCI
Tunisia | 2015-01-12 | 8 | 114.7 | Case Number TU-B-USS
Mexico | 2014-08-08 | 7 | 163.6 | Case Number MX-B-UEU
Mexico | 2014-07-22 | 18 | 462.2 | Case Number MX-B-UES
Thailand | 2012-09-25 | 1 | 31 | Case Number TH-B-UAD
Thailand | 2011-12-26 | 2 | 62.3 | Case Number TH-B-UAE
Saudi Arabia | 2011-11-30 | 24 | 638.3 | Case Number SI-B-WXP
Sweden | 2011-01-14 | 15 | 275.7 | Case Number SW-B-WAD
Taiwan | 2010-11-22 | 60 | 1717.7 | Case Number TW-B-YZC
Jordan | 2010-09-01 | 2 | 26.3 | Case Number JO-B-WAT
Mexico | 2010-08-03 | 3 | 83.9 | Case Number MX-B-UEJ
United Arab Emirates | 2007-12-12 | 40 | 825 | Case Number AE-B-ZUE
Bahrain | 2007-09-18 | 9 | 151.9 | Case Number BA-B-UIR
Notes
To date all FMS have been for the UH-60M Black Hawk configuration of the aircraft. The Total Cost reflects all costs associated with the procurement of the aircraft and other services provided to the specific country to include training, spares, et cetera.
Nuclear Costs
None

## Table 24
Unit Cost
Unit Cost Report
Item |  | BY 2005 $M | BY 2005 $M |  | % Change
|  | Current UCR Baseline (Jun 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 22635 |  |  | 21431.4
Quantity | 1375 |  |  | 1375
Unit Cost | 16.462 |  |  | 15.586 |  |  | -5.32
Average Procurement Unit Cost
Cost | 21873.7 |  |  | 20670.1
Quantity | 1367 |  |  | 1367
Unit Cost | 16.001 |  |  | 15.121 |  |  | -5.5
Item |  | BY 2005 $M | BY 2005 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Mar 2005 APB)
Program Acquisition Unit Cost
Cost | 16801.7 |  |  | 21431.4
Quantity | 1235 |  |  | 1375
Unit Cost | 13.605 |  |  | 15.586 |  | 14.56
Average Procurement Unit Cost
Cost | 16084.2 |  |  | 20670.1
Quantity | 1227 |  |  | 1367
Unit Cost | 13.109 |  |  | 15.121 |  | 15.35

## Table 25
Unit Cost History
Item | [7 empty] | Date |  |  | BY 2005 $M | [6 empty] | TY $M
[11 empty] | PAUC |  |  | APUC |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Feb 2002 | [5 empty] | 9.25 |  |  |  |  | 9.042 |  |  | 12.008 |  |  |  | 11.812
APB as of January 2006 |  |  |  |  | Mar 2005 | [5 empty] | 13.605 |  |  |  |  | 13.109 |  |  | 16.88 |  |  |  | 16.388
Revised Original APB |  |  |  |  | Mar 2005 | [5 empty] | 13.605 |  |  |  |  | 13.109 |  |  | 16.88 |  |  |  | 16.388
Prior APB |  |  |  |  | Feb 2007 | [5 empty] | 14.872 |  |  |  |  | 14.338 |  |  | 18.84 |  |  |  | 18.319
Current APB |  |  |  |  | Jun 2011 | [5 empty] | 16.462 |  |  |  |  | 16.001 |  |  | 20.432 |  |  |  | 19.981
Prior Annual SAR |  |  |  |  | Dec 2014 | [5 empty] | 15.63 |  |  |  |  | 15.165 |  |  | 19.566 |  |  |  | 19.11
Current Estimate |  |  |  |  | Dec 2015 | [5 empty] | 15.586 |  |  |  |  | 15.121 |  |  | 19.39 |  |  |  | 18.932
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [19 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng | Est |  |  | Oth |  |  | Spt |  | Total
12.008 -0.325 4.705 -0.262 0.996 -0.326 0.000 0.084 4.872 16.880
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [17 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  | Eng | Est |  | Oth |  |  | Spt |  | Total
16.880 -0.265 0.677 0.938 0.476 0.147 0.000 0.537 2.510 19.390

## Table 26
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [10 empty] | APUC Production Estimate
| Econ | Qty |  | Sch | Eng |  | Est |  | Oth | Spt | Total
11.812 -0.324 4.469 -0.287 0.987 -0.354 0.000 0.085 4.576 16.388
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [10 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth |  | Spt | Total
16.388 -0.270 0.728 0.924 0.481 0.140 0.000 0.541 2.544 18.932
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  | Apr 2001 |  |  |  | Mar 2001 |  |  | Mar 2001
Milestone C |  |  | N/A |  |  | Mar 2004 |  |  |  | Feb 2005 |  |  | Mar 2005
FUE |  |  | N/A |  |  | Sep 2006 |  |  |  | Jan 2008 |  |  | Feb 2008
Total Cost (TY $M) |  |  | N/A |  |  | 14662 |  |  |  | 20847.1 |  |  | 26660.8
Total Quantity |  |  | N/A |  |  | 1221 |  |  |  | 1235 |  |  | 1375
PAUC |  |  | N/A |  |  | 12.008 |  |  |  | 16.88 |  |  | 19.39

## Table 27
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
739.3 20107.8 -- 20847.1
Economic |  | 3.9 |  | -247.1 |  | -- |  | -243.2
Quantity |  | -- |  | 3291.3 |  | -- |  | 3291.3
Schedule |  | 27.5 |  | 1388.7 |  | -- |  | 1416.2
Engineering |  | -2.1 |  | 657.2 |  | -- |  | 655.1
Estimating |  | 11.8 |  | 159.2 |  | -- |  | 171
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 765.8 |  | -- |  | 765.8
Subtotal |  | 41.1 |  | 6015.1 |  | -- |  | 6056.2
Current Changes Economic |  | -- |  | -121.4 |  | -- |  | -121.4
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -125.9 |  | -- |  | -125.9
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | 31.6 |  | -- |  | 31.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -26.8 |  | -- |  | -26.8
Subtotal |  | -- |  | -242.5 |  | -- |  | -242.5
Total Changes |  | 41.1 |  | 5772.6 |  | -- |  | 5813.7
CE - Cost Variance |  | 780.4 |  | 25880.4 |  | -- |  | 26660.8
CE - Cost & Funding |  | 780.4 |  | 25880.4 |  | -- |  | 26660.8

## Table 28
Summary BY 2005 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
717.5 16084.2 -- 16801.7
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 2330 |  | -- |  | 2330
Schedule |  | 24.1 |  | 945.4 |  | -- |  | 969.5
Engineering |  | 9.5 |  | 529.3 |  | -- |  | 538.8
Estimating |  | 10.2 |  | 236.3 |  | -- |  | 246.5
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 604.9 |  | -- |  | 604.9
Subtotal |  | 43.8 |  | 4645.9 |  | -- |  | 4689.7
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -66.4 |  | -- |  | -66.4
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | 25.9 |  | -- |  | 25.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -19.5 |  | -- |  | -19.5
Subtotal |  | -- |  | -60 |  | -- |  | -60
Total Changes |  | 43.8 |  | 4585.9 |  | -- |  | 4629.7
CE - Cost Variance |  | 761.3 |  | 20670.1 |  | -- |  | 21431.4
CE - Cost & Funding |  | 761.3 |  | 20670.1 |  | -- |  | 21431.4
Previous Estimate: December 2014

## Table 29
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -121.4
Adjustment for current and prior escalation. (Estimating) | 25.9 | 31.6
Acceleration of procurement buy profile from FY 2016 through FY 2021. (Schedule) | 0 | -40.7
Additional schedule variance related to the buy profile unit cost computations. (Schedule) | -66.4 | -85.2
Adjustment for current and prior escalation. (Support) | 1.6 | 2.1
Decrease in Other Support due to acceleration of procurement buy profile which reduced | -15.2 | -20.2
out-year fieldings. (Support)
Decrease in Initial Spares due to acceleration of procurement buy profile which reduced spares requirement. (Support)
-5.9 -8.7
Procurement Subtotal -60.0 -242.5

## Table 30
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: Multi-Year/Multi-Service 8
Contractor: Sikorsky Aircraft Corporation
Contractor Location: 6900 Main St
Stratford, CT 06614
Contract Number: W58RGZ-12-C-0008
Contract Type: Firm Fixed Price (FFP)
Award Date: July 06, 2012
Definitization Date: July 06, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
4347.5 N/A 354 5091.9 N/A 424 5091.9 5091.9
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to purchase of additional aircraft.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This information includes only the Army portion of the current Multi-Year 8 contract.
Initial Target Price and Quantity were updated to correct an administrative error.

## Table 31
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 8 | 8 | 8 | 100%
Production | 724 | 718 | 1367 | 52.52%
Total Program Quantity Delivered | 732 | 726 | 1375 | 52.8%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
26660.8
14809.1
55.55%
28
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
17
60.71%
15844
59.43%
The above data is current as of February 29, 2016.

## Table 32
Operating and Support Cost
Cost Estimate Details
Date of Estimate: March 07, 2016
Source of Estimate: POE
Quantity to Sustain: 1365
Unit of Measure: Aircraft
Service Life per Unit: 25.00 Years
Fiscal Years in Service: FY 2006 - FY 2051
A total of 1,375 UH/HH aircraft will be procured with 1,365 fielded and sustained. The original eight RDT&E-funded prototype aircraft and two procurement aircraft in upgrade configuation will not be fielded or sustained. The two aircraft in the upgrade configuration are test aircraft.
Sustainment Strategy
The maintenance concept for the UH-60M Black Hawk is organic, two-level maintenance with the exception of the training base. The training base will continue as Contractor Logistics Support.
Antecedent Information
The antecedent system is UH-60L Black Hawk. The total O&S Costs for UH-60L Black Hawk were not reported in the last UH-60L Black Hawk SAR dated December 31, 1999. The information in the O&S Cost Table is based on O&S Management Information Systems (OSMIS) data for the UH-60L Black Hawk (excluding Contingency
Operations). Sustaining support costs for the UH-60L Black Hawk aircraft are not included in the table because the costs (software maintenance, system specific base operations, systems engineering/program management and transportation) are not collected in the OSMIS database. There are 780 UH-60L Black Hawks in the current fleet with
an Economic Useful Life expectancy of 25-years.
Annual O&S Costs BY2005 $K
Cost Element | UH-60M Black Hawk Average Annual Cost Per Aircraft | UH-60L Black Hawk (Antecedent) Avg Annual Cost Per Aircraft
Unit-Level Manpower | 426.285 | 426.285
Unit Operations | 54.142 | 54.142
Maintenance | 373.395 | 284.669
Sustaining Support | 1.225 | 0
Continuing System Improvements | 6.157 | 0
Indirect Support | 215.849 | 215.849
Other | 0 | 0
Total | 1077.053 | 980.945

## Table 33
Item | Total O&S Cost $M
| UH-60M Black Hawk | [6 empty] | UH-60L Black Hawk (Antecedent)
| Current Production APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year |  | 17652.5 |  | 19417.8 |  |  | 36754.41 |  | N/A
Then Year 1 APB O&S Cost Breach |  | 26086.5 |  | N/A |  |  | 57989.3 |  | N/A
The current O&S cost in the UH-60M Black Hawk APB dated June 2011 represents O&M costs not O&S costs. The key difference between the two is that O&M costs do not include Military Personnel costs. Also the Current Estimate includes the extension of Expected Useful Life from 20 years to 25 years.
Equation to Translate Annual Cost to Total Cost
Equation: Average Annual Cost Per Aircraft * Quantity Fielded * System Life
$1.077053M * 1365 aircraft * 25 years = $36,754.4 (BY 2005 $M)
O&S Cost Variance
Category |  |  | BY 2005 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
36745.5
Programmatic/Planning Factors 8.9 Adjustments due to changes in the flying hour profile.
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 8.9
Current Estimate 36754.4
Disposal Estimate Details
Date of Estimate: March 07, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2005 $M): Total costs for disposal of all Aircraft are 75.5