## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-349
Warfighter Information Network-Tactical Increment 2 (WIN-T Inc 2)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 9
Schedule 10
Performance 12
Track to Budget 16
Cost and Funding 17
Low Rate Initial Production 24
Foreign Military Sales 25
Nuclear Costs 25
Unit Cost 26
Cost Variance 31
Contracts 34
Deliveries and Expenditures 35
Operating and Support Cost 36

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Warfighter Information Network-Tactical Increment 2 (WIN-T Inc 2)
DoD Component
Army
Responsible Office
COL Gregory Coile PM WIN-T
6010 Frankford Street
Aberdeen Proving Ground, MD 21005-1848
gregory.h.coile.mil@mail.mil
Phone: | 443-395-7223
Fax: | 443-395-7208
DSN Phone: | 648-7223
DSN Fax: | 648-7208
Date Assigned: | July 20, 2015
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acqusition Program Baseline (APB) dated March 8, 2010
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated June 21, 2015

## Table 6
Mission and Description
Warfighter Information Network-Tactical Increment 2 (WIN-T Inc 2) provides the Army with On-The-Move (OTM) networking capability. The WIN-T Inc 2 network retains capabilities delivered by WIN-T Inc 1 and by leveraging proven Government and commercial technologies, adds greater network throughput and automated network management to optimize planning (to include spectrum use), initialization, monitoring and troubleshooting. WIN-T Inc 2 employs satellite communication OTM to extend the network in maneuver Brigade Combat Teams to Company-level. Using equipment mounted on combat platforms, WIN-T Inc 2 delivers a mobile capability that reduces reliance on fixed infrastructure and allows key leaders to move on the battlefield while retaining situational awareness and mission command capabilities. Using the Highband Networking Radio, with the Highband Networking Waveform and high performance antennas, the WIN-T Inc 2 line-of-sight network offers an adaptive 30 Megabit per second aggregate throughput to key leaders in their Command Post or in their vehicle. The WIN-T Inc 2 network is self-forming, which means that it automatically creates transmission paths based on terrain and environmental conditions; and self-healing, meaning that the paths will automatically re-route traffic to complete network transactions and calls even if one or more nodes break down or lose connectivity. This offers greater network reliability and better end-to-end connectivity than traditional point-to-point networks. WIN-T Inc 2 introduces the network management capability needed to keep the mobile and dispersed forces networked through automated planning, initialization, monitoring, and troubleshooting. Finally, WIN-T Inc 2 adopts “Colorless Core” technology that encrypts both classified and unclassified user information in the network and minimizes the number of users on the “core” of the network. The Colorless Core allows commanders to utilize the tactical network without fear of the enemy intercepting information. Colorless Core is a technical insertion in the WIN-T Inc 1b network which enables information sharing between WIN-T Inc 1b and WIN-T Inc 2.
WIN-T Inc 3 developed NetOps software and NetCentric Waveform updates will be inserted into WIN-T Inc 2 equipped units.

## Table 7
Executive Summary
The following WIN-T Inc 2 New Equipment Training and New Equipment Fielding activities were completed during 2015: 2/82 Infantry Brigade Combat Team (IBCT) (Airborne) at Fort Bragg; 1st Armored Division (AD) Headquarters and 1/1 Armor Division Stryker BCT (SBCT) at Fort Bliss; 3/2 and 2/2 SBCTs at Joint Base Lewis-McChord; 4/10 IBCT (Mountain) at Fort Polk (reflagged as 3/10); 2/101 and 3/101 IBCT (Air Assault) Engineer Company and Maneuver Support Battalion additions at Fort Campbell; 2/82 IBCT (Airborne) Engineer Company and Maneuver Support Battalion additions at Fort
Bragg; 1st Cavalry Division Headquarters at Fort Hood; and the 25th Infantry Division Headquarters at Schofield Barracks.
101st Air Assault Division Headquarters Tactical Communications Nodes were deployed and integrated into the Africa Command overall mission support network as part of Operation United Assistance. The 82d Airborne Division Headquarters, 2/82 IBCT and 1/10 Mountain IBCT deployed in support of Operation Inherent Resolve.
During 2015, WIN-T Inc 2 successfully completed support to 2/1 Armor BCT and Network Integration Evaluation 15.2 and
16.1. WIN-T Increment 2 participated as a baseline system in both events.
On February 4, 2015, the Office of the Deputy Assistant Secretary of Defense for Systems Engineering (ODASD(SE)) and the Defense Contract Management Agency conducted a Program Support Assessment at the General Dynamics facility in Taunton, Massachusetts. The review supported the ODASD(SE) assessment for the FRP Decision Review. The program was assessed in five categories: Mission Capabilities, Resources, Management, Technical Process and Performance. The evaluation showed mature, stable and disciplined processes that are in accordance with DoD policy/guidelines. The team determined that the program was at low risk in proceeding to FRP.
On May 29, 2015, the program office successfully completed Record Testing for the Joint Interoperability Certification 2015 with 100% of the test threads completed with no issues. Certification was granted on January 15, 2016.
On June 3, 2015, the DAE authorized entry into FRP for WIN-T Inc 2. The ADM required that the Army: a) Fund the program in accordance with the validated SCP; b) Submit a corrective action plan to the DAE by June 30, 2015 to address Stryker integration issues and improvements to Network Operations tools and training to optimize performance of the Highband Networking Waveform, Tactical Relay-Tower, and Range Throughput Extension Kit; and c) Provide to the DAE an independent cyber design and implementation assessment using a system analysis no later than September 30, 2015 which identifies program cyber vulnerabilities and provides corrective action recommendations for future implementation.
The program office completed all three ADM actions, received DAE concurrence, and is working to execute corrective actions as outlined and in accordance with the submitted plans.
On June 12, 2015, the Army Communications-Electronics Command (CECOM) granted WIN-T Inc 2 Full Materiel Release (FMR). FMR was based on satisfying conditions set forth by CECOM in a Conditional Materiel Release dated November 8, 2012.
On June 21, 2015, the DAE approved the WIN-T Inc 2 FRP APB. This APB provides updated program cost thresholds and establishes acquisition and sustainment affordability caps.
In 2014 the program experienced a unit cost increase greater than or equal to the significant cost growth threshold, resulting in a significant Nunn-McCurdy cost breach to the PAUC and APUC against its original APB. Congressional notification of this Nunn-McCurdy breach was completed on February 25, 2015. The program office is aggressively managing cost growth.
The program office is using Alpha contracting processes to negotiate a follow-on production contract. The program office held a technical integrated product team discussions and reviews during September through December 2015. Meetings are continuing in FY 2016. On January 8, 2016, a justification and authorization was signed to allow extension of the current production contract period of performance into FY 2017 to ensure required equipment can be procured and that services can be provided in support of fielded units.

## Table 8
The FY 2016 PB request decremented $88M in FY 2016 Procurement funding and rescinded $40M in FY 2014 Procurement funding. The impact is procuring one less IBCT, one less Division and one less IBCT Engineer Company and Maneuver Support Battalion. In the FY 2017 PB, the program received decrements totaling $443.7M across FY 2017 to FY 2021, including a reduction in FY 2017 Procurement funding of $228M. This caused a major reduction in units procured from FY 2017 to FY 2021 and slipped procurement beyond the FYDP and into the Extended Planning Period to include an additional year of procurement. It reduces FY 2017 procurement to the minimum sustaining rate. Any further funding decrements in FY 2017 will cause a break in production and the loss of economic order quantities.
There are no significant software-related issues with this program at this time.

## Table 9
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
The RDT&E cost breach in FY 2015 is due to an increase in FY 2017 to FY 2021 funding to provide additional capability to develop small, phased array satellite communication on-the-move product for armored platforms. A Program Deviation Report will be submitted.
The Nunn-McCurdy cost breach against the original APB was previously previously in the December 2014 SAR.
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC Significant APUC Significant

## Table 10
Schedule
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B | Jun 2007 | Jun 2007 | Jun 2007 | Jun 2007
Limited User Test (LUT)
Start | Mar 2009 | Mar 2009 | Mar 2009 | Mar 2009
Complete | Mar 2009 | Mar 2009 | Mar 2009 | Mar 2009
Milestone C | Feb 2010 | Mar 2010 | Mar 2010 | Mar 2010
Initial Operational Test (IOT)
Start | Nov 2011 | May 2012 | May 2012 | May 2012
Complete | Nov 2011 | May 2012 | May 2012 | May 2012
Defense Acquisition Board Review | N/A | Sep 2012 | Sep 2012 | Sep 2012
IOC | Nov 2012 | Aug 2013 | Aug 2013 | Aug 2013
Follow-On Operational Test and Evaluation (FOT&E) #1 | N/A | May 2013 | May 2013 | May 2013
Defense Acquisition Board Review #2 | N/A | Sep 2013 | Sep 2013 | Sep 2013
FOT&E #2 | N/A | Oct 2014 | Oct 2014 | Oct 2014
Full Rate Production (FRP) Decision Review | Feb 2012 | Jun 2015 | Jun 2015 | May 2015

## Table 11
Change Explanations
None
Notes
The FRP Decision Review was held on May 11, 2015. The program was granted approval for FRP; the ADM in support of this decision was signed by the DAE on June 3, 2015.

## Table 12
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Net Ready
The system must | The system must fully | The system must fully | Achieved | The system must fully
fully support | support execution of all | support execution of | threshold at IOT. | support execution of all
execution of all | operational activities | joint critical operational |  | operational activities
operational activities | identified in the | activities identified in the |  | identified in the
identified in the | applicable joint and | applicable joint and |  | applicable joint and
applicable joint and | system integrated | system integrated |  | system integrated
system integrated | architectures and the | architectures and the |  | architectures and the
architectures and | system must satisfy the | system must satisfy the |  | system must satisfy the
the system must | technical requirements | technical requirements |  | technical requirements
satisfy the technical | for Net-Centric military | for transition to Net- |  | for Net-Centric military
requirements for Net | operations to include 1) | Centric military |  | operations to include 1)
-Centric military | DISR mandated GIG IT | operations to include 1) |  | DISR mandated GIG IT
operations to | standards and profiles | DISR mandated GIG IT |  | standards and profiles
include 1) DISR | identified in the TV-1, 2) | standards and profiles |  | identified in the TV-1, 2)
mandated GIG IT | DISR mandated GIG | identified in the TV-1, 2) |  | DISR mandated GIG
standards and | KIPs identified in the | DISR mandated GIG |  | KIPs identified in the KIP
profiles identified in | KIP declaration table, 3) | KIPs identified in the KIP |  | declaration table, 3)
the TV-1, 2) DISR | NCOW RM Enterprise | declaration table, 3) |  | NCOW RM Enterprise
mandated GIG KIPs | Services 4) IA | NCOW RM Enterprise |  | Services 4) IA
identified in the KIP | requirements including | Services 4) IA |  | requirements including
declaration table, 3) | availability, integrity, | requirements including |  | availability, integrity,
NCOW RM | authentication, | availability, integrity, |  | authentication,
Enterprise Services | confidentiality, and non- | authentication, |  | confidentiality, and
4) IA requirements | repudiation, and | confidentiality, and non- |  | nonrepudiation,
including availability, | issuance of an ATO by | repudiation, and |  | issuance of an ATO by
integrity, authenticat | the DAA, and 5) | issuance of an IATO by |  | the DAA, and 5)
-ion, confidential-ity, | Operationally effective | the DAA, and 5) |  | Operationally effective
and non-repudiation, | information exchanges; | Operationally effective |  | information exchanges;
issuance of an ATO | and mission critical | information exchanges; |  | and mission critical
by the DAA, and 5) | performance and IA | and mission critical |  | performance and
Operationally | attributes, data | performance and IA |  | information assurance
effective information | correctness, data | attributes, data |  | attributes, data
exchanges; and | availability, and | correctness, data |  | correctness, data
mission critical | consistent data | availability, and |  | availability, and
performance and | processing specified in | consistent data |  | consistent data
information | the applicable joint and | processing specified in |  | processing specified in
assurance | system integrated | the applicable joint and |  | the applicable joint and
attributes, data | architecture views. | system integrated |  | system integrated
correctness, data |  | architecture views. |  | architecture views.
availability, and
consistent data
processing
specified in the
applicable joint and

## Table 13
system integrated architecture views.
Network Management
Increment 2 will enable the BCT S6 NetOps managers to plan, monitor, prioritize, control and visually display (e.g., current network status and connectivity) its WIN -T equipped units (Bde, Bn, Co) that connect: Objective: Top Secret, Secret, and Unclassified users. | Increment 2 will enable the BCT S6 NetOps managers to plan, monitor, prioritize, control and visually display (e.g., current network status and connectivity) its WIN-T equipped units (Bde, Bn, Co) that connect: Objective: Top Secret, Secret, and Unclassified users. | Increment 2 will enable the BCT S6 NetOps managers to plan, monitor, prioritize, control and visually display (e.g., current network status and connectivity) its WIN-T equipped units (Bde, Bn, Co) that connect: Threshold: Secret and Unclassified users. | Achieved threshold at IOT. | Inc 2 will enable the BCT S6 NetOps managers to plan, monitor, prioritize, control and visually display (e.g., current network status and connectivity) its WIN-T equipped units (Bde, Bn, Co) that connect: Objective: Top Secret, Secret, and Unclassified users.
Information Dissemination
Increment 2 will provide a transport capability that enables battle command and situational awareness data message information to be exchanged within a BCT's WIN-T Increment 2 enabled ATH platforms and to its WIN-T enabled ATH Divisional HQ: Objective: Critical survival information (Category 1) delivery in <0.5 seconds (95% of completed messages) and time sensitive information (Category 2) in <1 seconds (92% of completed messages). | Increment 2 will provide a transport capability that enables battle command and situational awareness data message information to be exchanged within a BCT's WIN-T Increment 2 enabled ATH platforms and to its WIN -T enabled ATH Divisional HQ: Objective: Critical survival information (Category 1) delivery in <0.5 seconds (95% of completed messages) and time sensitive information (Category 2) in <1 seconds (92% of completed messages). | Increment 2 will provide a transport capability that enables battle command and situational awareness data message information to be exchanged within a BCT's WIN-T Increment 2 enabled ATH platforms and to its WIN -T enabled ATH Divisional HQ: Threshold: Critical survival information (Category 1) delivery in < or = to 5 seconds (95% of completed messages) and time sensitive information (Category 2) in <8 seconds (92% of completed messages). | Achieved threshold at IOT. | Inc 2 will provide a transport capability that enables battle command and situational awareness data message information to be exchanged within a BCT's WIN-T Inc 2 enabled ATH platforms and to its WIN-T enabled ATH Divisional HQ: Objective: Critical survival information (Category 1) delivery in <0.5 seconds (95% of completed messages) and time sensitive information (Category 2) in <1 seconds (92% of completed messages).
Force Protection Armor required for protection of passengers inside the vehicle cab from small arms fire, mines, and other anti-vehicle/personnel threats
Increment 2 unique vehicles require | N/A | N/A | Achieved threshold at IOT. | Increment 2 unique vehicles require armor

## Table 14
armor kits for protection of passengers inside the vehicle cab from small arms fire, mines, and other anti-vehicle/ personnel |  |  |  | kits for protection of passengers inside the vehicle cab from small arms fire, mines, and other anti- vehicle/personnel threats (IAW JROCM 120-05).
Mobile Throughput For Brigade/Battalion maneuver commanders and their CPs
Increment 2 will | Increment 2 will enable | Increment 2 will enable | Achieved | Inc 2 will enable
enable selected | selected warfighters | selected warfighters | threshold at PQT | selected warfighters
warfighters (Bde/Bn | (Bde/Bn maneuver | (Bde/Bn maneuver | -G (DT) in 2011. | (Bde/Bn maneuver
maneuver | commanders and their | commanders and their | User feedback | commanders and their
commanders and | CPs) to conduct | CPs) to conduct | from IOT | CPs) to conduct
their CPs) to | decisive operations | decisive operations | indicated | decisive operations
conduct decisive | while moving "cross- | while moving "cross- | potential mobility | while moving "cross-
operations while | country" utilizing | country" utilizing satellite | and connectivity | country" utilizing satellite
moving "cross- | satellite | communications: | issues. Mobility | communications:
country" utilizing | communications: | Threshold: Ground | and connectivity | Objective: Ground
satellite | Objective: Ground | vehicles: from 0 to 25 | issues | vehicles: from 0 to 45
communicat-ions: | vehicles: from 0 to 45 | mph with 256 Kbps per | demonstrated | mph with 4 Mbps per
Objective: Ground | mph with 4 Mbps per | link available for user | significant | link available for user
vehicles: from 0 to | link available for user | data. | improvement at | data.
45 mph with 4 Mbps | data. |  | the FOT in May
per link available for |  |  | 2013
user data.
Requirements Reference
CPD Revision 1 dated February 14, 2012 as modified by Revision 3 approved October 17, 2014
Change Explanations
None
Notes
JROCM 069-15 of June 24, 2015 revalidated the program and established thresholds for cost growth and reductions in end item quantities.
Demonstrated performance is as demonstrated at the PQT-G of 2011 and the IOT of May 2012 and documented in the Operational Test Agency Evaluation Report for the WIN-T Inc 2 dated July 2012.

## Table 15
Acronyms and Abbreviations
ATH - At-The-Halt
ATO - Authority to Operate BCT - Brigade Combat Team Bde - Brigade
Bn - Battalion Co - Company
CP - Command Post
DAA - Designated Approving Authority
DISR - Department of Defense Information Technology Standards and Profile Registry DT - Development Test
FOT - Follow-On Test
GIG - Global Information Grid HQ - Headquarters
IA - Information Assurance
IATO - Interim Authority to Operate IAW - In Accordance With
IOT - Initial Operational Test IT - Information Technology
JROCM - Joint Requirements Oversight Council Memorandum Kbps - Kilobits Per Second
KIPs - Key Interface Profiles Mbps - Megabits Per Second mph - miles per hour
NCOW - Network Centric Operations and Warfare NetOps - Network Operations
PQT-G - Production Qualification Testing - Government RM - Reference Model
S6 - Battalion or Brigade Communications Cell TV - Technical View

## Table 16
Track to Budget
RDT&E
Appn |  |  | BA | PE
Army 2040 07 0370349A
Project | Name
EE7 WIN-T Inc 2 Initial Networking
Notes: This was not a new start in FY 2015. This effort was funded under 0603782A Project 367 through FY 2014. It is currently funded under PE 0310349A, Project EE7.
Army 2040 04 0603782A
Project | Name
355 WIN-T DEM/VAL/Warfighter Information Network Tactical - DEM/VAL
367 WIN-T DEM/VAL/Warfighter Information Network Tactical - DEM/VAL
(Sunk)
(Sunk)
Notes: Project 367 began in FY 2009 for WIN-T Inc 2 exclusively. Prior to FY 2009 Project 355 was a shared line for both WIN-T Inc 2 and WIN-T Inc 3.
Notes
PE number changed from 0310349A to 0370349A to reflect accurate account code. BA number changed from 03 to 07 to reflect accurate account code.
Procurement
Appn |  |  | BA | PE
Army |  | 2035 04 |  | 0310706A
|  | Line Item |  | Name
|  | BS9741 |  | WIN-T INCREMENT 2 Spares
Army |  | 2035 02 |  | 0310706A
|  | Line Item |  | Name
|  | BW7115 |  | Increment 2 Initial Networking On The Move
Notes
The parent Line Item for the WIN-T Inc 2 Spares (BS9741) is Initial Spares - C&E (BS9100). The parent Line Item for the WIN-T Inc 2 procurement (BW7115) is Win-T - Ground Forces Tactical Network (BW7100).

## Table 17
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2010 $M | [5 empty] | BY 2010 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E | 264.7 |  |  | 260.8 | 286.9 |  |  | 289.21 |  | 266.5 |  |  | 262.3 |  | 296.5
Procurement | 4421.3 |  |  | 9128.5 | 9800 |  |  | 9296.1 |  | 4730.4 |  |  | 11089.6 |  | 11364.8
Flyaway | -- |  |  | -- | -- |  |  | 5992.9 |  | -- |  |  | -- |  | 7205.5
Recurring | -- |  |  | -- | -- |  |  | 5593.8 |  | -- |  |  | -- |  | 6753.8
Non Recurring | -- |  |  | -- | -- |  |  | 399.1 |  | -- |  |  | -- |  | 451.7
Support | -- |  |  | -- | -- |  |  | 3303.2 |  | -- |  |  | -- |  | 4159.3
Other Support | -- |  |  | -- | -- |  |  | 2853 |  | -- |  |  | -- |  | 3604.9
Initial Spares | -- |  |  | -- | -- |  |  | 450.2 |  | -- |  |  | -- |  | 554.4
MILCON | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 4686 |  |  | 9389.3 | N/A |  |  | 9585.3 |  | 4996.9 |  |  | 11351.9 |  | 11661.3
1 APB Breach
Current APB Cost Estimate Reference
Army Cost Position (ACP) dated April 28, 2015
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The ACP is considered low risk due to the Increment 2 phase of its life cycle. The variability of funding and corresponding changes in procurement quantities are the only identifiable risks.
Total Quantity
Quantity |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  | 56 |  |  |  | 56 |  |  |  |  | 56
Procurement |  | 2160 |  |  |  | 3674 |  |  |  |  | 3674
Total |  | 2216 |  |  |  | 3730 |  |  |  |  | 3730
Quantity Notes
The unit of measure is a combination of communications nodes which vary in capability. The WIN-T Inc 2 unit of measure is comprised of Tactical Communications Nodes, Points of Presence, and Soldier Network Extensions.

## Table 18
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 258.4 | 3.8 |  | 4.9 |  | 6 |  | 4.8 |  | 5.1 |  | 13.5 |  | 0 |  | 296.5
Procurement | 2767.9 | 456.1 |  | 311.8 |  | 625.4 |  | 612.9 |  | 712.8 |  | 679.3 |  | 5198.6 |  | 11364.8
MILCON | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 3026.3 | 459.9 |  | 316.7 |  | 631.4 |  | 617.7 |  | 717.9 |  | 692.8 |  | 5198.6 |  | 11661.3
PB 2016 Total | 3066.3 | 547.8 |  | 545.6 |  | 666.9 |  | 678.4 |  | 755.3 |  | 714.7 |  | 4481.2 |  | 11456.2
Delta | -40 | -87.9 |  | -228.9 |  | -35.5 |  | -60.7 |  | -37.4 |  | -21.9 |  | 717.4 |  | 205.1
Funding Notes
The FY 2016 PB request decremented $88M in FY 2016 Procurement funding and rescinded $40M FY 2014 Procurement funding. The impact is procuring one less Infantry Brigade Combat Team (IBCT), one less Division and one less IBCT Engineer Company and Maneuver Suport Battalion. In the FY 2017 PB the program received decrements totaling $443.7M across FY 2017 to FY 2021, including a reduction in FY 2017 Procurement funding of $228M. This caused a major reduction in units procured from FY 2017 through FY 2021 and slipped procurement beyond the FYDP and into the Extended Planning Period to include an additional year of procurement. It reduces FY 2017 procurement to the minimum sustaining rate. Any further funding decrements in FY 2017 will cause a break in production and the loss of economic order quantities.
Node counts in FY 2017 through FY 2019 reflect the lateral transfer of Soldier Network Extensions (SNE) from previously fielded units, hence fewer nodes are required. Funding in FY 2019 and FY 2020 increases slightly while quantities increase significantly. This is due to the reintroduction of the lower cost SNE configuration item in FY 2020.
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 56 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 56
Production | 0 |  | 1367 |  | 170 | 12 | 139 |  | 114 |  | 250 |  | 241 |  | 1381 |  | 3674
PB 2017 Total | 56 |  | 1367 |  | 170 | 12 | 139 |  | 114 |  | 250 |  | 241 |  | 1381 |  | 3730
PB 2016 Total | 56 |  | 1303 |  | 248 | 201 | 129 |  | 135 |  | 266 |  | 254 |  | 1047 |  | 3639
Delta | 0 |  | 64 |  | -78 | -189 | 10 |  | -21 |  | -16 |  | -13 |  | 334 |  | 91

## Table 19
Cost and Funding
Annual Funding By Appropriation
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 107.6
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 91.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.8
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.7
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.1
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.1
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.8
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.9
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.8
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.1
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.5
Subtotal |  | 56 | -- |  | -- |  | -- |  | -- |  | -- |  | 296.5

## Table 20
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 108.6
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 91
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.5
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.4
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.3
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.2
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.9
Subtotal |  | 56 | -- |  | -- |  | -- |  | -- |  | -- |  | 289.2

## Table 21
The RDT&E cost breach in FY 2015 is due to an increase in FY 2017 to FY 2021 funding to provide additional capability to develop small, phased array satellite communication on-the-move capability for armored platforms.

## Table 22
Annual Funding 2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2009 |  | 56 | 135.8 |  | -- |  | -- |  | 135.8 |  | 0.1 |  | 135.9
2010 |  | 248 | 333.1 |  | -- |  | 71.9 |  | 405 |  | 62.2 |  | 467.2
2011 |  | 96 | 185.1 |  | -- |  | 74.4 |  | 259.5 |  | 80.7 |  | 340.2
2012 |  | 532 | 543.1 |  | -- |  | 44.5 |  | 587.6 |  | 105.9 |  | 693.5
2013 |  | 66 | 209.8 |  | -- |  | 30.1 |  | 239.9 |  | 176.4 |  | 416.3
2014 |  | 124 | 197.1 |  | -- |  | 39.4 |  | 236.5 |  | 90.4 |  | 326.9
2015 |  | 245 | 274.2 |  | -- |  | 17 |  | 291.2 |  | 96.7 |  | 387.9
2016 |  | 170 | 281.5 |  | -- |  | 20 |  | 301.5 |  | 154.6 |  | 456.1
2017 |  | 12 | 115.2 |  | -- |  | 10.5 |  | 125.7 |  | 186.1 |  | 311.8
2018 |  | 139 | 386.6 |  | -- |  | 10.7 |  | 397.3 |  | 228.1 |  | 625.4
2019 |  | 114 | 363.3 |  | -- |  | 10.9 |  | 374.2 |  | 238.7 |  | 612.9
2020 |  | 250 | 470.5 |  | -- |  | 11.2 |  | 481.7 |  | 231.1 |  | 712.8
2021 |  | 241 | 442 |  | -- |  | 11.4 |  | 453.4 |  | 225.9 |  | 679.3
2022 |  | 223 | 453.9 |  | -- |  | 11.6 |  | 465.5 |  | 232.3 |  | 697.8
2023 |  | 222 | 420.7 |  | -- |  | 11.9 |  | 432.6 |  | 240.3 |  | 672.9
2024 |  | 220 | 427.3 |  | -- |  | 12.1 |  | 439.4 |  | 246.2 |  | 685.6
2025 |  | 192 | 412.4 |  | -- |  | 12.3 |  | 424.7 |  | 273.8 |  | 698.5
2026 |  | 176 | 378.8 |  | -- |  | 12.6 |  | 391.4 |  | 288.7 |  | 680.1
2027 |  | 199 | 397.9 |  | -- |  | 12.8 |  | 410.7 |  | 329.1 |  | 739.8
2028 |  | 149 | 325.5 |  | -- |  | 13.1 |  | 338.6 |  | 316.3 |  | 654.9
2029 |  | -- | -- |  | -- |  | 13.3 |  | 13.3 |  | 355.7 |  | 369
Subtotal |  | 3674 | 6753.8 |  | -- |  | 451.7 |  | 7205.5 |  | 4159.3 |  | 11364.8

## Table 23
Annual Funding 2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2009 |  | 56 | 134.9 |  | -- |  | -- |  | 134.9 |  | 0.1 |  | 135
2010 |  | 248 | 325 |  | -- |  | 70.1 |  | 395.1 |  | 60.7 |  | 455.8
2011 |  | 96 | 177.4 |  | -- |  | 71.3 |  | 248.7 |  | 77.4 |  | 326.1
2012 |  | 532 | 512.8 |  | -- |  | 42 |  | 554.8 |  | 100 |  | 654.8
2013 |  | 66 | 194.2 |  | -- |  | 27.9 |  | 222.1 |  | 163.2 |  | 385.3
2014 |  | 124 | 179.4 |  | -- |  | 35.9 |  | 215.3 |  | 82.3 |  | 297.6
2015 |  | 245 | 246.2 |  | -- |  | 15.3 |  | 261.5 |  | 86.8 |  | 348.3
2016 |  | 170 | 249.5 |  | -- |  | 17.7 |  | 267.2 |  | 137 |  | 404.2
2017 |  | 12 | 100.2 |  | -- |  | 9.1 |  | 109.3 |  | 161.9 |  | 271.2
2018 |  | 139 | 329.7 |  | -- |  | 9.1 |  | 338.8 |  | 194.6 |  | 533.4
2019 |  | 114 | 303.8 |  | -- |  | 9.1 |  | 312.9 |  | 199.6 |  | 512.5
2020 |  | 250 | 385.7 |  | -- |  | 9.2 |  | 394.9 |  | 189.4 |  | 584.3
2021 |  | 241 | 355.2 |  | -- |  | 9.2 |  | 364.4 |  | 181.5 |  | 545.9
2022 |  | 223 | 357.6 |  | -- |  | 9.1 |  | 366.7 |  | 183.1 |  | 549.8
2023 |  | 222 | 325 |  | -- |  | 9.2 |  | 334.2 |  | 185.6 |  | 519.8
2024 |  | 220 | 323.6 |  | -- |  | 9.2 |  | 332.8 |  | 186.4 |  | 519.2
2025 |  | 192 | 306.2 |  | -- |  | 9.1 |  | 315.3 |  | 203.3 |  | 518.6
2026 |  | 176 | 275.7 |  | -- |  | 9.2 |  | 284.9 |  | 210.2 |  | 495.1
2027 |  | 199 | 284 |  | -- |  | 9.1 |  | 293.1 |  | 234.8 |  | 527.9
2028 |  | 149 | 227.7 |  | -- |  | 9.2 |  | 236.9 |  | 221.3 |  | 458.2
2029 |  | -- | -- |  | -- |  | 9.1 |  | 9.1 |  | 244 |  | 253.1
Subtotal |  | 3674 | 5593.8 |  | -- |  | 399.1 |  | 5992.9 |  | 3303.2 |  | 9296.1

## Table 24
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2007-06-05 | 2013-09-27
Approved Quantity | 408 | 1030
Reference | Restructure ADM | WIN-T Inc 2 Additional LRIP ADM
Start Year | 2009 | 2009
End Year | 2010 | 2015
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the following:
The WIN-T Inc 2 LRIP program is consistent with DAE direction contained in the WIN-T ADM dated June 5, 2007 and corresponding OSD Cost Analysis Improvement Group estimate. The ADM states “The Army will fund to the Chairman of the Cost Analysis Improvement Group's (CAIG) estimate for Increments 1 and 2; procure Increment 1 equipment to complete fielding to about 199 Army units; and procure Increment 2 equipment for about 37 Army units, based on affordability through FY 2013.” The current WIN-T Inc 2 program only procured 25 Army units through FY 2013.
The original LRIP quantity was reported to Congress in the initial September 2007 SAR and again in the December 2007 SAR. This initial LRIP plan consisted of a two-year LRIP phase with quantities totaling 408 communications nodes, or approximately 22%, of the total Army Procurement Objective (APO) of 1,837. These LRIP units were to be procured over two years, with the first year providing units to support Production Qualification Test and Initial Operational Test (IOT) and the second year supporting production ramp up and fielding.
The LRIP start year changed from 2009 to 2010 as a result of program schedule changes. The Milestone C meeting was held on February 3, 2010 after which the program entered into LRIP. The initial LRIP quantities and costs were funded with FY 2009 dollars.
The September 26, 2012 ADM approved an additional LRIP Lot 3 of 538 communications nodes to bring the total LRIP quantities to 938 communications nodes. The WIN-T Inc 2 LRIP plan consisted of a three-year LRIP phase with quantities totaling 932 communications nodes, or approximately 44%, of the total APO of 2,100. The PM received approval to exceed the 10% limit. The first year of LRIP provided units to support IOT and the second and third years permitted an orderly increase in the production rate for the system sufficient to lead to FRP upon the successful completion of operational testing.
The September 27, 2013 ADM approved an additional LRIP Lot 4 (excluding 119 Soldier Network Extension CIs) and Lot 5a training base articles. The duration of the LRIP phase was six years, FY 2009 through FY 2015. During this time Lots 1-5a were procured. The total LRIP quantity was 1,030 communications nodes, approximately 28% of the total 3,674 production communications nodes required.
The June 3, 2015 ADM authorized the Army to enter into FRP. Lots 5b and 6, procured in June 2015, were the first FRP lots procured.

## Table 25
Foreign Military Sales
None
Nuclear Costs
None

## Table 26
Unit Cost
Unit Cost Report
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
|  | Current UCR Baseline (Jun 2015 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 9389.3 |  |  | 9585.3
Quantity | 3730 |  |  | 3730
Unit Cost | 2.517 |  |  | 2.57 |  |  | 2.11
Average Procurement Unit Cost
Cost | 9128.5 |  |  | 9296.1
Quantity | 3674 |  |  | 3674
Unit Cost | 2.485 |  |  | 2.53 |  |  | 1.81
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
|  | Original UCR Baseline (Oct 2007 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 3617.2 |  |  | 9585.3
Quantity | 1893 |  |  | 3730
Unit Cost | 1.911 |  |  | 2.57 |  | +34.481
Average Procurement Unit Cost
Cost | 3384.5 |  |  | 9296.1
Quantity | 1837 |  |  | 3674
Unit Cost | 1.842 |  |  | 2.53 |  | +37.351
Item |  | TY $M |  |  | TY % Change
|  | Current UCR Baseline (Jun 2015 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost (PAUC)
Cost | 11351.9 |  |  | 11661.3
Unit Cost | 3.043 |  |  | 3.126 |  |  | 2.73
Average Procurement Unit Cost (APUC)
Cost | 11089.6 |  |  | 11364.8
Unit Cost | 3.018 |  |  | 3.093 |  |  | 2.49

## Table 27
Item |  | TY $M | [6 empty] | TY % Change
|  | Original UCR Baseline (Oct 2007 APB) |  |  | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost (PAUC)
Cost | 3907 |  |  |  |  | 11661.3
Unit Cost | 2.064 |  |  |  |  | 3.126 |  |  |  | 51.45
Average Procurement Unit Cost (APUC)
Cost | 3672 |  |  |  |  | 11364.8
Unit Cost | 1.999 |  |  |  |  | 3.093 |  |  |  | 54.73
1
Nunn-McCurdy Breach
Unit Cost Breach Data
Changes From Previous SAR |  |  | $M/Qty. |  |  |  | Percent
PAUC (BY $M) |  |  |  | -0.032 |  |  |  | -1.23
APUC (BY $M) |  |  |  | -0.039 |  |  |  | -1.52
PAUC Quantity |  |  |  | 91 |  |  |  | 0
PAUC (TY $M) |  |  |  | -0.022 |  |  |  | -0.7
APUC (TY $M) |  |  |  | -0.031 |  |  |  | -0.99
Initial SAR Information - Sep 2007 |  |  | BY2 | 007 $M |  |  | TY $M
Program Acquisition Cost |  |  | 1.8 |  |  |  | 2.1
Unit Cost PAUC Changes
The PAUC decreased from the December 2014 SAR to the December 2015 SAR due to increased quantity of Nodes procured and revised Configuration Item (CI) unit costs. The PAUC increased from the June 2015 APB due to an additional year of procurement.
Unit Cost APUC Changes
The APUC decreased from the December 2014 SAR to the December 2015 SAR due to increased quantity of Nodes procured and revised CI unit costs. The APUC increased from the June 2015 APB due to an additional year of procurement.
Impact of Performance or Schedule Changes
Schedule negatively impacts the PAUC and APUC through the addition of years to the program. WIN-T Inc 2 incurs additional fixed costs associated with program management, hardware refresh, and software licenses spread over fewer nodes being procured under the Army's modernization strategy.
Program Management or Control
The PM is aggressively controlling unit cost growth on the program as demonstrated by the decrease in PAUC and APUC

## Table 28
since the December 2014 SAR. As a result, since the Original APB, the cost of the individual CIs have, on the average, shown overall cost reductions. The PM is seeking to negotiate lower prices on CIs and incentives to reduce costs over the life of the program.
Cost Control Actions
The PM employs the best practices contained within the Better Buying Power to control future costs. In particular, WIN-T Inc 2 plans to use incentive type contracts on the follow-on production contract, gain efficiencies in the hardware refresh cycle and explore ways to promote competition for subsystem components. These initiatives have the potential to yield significant savings throughout the life cycle. Additionally, through Alpha contracting negotiations for the follow-on production contract the program office is establishing more accountability requirements for the prime contractor to incentivize productivity. The program office and Communications-Electronics Command will implement a plan for incremental transition of Lots 1-6 to Post-Production Software Support. This transition is scheduled for FY 2020 and will provide relief to the PAUC and APUC.
Nunn-McCurdy Comments
A Program Deviation Report and a revised APB were signed by the Army Acquisition Executive on January 23, 2015. The DAE was informed of the program deviation on February 9, 2015. The revised APB was signed by the DAE on February 12, 2015. Congressional notification was completed on February 25, 2015.

## Table 29
Unit Cost History
Item | [6 empty] | Date |  |  |  |  | BY 2010 $M | [6 empty] | TY $M
[12 empty] | PAUC |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Oct 2007 | [6 empty] | 1.911 |  |  |  | 1.842 |  |  |  | 2.064 |  |  |  | 1.999
APB as of January 2006 |  |  |  |  | N/A | [6 empty] | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Revised Original APB |  |  |  |  | N/A | [6 empty] | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | Feb 2015 | [6 empty] | 2.576 |  |  |  | 2.544 |  |  |  | 3.149 |  |  |  | 3.125
Current APB |  |  |  |  | Jun 2015 | [6 empty] | 2.517 |  |  |  | 2.485 |  |  |  | 3.043 |  |  |  | 3.018
Prior Annual SAR |  |  |  |  | Dec 2014 | [6 empty] | 2.602 |  |  |  | 2.569 |  |  |  | 3.148 |  |  |  | 3.124
Current Estimate |  |  |  |  | Dec 2015 | [6 empty] | 2.57 |  |  |  | 2.53 |  |  |  | 3.126 |  |  |  | 3.093
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [20 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth |  | Spt |  |  | Total
2.064 -0.055 -0.063 0.016 0.000 0.093 0.000 0.200 0.191 2.255
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [18 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  | Sch |  | Eng |  | Est |  |  | Oth | Spt |  |  | Total
2.255 -0.026 0.199 0.084 -0.141 -0.083 0.000 0.838 0.871 3.126

## Table 30
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [10 empty] | APUC Production Estimate
| Econ | Qty |  |  | Sch |  | Eng | Est | Oth | Spt | Total
1.999 -0.055 -0.055 0.017 0.000 0.079 0.000 0.205 0.191 2.190
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [10 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng |  | Est | Oth | Spt | Total
2.190 -0.027 0.228 0.086 -0.143 -0.092 0.000 0.851 0.903 3.093
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  |  | Jun 2007 |  |  | N/A |  |  | Jun 2007
Milestone C |  |  | N/A |  |  |  | Apr 2009 |  |  | N/A |  |  | Mar 2010
IOC |  |  | N/A |  |  |  | Aug 2011 |  |  | N/A |  |  | Aug 2013
Total Cost (TY $M) |  |  | N/A |  |  |  | 3907 |  |  | N/A |  |  | 11661.3
Total Quantity |  |  | N/A |  |  |  | 1893 |  |  | N/A |  |  | 3730
PAUC |  |  | N/A |  |  |  | 2.064 |  |  | N/A |  |  | 3.126

## Table 31
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
266.5 4730.4 -- 4996.9
Economic |  | 1.2 |  | -27.6 |  | -- |  | -26.4
Quantity |  | -- |  | 3937.1 |  | -- |  | 3937.1
Schedule |  | -- |  | 232.5 |  | -- |  | 232.5
Engineering |  | -- |  | -526.8 |  | -- |  | -526.8
Estimating |  | -5.4 |  | 26.6 |  | -- |  | 21.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 2821.7 |  | -- |  | 2821.7
Subtotal |  | -4.2 |  | 6463.5 |  | -- |  | 6459.3
Current Changes Economic |  | -- |  | -71.3 |  | -- |  | -71.3
Quantity |  | -- |  | 219.8 |  | -- |  | 219.8
Schedule |  | -- |  | 82.2 |  | -- |  | 82.2
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 34.2 |  | -363.7 |  | -- |  | -329.5
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 303.9 |  | -- |  | 303.9
Subtotal |  | 34.2 |  | 170.9 |  | -- |  | 205.1
Total Changes |  | 30 |  | 6634.4 |  | -- |  | 6664.4
CE - Cost Variance |  | 296.5 |  | 11364.8 |  | -- |  | 11661.3
CE - Cost & Funding |  | 296.5 |  | 11364.8 |  | -- |  | 11661.3

## Table 32
Summary BY 2010 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
264.7 4421.3 -- 4686.0
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 3113.8 |  | -- |  | 3113.8
Schedule |  | -- |  | 3.5 |  | -- |  | 3.5
Engineering |  | -- |  | -445.7 |  | -- |  | -445.7
Estimating |  | -3.9 |  | 15.8 |  | -- |  | 11.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 2097.8 |  | -- |  | 2097.8
Subtotal |  | -3.9 |  | 4785.2 |  | -- |  | 4781.3
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 153.8 |  | -- |  | 153.8
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 28.4 |  | -275.2 |  | -- |  | -246.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 211 |  | -- |  | 211
Subtotal |  | 28.4 |  | 89.6 |  | -- |  | 118
Total Changes |  | 24.5 |  | 4874.8 |  | -- |  | 4899.3
CE - Cost Variance |  | 289.2 |  | 9296.1 |  | -- |  | 9585.3
CE - Cost & Funding |  | 289.2 |  | 9296.1 |  | -- |  | 9585.3
Previous Estimate: December 2014

## Table 33
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Decrease due to prior year fact of life Congressional adjustments. (Estimating) -0.1 -0.1
Increase due to the addition of the Distributed Embedded Satellite Communication On-The- Move Standard Terminal Architecture capability for the WIN-T Inc 2 Armor Brigade Combat Teams. (Estimating)
+28.5 +34.3
RDT&E Subtotal +28.4 +34.2
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -71.3
Quantity variance resulting from an increase of 91 Nodes from 3,583 to 3,674 due to the new Army Structure Memorandum FY 2018 to FY 2022 dated October 2015. (Quantity) | 153.8 | 219.8
Stretch-out of procurement buy profile by one year from FY 2028 to FY 2029 due to the | 0 | 82.2
funding reductions from FY 2015 to FY 2021. (Schedule)
Decrease due to a revised estimate for Configuration Items unit costs based on an analysis of vendor actuals. (Estimating)
-281.7 -370.8
Adjustment for current and prior escalation. (Estimating) +6.5 +7.1
Adjustment for current and prior escalation. (Support) +2.2 +2.7
Increase in Other Support is due to a change in Fielding, New Equipment Training, and Software Maintenance costs resulting from increase of 91 nodes from 3,583 to 3,674 and an additional year of procurement. (Support) (QR)
Increase in Initial Spares quantity resulting from increase of 91 Nodes from 3,583 to 3,674, an additional year of procurement, and revised spares kit configurations and pricing. (Support) (QR)
+51.9 +97.0
+156.9 +204.2
Procurement Subtotal +89.6 +170.9
(QR) Quantity Related

## Table 34
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: WIN-T Increment 2 Production
Contractor: General Dynamics C4 Systems, Inc.
Contractor Location: 400 John Quincy Adams Rd
Taunton, MA 02780
Contract Number: W15P7T-10-D-C007
Contract Type: Firm Fixed Price (FFP), Fixed Price Incentive(Firm Target) (FPIF)
Award Date: March 24, 2010
Definitization Date: December 30, 2010
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
299.7 299.7 160 2123.0 2123.0 1367 2123.0 2123.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the procurement of Lots 1B through 5a which equate to an additional 870 nodes LRIP and Lots 5b and 6 which equate to 337 nodes FRP. Additionally, production support efforts were added to the contract price.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP/FPIF) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract because no active task order or related task order exceeds the threshold requirement for EVM reporting.

## Table 35
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 56 | 56 | 56 | 100%
Production | 883 | 883 | 3674 | 24.03%
Total Program Quantity Delivered | 939 | 939 | 3730 | 25.17%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
11661.3
2968.3
25.45%
23
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
10
43.48%
3486.2
29.9%
The above data is current as of February 09, 2016.

## Table 36
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 14, 2016
Source of Estimate: POE
Quantity to Sustain: 3674
Unit of Measure: Node
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2012 - FY 2049
1. A Node is defined as Tactical Communications Node, Point of Presence, and Soldier Network Extension Configuration Item.
2. Quantity of 3,674 Nodes to sustain does not include 56 Nodes procured in RDT&E.
3. Costs are estimated in accordance with Department of the Army Cost Analysis Manual, Deputy Assistant Secretary of the Army, U.S. Army Cost and Economic Analysis Center, May 2002.
4. O&S cost factors taken from the Army Operating and Support Management Information System.
5. Military Personnel costs are taken from the Army Military Cost System (AMCOS).
6. Mission Pay and Allowance estimates based on the WIN-T manpower estimates included in the WIN-T Inc 2 CARD dated November 21, 2014.
7. Estimated costs are based on the operating tempo approved by the Army's Training and Doctrine Command as well as individual Configuration Item component reliability.
Sustainment Strategy
Costs are based on the two-level maintenance concept. WIN-T Inc 2 employs the Army's two-level maintenance concept focusing on organic field level operations and a combination of contractor and Government services for sustainment / depot-level operations. All maintenance planning will comply with applicable section 2460, title 10, U.S.C. Core Depot statutes.
Antecedent Information
No Antecedent. WIN-T Inc 2 provides a different (on-the-move) capability from WIN-T Inc 1 (at-the-halt) communications and is not descended from the WIN-T Inc 1 system. Both programs are being fielded simultaneously to separate users, one is not replacing the other.
Annual O&S Costs BY2010 $K
Cost Element | WIN-T Inc 2 Average Annual Cost Per Node | N/A (Antecedent) N/A
Unit-Level Manpower | 78.742 | 0
Unit Operations | 2.288 | 0
Maintenance | 29.189 | 0
Sustaining Support | 18.579 | 0
Continuing System Improvements | 14.249 | 0
Indirect Support | 0 | 0
Other | 0 | 0
Total | 143.047 | --

## Table 37
Item | Total O&S Cost $M
| WIN-T Inc 2 | [5 empty] | N/A (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 10613.4 |  | 11674.7 |  |  | 10511.1 | N/A
Then Year | 15198.3 |  | N/A |  |  | 15152 | N/A
Equation to Translate Annual Cost to Total Cost
Multiplying the total average annual unitized cost by 20 years and by 3,674 communications nodes will achieve the total costs.
$143.047K * 20 * 3,674 = $10,511,093K - $10,511.1M
O&S Cost Variance
Category |  | BY 2010 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
11196.8
Programmatic/Planning Factors 59.5 Increase in cost due to 91 additional Nodes from 3,583 to 3,674 due to alignment with the new Army Structure Memorandum FY 2018 - FY 2022 and an additional year of support caused by the FY 2015 - FY 2021 funding decrements.
Cost Estimating Methodology 0.0
Cost Data Update -453.1 Reduction due to revised spares configuration, pricing, and Mean Time Between Failures; and revised software subscription costs.
Labor Rate -292.1 Reduction due to revised Military Personnel costs from the AMCOS database.
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes -685.7
Current Estimate 10511.1
Disposal Estimate Details
Date of Estimate: January 14, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2010 $M): Total costs for disposal of all Node are 32.7
Disposal costs increased by $13.9M from $18.8M to $32.7M due to revised lithium ion battery disposal costs.