## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-350
Warfighter Information Network-Tactical Increment 3 (WIN-T Inc 3)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 14
Cost and Funding 15
Low Rate Initial Production 20
Foreign Military Sales 21
Nuclear Costs 21
Unit Cost 22
Cost Variance 25
Contracts 28
Deliveries and Expenditures 29
Operating and Support Cost 30

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Warfighter Information Network-Tactical Increment 3 (WIN-T Inc 3)
DoD Component
Army
Responsible Office
COL Gregory Coile PM WIN-T
6010 Frankford Street
Aberdeen Proving Ground, MD 21005-1848
gregory.h.coile.mil@mail.mil
Phone: | 443-395-7223
Fax: | 443-395-7208
DSN Phone: | 648-7223
DSN Fax: | 648-7208
Date Assigned: | July 20, 2015
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated May 18, 2009
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated September 15, 2014

## Table 6
Mission and Description
Warfighter Information Network-Tactical Increment 3 (WIN-T Inc 3) develops the Network Operations (NetOps) software to meet the Army’s Network Convergence goals. NetOps provides the monitoring, control and planning tools to ensure management of the voice, data and internet transport networks. The NetOps software will also provide Information Assurance and Network Centric Enterprise Services. This allows for seamless integration of the tactical network planning, management, monitoring, and defense for the Signal staff. These NetOps improvements simplify the management of the network and increase the automation of tools and reporting. The developed NetOps software enhancements will be provided as a technical insertion to WIN-T Inc 1 and WIN-T Inc 2 for fielding and support.
WIN-T Inc 3 develops the enhanced Net Centric Waveform (NCW) version 10.x for increased throughput capability for beyond the line of sight satellite communication and the Highband Networking Waveform (HNW) version 3.0 for line of sight communications. Both NCW and HNW provide improved network capacity and robustness. The waveform improvements will be available for use in WIN-T and other Army and DoD programs.

## Table 7
Executive Summary
The program is greater than 90% expended. Per the May 30, 2014 ADM, the program will continue submitting SARs reflecting a software only program until the Army Acquisition Executive (AAE) authorizes deployment of both the Net-Centric Waveform (NCW) 10.x and Network Operations Build 4/5. A Deployment Decision Review with the AAE is planned for 4th Quarter FY 2016.
Throughout FY 2015, Network Operations (NetOps) and waveform software development and test was on-going.
The NetOps Build 4 Production Release Test Readiness Review was held on March 5, 2015. General Dynamics successfully met all required entrance criteria and was authorized to proceed to Level 3/Level 4 system integration testing. A NetOps Build 5 Point Release 15.1 technical interchange meeting was held with General Dynamics and Lockheed Martin on April 1, 2015. Test progress of NetOps Build 4 was also reviewed to assess the readiness for Formal Qualification Test (FQT) #2.
In May 11-12, 2015, WIN-T Inc 3 Program Management Office (PMO) led a technical interchange meeting for the NetOps Build 5 Point Release 15.2 with General Dynamics and Lockheed Martin. The PM reviewed test progress of Build 4 to assess the release schedule, testing priorities and key milestones leading up to the FQT #2 conducted in June 2015.
On June 30, 2015, the PMO completed the FQT #2 at the General Dynamics facility in Taunton, Massachusetts. All but one of the vignettes tested successfully. The vignette to test Private Key Infrastructure functionality failed due to test execution and not functionality. General Dynamics and the PMO successfully retested this vignette in August 2015. A second logistics software demonstration was completed in July 2015. The third logistics software demonstration and the FQT #3 were both successfully completed in December 2015.
The NCW 10.x developmental testing occurred October 12-14, 2015. The test demonstrated two performance requirements: 1) Throughput of 12 Megabits per second at the 2.4 meter satellite dishes and 2) interoperability with the previous NCW 8.x version. Test results demonstrated that NCW 10.x successfully passed the requirements and is ready for operational testing at Network Integration Evaluation 16.2.
On May 12, 2015, the PMO hosted Harris and U.S. Army Communications-Electronics Research, Development and Engineering Center (CERDEC) subject matter experts for the equipment integration of the Highband Networking Waveform (HNW) test bed at Aberdeen Proving Ground, Maryland and the installation of HNW 3.0 software on to radio platforms. This combined effort resulted in establishing a live HNW link in the PM WIN-T lab. On May 26, 2015, the PMO, with support
from CERDEC Flight Activity (CFA), commenced safety flight-testing of the air tier antenna pod at Fort Eustis, Virginia. CFA found no issues during the testing. On July 16, 2015, the PM presented a briefing on the status and plan for the HNW 3.0 Demonstration, to the USD(AT&L) and other OSD organizations: no issues were identified. On October 7, 2015, the PM held an HNW test vehicle design review. The review confirmed the A/B-Kit vehicle integration plan was suitable with a few minor edits. A live node checkout was completed in January 2016, in preparation for the live full-scale HNW demo in 4th Quarter FY 2016.
The program received a decrement of $6.185M in the FY 2016 PB. The PMO realigned priorities and resources so as to not impact completion of ADM directed requirements. The PM continues transition planning discussions with both the WIN-T Inc 1 and WIN-T Inc 2 PMOs to set the conditions for a Deployment Decision Review with the AAE in 4th Quarter FY 2016.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
(Ch-1)
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B (Original WIN-T Program) | Jul 2003 | Jul 2003 | Jul 2003 | Jul 2003
WIN-T Increment 3 Program Restructure Certification | Jun 2007 | Jun 2007 | Jun 2007 | Jun 2007
Limited User Test (LUT) - Start | Nov 2012 | N/A | N/A | N/A
Limited User Test (LUT)- End | Dec 2012 | N/A | N/A | N/A
Milestone C | May 2013 | N/A | N/A | N/A
Initial Operational Test (IOT) - Start | Mar 2016 | N/A | N/A | N/A
Initial Operational Test (IOT) - End | Apr 2016 | N/A | N/A | N/A
Full Rate Production (FRP) Decision Review | Sep 2016 | N/A | N/A | N/A
IOC | Apr 2017 | N/A | N/A | N/A
CDR | N/A | Dec 2013 | Dec 2013 | Dec 2013
NetOps Demonstration at NIE 14.2 | N/A | May 2014 | May 2014 | May 2014
NCW Test | N/A | May 2015 | Nov 2015 | Oct 2015
NetOps LUT at NIE 16.2 | N/A | May 2016 | Nov 2016 | May 2016
HNW Demonstration | N/A | Mar 2016 | Sep 2016 | Jul 2016
(Ch-2)

## Table 10
Change Explanations
(Ch-1) The Current Estimate for the NCW Test changed from May 2015 to October 2015 to align with the development and resource schedule and is now completed.
(Ch-2) The Current Estimate for the HNW Demonstration changed from March 2016 to July 2016 to align with the current test range availability.
Notes
The NetOps LUT at NIE 16.2 will be a FOT&E including both NetOps and NCW per the approved TEMP Appendix.
Acronyms and Abbreviations
CDR - Critical Design Review
FOT&E - Follow-On Operational Test and Evaluation HNW - Highband Networking Waveform
NCW - NetCentric Waveform NetOps - Network Operations
NIE - Network Integration Evaluation TEMP - Test and Evaluation Master Plan

## Table 11
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Net Ready
The system must fully support | Enter and be | Enter and be | FQT #1 | Enter and be
execution of all operational | managed in the | managed in the | successfully | managed in the
activities identified in the | network. Provide | network. Provide | demonstrated all | network. Provide
applicable joint and system | NetOps for the US | NetOps for the US | features developed | NetOps for the US
integrated architectures and the | Army Network to | Army Network to | for Build 4e. FQT | Army Network to
system must satisfy the | allow for | allow for | #2 successfully | allow for
technical requirements for Net- | management and | management and | demonstrated all | management and
Centric military operations to | control of | control of | features developed | control of
include 1) DISR mandated GIG | transmissions. | transmissions. Two | for Build 4. FQT #3 | transmissions. Two
IT standards and profiles | Four (4) separate | (2) separate | successfully | (2) separate
identified in the TV-1, 2) DISR | enclaves | enclaves | demonstrated all | enclaves
mandated GIG KIPs: KIP 2 – | (SIPRNET, | (SIPRNET, | features developed | (SIPRNET,
Space to Terrestrial Interface, | NIPRNET, Top | NIPRNET) across | for Build 5. | NIPRNET) across
KIP 3 – JTF to Coalition, KIP 4 – | Secret, Mission | WIN-T's colorless |  | WIN-T's colorless
JTF Component to JTF | Area defined) | transmission path |  | transmission path
Headquarters , KIP 5 – STEP | across colorless | at a location in or |  | at a lociation in or
and Teleport, and KIP 7 – DISN | transmission path | outside the tactical |  | outside the tactical
Service Delivery Point 3) | at any ATH Army | operational |  | operational
NCOW RM Enterprise Services | location or echelon. | geographic area. |  | geographic area.
4) Information assurance
requirements including
availability, integrity, authenticat-
ion, confidential-ity, and
nonrepudiat-ion, and issuance
of an ATO by the DAA, and 5)
Operationally effective
information exchanges; and
mission critical performance
and information assurance
attributes, data correctness,
data availability, and consistent
data processing specified in the
applicable joint and system
integrated architecture views.
Network Management: WIN-T will enable the G6/S6 to implement the commander's priorities by providing the capability and tools to plan, monitor, control, prioritize and visually display (e.g., current network status and connectivity) the various networking components for networks that connect secret and unclass users from a location at the Corps, Division, and Brigade in the AOR (Threshold) and for a location outside the AOR (Objective)
Outside of the AOR. | N/A | N/A | N/A | N/A
Information Dissemination Category 1/Category 2
Critical survival information | N/A | N/A | N/A | N/A

## Table 12
(Category 1) delivery in less than or equal to 0.5 seconds and time sensitive information (Category 2) in less than 1 seconds.
Force Protection
Armor required to protect personnel operating WIN-T vehicles employed at BCT, Fires, AVN, BfSB, and select force pooled assets operating within the Division battlespace. WIN-T components at Brigade and below require armor kits for protection of passengers and crew from small arms fire, mines, IED and other anti- vehicle/ personnel threats. | N/A | N/A | N/A | N/A
Mobile Throughput: Traveling Speed (mph) with Bps throughout (ground speed)
Modular Force Ground vehicles: from 0 to 45 miles per hour with 4 Mbps per link available for user data. FCS BCT Ground Vehicles: from 0 to 72 kilometers per hour with 4 Mbps per link available for user data. | N/A | N/A | N/A | N/A
Requirements Reference
Warfighter Information Network - Tactical CDD dated November 6, 2006 and revalidated on May 2, 2007 as revised on August 13, 2013
Change Explanations
None
Notes
The WIN-T CDD does not include the Sustainment KPP for Materiel Availability and the associated Key System Attributes.

## Table 13
Acronyms and Abbreviations
AOR - Area of Responsibility ATH - At-the-Halt
ATO - Approval to Operate AVN - Aviation
BCT - Brigade Combat Team
BfSB - Battlefield Surveillance Brigades DAA - Designated Approval Authority
DISN - Defense Information Systems Network
DISR - Department of Defense IT Standards Registry FCS - Future Combat Systems
FQT - Formal Qualification Test
G6 - Communications Staff Office, Division or Higher GIG - Global Information Grid
IED - Improvised Explosive Devices IT - Information Technology
JTF - Joint Task Force KIP - Key Interface Profile
KSA - Key System Attributes Mbps - Megabits per second
NCOW RM - Net Centric Operations and Warfare Reference Model NetOps - Network Operations
NIPRNET - Non-Secure Internet Protocol Router Network S6 - Communications Staff Office, Brigade and Below SIPRNET - Secure Internet Protocol Network
STEP - Standardized Tactical Entry Point TV - Technical View

## Table 14
Track to Budget
General Notes
Based on the approved program restructure, the Other Procurement, Army (OPA2) (BW7120) and Spares (OPA4) (BS9723) funding lines reflect zero funding in the FY 2016 PB and beyond.
RDT&E
Appn |  | BA | PE
Army 2040 04 0603782A
Project | Name
355 WIN-TACTICAL DEM/VAL (Sunk)
372 WIN-T INCREMENT 3 - FULL NETWORKING ON THE MOVE
(Sunk)
Notes: Project 372 began in FY 2009 for WIN-T Inc 3 exclusively.
Army 2040 05 0605350A
Project | Name
EE8 WIN-T INC 3 Full Networking (Sunk)
Notes: This Project EE8 was not a new start in FY 2015. This effort was funded under PE 0603782A Project 372 through FY 2014. It is funded under 0605350A Project EE8 in FY 2015 and FY 2016.
Procurement
Notes
Per the May 30, 2014 ADM, the program was restructured as a software development program. All procurement quantities were removed during EMD. The parent Line Item for the WIN-T Inc 3 Procurement (BW7120) was BW7100. The parent Line Item for the WIN-T Inc 3 Spares (BW9723) was BS9100.

## Table 15
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2009 $M |  |  |  | BY 2009 $M |  | TY $M
| SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Development Estimate |  | Current APB Development Objective |  | Current Estimate
RDT&E | 2595.5 |  | 1820.8 | 2002.9 |  | 1815 |  | 2656.5 |  | 1856.8 |  | 1846.2
Procurement | 13212.4 |  | 0 | 0 |  | 0 |  | 16156.7 |  | 0 |  | 0
Flyaway | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Recurring | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Non Recurring | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Other Support | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Initial Spares | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
MILCON | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 15807.9 |  | 1820.8 | N/A |  | 1815 |  | 18813.2 |  | 1856.8 |  | 1846.2
Current APB Cost Estimate Reference
Army Cost Position (ACP) dated July 29, 2014
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The ACP, like all life-cycle cost estimates built by the Deputy Assistant Secretary of the Army for Cost and Economics (DASA-CE), was built upon a product-oriented work breakdown structure, based on historical actual cost information to the maximum extent possible and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for MDAPs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.
Cost Notes
The costs for WIN-T Inc 3 reflect all sunk costs associated with the original WIN-T program as well as the costs to implement WIN-T Inc 3. Technology development prior to the FY 2007 Nunn-McCurdy certification that is now identified as WIN-T Inc 2 functionality appears as sunk costs in WIN-T Inc 3. WIN-T Inc 3 develops the technologies which will be inserted into WIN-T Inc 2. All funds required for development and testing are included in WIN-T Inc 3 and reflected in the costs in this report.
The Current Estimate reflects September 15, 2014 APB and FY 2017 PB funding. The program no longer reports cost

## Table 16
growth against PAUC and APUC due to the reduction in procurement quantities to zero.
Total Quantity
Quantity | SAR Baseline Development Estimate | Current APB Development | Current Estimate
RDT&E | 39 | 0 | 0
Procurement | 3443 | 0 | 0
Total | 3482 | 0 | 0
Quantity Notes
The unit of measure is a communications node which varies in capability depending upon the increment of
WIN-T being executed. The WIN-T Inc 3 unit of measure is comprised of Tactical Communications Nodes, Points of Presence, and Soldier Network Extensions. The sum of these three items equates to the total number of communications nodes to be procured for WIN-T Inc 3. Procurement quantities have been reduced to zero to reflect the May 30, 2014 ADM direction.

## Table 17
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 1812.7 | 33.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1846.2
Procurement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
MILCON | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 1812.7 | 33.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1846.2
PB 2016 Total | 1817 | 39.7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1856.7
Delta | -4.3 | -6.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -10.5
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Production | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2016 Total | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Table 18
Cost and Funding
Annual Funding By Appropriation
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.1
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.8
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 87.7
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 95.1
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 92
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 119.3
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 191.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 300.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 145.7
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 167.3
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 167.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 158.8
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 117.2
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 108.9
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.5
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1846.2

## Table 19
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2009 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 55.2
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 96.9
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 102.2
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 96.2
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 121.8
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 192
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 297.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 141.9
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 159.9
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 157.4
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 146.9
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 106.3
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 97.2
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.6
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1815

## Table 20
Low Rate Initial Production
There is no LRIP for this program.

## Table 21
Foreign Military Sales
None
Nuclear Costs
None

## Table 22
Unit Cost
Unit Cost Report
Item |  | BY 2009 $M | BY 2009 $M |  | % Change
|  | Current UCR Baseline (Sep 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1820.8 |  |  | 1815
Quantity | 0 |  |  | 0
Unit Cost | -- |  |  | -- |  | --
Average Procurement Unit Cost
Cost | 0 |  |  | 0
Quantity | 0 |  |  | 0
Unit Cost | -- |  |  | -- |  | --
Item |  | BY 2009 $M | BY 2009 $M |  | % Change
|  | Original UCR Baseline (May 2009 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 15807.9 |  |  | 1815
Quantity | 3482 |  |  | 0
Unit Cost | 4.54 |  |  | -- |  | --
Average Procurement Unit Cost
Cost | 13212.4 |  |  | 0
Quantity | 3443 |  |  | 0
Unit Cost | 3.837 |  |  | -- |  | --

## Table 23
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2009 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | May 2009 |  |  |  |  | 4.54 |  |  | 3.837 |  |  | 5.403 |  |  | 4.693
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | Oct 2010 |  |  |  |  | 4.177 |  |  | 3.551 |  |  | 5.013 |  |  | 4.382
Current APB |  |  | Sep 2014 |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Current Estimate |  |  | Dec 2015 |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
5.403 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
4.693 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000

## Table 24
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Jul 2003 | N/A | Jul 2003
Milestone C | N/A | May 2013 | N/A | N/A
IOC | N/A | Apr 2017 | N/A | N/A
Total Cost (TY $M) | N/A | 18813.2 | N/A | 1846.2
Total Quantity | N/A | 3482 | N/A | 0
PAUC | N/A | 5.403 | N/A | N/A

## Table 25
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 2656.5 | 16156.7 | -- | 18813.2
Previous Changes
Economic | 7.5 | 247.1 | -- | 254.6
Quantity | -141.9 | -12821.9 | -- | -12963.8
Schedule | -14 | -98.5 | -- | -112.5
Engineering | -761.3 | 450.9 | -- | -310.4
Estimating | 109.9 | 260.2 | -- | 370.1
Other | -- | -- | -- | --
Support | -- | -4194.5 | -- | -4194.5
Subtotal | -799.8 | -16156.7 | -- | -16956.5
Current Changes
Economic | -1.9 | -- | -- | -1.9
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -8.6 | -- | -- | -8.6
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -10.5 | -- | -- | -10.5
Total Changes | -810.3 | -16156.7 | -- | -16967
CE - Cost Variance | 1846.2 | -- | -- | 1846.2
CE - Cost & Funding | 1846.2 | -- | -- | 1846.2

## Table 26
Summary BY 2009 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 2595.5 | 13212.4 | -- | 15807.9
Previous Changes
Economic | -- | -- | -- | --
Quantity | -124.4 | -10115.9 | -- | -10240.3
Schedule | -0.5 | -394.3 | -- | -394.8
Engineering | -739.5 | 378.5 | -- | -361
Estimating | 91.4 | 143.3 | -- | 234.7
Other | -- | -- | -- | --
Support | -- | -3224 | -- | -3224
Subtotal | -773 | -13212.4 | -- | -13985.4
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -7.5 | -- | -- | -7.5
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -7.5 | -- | -- | -7.5
Total Changes | -780.5 | -13212.4 | -- | -13992.9
CE - Cost Variance | 1815 | -- | -- | 1815
CE - Cost & Funding | 1815 | -- | -- | 1815
Previous Estimate: December 2014

## Table 27
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -1.9
Decrease due to fact of life Congressional adjustments. (Estimating) -3.8 -4.3
Decrease due to fewer than expected Program Trouble Reports, more efficient senior staff allocated to Build 4, and the Cost Plus Incentive Fee contract type. (Estimating)
-5.5 -6.2
Adjustment for current and prior escalation. (Estimating) +1.8 +1.9
RDT&E Subtotal -7.5 -10.5

## Table 28
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: Follow-On EMD
Contractor: General Dynamics C4 Systems, Incorporated
Contractor Location: 400 John Quincy Adams Road
Taunton, MA 02780
Contract Number: W15P7T-14-D-0002
Contract Type: Cost Plus Incentive Fee (CPIF), Indefinite Delivery Indefinite Quantity (IDIQ)
Award Date: October 31, 2013
Definitization Date: October 31, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
89.4 N/A 0 237.6 N/A 0 236.0 229.3
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to modification of task orders for continued Network Operations and Net Centric Waveform development and test.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +17.5 -2.1
Previous Cumulative Variances +13.6 -0.7
Net Change +3.9 -1.4
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to fewer than expected Program Trouble Reports and more efficient senior staff allocated to Build 4.
The unfavorable net change in the schedule variance is due to complexities in operating environment software development. Critical path items remain on schedule.

## Table 29
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 0 | 0 | 0 | --
Total Program Quantity Delivered | 0 | 0 | 0 | --
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
1846.2
1813.8
98.25%
15
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
15
100%
1846.2
100%
The above data is current as of February 09, 2016.
The program is greater than 90% expended. Per the May 30, 2014 ADM the program will continue submitting SARs reflecting a software only program until the Army Acquisition Executive (AAE) authorizes deployment of both the Net-Centric Waveform 10.x and Network Operations Build 4/5. A Deployment Decision Review with the AAE is planned for 4th Quarter FY 2016.
Expenditures reflect only direct program funding.

## Table 30
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 14, 2015
Source of Estimate: POE
Quantity to Sustain: 0
Unit of Measure: Node
Service Life per Unit: 0.00 Years
Fiscal Years in Service: FY 2002 - FY 2016
A Node is defined as Tactical Communications Node, Point of Presence, and Soldier Network Extension Configuration Items.
Sustainment Strategy
There is no longer a requirement for Sustainment on WIN-T Inc 3 due to the May 30, 2014 ADM direction to transfer fielding requirements to WIN-T Inc 2.
Antecedent Information
No Antecedent
Annual O&S Costs BY2009 $K
Cost Element |  | WIN-T Inc 3 Average Annual Cost Per Node |  |  |  | No Antecedent (Antecedent) N/A
Unit-Level Manpower |  | 0 |  |  |  | 0
Unit Operations |  | 0 |  |  |  | 0
Maintenance |  | 0 |  |  |  | 0
Sustaining Support |  | 0 |  |  |  | 0
Continuing System Improvements |  | 0 |  |  |  | 0
Indirect Support |  | 0 |  |  |  | 0
Other |  | 0 |  |  |  | 0
Total |  | -- |  |  |  | --
Total O&S requirement is $3.3M which consists only of Military Personnel costs from FY 2002 to FY 2016. Ordinarily, these costs would appear in the Sustaining Support Cost Element. However, with the removal of the Nodes there is no longer a unitized cost.
Item | Total O&S Cost $M
| WIN-T Inc 3 | [5 empty] | No Antecedent (Antecedent)
| Current Development APB Objective/Threshold |  |  | Current Estimate
Base Year | 3.3 |  | 3.6 |  | 3.3 |  | N/A
Then Year | 3.5 |  | N/A |  | 3.5 |  | 0

## Table 31
Total O&S requirement is $3.3M which consists only of Military Personnel supporting the program office from FY 2002 to FY 2016.
O&S Cost Variance
Category | BY 2009 $M | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
3.3
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 3.3
Disposal Estimate Details
Date of Estimate: January 14, 2015
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2009 $M): Total costs for disposal of all Node are 0.0
There are no disposal/demilitarization costs associated with this program.