## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-368
AGM-88E Advanced Anti-Radiation Guided Missile (AGM-88E AARGM)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 12
Cost and Funding 13
Low Rate Initial Production 20
Foreign Military Sales 21
Nuclear Costs 21
Unit Cost 22
Cost Variance 25
Contracts 28
Deliveries and Expenditures 31
Operating and Support Cost 32

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
AGM-88E Advanced Anti-Radiation Guided Missile (AGM-88E AARGM)
DoD Component
Navy
Joint Participants
Italian Ministry of Defense
Responsible Office
CAPT Albert Mousseau
Program Executive Office (Unmanned Aviation and Strike Weapons)
Attn: PMA-242, Bldg. 2272, R252
47123 Buse Road, Unit IPT Patuxent River, MD 20670-1557
albert.g.mousseau@navy.mil
Phone: 301-757-7422
Fax: 301-757-7418
DSN Phone: 757-7422
DSN Fax:
Date Assigned: June 20, 2013
References
SAR Baseline (Production Estimate)
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated January 21, 2009
Approved APB
Assistant Secretary of the Navy (Research, Development & Acquisition) (ASN(RDA)) Approved Acquisition Program Baseline (APB) dated November 7, 2012

## Table 6
Mission and Description
The AGM-88E Advanced Anti-Radiation Guided Missile (AGM-88E AARGM) program fields a major system upgrade to the AGM-88 High Speed Anti-Radiation Missile (HARM) inventory. The AGM-88E AARGM provides a significant enhancement to Naval operational capability in the Offensive Counter Air/Suppression of Enemy Air Defenses (SEAD) mission area by technological upgrade to the HARM guidance system to counter enemy use of simple and cheap countermeasures and tactics such as mobility and radar shutdown. The AGM-88E AARGM is employed in the Offensive Counter Air/SEAD role in direct support of all mission areas within the objective force (e.g., Strike Warfare, Amphibious Warfare, Anti-Surface Ship Warfare, and Command and Control Warfare and Information Warfare) providing a rapid, organic response to air defense threats ranging from Smaller Scale Contingencies to Major Theater War. It will be employed by Naval aircraft operating from both sea and land bases.
The AGM-88E AARGM missile provides a new multi-mode guidance section and modified control section mated with existing HARM propulsion and warhead sections. The new guidance section has a passive Anti-Radiation Homing receiver and associated antennae, a Global Positioning System/Inertial Navigation System, and Millimeter Wave radar for terminal guidance capability. The AGM-88E AARGM also has the capability to transmit terminal (end game) data via a Weapon Impact Assessment transmitter to national satellites just before AGM-88E AARGM impacts its target. Additionally, a provision to receive off-board targeting information, via the Integrated Broadcast System, is in development for the weapon system.
The AGM-88E AARGM is the acquisition upgrade and complement to HARM, the Navy's only Defense Suppression missile. Acquisition of AGM-88E AARGM is critical to addressing the limitations and shortcomings of HARM, which include counter shutdown capability, limited lethality against advanced threat air defense units, limited captive carry life, no impact reporting capability, and no off-board targeting reception capability.
The AGM-88E AARGM is fielded on the F/A-18C-F and the EA-18G. Objective aircraft include EA-6B, F-16C/J and F-35 external carriage (post platform IOC).

## Table 7
Executive Summary
AARGM weapon system production is scheduled to continue through 2023. A total of 2,435 AGM-88E AARGM (including Captive Air Training Missiles (CATMs) and spare Guidance and Control Sections) are planned for production. The contract for the fourth FRP lot was awarded September 3, 2015 within program cost goals. The Cooperative Production, Sustainment and follow-on Development Memorandum of Agreement between the United States and Italy remains in effect. Letter of Offer and Acceptance between the United States and Australia signed May 31, 2013 established an FMS Case to procure AARGM Captive Air Training Missiles and support. Block 1 Upgrade (software update) entered Integrated Test (Follow-on Test and Evaluation) in August 2014, with fleet delivery estimated in 2nd Quarter FY 2017.
When measured against the original Milestone B 2003 baseline, AARGM's current Average Procurement Unit Cost exceeds the JROC Tripwire threshold (25% above original baseline). This was due to program restructuring and budget profile adjustments. AARGM successfully completed a JROC Tripwire review in May 2014, and no further action was required.
The FY 2017 PB increases the total quantity objective from 1,879 to 2,435 AGM-88E AARGM and extends production to 2023. The proposed APB change will reflect the updated quantity profile and budget requirements.
The FY 2017 PB includes development and procurement funding for the AARGM Extended Range (AARGM-ER) program. Anticipated to be a distinct acquisition effort, all funding related to AARGM-ER is excluded from this SAR.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
The Procurement Cost breach is due to FY 2017 PB, which increased the total quantity objective from 1,879 to 2,435 AARGM and extended production from FY 2020 to FY 2023.
The O&S Cost breach is due to the increased quantity profile and corresponding service life assumption.
The proposed APB change will reflect the updated procurement quantity profile, budget requirements, and O&S costs.
A Program Deviation Report and re-baselining of the APB are in process.
Nunn-McCurdy Breaches

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B Decision | Apr 2003 | Apr 2003 | Oct 2003 | Jun 2003
SD&D Contract Award | May 2003 | May 2003 | Nov 2003 | Jun 2003
Beginning of TECHEVAL | Mar 2007 | Mar 2007 | Sep 2007 | Mar 2007
Milestone C Decision (LRIP) | Mar 2008 | Mar 2008 | Sep 2008 | Sep 2008
Beginning of OPEVAL | Mar 2009 | Mar 2010 | Sep 2010 | Jun 2010
IOC | Nov 2010 | Feb 2012 | Aug 2012 | Jul 2012
FRP Decision | Jul 2010 | Mar 2012 | Sep 2012 | Aug 2012
FRP Contract Award | Dec 2010 | Apr 2012 | Oct 2012 | Sep 2012
Change Explanations
Acronyms and Abbreviations
OPEVAL - Operational Evaluation
SD&D - System Development & Demonstration TECHEVAL - Technical Evaluation

## Table 10
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Material Availability
>=0.95 | >=0.95 | >=0.9 | 0.98 | 0.98
Net Ready
The system must | The system must | The system must | The system must fully | The system must
fully support | fully support | fully support | support execution of | fully support
execution of all | execution of all | execution of joint | joint critical operational | execution of joint
operational activities | operational activities | critical operational | activities identified in | critical operational
identified in the | identified in the | activities identified in | the applicable joint and | activities identified in
applicable joint and | applicable joint and | the applicable joint | system intregrated | the applicable joint
system integrated | system integrated | and system | architectures and the | and system
architectures and the | architectures and the | intregrated | system must satisfy the | intregrated
system must satisfy | system must satisfy | architectures and the | technical requirements | architectures and the
the technical | the technical | system must satisfy | for transition to Net- | system must satisfy
requirements for Net- | requirements for Net- | the technical | Centric military | the technical
Centric military | Centric military | requirements for | operations to include 1) | requirements for
operations to include | operations to include | transition to Net- | DISR - mandated GIG | transition to Net-
(1) DISR-mandated | (1) DISR-mandated | Centric military | IT standards and | Centric military
GIG IT standards and | GIG IT standards and | operations to include | profiles indentified in the | operations to include
profiles identified in | profiles identified in | 1) DISR - mandated | TV-1; 2) DISR- | 1) DISR - mandated
the TV-1; (2) DISR- | the TV-1; (2) DISR- | GIG IT standards and | mandated GIG KIPs | GIG IT standards and
man dated GIG KIPs | man dated GIG KIPs | profiles indentified in | identified in the KIP | profiles indentified in
identified in the KIP | identified in the KIP | the TV-1; 2) DISR- | declaration table; 3) | the TV-1; 2) DISR-
declaration table; (3) | declaration table; (3) | mandated GIG KIPs | NCOW RM Enterprise | mandated GIG KIPs
NCOW RM | NCOW RM | identified in the KIP | Services; 4) IA | identified in the KIP
Enterprise Services; | Enterprise Services; | declaration table; 3) | requirements including | declaration table; 3)
(4) IA requirements | (4) IA requirements | NCOW RM | availability, integrity, | NCOW RM
including availability, | including availability, | Enterprise Services; | authentica-tion, | Enterprise Services;
integrity, authentic- | integrity, authentic- | 4) IA requirements | confidentiality and non- | 4) IA requirements
ation, confidential-ity, | ation, confidential-ity, | including availability, | repudiation, and | including availability,
and non-repudiation, | and non-repudiation, | integrity, authentic- | issuance of an IATO by | integrity, authentica-
and issuance of an | and issuance of an | ation, confidential-ity | the DAA; and 5) | tion, confidentiality
ATO by the DAA; and | ATO by the DAA; and | and non-repudiation, | Operation-ally effective | and non-repudiation,
5) Operationally | 5) Operationally | and issuance of an | IEs; and mission critical | and issuance of an
effective IEs, and | effective IEs, and | IATO by the DAA; and | performance and IA | IATO by the DAA; and
mission critical | mission critical | 5) Operationally | attributes, data | 5) Operation-ally
performance and IA | performance and IA | effective IEs; and | correctness, data | effective IEs; and
attributes, data | attributes, data | mission critical | availability, and | mission critical
correctness, data | correctness, data | performance and IA | consistent data | performance and IA
availability, and | availability, and | attributes, data | processing specified in | attributes, data
consistent data | consistent data | correctness, data | the applicable joint and | correctness, data
processing specified | processing specified | availability, and | system integrated | availability, and
in the applicable joint | in the applicable joint | consistent data | architecture views. | consistent data
and system | and system | processing specified |  | processing specified
integrated | integrated | in the applicable joint |  | in the applicable joint

## Table 11
architecture views. | architecture views. | and system integrated architecture views. |  | and system integrated architecture views.
Probability of Correct Identification (PCID) of a Target Emitter
>=0.99 PCID for all | >=0.99 PCID for all | >=0.95 PCID of | 0.95 PCID of available | 0.95 PCID for all
emitters in the | emitters in the | available threshold | threshold emitters in | emitters in the
AARGM CPD | AARGM CPD | emitters in the | the AARGM CPD | AARGM CPD
Appendix D | Appendix D | AARGM CPD | Appendix D | Appendix D
Appendix D
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Capability Production Document (CPD) dated April 1, 2010
Change Explanations
None
Acronyms and Abbreviations
ATO - Authority to Operate
DAA - Designated Approval Authority DISR - DoD IT Standards Registry GIG - Global Information Grid
IA - Information Assurance
IATO - Interim Authority to Operate IE - Information Exchange
IT - Information Technology KIP - Key Interface Profile
NCOW RM - Net Centric Operations and Warfare Reference Model TV - Technical View

## Table 12
Track to Budget
RDT&E
Appn |  | BA | PE
Navy 1319 07 0205601N
Project | Name
2185 AARGM (Shared)
2661 AARGM Cong Add (Sunk)
9C58A AARGM Cong Add (Sunk)
Procurement
Appn |  | BA | PE
Navy 1507 02 0204162N
Line Item | Name
2327 HARM Mods (Shared)
Navy 1507 06 0204162N
Line Item | Name
6120 Initial Spares (Shared)
Notes
Initial spares were procured in FY 2015.

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2003 $M |  |  |  | BY 2003 $M |  | TY $M
| SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E | 578.9 |  | 620.3 | 682.3 |  | 673 |  | 600.3 |  | 648.6 |  | 716.7
Procurement | 949.6 |  | 1040.8 | 1123.7 |  | 1434.41 |  | 1261.1 |  | 1377.6 |  | 1947
Flyaway | -- |  | -- | -- |  | 1322.9 |  | -- |  | -- |  | 1797.5
Recurring | -- |  | -- | -- |  | 1222.5 |  | -- |  | -- |  | 1663.3
Non Recurring | -- |  | -- | -- |  | 100.4 |  | -- |  | -- |  | 134.2
Support | -- |  | -- | -- |  | 111.5 |  | -- |  | -- |  | 149.5
Other Support | -- |  | -- | -- |  | 101.9 |  | -- |  | -- |  | 137.8
Initial Spares | -- |  | -- | -- |  | 9.6 |  | -- |  | -- |  | 11.7
MILCON | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Total | 1528.5 |  | 1661.1 | N/A |  | 2107.4 |  | 1861.4 |  | 2026.2 |  | 2663.7
1 APB Breach
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The Acquisition Program Baseline (APB) cost estimate provides sufficient resources to execute the program under normal conditions, encountering average levels of technical, schedule, and programmatic risk and external interference. Based on the rigor in methods used in building estimates, strong adherence to the collection and use of historical cost information, and review of applied assumptions, the program office projects that it is about as likely the estimate will prove too low or too high for the program as described.
Cost Notes
Costs reflect updated Service Cost Position, approved on June 19, 2012 for FRP.

## Table 14
Total Quantity
Quantity | SAR Baseline Production Estimate | Current APB Production | Current Estimate
RDT&E | 40 | 40 | 40
Procurement | 1879 | 1879 | 2435
Total | 1919 | 1919 | 2475
Quantity Notes
FY 2017 PB increases the total quantity objective from 1,879 to 2,435 AGM-88E AARGM and extends production to 2023. The proposed APB change will reflect the updated quantity profile and budget requirements.

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 701.7 | 12.9 |  |  | 2.1 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 716.7
Procurement | 543.4 | 120.8 |  |  | 178.2 | 222.6 | 222.2 |  | 156.5 |  | 159.6 |  |  | 343.7 |  | 1947
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 1245.1 | 133.7 |  |  | 180.3 | 222.6 | 222.2 |  | 156.5 |  | 159.6 |  |  | 343.7 |  | 2663.7
PB 2016 Total | 1240.1 | 135.2 |  |  | 195.5 | 224.8 | 224.5 |  | 158.8 |  | 0 |  |  | 0 |  | 2178.9
Delta | 5 | -1.5 |  |  | -15.2 | -2.2 | -2.3 |  | -2.3 |  | 159.6 |  |  | 343.7 |  | 484.8
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 40 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 40
Production | 0 |  | 537 |  | 155 | 253 | 336 |  | 322 |  | 183 | 181 |  | 468 |  | 2435
PB 2017 Total | 40 |  | 537 |  | 155 | 253 | 336 |  | 322 |  | 183 | 181 |  | 468 |  | 2475
PB 2016 Total | 40 |  | 507 |  | 138 | 296 | 356 |  | 358 |  | 224 | 0 |  | 0 |  | 1919
Delta | 0 |  | 30 |  | 17 | -43 | -20 |  | -36 |  | -41 | 181 |  | 468 |  | 556

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.6
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.4
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.3
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.6
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.8
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.2
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.6
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.2
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 46.5
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.2
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 84
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 76.2
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 89.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.8
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.2
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.9
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.1
Subtotal |  | 40 | -- |  | -- |  | -- |  | -- |  | -- |  | 716.7

## Table 17
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2003 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.9
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.8
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.7
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.5
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.6
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.6
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.7
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.9
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.2
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 45.9
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 78.6
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 69.2
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 79.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.1
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.7
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.9
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.6
Subtotal |  | 40 | -- |  | -- |  | -- |  | -- |  | -- |  | 673

## Table 18
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | 25 | 32.7 |  | -- |  | 6 |  | 38.7 |  | 2.3 |  | 41
2009 |  | 4 | 16.8 |  | -- |  | 1.1 |  | 17.9 |  | 7.7 |  | 25.6
2010 |  | 36 | 39.5 |  | -- |  | 1 |  | 40.5 |  | 10.2 |  | 50.7
2011 |  | 47 | 42 |  | -- |  | 4 |  | 46 |  | 6.6 |  | 52.6
2012 |  | 82 | 66.1 |  | -- |  | 9.4 |  | 75.5 |  | 8.4 |  | 83.9
2013 |  | 96 | 67.4 |  | -- |  | 14.3 |  | 81.7 |  | 4.1 |  | 85.8
2014 |  | 116 | 82.1 |  | -- |  | 8.4 |  | 90.5 |  | 3.6 |  | 94.1
2015 |  | 131 | 94.2 |  | -- |  | 8.6 |  | 102.8 |  | 6.9 |  | 109.7
2016 |  | 155 | 104.9 |  | -- |  | 12 |  | 116.9 |  | 3.9 |  | 120.8
2017 |  | 253 | 159.5 |  | -- |  | 9.6 |  | 169.1 |  | 9.1 |  | 178.2
2018 |  | 336 | 196.1 |  | -- |  | 9.8 |  | 205.9 |  | 16.7 |  | 222.6
2019 |  | 322 | 191.7 |  | -- |  | 10 |  | 201.7 |  | 20.5 |  | 222.2
2020 |  | 183 | 125.5 |  | -- |  | 10.2 |  | 135.7 |  | 20.8 |  | 156.5
2021 |  | 181 | 128.4 |  | -- |  | 10.4 |  | 138.8 |  | 20.8 |  | 159.6
2022 |  | 277 | 179.2 |  | -- |  | 10.7 |  | 189.9 |  | 4.3 |  | 194.2
2023 |  | 191 | 137.2 |  | -- |  | 8.7 |  | 145.9 |  | 3.6 |  | 149.5
Subtotal |  | 2435 | 1663.3 |  | -- |  | 134.2 |  | 1797.5 |  | 149.5 |  | 1947

## Table 19
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | BY 2003 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | 25 | 28.2 |  | -- |  | 5.1 |  | 33.3 |  | 2 |  | 35.3
2009 |  | 4 | 14.3 |  | -- |  | 0.9 |  | 15.2 |  | 6.5 |  | 21.7
2010 |  | 36 | 33 |  | -- |  | 0.8 |  | 33.8 |  | 8.5 |  | 42.3
2011 |  | 47 | 34.4 |  | -- |  | 3.3 |  | 37.7 |  | 5.4 |  | 43.1
2012 |  | 82 | 53.4 |  | -- |  | 7.5 |  | 60.9 |  | 6.8 |  | 67.7
2013 |  | 96 | 53.6 |  | -- |  | 11.4 |  | 65 |  | 3.3 |  | 68.3
2014 |  | 116 | 64.4 |  | -- |  | 6.7 |  | 71.1 |  | 2.8 |  | 73.9
2015 |  | 131 | 72.8 |  | -- |  | 6.6 |  | 79.4 |  | 5.4 |  | 84.8
2016 |  | 155 | 79.7 |  | -- |  | 9.1 |  | 88.8 |  | 3 |  | 91.8
2017 |  | 253 | 119 |  | -- |  | 7.1 |  | 126.1 |  | 6.8 |  | 132.9
2018 |  | 336 | 143.5 |  | -- |  | 7.2 |  | 150.7 |  | 12.1 |  | 162.8
2019 |  | 322 | 137.5 |  | -- |  | 7.2 |  | 144.7 |  | 14.7 |  | 159.4
2020 |  | 183 | 88.2 |  | -- |  | 7.2 |  | 95.4 |  | 14.6 |  | 110
2021 |  | 181 | 88.5 |  | -- |  | 7.2 |  | 95.7 |  | 14.3 |  | 110
2022 |  | 277 | 121.1 |  | -- |  | 7.3 |  | 128.4 |  | 2.9 |  | 131.3
2023 |  | 191 | 90.9 |  | -- |  | 5.8 |  | 96.7 |  | 2.4 |  | 99.1
Subtotal |  | 2435 | 1222.5 |  | -- |  | 100.4 |  | 1322.9 |  | 111.5 |  | 1434.4

## Table 20
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2008-09-30 | 2011-01-18
Approved Quantity | 187 | 112
Reference | Milestone C ADM | Gate 6 Sufficiency Review
Start Year | 2008 | 2008
End Year | 2010 | 2011
Milestone C ADM of September 30, 2008 originally granted LRIP authority utilizing FY 2008 - FY 2010 funding, with a not-to- exceed quantity of 187 units. Deliveries for Phase I of LRIP, utilizing FY 2008 and FY 2009 funding, completed in October 2011. Deliveries for LRIP II, a Firm-Fixed-Price (FFP) contract utilizing FY 2010 funding, completed November 2012. Due to delays in Initial Operational Test & Evaluation, and to avoid a production line break, the incorporation of a third LRIP into the AGM-88E AARGM Acquisition Strategy, utilizing FY 2011 funding, was approved on January 18, 2011 by the Assistant Secretary of the Navy (Research, Development, and Acquisition) at the Gate 6 Sufficiency Review. The total LRIP quantity remained under the not-to-exceed quantity of 187 units, which does not exceed the 10% guideline. The LRIP III FFP contract was awarded on October 31, 2011 at the Government's cost goal. Deliveries for LRIP III began in December 2012 and completed in December 2013.

## Table 21
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Australia | 2015-07-23 | 14 | 11.7 | Letter of Offer and Acceptance between the United States and Australia was amended on July 23, 2015 for the procurement of additional AGM-88E AARGM All Up Rounds and spares under FMS Case AT-P- AZN. The missiles are expected to deliver in FY 2017.
Australia | 2013-05-31 | 11 | 37.1 | Letter of Offer and Acceptance between the United States and Australia was signed on May 31, 2013 establishing FMS Case AT-P-AZN for the procurement of AGM-88E AARGM Captive Air Training Missiles, spares and support. The missiles and spares were delivered in FY 2015 with support continuing through FY 2018.
Italy | 2005-11-15 | 181 | 132.6 | Cooperative Development Memorandum of Agreement (MOA) between Italy and the United States was signed on November 15, 2005. Cooperative Production, Sustainment and Follow- on Development MOA between Italy and the United States was signed on November 18, 2009. The quantity of 181 represents the total estimated number of missiles that Italy is expected to receive through Full Rate Production.
Notes
Nuclear Costs
None

## Table 22
Unit Cost
Unit Cost Report
Item |  | BY 2003 $M |  | BY 2003 $M |  |  | % Change
|  | Current UCR Baseline (Nov 2012 APB) |  | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1661.1 |  |  |  |  | 2107.4
Quantity | 1919 |  |  |  |  | 2475
Unit Cost | 0.866 |  |  |  |  | 0.851 |  |  | -1.73
Average Procurement Unit Cost
Cost | 1040.8 |  |  |  |  | 1434.4
Quantity | 1879 |  |  |  |  | 2435
Unit Cost | 0.554 |  |  |  |  | 0.589 |  |  | 6.32
Item |  | BY 2003 $M | BY 2003 $M |  |  |  | % Change
|  | Original UCR Baseline (Jul 2003 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1339.8 |  |  |  | 2107.4
Quantity | 1790 |  |  |  | 2475
Unit Cost | 0.748 |  |  |  | 0.851 |  |  | 13.77
Average Procurement Unit Cost
Cost | 806.5 |  |  |  | 1434.4
Quantity | 1750 |  |  |  | 2435
Unit Cost | 0.461 |  |  |  | 0.589 |  |  | 27.77

## Table 23
Unit Cost History
Item | [7 empty] | Date |  |  |  | BY 2003 $M | [6 empty] | TY $M
[12 empty] | PAUC |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Jul 2003 | [6 empty] | 0.748 |  |  |  | 0.461 |  |  |  | 0.844 |  |  |  | 0.556
APB as of January 2006 |  |  |  |  | Jul 2003 | [6 empty] | 0.748 |  |  |  | 0.461 |  |  |  | 0.844 |  |  |  | 0.556
Revised Original APB |  |  |  |  | N/A | [6 empty] | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | Nov 2011 | [6 empty] | 0.797 |  |  |  | 0.505 |  |  |  | 0.97 |  |  |  | 0.671
Current APB |  |  |  |  | Nov 2012 | [6 empty] | 0.866 |  |  |  | 0.554 |  |  |  | 1.056 |  |  |  | 0.733
Prior Annual SAR |  |  |  |  | Dec 2014 | [6 empty] | 0.925 |  |  |  | 0.587 |  |  |  | 1.135 |  |  |  | 0.779
Current Estimate |  |  |  |  | Dec 2015 | [6 empty] | 0.851 |  |  |  | 0.589 |  |  |  | 1.076 |  |  |  | 0.8
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [20 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth |  | Spt |  |  | Total
0.844 0.039 -0.026 0.028 0.010 0.053 0.000 0.022 0.126 0.970
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [18 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng | Est |  | Oth | Spt |  |  | Total
0.970 -0.014 -0.054 0.049 0.032 0.081 0.000 0.012 0.106 1.076

## Table 24
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [10 empty] | APUC Production Estimate
| Econ | Qty |  |  | Sch | Eng |  | Est | Oth | Spt | Total
0.556 0.033 -0.006 0.026 0.000 0.039 0.000 0.023 0.115 0.671
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [10 empty] | APUC Current Estimate
| Econ |  | Qty |  | Sch | Eng |  | Est | Oth | Spt | Total
0.671 -0.015 0.015 0.049 0.000 0.068 0.000 0.012 0.129 0.800
SAR Baseline History
Item |  |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Milestone B |  |  |  | N/A |  |  | Apr 2003 |  |  | Apr 2003 |  |  | Jun 2003
Milestone C |  |  |  | N/A |  |  | Mar 2008 |  |  | Mar 2008 |  |  | Sep 2008
IOC |  |  |  | N/A |  |  | May 2010 |  |  | Nov 2010 |  |  | Jul 2012
Total Cost (TY $M) |  |  |  | N/A |  |  | 1510.9 |  |  | 1861.4 |  |  | 2663.7
Total Quantity |  |  |  | N/A |  |  | 1790 |  |  | 1919 |  |  | 2475
PAUC |  |  |  | N/A |  |  | 0.844 |  |  | 0.97 |  |  | 1.076

## Table 25
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
600.3 1261.1 -- 1861.4
Economic |  | 0.1 |  | -26.9 |  | -- |  | -26.8
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 114.2 |  | -- |  | 114.2
Engineering |  | 79.5 |  | -- |  | -- |  | 79.5
Estimating |  | 34.8 |  | 166.3 |  | -- |  | 201.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -50.5 |  | -- |  | -50.5
Subtotal |  | 114.4 |  | 203.1 |  | -- |  | 317.5
Current Changes Economic |  | -- |  | -8.9 |  | -- |  | -8.9
Quantity |  | -- |  | 407.5 |  | -- |  | 407.5
Schedule |  | 2.1 |  | 5.1 |  | -- |  | 7.2
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -0.1 |  | -0.8 |  | -- |  | -0.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 79.9 |  | -- |  | 79.9
Subtotal |  | 2 |  | 482.8 |  | -- |  | 484.8
Total Changes |  | 116.4 |  | 685.9 |  | -- |  | 802.3
CE - Cost Variance |  | 716.7 |  | 1947 |  | -- |  | 2663.7
CE - Cost & Funding |  | 716.7 |  | 1947 |  | -- |  | 2663.7

## Table 26
Summary BY 2003 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
578.9 949.6 -- 1528.5
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 66.8 |  | -- |  | 66.8
Engineering |  | 64.2 |  | -- |  | -- |  | 64.2
Estimating |  | 28.4 |  | 122.7 |  | -- |  | 151.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -36.4 |  | -- |  | -36.4
Subtotal |  | 92.6 |  | 153.1 |  | -- |  | 245.7
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 274.7 |  | -- |  | 274.7
Schedule |  | 1.6 |  | 3.1 |  | -- |  | 4.7
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -0.1 |  | -2.9 |  | -- |  | -3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 56.8 |  | -- |  | 56.8
Subtotal |  | 1.5 |  | 331.7 |  | -- |  | 333.2
Total Changes |  | 94.1 |  | 484.8 |  | -- |  | 578.9
CE - Cost Variance |  | 673 |  | 1434.4 |  | -- |  | 2107.4
CE - Cost & Funding |  | 673 |  | 1434.4 |  | -- |  | 2107.4
Previous Estimate: December 2014

## Table 27
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised estimate in FY 2017 due to rephrasing of Block 1 software for additional activities with fielding. (Schedule)
+1.6 +2.1
Revised estimate in FY 2015 to reflect resource budget adjustment. (Estimating) -0.1 -0.1
RDT&E Subtotal +1.5 +2.0
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -8.9
Additional quantity variance resulting from an increase of 556 AGM-88E AARGM missiles from 1,879 to 2,435. (Subtotal)
Additional quantity variance resulting from an increase of 556 AGM-88E AARGM missiles from 1,879 to 2,435. (Quantity)
+206.3 +306.3
(+198.6) (+294.9)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) (+3.1) (+4.6)
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (+4.6) (+6.8) Additional increase in Recurring Fly Away for FY 2021- FY 2023. (Quantity) +41.3 +61.0
Additional schedule variance due to procurement buy profile being extended three years (FY 2021 - FY 2023). (Quantity)
Stretch-out of procurement buy profile due to being extended three years (FY 2013 - FY 2021). (Schedule)
+34.8 +51.6
0.0 +0.5
Revised estimate to reflect budget reductions across the FYDP. (Estimating) | -17.3 |  | -20.9
Revised estimate to reflect FY 2013 actuals. (Estimating) | 1.5 |  | 1.9
Adjustment for current and prior escalation. (Estimating) | 1.8 |  | 2.5
Revised estimate to reflect the application of new out year escalation indices. (Estimating) | 6.5 |  | 8.9
Increase in other support due to telemetry kit requirement for FY 2017- FY 2021. (Support) | 54.1 |  | 76.6
Increase to reflect revised estimate of initial spares. (Support) (QR) | 2.5 |  | 3.2
Adjustment for current and prior escalation. (Support) | 0.2 |  | 0.1
Procurement Subtotal (QR) Quantity Related | 331.7 |  | 482.8

## Table 28
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: AARGM FRP 4/5
Contractor: Orbital Alliant TechSystems (OATK)
Contractor Location: 9401 Corbin Avenue
Los Angeles, CA 91324
Contract Number: N00019-15-C-0123
Contract Type: Firm Fixed Price (FFP)
Award Date: September 03, 2015
Definitization Date: September 03, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
118.7 N/A 154 118.7 N/A 154 252.2 252.2
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This is the first time this contract is being reported.
The contract current value of $118.7M includes $11.3M of Italian requirements for fourteen All Up Rounds and $11.7M of Royal Australian Air Force (RAAF) requirements for fourteen All Up Rounds and three spares.
The difference between the Initial Contract Price and the Estimated Price At Completion includes an estimated $133.5M for the FRP 5 Option Award planned for May 2016.

## Table 29
Contract Identification
Appropriation: Procurement
Contract Name: AARGM FRP 2/3
Contractor: Orbital Alliant TechSystems (OATK)
Contractor Location: 9401 Corbin Avenue
Los Angeles, CA 91324
Contract Number: N00019-13-C-0162
Contract Type: Firm Fixed Price (FFP)
Award Date: September 25, 2013
Definitization Date: September 25, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
102.4 N/A 123 201.2 N/A 248 201.2 201.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the subsequent exercise of the FRP 3 Option (USN/ITAF). The United States Navy (USN) quantities were awarded on April, 23 2014, for
$83.9M. The Italian Air Force (ITAF) quantities were awarded on August 7, 2014, for $12.7M. An additional $2.2M in funds were provided to execute Engineering Change Proposals and Life Of Type procurements for obsolete parts.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 30
Contract Identification
Appropriation: Procurement
Contract Name: AARGM FRP 1
Contractor: Orbital Alliant TechSystems (OATK)
Contractor Location: 9401 Corbin Avenue
Los Angeles, CA 91324
Contract Number: N00019-12-C-0113
Contract Type: Firm Fixed Price (FFP)
Award Date: September 10, 2012
Definitization Date: September 10, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
70.6 N/A 72 79.9 N/A 81 79.9 79.9
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the subsequent exercise of option contract line item number for Italian units due to late receipt of funds. An additional $3.2M in Italian funding was added for this effort. An additional $2.6M in funds were also provided to incorporate Statement of Work for Stage 2 of the Front End Assembly Transition Plan. An additional $3.5M in funds were provided to execute Cost Improvement Initiatives, Engineering Change Proposals and Life Of Type procurements for obsolete parts.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
The contract current value of $79.9M includes $8.79M of Italian requirements for seven All Up Rounds, two Captive Air Training Missiles, and contractor production support.
The quantity reflects United States and Italian quantities.
The initial contract quantity (76) was incorrectly reported in the December 2014 SAR; 72 is the correct initial contract quantity.

## Table 31
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 40 | 40 | 40 | 100%
Production | 2435 | 251 | 2435 | 10.31%
Total Program Quantity Delivered | 2475 | 291 | 2475 | 11.76%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
2663.7
1077.8
40.46%
31
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
24
77.42%
1378.8
51.76%
The above data is current as of February 09, 2016.
The 40 assets procured under the development phase are not fleet representative assets, and are not reflected in the AARGM sustainment strategy.

## Table 32
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 08, 2016
Source of Estimate: POE
Quantity to Sustain: 2435
Unit of Measure: Total Quantity
Service Life per Unit: 15.00 Years
Fiscal Years in Service: FY 2012 - FY 2039
The estimate concentrates on the costs for AGM-88E AARGM unique components. AGM-88E AARGM has a 60 month Serviceable In-Service Time Maintenance and Reliability Monitoring Program. The total quantity of missiles to be procured is 2435. Weapon service life is 15 years per AGM-88E AARGM All Up Round. The O&S life is 29 years. The planned last production lot buy is FY 2023. The last unit delivery would be FY 2024 with a corresponding service life assumption through FY 2039. The 2435 quantity to sustain does not include 40 developmental assets that are not maintained.
Sustainment Strategy
The AGM-88E AARGM sustainment approach is leveraged off of the existing High Speed Anti-Radiation Missile (HARM) maintenance structure. The system is supported via a modified three level maintenance concept utilizing Organizational (O), Intermediate (I), Depot levels and a Designated Overhaul Point (DOP) for the AGM-88E AARGM
unique components (guidance and control sections). The Original Equipment Manufacturer is the DOP for guidance and control section repair based on the completed Joint Depot Source of Repair Decision process. There are no changes to the manpower requirements or manning levels at activities that will operate and provide support to AGM-88E AARGM as O-level and I-level; capabilities are consistent with the HARM operations.
Antecedent Information
Antecedent is the HARM. Data is based on a HARM period of performance of FY 1990 - FY 2009 (20 years), vice FY 2011
- FY 2039 (29 years) for AARGM. Historical O&S costs were collected from the Naval Visibility & Management of Operating and Support Costs database. Antecedent costs are not normalized to the AGM-88E AARGM parameters.
Annual O&S Costs BY2003 $M
Cost Element | AGM-88E AARGM Average Annual Cost Per Total Quantity | AGM-88 HARM (Antecedent) Average Annual Cost Per Total Quantity
Unit-Level Manpower | 0 | 0
Unit Operations | 0 | 0
Maintenance | 0.59 | 1.8
Sustaining Support | 3.3 | 1.7
Continuing System Improvements | 1.71 | 1.6
Indirect Support | 0 | 0
Other | 0 | 0
Total | 5.6 | 5.1

## Table 33
Item | Total O&S Cost $M
| AGM-88E AARGM | [6 empty] | AGM-88 HARM (Antecedent)
| Current Production APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year |  | 142.6 |  | 156.9 |  |  | 162.61 |  | 101.3
Then Year 1 APB O&S Cost Breach |  | 215.8 |  | N/A |  |  | 254.8 |  | N/A
Note 1 APB Breach Explanation: The FY 2017 PB increases the total quantity objective from 1,879 to 2,435 AGM-88E AARGM and extends production to 2023. The proposed APB change will reflect the updated quantity profile and O&S Cost.
Equation to Translate Annual Cost to Total Cost
Total Cost / Total Years of Service = Annual Cost
$162.6M / 29 years = $5.6M per year
O&S Cost Variance
Category |  |  | BY 2003 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
142.6
Programmatic/Planning Factors 20.0 Increase quantity and increase production schedule. O&S
period of performance extended by three years.
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 20.0
Current Estimate 162.6
Disposal Estimate Details
Date of Estimate: January 08, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2003 $M): Total costs for disposal of all Total Quantity are 8.6
Increase quantity profile of 556 missiles will support Fleet training; missiles are anticipated to be expended through additional Fleet firings. No further disposal costs are planned.