## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-582
Cooperative Engagement Capability (CEC)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 12
Track to Budget 14
Cost and Funding 17
Low Rate Initial Production 31
Foreign Military Sales 32
Nuclear Costs 32
Unit Cost 33
Cost Variance 36
Contracts 40
Deliveries and Expenditures 45
Operating and Support Cost 46

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Cooperative Engagement Capability (CEC)
DoD Component
Navy
Joint Participants
United States Marine Corps; United States Air Force; United States Army
Responsible Office
CAPT Joseph Reason Program Executive Office Integrated Warfare Systems 1333 Isaac Hull Avenue, S.E. Washington, DC 20376-4401
joseph.reason@navy.mil
Phone: | 202-781-2029
Fax: | 202-781-4752
DSN Phone: | 326-2029
DSN Fax: | 326-4752
Date Assigned: | June 27, 2012
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 3, 2002
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated June 16, 2004

## Table 6
Mission and Description
Mission
The Cooperative Engagement Capability (CEC) increases overall Naval Air Defense capabilities by integrating sensors and weapon assets into a single, integrated, real-time network which expands the battlespace; enhances situational awareness; increases depth of fire and enables longer intercept ranges; and improves decision and reaction times.
Description
CEC is a real-time sensor netting system that enables high quality situational awareness and Integrated Fire Control (IFC) capability, which revolutionizes Naval Air Defense by providing improved accuracy, continuity, and identification consistency. This sensor netting system significantly improves Naval Carrier and Expeditionary Strike Group's Area Air
Defense capabilities by extracting and distributing sensor-derived information such that the superset of this data is available to all participating CEC Cooperating Units (CUs). CEC fuses the distributed data from shipboard, airborne, Composite Tracking Network (CTN) ground mobile units, Joint Land Attack Cruise Missile Defense Elevated Netted Sensor System (JLENS), and select coalition partners into a single fire control quality air track picture. Radar measurement data from individual CUs within a CEC equipped force are transmitted to other CUs using the Line-Of-Sight Data Distribution System. A variety of automated network configurations are possible since CEC terminals provide highly directional, point-to-point data exchanges.
The CEC system distributes data between sensor and weapon assets to create a single, distributed, integrated air picture that supports and enables IFC. Individual sensors on all platforms in a CEC network are used in a cooperative manner as a distributed system to obtain track information to form a single, real-time composite track. This real-time composite tracking enables CEC to support Theater Air and Missile Defense allowing coordination of Naval and Joint sensor system assets among CEC-equipped ships, aircraft, and land platforms and joint operational access to engage cruise missiles that threaten joint forces in a denied access environment.
CEC consists of the following variants:
AN/USG-2: Shipboard designation of CEC deployed aboard the Aegis Guided Missile Cruisers (CG), Aegis Guided Missile Destroyers (DDG), Aircraft Carriers (CVN) and Amphibious Transport Dock (LPD)/Amphibious Assault (LHD) ships
AN/USG-3: Airborne designation of CEC deployed in E-2C and E-2D aircraft
AN/USG-4: United States Marine Corps (USMC) CTN platform
AN/USG-5: United States Army JLENS platform
AN/USG-6/7/8/10: FMS
AN/USG-9: CEC with USMC Common Aviation Command and Control System

## Table 7
Executive Summary
The CEC program achieved a Milestone III FRP decision in April 2002 for the AN/USG-2 shipboard variant and is continuing development efforts to keep pace with the security threats and ensure producibility. The program remains focused on ensuring compatibility, appropriate maintenance, and ultimate disposal.
The Assistant Secretary of the Navy (Research, Development and Acquisition) Memorandum for PEO for Integrated Warfare Systems, dated April 14, 2014, authorized FRP for the CEC AN/USG-3B (E-2D Airborne Variant) System in support of E-2D Advanced Hawkeye FRP.
The CEC program has developed a three phase approach to resolve interoperability issues.
• Phase 1 - Near Term of the Track File Concurrence software updates to resolve software shortfalls discovered during Development Test (DT-IIID)/Operational Test (OT-IIIF) testing for the CEC AN/USG-3B (E-2D Airborne Variant) System were fielded in FY 2014.
• Phase 2 - Accelerated Mid-Term Interoperability Improvement Project (AMIIP) (FY 2011 - FY 2019) corrects interoperability, including Dual Tracks improvements, and is certified within Aegis, Ship Self Defense System, and E- 2C Hawkeye 2000 combat systems. Fleet delivery of AMIIP to Aegis Cruisers and Destroyers is ongoing. E-2C fielding is complete. E-2D AMIIP development has started and delivery is planned in FY 2019. AMIIP design was included in Common Aviation Command and Control System (CAC2S) Phase 2 during the design phase. CAC2S Phase 2 is conducting DT now, with OT scheduled in second quarter FY 2016. DDG 1000 has not included the AMIIP features in their design and there is no plan to include AMIIP in DDG 1000.
• Phase 3 – Far Term Interoperability Improvement Project (Far Term Host Combat System Design Changes) are in early planning stages and will be influenced by the results obtained from AMIIP. There is no funding allocated beyond FY 2016. However, Program Objective Memorandum (POM) issues were submitted in POM 16, POM 17 and POM 18 for the Far Term Interoperability Improvement Project efforts.
The RDT&E FY 2016 Congressional reduction will delay the development of the Common Array Block antenna that replaces Planar Array Antenna Assembly (PAAA) antennas. This reduction will cause a four-month delay in the delivery of the Common Array Block Functional Design Package for Aegis Flight III ships which will compromise the Flight III schedule.
CEC will not be able to produce PAAA antennas beyond FY 2016 and an additional program cost of $14M will be incurred in order to qualify a second vendor for PAAA antennas, if necessary.
CEC continues to follow an evolutionary acquisition process, delivering capability in increments of hardware and/or software upgrades. This evolutionary approach acknowledges the need for future capability improvements to pace evolutionary trends.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
The breach to RDT&E was previously reported in the December 2011 SAR and will not be cleared, as the Single Integrated Air Picture aspect of our program was removed.
APB will be updated 30 days after the CPD is approved.
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule

## Table 10
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone II | May 1995 | May 1995 | Nov 1995 | May 1995
Development Contract Modification | May 1995 | May 1995 | Nov 1995 | May 1995
Preliminary Design Review Complete | Feb 1996 | Feb 1996 | Aug 1996 | Jul 1996
Baseline System Initial Operational Capability | Sep 1996 | Sep 1996 | Mar 1997 | Sep 1996
Critical Design Review Complete | Aug 1996 | Aug 1996 | Feb 1997 | Dec 1996
IOT&E (DT-IIB/OT-IIA1)
Start | May 1997 | May 1997 | Nov 1997 | May 1997
Complete | Aug 1997 | Aug 1997 | Feb 1998 | Aug 1997
LRIP Decision | Dec 1997 | Dec 1997 | Jun 1998 | Feb 1998
Low Rate Production Contract Award | Apr 1998 | Apr 1998 | Oct 1998 | Apr 1998
Service Depot Support Date | Oct 2000 | Oct 2000 | Apr 2001 | Oct 2000
Service Final DT&E
Start | Jul 2000 | Jul 2000 | Jan 2001 | Jan 2001
Complete | Nov 2000 | Nov 2000 | May 2001 | May 2001
IOT&E - OPEVAL (OT-IIA2)
Start | Sep 2000 | Sep 2000 | Mar 2001 | Mar 2001
Complete | Nov 2000 | Nov 2000 | May 2001 | May 2001
Organic Support Date | Oct 2001 | Oct 2001 | Apr 2002 | Oct 2001
FOT&E-1 (DTIIIA/OT-IIIA)E-2C
Start | Jan 2002 | Jan 2002 | Jul 2002 | Jan 2002
Complete | Aug 2002 | Nov 2002 | May 2003 | Nov 2002
Milestone III | Apr 2002 | Apr 2002 | Oct 2002 | Apr 2002
Full Rate Production Contract Award | May 2002 | May 2002 | Nov 2002 | Apr 2002
FOT&E-2 (DTIIIB/OT-IIIB)E-2C
Start | Mar 2003 | Mar 2004 | Sep 2004 | Mar 2004
Complete | Jul 2003 | Apr 2004 | Oct 2004 | Apr 2004
Full Operational Capability | Dec 2003 | Nov 2004 | May 2005 | May 2005
Airborne IOC | Dec 2003 | Nov 2004 | May 2005 | May 2005
Change Explanations
None

## Table 11
Acronyms and Abbreviations
DT - Developmental Test
DT&E - Developmental Test and Evaluation FOT&E - Follow-on Test and Evaluation IOT&E - Initial Operational Test and Evaluation OPEVAL - Operational Evaluation
OT - Operational Test

## Table 12
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Operational Availability
>=.95 | >=.95 | >=.90 | >=.89 | >=.91
Interoperability
Information Exchange Requirements (IER)
100% of top-level IERs | 100% of top-level IERs. | 100% of top-level IERs designated critical | 100% of top-level IERs designated critical | 100% of top-level IERs designated critical
Track File Consistency
Integration will improve track file consistency in each host system | CEC integration will improve track file consistency as measured in each host system | CEC integration must not degrade track file consistency (0% degradation)as measured in each host system | CEC integration will improve track file consistency as measured in each host system | CEC integration will improve track file consistency in each host system
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
ORD dated January 31, 2002 and ORD Change 1 dated January 31, 2011
Change Explanations
None
Notes
The AN/USG-2/2A legacy shipboard systems Demonstrated Performance changed from 0.91 to 0.89 due to an increase in MDT resulting from aging assemblies including the Antenna Environmental Control Units which are beyond their intended service life. AN/USG-2/2A re-utilization assets made available from AN/USG-2B back fits are being used to minimize MDT. The AN/USG-2/2A systems are being backfitted with the AN/USG-2B systems and will no longer be in use after CY 2020. The AN/USG-2B will start reporting sustainment metrics by mid FY 2016.
The following Demonstrated Performance for the AN/USG-3 and AN/USG-3B is provided since the Performance characteristics table above only identifies the AN/USG-2/2A Demonstrated Performance.
The AN/USG-3 Demonstrated Performance of 0.61 is due to extended MDT resulting directly from the Naval Sea Systems Command's lack of funding and Naval Supply Systems Command contracting issues with Raytheon, the Original Equipment Manufacturer, since the NAVSUP Performance Based Logistics contract expired in April 2012. The MDT is expected to decrease over time since NAVSUP signed a repair BOA on December 8, 2014 with Raytheon and NAVSEA has a repair BOA in place with Raytheon.

## Table 13
The AN/USG-3B Demonstrated Performance is 0.95. The AN/USG-3B is the latest airborne system. The AN/USG-3 legacy airborne system is being retired and will no longer be in use after CY 2023.
Acronyms and Abbreviations
BOA - Basic Order Agreement
IER - Information Exchange Requirements MDT - Mean Down Time
NAVSUP - Naval Supply Systems Command

## Table 14
Track to Budget
General Notes
All APPNs and PEs have been updated to align with FY 2017 PB values.
Program element 0607658N Project 2039 CEC RDT&E established as of FY 2017 PB. Program element 0603658N Project 2039 CEC RDT&E reported as sunk as of FY 2017 PB.
Program element 0204228N Line Item 0900 DDG Modernization OPN reported as sunk as of FY 2017 PB. Program element 0206313M Line Item 4644 PMC established as of FY 2017 PB.
RDT&E
Appn |  | BA | PE
Navy | 1319 07 |  | 0206313M
| Project |  | Name
| 2273 |  | Marine Corps Communication (Shared) Systems/Marine Corps Communication Systems
| Notes: |  | Shared with Composite Tracking Network
Navy | 1319 04 |  | 0603658N
| Project |  | Name
| 2039 |  | COOP Engagement (Sunk)
| Notes: |  | Reported Sunk as of FY 2017 PB.
| 2616 |  | Cooperative Engagement (Sunk) Capability (CEC)
Navy | 1319 05 |  | 0604234N
| Project |  | Name
| 3051 |  | E2-D Advanced Hawkeye (Shared) (Sunk)
| Notes: |  | Shared with Advanced Hawkeye Program
| 5EJ |  | E2-D Advanced Hawkeye (Shared) (Sunk)
| Notes: |  | Shared with Advanced Hawkeye Program
Navy | 1319 07 |  | 0607658N
| Project |  | Name
| 2039 |  | COOP Engagement
Army | 2040 07 |  | 0102419A
| Project |  | Name
| E55 |  | Joint Aero Stat Program EMD (Shared) (Sunk) Effort
| Notes: |  | Shared with Joint Land Attack Cruise Missile Defense Elevated Netted Sensor System
Procurement
Appn |  | BA | PE

## Table 15
Navy 1109 04 0206313M
Line Item | Name
4640 Air Operations C2 Systems (Shared)
Notes: Shared with Composite Tracking Network
4644 Common Aviation Command and Control System (CAC2S)
(Shared)
Notes: Shared with Composite Tracking Network
Navy 1506 01 0204152N
Line Item | Name
0195 E-2D Adv Hawkeye (Shared)
Notes: Shared with E-2C Hawkeye
Navy 1611 02 0204112N
Line Item | Name
2001 Carrier Replacement Program (Shared) (Sunk)
Notes: Shared with CVN Replacement Program 2086 CVN Refueling Overhauls (Shared)
Notes: Shared with Refueling Complex Overhaul
Navy 1611 05 0204228N
Line Item | Name
2119 DDG 1000 (Shared) (Sunk)
Notes: Shared with DDG 1000 Program
Navy 1611 02 0204222N
Line Item | Name
2119 DDG 1000 (Shared) (Sunk)
Notes: Shared with DDG 1000 Program
2122 DDG-51 (Shared)
Notes: Shared with DDG-51 Program
Navy 1611 03 0204411N
Line Item | Name
3035 LHD-1 (Shared) (Sunk)
Notes: Shared with Amphibious Assault Ships 3036 LPD-17 (Shared)
Notes: Shared with Amphibious Assault Ships
3041 LHA Replacement (Shared)
Notes: Shared with Amphibious Assault Ships
Navy 1810 01 0204228N
Line Item | Name
0900 DDG Modernization (Shared) (Sunk)
Notes: Shared with DDG Modernization Program - Reported as sunk as of 2017 PB.
Navy 1810 01 0204162N
Line Item | Name
0960 CG Modernization (Shared)

## Table 16
Notes: Shared with Cruiser Modernization Program.
Navy 1810 02 0204228N
Line Item | Name
2606 Cooperative Engagement Capability (CEC)
Navy 1810 02 0204221N
Line Item | Name
2606 Cooperative Engagement Capability (CEC)
(Sunk)

## Table 17
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2002 $M | [5 empty] | BY 2002 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  |  | Current APB Production Objective |  | Current Estimate
RDT&E | 2028.1 |  |  | 2435.7 | 2679.3 |  |  | 2985.91 |  | 1946.5 |  |  |  | 2394.3 |  | 3171.2
Procurement | 2095.2 |  |  | 2095.2 | 2304.7 |  |  | 1751.6 |  | 2364.2 |  |  |  | 2364.2 |  | 2127.9
Flyaway | -- |  |  | -- | -- |  |  | 1516.6 |  | -- |  |  |  | -- |  | 1824.1
Recurring | -- |  |  | -- | -- |  |  | 1516.6 |  | -- |  |  |  | -- |  | 1824.1
Non Recurring | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  |  | -- |  | 0
Support | -- |  |  | -- | -- |  |  | 235 |  | -- |  |  |  | -- |  | 303.8
Other Support | -- |  |  | -- | -- |  |  | 235 |  | -- |  |  |  | -- |  | 303.8
Initial Spares | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  |  | -- |  | 0
MILCON | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Total APB Breach | 4123.3 |  |  | 4530.9 | N/A |  |  | 4737.5 |  | 4310.7 |  |  |  | 4758.5 |  | 5299.1
RDT&E | 16 | [6 empty] | 27 |  |  |  | 30
Procurement | 256 | [6 empty] | 256 |  |  |  | 253
Total | 272 | [6 empty] | 283 |  |  |  | 283
1
Total Quantity
Quantity |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate

## Table 18
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 2631 | 74.9 |  |  | 88 | 91.1 | 97.6 |  | 93.6 |  | 95 |  | 0 |  |  | 3171.2
Procurement | 1516.2 | 84.8 |  |  | 66.1 | 90.7 | 64 |  | 62.3 |  | 68.7 |  | 175.1 |  |  | 2127.9
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0
PB 2017 Total | 4147.2 | 159.7 |  |  | 154.1 | 181.8 | 161.6 |  | 155.9 |  | 163.7 |  | 175.1 |  |  | 5299.1
PB 2016 Total | 4105.2 | 127.9 |  |  | 152.4 | 150.1 | 140.4 |  | 137.6 |  | 24.6 |  | 56.6 |  |  | 4894.8
Delta | 42 | 31.8 |  |  | 1.7 | 31.7 | 21.2 |  | 18.3 |  | 139.1 |  | 118.5 |  |  | 404.3
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 30 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 30
Production | 0 |  | 173 |  | 13 | 11 | 13 |  | 8 |  | 6 | 7 |  | 22 |  | 253
PB 2017 Total | 30 |  | 173 |  | 13 | 11 | 13 |  | 8 |  | 6 | 7 |  | 22 |  | 283
PB 2016 Total | 30 |  | 171 |  | 8 | 11 | 10 |  | 7 |  | 6 | 6 |  | 15 |  | 264
Delta | 0 |  | 2 |  | 5 | 0 | 3 |  | 1 |  | 0 | 1 |  | 7 |  | 19

## Table 19
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 203.2
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 154.1
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 256.4
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 224.7
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 200.8
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 189.8
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 179.8
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 173.4
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 106.7
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 107.1
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 91.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 114
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 99.8
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 55
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 53.4
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44.2
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 60
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 52.5
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 60
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42.6
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 74.9
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 88
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 91.1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 97.6
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 93.6
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 95
Subtotal |  | 22 | -- |  | -- |  | -- |  | -- |  | -- |  | 3134.2

## Table 20
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2002 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 224.2
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 166.8
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 272.9
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 236.3
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 209.4
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 195.7
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 182.7
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 173.8
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 105.9
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 104.7
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 86.7
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 105.7
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 89.7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.3
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 46
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.6
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 55.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.8
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.8
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.1
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.1
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57.2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 67
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 70.4
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66.2
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.9
Subtotal |  | 22 | -- |  | -- |  | -- |  | -- |  | -- |  | 2953.4

## Table 21
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.7
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.6
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.6
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.4
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
Subtotal |  | 8 | -- |  | -- |  | -- |  | -- |  | -- |  | 37

## Table 22
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2002 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.1
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.5
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
Subtotal |  | 8 | -- |  | -- |  | -- |  | -- |  | -- |  | 32.5

## Table 23
Annual Funding 1109 ¦ Procurement ¦ Procurement, Marine Corps
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | 3 |  | -- |  | 3 |  | -- |  | 3
2009 |  | 10 | 16 |  | -- |  | -- |  | 16 |  | -- |  | 16
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | 11.3 |  | -- |  | 11.3 |  | -- |  | 11.3
2012 |  | -- | -- |  | 3.8 |  | -- |  | 3.8 |  | -- |  | 3.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | 1.9 |  | -- |  | 1.9 |  | -- |  | 1.9
2016 |  | -- | -- |  | 6.3 |  | -- |  | 6.3 |  | -- |  | 6.3
2017 |  | -- | -- |  | 6.5 |  | -- |  | 6.5 |  | -- |  | 6.5
2018 |  | -- | -- |  | 8.1 |  | -- |  | 8.1 |  | -- |  | 8.1
2019 |  | -- | -- |  | 3.5 |  | -- |  | 3.5 |  | -- |  | 3.5
2020 |  | -- | -- |  | 3.6 |  | -- |  | 3.6 |  | -- |  | 3.6
Subtotal |  | 10 | 16 |  | 48 |  | -- |  | 64 |  | -- |  | 64

## Table 24
Annual Funding 1109 ¦ Procurement ¦ Procurement, Marine Corps
Fiscal Year | Quantity |  | BY 2002 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | 2.6 |  | -- |  | 2.6 |  | -- |  | 2.6
2009 |  | 10 | 13.5 |  | -- |  | -- |  | 13.5 |  | -- |  | 13.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | 9.2 |  | -- |  | 9.2 |  | -- |  | 9.2
2012 |  | -- | -- |  | 3 |  | -- |  | 3 |  | -- |  | 3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | 1.5 |  | -- |  | 1.5 |  | -- |  | 1.5
2016 |  | -- | -- |  | 4.8 |  | -- |  | 4.8 |  | -- |  | 4.8
2017 |  | -- | -- |  | 4.8 |  | -- |  | 4.8 |  | -- |  | 4.8
2018 |  | -- | -- |  | 5.9 |  | -- |  | 5.9 |  | -- |  | 5.9
2019 |  | -- | -- |  | 2.5 |  | -- |  | 2.5 |  | -- |  | 2.5
2020 |  | -- | -- |  | 2.5 |  | -- |  | 2.5 |  | -- |  | 2.5
Subtotal |  | 10 | 13.5 |  | 36.8 |  | -- |  | 50.3 |  | -- |  | 50.3

## Table 25
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | 6 | 35 |  | -- |  | -- |  | 35 |  | -- |  | 35
2001 |  | 1 | 14.7 |  | -- |  | -- |  | 14.7 |  | -- |  | 14.7
2002 |  | 5 | 27.6 |  | -- |  | -- |  | 27.6 |  | -- |  | 27.6
2003 |  | 6 | 33.3 |  | -- |  | -- |  | 33.3 |  | -- |  | 33.3
2004 |  | 6 | 27.9 |  | -- |  | -- |  | 27.9 |  | -- |  | 27.9
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | 2 | 7.7 |  | -- |  | -- |  | 7.7 |  | -- |  | 7.7
2010 |  | 3 | 12.6 |  | -- |  | -- |  | 12.6 |  | -- |  | 12.6
2011 |  | 5 | 16.3 |  | -- |  | -- |  | 16.3 |  | -- |  | 16.3
2012 |  | 5 | 15.6 |  | -- |  | -- |  | 15.6 |  | -- |  | 15.6
2013 |  | 5 | 14.9 |  | -- |  | -- |  | 14.9 |  | -- |  | 14.9
2014 |  | 5 | 13.1 |  | -- |  | -- |  | 13.1 |  | -- |  | 13.1
2015 |  | 5 | 16 |  | -- |  | -- |  | 16 |  | -- |  | 16
2016 |  | 5 | 16.3 |  | -- |  | -- |  | 16.3 |  | -- |  | 16.3
2017 |  | 6 | 19.9 |  | -- |  | -- |  | 19.9 |  | -- |  | 19.9
2018 |  | 5 | 16.9 |  | -- |  | -- |  | 16.9 |  | -- |  | 16.9
2019 |  | 3 | 10.3 |  | -- |  | -- |  | 10.3 |  | -- |  | 10.3
2020 |  | 4 | 14.1 |  | -- |  | -- |  | 14.1 |  | -- |  | 14.1
2021 |  | 5 | 17.9 |  | -- |  | -- |  | 17.9 |  | -- |  | 17.9
2022 |  | 5 | 18.3 |  | -- |  | -- |  | 18.3 |  | -- |  | 18.3
2023 |  | 5 | 18.7 |  | -- |  | -- |  | 18.7 |  | -- |  | 18.7
2024 |  | 2 | 7.6 |  | -- |  | -- |  | 7.6 |  | -- |  | 7.6
Subtotal |  | 94 | 374.7 |  | -- |  | -- |  | 374.7 |  | -- |  | 374.7

## Table 26
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | BY 2002 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | 6 | 35.1 |  | -- |  | -- |  | 35.1 |  | -- |  | 35.1
2001 |  | 1 | 14.6 |  | -- |  | -- |  | 14.6 |  | -- |  | 14.6
2002 |  | 5 | 27 |  | -- |  | -- |  | 27 |  | -- |  | 27
2003 |  | 6 | 32 |  | -- |  | -- |  | 32 |  | -- |  | 32
2004 |  | 6 | 26.1 |  | -- |  | -- |  | 26.1 |  | -- |  | 26.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | 2 | 6.5 |  | -- |  | -- |  | 6.5 |  | -- |  | 6.5
2010 |  | 3 | 10.4 |  | -- |  | -- |  | 10.4 |  | -- |  | 10.4
2011 |  | 5 | 13.2 |  | -- |  | -- |  | 13.2 |  | -- |  | 13.2
2012 |  | 5 | 12.4 |  | -- |  | -- |  | 12.4 |  | -- |  | 12.4
2013 |  | 5 | 11.7 |  | -- |  | -- |  | 11.7 |  | -- |  | 11.7
2014 |  | 5 | 10.2 |  | -- |  | -- |  | 10.2 |  | -- |  | 10.2
2015 |  | 5 | 12.3 |  | -- |  | -- |  | 12.3 |  | -- |  | 12.3
2016 |  | 5 | 12.3 |  | -- |  | -- |  | 12.3 |  | -- |  | 12.3
2017 |  | 6 | 14.7 |  | -- |  | -- |  | 14.7 |  | -- |  | 14.7
2018 |  | 5 | 12.3 |  | -- |  | -- |  | 12.3 |  | -- |  | 12.3
2019 |  | 3 | 7.3 |  | -- |  | -- |  | 7.3 |  | -- |  | 7.3
2020 |  | 4 | 9.8 |  | -- |  | -- |  | 9.8 |  | -- |  | 9.8
2021 |  | 5 | 12.2 |  | -- |  | -- |  | 12.2 |  | -- |  | 12.2
2022 |  | 5 | 12.3 |  | -- |  | -- |  | 12.3 |  | -- |  | 12.3
2023 |  | 5 | 12.3 |  | -- |  | -- |  | 12.3 |  | -- |  | 12.3
2024 |  | 2 | 4.9 |  | -- |  | -- |  | 4.9 |  | -- |  | 4.9
Subtotal |  | 94 | 309.6 |  | -- |  | -- |  | 309.6 |  | -- |  | 309.6

## Table 27
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1995 |  | 1 | 13.9 |  | -- |  | -- |  | 13.9 |  | 1.6 |  | 15.5
1996 |  | 1 | 11.3 |  | -- |  | -- |  | 11.3 |  | 0.1 |  | 11.4
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1998 |  | 3 | 31.8 |  | -- |  | -- |  | 31.8 |  | 3.2 |  | 35
1999 |  | 1 | 9 |  | -- |  | -- |  | 9 |  | 0.9 |  | 9.9
2000 |  | 2 | 14.3 |  | -- |  | -- |  | 14.3 |  | 1.7 |  | 16
2001 |  | 2 | 12.3 |  | -- |  | -- |  | 12.3 |  | 1.1 |  | 13.4
2002 |  | 2 | 15.4 |  | -- |  | -- |  | 15.4 |  | 1.7 |  | 17.1
2003 |  | 1 | 5.8 |  | -- |  | -- |  | 5.8 |  | 0.8 |  | 6.6
2004 |  | 1 | 6.3 |  | -- |  | -- |  | 6.3 |  | 0.6 |  | 6.9
2005 |  | 1 | 7.6 |  | -- |  | -- |  | 7.6 |  | 0.6 |  | 8.2
2006 |  | 2 | 12.6 |  | -- |  | -- |  | 12.6 |  | 1.3 |  | 13.9
2007 |  | 3 | 16.8 |  | -- |  | -- |  | 16.8 |  | 5.9 |  | 22.7
2008 |  | 2 | 12.8 |  | -- |  | -- |  | 12.8 |  | 3.3 |  | 16.1
2009 |  | 3 | 13.8 |  | -- |  | -- |  | 13.8 |  | 6.4 |  | 20.2
2010 |  | 1 | 6.9 |  | -- |  | -- |  | 6.9 |  | 0.7 |  | 7.6
2011 |  | 3 | 12.1 |  | -- |  | -- |  | 12.1 |  | 4.9 |  | 17
2012 |  | 2 | 8.6 |  | -- |  | -- |  | 8.6 |  | 3.3 |  | 11.9
2013 |  | 5 | 24.1 |  | -- |  | -- |  | 24.1 |  | 6.2 |  | 30.3
2014 |  | 1 | 5 |  | -- |  | -- |  | 5 |  | 1.4 |  | 6.4
2015 |  | 2 | 8.8 |  | -- |  | -- |  | 8.8 |  | 2.4 |  | 11.2
2016 |  | 5 | 27.3 |  | -- |  | -- |  | 27.3 |  | 6.8 |  | 34.1
2017 |  | 3 | 14.2 |  | -- |  | -- |  | 14.2 |  | 3.5 |  | 17.7
2018 |  | 4 | 25 |  | -- |  | -- |  | 25 |  | 6.3 |  | 31.3
2019 |  | 3 | 14.5 |  | -- |  | -- |  | 14.5 |  | 3.6 |  | 18.1
2020 |  | 2 | 10 |  | -- |  | -- |  | 10 |  | 2.5 |  | 12.5
2021 |  | 2 | 10.1 |  | -- |  | -- |  | 10.1 |  | 2.6 |  | 12.7
2022 |  | 2 | 10.2 |  | -- |  | -- |  | 10.2 |  | 2.6 |  | 12.8
2023 |  | 2 | 10.2 |  | -- |  | -- |  | 10.2 |  | 2.6 |  | 12.8
2024 |  | 2 | 10.2 |  | -- |  | -- |  | 10.2 |  | 2.6 |  | 12.8
2025 |  | 2 | 10.2 |  | -- |  | -- |  | 10.2 |  | 2.6 |  | 12.8
2026 |  | 2 | 10.2 |  | -- |  | -- |  | 10.2 |  | 2.6 |  | 12.8
Subtotal |  | 68 | 401.3 |  | -- |  | -- |  | 401.3 |  | 86.4 |  | 487.7

## Table 28
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | BY 2002 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1995 |  | 1 | 14.7 |  | -- |  | -- |  | 14.7 |  | 1.7 |  | 16.4
1996 |  | 1 | 11.8 |  | -- |  | -- |  | 11.8 |  | 0.1 |  | 11.9
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1998 |  | 3 | 32 |  | -- |  | -- |  | 32 |  | 3.2 |  | 35.2
1999 |  | 1 | 8.9 |  | -- |  | -- |  | 8.9 |  | 0.9 |  | 9.8
2000 |  | 2 | 13.8 |  | -- |  | -- |  | 13.8 |  | 1.7 |  | 15.5
2001 |  | 2 | 11.5 |  | -- |  | -- |  | 11.5 |  | 1 |  | 12.5
2002 |  | 2 | 14.3 |  | -- |  | -- |  | 14.3 |  | 1.6 |  | 15.9
2003 |  | 1 | 5.1 |  | -- |  | -- |  | 5.1 |  | 0.7 |  | 5.8
2004 |  | 1 | 5.3 |  | -- |  | -- |  | 5.3 |  | 0.5 |  | 5.8
2005 |  | 1 | 6.2 |  | -- |  | -- |  | 6.2 |  | 0.5 |  | 6.7
2006 |  | 2 | 9.9 |  | -- |  | -- |  | 9.9 |  | 1 |  | 10.9
2007 |  | 3 | 12.6 |  | -- |  | -- |  | 12.6 |  | 4.4 |  | 17
2008 |  | 2 | 9.3 |  | -- |  | -- |  | 9.3 |  | 2.4 |  | 11.7
2009 |  | 3 | 9.7 |  | -- |  | -- |  | 9.7 |  | 4.5 |  | 14.2
2010 |  | 1 | 4.7 |  | -- |  | -- |  | 4.7 |  | 0.5 |  | 5.2
2011 |  | 3 | 8 |  | -- |  | -- |  | 8 |  | 3.2 |  | 11.2
2012 |  | 2 | 5.5 |  | -- |  | -- |  | 5.5 |  | 2.2 |  | 7.7
2013 |  | 5 | 15.2 |  | -- |  | -- |  | 15.2 |  | 3.9 |  | 19.1
2014 |  | 1 | 3.1 |  | -- |  | -- |  | 3.1 |  | 0.9 |  | 4
2015 |  | 2 | 5.4 |  | -- |  | -- |  | 5.4 |  | 1.4 |  | 6.8
2016 |  | 5 | 16.3 |  | -- |  | -- |  | 16.3 |  | 4.1 |  | 20.4
2017 |  | 3 | 8.3 |  | -- |  | -- |  | 8.3 |  | 2.1 |  | 10.4
2018 |  | 4 | 14.4 |  | -- |  | -- |  | 14.4 |  | 3.6 |  | 18
2019 |  | 3 | 8.2 |  | -- |  | -- |  | 8.2 |  | 2 |  | 10.2
2020 |  | 2 | 5.5 |  | -- |  | -- |  | 5.5 |  | 1.4 |  | 6.9
2021 |  | 2 | 5.5 |  | -- |  | -- |  | 5.5 |  | 1.4 |  | 6.9
2022 |  | 2 | 5.4 |  | -- |  | -- |  | 5.4 |  | 1.4 |  | 6.8
2023 |  | 2 | 5.3 |  | -- |  | -- |  | 5.3 |  | 1.4 |  | 6.7
2024 |  | 2 | 5.2 |  | -- |  | -- |  | 5.2 |  | 1.3 |  | 6.5
2025 |  | 2 | 5.1 |  | -- |  | -- |  | 5.1 |  | 1.3 |  | 6.4
2026 |  | 2 | 5 |  | -- |  | -- |  | 5 |  | 1.3 |  | 6.3
Subtotal |  | 68 | 291.2 |  | -- |  | -- |  | 291.2 |  | 57.6 |  | 348.8

## Table 29
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1998 |  | 5 | 55.2 |  | -- |  | -- |  | 55.2 |  | 12.1 |  | 67.3
1999 |  | 5 | 79.7 |  | -- |  | -- |  | 79.7 |  | 1.7 |  | 81.4
2000 |  | 3 | 53.2 |  | -- |  | -- |  | 53.2 |  | 6 |  | 59.2
2001 |  | 6 | 36.4 |  | -- |  | -- |  | 36.4 |  | -- |  | 36.4
2002 |  | 4 | 77.6 |  | -- |  | -- |  | 77.6 |  | 6.4 |  | 84
2003 |  | 6 | 64.9 |  | -- |  | -- |  | 64.9 |  | 6.1 |  | 71
2004 |  | 4 | 60.4 |  | -- |  | -- |  | 60.4 |  | 5.8 |  | 66.2
2005 |  | 3 | 60.9 |  | -- |  | -- |  | 60.9 |  | 6.2 |  | 67.1
2006 |  | 3 | 21.2 |  | -- |  | -- |  | 21.2 |  | 3.8 |  | 25
2007 |  | 5 | 34.4 |  | -- |  | -- |  | 34.4 |  | 3.6 |  | 38
2008 |  | 4 | 33.1 |  | -- |  | -- |  | 33.1 |  | 5.8 |  | 38.9
2009 |  | 4 | 29.3 |  | -- |  | -- |  | 29.3 |  | 4.9 |  | 34.2
2010 |  | 5 | 42.1 |  | -- |  | -- |  | 42.1 |  | 7.9 |  | 50
2011 |  | 5 | 47.7 |  | -- |  | -- |  | 47.7 |  | 13.7 |  | 61.4
2012 |  | -- | -- |  | 40.2 |  | -- |  | 40.2 |  | -- |  | 40.2
2013 |  | 2 | 20.3 |  | -- |  | -- |  | 20.3 |  | 11.2 |  | 31.5
2014 |  | 2 | 19.9 |  | -- |  | -- |  | 19.9 |  | 15.7 |  | 35.6
2015 |  | 4 | 24.3 |  | -- |  | -- |  | 24.3 |  | 36.5 |  | 60.8
2016 |  | 3 | 11.2 |  | -- |  | -- |  | 11.2 |  | 16.9 |  | 28.1
2017 |  | 2 | 8.8 |  | -- |  | -- |  | 8.8 |  | 13.2 |  | 22
2018 |  | 4 | 13.8 |  | -- |  | -- |  | 13.8 |  | 20.6 |  | 34.4
2019 |  | 2 | 12.8 |  | -- |  | -- |  | 12.8 |  | 19.3 |  | 32.1
2020 |  | -- | -- |  | 32.1 |  | -- |  | 32.1 |  | -- |  | 32.1
2021 |  | -- | -- |  | 38.1 |  | -- |  | 38.1 |  | -- |  | 38.1
2022 |  | -- | -- |  | 32.5 |  | -- |  | 32.5 |  | -- |  | 32.5
2023 |  | -- | -- |  | 34 |  | -- |  | 34 |  | -- |  | 34
Subtotal |  | 81 | 807.2 |  | 176.9 |  | -- |  | 984.1 |  | 217.4 |  | 1201.5

## Table 30
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | BY 2002 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1998 |  | 5 | 57.3 |  | -- |  | -- |  | 57.3 |  | 12.5 |  | 69.8
1999 |  | 5 | 81.6 |  | -- |  | -- |  | 81.6 |  | 1.8 |  | 83.4
2000 |  | 3 | 53.7 |  | -- |  | -- |  | 53.7 |  | 6.1 |  | 59.8
2001 |  | 6 | 36.3 |  | -- |  | -- |  | 36.3 |  | -- |  | 36.3
2002 |  | 4 | 76.3 |  | -- |  | -- |  | 76.3 |  | 6.3 |  | 82.6
2003 |  | 6 | 62.6 |  | -- |  | -- |  | 62.6 |  | 5.9 |  | 68.5
2004 |  | 4 | 56.9 |  | -- |  | -- |  | 56.9 |  | 5.4 |  | 62.3
2005 |  | 3 | 55.8 |  | -- |  | -- |  | 55.8 |  | 5.6 |  | 61.4
2006 |  | 3 | 18.8 |  | -- |  | -- |  | 18.8 |  | 3.4 |  | 22.2
2007 |  | 5 | 29.8 |  | -- |  | -- |  | 29.8 |  | 3.2 |  | 33
2008 |  | 4 | 28.3 |  | -- |  | -- |  | 28.3 |  | 4.9 |  | 33.2
2009 |  | 4 | 24.7 |  | -- |  | -- |  | 24.7 |  | 4.1 |  | 28.8
2010 |  | 5 | 34.8 |  | -- |  | -- |  | 34.8 |  | 6.5 |  | 41.3
2011 |  | 5 | 38.9 |  | -- |  | -- |  | 38.9 |  | 11.1 |  | 50
2012 |  | -- | -- |  | 32.2 |  | -- |  | 32.2 |  | -- |  | 32.2
2013 |  | 2 | 16.1 |  | -- |  | -- |  | 16.1 |  | 8.8 |  | 24.9
2014 |  | 2 | 15.5 |  | -- |  | -- |  | 15.5 |  | 12.3 |  | 27.8
2015 |  | 4 | 18.7 |  | -- |  | -- |  | 18.7 |  | 28.1 |  | 46.8
2016 |  | 3 | 8.5 |  | -- |  | -- |  | 8.5 |  | 12.8 |  | 21.3
2017 |  | 2 | 6.5 |  | -- |  | -- |  | 6.5 |  | 9.8 |  | 16.3
2018 |  | 4 | 10.1 |  | -- |  | -- |  | 10.1 |  | 15 |  | 25.1
2019 |  | 2 | 9.1 |  | -- |  | -- |  | 9.1 |  | 13.8 |  | 22.9
2020 |  | -- | -- |  | 22.5 |  | -- |  | 22.5 |  | -- |  | 22.5
2021 |  | -- | -- |  | 26.2 |  | -- |  | 26.2 |  | -- |  | 26.2
2022 |  | -- | -- |  | 21.9 |  | -- |  | 21.9 |  | -- |  | 21.9
2023 |  | -- | -- |  | 22.4 |  | -- |  | 22.4 |  | -- |  | 22.4
Subtotal |  | 81 | 740.3 |  | 125.2 |  | -- |  | 865.5 |  | 177.4 |  | 1042.9

## Table 31
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 1998-03-02 | 2013-10-31
Approved Quantity | 7 | 84
Reference | LRIP 1 ADM | LRIP 14 ADM
Start Year | 1998 | 1998
End Year | 1998 | 2013
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the requirements (1) to meet ship installation schedules, (2) to outfit Land Based Test Sites in preparation for completion of Operational Testing (OT), and (3) to maintain the Minimum Sustaining Rate for production of CEC systems pending completion of OT and entry into FRP.

## Table 32
Foreign Military Sales
Classified FMS information is provided in the classified annex to this submission.
Nuclear Costs
None

## Table 33
Unit Cost
Unit Cost Report
Item |  | BY 2002 $M | BY 2002 $M |  | % Change
|  | Current UCR Baseline (Jun 2004 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 4530.9 |  |  | 4737.5
Quantity | 283 |  |  | 283
Unit Cost | 16.01 |  |  | 16.74 |  | 4.56
Average Procurement Unit Cost
Cost | 2095.2 |  |  | 1751.6
Quantity | 256 |  |  | 253
Unit Cost | 8.184 |  |  | 6.923 |  | -15.41
Item |  | BY 2002 $M | BY 2002 $M |  | % Change
|  | Original UCR Baseline (Jul 1995 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2443.4 |  |  | 4737.5
Quantity | 183 |  |  | 283
Unit Cost | 13.352 |  |  | 16.74 |  | 25.37
Average Procurement Unit Cost
Cost | 1262.8 |  |  | 1751.6
Quantity | 174 |  |  | 253
Unit Cost | 7.257 |  |  | 6.923 |  | -4.6

## Table 34
Unit Cost History
Item | [7 empty] | Date |  |  |  | BY 2002 $M | [6 empty] | TY $M
[12 empty] | PAUC |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Jul 1995 | [6 empty] | 13.326 |  |  |  | 7.257 |  |  |  | 14.061 |  |  |  | 8.222
APB as of January 2006 |  |  |  |  | Jun 2004 | [6 empty] | 16.01 |  |  |  | 8.184 |  |  |  | 16.814 |  |  |  | 9.235
Revised Original APB |  |  |  |  | N/A | [6 empty] | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | Apr 2002 | [6 empty] | 15.159 |  |  |  | 8.184 |  |  |  | 15.848 |  |  |  | 9.235
Current APB |  |  |  |  | Jun 2004 | [6 empty] | 16.01 |  |  |  | 8.184 |  |  |  | 16.814 |  |  |  | 9.235
Prior Annual SAR |  |  |  |  | Dec 2014 | [6 empty] | 16.902 |  |  |  | 6.725 |  |  |  | 18.541 |  |  |  | 7.943
Current Estimate |  |  |  |  | Dec 2015 | [6 empty] | 16.74 |  |  |  | 6.923 |  |  |  | 18.725 |  |  |  | 8.411
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [20 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth |  | Spt |  |  | Total
14.060 -0.656 -2.840 0.590 0.420 5.010 0.000 -0.736 1.788 15.848
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [18 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng | Est |  | Oth | Spt |  |  | Total
15.848 0.252 -0.838 2.089 1.059 0.229 0.000 0.086 2.877 18.725

## Table 35
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [14 empty] | APUC Production Estimate
| Econ |  | Qty |  |  | Sch |  | Eng |  |  | Est | Oth | Spt |  | Total
8.220 -0.532 -0.797 0.291 -0.439 1.761 0.000 0.731 1.015 9.235
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [14 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch |  | Eng |  |  | Est |  | Oth | Spt | Total
9.235 0.180 -0.343 0.702 -0.707 -0.737 0.000 0.081 -0.824 8.411
SAR Baseline History
Item |  |  |  | SAR Planning Estimate |  |  |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  |  | Current Estimate
Milestone I |  |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Milestone II |  |  |  | N/A |  |  |  |  | May 1995 |  |  |  | May 1995 |  |  |  | May 1995
Milestone III |  |  |  | N/A |  |  |  |  | Oct 1998 |  |  |  | Apr 2002 |  |  |  | Apr 2002
IOC |  |  |  | N/A |  |  |  |  | Sep 1996 |  |  |  | Sep 1996 |  |  |  | Sep 1996
Total Cost (TY $M) |  |  |  | N/A |  |  |  |  | 2573.1 |  |  |  | 4310.7 |  |  |  | 5299.1
Total Quantity |  |  |  | N/A |  |  |  |  | 183 |  |  |  | 272 |  |  |  | 283
PAUC |  |  |  | N/A |  |  |  |  | 14.061 |  |  |  | 15.848 |  |  |  | 18.725
IOC identified above refers to the CEC Shipboard configuration, AN/USG-2. FOC occurred in conjunction with Airborne IOC in May 2005.

## Table 36
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 1946.5 | 2364.2 | -- | 4310.7
Previous Changes
Economic | 28.9 | 47.8 | -- | 76.7
Quantity | 51.6 | -261.9 | -- | -210.3
Schedule | 318.7 | 63.6 | -- | 382.3
Engineering | 478.7 | -146.1 | -- | 332.6
Estimating | 208.1 | -194.4 | -- | 13.7
Other | -- | -- | -- | --
Support | 3.6 | -14.5 | -- | -10.9
Subtotal | 1089.6 | -505.5 | -- | 584.1
Current Changes
Economic | -3 | -2.3 | -- | -5.3
Quantity | -- | 147.4 | -- | 147.4
Schedule | 95 | 113.9 | -- | 208.9
Engineering | -- | -32.8 | -- | -32.8
Estimating | 43.1 | 7.9 | -- | 51
Other | -- | -- | -- | --
Support | -- | 35.1 | -- | 35.1
Subtotal | 135.1 | 269.2 | -- | 404.3
Total Changes | 1224.7 | -236.3 | -- | 988.4
CE - Cost Variance | 3171.2 | 2127.9 | -- | 5299.1
CE - Cost & Funding | 3171.2 | 2127.9 | -- | 5299.1

## Table 37
Summary BY 2002 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
2028.1 2095.2 -- 4123.3
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | 47.8 |  | -227.3 |  | -- |  | -179.5
Schedule |  | 227.8 |  | -21.3 |  | -- |  | 206.5
Engineering |  | 418.9 |  | -111 |  | -- |  | 307.9
Estimating |  | 163.2 |  | -38.4 |  | -- |  | 124.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | 2.8 |  | -123.6 |  | -- |  | -120.8
Subtotal |  | 860.5 |  | -521.6 |  | -- |  | 338.9
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 84 |  | -- |  | 84
Schedule |  | 65.4 |  | 77.6 |  | -- |  | 143
Engineering |  | -- |  | -18.9 |  | -- |  | -18.9
Estimating |  | 31.9 |  | 12.1 |  | -- |  | 44
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 23.2 |  | -- |  | 23.2
Subtotal |  | 97.3 |  | 178 |  | -- |  | 275.3
Total Changes |  | 957.8 |  | -343.6 |  | -- |  | 614.2
CE - Cost Variance |  | 2985.9 |  | 1751.6 |  | -- |  | 4737.5
CE - Cost & Funding |  | 2985.9 |  | 1751.6 |  | -- |  | 4737.5
Previous Estimate: December 2014

## Table 38
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | -3
Stretch-out of development effort from FY 2020 to FY 2021. (Schedule) |  | 65.4 | 95
Additional funding for CVN 78 integration and testing. (Estimating) |  | 3.5 | 4.5
Additional funding for CEC integration and development efforts. (Estimating) |  | 23.2 | 32.3
Additional U.S. Marine Corps funding to support Composite Tracking Network (CTN) and |  | 4.6 | 5.5
Common Aviation Command and Control System (CAC2S). (Estimating)
Adjustment for current and prior escalation. (Estimating) |  | 0.6 | 0.8
RDT&E Subtotal |  | 97.3 | 135.1
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -2.3
Adjustment for current and prior escalation. (Estimating) +0.4 +0.3
Quantity variance resulting from an increase of 12 CEC systems from 56 to 68 (Shipbuilding and Conversion, Navy (SCN)). (Subtotal)
Quantity variance resulting from an increase of 12 CEC systems from 56 to 68 (SCN). (Quantity)
+37.1 +72.0
(+59.3) (+115.1)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) (+4.8) (+9.3) Allocation to Engineering resulting from Quantity change. (Engineering) (QR) (-12.0) (-23.3) Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (-15.0) (-29.1) Additional quantity variance allocated to DDG systems (SCN). (Quantity) -4.1 -8.0
Additional quantity variance CVN 73 and CVN74 CEC systems added to procurement buy profile (SCN). (Quantity)
Quantity variance resulting from an increase of 7 AN/USG-2 OPN systems from 74 to 81 (Aircraft Procurement, Navy (APN)). (Subtotal)
Quantity variance resulting from an increase of 7 AN/USG-2 OPN systems from 74 to 81.(APN). (Quantity)
+4.3 +7.5
+23.1 +31.8
(+36.1) (+49.7)
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) | -9 |  |  | -12.3
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) | -2.9 |  |  | -3.9
Allocation to Engineering resulting from Quantity change. (Engineering) (QR) | -6.9 |  |  | -9.5
Additional quantity variance resulting from CG modernization budget adjustments (funds to | -11.6 |  |  | -16.9
be provided at year of execution) (APN). (Quantity)
Acceleration of procurement buy profile from FY 2016 to FY 2015 Other Procurement, Navy (OPN). (Schedule)
0.0 -0.8
Stretch-out of CEC OPN buy profile from FY 2020 to FY 2023 (OPN). (Schedule) +71.9 +106.5 Acceleration of procurement buy profile (APN). (Schedule) 0.0 -0.1
Additional schedule variance resulting from acceleration of procurement buy profile (APN). (Schedule)
Acceleration of procurement buy profile by one year for DDG 127-135 systems (SCN). (Schedule)
Additional Schedule Variance resulting from one LHD OPN system shifting from FY 2017 to FY 2018 (SCN). (Schedule)
+3.4 +5.0
0.0 -2.6
-5.4 -7.3

## Table 39
Revised estimate for DDG Modernization (OPN). (Estimating) -1.1 -1.4
Allocation to estimating as a result of revised unit cost based on actual system cost (APN). (Estimating)
Revised estimate to support CTN and CAC2S Procurement Marine Corps (PMC). (Estimating)
+15.6 +21.8
+21.7 +29.5
Refined unit cost estimates for CEC DDG systems (SCN). (Estimating) -0.5 -0.9 Increase in Other Support for CEC as a result of 12 additional systems (SCN). (Support) +9.1 +17.2
Increase in Other support for CEC back-fit and system installation support (OPN). (Support)
+13.9 +17.6
Adjustment for current and prior escalation. (Support) +0.2 +0.3
Procurement Subtotal +178.0 +269.2
(QR) Quantity Related

## Table 40
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: CEC Signal Data Processor-Sierra (SDP-S) Production
Contractor: Sechan Electronics Inc
Contractor Location: 525 Furnace Hills Pike
Lititz, PA 17543-8902
Contract Number: N00024-12-D-5203/1
Contract Type: Indefinite Delivery Indefinite Quantity (IDIQ), Firm Fixed Price (FFP)
Award Date: December 20, 2011
Definitization Date: December 20, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
13.8 N/A 84 64.2 N/A 244 64.2 64.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the award of Delivery Orders 0001, 0002, 0003, and 0004.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (IDIQ/FFP) contract.
Notes
This is a Delivery Order contract to procure SDP-S. Production units are FFP, the engineering support services are Cost Plus Fixed-Fee. This is an IDIQ contract, therefore, the estimated ceiling price at completion is not applicable.

## Table 41
Contract Identification
Appropriation: RDT&E
Contract Name: Design Agent/Engineering Services (FY 2014 - FY 2018)
Contractor: Raytheon - Network Centric Systems
Contractor Location: 8333 Bryan Dairy Road
Largo, FL 33777-1444
Contract Number: N00024-13-C-5212/0
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: September 27, 2013
Definitization Date: September 27, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
32.8 N/A 0 157.5 N/A 0 288.6 288.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to exercising options for FY 2014, FY 2015, and FY 2016 Design Agent/Engineering Services (DA/ES) efforts.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +96.7 0.0
Previous Cumulative Variances +77.0 -20.0
Net Change +19.7 +20.0
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to the Program Management and administrative support functions continuing to be shared resources across the entire DA/ES contract rather than solely being functions of the Design Agent effort.
The favorable net change in the schedule variance is due to the placement of the purchase order of the software license renewal previously delayed. This delay caused the unfavorable schedule variance in the previous SAR.
Notes
The FY 2014 - FY 2018 DA/ES contract was awarded September 27, 2013 and is the follow-on contract to the FY 2008 - FY 2013 DA/ES contract. The current end date including all option years is September 26, 2018.
This follow-on effort includes labor, facilities, engineering, and technical support services required for CEC System Design Agent Services, support equipment, and computer program installations as well as Engineering and Technical services in support of existing CEC assets, auxiliary equipment, and stand alone equipment.

## Table 42
Contract Identification
Appropriation: Procurement
Contract Name: CEC Production (FY 2012 - FY 2016)
Contractor: Raytheon - Network Centric Systems
Contractor Location: 8333 Bryan Dairy Road
Largo, FL 33777-1444
Contract Number: N00024-12-C-5231/0
Contract Type: Firm Fixed Price (FFP)
Award Date: September 28, 2012
Definitization Date: May 01, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
20.3 N/A 0 131.6 N/A 28 267.1 267.1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to incorporating following year production efforts.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
FY 2012 - FY 2016 CEC production contract was awarded September 28, 2012 and is the follow-on contract to FY 2008-FY 2011 CEC production. This contract includes production requirements for CEC systems requirements for associated Installations and Checkout Kits and Planar Array Antenna Assemblies back-fit and other ancillary equipment are also included.

## Table 43
Contract Identification
Appropriation: RDT&E
Contract Name: Common Array Block (CAB) Antenna Development and Production
Contractor: Raytheon
Contractor Location: 8333 Bryan Dairy Road
Largo, FL 33777-1444
Contract Number: N00024-13-C-5230/0 Contract Type: Cost Plus Incentive Fee (CPIF) Award Date: September 27, 2013
Definitization Date: September 27, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
7.3 N/A 6 20.2 N/A 6 59.1 59.1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to exercising Year 1 options.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/26/2016) -1.0 -1.2
Previous Cumulative Variances +0.2 0.0
Net Change -1.2 -1.2
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to being behind plan performance on the Hardware and Firmware detail design and development for several efforts. Although the efforts are progressing they have proven to be more complex than planned resulting in negative cost and schedule trends. Labor usage is also a contributing factor to the negative cost trend.
The unfavorable cumulative schedule variance is due to being behind plan performance on the Hardware and Firmware design and development efforts. Labor usage is also a contributing factor to the negative schedule variance due to designs being more complex than originally planned in the Integrated Master Schedule Discussion Analysis, Data Item Description.
Notes
This contract is for development and production of the next generation CEC antenna.

## Table 44
Contract Identification
Appropriation: Procurement
Contract Name: CEC Production (FY 2015- FY2021)
Contractor: DRS Laurel Technologies
Contractor Location: 246 Airport Rd
Johnstown, PA 15904-7224
Contract Number: N00024-15-C-5228/0
Contract Type: Firm Fixed Price (FFP)
Award Date: February 25, 2015
Definitization Date: February 25, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
2.0 N/A 2 13.9 N/A 8 227.0 227.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to increase of six CEC systems procured since initial contract.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This is the first time this contract is being reported.
The FFP portion of this contract includes production and testing for AN/USG-2B, AN/USG-3B, AN/USG-4B CEC systems as well as AN/USG -2/2A to 2B backfit kits. The CPFF portion of the contract includes Engineering Services in support of the manufacture, assembly, and testing of the CEC production systems under the contract.

## Table 45
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 30 | 30 | 30 | 100%
Production | 162 | 151 | 253 | 59.68%
Total Program Quantity Delivered | 192 | 181 | 283 | 63.96%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
5299.1
4080.5
77%
33
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
23
69.7%
4306.9
81.28%
The above data is current as of February 09, 2016.

## Table 46
Operating and Support Cost
Cost Estimate Details
Date of Estimate: February 05, 2016
Source of Estimate: POE
Quantity to Sustain: 283
Unit of Measure: System
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 1994 - FY 2046
The quantity to sustain changed from 264 to 283 due to the increase of 19 systems. The unit of measure is the AN/USG- 2/2A/2B Shipboard variant and AN/USG-3/3B Airborne Variant.
The sustainment strategy costs includes: prime contractor and government in-service engineering support, continuing engineering support for Navy in-house facilities and software maintenance, depot repairs of CEC equipment, modification kit procurements and installations, and fleet recurring training.
Sustainment Strategy
Sustainment strategy efforts include: Maintenance and repair of CEC fielded systems (AN/USG-2, Land Based Test Sites, AN/USG-3), Integrated Logistics Support, Software Trouble Reports, Original Equipment Manufacturer Design Agent support, In-Service Engineering, Diminishing Manufacturing Supply Material Shortages, Obsolescence Management.
Antecedent Information
No Antecedent
Annual O&S Costs BY2002 $K
Cost Element | CEC Average Annual Cost Per System | No Antecedent (Antecedent) N/A
Unit-Level Manpower | 0 | 0
Unit Operations | 8.1 | 0
Maintenance | 111.2 | 0
Sustaining Support | 96.7 | 0
Continuing System Improvements | 175.6 | 0
Indirect Support | 0 | 0
Other | 0 | 0
Total | 391.6 | --

## Table 47
Item | Total O&S Cost $M
| CEC | [5 empty] | No Antecedent (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | N/A |  | N/A |  |  | 2189.3 | N/A
Then Year | N/A |  | N/A |  |  | 3045.9 | N/A
Equation to Translate Annual Cost to Total Cost
An equation would not accurately depict the total cost since platform (Airborne/Shipboard) service is not always 20 years. The service life per platform (Airborne/Shipboard) varies anywhere from five years to 20 years.
O&S Cost Variance
Category |  | BY 2002 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
1912.8
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 276.5 A revised cost model was used to account for varying service-life years per system which reflects a more accurate O&S cost estimate. This is due to additional platforms with required maintenance. The quantity to sustained changed from 264 to 283 due to increased of 19 systems.
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 276.5
Current Estimate 2189.3
Disposal Estimate Details
Date of Estimate: February 05, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2002 $M): Total costs for disposal of all System are 28.1
Disposal costs are based on an estimated 20-year service-life and not included in the unitized cost.