## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-378
EA-18G Growler Aircraft (EA-18G)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 12
Cost and Funding 13
Low Rate Initial Production 22
Foreign Military Sales 23
Nuclear Costs 23
Unit Cost 24
Cost Variance 27
Contracts 30
Deliveries and Expenditures 36
Operating and Support Cost 37

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
EA-18G Growler Aircraft (EA-18G)
DoD Component
Navy
Responsible Office
CAPT David Kindley, USN
Program Executive Officer (PMA265)
Bldg 2272, Suite 445, NAVAIRSYSCOMHQ
47123 Buse Road, Unit IPT Patuxent River, MD 20670-1547
david.kindley@navy.mil
Phone: | 301-757-7669
Fax: | 301-757-7520
DSN Phone: | 757-7669
DSN Fax: | 757-7520
Date Assigned: | July 16, 2015
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated July 18, 2007
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated February 15, 2011

## Table 6
Mission and Description
The EA-18G Growler Aircraft (EA-18G) is the fourth major variant of the F/A-18 family of aircraft. The EA-18G serves as the Navy's replacement for the EA-6B providing a capability to detect, identify, locate, and suppress hostile emitters. The EA- 18G provides organic accurate emitter targeting for employment of onboard suppression weapons such as High-Speed Anti
-Radiation Missile. The EA-18G aircraft is a missionized F/A-18F airframe coupled with the integration of its primary Airborne Electronic Attack systems that include the ALQ-99 Tactical Jamming System pods, AN/ALQ-218 Receiver, Communication Countermeasures Set with functionality equivalent to the USQ-113, and the Multi-Mission Advanced Tactical Terminal.

## Table 7
Executive Summary
The procurement profile of the FY 2017 PB adds 7 EA-18G aircraft in FY 2016. The result of this addition will be a FY 2016 FRP contract for Lot 40 EA-18G aircraft, which increases the total Program of Record (PoR) from 150 to 157. As part of the A-12 settlement, the EA-18G Program received three EA-18G airframes, Contractor Furnished Equipment (CFE), and Airborne Electronic Attack (AEA) kits from the Boeing Company. The value to the program was $198M. These aircraft are in the process of delivery and are annotated as Lot 37A aircraft. There was not a Total Obligation Authority (TOA) increase to the program. The three Growler aircraft have been added to FY 2013 and will be included in the PoR. FY 2016 $198 Million A
-12 In-kind Settlement does not reflect TOA. No additional resources were provided in FY 2016 to the Department of the Navy.
The Assistant Secretary of the Navy, Research, Development, and Acquisition (ASN (RD&A)) acknowledged and concurred with the FY 2015 Program Deviation Report (PDR) on June 2, 2015. ASN(RD&A) approved the APB on October 15, 2015. The additional 7 EA-18G aircraft and related support in FY 2016 caused Procurement and O&S cost breaches. Additionally, an RDT&E breach occurred as a result of increased funding for Complex Emitter, Tactical Targeting Network Technology, and Distributed Targeting Processor-Networked efforts. As a result, a PDR and updated APB will be submitted.
A contract modification to the Lot 38 FRP contract for the Lot 39 FRP procurement awarded on October 26, 2015.
As of November 30, 2015, EA-18G aircraft have flown 141,141 hours.
As of January 31, 2016, the program has delivered 114 aircraft to the Fleet.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
As a result of the changes in the FY 2017 PB, the EA-18G program APB thresholds for RDT&E, Procurement, and O&S cost
are breached.
The RDT&E cost breach is the result of increased funding for Complex Emitter, Tactical Targeting Network Technology, and Distributed Targeting Processor-Networked efforts.
The Procurement cost breach is the result of 7 aircraft being added to the Program of Record (PoR) in FY 2016.
The O&S cost breach is the result of updated methodology being used to estimate flight hours to more closely align flight hour projections with those in the Naval Synchronization Tool (NST). The updated methodology calculates aircraft operating years based on EA
-18G Total Aircraft Inventory (TAI) that includes pipeline aircraft to align with NST. Previous methodology utilized Primary Aircraft Authorized (PAA) that does not include pipeline aircraft. Also contributing to the O&S cost breach are 7 aircraft being added to the POR in FY 2016 (Lot 40).
A Program Deviation Report and an APB will be prepared for submission to the Assistant Secretary of the Navy, Research, Development, and Acquisition for review and approval.
Nunn-McCurdy Breaches

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B | Dec 2003 | Nov 2003 | Apr 2004 | Dec 2003
Critical Design Review (CDR) | Apr 2005 | Apr 2005 | Oct 2005 | Apr 2005
Milestone C | Jul 2007 | Apr 2007 | Oct 2007 | Jul 2007
Initial Operational Test and Evaluation (IOT&E)(Start) | Sep 2008 | Sep 2008 | Mar 2009 | Sep 2008
Initial Operational Capability (IOC) | Sep 2009 | Sep 2009 | Mar 2010 | Sep 2009
Full Rate Production (FRP) | Apr 2009 | Apr 2009 | Nov 2009 | Nov 2009
Change Explanations

## Table 10
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Net-ready
EA-18G must fully support | EA-18G must fully support | EA-18G must fully support | Meets all Net- | Meets all
execution of joint critical | execution of joint critical | execution of joint critical | Centric Require | Net-
operational activities | operational activities | operational activities | - ments | Centric
identified in the applicable | identified in the applicable | identified in the applicable |  | Require-
joint and system integrated | joint and system integrated | joint and system integrated |  | ments
architectures and the | architectures and the | architectures and the
system must satisfy the | system must satisfy the | system must satisfy the
technical requirements for | technical requirements for | technical requirements for
transition to Net-Centric | transition to Net-Centric | transition to Net-Centric
military operations to | military operations to | military operations to
include: 1) DISR mandated | include: 1) DISR mandated | include: 1) DISR mandated
GIG IT standards and | GIG IT standards and | GIG IT standards and
profiles identified in the TV- | profiles identified in the TV- | profiles identified in the TV-
1, 2) DISR mandated GIG | 1, 2) DISR mandated GIG | 1, 2) DISR mandated GIG
KIPs identified in the KIP | KIPs identified in the KIP | KIPs identified in the KIP
declaration table, 3) NCOW | declaration table, 3) NCOW | declaration table, 3) NCOW
RM Enterprise Services, 4) | RM Enterprise Services, 4) | RM Enterprise Services, 4)
Information assurance | Information assurance | Information assurance
requirements including | requirements including | requirements including
availability, integrity, | availability, integrity, | availability, integrity,
authenticat-ion, confidential- | authenticat-ion, confidential- | authenticat-ion, confidential-
ity, and nonrepudiat-ion, and | ity, and nonrepudiat-ion, and | ity, and nonrepudiat-ion, and
issuance of an ATO by the | issuance of an ATO by the | issuance of an IATO by the
DAA, and 5) Operationally | DAA, and 5) Operationally | DAA, and 5) Operationally
effective information | effective information | effective information
exchanges; and mission | exchanges; and mission | exchanges; and mission
critical performance and | critical performance and | critical performance and
information assurance | information assurance | information assurance
attributes, data correctness, | attributes, data correctness, | attributes, data correctness,
data availability, and | data availability, and | data availability, and
consistent data processing | consistent data processing | consistent data processing
specified in the applicable | specified in the applicable | specified in the applicable
joint and system integrated | joint and system integrated | joint and system integrated
architecture views. | architecture views. | architecture views.
Receive Azimuth Coverage
360 deg | 360 deg | 360 deg | 360 deg | 360 deg
Operational Availability
>=0.98 | >=0.98 | >=0.85 | 0.98 | >=0.98
Carrier Suitability
Launch Catapult WOD (Max Gross Weight, Tropical Day)

## Table 11
<=25 knots | <=25 knots | <=30 knots | 21 knots | <=25 knots
Deck Spot Factor
<=1.4 | <=1.4 | <=1.5 | 1.46 | 1.46
Recovery Payload (empty wing and centerline pylons and nacelle ejectors, 47,000 lbs, 14 knots WOD)
>=9,000 lbs | >=9,000 lbs | >=9,000 lbs | 11,037 lbs | >=9,000 lbs
Additional Internal Fuel Capacity (over F/A-18C/D)
>=3,000 lbs | >=3,000 lbs | >=3,000 lbs | 3,802 lbs | >=3,000 lbs
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
CPD Change 1 dated October 19, 2009
Change Explanations
None
Acronyms and Abbreviations
ATO - Authority to Operate
DAA - Designated Approval Authority deg - Degrees
DISR - DoD Information Technology Standards and Profile Registry GIG IT - Global Information Grid Information Technology
IATO - Interim Authority to Operate KIP - Key Interface Profile
lbs - Pounds
NCOW RM - Net-Centric Operations and Warfare Reference Model TV - Technical View
WOD - Wind Over Deck

## Table 12
Track to Budget
RDT&E
Appn |  | BA | PE
Navy 1319 05 0604269N
Project | Name
3063 EA-18G Development
Procurement
Appn |  | BA | PE
Navy 1506 01 0204154N
Line Item Name
0143 EA-18G
Navy 1506 06 0204154N
Line Item Name
0605 Spares and Repair Parts (Shared) (Sunk)
MILCON
Appn |  | BA | PE
Navy 1205 01 0703676N
Project Name
P193 EA-18G Facility Improvements (Sunk)

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2004 $M | [5 empty] | BY 2004 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E | 1755.3 |  |  | 1700.8 | 1870.9 |  |  | 2120.51 |  | 1899.9 |  |  | 1832.3 |  | 2419.3
Procurement | 5754.6 |  |  | 8329.7 | 9162.7 |  |  | 11045.01 |  | 6712.5 |  |  | 9693.8 |  | 13229.1
Flyaway | -- |  |  | -- | -- |  |  | 9328.2 |  | -- |  |  | -- |  | 11138
Recurring | -- |  |  | -- | -- |  |  | 9239.8 |  | -- |  |  | -- |  | 11036.9
Non Recurring | -- |  |  | -- | -- |  |  | 88.4 |  | -- |  |  | -- |  | 101.1
Support | -- |  |  | -- | -- |  |  | 1716.8 |  | -- |  |  | -- |  | 2091.1
Other Support | -- |  |  | -- | -- |  |  | 1477.6 |  | -- |  |  | -- |  | 1815.4
Initial Spares | -- |  |  | -- | -- |  |  | 239.2 |  | -- |  |  | -- |  | 275.7
MILCON | 20.9 |  |  | 21.4 | 23.5 |  |  | 21.4 |  | 24 |  |  | 24 |  | 24
Acq O&M | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 7530.8 |  |  | 10051.9 | N/A |  |  | 13186.9 |  | 8636.4 |  |  | 11550.1 |  | 15672.4
1 APB Breach
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The current estimate recommendation aims to provide sufficient resources to execute the program under normal conditions, encountering average levels of technical, schedule and programmatic risk, and external interference. It is consistent with average resource expenditures on historical efforts of similar size, scope, and complexity.
Total Quantity
Quantity |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  | 84 |  |  |  | 114 |  |  |  |  | 160
Total |  | 84 |  |  |  | 114 |  |  |  |  | 160

## Table 14
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 1814.8 | 46.9 |  | 116.8 |  | 165 |  | 142.8 |  | 65.6 |  | 67.4 |  | 0 |  | 2419.3
Procurement | 12371.1 | 858 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 13229.1
MILCON | 24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 24
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 14209.9 | 904.9 |  | 116.8 |  | 165 |  | 142.8 |  | 65.6 |  | 67.4 |  | 0 |  | 15672.4
PB 2016 Total | 14089.6 | 56.9 |  | 47.3 |  | 104.4 |  | 56.4 |  | 40.6 |  | 0 |  | 0 |  | 14395.2
Delta | 120.3 | 848 |  | 69.5 |  | 60.6 |  | 86.4 |  | 25 |  | 67.4 |  | 0 |  | 1277.2
Funding Notes
As part of the A-12 settlement, the EA-18G Program received three EA-18G airframes, Contractor Furnished Equipment (CFE), and Airborne Electronic Attack (AEA) kits from the Boeing Company. The value to the program was $198M. These aircraft are in the process of delivery and are annotated as Lot 37A aircraft. There was not a TOA increase to the program. The three Growler aircraft have been added to FY 2013 and will be included in the Program of Record.
FY 2016 $198 Million A-12 In-kind Settlement does not reflect Total Obligation Authority (TOA). No additional resources were provided in FY 2016 to the Department of the Navy. The three EA-18G aircraft from the A-12 settlement and the FY 2017 PB addition of 7 EA-18G aircraft in FY 2016 increases the total PoR from 150 to 160.
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Production | 0 |  | 153 |  | 7 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 160
PB 2017 Total | 0 |  | 153 |  | 7 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 160
PB 2016 Total | 0 |  | 150 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 150
Delta | 0 |  | 3 |  | 7 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 10

## Table 15
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 203.7
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 353.7
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 379.7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 361
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 269.4
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 115.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 55.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.8
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.6
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 46.9
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 116.8
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 165
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 142.8
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.6
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 67.4
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2419.3

## Table 16
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2004 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 199.6
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 337.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 351.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 326.3
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 239.2
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 101.4
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.9
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.7
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.6
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.9
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36.9
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 90.2
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 125.1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 106.1
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.8
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.1
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2120.5

## Table 17
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | 8.2 |  | -- |  | -- |  | 8.2 |  | -- |  | 8.2
2006 |  | 4 | 308 |  | -- |  | 7.5 |  | 315.5 |  | 55.7 |  | 371.2
2007 |  | 9 | 638.7 |  | -- |  | 5.8 |  | 644.5 |  | 104.9 |  | 749.4
2008 |  | 21 | 1396.4 |  | -- |  | 63.4 |  | 1459.8 |  | 164.9 |  | 1624.7
2009 |  | 22 | 1563.3 |  | -- |  | 17.1 |  | 1580.4 |  | 157.3 |  | 1737.7
2010 |  | 22 | 1482 |  | -- |  | -- |  | 1482 |  | 85.6 |  | 1567.6
2011 |  | 12 | 819 |  | -- |  | 0.2 |  | 819.2 |  | 144.4 |  | 963.6
2012 |  | 12 | 799.4 |  | -- |  | 0.3 |  | 799.7 |  | 147.7 |  | 947.4
2013 |  | 15 | 816 |  | -- |  | 0.1 |  | 816.1 |  | 184 |  | 1000.1
2014 |  | 21 | 1463.9 |  | -- |  | 6.7 |  | 1470.6 |  | 426.7 |  | 1897.3
2015 |  | 15 | 1178.9 |  | -- |  | -- |  | 1178.9 |  | 325 |  | 1503.9
2016 |  | 7 | 563.1 |  | -- |  | -- |  | 563.1 |  | 294.9 |  | 858
Subtotal |  | 160 | 11036.9 |  | -- |  | 101.1 |  | 11138 |  | 2091.1 |  | 13229.1

## Table 18
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | BY 2004 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | 7.7 |  | -- |  | -- |  | 7.7 |  | -- |  | 7.7
2006 |  | 4 | 281.1 |  | -- |  | 6.8 |  | 287.9 |  | 50.9 |  | 338.8
2007 |  | 9 | 569.7 |  | -- |  | 5.2 |  | 574.9 |  | 93.5 |  | 668.4
2008 |  | 21 | 1227 |  | -- |  | 55.7 |  | 1282.7 |  | 145 |  | 1427.7
2009 |  | 22 | 1354.8 |  | -- |  | 14.8 |  | 1369.6 |  | 136.4 |  | 1506
2010 |  | 22 | 1258.1 |  | -- |  | -- |  | 1258.1 |  | 72.6 |  | 1330.7
2011 |  | 12 | 681.7 |  | -- |  | 0.2 |  | 681.9 |  | 120.2 |  | 802.1
2012 |  | 12 | 656 |  | -- |  | 0.2 |  | 656.2 |  | 121.3 |  | 777.5
2013 |  | 15 | 662.5 |  | -- |  | 0.1 |  | 662.6 |  | 149.4 |  | 812
2014 |  | 21 | 1173.3 |  | -- |  | 5.4 |  | 1178.7 |  | 341.9 |  | 1520.6
2015 |  | 15 | 930.8 |  | -- |  | -- |  | 930.8 |  | 256.7 |  | 1187.5
2016 |  | 7 | 437.1 |  | -- |  | -- |  | 437.1 |  | 228.9 |  | 666
Subtotal |  | 160 | 9239.8 |  | -- |  | 88.4 |  | 9328.2 |  | 1716.8 |  | 11045

## Table 19
Cost Quantity Information 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2004 $M
2005 | -- | --
2006 | 4 | 288.8
2007 | 9 | 569.7
2008 | 21 | 1227
2009 | 22 | 1354.8
2010 | 22 | 1258.1
2011 | 12 | 681.7
2012 | 12 | 656
2013 | 15 | 662.5
2014 | 21 | 1173.3
2015 | 15 | 930.8
2016 | 7 | 437.1
Subtotal | 160 | 9239.8

## Table 20
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
2007 24.0
Subtotal 24.0

## Table 21
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 2004 $M
Total Program
2007 21.4
Subtotal 21.4

## Table 22
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2003-12-18 | 2008-05-08
Approved Quantity | 9 | 30
Reference | Milestone B ADM | Milestone C ADM
Start Year | 2006 | 2006
End Year | 2009 | 2009
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the determination that 30 EA-18G aircraft would be the minimum requirement to conduct LRIP, permit a systematic increase in the production rate of the ALQ- 218 system, and avoid a break in the production line.
In LRIP I (FY 2007), the EA-18G program office procured nine EA-18G systems (including one FY 2007 supplemental). For LRIP II (FY 2008), the EA-18G program office procured 21 EA-18G systems (including three FY 2008 supplementals).

## Table 23
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Australia | 2013-09-24 | 0 | 17.7 | FMS Case, AT-P-GTM, provides for EA-18G Aircrew initial training and support related to AT-P- SCI and AT-P-LEN FMS Cases.
Australia | 2013-07-04 | 12 | 1346.7 | FMS Case, AT-P-SCI, provides for the procurement of 12 EA-18G aircraft and support. The 12 aircraft were included in the Lot 38 procurement contract, which was awarded on June 30, 2014.
Australia | 2012-08-30 | 12 | 992.4 | FMS Case, AT-P-LEN, provides for the procurement of 12 Airborne Electronic Attack (AEA) kit sets, the modification effort to convert six Australian Lot 33 F/A-18F to AEA-18G Aircraft, and support. Per AT-P-SCI, Australia elected to obtain 12 new build EA-18G aircraft vice converting six Australian Lot 33 F/A-18F to EA-18G.
Notes
Nuclear Costs
None

## Table 24
Unit Cost
Unit Cost Report
Item |  |  | BY 2004 $M | BY 2004 $M |  | % Change
|  |  | Current UCR Baseline (Feb 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 10051.9 |  |  |  | 13186.9
Quantity | 114 |  |  |  | 160
Unit Cost | 88.175 |  |  |  | 82.418 |  | -6.53
Average Procurement Unit Cost
Cost | 8329.7 |  |  |  | 11045
Quantity | 114 |  |  |  | 160
Unit Cost | 73.068 |  |  |  | 69.031 |  | -5.52
Item |  |  | BY 2004 $M | BY 2004 $M |  | % Change
|  |  | Original UCR Baseline (Dec 2003 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost |  | 7662.6 |  |  | 13186.9
Quantity |  | 90 |  |  | 160
Unit Cost |  | 85.14 |  |  | 82.418 |  | -3.2
Average Procurement Unit Cost
Cost |  | 6030.5 |  |  | 11045
Quantity |  | 90 |  |  | 160
Unit Cost |  | 67.006 |  |  | 69.031 |  | 3.02

## Table 25
Unit Cost History
Item | [7 empty] | Date |  |  |  |  | BY 2004 $M | [5 empty] | TY $M
[13 empty] | PAUC |  | APUC |  |  |  | PAUC |  |  |  |  | APUC
Original APB |  |  |  |  | Dec 2003 | [7 empty] | 85.14 |  |  | 67.006 |  |  |  |  | 93.573 |  |  |  | 74.6
APB as of January 2006 |  |  |  |  | Dec 2003 | [7 empty] | 85.14 |  |  | 67.006 |  |  |  |  | 93.573 |  |  |  | 74.6
Revised Original APB |  |  |  |  | N/A | [7 empty] | N/A |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | Jan 2010 | [7 empty] | 90.989 |  |  | 71.149 |  |  |  |  | 103.828 |  |  |  | 82.449
Current APB |  |  |  |  | Feb 2011 | [7 empty] | 88.175 |  |  | 73.068 |  |  |  |  | 101.317 |  |  |  | 85.033
Prior Annual SAR |  |  |  |  | Dec 2014 | [7 empty] | 81.188 |  |  | 68.401 |  |  |  |  | 95.968 |  |  |  | 81.672
Current Estimate |  |  |  |  | Dec 2015 | [7 empty] | 82.418 |  |  | 69.031 |  |  |  |  | 97.952 |  |  |  | 82.682
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [21 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  |  | Oth |  |  | Spt |  |  | Total
93.573 4.150 1.442 -0.319 0.947 -0.348 0.000 3.369 9.241 102.814
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [19 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth |  | Spt |  | Total
102.814 -0.522 -11.764 -0.082 1.062 -2.048 0.000 8.492 -4.862 97.952

## Table 26
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [13 empty] | APUC Production Estimate
| Econ | Qty |  | Sch |  | Eng |  | Est |  | Oth |  | Spt |  | Total
74.600 3.679 0.057 -0.319 0.138 -1.613 0.000 3.369 5.311 79.911
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch |  | Eng |  | Est |  | Oth |  | Spt | Total
79.911 -0.593 -0.885 -0.082 0.000 -4.161 0.000 8.492 2.771 82.682
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate |  |  |  |  | SAR Production Estimate |  |  |  | Current Estimate
Milestone A |  |  | N/A |  |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A
Milestone B |  |  | N/A |  |  |  | Nov 2003 |  |  |  |  | Dec 2003 |  |  |  | Dec 2003
Milestone C |  |  | N/A |  |  |  | Apr 2007 |  |  |  |  | Jul 2007 |  |  |  | Jul 2007
IOC |  |  | N/A |  |  |  | Sep 2009 |  |  |  |  | Sep 2009 |  |  |  | Sep 2009
Total Cost (TY $M) |  |  | N/A |  |  |  | 8421.6 |  |  |  |  | 8636.4 |  |  |  | 15672.4
Total Quantity |  |  | N/A |  |  |  | 90 |  |  |  |  | 84 |  |  |  | 160
PAUC |  |  | N/A |  |  |  | 93.573 |  |  |  |  | 102.814 |  |  |  | 97.952

## Table 27
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
1899.9 6712.5 24.0 8636.4
Economic |  | 13.5 |  | -70.9 |  | -- |  | -57.4
Quantity |  | -- |  | 5180.2 |  | -- |  | 5180.2
Schedule |  | -- |  | -6.7 |  | -- |  | -6.7
Engineering |  | 170 |  | -- |  | -- |  | 170
Estimating |  | 37 |  | -444 |  | -- |  | -407
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 879.7 |  | -- |  | 879.7
Subtotal |  | 220.5 |  | 5538.3 |  | -- |  | 5758.8
Current Changes Economic |  | -2.2 |  | -24 |  | -- |  | -26.2
Quantity |  | -- |  | 751.5 |  | -- |  | 751.5
Schedule |  | -- |  | -6.4 |  | -- |  | -6.4
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 301.1 |  | -221.8 |  | -- |  | 79.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 479 |  | -- |  | 479
Subtotal |  | 298.9 |  | 978.3 |  | -- |  | 1277.2
Total Changes |  | 519.4 |  | 6516.6 |  | -- |  | 7036
CE - Cost Variance |  | 2419.3 |  | 13229.1 |  | 24 |  | 15672.4
CE - Cost & Funding |  | 2419.3 |  | 13229.1 |  | 24 |  | 15672.4

## Table 28
Summary BY 2004 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
1755.3 5754.6 20.9 7530.8
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 4159.9 |  | -- |  | 4159.9
Schedule |  | -- |  | -4.2 |  | -- |  | -4.2
Engineering |  | 126.1 |  | -- |  | -- |  | 126.1
Estimating |  | 15.2 |  | -354.8 |  | 0.5 |  | -339.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 704.7 |  | -- |  | 704.7
Subtotal |  | 141.3 |  | 4505.6 |  | 0.5 |  | 4647.4
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 586.3 |  | -- |  | 586.3
Schedule |  | -- |  | -0.4 |  | -- |  | -0.4
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 223.9 |  | -176.1 |  | -- |  | 47.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 375 |  | -- |  | 375
Subtotal |  | 223.9 |  | 784.8 |  | -- |  | 1008.7
Total Changes |  | 365.2 |  | 5290.4 |  | 0.5 |  | 5656.1
CE - Cost Variance |  | 2120.5 |  | 11045 |  | 21.4 |  | 13186.9
CE - Cost & Funding |  | 2120.5 |  | 11045 |  | 21.4 |  | 13186.9
Previous Estimate: December 2014

## Table 29
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -2.2
Adjustment for current and prior escalation. (Estimating) +0.4 +0.5
Revised estimate for Tactical Targeting Network Technology in FY 2017 to FY 2019. (Estimating)
Revised estimate for Distributed Targeting Processor-Networked in FY 2017 to FY 2021.
+38.5 +50.9
+38.1 +52.4
(Estimating) Revised estimate for Complex Emitter in FY 2017 to FY 2020. (Estimating) Decrease in FY 2016 funding due to Congressional reduction. (Estimating) | +154.8 -7.9 | +207.3 -10.0
RDT&E Subtotal | 223.9 | 298.9
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -24
Quantity variance resulting from an increase of 7 aircraft from 153 to 160. (Subtotal) | 562.2 | 720.7
Quantity variance resulting from an increase of 7 aircraft from 153 to 160. (Quantity) | -586.3 | -751.5
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) | -0.4 | -0.5
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) | -23.7 | -30.3
Acceleration of procurement buy profile. (Schedule) (QR) | 0 | -5.9
Decrease in FY 2013, FY 2014, and FY 2015 due to internal Navy realignments. | -168.5 | -211.4
(Estimating)
Adjustment for current and prior escalation. (Estimating) | 16.1 | 19.9
Adjustment for current and prior escalation. (Support) | 3.2 | 4.1
Increase in Other Support resulting from increase in 7 additional aircraft. (Support) (QR) | 371.5 | 474.5
Increase in Initial Spares resulting from increase in 7 additional aircraft. (Support) (QR) | 0.3 | 0.4
Procurement Subtotal | 784.8 | 978.3
(QR) Quantity Related

## Table 30
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: Airframe Multi-Year Procurement III (MYP III)
Contractor: The Boeing Company
Contractor Location: 6200 JS McDonnell Blvd.
St. Louis, MO 63166
Contract Number: N00019-09-C-0019
Contract Type: Firm Fixed Price (FFP)
Award Date: December 04, 2008
Definitization Date: September 28, 2010
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
2528.7 N/A 58 2644.3 N/A 58 2644.3 2644.3
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to multiple funded modifications and the incorporation of Engineering Change Proposals.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
The EA-18G aircraft (Lots 34 through 37) are being procured on the MYP III contract from FY 2010 through FY 2013. The MYP III contract values above reflect the EA-18G portion of this contract only.
The MYPIII contract was awarded on December 4, 2008, for the advance procurement of long-lead materials. A contract modification, P00009, funded the contract for the procurement of Lot 34 aircraft and associated requirements.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 31
Contract Identification
Appropriation: Procurement
Contract Name: F414 Engine Production Lots 16-19
Contractor: GE Aircraft Engines
Contractor Location: 1000 Western Ave.
Lynn, MA 01910
Contract Number: N00019-11-C-0045
Contract Type: Firm Fixed Price (FFP)
Award Date: April 20, 2011
Definitization Date: September 26, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
5.2 N/A 0 507.9 N/A 114 507.9 507.9
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the FY 2012 procurement of 24 engines and devices, FY 2013 procurement of long lead material, FY 2013 procurement of 18 engines and devices, modifications executed for advanced procurement for FY 2014 engines, modification executed for the FY 2014 procurement of 42 engines and devices, and the modification executed for the FY 2015 procurement of 30 engines and devices.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
The original contract value only reflects the procurement of time-critical long-lead material in support of the FY 2012 F414 engine production.

## Table 32
Contract Identification
Appropriation: Procurement
Contract Name: EA-18G FRP AEA Kits
Contractor: The Boeing Company
Contractor Location: 6200 JS McDonnell Blvd.
St. Louis, MO 63166-0516
Contract Number: N00019-09-C-0086
Contract Type: Firm Fixed Price (FFP)
Award Date: December 23, 2008
Definitization Date: May 11, 2009
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
50.3 N/A N/A 993.8 N/A 92 993.8 993.8
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to adding Lots 33, 34, 35, 36, 37 and Royal Australian Air Force Airborne Electronic Attack (AEA) kits after program approval into FRP, dated November 23, 2009.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
The original contract value reflected the advanced procurement of time-critical parts only.
The December 2013 SAR erroneously reported a Current Quantity of 68 kits vice 92 kits. There are no additional quantity changes this year and the Current Contract Price and Estimated Price at Completion values remain the same.
AEA kit deliveries on this contract were completed ahead of schedule.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 33
Contract Identification
Appropriation: Procurement
Contract Name: System Configuration Sets (SCS) Contract
Contractor: The Boeing Company
Contractor Location: 6200 JS McDonnell Blvd.
St. Louis, MO 63166
Contract Number: N68936-14-D-0008
Contract Type: Indefinite Delivery Indefinite Quantity (IDIQ), Cost Plus Incentive Fee (CPIF), Cost Plus Fixed Fee (CPFF)
Award Date: December 12, 2013
Definitization Date: December 12, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
872.8 N/A 90 872.8 N/A 90 872.8 872.8
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (IDIQ/CPIF/CPFF) contract.
Notes
The Program Executive Officer for Tactical Aircraft Programs approved a deviation (dated July 24, 2013) to exclude EVM requirements for CPFF level-of-effort task orders on this contract. There have been no CPIF orders awarded on this contract. As a result, there are no EVM metrics reported.
The Current Contract Price Target for the basic contract reflects the value at contract award.
The value, quantities, and funding for each delivery or task order issued under this IDIQ contract are individually negotiated.
This contract includes shared costs and quantities for U.S. Navy and Royal Australian Air Force F/A-18 and EA-18G platforms.

## Table 34
Contract Identification
Appropriation: RDT&E
Contract Name: EA-18G ALQ-218 Operational Test Program Sets (OTPSs)
Contractor: The Boeing Company
Contractor Location: 6200 James S McDonnell Boulevard
Berkeley, MO 63134
Contract Number: N68335-10-G-0012/46
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: September 25, 2013
Definitization Date: September 25, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
41.8 N/A 14 49.8 N/A 14 49.8 49.8
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract modifications being awarded to fund technical support for the development efforts from Northrop Grumman (NGC) to Boeing on CLIN 0001.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/28/2016) +2.4 -1.2
Previous Cumulative Variances +1.8 -0.7
Net Change +0.6 -0.5
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to the ability to automate requirements generation, use of existing Boeing Unigraphics models of Weapons Replaceable Assemblies, and use of existing cable designs provided by Northrop Grumman.
The unfavorable net change in the schedule variance is due to additional time required to complete requirements documentation primarily due to Critical Design Review documentation associated with the Ancillary Set, resulting in a scheduled delay starting Integration.

## Table 35
Contract Identification
Appropriation: Procurement
Contract Name: EA-18G FRP (Lot 38-39)
Contractor: The Boeing Company
Contractor Location: 6200 JS McDonnell Blvd.
St. Louis, MO 63166
Contract Number: N00019-14-C-0032
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: June 30, 2014
Definitization Date: June 30, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
1466.9 1488.9 33 2568.0 2635.3 48 2568.0 2568.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the contract modification to include the procurement of Lot 38-39 AEA kits, Airborne Electronic Attack (AEA) specific obsolescence efforts, and Royal Australian Air Force (RAAF) unique hardware and support.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF) contract.
Notes
The EA-18G FRP (Lot 38) contract was awarded on June 30, 2014 for the procurement of 33 EA-18G aircraft with Airborne Electronic Attack (AEA) kits, which includes 21 U.S. Navy (USN) aircraft and 12 RAAF aircraft. A contract modification was awarded on October 26, 2015 for the procurement of 15 EA-18G aircraft with AEA kits.
The Deputy Assistant Secretary of the Navy for Acquisition and Procurement approved a deviation (Deviation No. 14-N-907, dated May 29, 2014) to exclude EVM requirements on this contract.
All contract values above reflect the procurement of the EA-18G variant only.

## Table 36
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 114 | 114 | 160 | 71.25%
Total Program Quantity Delivered | 114 | 114 | 160 | 71.25%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
15672.4
10583
67.53%
18
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
13
72.22%
15114.8
96.44%
The above data is current as of February 17, 2016.
The previous reported aircraft deliveries of 116 aircraft was an error due to miscalculation.

## Table 37
Operating and Support Cost
Cost Estimate Details
Date of Estimate: February 16, 2016
Source of Estimate: POE
Quantity to Sustain: 160
Unit of Measure: Aircraft
Service Life per Unit: 29.00 Years
Fiscal Years in Service: FY 2008 - FY 2046
The variable components of the cost estimate such as the Flying Hour Program (FHP) are based on the number of aircraft operational years available and the flight hours which they generate. Some elements such as personnel and their associated indirect and training costs are dependent on the number of squadrons and their manning requirements. Other fixed elements such as sustaining engineering are based on a cost per aircraft. Modification and airframe and support equipment depot maintenance are estimated as the total requirement and then applied on a cost per aircraft basis.
Consumption rate, gallons per hour: 1,305
Number of Aircraft Operating Years: 4,449
Flight Hours per aircraft per month: 26.4
Petroleum, Oil, Lubrication (POL) cost, JP-5 per gallon FY 2004$: 1.00
Fatigue Life (Flight Hours): 7,500
Operational Service Life (Flight Hours): 9,000
Total Life Cycle Flight Hours: 1,334,563
Sustainment Strategy
The EA-18G Support strategy is based on the following assumptions for basing and utilization.
Primary Mission Authorized Aircraft (PMAA) will be comprised of ten Carrier Air Wing (CVW) squadrons (each with 7 PMAA), one of which will be part of the Forward Deployed Naval Force (FDNF) stationed out of Yokosuka, Japan, five Expeditionary Squadrons (each with 5 PMAA), and one reserve Squadron (5 PMAA). All squadrons are manned to the level required to execute the Expeditionary mission for a total of 100 PMAA aircraft. The Fleet Replacement Squadron will consist of 26 Aircraft Primary Training Aircraft Authorization (PTAA) aircraft.
EA-18G and F/A-18E/F common maintenance training will be conducted at Naval Air Station (NAS), Lemoore, California (CA), with peculiar EA-18G AEA maintenance training being conducted at NAS Whidbey Island, WA. Initial aircrew training will be conducted at NAS Whidbey Island, WA.
EA-18G and F/A-18E/F common Intermediate Level (I-Level) maintenance will be conducted at NAS Lemoore, CA to include the F414 engine. Limited I-Level for some EA-18G and F/A-18E/F common maintenance tasks has been established at Whidbey Island, WA. Airborne Electronic Attack (AEA) I-Level maintenance will be stood up at Whidbey Island and aboard the CVWs commencing FY18. EA-18G Depot Level (D-Level) maintenance will follow the directives as

## Table 38
published in the ILS, SCM and F414 support contracts. This support strategy focuses on the integration of existing F/A- 18F support, support that was developed for the EA-6B equipment common to the EA-18G, and development of support for EA-18G unique design circumstances. While the EA-18G AEA equipment is based on the ICAP-III system that was developed for the EA-6B, much of it is repackaged, some with added EA-18G unique components, and some new design EA-18G equipment.
Antecedent Information
Antecedent program: EA-6B
Consumption rate, gallons per hour: 1,084
Number of Aircraft Operating Years: 4,449 (not actual, but used in order to provide a comparison between the EA-18G and its antecedent platform)
Flight Hours per aircraft per month: 29.2 POL Cost, JP-5 per gallon FY 2004$: 1.00
Source of Antecedent Information: Naval Visibility and Management Operating and Support Costs (VAMOSC) database Aircraft Type Model Series Report (ATMSR)
For comparison purposes, the BY Antecedent’s Average Annual Cost per Aircraft is derived from total FY 2010 - FY 2014 cost from the Navy VAMOSC ATMSR, divided by the total number of aircraft in ATMSR for FY 2010 - FY 2014. This value is then multiplied by the total number of aircraft operating years associated with EA-18G to provide a point of comparison.
Annual O&S Costs BY2004 $M
Cost Element |  |  | EA-18G Average Annual Cost Per Aircraft |  |  |  | EA-6B (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower |  |  | 1.47 |  |  |  | 2.043
Unit Operations |  |  | 0.625 |  |  |  | 0.535
Maintenance |  |  | 2.39 |  |  |  | 3.313
Sustaining Support |  |  | 0.132 |  |  |  | 0.29
Continuing System Improvements |  |  | 1.053 |  |  |  | 1.629
Indirect Support |  |  | 0.341 |  |  |  | 0.341
Other |  |  | 0 |  |  |  | 0
Total |  |  | 6.011 |  |  |  | 8.151
Item | Total O&S Cost $M
| EA-18G | [6 empty] | EA-6B (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year |  | 14743 |  | 16217.3 |  | 26743.01 |  |  | 36262.8
Then Year 1 APB O&S Cost Breach |  | 24508.2 |  | N/A |  | 48459.2 |  |  | N/A

## Table 39
Due to an updated methodology being used to estimate flight hours to more closely align flight hour projections with those in the Naval Synchronization Tool (NST) an additional 691 aircraft operating years and $3,062 BY 2004 $M was added to the O&S Cost Estimate. The updated methodology calculates aircraft operating years based on EA-18G Total Aircraft Inventory (TAI) that includes pipeline aircraft to align with NST. Previous methodology utilized Primary Aircraft Authorized (PAA) that does not include pipeline aircraft. Due to the addition of 7 aircraft to the Program of Record (PoR) in FY 2016 (Lot 40), 203 operating years have been added to the PoR which adds $868 BY 2004 $M to the O&S Cost Estimate.
Both of these contributed to the O&S cost breach.
Equation to Translate Annual Cost to Total Cost
The Average Annual Cost Per Aircraft for the EA-18G is calculated by Dividing the Total O&S Cost of $26,743.0 BY 2004
$M by the Total Aircraft Operating Years of 4,449 for the program resulting in $6.011 BY 2004 $M per aircraft per year.
O&S Cost Variance
Category | BY 2004 $M | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
23232.6
Programmatic/Planning Factors 868.2 Seven EA-18G aircraft added to Lot 40: PMAA of CVW
squadrons increased from six to seven.
Cost Estimating Methodology 3061.9 Updated methodology used to calculate flight hours to more closely align with the flight hour projections in the NST.
Cost Data Update 60.2 Updates in aviation depot-level repairable and aviation fleet maintenance pricing.
Labor Rate 14.9 Slight increases in FY 2016 composite labor rates.
Energy Rate -103.7 Decrease in fuel price.
Technical Input -391.1 Decrease in the Service Life Extension Program (SLEP) estimate and increase in F414 Engine/Module Mean Engine Flight Hour Between Repair (MEFHBR).
Other 0.0
Total Changes 3510.4
Current Estimate 26743.0
Disposal Estimate Details
Date of Estimate: February 16, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2004 $M): Total costs for disposal of all Aircraft are 29.8
The TY $M value is $55.1.