## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-386
Ground/Air Task Oriented Radar (G/ATOR)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 9
Schedule 10
Performance 12
Track to Budget 16
Cost and Funding 18
Low Rate Initial Production 29
Foreign Military Sales 30
Nuclear Costs 30
Unit Cost 31
Cost Variance 34
Contracts 37
Deliveries and Expenditures 42
Operating and Support Cost 43

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Ground/Air Task Oriented Radar (G/ATOR)
DoD Component
Navy
Responsible Office
Mr. John Karlovich 2200 Lester Ave
Quantico, VA 22134
john.karlovich@usmc.mil
Phone: | 703-432-4982
Fax: | 703-784-0307
DSN Phone: | 378-4982
DSN Fax: | 278-0307
Date Assigned: | August 1, 2014
References
SAR Baseline (Production Estimate)
Assistant Secretary of the Navy (Research, Development & Acquisition) (ASN(RDA)) Approved Acquisition Program Baseline (APB) dated April 14, 2014
Approved APB
Assistant Secretary of the Navy (Research, Development & Acquisition) (ASN(RDA)) Approved Acquisition Program Baseline (APB) dated April 14, 2014

## Table 6
Mission and Description
The Ground/Air Task Oriented Radar (G/ATOR) is a single material solution for the mobile Multi-Role Radar System and Ground Weapons Locating Radar (GWLR) requirements. It is a three-dimensional, short/medium range multi-role radar designed to detect unmanned aerial systems, cruise missiles, air breathing targets, rockets, artillery, and mortars. G/ATOR satisfies the warfighter's expeditionary needs across the Marine Air Ground Task Force spectrum replacing five legacy radar systems with a single solution. The Air Defense/ Surveillance Radar G/ATOR Block 1 provides capabilities in the Short Range Air Defense and Air Surveillance mission areas; GWLR G/ATOR Block 2 will address Counter-fire Targeting Missions; and Expeditionary Airport Surveillance Radar G/ATOR Block 4 will address Air Traffic Control missions. G/ATOR Block 4 is not included in the Acquisition Program Baseline. Resourcing may be included in future budget builds. G/ATOR provides real-time radar measurement data to the Tactical Air Operations Module, Common Aviation Command and Control System, Composite Tracking Network, and Advanced Field Artillery Tactical Data System.

## Table 7
Executive Summary
Program Highlights Since Last Report:
The G/ATOR program received a waiver for a Gate Review prior to award of LRIP Lot 2 and extended the timeline for submission of the Test and Evaluation Master Plan for MDA signature on March 10, 2014 from the Assistant Secretary of the Navy, Research, Development and Acquisition (ASN (RDA)). Also, on June 11, 2015, the ASN (RDA) amended the Milestone C ADM to require Director, Marine Corps Operational Test and Evaluation Activity (MCOTEA) to provide an assessment of progress towards Operational Effectiveness/Operational Suitable (OE/OS) to support an Early Deployment Decision (EDD) for Gallium Arsenide-based G/ATOR Block (GB) 1 and 2 assets, and defer final certification of OE/OS to Initial Operational Test and Evaluation.
The award of LRIP Lot 2 to Northrop Grumman was exercised on March 20, 2015. It provided for the required systems to support the IOC of GB2 with all spares for initial fielding and Developmental Test/Operational Test. The G/ATOR program awarded to Northrop Grumman three additional contract actions: a sole source contract for the procurement of an additional eight LRIP units capable of meeting operational requirements for G/ATOR. The Gallium Nitride (GaN) Transition Phase 2 contract was awarded August 26, 2015 to complete transition to GaN Technology in preparation for GaN LRIP and the August 28, 2015 contract awarded to develop and verify the GB2 capability, Counterfire Targeting missions.
The G/ATOR program received on March 30, 2015, Director, Capabilities Development Directorate letter that clarified G/ATOR reliability requirements and the development of an operationally meaningful Key System Attribute with a timeline for achieving the threshold and objective values.
There are no significant software-related issues with this program at this time.
History of Significant Developments Since Program Initiation:
July 26, 2005: G/ATOR Program Milestone B ADM. This memorandum designated G/ATOR as an Acquisition Category (ACAT) II program and approved entry into the System Development and Demonstration (SDD) phase. The MDA at program initiation was ASN (RDA).
September 16, 2005: Initial development contract awarded to Northrop Grumman and became a subject of protest.
February 2007: The Fiscal Year (FY) 2008 Senate Armed Services Committee Report directed the Secretary of the Navy to conduct an independent assessment, and submit a report to the Congressional Defense Committees, with the FY 2009 budget request on the Marine Corps acquisition of the G/ATOR. The report was provided to the Congressional Defense Committees on February 4, 2008. The report concluded the G/ATOR system design provides optimal capability across a wide variety of operational mission profiles. The system is properly phased to provide the necessary air defense capabilities to Joint forces with performance that exceeds that of the legacy systems it replaces.
March 20, 2007: Deputy Commandant, Combat Development and Integration letter, and the subsequent Director, Force Protection Integration Division letter, dated August 3, 2007, clarified G/ATOR’s compliance with Joint Requirements Oversight Council Memorandum 120-05, “Policy for Updating Capabilities Documents to Incorporate Force Protection and Survivability KPPs” dated June 13, 2005, by requiring G/ATOR to procure M1152A1 up-armored High Mobility Multipurpose Wheeled Vehicles. This Key Performance Parameter (KPP) forced significant system redesign.
March 30, 2007: Awarded SDD Contract to Northrop Grumman
April 5, 2007: ASN (RDA) directed transition of the G/ATOR Program from Marine Corps Systems Command to the newly established Program Executive Office Land Systems.
February 9, 2009: The G/ATOR Program was designated a Department of Defense Special Interest program by a USD

## Table 8
(AT&L) Memorandum.
October 28, 2011: USD (AT&L) ADM, designated G/ATOR an ACAT IC program with the Navy as the lead component. G/ATOR was no longer a special interest program.
January 24, 2014: The Milestone C LRIP Decision for G/ATOR Lots 1 and 2, and permission to release the GB2 Request for Proposal (RFP) was presented to the MDA, ASN (RDA). This meeting also constituted the G/ATOR Program’s annual Configuration Steering Board and was documented in the March 10, 2015 ADM.
March 10, 2014: ASN (RDA) G/ATOR Milestone C ADM authorized the procurement of LRIP Lot 1 units contingent upon approval of all statutory acquisition documentation. The memorandum also required ASN (RDA) authorization for an EDD based on MCOTEA certification of OE/OS. Permission to release the GB2 RFP was deferred pending completion of a Deputy Assistant Secretary of the Navy for Acquisition and Procurement Peer Review, and an Office of the Secretary of Defense Developmental Test and Evaluation review of GB2 RFP test language. The memorandum also defined the entrance criteria for a Full deployment decision.

## Table 9
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 10
Schedule
(Ch-1)
(Ch-1)
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
G/ATOR
Milestone B | Aug 2005 | Aug 2005 | Aug 2005 | Aug 2005
Milestone C | Mar 2014 | Mar 2014 | Mar 2014 | Mar 2014
Initial Operational Test & Evaluation | Oct 2018 | Oct 2018 | Oct 2019 | Oct 2018
FRP Decision | Mar 2019 | Mar 2019 | Mar 2020 | Mar 2019
AD/SR (GB1)
Operational Assessment | Aug 2016 | Aug 2016 | Aug 2017 | Apr 2017
IOC | Feb 2017 | Feb 2017 | Feb 2018 | Feb 2018
GWLR (GB2)
Operational Assessment | Oct 2017 | Oct 2017 | Oct 2018 | May 2018
IOC | Feb 2018 | Feb 2018 | Feb 2019 | Sep 2018
(Ch-1)
(Ch-1)

## Table 11
Change Explanations
(Ch-1) AD/SR (GB1) Operational Assessment Current Estimate changed from Aug 2016 to Apr 2017 due to late LRIP Contract Award.
AD/SR (GB1) IOC Current Estimate changed from Feb 2017 to Feb 2018 due to late LRIP Contract Award.
GWLR (GB2) Operational Assessment Current Estimate changed from Oct 2017 to May 2018 due to late LRIP Contract Award.
GWLR (GB2) IOC Current Estimate changed from Feb 2018 to Sep 2018 due to late LRIP Contract Award.
Acronyms and Abbreviations
AD/SR - Air Defense/Surveillance Radar
GB1/2 - Ground/Air Task Oriented Radar Block 1/2 GWLR - Ground Weapons Locating Radar

## Table 12
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
AD/SR (GB1)
Tier 1: Net-Centric Tier 2: Information Transport, Information Assurance
Enter and be managed in the network
Network: Direct Fiber to TAOM, CAC2S or CTN Measure: Time to connect to an operational network from power up Conditions: Network connectivity Network: EPLRS to TAOM or CAC2S
30 min Reconfigure from transport to full operation 30 min | 30 min Reconfigure from transport to full operation 30 min | 60 min Reconfigure from transport to full operation 60 min | TBD | 30 min Reconfigure from transport to full operation 30 min
Exchange information
Information Element: Air Track Data Measure: Dissemination of target biographic and physical data Measure: Receipt of HVT data Measure: Latency of data Measure: Strenght of encryption Conditions: Tactical/Geopolitical
Non Permissive | Non Permissive | Data: Date and time, Azimuth, range, elevation, time, size, speed and IFF NRT Data Rate: -524 Kbps TFOCA-11 Not Encrypted EPLRS: Communic-ation / Transmission Integrated Circuit (CTIC), CTIC DS- 101 Hybrid (CDH) Permissive | TBD | Non Permissive
Tier 1: Battlespace Awareness Tier 2: Intelligence, Surveillance & Reconnaissance, Environment
Combat Identification (Block 1) (Applicable to Block 4)
(Threshold=Objective) AD/SR's IFF system shall be compatible with MK XII IFF systems (Modes 1, 2, 3/A, C, 4). | (Threshold= Objective) AD/SR's IFF system shall be compatible with MK XII IFF systems (Modes 1, 2, 3/A, C, 4). | AD/SR's IFF system shall be compatible with MK XII IFF systems (Modes 1, 2, 3/A, C, 4). | TBD | (Threshold= Objective) AD/SR's IFF system shall be compatible with MK XII IFF systems (Modes 1, 2, 3/A, C, 4).
Combat Identification (Block 1) (Applicable to Block 4

## Table 13
Integrate IFF Mode 5 (Level 3) and Mode S (Level 3) | Integrate IFF Mode 5 (Level 3) and Mode S (Level 3) | Growth - Block 4. AD/SR shall integrate MK XIIA IFF Mode 5 (Level 2) capabilities and Mode S (level 2) | TBD | Integrate IFF Mode 5 (Level 3) and Mode S (Level 3)
Tier 1: Logistics Tier 2: 0perational Contract Support
Sustainment
Material Availability
Materiel Availability The | Materiel Availability The | Materiel Availability | TBD | Materiel Availability
AD/SR shall have a Materiel | AD/SR shall have a Materiel | The AD/SR shall |  | The AD/SR shall
Availability of 0.90 | Availability of 0.90 | have a Materiel |  | have a Materiel
(Objective) | (Objective) | Availability of 0.85 |  | Availability of 0.90
|  | (Threshold) |  | (Objective)
Operational availability
Operational availability The | Operational availability The | Operational | TBD | Operational
AD/SR shall have an Ao of | AD/SR shall have an Ao of | availability The |  | availability The
0.95 (Objective) | 0.95 (Objective) | AD/SR shall have |  | AD/SR shall have
|  | an Ao of 0.90 |  | an Ao of 0.95
|  | (Threshold) |  | (Objective)
GWLR (GB2)
Detection, Tracking and Classification (all ranges in (km))
(Mortar (Light .5-30) | (Mortar (Light .5-30) | (Mortar (Light .75- | TBD | (Mortar (Light .75-
(Medium .5-40) (Heavy .5- | (Medium .5-40) (Heavy .5- | 20) (Medium .75- |  | 20) (Medium .75-
40)) (Artillery (Light 3-60) | 40)) (Artillery (Light 3-60) | 30) (Heavy .75-30)) |  | 30) (Heavy .75-
(Medium 3-60) (Heavy 3- | (Medium 3-60) (Heavy 3- | (Artillery (Light 3-30) |  | 30)) (Artillery (Light
60)) (Rockets (Light 6-60) | 60)) (Rockets (Light 6-60) | (Medium 3-40) |  | 3-30) (Medium 3-
(Medium 6-60) (Heavy 15- | (Medium 6-60) (Heavy 15- | (Heavy 3-40)) |  | 40) (Heavy 3- 40))
90)) | 90)) | (Rockets (Light 10- |  | (Rockets (Light 10-
|  | 40) (Medium 10-50) |  | 40) (Medium 10-
|  | (Heavy 10-60)) |  | 50) (Heavy 10-60))
Probability of location (acquisition)
Assuming no targets in | Assuming no targets in | Assuming no | TBD | Assuming no
track, 0.97 for at least 90% | track, 0.97 for at least 90% | targets in track, |  | targets in track,
of the cases in the shot | of the cases in the shot | 0.90 for at least |  | 0.90 for at least
array with +/-800 mils | array with +/-800 mils | 90% of the cases in |  | 90% of the cases
coverage (1600 mils total) | coverage (1600 mils total) | the shot array with |  | in the shot array
with the radar in either | with the radar in either | +/-800 mils |  | with +/-800 mils
normal or extended range | normal or extended range | coverage (1600 |  | coverage (1600
operating mode in the | operating mode in the | mils total) with the |  | mils total) with the
defined nominal | defined nominal | radar in either |  | radar in either
environment. | environment. | normal or extended |  | normal or extended
|  | range operating |  | range operating
|  | mode in the defined |  | mode in the
|  | nominal |  | defined nominal
|  | environment. |  | environment
Hostile Weapon Location (range in (m))
The CEP50 of weapon | The CEP50 of weapon | The CEP50 of | TBD | The CEP50 of

## Table 14
location shall be less than the greater of 30m or 0.252% of range for at least 90% (threshold) of the cases in the shot array in the defined nominal environment. | location shall be less than the greater of 30m or 0.252% of range for at least 90% (threshold) of the cases in the shot array in the defined nominal environment. | weapon location shall be less than the greater of 30m or 0.252% of range for at least 80% (objective) of the cases in the shot array in the defined nominal environment. |  | weapon location shall be less than the greater of 30m or 0.252% of range for at least 80% (objective) of the cases in the shot array in the defined nominal
Projectile Impact (CEP50)
The CEP50 of weapon location shall be less than the greater of 30m or 0.252% of range (in meters) for at least 90% (threshold) of the cases in the shot array in the defined nominal environment. | The CEP50 of weapon location shall be less than the greater of 30m or 0.252% of range (in meters) for at least 90% (threshold) of the cases in the shot array in the defined nominal environment. | The CEP50 of weapon location shall be less than the greater of 30m or 0.252% of range (in meters) for at least 80% (objective) of the cases in the shot array in the defined nominal environment. | TBD | The CEP50 of weapon location shall be less than the greater of 30m or 0.252% of range (in meters) for at least 80% objective) of the cases in the shot array in the defined nominal environment.
Transportability
(Objective=Threshold) C- 130 drive-on, drive-off | (Objective=Threshold) C- 130 drive-on, drive-off | C-130 drive-on, drive-off | TBD | C-130 drive-on, drive-off
Net Ready
100% of interfaces certified; services; policy- enforcement controls; and data correctness, availability and processing requirements in the Joint integrated architecture. | 100% of interfaces certified; services; policy- enforcement controls; and data correctness, availability and processing requirements in the Joint integrated architecture. | 100% of interfaces certified; services; policy-enforcement controls; and data correctness, availability and processing requirements designated as enterprise-level or critical in the Joint integrated architecture. | TBD | 100 percent of interfaces certified; services; policy enforcement controls; and data correctness, availability and processing requirements designated as enterprise level or critical in the Joint integrated architecture.
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
CPD (GB1) dated December 3, 2012 and ORD (GB2) dated July 20, 2004

## Table 15
Change Explanations
None
Acronyms and Abbreviations
AD/SR - Air Defense/Surveillance Radar
CAC2S - Common Aviation Command and Control System CEP50 - Circular Error Probable 50
CTN - Composite Tracking Network
EPLRS - Enhanced Position Location Reporting System GB1/2/4 - Ground/Air Task Oriented Radar Block 1/2/4 GWLR - Ground Weapons Locating Radar
HVT - High Value Target
IFF - Identification Friend or Foe kbps - kilobits per second
km - Kilometers m - meters
mils - milliradians min - minutes
NRT - Near Real Time
TAOM - Tactical Air Operations Modules TFOCA - Tactical Fiber Optic Cable Assembly

## Table 16
Track to Budget
RDT&E
Appn |  | BA | PE
Navy | 1319 07 |  | 0204460M
| Project |  | Name
| 9C89 |  | Marine Ground-Air Radar
| Notes: |  | Sub activity changed to C9C890 from C9C89B FY2013 when G/ATOR PE was created and no longer shared.
Navy | 1319 04 |  | 0206313M
| Project |  | Name
| 3099D |  | Radar Systems (Shared) (Sunk)
| Notes: |  | Added based on historical data. This line started its use with G/ATOR in 2004.
Navy | 1319 07 |  | 0206313M
| Project |  | Name
| 9C89 |  | G/ATOR (Shared) (Sunk)
| Notes: |  | Ground/Air Task Oriented Radar (G/ATOR)
Procurement
Appn |  | BA | PE
Navy | 1109 04 |  | 0206313M
| Line Item |  | Name
| 4650 |  | Radar Systems (Shared)
| Notes: |  | Radar Systems
Navy | 1109 04 |  | 0204460M
| Line Item |  | Name
| 4650 |  | Radar Systems (Shared) (Sunk)
| Notes: |  | Radar Systems FY2013 and FY2014
| 4655 |  | G/ATOR
| Notes: |  | G/ATOR FY2015 and beyond.
Navy | 1109 04 |  | 0506313M
| Line Item |  | Name
| 4655 |  | G/ATOR
| Notes: |  | G/ATOR FY2015 and beyond.
Navy | 1109 07 |  | 0204460M
| Line Item |  | Name
| 7000 |  | Spares and Repairs Parts (Shared)
| Notes: |  | Spares and Repairs Parts
MILCON

## Table 17
Notes
The MILCON funding line has not yet been established.

## Table 18
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2012 $M | [6 empty] | BY 2012 $M |  | TY $M
| SAR Baseline Production Estimate |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 986.5 |  |  | 986.5 | 1085.2 |  |  | 989.6 |  | 1019.2 |  |  | 1019.2 |  | 1017.3
Procurement |  | 1625.3 |  |  | 1625.3 | 1787.8 |  |  | 1633.4 |  | 1894.8 |  |  | 1894.8 |  | 1892.2
Flyaway |  | -- |  |  | -- | -- |  |  | 1424.9 |  | -- |  |  | -- |  | 1652.5
Recurring |  | -- |  |  | -- | -- |  |  | 1299.5 |  | -- |  |  | -- |  | 1510.3
Non Recurring |  | -- |  |  | -- | -- |  |  | 125.4 |  | -- |  |  | -- |  | 142.2
Support |  | -- |  |  | -- | -- |  |  | 208.5 |  | -- |  |  | -- |  | 239.7
Other Support |  | -- |  |  | -- | -- |  |  | 133.6 |  | -- |  |  | -- |  | 154.1
Initial Spares |  | -- |  |  | -- | -- |  |  | 74.9 |  | -- |  |  | -- |  | 85.6
MILCON |  | 3.5 |  |  | 3.5 | 3.9 |  |  | 3.5 |  | 3.9 |  |  | 3.9 |  | 3.9
Acq O&M |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 2615.3 |  |  | 2615.3 | N/A |  |  | 2626.5 |  | 2917.9 |  |  | 2917.9 |  | 2913.4
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The ICE to support the G/ATOR program to establish a new APB; like all life-cycle cost estimates previously performed by the Naval Center for Cost Analysis (NCCA) is built upon a product-oriented work breakdown structure, based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Department has been successful.
Total Quantity
Quantity |  |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  |  | 45 |  |  |  | 45 |  |  |  |  | 45
Total |  |  | 45 |  |  |  | 45 |  |  |  |  | 45

## Table 19
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 750.6 | 65.6 |  | 83.5 |  | 50.3 | 10.1 |  | 12.5 |  | 6.3 |  |  | 38.4 |  | 1017.3
Procurement | 275.3 | 126.9 |  | 135 |  | 145 | 233.2 |  | 283.3 |  | 297.2 |  |  | 396.3 |  | 1892.2
MILCON | 0 | 3.9 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 3.9
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 1025.9 | 196.4 |  | 218.5 |  | 195.3 | 243.3 |  | 295.8 |  | 303.5 |  |  | 434.7 |  | 2913.4
PB 2016 Total | 1035.2 | 214.8 |  | 225.4 |  | 182 | 244.9 |  | 230.8 |  | 344.2 |  |  | 438.1 |  | 2915.4
Delta | -9.3 | -18.4 |  | -6.9 |  | 13.3 | -1.6 |  | 65 |  | -40.7 |  |  | -3.4 |  | -2
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Production | 0 |  | 6 |  | 3 | 3 | 3 |  | 6 |  | 8 | 8 |  | 8 |  | 45
PB 2017 Total | 0 |  | 6 |  | 3 | 3 | 3 |  | 6 |  | 8 | 8 |  | 8 |  | 45
PB 2016 Total | 0 |  | 6 |  | 3 | 3 | 3 |  | 6 |  | 6 | 9 |  | 9 |  | 45
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 2 | -1 |  | -1 |  | 0

## Table 20
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.7
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.9
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 88.9
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 127.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 67.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 63.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 102.5
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 70.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 74.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 90.6
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.6
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83.5
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 50.3
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.1
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.5
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.3
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.6
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.3
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.4
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.5
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.6
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.7
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2034 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.9
2035 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2036 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3
2037 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2038 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.1

## Table 21
2039 | -- | -- | -- | -- | -- | -- | --
2040 | -- | -- | -- | -- | -- | -- | 3.2
2041 | -- | -- | -- | -- | -- | -- | --
2042 | -- | -- | -- | -- | -- | -- | 3.2
2043 | -- | -- | -- | -- | -- | -- | --
2044 | -- | -- | -- | -- | -- | -- | 3.6
Subtotal | -- | -- | -- | -- | -- | -- | 1017.3

## Table 22
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2012 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.8
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.1
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.8
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.8
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 93.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 132.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 68.7
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 63.1
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 100.7
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 68.3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 71.3
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 85.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 61.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 76.4
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 45.1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.9
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.8
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.3
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.5
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2034 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2035 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2036 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2037 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2038 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2039 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2040 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2041 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2042 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2043 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --

## Table 23
2044 | -- | -- | -- | -- | -- | -- | 1.9
Subtotal | -- | -- | -- | -- | -- | -- | 989.6

## Table 24
Annual Funding 1109 ¦ Procurement ¦ Procurement, Marine Corps
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | -- |  | -- |  | 4.2 |  | 4.2 |  | -- |  | 4.2
2013 |  | 2 | 74 |  | -- |  | 10.6 |  | 84.6 |  | 1.8 |  | 86.4
2014 |  | 2 | 74 |  | -- |  | 10.6 |  | 84.6 |  | 9.2 |  | 93.8
2015 |  | 2 | 72.6 |  | -- |  | 6.4 |  | 79 |  | 11.9 |  | 90.9
2016 |  | 3 | 103.9 |  | -- |  | 11.5 |  | 115.4 |  | 11.5 |  | 126.9
2017 |  | 3 | 92.8 |  | 0.3 |  | 10.7 |  | 103.8 |  | 31.2 |  | 135
2018 |  | 3 | 89.2 |  | 0.2 |  | 10.9 |  | 100.3 |  | 44.7 |  | 145
2019 |  | 6 | 181.1 |  | -- |  | 20.5 |  | 201.6 |  | 31.6 |  | 233.2
2020 |  | 8 | 231.7 |  | 0.5 |  | 17.8 |  | 250 |  | 33.3 |  | 283.3
2021 |  | 8 | 247.4 |  | -- |  | 21.2 |  | 268.6 |  | 28.6 |  | 297.2
2022 |  | 8 | 274.4 |  | 0.8 |  | 11.3 |  | 286.5 |  | 22.2 |  | 308.7
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | 3.5 |  | 3.5
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | 10.2 |  | 10.2
2025 |  | -- | -- |  | -- |  | 6.5 |  | 6.5 |  | -- |  | 6.5
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2027 |  | -- | 9.8 |  | -- |  | -- |  | 9.8 |  | -- |  | 9.8
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2030 |  | -- | 10.3 |  | -- |  | -- |  | 10.3 |  | -- |  | 10.3
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2033 |  | -- | 10.9 |  | -- |  | -- |  | 10.9 |  | -- |  | 10.9
2034 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2035 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2036 |  | -- | 11.5 |  | -- |  | -- |  | 11.5 |  | -- |  | 11.5
2037 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2038 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2039 |  | -- | 12.1 |  | -- |  | -- |  | 12.1 |  | -- |  | 12.1
2040 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2041 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2042 |  | -- | 12.8 |  | -- |  | -- |  | 12.8 |  | -- |  | 12.8
Subtotal |  | 45 | 1508.5 |  | 1.8 |  | 142.2 |  | 1652.5 |  | 239.7 |  | 1892.2

## Table 25
Annual Funding 1109 ¦ Procurement ¦ Procurement, Marine Corps
Fiscal Year | Quantity |  | BY 2012 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | -- |  | -- |  | 4.1 |  | 4.1 |  | -- |  | 4.1
2013 |  | 2 | 71.3 |  | -- |  | 10.2 |  | 81.5 |  | 1.7 |  | 83.2
2014 |  | 2 | 70.4 |  | -- |  | 10.1 |  | 80.5 |  | 8.7 |  | 89.2
2015 |  | 2 | 68.1 |  | -- |  | 6 |  | 74.1 |  | 11.1 |  | 85.2
2016 |  | 3 | 95.7 |  | -- |  | 10.6 |  | 106.3 |  | 10.6 |  | 116.9
2017 |  | 3 | 83.9 |  | 0.3 |  | 9.7 |  | 93.9 |  | 28.2 |  | 122.1
2018 |  | 3 | 79.1 |  | 0.2 |  | 9.7 |  | 89 |  | 39.6 |  | 128.6
2019 |  | 6 | 157.4 |  | -- |  | 17.8 |  | 175.2 |  | 27.5 |  | 202.7
2020 |  | 8 | 197.5 |  | 0.4 |  | 15.2 |  | 213.1 |  | 28.3 |  | 241.4
2021 |  | 8 | 206.7 |  | -- |  | 17.7 |  | 224.4 |  | 23.9 |  | 248.3
2022 |  | 8 | 224.8 |  | 0.7 |  | 9.3 |  | 234.8 |  | 18.1 |  | 252.9
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | 2.8 |  | 2.8
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | 8 |  | 8
2025 |  | -- | -- |  | -- |  | 5 |  | 5 |  | -- |  | 5
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2027 |  | -- | 7.3 |  | -- |  | -- |  | 7.3 |  | -- |  | 7.3
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2030 |  | -- | 7.2 |  | -- |  | -- |  | 7.2 |  | -- |  | 7.2
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2033 |  | -- | 7.2 |  | -- |  | -- |  | 7.2 |  | -- |  | 7.2
2034 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2035 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2036 |  | -- | 7.1 |  | -- |  | -- |  | 7.1 |  | -- |  | 7.1
2037 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2038 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2039 |  | -- | 7.1 |  | -- |  | -- |  | 7.1 |  | -- |  | 7.1
2040 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2041 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2042 |  | -- | 7.1 |  | -- |  | -- |  | 7.1 |  | -- |  | 7.1
Subtotal |  | 45 | 1297.9 |  | 1.6 |  | 125.4 |  | 1424.9 |  | 208.5 |  | 1633.4

## Table 26
Cost Quantity Information 1109 ¦ Procurement ¦ Procurement, Marine Corps
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2012 $M
2012 | -- | --
2013 | 2 | 73.1
2014 | 2 | 72
2015 | 2 | 69.6
2016 | 3 | 97.9
2017 | 3 | 87.3
2018 | 3 | 82.6
2019 | 6 | 163.3
2020 | 8 | 205
2021 | 8 | 214.2
2022 | 8 | 232.9
2023 | -- | --
2024 | -- | --
2025 | -- | --
2026 | -- | --
2027 | -- | --
2028 | -- | --
2029 | -- | --
2030 | -- | --
2031 | -- | --
2032 | -- | --
2033 | -- | --
2034 | -- | --
2035 | -- | --
2036 | -- | --
2037 | -- | --
2038 | -- | --
2039 | -- | --
2040 | -- | --
2041 | -- | --
2042 | -- | --
Subtotal | 45 | 1297.9

## Table 27
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
2016 3.9
Subtotal 3.9

## Table 28
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 2012 $M
Total Program
2016 3.5
Subtotal 3.5

## Table 29
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2014-03-10 | 2015-03-10
Approved Quantity | 4 | 6
Reference | MS C ADM | MS C ADM
Start Year | 2014 | 2016
End Year | 2014 | 2016
The Current Total LRIP Quantity is more than 10% of the total production quantity The MDA authorized additional LRIP units to mitigate risk associated with conversion to Gallium Arsenide (GaN) technology and associated testing.

## Table 30
Foreign Military Sales
None
Nuclear Costs
None

## Table 31
Unit Cost
Unit Cost Report
Item |  | BY 2012 $M | BY 2012 $M |  | % Change
|  | Current UCR Baseline (Apr 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2615.3 |  |  | 2626.5
Quantity | 45 |  |  | 45
Unit Cost | 58.118 |  |  | 58.367 |  | 0.43
Average Procurement Unit Cost
Cost | 1625.3 |  |  | 1633.4
Quantity | 45 |  |  | 45
Unit Cost | 36.118 |  |  | 36.298 |  | 0.5
Item |  | BY 2012 $M | BY 2012 $M |  | % Change
|  | Original UCR Baseline (May 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2987.3 |  |  | 2626.5
Quantity | 57 |  |  | 45
Unit Cost | 52.409 |  |  | 58.367 |  | 11.37
Average Procurement Unit Cost
Cost | 2103.1 |  |  | 1633.4
Quantity | 57 |  |  | 45
Unit Cost | 36.896 |  |  | 36.298 |  | -1.62

## Table 32
Unit Cost History
Item | [7 empty] | Date |  |  |  | BY 2012 $M | [7 empty] | TY $M
[12 empty] | PAUC |  | APUC | [5 empty] | PAUC |  |  |  | APUC
Original APB |  |  |  |  | May 2012 | [6 empty] | 52.409 |  |  |  |  | 36.896 |  |  |  | 58.349 |  |  |  | 42.665
APB as of January 2006 |  |  |  |  | N/A | [6 empty] | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Revised Original APB |  |  |  |  | N/A | [6 empty] | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | May 2012 | [6 empty] | 52.409 |  |  |  |  | 36.896 |  |  |  | 58.349 |  |  |  | 42.665
Current APB |  |  |  |  | Apr 2014 | [6 empty] | 58.118 |  |  |  |  | 36.118 |  |  |  | 64.842 |  |  |  | 42.107
Prior Annual SAR |  |  |  |  | Dec 2014 | [6 empty] | 58.111 |  |  |  |  | 36.078 |  |  |  | 64.787 |  |  |  | 42.098
Current Estimate |  |  |  |  | Dec 2015 | [6 empty] | 58.367 |  |  |  |  | 36.298 |  |  |  | 64.742 |  |  |  | 42.049
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [21 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth |  |  | Spt |  |  | Total
58.349 0.367 5.249 0.813 0.000 1.451 0.000 -1.387 6.493 64.842
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [19 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng | Est |  | Oth |  | Spt |  |  | Total
64.842 -0.807 0.000 -0.073 0.000 -2.067 0.000 2.847 -0.100 64.742

## Table 33
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [14 empty] | APUC Production Estimate
| Econ | Qty |  |  | Sch | Eng |  |  | Est |  | Oth |  | Spt |  | Total
42.665 0.276 1.067 0.813 0.000 -1.327 0.000 -1.387 -0.558 42.107
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [14 empty] | APUC Current Estimate
| Econ |  | Qty |  | Sch |  | Eng |  |  | Est |  | Oth |  | Spt | Total
42.107 -0.638 0.000 -0.073 0.000 -2.073 0.000 2.727 -0.057 42.049
SAR Baseline History
Item |  |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate | [5 empty] | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  |  | N/A |  |  |  | N/A | [5 empty] | N/A |  |  | N/A
Milestone B |  |  |  | N/A |  |  |  | Aug 2005 | [5 empty] | Aug 2005 |  |  | Aug 2005
Milestone C |  |  |  | N/A |  |  |  | Jul 2013 | [5 empty] | Mar 2014 |  |  | Mar 2014
IOC |  |  |  | N/A |  |  |  | Aug 2016 | [5 empty] | Feb 2017 |  |  | Feb 2018
Total Cost (TY $M) |  |  |  | N/A |  |  |  | 3325.9 | [5 empty] | 2917.9 |  |  | 2913.4
Total Quantity |  |  |  | N/A |  |  |  | 57 | [5 empty] | 45 |  |  | 45
PAUC |  |  |  | N/A |  |  |  | 58.349 | [5 empty] | 64.842 |  |  | 64.742

## Table 34
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 1019.2 | 1894.8 | 3.9 | 2917.9
Previous Changes
Economic | -5.1 | -14.7 | -0.1 | -19.9
Quantity | -- | -- | -- | --
Schedule | -- | -1.1 | -- | -1.1
Engineering | -- | -- | -- | --
Estimating | -2.4 | 5 | 0.1 | 2.7
Other | -- | -- | -- | --
Support | 5.4 | 10.4 | -- | 15.8
Subtotal | -2.1 | -0.4 | -- | -2.5
Current Changes
Economic | -2.4 | -14 | -- | -16.4
Quantity | -- | -- | -- | --
Schedule | -- | -2.2 | -- | -2.2
Engineering | -- | -- | -- | --
Estimating | 2.6 | -98.3 | -- | -95.7
Other | -- | -- | -- | --
Support | -- | 112.3 | -- | 112.3
Subtotal | 0.2 | -2.2 | -- | -2
Adjustments | -- | -- | -- | --
Total Changes | -1.9 | -2.6 | -- | -4.5
CE - Cost Variance | 1017.3 | 1892.2 | 3.9 | 2913.4
CE - Cost & Funding | 1017.3 | 1892.2 | 3.9 | 2913.4

## Table 35
Summary BY 2012 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
986.5 1625.3 3.5 2615.3
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -0.1 |  | -0.1
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 1.5 |  | -10.1 |  | 0.1 |  | -8.5
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 8.3 |  | -- |  | 8.3
Subtotal |  | 1.5 |  | -1.8 |  | -- |  | -0.3
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 1.6 |  | -89 |  | -- |  | -87.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 98.9 |  | -- |  | 98.9
Subtotal |  | 1.6 |  | 9.9 |  | -- |  | 11.5
Adjustments |  | -- |  | -- |  | -- |  | --
Total Changes |  | 3.1 |  | 8.1 |  | -- |  | 11.2
CE - Cost Variance |  | 989.6 |  | 1633.4 |  | 3.5 |  | 2626.5
CE - Cost & Funding |  | 989.6 |  | 1633.4 |  | 3.5 |  | 2626.5
Previous Estimate: December 2014

## Table 36
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | -2.4
Congressional Reduction in FY 2016 and FY 2019 with payback in FY 2018. (Estimating) |  | -0.7 | -0.2
Decreased estimate resulting from contract negotiations. (Estimating) |  | -8.3 | -8.9
Revised estimate to incorporate additional rigor of testing. (Estimating) |  | 5.5 | 6.3
Engineering Change Order/Engineering Change Proposal (ECO/ECP) costs increase as a |  | 8.4 | 10.1
function of Hardware procurement costs and rephasing of funding. (Estimating)
Revised estimate in FY 2013 to reflect actuals. (Estimating) |  | 0 | -0.1
Revised estimate for out-year ECO/ECP rates. (Estimating) |  | -4.6 | -5.9
Adjustment for current and prior escalation. (Estimating) |  | 1.3 | 1.3
RDT&E Subtotal |  | 1.6 | 0.2
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -14.0
Acceleration of procurement buy profile, moving 1 unit each from FY 2021 and FY 2022 to FY 2020 to achieve production rate efficiencies. (Schedule)
Updated estimating methodology factor to incorporate HW reliability metric trends, through delivery of the final production lot. (Estimating)
0.0 -2.2
-77.1 -88.1
Revised estimate due to Congressional reduction. (Estimating) -11.2 -12.4
Revised estimate and phasing for facilitization and training costs to support FOC. (Estimating)
+4.6 +6.4
Revised estimate due to surge in Post FOC ECO/ECP. (Estimating) | 5 |  |  | 6.5
Adjustment for current and prior escalation. (Estimating) | 2 |  |  | 2.1
Revised estimate reconcile POE to OSD out-year inflation. (Estimating) | 0.5 |  |  | 0.8
Revised estimate in FY 2013 through FY 2015 to reflect actuals. (Estimating) | -12.8 |  |  | -13.6
Increase to Other Support due to refined estimate in HW costs and the associated factor used in the estimating methodology through delivery of the final production lot. (Support) | 118 |  |  | 135.2
Decrease in Initial Spares due to Congressional reduction. (Support) | -19.1 |  |  | -22.9
Procurement Subtotal | 9.9 |  |  | -2.2

## Table 37
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: LRIP GaAs
Contractor: Northrop Grumman Corporation
Contractor Location: 1580 West Nursery Road
Linthicum Heights, MD 21090
Contract Number: M67854-07-C-2072/4
Contract Type: Fixed Price Incentive(Firm Target) (FPIF), Firm Fixed Price (FFP), Cost Plus Incentive Fee (CPIF)
Award Date: October 23, 2014
Definitization Date: October 23, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
0.0 207.3 4 327.1 340.2 6 325.0 327.1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to an omission of target cost during data entry at initial contract award.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/29/2016) +2.0 -17.1
Previous Cumulative Variances 0.0 0.0
Net Change +2.0 -17.1
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to cost savings associated with change in supplier, new machining process, and decrease in ramp up of staffing.
The unfavorable cumulative schedule variance is due to material supply chain management delays.

## Table 38
Contract Identification
Appropriation: RDT&E
Contract Name: Ground Weapons Locating Radar (GWLR) GB2
Contractor: Northrop Grumman Corporation
Contractor Location: 1580 West Nursery Road
Linthicum Heights, MD 21090
Contract Number: M67854-15-C-0230/7 Contract Type: Cost Plus Incentive Fee (CPIF) Award Date: August 28, 2015
Definitization Date: August 28, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
58.7 N/A 0 58.7 N/A 0 58.7 58.7
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/29/2016) 0.0 -0.4
Previous Cumulative Variances -- --
Net Change +0.0 -0.4
Cost and Schedule Variance Explanations
The unfavorable cumulative schedule variance is due to limited performance taken on subcontractor tasks.
Notes
This is the first time this contract is being reported.

## Table 39
Contract Identification
Appropriation: RDT&E
Contract Name: GaN Transition Phase 2
Contractor: Northrop Grumman Corporation
Contractor Location: 1580 West Nursery Road
Linthicum Heights, MD 21090
Contract Number: M67854-07-C-2072/8
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: August 28, 2015
Definitization Date: August 28, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
9.2 N/A 0 9.2 N/A 0 9.2 9.2
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/29/2016) +0.3 -0.5
Previous Cumulative Variances -- --
Net Change +0.3 -0.5
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to efficiencies gained through elimination of redundancy in test planning efforts.
The unfavorable cumulative schedule variance is due to delay in staffing up resources to plan as well as late material receipts.
Notes
This is the first time this contract is being reported.

## Table 40
Contract Identification
Appropriation: RDT&E
Contract Name: OCC Migration Phase II
Contractor: Northrop Grumman Corporation
Contractor Location: 1580 West Nursery Road
Linthicum Heights, MD 21090
Contract Number: M67854-07-C-2072/5
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: December 03, 2014
Definitization Date: December 03, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
10.2 N/A 0 10.8 N/A 0 10.8 10.8
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to Authorized Undefinitized Work (AUW) at initial contract award.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/29/2016) 0.0 -0.1
Previous Cumulative Variances -- --
Net Change +0.0 -0.1
Cost and Schedule Variance Explanations
The unfavorable cumulative schedule variance is due to late subcontractor receipts and inability to staff to plan.
Notes
This is the first time this contract is being reported.

## Table 41
Contract Identification
Appropriation: RDT&E
Contract Name: Reliability Phase II
Contractor: Northrop Grumman Corporation
Contractor Location: 1580 West Nursery Road
Linthicum Heights, MD 21090
Contract Number: M67854-07-C-2072/6
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: March 30, 2015
Definitization Date: March 31, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
15.3 N/A 0 15.3 N/A 0 15.3 15.3
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/29/2016) +0.1 0.0
Previous Cumulative Variances -- --
Net Change +0.1 +0.0
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to completion of software change request at a greater efficiency.
Notes
This is the first time this contract is being reported.

## Table 42
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 45 | 0 | 45 | 0%
Total Program Quantity Delivered | 45 | 0 | 45 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
2913.4
740.9
25.43%
41
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
13
31.71%
1222.3
41.95%
The above data is current as of January 05, 2016.

## Table 43
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 12, 2016
Source of Estimate: POE
Quantity to Sustain: 45
Unit of Measure: System
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2016 - FY 2044
A system consists of the Radar Equipment Group, the Communications Equipment Group and the Power Equipment Group.
Sustainment Strategy
The sustainment strategy includes organic support with contract support for the depot level. Current Product Support Strategy employs Contractor Logistics Support (CLS) during the EMD phase to provide support for the two Engineering Development Models and up to eight LRIP systems. Interim CLS will be provided as part of the FRP contract. During production some components may remain under CLS, others may transition to Performance Based Logistics and others may transition to traditional organic support.
Antecedent Information
The AN/TPS-63B Radar is the antecedent system. There is no data in the Naval Visibility and Management of Operating and Support Costs database for the antecedent system.
Annual O&S Costs BY2012 $M
Cost Element | G/ATOR Average Annual Cost Per System | AN/TPS-63B Radar (Antecedent) Average Annual Cost Per System
Unit-Level Manpower | 0.25 | 0
Unit Operations | 0.013 | 0
Maintenance | 1.261 | 0
Sustaining Support | 0.596 | 0
Continuing System Improvements | 0.712 | 0
Indirect Support | 0.033 | 0
Other | -- | --
Total | 2.865 | --
The G/ATOR profile reflects a 20-year Life Cycle Cost and is based upon the Operations and Support developed jointly by NCCA and the program office. The data reflected to date includes fact of life changes incorporated during the last Program Office Estimate review.

## Table 44
Item | Total O&S Cost $M
| G/ATOR | [5 empty] | AN/TPS-63B Radar (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 2522.6 |  | 2774.9 |  |  | 2578.5 | 0
Then Year | 3326.3 |  | N/A |  |  | 3616.2 | N/A
Disposal Cost is included in the Operating and Support Cost of the current APB objective and threshold for this program.
Equation to Translate Annual Cost to Total Cost
Total O&S cost = Average Annual Cost Per System * # of systems * Service Life = $2.865M * 45 * 20 = $2578.5M
O&S Cost Variance
Category |  | BY 2012 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
2519.4
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 59.1 Revised methodology for reliability and maintainability, sustaining engineering and software maintenance. Revised methodology is a more applicable cost estimating relationship based on historical costs. Also includes revised manpower projection associated with software support activity.
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 59.1
Current Estimate 2578.5
Disposal Estimate Details
Date of Estimate: January 12, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2012 $M): Total costs for disposal of all System are 2.9
TY Total disposal cost are $5.2M.