## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-542
LPD 17 San Antonio Class Amphibious Transport Dock (LPD 17)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 12
Track to Budget 14
Cost and Funding 15
Low Rate Initial Production 22
Foreign Military Sales 23
Nuclear Costs 23
Unit Cost 24
Cost Variance 27
Contracts 30
Deliveries and Expenditures 33
Operating and Support Cost 34

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
LPD 17 San Antonio Class Amphibious Transport Dock (LPD 17)
DoD Component
Navy
Responsible Office
CAPT Darren Plath
LPD 17 Amphibious Transport Dock Ship Program Office (PMS317) PEO Ships
Washington, DC 20376-2401
darren.plath@navy.mil
Phone: 202-781-0159
Fax:
DSN Phone: 326-0159
DSN Fax:
Date Assigned: August 27, 2012
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated June 17, 1996
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated March 25, 2015

## Table 6
Mission and Description
The LPD 17 San Antonio Class Amphibious Transport Dock Ship (LPD 17) is the functional replacement for the LPD 4, LSD 36, LKA 113, and LST 1179 Classes of Amphibious Ships for embarking, transporting and landing elements of a Marine landing force in an assault by helicopters, landing craft, amphibious vehicles, and by a combination of these methods to conduct the primary amphibious warfare mission.

## Table 7
Executive Summary
Stability in ship construction and sustained operational availability above 90% have characterized the LPD 17 program over the past year. Nine LPD 17 class ships are operating as Fleet assets; and the two ships in construction are projected to deliver below the contract ceiling price.
USS SOMERSET (LPD 25) was officially transferred to the in-service program office in July 2015.
As of December 2015, LPD 26 and LPD 27 were 94% and 69% complete, respectively. The FY 2017 PB request includes cost to complete funding to cover cost growth associated with rate and Estimate at Completion increases on LPD 27.
The FY 2015 Consolidated Appropriations Act provided $1B for the twelfth LPD 17 class ship (LPD 28); and the balance of full funding was appropriated in FY 2016. An Undefinitized Contract Action for Long Lead Time Material on LPD 28 was awarded in December 2015; and the Request for Proposal for Detail Design and Construction of the ship was released, on a sole-source basis, to Huntington Ingalls Industries on January 6, 2016.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule

## Table 10
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone I | Jan 1993 | Jan 1993 | Jul 1993 | Jan 1993
DT&E (DT-I)
Start | Mar 1993 | Mar 1993 | Sep 1993 | Mar 1993
Complete | Feb 1996 | Feb 1996 | Aug 1996 | Feb 1996
OT&E (OT-IA)
Start | Jan 1995 | Jan 1995 | Jul 1995 | Jan 1995
Complete | Mar 1995 | Mar 1995 | Sep 1995 | Mar 1995
OT&E (OT-IB)
Start | Feb 1996 | Feb 1996 | Aug 1996 | Feb 1996
Complete | Apr 1996 | Apr 1996 | Oct 1996 | Apr 1996
Milestone II | Jun 1996 | Jun 1996 | Dec 1996 | Jun 1996
Lead Ship Award | Aug 1996 | Aug 1996 | Feb 1997 | Dec 1996
DT&E (DT-IIA)
Start | Sep 1996 | Apr 1997 | Oct 1997 | Apr 1997
Complete | Aug 1998 | Mar 2003 | Sep 2003 | Mar 2003
OT&E (OT-IC)
Start | Sep 1998 | N/A | N/A | N/A
Complete | Mar 1999 | N/A | N/A | N/A
OT&E (OT-IIA)
Start | Jun 2003 | May 1999 | Nov 1999 | May 1999
Complete | Sep 2003 | May 2000 | Nov 2000 | May 2000
DIT (OT-IIB)
Start | N/A | Jan 2002 | Jul 2002 | Jan 2002
Complete | N/A | Mar 2003 | Sep 2003 | May 2003
DT&E (DT-IIB)
Start | Sep 1998 | Sep 2002 | Mar 2003 | Sep 2002
Complete | Jun 2002 | Jul 2005 | Jan 2006 | Jul 2005
Lead Ship Delivery | Jun 2002 | Jul 2005 | Jan 2006 | Jul 2005
DT&E (DT-IIC)
Start | Jul 2002 | Jul 2005 | Jan 2006 | Jul 2005
Complete | Jan 2004 | Nov 2006 | May 2007 | May 2007
IOT&E (OT-IIC)
Start | N/A | Jan 2006 | Jul 2006 | Jan 2006
Complete | N/A | Oct 2008 | Apr 2009 | Dec 2008
Milestone III | Aug 2007 | N/A | N/A | N/A

## Table 11
LEAD SHIP IOC | Jan 2004 | Apr 2008 | Oct 2008 | Apr 2008
FOT&E (OT-III)
Start | Jan 2011 | Jul 2010 | Jan 2011 | Jul 2010
Change Explanations
None
Acronyms and Abbreviations
DIT - Design Integration Testing DT - Developmental Test
DT&E - Developmental Test and Evaluation
FOT&E - Follow-on Operational Test and Evaluation IOT&E - Initial Operational Test and Evaluation
OT - Operational Test
OT&E - Operational Test and Evaluation

## Table 12
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Mobility
Sustained Speed (Kts)
23 | 23 | 21.5 | 24 | 24
Endurance ((NM)(K) @ Kts)
10/22 | 10/22 | 9.5/20 | 10.6/20 | 10.6/20
Amphibious Warfare Embarkation (Net)
Troops
750 | 750 | 650 | 720 | 720
Vehicles (Sq Ft)(k)
25 | 25 | 22 | 22 | 22
Cargo (Cubic Feet)(k)
25 | 25 | 22 | 34 | 34
Bulk Fuel (Gals)(k)
325 | 325 | 250 | 307 | 307
LCAC
2 | 2 | 1(+1) | 2 | 2
VTOL Land/Launch Spots (CH-46 or CH-53E or MV-22)
2002-04-03 | 2002-04-03 | 2002-04-02 | 2002-04-02 | 2002-04-02
VTOL Maint/Storage (CH-46 or CH-53E or MV-22)
2001-03-01 | 2001-03-01 | 2001-02-01 | 2001-02-01 | 2001-02-01
Ship To Shore Capability (LCAC)
Sustained Operations (reload 6 LCACs)(mins)
220 | 220 | 285 | 274 | 274
Operational Availability (Ao)
0.9 | 0.9 | 0.8 | 0.92 | 0.91
(Ch-1)
Requirements Reference
Operational Requirements Document (ORD) Revision 3 dated April 8, 1996

## Table 13
Change Explanations
(Ch-1) Current estimate for Operational Availability changed from .90 to .91 to reflect the calculation for the LPD 17 class as of December 31, 2015.
Notes
Demonstrated Performance for Sustained Speed and Vehicles (Sq Ft) reflect performance during LPD 17 BT.
Demonstrated Performance for Troops, Cargo (Cubic Feet), LCAC, and VTOL Land/Launch Spots reflect measurements taken during LPD 17 Sail Away Trials.
Demonstrated Performance for Bulk Fuel, VTOL Maint/Storage, and Sustained Operations reflect performance during LPD 17 Class IOT&E events.
Demonstrated Performance for Ao reflects performance cited in the LPD 17 Class OPEVAL report dated January 2010.
Acronyms and Abbreviations
Ao - Operational Availability BT - Builder's Trials
Gals - gallons
IOT&E - Initial Operational Test and Evaluation K/k - Thousands
Kts - Knots
LCAC - Landing Craft Air Cushion mins - minutes
NM - Nautical Miles
OPEVAL - Operational Evaluation Sq Ft - square feet
VTOL - Vertical Take-Off and Landing

## Table 14
Track to Budget
RDT&E
Appn |  | BA | PE
Navy 1319 05 0604311N
Project Name
2283 LPD 17 Class Systems Integration (Shared) (Sunk)
Procurement
Appn |  | BA | PE
Navy 1611 01 0204411N
| Line Item |  | Name
| 946 |  | LPD 17 Class Support Equipment | (Shared)
| 981 |  | Items Less Than $5M | (Shared) (Sunk)
Navy | 1611 03 |  | 0204411N
| Line Item |  | Name
| 3036 |  | LPD-17
Navy | 1611 05 |  | 0204411N
| Line Item |  | Name
| 5110 |  | Outfitting | (Shared)
| 5300 |  | Completion of Prior Year Shipbuilding Programs | (Shared)
Notes
Funding in BA 01 / Line Item 0981 and BA 01 / Line Item 0946 is Other Procurement, Navy funding for non-acquisition related efforts and is not included in the APB objective.

## Table 15
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 1996 $M | [5 empty] | BY 1996 $M |  | TY $M
| SAR Baseline Development Estimate |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E | 78.7 |  |  | 111.3 | 122.4 |  |  | 116.1 |  | 77.8 |  |  | 114 |  | 120.1
Procurement | 8939.4 |  |  | 15281.2 | 16809.3 |  |  | 15146.1 |  | 10684 |  |  | 20817.5 |  | 20591.4
Flyaway | -- |  |  | -- | -- |  |  | 15146.1 |  | -- |  |  | -- |  | 20591.4
Recurring | -- |  |  | -- | -- |  |  | 15146.1 |  | -- |  |  | -- |  | 20591.4
Non Recurring | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Other Support | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Initial Spares | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
MILCON | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 9018.1 |  |  | 15392.5 | N/A |  |  | 15262.2 |  | 10761.8 |  |  | 20931.5 |  | 20711.5
Current APB Cost Estimate Reference
Program Office Estimate dated February 13, 2015
Confidence Level
Confidence Level of cost estimate for current APB: 95%
The confidence level is supported by the maturity level of the program which is 75% delivered. The tenth and eleventh ships are in construction under fixed price contracts; the last ship of the class is incrementally funded in FY 2015/2016.
Total Quantity
Quantity |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  | 12 |  |  |  | 12 |  |  |  |  | 12
Total |  | 12 |  |  |  | 12 |  |  |  |  | 12

## Table 16
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 120.1 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 120.1
Procurement | 19791.3 | 655.2 |  |  | 114.7 | 30.2 | 0 |  | 0 |  | 0 |  | 0 |  | 20591.4
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 19911.4 | 655.2 |  |  | 114.7 | 30.2 | 0 |  | 0 |  | 0 |  | 0 |  | 20711.5
PB 2016 Total | 19910.2 | 668 |  |  | 110.6 | 30.4 | 0 |  | 0 |  | 0 |  | 0 |  | 20719.2
Delta | 1.2 | -12.8 |  |  | 4.1 | -0.2 | 0 |  | 0 |  | 0 |  | 0 |  | -7.7
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Production | 0 |  | 11 |  | 1 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 12
PB 2017 Total | 0 |  | 11 |  | 1 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 12
PB 2016 Total | 0 |  | 11 |  | 1 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 12
Delta | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Table 17
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.9
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.2
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.3
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.8
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.2
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.3
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.9
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.3
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.3
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.6
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.4
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.8
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 120.1

## Table 18
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 1996 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.6
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.4
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.3
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.8
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.7
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.9
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.1
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.2
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.5
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.2
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.2
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.1
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.7
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.4
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.1
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.9
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.1
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 116.1

## Table 19
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1996 |  | 1 | 1051.9 |  | -- |  | -- |  | 1051.9 |  | -- |  | 1051.9
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1998 |  | -- | 96 |  | -- |  | -- |  | 96 |  | -- |  | 96
1999 |  | 1 | 653.2 |  | -- |  | -- |  | 653.2 |  | -- |  | 653.2
2000 |  | 2 | 1557.6 |  | -- |  | -- |  | 1557.6 |  | -- |  | 1557.6
2001 |  | -- | 592.3 |  | -- |  | -- |  | 592.3 |  | -- |  | 592.3
2002 |  | -- | 418.5 |  | -- |  | -- |  | 418.5 |  | -- |  | 418.5
2003 |  | 1 | 1240.8 |  | -- |  | -- |  | 1240.8 |  | -- |  | 1240.8
2004 |  | 1 | 1654.8 |  | -- |  | -- |  | 1654.8 |  | -- |  | 1654.8
2005 |  | 1 | 1314.2 |  | -- |  | -- |  | 1314.2 |  | -- |  | 1314.2
2006 |  | 1 | 3303 |  | -- |  | -- |  | 3303 |  | -- |  | 3303
2007 |  | -- | 468.7 |  | -- |  | -- |  | 468.7 |  | -- |  | 468.7
2008 |  | 1 | 1601 |  | -- |  | -- |  | 1601 |  | -- |  | 1601
2009 |  | 1 | 1047.2 |  | -- |  | -- |  | 1047.2 |  | -- |  | 1047.2
2010 |  | -- | 1234.1 |  | -- |  | -- |  | 1234.1 |  | -- |  | 1234.1
2011 |  | -- | 61.9 |  | -- |  | -- |  | 61.9 |  | -- |  | 61.9
2012 |  | 1 | 1969.7 |  | -- |  | -- |  | 1969.7 |  | -- |  | 1969.7
2013 |  | -- | 391.4 |  | -- |  | -- |  | 391.4 |  | -- |  | 391.4
2014 |  | -- | 57.9 |  | -- |  | -- |  | 57.9 |  | -- |  | 57.9
2015 |  | -- | 1077.1 |  | -- |  | -- |  | 1077.1 |  | -- |  | 1077.1
2016 |  | 1 | 655.2 |  | -- |  | -- |  | 655.2 |  | -- |  | 655.2
2017 |  | -- | 114.7 |  | -- |  | -- |  | 114.7 |  | -- |  | 114.7
2018 |  | -- | 30.2 |  | -- |  | -- |  | 30.2 |  | -- |  | 30.2
Subtotal |  | 12 | 20591.4 |  | -- |  | -- |  | 20591.4 |  | -- |  | 20591.4

## Table 20
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | BY 1996 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1996 |  | 1 | 1024.9 |  | -- |  | -- |  | 1024.9 |  | -- |  | 1024.9
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1998 |  | -- | 90.1 |  | -- |  | -- |  | 90.1 |  | -- |  | 90.1
1999 |  | 1 | 603.5 |  | -- |  | -- |  | 603.5 |  | -- |  | 603.5
2000 |  | 2 | 1403.4 |  | -- |  | -- |  | 1403.4 |  | -- |  | 1403.4
2001 |  | -- | 515.9 |  | -- |  | -- |  | 515.9 |  | -- |  | 515.9
2002 |  | -- | 362.5 |  | -- |  | -- |  | 362.5 |  | -- |  | 362.5
2003 |  | 1 | 1015.9 |  | -- |  | -- |  | 1015.9 |  | -- |  | 1015.9
2004 |  | 1 | 1307.4 |  | -- |  | -- |  | 1307.4 |  | -- |  | 1307.4
2005 |  | 1 | 994.2 |  | -- |  | -- |  | 994.2 |  | -- |  | 994.2
2006 |  | 1 | 2413.7 |  | -- |  | -- |  | 2413.7 |  | -- |  | 2413.7
2007 |  | -- | 327.5 |  | -- |  | -- |  | 327.5 |  | -- |  | 327.5
2008 |  | 1 | 1081.7 |  | -- |  | -- |  | 1081.7 |  | -- |  | 1081.7
2009 |  | 1 | 686.4 |  | -- |  | -- |  | 686.4 |  | -- |  | 686.4
2010 |  | -- | 781.5 |  | -- |  | -- |  | 781.5 |  | -- |  | 781.5
2011 |  | -- | 38 |  | -- |  | -- |  | 38 |  | -- |  | 38
2012 |  | 1 | 1181.2 |  | -- |  | -- |  | 1181.2 |  | -- |  | 1181.2
2013 |  | -- | 230.1 |  | -- |  | -- |  | 230.1 |  | -- |  | 230.1
2014 |  | -- | 33.4 |  | -- |  | -- |  | 33.4 |  | -- |  | 33.4
2015 |  | -- | 611 |  | -- |  | -- |  | 611 |  | -- |  | 611
2016 |  | 1 | 364.9 |  | -- |  | -- |  | 364.9 |  | -- |  | 364.9
2017 |  | -- | 62.7 |  | -- |  | -- |  | 62.7 |  | -- |  | 62.7
2018 |  | -- | 16.2 |  | -- |  | -- |  | 16.2 |  | -- |  | 16.2
Subtotal |  | 12 | 15146.1 |  | -- |  | -- |  | 15146.1 |  | -- |  | 15146.1

## Table 21
Cost Quantity Information 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 1996 $M
1996 | 1 | 1812.3
1997 | -- | --
1998 | -- | --
1999 | 1 | 1160.9
2000 | 2 | 2343.3
2001 | -- | --
2002 | -- | --
2003 | 1 | 1318.7
2004 | 1 | 1250.8
2005 | 1 | 1135.1
2006 | 1 | 1219.4
2007 | -- | --
2008 | 1 | 1302.5
2009 | 1 | 1299
2010 | -- | --
2011 | -- | --
2012 | 1 | 1287.8
2013 | -- | --
2014 | -- | --
2015 | -- | --
2016 | 1 | 1016.3
2017 | -- | --
2018 | -- | --
Subtotal | 12 | 15146.1

## Table 22
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 1996-06-17 | 1996-06-17
Approved Quantity | 12 | 12
Reference | Milestone II ADM | Milestone II ADM
Start Year | 1996 | 1996
End Year | 2016 | 2016
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the ADM dated June 17, 1996 approving 12 LRIP ships which is standard for shipbuilding programs.

## Table 23
Foreign Military Sales
None
Nuclear Costs
None

## Table 24
Unit Cost
Unit Cost Report
Item |  | BY 1996 $M | BY 1996 $M |  | % Change
|  | Current UCR Baseline (Mar 2015 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 15392.5 |  |  | 15262.2
Quantity | 12 |  |  | 12
Unit Cost | 1282.708 |  |  | 1271.85 |  |  | -0.85
Average Procurement Unit Cost
Cost | 15281.2 |  |  | 15146.1
Quantity | 12 |  |  | 12
Unit Cost | 1273.433 |  |  | 1262.175 |  |  | -0.88
Item |  | BY 1996 $M | BY 1996 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Oct 2005 APB)
Program Acquisition Unit Cost
Cost | 12955.2 |  |  | 15262.2
Quantity | 12 |  |  | 12
Unit Cost | 1079.6 |  |  | 1271.85 |  | 17.81
Average Procurement Unit Cost
Cost | 12842.4 |  |  | 15146.1
Quantity | 12 |  |  | 12
Unit Cost | 1070.2 |  |  | 1262.175 |  | 17.94

## Table 25
Unit Cost History
Item |  |  |  | Date |  |  | BY 1996 $M | [5 empty] | TY $M
[7 empty] | PAUC |  |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Jun 1996 |  |  |  | 751.508 |  |  |  | 744.95 |  |  | 896.817 |  |  | 890.333
APB as of January 2006 |  |  | Oct 2005 |  |  |  | 1079.6 |  |  |  | 1070.2 |  |  | 1283.233 |  |  | 1273.642
Revised Original APB |  |  | Oct 2005 |  |  |  | 1079.6 |  |  |  | 1070.2 |  |  | 1283.233 |  |  | 1273.642
Prior APB |  |  | Sep 2011 |  |  |  | 1314.4 |  |  |  | 1304.282 |  |  | 1711.636 |  |  | 1701.273
Current APB |  |  | Mar 2015 |  |  |  | 1282.708 |  |  |  | 1273.433 |  |  | 1744.292 |  |  | 1734.792
Prior Annual SAR |  |  | Dec 2014 |  |  |  | 1272.692 |  |  |  | 1263.017 |  |  | 1726.6 |  |  | 1716.592
Current Estimate |  |  | Dec 2015 |  |  |  | 1271.85 |  |  |  | 1262.175 |  |  | 1725.958 |  |  | 1715.95
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  |  | Sch | Eng |  | Est | Oth |  |  | Spt | Total
896.817 85.308 -68.184 84.192 0.000 538.108 189.842 -0.125 829.141 1725.958
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch | Eng |  | Est | Oth |  |  | Spt | Total
890.333 85.292 -68.183 83.683 0.000 535.108 189.842 -0.125 825.617 1715.950

## Table 26
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone I | Jan 1993 | Jan 1993 | N/A | Jan 1993
Milestone II | Jul 1995 | Jun 1996 | N/A | Jun 1996
Milestone III | Oct 2003 | Aug 2007 | N/A | N/A
IOC | Oct 2003 | Jan 2004 | N/A | Apr 2008
Total Cost (TY $M) | 59.1 | 10761.8 | N/A | 20711.5
Total Quantity | N/A | 12 | N/A | 12
PAUC | N/A | 896.817 | N/A | 1725.958

## Table 27
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
77.8 10684.0 -- 10761.8
Economic |  | 0.2 |  | 1013.8 |  | -- |  | 1014
Quantity |  | -- |  | -818.2 |  | -- |  | -818.2
Schedule |  | 6.1 |  | 1004.2 |  | -- |  | 1010.3
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 36 |  | 6438.7 |  | -- |  | 6474.7
Other |  | -- |  | 2278.1 |  | -- |  | 2278.1
Support |  | -- |  | -1.5 |  | -- |  | -1.5
Subtotal |  | 42.3 |  | 9915.1 |  | -- |  | 9957.4
Current Changes Economic |  | -- |  | 9.7 |  | -- |  | 9.7
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | -17.4 |  | -- |  | -17.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -- |  | -7.7 |  | -- |  | -7.7
Total Changes |  | 42.3 |  | 9907.4 |  | -- |  | 9949.7
CE - Cost Variance |  | 120.1 |  | 20591.4 |  | -- |  | 20711.5
CE - Cost & Funding |  | 120.1 |  | 20591.4 |  | -- |  | 20711.5

## Table 28
Summary BY 1996 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
78.7 8939.4 -- 9018.1
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -946.2 |  | -- |  | -946.2
Schedule |  | 4.8 |  | 461.6 |  | -- |  | 466.4
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 32.6 |  | 5049.7 |  | -- |  | 5082.3
Other |  | -- |  | 1651.7 |  | -- |  | 1651.7
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 37.4 |  | 6216.8 |  | -- |  | 6254.2
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | -10.1 |  | -- |  | -10.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -- |  | -10.1 |  | -- |  | -10.1
Total Changes |  | 37.4 |  | 6206.7 |  | -- |  | 6244.1
CE - Cost Variance |  | 116.1 |  | 15146.1 |  | -- |  | 15262.2
CE - Cost & Funding |  | 116.1 |  | 15146.1 |  | -- |  | 15262.2
Previous Estimate: December 2014

## Table 29
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 9.7
Miscellaneous adjustments to post delivery and outfitting. (Estimating) | -4.6 | -7.9
Adjustment for current and prior escalation. (Estimating) | -5.5 | -9.5
Procurement Subtotal | -10.1 | -7.7

## Table 30
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: LPD 26
Contractor: Huntington Ingalls Industries
Contractor Location: 1000 Access Road
Pascagoula, MS 39567-0149
Contract Number: N00024-06-C-2222/26
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: April 01, 2011
Definitization Date: April 01, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1487.2 1690.0 1 1519.4 1725.9 1 1593.9 1577.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the incorporation of engineering change proposals and negotiation of contract price adjustments to cover the Navy's shares of corporate office and general insurance expenses following completion of the spin-off of Northrop Grumman's shipbuilding division and deferred depreciation expenses for recovery of insurance proceeds associated with Hurricane Katrina damages.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) -116.9 +2.0
Previous Cumulative Variances -96.6 +12.7
Net Change -20.3 -10.7
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to the requirement for additional supervision and rework driven by the level of inexperienced personnel in some crafts, increased work scope driven by the implementation of production improvements, and excessive weather conditions, which drove schedule delays in the earlier stages of construction.
The unfavorable net change in the schedule variance is due to coordination challenges, both internal and external, driven by inconsistent material availability and facility capacity.

## Table 31
Notes
LPD 26 construction is being performed at Huntington Ingalls Industries, Pascagoula Operations.
The program manager's estimated price at completion includes the estimate of the government liability for a contract clause associated with the Avondale restructuring/closure and the implementation of changes to safety regulations and federal law associated with the Occupational Safety and Health Administration and the Pension Protection Act. The government liability for deferred depreciation from Hurricane Katrina was negotiated lower than the original estimate; and the current estimate of the government liability for the Avondale restructuring/closure is also lower than the initial estimate.
Cost growth can be attributed to overhead rate increases, unforeseen craft inefficiencies, engineering overruns, and material escalation.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 32
Contract Identification
Appropriation: Procurement
Contract Name: LPD 27
Contractor: Huntington Ingalls Industries
Contractor Location: 1000 Access Road
Pascagoula, MS 39567-0149
Contract Number: N00024-06-C-2222/27
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: July 27, 2012
Definitization Date: July 27, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1507.1 1692.2 1 1508.9 1694.2 1 1582.5 1549.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the incorporation of engineering change proposals and negotiation of a contract price adjustment to cover the Navy's share of deferred depreciation expenses for recovery of insurance proceeds associated with Hurricane Katrina damages.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) -108.3 -13.2
Previous Cumulative Variances -84.9 +5.8
Net Change -23.4 -19.0
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to the assignment of additional supervision to overcome training issues driven by new or inexperienced employees hired to address increased workload capacity and the execution of work in areas subject to inclement weather.
The unfavorable net change in the schedule variance is due to the unavailability of cable for scheduled hook-up/installation, which was partially driven by overly aggressive plans in select crafts.
Notes
LPD 27 construction is being performed at Huntington Ingalls Industries, Pascagoula Operations.
The program manager's estimated price at completion includes the estimate of the government liability for a contract clause associated with the Avondale restructuring/closure. The government liability for deferred depreciation from Hurricane Katrina was negotiated lower than the original estimate; and the current estimate of the government liability for the Avondale restructuring/closure is also lower than the initial estimate.
Cost growth can be attributed to early challenges in facility capacity, including weathered and congested work areas, and the use of inexperienced labor.

## Table 33
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 9 | 9 | 12 | 75%
Total Program Quantity Delivered | 9 | 9 | 12 | 75%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
20711.5
17576
84.86%
29
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
27
93.1%
20566.6
99.3%
The above data is current as of January 15, 2016.

## Table 34
Operating and Support Cost
Cost Estimate Details
Date of Estimate: February 04, 2016
Source of Estimate: POE
Quantity to Sustain: 12
Unit of Measure: Ship
Service Life per Unit: 40.00 Years
Fiscal Years in Service: FY 2005 - FY 2061
The cost element data for the LPD 17 class was pulled from the Naval Visibility and Management of Operating & Support Costs (VAMOSC) database. The average annual costs per LPD 17 class ship are based on actual VAMOSC data from 2006 through 2015.
Average crew size for an LPD 17 class ship is 382.
The increase in the average crew size was driven by additional manning requirements related to system upgrades and the results of Navy Manpower Analysis Center studies which identified, and subsequently corrected, other manning deficiencies.
Sustainment Strategy
Life cycle engineering and support contracts with the shipbuilder and the Integrated Shipboard Electronics contractor, along with In Service Engineering Agent support contracts, are in place to support sustainment efforts.
Responsibilities have been divided to leverage strengths; the shipbuilder maintains the planning yard while the program office manages life-cycle maintenance, modernization, and logistics. Phased maintenance and dry dock availabilities are planned on a standard cycle; and continuous maintenance availabilities are conducted in between.
Antecedent Information
The LPD 4 class is one of the four amphibious ship classes being functionally replaced by the LPD 17 class. The cost element data for the LPD 4 class was pulled from the Naval VAMOSC database for all available years of data; the average annual costs per LPD 4 class ship were based on all available years of data. The current estimate includes 12 ships and a 40-year life cycle to mirror the LPD 17 class profile and expected service life. The estimate also incorporated actual LPD 4 commissioning and decommissioning profiles. The average annual costs per LPD 4 class ship were calculated in BY 1996 dollars for each cost element.
The cost element estimates for the LPD 4 class were not revised from last year’s SAR submission as all, but one, LPD 4 class ships were decommissioned prior to 2013. USS DENVER was decommissioned in August 2014.
Average crew size for an LPD 4 class ship was 364.

## Table 35
Annual O&S Costs BY1996 $M
Cost Element |  | LPD 17 Average Annual Cost Per Ship | [5 empty] | LPD 4 (Antecedent) Average Annual Cost Per Ship
Unit-Level Manpower |  | 16.1 | [5 empty] | 12.3
Unit Operations |  | 4.8 | [5 empty] | 3.9
Maintenance |  | 8.7 | [5 empty] | 8.6
Sustaining Support |  | 1.2 | [5 empty] | 0.9
Continuing System Improvements |  | 1.7 | [5 empty] | 2.4
Indirect Support |  | 10.3 | [5 empty] | 8.3
Other |  | 0 | [5 empty] | 0
Total |  | 42.8 | [5 empty] | 36.4
Item | Total O&S Cost $M
| LPD 17 | [7 empty] | LPD 4 (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | N/A |  |  | N/A |  |  | 20544 |  | 17472
Then Year | N/A |  |  | N/A |  |  | 48161 |  | N/A
Equation to Translate Annual Cost to Total Cost
The total O&S cost estimates for both the LPD 17 class and LPD 4 class are based on 12 ships over the same 40-year life cycle timeframe. The estimates were calculated using the following formula.
(Total Average Annual Cost per Hull x 12 hulls x 40 years)
LPD 17: $42.8M x 12 x 40 = $20,544M
LPD 4: $36.4M x 12 x 40 = $17,472M
O&S Cost Variance
Category |  |  | BY 1996 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
17820
Programmatic/Planning Factors 1712.0 Quantity profile increase from 11 to 12 ships. Cost Estimating Methodology 0.0
Cost Data Update 704.0 Additional years of data incorporated in determination of estimate.
Labor Rate 0.0
Energy Rate 0.0
Technical Input 308.0 Technological advancements drove cost on systems upgrades.
Other 0.0

## Table 36
Total Changes 2724.0
Current Estimate 20544.0
Disposal Estimate Details
Date of Estimate: February 04, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 1996 $M): Total costs for disposal of all Ship are 61.2
The disposal cost estimate per ship is unchanged. The increase to the total disposal cost is due to the inclusion of the 12th LPD 17 class ship.