## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-253
MQ-8 Fire Scout Unmanned Aircraft System (MQ-8 Fire Scout)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 12
Cost and Funding 13
Low Rate Initial Production 19
Foreign Military Sales 20
Nuclear Costs 20
Unit Cost 21
Cost Variance 24
Contracts 27
Deliveries and Expenditures 28
Operating and Support Cost 29

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
MQ-8 Fire Scout Unmanned Aircraft System (MQ-8 Fire Scout)
DoD Component
Navy
Responsible Office
CAPT Jeffrey Dodge 22707 Cedar Point Road Building 3261
Patuxent River, MD 20670
jeffrey.dodge@navy.mil
Phone: | 301-757-9020
Fax: | 301-757-7261
DSN Phone: | 757-9020
DSN Fax: | 757-7261
Date Assigned: | October 16, 2014
References
SAR Baseline (Production Estimate)
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated February 2, 2009
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated June 20, 2011

## Table 6
Mission and Description
The MQ-8 Fire Scout Unmanned Aircraft System (MQ-8 Fire Scout) program supports the Close Range Reconnaissance, Surveillance and Target Acquisition Capability Mission Need Statement, and the CPD for the Vertical Take-off and Landing Tactical Unmanned Aerial Vehicle System, as amended May 15, 2009. Additionally, the performance attributes of the MQ-8 Fire Scout support the Initial Capabilities Documents for Littoral Combat Ship, Vertical Unmanned Air Vehicle (UAV), Assured Maritime Access in the Littorals, Joint Strike Enable, and Penetrating Intelligence, Surveillance, and Reconnaissance for Area Denial Threat Environments.
A deployed MQ-8 system includes air vehicle(s), payloads (i.e. Electro Optic/Infrared/Laser Designator Range Finder, Automated Identification System, voice communications relay, Radar, Weapons, and other specialty payloads), Mission Control Systems (MCS) (with Tactical Control System software and Tactical Common Data Link integrations for interoperability), a UAV Common Automatic Recovery System for automatic take-offs and landings, and associated spares and support equipment. The MQ-8 Fire Scout air vehicle launches and recovers vertically, and can operate from suitably- equipped air-capable ships as well as confined area land bases. Other characteristics include autonomous waypoint navigation with command override capability, a heavy fuel engine, and the ability to incorporate future mission
packages. There are two MQ-8 air vehicle variants: the MQ-8B and the MQ-8C. The MQ-8C uses the majority of the components and software developed for the MQ-8B but is based on a larger airframe, expanding the range, endurance, and payload capacity of the air vehicle and the system. The MCS will perform mission planning, air vehicle and mission payload control, receive incoming payload data and distribute the data to existing shipboard Command, Control, Communication, and Computer Information systems.

## Table 7
Executive Summary
The MQ-8 Fire Scout was delegated to an ACAT IC program on December 11, 2015. The program is aligned to Navy small surface combatants, including the Littoral Combat Ship, for Surface Warfare and Mine Counter Measures missions.
The MQ-8 Fire Scout program went through a Title 10 Section 2433 (Nunn-McCurdy Breach) review in 2014 due to a unit cost breach in the FY 2015 PB. The Department certified a restructured program to Congress on June 16, 2014. The restructured program that was certified includes both the MQ-8B and MQ-8C air vehicles variants. The MQ-8B based system had an approved Milestone (MS) C on May 29, 2007. The Nunn-McCurdy certification process rescinded the MS C approval. A MS C for the restructured MQ-8 program is currently scheduled for the third quarter of FY 2016. A new Acquisition Strategy and APB will be prepared for the MS C decision.
The MQ-8B variant has completed over 15,000 operational flight hours while deployed aboard the Littoral Combat Ships, Guided Missile Frigates, and supporting the Intelligence, Surveillance, and Reconnaissance Task Force in Afghanistan. IOC for this variant was declared on March 31, 2014.
The MQ-8C variant has completed more than 750 flight hours of developmental testing and an Operational Assessment in November 2015. Dynamic Interface testing aboard the Guided Missile Destroyer USS James Dunham was completed successfully in December of 2014.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
As previously reported in the December 2013 and December
2014 SARs, MQ-8 Fire Scout had a Nunn-McCurdy breach, RDT&E breach, and a schedule breach. A new APB is expected in the third quarter of FY 2016.
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC Critical
APUC Critical
Original UCR Baseline
PAUC Critical
APUC Critical

## Table 9
Schedule
1 APB Breach
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone II | Jan 2000 | Jan 2000 | Jul 2000 | Jan 2000
Milestone C | Feb 2007 | Feb 2007 | Aug 2007 | May 2007
OPEVAL Complete | Sep 2009 | Nov 2011 | May 2012 | N/A1
FRP Decision Review | Nov 2009 | Apr 2012 | Oct 2012 | N/A1
IOC | Sep 2009 | Nov 2011 | May 2012 | Mar 20141
Change Explanations
None
Notes
As reported previously in the December 2013 SAR, OPEVAL and FRP are no longer applicable for the MQ-8B variant and the IOC for the MQ-8B variant was completed in March 2014. Schedule events for the MQ-8C variant will be incorporated into the report when the new APB for the program is signed. The new APB is expected in the third quarter of FY 2016.
Acronyms and Abbreviations
OPEVAL - Operational Evaluation

## Table 10
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Automatic Launch/Recovery (Ship Operations)
Deck Pitch (degrees)
+/- 5 | +/- 5 | +/-3 | +/-2 at seas; +/- 5 land | +/-5
Deck Roll (degrees)
+/- 8 | +/- 8 | +/- 5 | +/-5 at seas; +/- 10 land | +/- 8
Target Identification
Slant Range (km)
16 | 16 | 6 | 10 | 16
Operational Availability
>= 0.95 | >= 0.95 | >= 0.85 | 0.88 | >= 0.85
Net-Ready
The system must fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net- Centric Military operations to include 1) DISR mandated GIG IT standards and profiles identified in the TV-1. 2) DISR mandated GIG IPs identified in the KIP declaration table. 3) NCOW RM Enterprise Services. 4) IA requirements including availability, integrity, authenticat-ion, confidential-ity, and issuance of an ATO by the DAA. 5) | The system must fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net- Centric Military operations to include 1) DISR mandated GIG IT standards and profiles identified in the TV-1. 2) DISR mandated GIG IPs identified in the KIP declaration table. 3) NCOW-RM Enterprise Services. 4) IA requirements including availability, integrity, authenticat-ion, confidential-ity, and issuance of an ATO by the DAA. 5) | The system must fully support execution of joint critical operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net- Centric Military operations to include 1) ISR mandated GIG IT standards and profiles identified in the TV-1. 2) DISR mandated GIG KIPs identified in the KIP declaration table. 3) NCOW-RM Enterprise Services. 4) IA requirements including availability, integrity, authenticat- ion, confidential-ity, and issuance of an IATO by the DAA. 5) Operationally effective | The system has demonstrated all Net Ready Capabilities that have been implemented in the host FFG and LCS class ships. | The system must fully support execution of joint critical operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net-Centric Military operations to include 1) ISR mandated GIG IT standards and profiles identified in the TV-1. 2) DISR mandated GIG KIPs identified in the KIP declaration table. 3) NCOW RM Enterprise Services. 4) IA requirements including availability, integrity, authentication, confidentiality, and issuance of an IATO by the DAA. 5) Operationally effective information exchanges;

## Table 11
Operationally effective | Operationally effective | information exchanges; | and mission critical
information | information | and mission critical | performance and IA
exchanges; and | exchanges; and | performance and IA | attributes, data
mission critical | mission critical | attributes, data | correctness, data
performance and IA | performance and IA | correctness, data | availability, and
attributes, data | attributes, data | availability, and | consistent data
correctness, data | correctness, data | consistent data | processing specified in
availability, and | availability, and | processing specified in | the applicable joint and
consistent data | consistent data | the applicable joint and | system integrated
processing specified in | processing specified in | system integrated | architectural views.
the applicable joint and | the applicable joint and | architectural views.
system integrated | system integrated
architectural views. | architectural views.
Requirements Reference
Capability Production Document (CPD) dated May 15, 2009
Change Explanations
None
Acronyms and Abbreviations
ATO - Authority to Operate
DAA - Designated Approving Authority
DISR - Defense Information Standards Registry FFG - Guided Missile Frigate
GIG - Global Information Grid IA - Information Assurance
IATO - Interim Authority to Operate IP - Information Protocol
ISR - Information Standards Registry IT - Information Technology
KIP - Key Information Protocol km - Kilometer
LCS - Littoral Combat Ship
NCOW RM - Net-Centric Operational Warfare Reference Model TV - Technical View

## Table 12
Track to Budget
RDT&E
Appn |  |  | BA | PE
Navy 1319 07 0305204N
Project | Name
2768 Tactical Unmanned Aerial Vehicles/VTUAV
Notes: PU2768, VTUAV
Navy 1319 07 0305231N
(Shared) (Sunk)
Project | Name
2768 MQ-8 Fire Scout
Notes: PU2768, MQ-8 UAV
Notes
In FY 2010, VTUAV was moved from PE 0305204N to PE 0305231N.
In FY 2014, the MQ-8 program was restructured as part of a Nunn-McCurdy certification. Separate efforts within the PE are now included in the program, so the PE is no longer shared.
Procurement
Appn |  |  | BA | PE
Navy |  | 1506 04 |  | 0305231N
|  | Line Item |  |  | Name
|  | 443 |  | MQ-8 UAV |  | (Shared)
Navy |  | 1506 04 |  | 0305204N
|  | Line Item |  |  | Name
|  | 443 |  | Vertical Take-off UAV (VTUAV) |  | (Sunk)
Navy |  | 1506 06 |  | 0305231N
|  | Line Item |  | Name
|  | 605 |  | Spares and Repair Parts
Notes
In FY 2010, VTUAV was moved from PE 0305204N to PE 0305231N.

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2006 $M | [5 empty] | BY 2006 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E | 541.1 |  |  | 617.1 | 678.8 |  |  | 1039.71 |  | 530.3 |  |  | 614.4 |  | 1109.2
Procurement | 1522.4 |  |  | 1748.9 | 1923.8 |  |  | 1409 |  | 1821.5 |  |  | 2226.1 |  | 1695.9
Flyaway | -- |  |  | -- | -- |  |  | 922.6 |  | -- |  |  | -- |  | 1106.4
Recurring | -- |  |  | -- | -- |  |  | 893.2 |  | -- |  |  | -- |  | 1069.5
Non Recurring | -- |  |  | -- | -- |  |  | 29.4 |  | -- |  |  | -- |  | 36.9
Support | -- |  |  | -- | -- |  |  | 486.4 |  | -- |  |  | -- |  | 589.5
Other Support | -- |  |  | -- | -- |  |  | 377.3 |  | -- |  |  | -- |  | 464.5
Initial Spares | -- |  |  | -- | -- |  |  | 109.1 |  | -- |  |  | -- |  | 125
MILCON | 119.6 |  |  | 0 | -- |  |  | 0 |  | 126 |  |  | 0 |  | 0
Acq O&M | 183.3 |  |  | 0 | -- |  |  | 0 |  | 309.3 |  |  | 0 |  | 0
Total | 2366.4 |  |  | 2366 | N/A |  |  | 2448.7 |  | 2787.1 |  |  | 2840.5 |  | 2805.1
1 APB Breach
Confidence Level
Confidence Level of cost estimate for current APB: 60%
The current estimate aims to provide sufficient resources to execute the program under normal conditions, encountering average levels of technical, schedule and programmatic risk, and external interference. It is consistent with average resource expenditures on historical efforts of similar size, scope, and complexity.
Total Quantity
Quantity |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  | 9 |  |  |  | 7 |  |  |  |  | 9
Procurement |  | 168 |  |  |  | 168 |  |  |  |  | 61
Total |  | 177 |  |  |  | 175 |  |  |  |  | 70
Quantity Notes
The quantity reduction aligns with the USD(AT&L) Nunn-McCurdy certification memo, dated June 16, 2014.

## Table 14
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 973.1 | 52.8 |  |  | 26.5 | 10.9 | 6.2 |  | 6.4 |  | 6.5 |  | 26.8 |  |  | 1109.2
Procurement | 917.2 | 163.8 |  |  | 73.9 | 92.4 | 102.7 |  | 90.9 |  | 85.4 |  | 169.6 |  |  | 1695.9
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0
PB 2017 Total | 1890.3 | 216.6 |  |  | 100.4 | 103.3 | 108.9 |  | 97.3 |  | 91.9 |  | 196.4 |  |  | 2805.1
PB 2016 Total | 1890.4 | 172.8 |  |  | 131.5 | 94.9 | 103.6 |  | 90.9 |  | 94.7 |  | 260.8 |  |  | 2839.6
Delta | -0.1 | 43.8 |  |  | -31.1 | 8.4 | 5.3 |  | 6.4 |  | -2.8 |  | -64.4 |  |  | -34.5
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 9 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 9
Production | 0 |  | 45 |  | 5 | 1 | 2 |  | 2 | 2 |  | 2 |  | 2 |  | 61
PB 2017 Total | 9 |  | 45 |  | 5 | 1 | 2 |  | 2 | 2 |  | 2 |  | 2 |  | 70
PB 2016 Total | 9 |  | 45 |  | 2 | 2 | 2 |  | 2 | 2 |  | 2 |  | 4 |  | 70
Delta | 0 |  | 0 |  | 3 | -1 | 0 |  | 0 | 0 |  | 0 |  | -2 |  | 0

## Table 15
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.8
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66.2
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.8
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.3
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.1
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 93.2
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 100.1
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.8
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 56.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 72.3
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 113.9
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83.8
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.7
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.3
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 52.8
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.5
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.9
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.2
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.4
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.5
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.7
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.7
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.7
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.7
Subtotal |  | 9 | -- |  | -- |  | -- |  | -- |  | -- |  | 1109.2

## Table 16
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2006 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.6
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 72.4
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 51.8
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.4
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 91.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 95.9
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.1
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.9
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 51.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 64.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 100.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 72.9
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.7
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.8
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.9
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.9
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.9
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.9
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.8
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.7
Subtotal |  | 9 | -- |  | -- |  | -- |  | -- |  | -- |  | 1039.7

## Table 17
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | 3 | 32.2 |  | -- |  | 3.9 |  | 36.1 |  | 11.5 |  | 47.6
2008 |  | 3 | 32.4 |  | -- |  | 1.4 |  | 33.8 |  | 11.6 |  | 45.4
2009 |  | 3 | 31.6 |  | -- |  | 3.2 |  | 34.8 |  | 22.3 |  | 57.1
2010 |  | 11 | 108.4 |  | -- |  | -- |  | 108.4 |  | 47.5 |  | 155.9
2011 |  | 3 | 46.5 |  | -- |  | -- |  | 46.5 |  | 15.5 |  | 62
2012 |  | 10 | 161.7 |  | -- |  | -- |  | 161.7 |  | 60.9 |  | 222.6
2013 |  | 5 | 88.1 |  | -- |  | -- |  | 88.1 |  | 29.9 |  | 118
2014 |  | 2 | 35.7 |  | -- |  | -- |  | 35.7 |  | 50.7 |  | 86.4
2015 |  | 5 | 73.9 |  | -- |  | 0.4 |  | 74.3 |  | 47.9 |  | 122.2
2016 |  | 5 | 104.1 |  | -- |  | 4.3 |  | 108.4 |  | 55.4 |  | 163.8
2017 |  | 1 | 31.3 |  | -- |  | 2.7 |  | 34 |  | 39.9 |  | 73.9
2018 |  | 2 | 61.2 |  | -- |  | 1.8 |  | 63 |  | 29.4 |  | 92.4
2019 |  | 2 | 58.3 |  | -- |  | 1 |  | 59.3 |  | 43.4 |  | 102.7
2020 |  | 2 | 60.2 |  | -- |  | 0.8 |  | 61 |  | 29.9 |  | 90.9
2021 |  | 2 | 61.7 |  | -- |  | 0.8 |  | 62.5 |  | 22.9 |  | 85.4
2022 |  | 2 | 82.2 |  | -- |  | 16.6 |  | 98.8 |  | 35 |  | 133.8
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | 24.6 |  | 24.6
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | 9.7 |  | 9.7
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | 1.5 |  | 1.5
Subtotal |  | 61 | 1069.5 |  | -- |  | 36.9 |  | 1106.4 |  | 589.5 |  | 1695.9

## Table 18
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | BY 2006 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | 3 | 30.4 |  | -- |  | 3.7 |  | 34.1 |  | 10.9 |  | 45
2008 |  | 3 | 30.2 |  | -- |  | 1.3 |  | 31.5 |  | 10.8 |  | 42.3
2009 |  | 3 | 29 |  | -- |  | 2.9 |  | 31.9 |  | 20.5 |  | 52.4
2010 |  | 11 | 97.5 |  | -- |  | -- |  | 97.5 |  | 42.8 |  | 140.3
2011 |  | 3 | 41 |  | -- |  | -- |  | 41 |  | 13.7 |  | 54.7
2012 |  | 10 | 140.6 |  | -- |  | -- |  | 140.6 |  | 53 |  | 193.6
2013 |  | 5 | 75.8 |  | -- |  | -- |  | 75.8 |  | 25.7 |  | 101.5
2014 |  | 2 | 30.3 |  | -- |  | -- |  | 30.3 |  | 43.1 |  | 73.4
2015 |  | 5 | 61.8 |  | -- |  | 0.3 |  | 62.1 |  | 40.2 |  | 102.3
2016 |  | 5 | 85.6 |  | -- |  | 3.5 |  | 89.1 |  | 45.6 |  | 134.7
2017 |  | 1 | 25.3 |  | -- |  | 2.2 |  | 27.5 |  | 32.2 |  | 59.7
2018 |  | 2 | 48.5 |  | -- |  | 1.4 |  | 49.9 |  | 23.3 |  | 73.2
2019 |  | 2 | 45.3 |  | -- |  | 0.8 |  | 46.1 |  | 33.6 |  | 79.7
2020 |  | 2 | 45.8 |  | -- |  | 0.6 |  | 46.4 |  | 22.8 |  | 69.2
2021 |  | 2 | 46 |  | -- |  | 0.6 |  | 46.6 |  | 17.1 |  | 63.7
2022 |  | 2 | 60.1 |  | -- |  | 12.1 |  | 72.2 |  | 25.7 |  | 97.9
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | 17.6 |  | 17.6
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | 6.8 |  | 6.8
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | 1 |  | 1
Subtotal |  | 61 | 893.2 |  | -- |  | 29.4 |  | 922.6 |  | 486.4 |  | 1409

## Table 19
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2007-05-29 | 2010-07-22
Approved Quantity | 4 | 23
Reference | Milestone C ADM | Congressional Emergency Supplemental Appropriation HR-4899
Start Year | 2007 | 2007
End Year | 2007 | 2012
The Current Total LRIP Quantity is more than 10% of the total production quantity due to August 4, 2010, Congressional Emergency Supplemental Appropriation HR-4899 which funded Overseas Contingency Operations to convert eight Army airframes bought under the Army's Future Combat System program into Navy Fire Scouts.
The initial ADM for Milestone C approved the program to purchase up to four aircraft, and to buy-to-budget. This guidance resulted in a purchase of three aircraft.
An LRIP decision on September 30, 2008 authorized purchase of three aircraft for LRIP 2 and three aircraft for LRIP 3.
An LRIP decision on July 22, 2010, authorized purchase of five aircraft for LRIP 4 and three aircraft for LRIP 5. Only three new aircraft were purchased under LRIP 4.

## Table 20
Foreign Military Sales
None
Nuclear Costs
None

## Table 21
Unit Cost
Unit Cost Report
Item |  | BY 2006 $M | BY 2006 $M |  | % Change
|  | Current UCR Baseline (Jun 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2366 |  |  | 2448.7
Quantity | 175 |  |  | 70
Unit Cost | 13.52 |  |  | 34.981 |  | +158.741
Average Procurement Unit Cost
Cost | 1748.9 |  |  | 1409
Quantity | 168 |  |  | 61
Unit Cost | 10.41 |  |  | 23.098 |  | +121.881
Item |  | BY 2006 $M | BY 2006 $M |  | % Change
|  | Original UCR Baseline (Dec 2006 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2366.4 |  |  | 2448.7
Quantity | 177 |  |  | 70
Unit Cost | 13.369 |  |  | 34.981 |  | +161.661
Average Procurement Unit Cost
Cost | 1522.4 |  |  | 1409
Quantity | 168 |  |  | 61
Unit Cost | 9.062 |  |  | 23.098 |  | +154.891
1
Nunn-McCurdy Breach
MQ-8 Fire Scout previously reported a critical Nunn-McCurdy breach and provided detailed Unit Cost reporting in the December 2013 SAR. The Department certified a restructured program to Congress on June 16, 2014. This section will be updated when an APB is approved at Milestone C.

## Table 22
Unit Cost History
Item | [7 empty] | Date |  |  | BY 2006 $M | [5 empty] | TY $M
[11 empty] | PAUC |  | APUC |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Dec 2006 | [5 empty] | 13.369 |  |  | 9.062 |  |  |  | 15.746 |  |  |  | 10.842
APB as of January 2006 |  |  |  |  | N/A | [5 empty] | N/A |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Revised Original APB |  |  |  |  | N/A | [5 empty] | N/A |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | Feb 2009 | [5 empty] | 13.369 |  |  | 9.062 |  |  |  | 15.746 |  |  |  | 10.842
Current APB |  |  |  |  | Jun 2011 | [5 empty] | 13.52 |  |  | 10.41 |  |  |  | 16.231 |  |  |  | 13.251
Prior Annual SAR |  |  |  |  | Dec 2014 | [5 empty] | 35.153 |  |  | 23.293 |  |  |  | 40.566 |  |  |  | 28.333
Current Estimate |  |  |  |  | Dec 2015 | [5 empty] | 34.981 |  |  | 23.098 |  |  |  | 40.073 |  |  |  | 27.802
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [18 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng | Est |  | Oth |  | Spt |  | Total
15.746 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 15.746
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [16 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
15.746 -0.341 8.891 6.454 11.344 -4.627 0.000 2.606 24.327 40.073

## Table 23
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [11 empty] | APUC Production Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth |  | Spt |  | Total
10.842 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 10.842
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [11 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt |  | Total
10.842 -0.318 1.225 7.407 5.141 0.515 0.000 2.990 16.960 27.802
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  |  | Current Estimate
Milestone I |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Milestone II |  |  | N/A |  |  | Jan 2000 |  |  |  | Jan 2000 |  |  |  | Jan 2000
Milestone C |  |  | N/A |  |  | Feb 2007 |  |  |  | Feb 2007 |  |  |  | May 2007
IOC |  |  | N/A |  |  | N/A |  |  |  | Sep 2009 |  |  |  | Mar 2014
Total Cost (TY $M) |  |  | N/A |  |  | 2787.1 |  |  |  | 2787.1 |  |  |  | 2805.1
Total Quantity |  |  | N/A |  |  | 177 |  |  |  | 177 |  |  |  | 70
PAUC |  |  | N/A |  |  | 15.746 |  |  |  | 15.746 |  |  |  | 40.073

## Table 24
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Acq O&M | Total
SAR Baseline (Production Estimate) | 530.3 | 1821.5 | 126 | 309.3 | 2787.1
Previous Changes
Economic | -2.7 | -10.5 | -- | -- | -13.2
Quantity | 22.9 | -1085.4 | -- | -- | -1062.5
Schedule | -- | 469.9 | -- | -- | 469.9
Engineering | 480.5 | 313.6 | -- | -- | 794.1
Estimating | 80.3 | 67.3 | -126 | -309.3 | -287.7
Other | -- | -- | -- | -- | --
Support | -- | 151.9 | -- | -- | 151.9
Subtotal | 581 | -93.2 | -126 | -309.3 | 52.5
Current Changes
Economic | -1.8 | -8.9 | -- | -- | -10.7
Quantity | -- | -- | -- | -- | --
Schedule | -- | -18.1 | -- | -- | -18.1
Engineering | -- | -- | -- | -- | --
Estimating | -0.3 | -35.9 | -- | -- | -36.2
Other | -- | -- | -- | -- | --
Support | -- | 30.5 | -- | -- | 30.5
Subtotal | -2.1 | -32.4 | -- | -- | -34.5
Total Changes | 578.9 | -125.6 | -126 | -309.3 | 18
CE - Cost Variance | 1109.2 | 1695.9 | -- | -- | 2805.1
CE - Cost & Funding | 1109.2 | 1695.9 | -- | -- | 2805.1

## Table 25
Summary BY 2006 $M
Item | RDT&E | Procurement | MILCON | Acq O&M | Total
SAR Baseline (Production Estimate) | 541.1 | 1522.4 | 119.6 | 183.3 | 2366.4
Previous Changes
Economic | -- | -- | -- | -- | --
Quantity | 20 | -663.7 | -- | -- | -643.7
Schedule | -- | 165.3 | -- | -- | 165.3
Engineering | 407.1 | 206.9 | -- | -- | 614
Estimating | 71.6 | 84.8 | -119.6 | -183.3 | -146.5
Other | -- | -- | -- | -- | --
Support | -- | 105.2 | -- | -- | 105.2
Subtotal | 498.7 | -101.5 | -119.6 | -183.3 | 94.3
Current Changes
Economic | -- | -- | -- | -- | --
Quantity | -- | -- | -- | -- | --
Schedule | -- | -8.9 | -- | -- | -8.9
Engineering | -- | -- | -- | -- | --
Estimating | -0.1 | -31.9 | -- | -- | -32
Other | -- | -- | -- | -- | --
Support | -- | 28.9 | -- | -- | 28.9
Subtotal | -0.1 | -11.9 | -- | -- | -12
Total Changes | 498.6 | -113.4 | -119.6 | -183.3 | 82.3
CE - Cost Variance | 1039.7 | 1409 | -- | -- | 2448.7
CE - Cost & Funding | 1039.7 | 1409 | -- | -- | 2448.7
Previous Estimate: December 2014

## Table 26
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -1.8
Adjustment for current and prior escalation. (Estimating) +1.0 +1.1
Revised estimate due to departmental adjustments to account for actual program execution. (Estimating)
-1.3 -1.6
Revised estimate to reflect the application of new out-year inflation indices. (Estimating) +0.2 +0.2
RDT&E Subtotal -0.1 -2.1
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -8.9
Acceleration of the procurement buy profile from FY 2017 (-1) and FY 2013 (-2) to FY 2016 (+3). (Schedule)
Additional schedule variance for Material Cost and Mission Control System procurement profile changes. (Schedule)
0.0 -7.6
-8.9 -10.1
Additional schedule variance to realign quantities in prior years. (Schedule) 0.0 -0.4
Adjustment for current and prior escalation. (Estimating) +1.2 +1.7
Realignment of ancillary equipment funds to Other Support for procurement of logistics and training equipment. (Estimating)
Adjustment to the phasing of the production line shutdown costs due to the change in procurement profile. (Estimating)
-34.2 -39.2
-0.4 -0.5
Shift in funding for the addition of the radar capability. (Estimating) +1.5 +2.1
Adjustment for current and prior escalation. (Support) +1.3 +1.2
Increase in Other Support funds due to realignment of ancillary equipment funds for procurement of logistics and training equipment and updated phasing due to the stretch out of the procurement buy profile. (Support)
+18.3 +17.5
Increase in Initial Spares due to shift IOC date. (Support) +9.3 +11.8
Procurement Subtotal -11.9 -32.4

## Table 27
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: MQ-8 Endurance Upgrade Development and Production
Contractor: Northrop-Grumman Systems Corporation
Contractor Location: 17066 Goldentop Road
San Diego, CA 92127
Contract Number: N00019-12-C-0059/1
Contract Type: Cost Plus Incentive Fee (CPIF), Cost Plus Fixed Fee (CPFF), Firm Fixed Price (FFP)
Award Date: April 23, 2012
Definitization Date: November 14, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
252.8 N/A 8 328.1 N/A 19 339.7 338.4
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to additional work contracted to transition the effort from a Rapid Deployment Capability to a Program of Record; additional airframes, training equipment, and spare parts required; and the maintenance concept migration from contractor supported to military organic maintenance.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/1/2016) -42.5 -1.4
Previous Cumulative Variances -30.2 -3.0
Net Change -12.3 +1.6
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to changes required to the network architecture which drove delays to software development and testing schedules; and aircraft delivery schedule adjustments made to provide for a more efficient production flow by evenly distributing delivery dates.
The favorable net change in the schedule variance is due to adjustments to the aircraft delivery schedules made to provide for a more efficient production flow by evenly distributing delivery dates.
Notes
This contract includes both RDT&E and Procurement APPNs.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 28
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 7 | 7 | 9 | 77.78%
Production | 30 | 31 | 61 | 50.82%
Total Program Quantity Delivered | 37 | 38 | 70 | 54.29%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
2805.1
1718.8
61.27%
26
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
17
65.38%
2106.9
75.11%
The above data is current as of February 11, 2016.
All MQ-8B deliveries are complete.
Nineteen MQ-8C Fire Scout aircraft were contracted under the Navy's Rapid Deployment Capability authority and have now been included in the Program of Record as part of the Nunn-McCurdy restructure in 2014. This includes two RDT&E aircraft and 17 procurement aircraft.

## Table 29
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 26, 2015
Source of Estimate: POE
Quantity to Sustain: 60
Unit of Measure: Aircraft
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2014 - FY 2035
The O&S costs are based on the updated Program Office Life Cycle Cost Estimate from January 2015, which reflects the Nunn-McCurdy certification and program restructure. The cost estimate was updated to reflect the most recently defined programmatic and sustainment strategy to include both the MQ-8B and MQ-8C. The MQ-8 Sustainment strategy supports 60 aircraft, which excludes seven stricken aircraft and three test assets from the total production quantity of 70. This estimate is based on 494 total operational aircraft years. This estimate includes MQ-8B attrition of one aircraft for every 14,500 flight hours and anticipated MQ-8C attrition of one aircraft loss per each of first four years (FY 2016 - FY 2019) based on current actual attrition rates on ship deployments, and learning curve; after FY 2019, includes attrition of one aircraft for every 14,500 flight hours. The MQ-8 will be deployed with the MH-60. The MQ-8 will be operated and maintained by MH-60 Aviation Detachment (AVDET) personnel while in deployed status. The addition of the MQ-8 capability does not directly impact manpower requirements of the Helicopter Sea Combat Squadron expeditionary MH-60 AVDET and the manpower costs associated with the MH-60 AVDET is the responsibility of Office of the Chief of Naval Operations N98; there are no costs associated with that AVDET included in this estimate. This estimate is being refined to support the upcoming Milestone C for the program. These refinements will be included in the December 2016 SAR.
Sustainment Strategy
The strategy includes a mixture of Organic and Contractor Organizational to Depot sustainment support. Upon further Business Case Analyses the anticipated mix of sustainment is to optimize Organic and Contractor solutions.
Antecedent Information
No Antecedent. Fire Scout is a distinctly new platform that will operate with a significant increase in persistence over current Naval helicopters, and for this primary reason there is no appropriate analogous program for O&S cost comparisons.

## Table 30
Annual O&S Costs BY2006 $K
Cost Element |  | MQ-8 Fire Scout Average Annual Cost Per Aircraft | [5 empty] | No Antecedent (Antecedent) N/A
Unit-Level Manpower |  | 51.477 | [5 empty] | --
Unit Operations |  | 247.057 | [5 empty] | --
Maintenance |  | 1685.35 | [5 empty] | --
Sustaining Support |  | 669.328 | [5 empty] | --
Continuing System Improvements |  | 408.631 | [5 empty] | --
Indirect Support |  | 11.296 | [5 empty] | --
Other |  | 0 | [5 empty] | --
Total |  | 3073.139 | [5 empty] | --
Item | Total O&S Cost $M
| MQ-8 Fire Scout | [7 empty] | No Antecedent (Antecedent)
| Current Production APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 3307 |  |  | 3637.7 |  |  | 1518.1 |  | N/A
Then Year | 5131.3 |  |  | N/A |  |  | 2181.7 |  | N/A
Equation to Translate Annual Cost to Total Cost
The Average Cost per Air Vehicle of $3.073M is calculated by dividing Total O&S of $1,518.1M by the total number of operational aircraft years of 494.
O&S Cost Variance
Category |  |  | BY 2006 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
1518.1
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 1518.1
Disposal Estimate Details
Date of Estimate: January 26, 2015
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2006 $M): Total costs for disposal of all Aircraft are 8.2

## Table 31
The disposal costs are based on 37 air vehicles at $220,600 each.