## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-391
Standard Missile-6 (SM-6)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 12
Cost and Funding 13
Low Rate Initial Production 20
Foreign Military Sales 21
Nuclear Costs 21
Unit Cost 22
Cost Variance 25
Contracts 28
Deliveries and Expenditures 31
Operating and Support Cost 32

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Standard Missile-6 (SM-6)
DoD Component
Navy
Responsible Office
CAPT Michael Ladner
Program Executive Office - Integrated Warfare Systems 3.0
2450 Crystal Drive
Suite 700
Arlington, VA 22202-3862
michael.ladner@navy.mil
Phone: 703-872-3700
Fax: 703-872-3796
DSN Phone: DSN Fax:
Date Assigned: May 3, 2013
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated March 26, 2010
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated August 9, 2013

## Table 6
Mission and Description
The Standard Missile-6 (SM-6) Extended Range Active Missile (ERAM) is designed to provide ship self-defense, fleet area defense, and theater air defense for sea and littoral forces. Raytheon Missile Systems has been chosen as the sole source contractor for SM-6 ERAM Block I. The SM-6 ERAM is a surface-to-air supersonic missile, launched from AEGIS Cruisers and Destroyers, capable of successfully engaging manned and unmanned, fixed or rotary wing aircraft and land attack or Anti-Ship Cruise Missiles in flight. The SM-6 ERAM program is an evolutionary, capabilities based acquisition program that will use spiral development to produce an initial Block I capability, with follow-on blocks to pace emerging threat systems as required. In addition to an extended range, the initial SM-6 ERAM Block I will have active missile seeker homing for improved flight responsiveness, guidance, sub-clutter visibility, and countermeasures resistance over present SM-2 missiles and will be "Engage-On-Remote" intercept capable.
SM-6 will be an effective weapon that will apply timely, precise, accurate and lethal fire power against cruise missile threats and launch platforms in a fleet area defense role and over hostile territory. SM-6 will provide in-flight destruction capabilities over the total flight path. SM-6 may be employed in concert with the developing Joint Theater Air and Missile Defense Family of Systems to provide continuous protection to forward deployed maneuver forces as well as theater rear assets.

## Table 7
Executive Summary
The SM-6 program was designated as an ACAT 1C program with the Navy as the lead Component as documented in the ADM dated April 1, 2015.
An Undefinitized Contract Action (UCA) for the SM-6 Block IA Engineering Change Proposal (ECP) FY 2015 production contract was awarded on April 30, 2015.
The SM-6 Block I/IA FRP FY 2015 production contract was definitized on May 29, 2015.
SM-6 has been integrated and authorized for use onto AEGIS Baselines 9A in February 2015 and Baseline 9C.1 in November 2015.
The program successfully completed ten of ten planned Follow-on Operational Test and Evaluation (FOT&E) flight tests. The program successfully completed two FOT&E flight tests in March 2015 and successfully completed the remaining four FOT&E flight tests in January 2016. Additional FOT&E events will be completed in order to validate deficiency discovered during IOT&E and support for FOC declaration in 2017.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
The SM-6 program submitted a Program Deviation Report to Assistant Secretary of the Navy for Research, Development, and Acquisition (ASN (RD&A)) in October 2015 with revised estimated milestone dates for FOC from March 2016 to December 2017. This revision in FOC date does not impact the capability level or number of missiles being delivered to the Fleet, but rather is driven by the inability to complete outstanding Operational Test and Evaluation events due to target moratoriums and FY 2015 and FY 2016 funding shortfalls. There is no plan to update the APB.
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule

## Table 10
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B Review | Jun 2004 | Jun 2004 | Dec 2004 | Jun 2004
Milestone C Review | Jun 2009 | Jun 2009 | Dec 2009 | Aug 2009
Land Based Testing
Start | Apr 2008 | Apr 2008 | Oct 2008 | Apr 2008
Complete | Oct 2009 | Oct 2009 | Apr 2010 | Jan 2010
Development Testing and Combined Development and Operational Testing
Start | Feb 2010 | Feb 2010 | Aug 2010 | May 2010
Complete | Apr 2010 | Jan 2011 | Jul 2011 | Jan 2011
Proof of Manufacturing Final Review | Oct 2010 | Oct 2010 | Apr 2011 | Apr 2011
Operational Testing
Start | Aug 2010 | Jul 2011 | Jan 2012 | Jul 2011
Complete | Sep 2010 | Oct 2011 | Apr 2012 | Oct 2011
IOC | Mar 2011 | May 2013 | Nov 2013 | Nov 2013
Full Rate Production Review | Jun 2011 | May 2013 | Nov 2013 | May 2013
Full Operational Capability (FOC) | Sep 2015 | Sep 2015 | Mar 2016 | Dec 20171
(Ch-1)
1 APB Breach
Change Explanations
(Ch-1) Current estimate for FOC changed from March 2016 to December 2017 due to inability to complete outstanding Operational Test and Evaluation events due to target moratoriums and FY 2015 and FY 2016 funding shortfalls. This revision in FOC does not impact the capability level or number of missiles being delivered to the Fleet.

## Table 11
Performance
Classified Performance information is provided in the classified annex to this submission.

## Table 12
Track to Budget
General Notes
The SM-6 Development was funded under PE 0604366N - Project 3092.
The FY 2017 PB includes RDT&E funding for other STANDARD Missile improvements, none of which are included in the SM-6 development program baseline: Insensitive Munitions, Portable All-Up Round Built In Test Tester, Naval Integrated Fire Control - Counter Air, and Future Capability Demonstration.
The FY 2017 PB for SM-6 procurement (APPN 1507, PE 0204228N) includes Line Item 2234 and 6120. Both are shared with SM-2 through FY 2011. All up rounds are reflected in Budget Line Item (BLI) 2234 P1-7. Initial Spares are included in BLI 6120 P1-35.
RDT&E
Appn |  | BA | PE
Navy 1319 05 0604366N
Project | Name
3092 Standard Missile 6 Program (Shared) (Sunk)
Notes: FY 2012 is the last year of SM-6 RDT&E funding related to the Baseline Program of Record as reported in the SAR.
Procurement
Appn |  | BA | PE
Navy 1507 02 0204228N
Line Item | Name
2234 STANDARD Missile
Notes: Shared with SM-2 through FY 2011.
Navy 1507 06 0204228N
Line Item | Name
6120 Spares and Repair Parts (Shared)
Notes: Shared with SM-2 in Standard Missile Replenishment Spares line through FY 2011 and continues to be shared with other Navy programs.

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2004 $M |  |  |  |  | BY 2004 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 861.6 |  | 834.5 | 918 |  | 834.7 |  | 963.2 |  | 933.4 |  | 933.4
Procurement |  | 4419.5 |  | 6854.1 | 7539.5 |  | 6401.7 |  | 5634 |  | 9623.8 |  | 8876.8
Flyaway |  | -- |  | -- | -- |  | 5609.8 |  | -- |  | -- |  | 7794.1
Recurring |  | -- |  | -- | -- |  | 5585.7 |  | -- |  | -- |  | 7766
Non Recurring |  | -- |  | -- | -- |  | 24.1 |  | -- |  | -- |  | 28.1
Support |  | -- |  | -- | -- |  | 791.9 |  | -- |  | -- |  | 1082.7
Other Support |  | -- |  | -- | -- |  | 549.1 |  | -- |  | -- |  | 743.7
Initial Spares |  | -- |  | -- | -- |  | 242.8 |  | -- |  | -- |  | 339
MILCON |  | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M |  | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Total |  | 5281.1 |  | 7688.6 | N/A |  | 7236.4 |  | 6597.2 |  | 10557.2 |  | 9810.2
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The Independent Cost Estimate (ICE) to support SM-6 Full Rate Production Decision, like all life-cycle cost estimates previously performed by the Office of the Secretary of Defense, Cost Assessment and Program Evaluation (OSD, CAPE), is built upon a product-oriented work breakdown structure, based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for Major Defense Acquisition Programs (MDAPs). Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is equally likely that the estimate will prove low or too high for execution of the program described.

## Table 14
Total Quantity
Quantity | SAR Baseline Production Estimate | Current APB Production | Current Estimate
RDT&E | 0 | 0 | 0
Procurement | 1200 | 1800 | 1800
Total | 1200 | 1800 | 1800
Quantity Notes
SM-6 received authorization to increase the procurement profile from 1200 missiles to 1800 missiles as documented in the Navy Electronic Resources and Requirements Review Board memorandum, dated March 18, 2013.

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 933.4 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 933.4
Procurement | 1860 | 434.4 |  |  | 506.2 | 526 | 537.4 |  | 555.9 |  | 565.2 |  |  | 3891.7 |  | 8876.8
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 2793.4 | 434.4 |  |  | 506.2 | 526 | 537.4 |  | 555.9 |  | 565.2 |  |  | 3891.7 |  | 9810.2
PB 2016 Total | 2825.6 | 452.4 |  |  | 513.6 | 532.3 | 544.8 |  | 559.8 |  | 673.7 |  |  | 3597.5 |  | 9699.7
Delta | -32.2 | -18 |  |  | -7.4 | -6.3 | -7.4 |  | -3.9 |  | -108.5 |  |  | 294.2 |  | 110.5
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Production | 0 |  | 460 |  | 113 | 125 | 125 |  | 125 |  | 125 | 125 |  | 602 |  | 1800
PB 2017 Total | 0 |  | 460 |  | 113 | 125 | 125 |  | 125 |  | 125 | 125 |  | 602 |  | 1800
PB 2016 Total | 0 |  | 470 |  | 113 | 125 | 125 |  | 125 |  | 125 | 125 |  | 592 |  | 1800
Delta | 0 |  | -10 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 10 |  | 0

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.5
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 114.8
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 150
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 172.6
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 195.4
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 112.6
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 61
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.7
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 933.4

## Table 17
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2004 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 80
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 106.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 135.6
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 153.2
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 171.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 97.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 51.4
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.7
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 834.7

## Table 18
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2009 |  | 19 | 92.4 |  | -- |  | 17.6 |  | 110 |  | 12.4 |  | 122.4
2010 |  | 11 | 54.5 |  | -- |  | 10.5 |  | 65 |  | 32.7 |  | 97.7
2011 |  | 59 | 210.5 |  | -- |  | -- |  | 210.5 |  | 32.5 |  | 243
2012 |  | 89 | 272.2 |  | -- |  | -- |  | 272.2 |  | 67.2 |  | 339.4
2013 |  | 89 | 264.6 |  | -- |  | -- |  | 264.6 |  | 54.4 |  | 319
2014 |  | 93 | 259.2 |  | -- |  | -- |  | 259.2 |  | 60 |  | 319.2
2015 |  | 100 | 364.2 |  | -- |  | -- |  | 364.2 |  | 55.1 |  | 419.3
2016 |  | 113 | 378.1 |  | -- |  | -- |  | 378.1 |  | 56.3 |  | 434.4
2017 |  | 125 | 458.7 |  | -- |  | -- |  | 458.7 |  | 47.5 |  | 506.2
2018 |  | 125 | 468.6 |  | -- |  | -- |  | 468.6 |  | 57.4 |  | 526
2019 |  | 125 | 479.7 |  | -- |  | -- |  | 479.7 |  | 57.7 |  | 537.4
2020 |  | 125 | 490.7 |  | -- |  | -- |  | 490.7 |  | 65.2 |  | 555.9
2021 |  | 125 | 498.7 |  | -- |  | -- |  | 498.7 |  | 66.5 |  | 565.2
2022 |  | 125 | 695.6 |  | -- |  | -- |  | 695.6 |  | 80.3 |  | 775.9
2023 |  | 125 | 704.2 |  | -- |  | -- |  | 704.2 |  | 81.9 |  | 786.1
2024 |  | 125 | 725.5 |  | -- |  | -- |  | 725.5 |  | 83.5 |  | 809
2025 |  | 125 | 737.2 |  | -- |  | -- |  | 737.2 |  | 85.2 |  | 822.4
2026 |  | 102 | 611.4 |  | -- |  | -- |  | 611.4 |  | 86.9 |  | 698.3
Subtotal |  | 1800 | 7766 |  | -- |  | 28.1 |  | 7794.1 |  | 1082.7 |  | 8876.8

## Table 19
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | BY 2004 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2009 |  | 19 | 80 |  | -- |  | 15.2 |  | 95.2 |  | 10.8 |  | 106
2010 |  | 11 | 46.4 |  | -- |  | 8.9 |  | 55.3 |  | 27.9 |  | 83.2
2011 |  | 59 | 175.9 |  | -- |  | -- |  | 175.9 |  | 27.2 |  | 203.1
2012 |  | 89 | 224.1 |  | -- |  | -- |  | 224.1 |  | 55.3 |  | 279.4
2013 |  | 89 | 214.8 |  | -- |  | -- |  | 214.8 |  | 44.2 |  | 259
2014 |  | 93 | 207.5 |  | -- |  | -- |  | 207.5 |  | 48.1 |  | 255.6
2015 |  | 100 | 287.3 |  | -- |  | -- |  | 287.3 |  | 43.4 |  | 330.7
2016 |  | 113 | 293.1 |  | -- |  | -- |  | 293.1 |  | 43.7 |  | 336.8
2017 |  | 125 | 349 |  | -- |  | -- |  | 349 |  | 36.1 |  | 385.1
2018 |  | 125 | 349.7 |  | -- |  | -- |  | 349.7 |  | 42.8 |  | 392.5
2019 |  | 125 | 350.9 |  | -- |  | -- |  | 350.9 |  | 42.2 |  | 393.1
2020 |  | 125 | 351.9 |  | -- |  | -- |  | 351.9 |  | 46.8 |  | 398.7
2021 |  | 125 | 350.7 |  | -- |  | -- |  | 350.7 |  | 46.7 |  | 397.4
2022 |  | 125 | 479.5 |  | -- |  | -- |  | 479.5 |  | 55.4 |  | 534.9
2023 |  | 125 | 475.9 |  | -- |  | -- |  | 475.9 |  | 55.4 |  | 531.3
2024 |  | 125 | 480.7 |  | -- |  | -- |  | 480.7 |  | 55.3 |  | 536
2025 |  | 125 | 478.9 |  | -- |  | -- |  | 478.9 |  | 55.3 |  | 534.2
2026 |  | 102 | 389.4 |  | -- |  | -- |  | 389.4 |  | 55.3 |  | 444.7
Subtotal |  | 1800 | 5585.7 |  | -- |  | 24.1 |  | 5609.8 |  | 791.9 |  | 6401.7

## Table 20
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2004-07-12 | 2012-04-05
Approved Quantity | 120 | 178
Reference | Milestone B ADM | LRIP Lot 4 ADM
Start Year | 2009 | 2009
End Year | 2011 | 2012
The SM-6 program received authorization to enter into a fourth year of LRIP as documented in the ADM dated April 5, 2012. This ADM authorized the increase in the total LRIP quantity from 120 (10 percent) to 178 (15 percent) based on a procurement profile of 1200 missiles, and deferred the FRP decision to FY 2013.
The SM-6 program received authorization to increase the procurement profile from 1200 missiles to 1800 missiles as documented in the Navy Electronic Resources and Requirements Review Board memorandum, dated March 18, 2013.
The SM-6 program built up 25 non-LRIP rounds to be test fired during the System Development and Demonstration phase of the program. All 25 missiles were expended prior to IOC.

## Table 21
Foreign Military Sales
None
Nuclear Costs
None

## Table 22
Unit Cost
Unit Cost Report
Item |  | BY 2004 $M |  | BY 2004 $M |  | % Change
|  | Current UCR Baseline (Aug 2013 APB) |  | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 7688.6 |  |  |  | 7236.4
Quantity | 1800 |  |  |  | 1800
Unit Cost | 4.271 |  |  |  | 4.02 |  | -5.88
Average Procurement Unit Cost
Cost | 6854.1 |  |  |  | 6401.7
Quantity | 1800 |  |  |  | 1800
Unit Cost | 3.808 |  |  |  | 3.556 |  | -6.62
Item |  | BY 2004 $M | BY 2004 $M |  |  | % Change
|  | Original UCR Baseline (Jul 2004 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 4866.3 |  |  |  | 7236.4
Quantity | 1200 |  |  |  | 1800
Unit Cost | 4.055 |  |  |  | 4.02 |  | -0.86
Average Procurement Unit Cost
Cost | 3949.6 |  |  |  | 6401.7
Quantity | 1200 |  |  |  | 1800
Unit Cost | 3.291 |  |  |  | 3.556 |  | 8.05

## Table 23
Unit Cost History
Item | [7 empty] | Date |  |  |  | BY 2004 $M | [7 empty] | TY $M
[12 empty] | PAUC |  |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Jul 2004 | [6 empty] | 4.055 |  |  |  |  | 3.291 |  |  |  | 4.986 |  |  |  | 4.163
APB as of January 2006 |  |  |  |  | Jul 2004 | [6 empty] | 4.055 |  |  |  |  | 3.291 |  |  |  | 4.986 |  |  |  | 4.163
Revised Original APB |  |  |  |  | N/A | [6 empty] | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | Mar 2010 | [6 empty] | 4.401 |  |  |  |  | 3.683 |  |  |  | 5.498 |  |  |  | 4.695
Current APB |  |  |  |  | Aug 2013 | [6 empty] | 4.271 |  |  |  |  | 3.808 |  |  |  | 5.865 |  |  |  | 5.347
Prior Annual SAR |  |  |  |  | Dec 2014 | [6 empty] | 3.962 |  |  |  |  | 3.498 |  |  |  | 5.389 |  |  |  | 4.87
Current Estimate |  |  |  |  | Dec 2015 | [6 empty] | 4.02 |  |  |  |  | 3.556 |  |  |  | 5.45 |  |  |  | 4.932
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [21 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  |  | Oth |  | Spt |  |  | Total
4.986 0.114 0.000 -0.046 0.000 0.153 0.000 0.291 0.512 5.498
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [19 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng | Est |  | Oth |  | Spt |  |  | Total
5.498 -0.050 -0.377 0.141 0.000 0.050 0.000 0.188 -0.048 5.450

## Table 24
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [11 empty] | APUC Production Estimate
| Econ | Qty |  |  | Sch |  | Eng |  | Est | Oth | Spt | Total
4.163 0.085 0.000 -0.046 0.000 0.202 0.000 0.291 0.532 4.695
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [11 empty] | APUC Current Estimate
| Econ |  | Qty |  |  | Sch | Eng |  | Est | Oth | Spt | Total
4.695 -0.050 -0.109 0.141 0.000 0.067 0.000 0.188 0.237 4.932
SAR Baseline History
Item |  |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Milestone B |  |  |  | N/A |  |  |  | Jun 2004 |  |  | Jun 2004 |  |  | Jun 2004
Milestone C |  |  |  | N/A |  |  |  | Sep 2008 |  |  | Jun 2009 |  |  | Aug 2009
IOC |  |  |  | N/A |  |  |  | Sep 2010 |  |  | Mar 2011 |  |  | Nov 2013
Total Cost (TY $M) |  |  |  | N/A |  |  |  | 5983.3 |  |  | 6597.2 |  |  | 9810.2
Total Quantity |  |  |  | N/A |  |  |  | 1200 |  |  | 1200 |  |  | 1800
PAUC |  |  |  | N/A |  |  |  | 4.986 |  |  | 5.498 |  |  | 5.45

## Table 25
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 963.2 | 5634 | -- | 6597.2
Previous Changes
Economic | 1.2 | -31.1 | -- | -29.9
Quantity | -- | 2619.6 | -- | 2619.6
Schedule | -- | 245.6 | -- | 245.6
Engineering | -- | -- | -- | --
Estimating | -31 | -21.8 | -- | -52.8
Other | -- | -- | -- | --
Support | -- | 320 | -- | 320
Subtotal | -29.8 | 3132.3 | -- | 3102.5
Current Changes
Economic | -- | -59.2 | -- | -59.2
Quantity | -- | -- | -- | --
Schedule | -- | 8.9 | -- | 8.9
Engineering | -- | -- | -- | --
Estimating | -- | 142.7 | -- | 142.7
Other | -- | -- | -- | --
Support | -- | 18.1 | -- | 18.1
Subtotal | -- | 110.5 | -- | 110.5
Total Changes | -29.8 | 3242.8 | -- | 3213
CE - Cost Variance | 933.4 | 8876.8 | -- | 9810.2
CE - Cost & Funding | 933.4 | 8876.8 | -- | 9810.2

## Table 26
Summary BY 2004 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 861.6 | 4419.5 | -- | 5281.1
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | 1761.1 | -- | 1761.1
Schedule | -- | 20.4 | -- | 20.4
Engineering | -- | -- | -- | --
Estimating | -26.9 | -97.2 | -- | -124.1
Other | -- | -- | -- | --
Support | -- | 193.4 | -- | 193.4
Subtotal | -26.9 | 1877.7 | -- | 1850.8
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | 92.7 | -- | 92.7
Other | -- | -- | -- | --
Support | -- | 11.8 | -- | 11.8
Subtotal | -- | 104.5 | -- | 104.5
Total Changes | -26.9 | 1982.2 | -- | 1955.3
CE - Cost Variance | 834.7 | 6401.7 | -- | 7236.4
CE - Cost & Funding | 834.7 | 6401.7 | -- | 7236.4
Previous Estimate: December 2014

## Table 27
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -59.2
Reduction in funding for other Navy priorities led to a re-distribution of the procurement buy profile from FY 2015 and FY 2026. (Schedule)
Revised estimate due to SM-6 Block IA FY 2015 / FY 2016 contract negotiation position being higher than previously budgeted All Up Round pricing. (Estimating)
Revised estimate for SM-6 Block IA pricing to align the out years with the higher FY 2015 / FY 2016 contract negotiation pricing position for All Up Round. (Estimating)
Revised estimate due to Congressional reduction in FY 2016 which resulted in a change in the SM-6 Block I and Block IA procurement buy mix. (Estimating)
0.0 +8.9
+45.4 +58.0
+77.8 +125.2
-14.0 -18.1
Realignment of funds in FYDP for higher Navy priorities. (Estimating) -22.6 -30.1
Adjustment for current and prior escalation. (Estimating) +6.1 +7.7
Adjustment for current and prior escalation. (Support) +0.9 +1.1
Increase in Other Support due to realignment of funds. (Support) +0.9 +1.7
Increase in Initial Spares requirements estimated as a percent of All Up Round hardware. (Support)
+10.0 +15.3
Procurement Subtotal +104.5 +110.5

## Table 28
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: SM-6 FRP
Contractor: RMS Missile Systems (RMS)
Contractor Location: 1151 Hermans Road
Tucson, AZ 85756
Contract Number: N00024-13-C-5407/0
Contract Type: Firm Fixed Price (FFP)
Award Date: January 31, 2013
Definitization Date: September 26, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
276.8 N/A 89 564.8 N/A 182 564.8 564.8
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract modification P00014 which awarded the FY 2014 contract option on June 25, 2014.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
On January 31, 2013, Raytheon Missile Systems was awarded a contract for Long Lead Material for the FY 2013 FRP contract. The base contract (FY 2013) was definitized on September 26, 2013. The FY 2014 contract option was awarded on June 25, 2014.

## Table 29
Contract Identification
Appropriation: Procurement
Contract Name: SM-6 FRP 15/16
Contractor: Raytheon
Contractor Location: 1151 East Hermans Road
Tucson, AZ 85756
Contract Number: N00024-15-C-5408/1
Contract Type: Firm Fixed Price (FFP)
Award Date: May 29, 2015
Definitization Date: May 29, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
259.1 N/A 93 515.0 N/A 101 515.0 515.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the Initial Contract Price Target reflects the FY 2015 basic contract awarded on May 30, 2015 and the Current Contract Price Target reflects the FY 2016 contract option awarded on February 26, 2016.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This is the first time this contract is being reported.

## Table 30
Contract Identification
Appropriation: Procurement
Contract Name: SM-6 LRIP 4
Contractor: Raytheon Missile Systems (RMS)
Contractor Location: 1151 East Hermans Road
Tucson, AZ 85756
Contract Number: N00024-12-C-5401/1
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: May 10, 2012
Definitization Date: July 05, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
266.4 279.2 89 266.4 279.2 89 266.4 266.4
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (8/31/2015) -1.1 -0.5
Previous Cumulative Variances -0.4 -7.6
Net Change -0.7 +7.1
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to actuals being slightly higher than the budget at completion.
The favorable net change in the schedule variance is due to Raytheon making deliveries in accordance with the baseline plan. 100% of the All Up Round deliveries were completed as of April 30, 2015.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 31
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 250 | 250 | 1800 | 13.89%
Total Program Quantity Delivered | 250 | 250 | 1800 | 13.89%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
9810.2
1955.7
19.94%
23
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
13
56.52%
3227.8
32.9%
The above data is current as of February 09, 2016.

## Table 32
Operating and Support Cost
Cost Estimate Details
Date of Estimate: May 13, 2013
Source of Estimate: CAPE ICE
Quantity to Sustain: 1800
Unit of Measure: Missile
Service Life per Unit: 30.00 Years
Fiscal Years in Service: FY 2013 - FY 2054
Since the SM-6 is a wooden round (a concept that pictures a weapon as being completely reliable and, while deployed on board a ship, having an infinite shelf life while at the same time requiring no special handling, storage, surveillance, or maintenance by ships force personnel), Personnel Costs are unnecessary for missile operation.
The average annual cost per missile assumes 1800 All Up Rounds over a 30 year life cycle.
Unit Level Consumption includes Range and Target Costs, as well as Post Flight Analysis.
Intermediate Maintenance consists of Intermediate Level Maintenance facility costs.
Depot Maintenance includes Depot Maintenance and Refurbishment.
Sustaining Support includes Sustaining Investment and Software Maintenance.
Indirect Costs includes Installation and Personnel Support.
Sustainment Strategy
SM-6 will leverage the proven and mature STANDARD Missile product support infrastructure. No unique storage, transportation, handling facilities, or launching systems will be required. The All Up Round will be considered a "wooden round" on board ship, with no Operational Level Maintenance (O-Level) required. In the future, a shipboard portable Maintenance Built-In-Test (MBIT) capability will allow a team to come aboard and test or install new software into the SM- 6 round.
Antecedent Information
For reporting purposes, SM-2 is the antecedent by definition of the closest analogous system to SM-6. The SM-6 program meets a different threat set and demonstrates enhanced capabilities in comparison to the SM-2 program.
SM-2 Cost/Missile/Year based on average quantity serviced in FY 2015, converted to BY 2004$. SM-2 BLK IIIA/IIIB FY 2015 PB is the basis for the SM-2 average annual cost per missile.
The final SM-2 SAR was reported in December 2003. The total O&S reported in the final SM-2 SAR has been converted to BY 2004$ for comparison.

## Table 33
Annual O&S Costs BY2004 $K
Cost Element |  | SM-6 Average Annual Cost Per Missile | [5 empty] | SM-2 (Antecedent) Average Annual Cost Per Missile
Unit-Level Manpower |  | 0 | [5 empty] | 0
Unit Operations |  | 3 | [5 empty] | 1.5
Maintenance |  | 3.2 | [5 empty] | 5
Sustaining Support |  | 2.1 | [5 empty] | 1.2
Continuing System Improvements |  | 0 | [5 empty] | 0
Indirect Support |  | 0.2 | [5 empty] | 0.5
Other |  | 0 | [5 empty] | 0
Total |  | 8.5 | [5 empty] | 8.2
Item | Total O&S Cost $M
| SM-6 | [7 empty] | SM-2 (Antecedent)
| Current Production APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 443 |  |  | 487.3 |  |  | 460.3 |  | 912.3
Then Year | 863.9 |  |  | N/A |  |  | 845.9 |  | 0
Equation to Translate Annual Cost to Total Cost
Average Annual Missile O&S Cost = Total O&S Cost / number of missiles / number of operational missile years.
Total O&S Cost = $460.3M (BY04$) Number of missiles = 1800
Number of operational years = 30 year life cycle
Differences in Annual Cost per Missile and Total O&S Cost are due to rounding issues.
O&S Cost Variance
Category |  |  | BY 2004 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
460.3
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 460.3
Disposal Estimate Details

## Table 34
Date of Estimate: Source of Estimate:
Disposal/Demilitarization Total Cost (BY 2004 $M):
The Army is responsible for demilitarization of all DoD missile systems at the end of the missile service life, including the STANDARD missile. Disposal costs are not identified at this time.