## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-303
Ship to Shore Connector Amphibious Craft (SSC)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 16
Cost and Funding 17
Low Rate Initial Production 29
Foreign Military Sales 30
Nuclear Costs 30
Unit Cost 31
Cost Variance 34
Contracts 37
Deliveries and Expenditures 38
Operating and Support Cost 39

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Ship to Shore Connector Amphibious Craft (SSC)
DoD Component
Navy
Responsible Office
Mr. Thomas Rivers
Program Executive Office, Ships Amphibious Warfare Program Office 1333 Isaac Hull Avenue
Washington, DC 20376-2101
thomas.m.rivers@navy.mil
Phone: | 202-781-0940
Fax: | 202-781-4596
DSN Phone: | 326-0940
DSN Fax: | 326-4597
Date Assigned: | September 28, 2015
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated July 5, 2012
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated July 5, 2012

## Table 6
Mission and Description
Ship to Shore Connector (SSC) is the Landing Craft, Air Cushion (LCAC) replacement. It is an Air Cushion Vehicle with the same footprint as the LCAC Service Life Extension Program. The SSC mission is to land surface assault elements in support of Operational Maneuver from the Sea at Over-The-Horizon distances, while operating from amphibious ships and mobile landing platforms. The primary role of SSC is to transport weapon systems, equipment, cargo, and personnel of the assault elements of the Marine Expeditionary Brigades and the Army Brigade Combat Teams during Ship-to-Objective Maneuver and Prepare for Movement operations.

## Table 7
Executive Summary
The end of 2015 marked the completion of another successful year for the SSC program. The program successfully revalidated the CDD, achieved Milestone C, began its first year of the Production and Development (P&D) phase, held two Integrated Baseline Reviews (IBRs) with the Shipbuilder and established Performance Measurement Baselines (PMBs).
The Navy also authorized the option for two additional craft, Landing Craft Air Cushion (LCAC) 102 and LCAC 103, on March 31, 2015.
The Government and Shipbuilder held an IBR for LCAC 101 in February 2015 and for LCACs 102 and 103 in November 2015. Lessons learned from Craft 100 and LCAC 101 IBRs were incorporated as applicable. This improved upon the integrity and reliability of each PMB resulting in its successful assessment. As a result, a mutual understanding of the budget, schedule, and program risks was achieved.
Craft 100 and LCAC 101 moved steadily through the production line in 2015. In November, Craft 100 marked a significant production milestone: hull turnover. The craft's hull is initially constructed upside down for ease of welding and construction, and then 'flipped' to complete its assembly. The turnover is a major transition point as the first craft entered the above deck module integration phase of production. LCAC 101 began fabrication in January and has progressed to the second station in hull construction to complete the buoyancy box structure and initial wiring of equipment. Moreover, all required work packages are complete for Craft 100 and LCAC 101 to sustain production. LCAC 102 and 103 production will begin in FY 2016. A delay in the delivery of aluminum slowed some shop work and Textron experienced challenges with their robotic welder. Despite these issues, Textron was able to implement workarounds to continue construction progress and remains on track to deliver Craft 100 and LCAC 101 within threshold.
Milestone C preparations occurred during the first two quarters of CY 2015. The program was required to complete 12 program-specific exit criteria in order to demonstrate the design is stable and meets requirements based on performance. The program updated the Acquisition Strategy, completed an Operational Assessment, developed mature software capability, re-validated the CDD, proved costs are within the affordability caps, and demonstrated no significant manufacturing risks, complete interoperability, and operational supportability.
In addition to program accomplishments, an Independent Logistics Assessment was conducted which evaluated the adequacy and program health of logistics planning, management, resources, affordability, risk mitigation, and execution of the SSC program. In February 2015, the program received certification of its product support program. The Naval Center for Cost Analysis completed an updated SCP in May 2015 projecting SSC program costs within the APB. The SSC CDD to support the Milestone C decision was revalidated by the Chief of Naval Operations and approved by the JROC on October 8, 2015, with no changes to the KPPs or Key System Attributes that impact design or production. The effort culminated on May 26, 2015 with a successful Milestone C review held with the MDA, the Assistant Secretary of the Navy for Research, Development and Acquisition. The review included an evaluation of key factors that ensured adequate design maturity, production readiness, efficient manufacturing capability and low technical risk. The MDA approved the SSC program to enter the P&D Phase based on demonstrating the low technical risk of the detail design, software development progress and solid reliability growth program. This is a major accomplishment, and paves the way for the production and delivery of 72 new LCACs for our fleet.
Software Release 1 is completed, and Release 2 integration tests and Release 3 development are ongoing.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | Jul 2012 | Jul 2012 | Jul 2012 | Jul 2012
T&T Craft DD&C Award | Jul 2012 | Jul 2012 | Jul 2012 | Jul 2012
Craft 101 OE | Mar 2013 | Mar 2013 | Sep 2013 | Dec 2012
OA | Mar 2014 | Mar 2014 | Sep 2014 | Jul 2014
Craft 101 Production Readiness Review | May 2014 | May 2014 | Nov 2014 | Sep 2014
Craft 101 Start Fabrication | Dec 2014 | Dec 2014 | Jun 2015 | Jan 2015
Milestone C | Nov 2014 | Nov 2014 | May 2015 | May 2015
T&T Craft Delivery | Feb 2017 | Feb 2017 | Aug 2017 | May 2017
Craft 101 Delivery | Aug 2017 | Aug 2017 | Feb 2018 | Aug 2017
OPEVAL/IOT&E | Apr 2018 | Apr 2018 | Oct 2018 | Apr 2018
FRP Decision | Sep 2018 | Sep 2018 | Mar 2019 | Sep 2018
IOC | Aug 2020 | Aug 2020 | Feb 2021 | Aug 2020
Change Explanations

## Table 10
Acronyms and Abbreviations
DD&C - Detail Design and Construction IOT&E - Initial Operational Test and Evaluation OA - Operational Assessment
OE - Option Exercise
OPEVAL - Operational Evaluation T&T - Test and Training

## Table 11
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Payload Capacity
The SSC should be | The SSC should be | The SSC should be | TBD | The SSC should be
capable of transporting | capable of transporting | capable of transporting |  | capable of transporting
79 short tons over the | 79 short tons over the | 74 short tons over the |  | 74 short tons over the
threshold range in the | threshold range in the | threshold range in the |  | threshold range in the
threshold temperature | threshold temperature | threshold temperature |  | threshold temperature
operating range and | operating range and | operating range and |  | operating range and
threshold sea state. | threshold sea state. | threshold sea state. |  | threshold sea state.
Interoperability
In addition to the | In addition to the | The SSC shall be able | TBD | The SSC shall be able
threshold Interoperabil- | threshold Interoperabil- | to: enter, exit, and |  | to: enter, exit, and
ity, the SSC should be | ity, the SSC should be | embark in well decks |  | embark in well decks of
able to operate with | able to operate with | of current and |  | current and
allied amphibious ships | allied amphibious | programmed USN |  | programmed USN
classes with suitable | ships classes with | amphibious ships, to |  | amphibious ships, to
well decks, to include | suitable well decks, to | include LHD-1, LPD- |  | include LHD-1, LPD-17,
French Mistral, | include French Mistral, | 17, LSD-41, LSD-49 |  | LSD-41, LSD-49
Japanese Osumi, | Japanese Osumi, | classes, without ship |  | classes, without ship
Korean Dokdo, Spanish | Korean Dokdo, | alterations, while |  | alterations, while
Juan Carlos, and | Spanish Juan Carlos, | transporting an |  | transporting an
Australian Canberra if | and Australian | embarked load 168" |  | embarked load 168"
this interoperabil-ity | Canberra if this | high; the off cushion |  | high; the off cushion
does not alter other | interoperabil-ity does | length of the SSC shall |  | length of the SSC shall
interfaces. | not alter other | permit embarkation of |  | permit embarkation of
| interfaces. | (4) SSCs in LSD-41 |  | (4) SSCs in LSD-41
|  | class, (2) SSCs in |  | class, (2) SSCs in LSD-
|  | LSD-49 and LPD-17 |  | 49 and LPD-17 classes,
|  | classes, and (3) SSCs |  | and (3) SSCs in LHD-1
|  | in LHD-1 class; and, |  | class; and, enter/exit
|  | enter/exit well decks of |  | well decks of
|  | amphibious ships while |  | amphibious ships while
|  | on cushion or in |  | on cushion or in
|  | displacement mode |  | displacement mode
|  | (wet well only). SSC |  | (wet well only). SSC
|  | shall embark on board |  | shall embark on board
|  | the planned MLP, |  | the planned MLP,
|  | without ship |  | without ship alterations,
|  | alterations, as |  | as designed and built for
|  | designed and built for |  | the LCAC. SSC shall be
|  | the LCAC. SSC shall |  | able to operate with
|  | be able to operate with |  | existing ships services,
|  | existing ships services, |  | including the planned
|  | including the planned |  | MLP, in place for the
|  | MLP, in place for the |  | LCAC including ship’s

## Table 12
|  | LCAC including ship’s |  | power, fueling/ defueling
|  | power, fueling/ |  | stations, compressed
|  | defueling stations, |  | air, potable and
|  | compressed air, |  | washdown water,
|  | potable and washdown |  | lighting, navigational
|  | water, lighting, |  | aids, footprint for spare /
|  | navigational aids, |  | consumable pack-up
|  | footprint for spare / |  | kits, and night vision
|  | consumable pack-up |  | systems. The SSC shall
|  | kits, and night vision |  | be able to enter and exit
|  | systems. |  | allied amphibious ships
Mistral (French) and
Osumi (Japan).
Net-Ready
The SSC should fully | The SSC should fully | The SSC must fully | TBD | The SSC must fully
support execution of all | support execution of all | support execution of |  | support execution of
operational activities | operational activities | joint critical operational |  | joint critical operational
and information | and information | activities and |  | activities and
exchanges identified in | exchanges identified in | information exchanges |  | information exchanges
DoD Enterprise | DoD Enterprise | identified in the DoD |  | identified in the DoD
Architecture and | Architecture and | Enterprise Architecture |  | Enterprise Architecture
solution architectures | solution architectures | and solution |  | and solution
based on integrated | based on integrated | architectures based on |  | architectures based on
DoDAF content, and | DoDAF content, and | integrated DoDAF |  | integrated DoDAF
must satisfy the | must satisfy the | content, and must |  | content, and must
technical requirements | technical requirements | satisfy the technical |  | satisfy the technical
for transition to Net- | for transition to Net- | requirements for |  | requirements for
Centric military | Centric military | transition to Net- |  | transition to Net-Centric
operations to include: 1) | operations to include: | Centric military |  | military operations to
Solution architecture | 1) Solution architecture | operations to include: |  | include: 1) Solution
products compliant with | products compliant | 1) Solution architecture |  | architecture products
DoD Enterprise | with DoD Enterprise | products compliant |  | compliant with DoD
Architecture based on | Architecture based on | with DoD Enterprise |  | Enterprise Architecture
integrated DoDAF | integrated DoDAF | Architecture based on |  | based on integrated
content, including | content, including | integrated DoDAF |  | DoDAF content,
specified operationally | specified operationally | content, including |  | including specified
effective information | effective information | specified operationally |  | operationally effective
exchanges. 2) | exchanges. 2) | effective information |  | information exchanges.
Compliant with Net - | Compliant with Net - | exchanges. 2) |  | 2) Compliant with Net-
Centric Data Strategy | Centric Data Strategy | Compliant with Net - |  | Centric Data Strategy
and Net-Centric | and Net-Centric | Centric Data Strategy |  | and Net-Centric
Services Strategy, and | Services Strategy, and | and Net-Centric |  | Services Strategy, and
the principles and rules | the principles and rules | Services Strategy, and |  | the principles and rules
identified in the DoD | identified in the DoD | the principles and rules |  | identified in the DoD
IEA, excepting tactical | IEA, excepting tactical | identified in the DoD |  | IEA, excepting tactical
and non-IP communica- | and non-IP | IEA, excepting tactical |  | and non-IP communica-
tions. 3) Compliant with | communica-tions. 3) | and non-IP communica |  | tions. 3) Compliant with
GIG Technical Guidance | Compliant with GIG | -tions. 3) Compliant |  | GIG Technical Guidance
to include IT Standards | Technical Guidance to | with GIG Technical |  | to include IT Standards
identified in the TV-1 | include IT Standards | Guidance to include IT |  | identified in the TV-1
and implementa-tion | identified in the TV-1 | Standards identified in |  | and implementa-tion
guidance of GESPs, | and implementa-tion | the TV-1 and |  | guidance of GESPs
necessary to meet all | guidance of GESPs, | implementa-tion |  | necessary to meet all

## Table 13
operational requirements specified in the DoD Enterprise Architecture and solution architecture views. 4) Information assurance requirements including availability, integrity, authentica-tion, confidential-ity, and non- repudiation, and issuance of an ATO by the DAA. 5) Supportabil- ity requirements to include SAASM, Spectrum and JTRS require-ments. See appendix A of the CDD for additional details on the NR-KPP. | necessary to meet all operational requirements specified in the DoD Enterprise Architecture and solution architecture views. 4) Information assurance requirements including availability, integrity, authenticat-ion, confidential-ity, and non-repudiation, and issuance of an ATO by the DAA. 5) Supportabil-ity requirements to include SAASM, Spectrum and JTRS require-ments. See appendix A of the CDD for additional details on the NR-KPP. | guidance of GESPs necessary to meet all operational requirements specified in the DoD Enterprise Architecture and solution architecture views. 4) Information assurance requirements including availability, integrity, authenticat-ion, confidential-ity, and non-repudiation, and issuance of an IATO or ATO by the DAA. 5) Supportabil-ity requirements to include SAASM, Spectrum and JTRS require-ments. See appendix A of the CDD for additional details on the NR-KPP. |  | operational requirements specified in the DoD Enterprise Architecture and solution architecture views. 4) Information assurance requirements including availability, integrity, authentication, confidentiality, and non- repudiation, and issuance of an IATO or ATO by the DAA. 5) Supportability requirements to include SAASM, Spectrum and JTRS require-ments. See appendix A of the CDD for additional details on the NR-KPP.
Force Protection
The SSC should be equipped with a remotely operated crew- served weapon system and provide ballistic and fragmenta-tion protection for crew, internally carried embarked forces and critical machinery spaces. Appendix F of the CDD describes the specific ballistic protection requirement. | The SSC should be equipped with a remotely operated crew-served weapon system and provide ballistic and fragmenta -tion protection for crew, internally carried embarked forces and critical machinery spaces. Appendix F of the CDD describes the specific ballistic protection requirement. | The SSC shall provide protection to the crew and internally carried embarked forces from small arms, crew served weapons and fragmenta-tion. Appendix F of the CDD describes the specific ballistic protection requirement. The SSC shall be equipped with mounts capable of accepting current US crew-served weapons to include the M2 .50 Caliber (12.7mm) Machine Gun, MK19 40mm Grenade Machine Gun and M60/M240 Series 7.62mm Light Machine Gun. | TBD | The SSC shall provide protection to the crew and internally carried embarked forces from small arms, crew served weapons and fragmentation. Appendix F of the CDD describes the specific ballistic protection requirement. The SSC shall be equipped with mounts capable of accepting current US crew-served weapons to include the M2 .50 Caliber (12.7mm) Machine Gun, MK19 40mm Grenade Machine Gun and M60/M240 Series 7.62mm Light Machine Gun.
Survivability (Sea-Worthiness)
T=O The SSC shall be capable of surviving (remaining afloat) in | T=O The SSC shall be capable of surviving (remaining afloat) in | T=O The SSC shall be capable of surviving (remaining afloat) in | TBD | T=O The SSC shall be capable of surviving (remaining afloat) in

## Table 14
displacement mode without power or steerage through seas up to ten foot SWH without incurring structural damage which would impair mission capability until recovered or towed to a boat haven. | displacement mode without power or steerage through seas up to ten foot SWH without incurring structural damage which would impair mission capability until recovered or towed to a boat haven. | displacement mode without power or steerage through seas up to ten foot SWH without incurring structural damage which would impair mission capability until recovered or towed to a boat haven. |  | displacement mode without power or steerage through seas up to ten foot SWH without incurring structural damage which would impair mission capability until recovered or towed to a boat haven.
Manpower
The SSC should be fully operable with a crew of no more than three (3). | The SSC should be fully operable with a crew of no more than three (3). | The SSC shall be fully operable, to include conducting on load/offload operations, with a crew of no more than five (5). | TBD | The SSC shall be fully operable, to include conducting on load/offload operations, with a crew of no more than five (5).
Materiel Availability (Am)
The SSC should have a Materiel Availability of 63 percent. | The SSC should have a Materiel Availability of 63 percent. | The SSC shall have a Materiel Availability of 59.5 percent. | TBD | The SSC shall have a Materiel Availability of 61.9 percent.
Inland Accessibility
T=O The SSC shall be capable of operating over the high water mark. This includes movement over ice, mud, rivers, swamps, and marshes. While moving inland, the SSC shall be able to negotiate obstacles found in the complex operational environment (natural and man- made). The SSC shall be able to operate over a beach high water mark, rocks, rubble, obstacles and walls up to 4 feet high, grass, reeds and dunes. | T=O The SSC shall be capable of operating over the high water mark. This includes movement over ice, mud, rivers, swamps, and marshes. While moving inland, the SSC shall be able to negotiate obstacles found in the complex operational environment (natural and man-made). The SSC shall be able to operate over a beach high water mark, rocks, rubble, obstacles and walls up to 4 feet high, grass, reeds and dunes. | T=O The SSC shall be capable of operating over the high water mark. This includes movement over ice, mud, rivers, swamps, and marshes. While moving inland, the SSC shall be able to negotiate obstacles found in the complex operational environment (natural and man-made). The SSC shall be able to operate over a beach high water mark, rocks, rubble, obstacles and walls up to 4 feet high, grass, reeds and dunes. | TBD | T=O The SSC shall be capable of operating over the high water mark. This includes movement over ice, mud, rivers, swamps, and marshes. While moving inland, the SSC shall be able to negotiate obstacles found in the complex operational environment (natural and man- made). The SSC shall be able to operate over a beach high water mark, rocks, rubble, obstacles and walls up to 4 feet high, grass, reeds and dunes.
Requirements Reference
Capability Development Document (CDD) dated June 10, 2010
Change Explanations
None

## Table 15
Notes
The following footnotes apply to Interoperability Threshold Key Performance Parameters:
1/ LSD-41 well deck can embark a fifth craft in a non-tactical capacity without ship services. 2/ LHD-1 Power converter for 3rd spot not part of Pack Up Kit footprint.
3/ MLP ship’s power for SSC may require alteration or separate pieces of equipment which is not part of Pack Up Kit footprint.
Acronyms and Abbreviations
ATO - Authority to Operate
CDD - Capability Development Document DAA - Designated Approval Authority
DoD IEA - Department of Defense Information Enterprise Architecture DoDAF - Department of Defense Architecture Framework
GESP - GIG Enterprise Service Profile GIG - Global Information Grid
IATO - Interim Authority to Operate IP - Internet Protocol
IT - Information Technology
JTRS - Joint Tactical Radio System LCAC - Landing Craft Air Cushion MLP - Mobile Landing Platform
mm - Millimeter
NR-KPP - Net Ready Key Performance Parameter O - Objective
SAASM - Selective Availability Anti-Spoofing Module SWH - Significant Wave Height
T - Threshold
TV - Technical View US - United States
USN - United States Navy

## Table 16
Track to Budget
RDT&E
Appn BA PE
Navy 1319 04 0603564N
Project Name
3127 Preliminary Design and Feasibility Study
(Shared) (Sunk)
Notes: Preliminary Design and Feasibility Study/SSC Design
Navy 1319 05 0604567N
Project Name
3133 Ship to Shore Connectors Contract Design
(Sunk)
3137 SSC Construction (Sunk) Navy 1319 05 0605220N
Project Name
3133 Ship to Shore Connectors Contract Design
3137 SSC Construction
Procurement
Appn BA PE
Navy 1611 05 0204411N
Line Item Name
5110 Outfitting (Shared)
Navy 1611 05 0204228N
Line Item Name
5112 Ship to Shore Connector
Notes: Ship to Shore Connector End Cost

## Table 17
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2011 $M | [6 empty] | BY 2011 $M |  | TY $M
| SAR Baseline Development Estimate |  |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E |  | 552.7 |  |  | 552.7 | 608 |  |  | 495.4 |  | 571.9 |  |  | 571.9 |  | 510.7
Procurement |  | 3354.4 |  |  | 3354.4 | 3689.8 |  |  | 3153.3 |  | 4137.5 |  |  | 4137.5 |  | 4034.7
Flyaway |  | -- |  |  | -- | -- |  |  | 3094.2 |  | -- |  |  | -- |  | 3959.1
Recurring |  | -- |  |  | -- | -- |  |  | 3094.2 |  | -- |  |  | -- |  | 3959.1
Non Recurring |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support |  | -- |  |  | -- | -- |  |  | 59.1 |  | -- |  |  | -- |  | 75.6
Other Support |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Initial Spares |  | -- |  |  | -- | -- |  |  | 59.1 |  | -- |  |  | -- |  | 75.6
MILCON |  | 18.5 |  |  | 18.5 | 20.4 |  |  | 13.5 |  | 21.7 |  |  | 21.7 |  | 16
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 3925.6 |  |  | 3925.6 | N/A |  |  | 3662.2 |  | 4731.1 |  |  | 4731.1 |  | 4561.4
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The estimate to support this program, like most cost estimates, is built upon a product-oriented work breakdown structure based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which we have been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for Major Defense Acquisition Programs (MDAPs). Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about as likely the estimate will prove too low or too high for the program as described.
Total Quantity
Quantity |  |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  |  | 2 |  |  |  | 2 |  |  |  |  | 1
Procurement |  |  | 71 |  |  |  | 71 |  |  |  |  | 72
Total |  |  | 73 |  |  |  | 73 |  |  |  |  | 73

## Table 18
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 481.4 | 7.8 |  | 11.1 |  | 7 | 1.4 |  | 2 |  | 0 |  |  | 0 |  | 510.7
Procurement | 159.6 | 210.7 |  | 128.1 |  | 335.9 | 529.1 |  | 641.9 |  | 685.2 |  |  | 1344.2 |  | 4034.7
MILCON | 0 | 0 |  | 0 |  | 11 | 0 |  | 2.5 |  | 2.5 |  |  | 0 |  | 16
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 641 | 218.5 |  | 139.2 |  | 353.9 | 530.5 |  | 646.4 |  | 687.7 |  |  | 1344.2 |  | 4561.4
PB 2016 Total | 642.5 | 263.4 |  | 282.6 |  | 547 | 585 |  | 528.2 |  | 435.2 |  |  | 1412.6 |  | 4696.5
Delta | -1.5 | -44.9 |  | -143.4 |  | -193.1 | -54.5 |  | 118.2 |  | 252.5 |  |  | -68.4 |  | -135.1
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 1 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 1
Production | 0 |  | 3 |  | 4 | 2 | 6 |  | 10 |  | 12 | 12 |  | 23 |  | 72
PB 2017 Total | 1 |  | 3 |  | 4 | 2 | 6 |  | 10 |  | 12 | 12 |  | 23 |  | 73
PB 2016 Total | 1 |  | 3 |  | 5 | 5 | 9 |  | 10 |  | 9 | 8 |  | 23 |  | 73
Delta | 0 |  | 0 |  | -1 | -3 | -3 |  | 0 |  | 3 | 4 |  | 0 |  | 0

## Table 19
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.9
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 95.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 51
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 112.5
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 68.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.6
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.8
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.1
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.4
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2
Subtotal |  | 1 | -- |  | -- |  | -- |  | -- |  | -- |  | 510.7

## Table 20
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2011 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.1
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.7
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.9
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.4
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.7
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 93.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 107.4
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 64.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.2
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.2
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
Subtotal |  | 1 | -- |  | -- |  | -- |  | -- |  | -- |  | 495.4

## Table 21
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2019 |  | -- | 20 |  | -- |  | -- |  | 20 |  | -- |  | 20
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2021 |  | -- | 15 |  | -- |  | -- |  | 15 |  | -- |  | 15
Subtotal |  | -- | 35 |  | -- |  | -- |  | 35 |  | -- |  | 35

## Table 22
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | BY 2011 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2019 |  | -- | 17.1 |  | -- |  | -- |  | 17.1 |  | -- |  | 17.1
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2021 |  | -- | 12.3 |  | -- |  | -- |  | 12.3 |  | -- |  | 12.3
Subtotal |  | -- | 29.4 |  | -- |  | -- |  | 29.4 |  | -- |  | 29.4

## Table 23
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2015 |  | 3 | 156.7 |  | -- |  | -- |  | 156.7 |  | 2.9 |  | 159.6
2016 |  | 4 | 206.5 |  | -- |  | -- |  | 206.5 |  | 4.2 |  | 210.7
2017 |  | 2 | 125.9 |  | -- |  | -- |  | 125.9 |  | 2.2 |  | 128.1
2018 |  | 6 | 329.5 |  | -- |  | -- |  | 329.5 |  | 6.4 |  | 335.9
2019 |  | 10 | 498.6 |  | -- |  | -- |  | 498.6 |  | 10.5 |  | 509.1
2020 |  | 12 | 629 |  | -- |  | -- |  | 629 |  | 12.9 |  | 641.9
2021 |  | 12 | 658 |  | -- |  | -- |  | 658 |  | 12.2 |  | 670.2
2022 |  | 10 | 551.6 |  | -- |  | -- |  | 551.6 |  | 10.3 |  | 561.9
2023 |  | 13 | 708.8 |  | -- |  | -- |  | 708.8 |  | 14 |  | 722.8
2024 |  | -- | 17 |  | -- |  | -- |  | 17 |  | -- |  | 17
2025 |  | -- | 11.7 |  | -- |  | -- |  | 11.7 |  | -- |  | 11.7
2026 |  | -- | 12 |  | -- |  | -- |  | 12 |  | -- |  | 12
2027 |  | -- | 12.4 |  | -- |  | -- |  | 12.4 |  | -- |  | 12.4
2028 |  | -- | 6.4 |  | -- |  | -- |  | 6.4 |  | -- |  | 6.4
Subtotal |  | 72 | 3924.1 |  | -- |  | -- |  | 3924.1 |  | 75.6 |  | 3999.7

## Table 24
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | BY 2011 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2015 |  | 3 | 135.4 |  | -- |  | -- |  | 135.4 |  | 2.5 |  | 137.9
2016 |  | 4 | 175.2 |  | -- |  | -- |  | 175.2 |  | 3.6 |  | 178.8
2017 |  | 2 | 104.8 |  | -- |  | -- |  | 104.8 |  | 1.8 |  | 106.6
2018 |  | 6 | 269 |  | -- |  | -- |  | 269 |  | 5.2 |  | 274.2
2019 |  | 10 | 399 |  | -- |  | -- |  | 399 |  | 8.4 |  | 407.4
2020 |  | 12 | 493.5 |  | -- |  | -- |  | 493.5 |  | 10.1 |  | 503.6
2021 |  | 12 | 506.1 |  | -- |  | -- |  | 506.1 |  | 9.4 |  | 515.5
2022 |  | 10 | 416 |  | -- |  | -- |  | 416 |  | 7.7 |  | 423.7
2023 |  | 13 | 524 |  | -- |  | -- |  | 524 |  | 10.4 |  | 534.4
2024 |  | -- | 12.3 |  | -- |  | -- |  | 12.3 |  | -- |  | 12.3
2025 |  | -- | 8.3 |  | -- |  | -- |  | 8.3 |  | -- |  | 8.3
2026 |  | -- | 8.4 |  | -- |  | -- |  | 8.4 |  | -- |  | 8.4
2027 |  | -- | 8.5 |  | -- |  | -- |  | 8.5 |  | -- |  | 8.5
2028 |  | -- | 4.3 |  | -- |  | -- |  | 4.3 |  | -- |  | 4.3
Subtotal |  | 72 | 3064.8 |  | -- |  | -- |  | 3064.8 |  | 59.1 |  | 3123.9

## Table 25
The 2015 Defense Appropriations Act directed the completion of Craft 101 with the Shipbuilding and Conversion, Navy, appropriation.
Cost Quantity Information 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2011 $M
2015 | 3 | 135.4
2016 | 4 | 175.2
2017 | 2 | 104.8
2018 | 6 | 269
2019 | 10 | 399
2020 | 12 | 493.5
2021 | 12 | 506.1
2022 | 10 | 431.5
2023 | 13 | 550.3
2024 | -- | --
2025 | -- | --
2026 | -- | --
2027 | -- | --
2028 | -- | --
Subtotal | 72 | 3064.8

## Table 26
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
2018 | 11
2019 | --
2020 | 2.5
2021 | 2.5
Subtotal | 16

## Table 27
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 2011 $M
Total Program
2018 | 9.4
2019 | --
2020 | 2.1
2021 | 2
Subtotal | 13.5

## Table 28
MILCON reflects changes made to the Department of the Navy Service Cost Position for the Ship to Shore Connector.

## Table 29
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2012-07-05 | 2015-07-21
Approved Quantity | 13 | 13
Reference | Milestone B ADM | Milestone C ADM
Start Year | 2013 | 2013
End Year | 2021 | 2021
The Current Total LRIP Quantity is more than 10% of the total production quantity per the Milestone B approved Acquisition Strategy which establishes an initial production base for the system, provide for an orderly increase in the production rate prior to approval for FRP, and meet fleet operational requirements by FY 2020.

## Table 30
Foreign Military Sales
None
Nuclear Costs
None

## Table 31
Unit Cost
Unit Cost Report
Item |  | BY 2011 $M | BY 2011 $M |  | % Change
|  | Current UCR Baseline (Jul 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 3925.6 |  |  | 3662.2
Quantity | 73 |  |  | 73
Unit Cost | 53.775 |  |  | 50.167 |  | -6.71
Average Procurement Unit Cost
Cost | 3354.4 |  |  | 3153.3
Quantity | 71 |  |  | 72
Unit Cost | 47.245 |  |  | 43.796 |  | -7.3
Item |  | BY 2011 $M | BY 2011 $M |  | % Change
|  | Original UCR Baseline (Jul 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 3925.6 |  |  | 3662.2
Quantity | 73 |  |  | 73
Unit Cost | 53.775 |  |  | 50.167 |  | -6.71
Average Procurement Unit Cost
Cost | 3354.4 |  |  | 3153.3
Quantity | 71 |  |  | 72
Unit Cost | 47.245 |  |  | 43.796 |  | -7.3

## Table 32
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2011 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Jul 2012 |  |  |  |  | 53.775 |  |  | 47.245 |  |  | 64.81 |  |  | 58.275
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Current APB |  |  | Jul 2012 |  |  |  |  | 53.775 |  |  | 47.245 |  |  | 64.81 |  |  | 58.275
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 51.81 |  |  | 45.518 |  |  | 64.336 |  |  | 57.964
Current Estimate |  |  | Dec 2015 |  |  |  |  | 50.167 |  |  | 43.796 |  |  | 62.485 |  |  | 56.038
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
64.810 2.405 -0.020 -0.290 0.000 -4.221 0.000 -0.199 -2.325 62.485
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
58.275 2.454 -0.297 -0.294 0.000 -3.899 0.000 -0.201 -2.237 56.038

## Table 33
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Jul 2012 | N/A | Jul 2012
Milestone C | N/A | Nov 2014 | N/A | May 2015
IOC | N/A | Aug 2020 | N/A | Aug 2020
Total Cost (TY $M) | N/A | 4731.1 | N/A | 4561.4
Total Quantity | N/A | 73 | N/A | 73
PAUC | N/A | 64.81 | N/A | 62.485

## Table 34
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 571.9 | 4137.5 | 21.7 | 4731.1
Previous Changes
Economic | -0.3 | 169.4 | 0.2 | 169.3
Quantity | -38.4 | 36.9 | -- | -1.5
Schedule | -- | -35.8 | -- | -35.8
Engineering | -- | -- | -- | --
Estimating | -31.8 | -132.2 | -0.2 | -164.2
Other | -- | -- | -- | --
Support | -- | -2.4 | -- | -2.4
Subtotal | -70.5 | 35.9 | -- | -34.6
Current Changes
Economic | -0.9 | 7.3 | -0.1 | 6.3
Quantity | -- | -- | -- | --
Schedule | -- | 14.6 | -- | 14.6
Engineering | -- | -- | -- | --
Estimating | 10.2 | -148.5 | -5.6 | -143.9
Other | -- | -- | -- | --
Support | -- | -12.1 | -- | -12.1
Subtotal | 9.3 | -138.7 | -5.7 | -135.1
Total Changes | -61.2 | -102.8 | -5.7 | -169.7
CE - Cost Variance | 510.7 | 4034.7 | 16 | 4561.4
CE - Cost & Funding | 510.7 | 4034.7 | 16 | 4561.4

## Table 35
Summary BY 2011 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 552.7 | 3354.4 | 18.5 | 3925.6
Previous Changes
Economic | -- | -- | -- | --
Quantity | -35.8 | 31.8 | -- | -4
Schedule | -- | -3.1 | -- | -3.1
Engineering | -- | -- | -- | --
Estimating | -30.5 | -104.8 | -0.1 | -135.4
Other | -- | -- | -- | --
Support | -- | -1 | -- | -1
Subtotal | -66.3 | -77.1 | -0.1 | -143.5
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 9 | -113.8 | -4.9 | -109.7
Other | -- | -- | -- | --
Support | -- | -10.2 | -- | -10.2
Subtotal | 9 | -124 | -4.9 | -119.9
Total Changes | -57.3 | -201.1 | -5 | -263.4
CE - Cost Variance | 495.4 | 3153.3 | 13.5 | 3662.2
CE - Cost & Funding | 495.4 | 3153.3 | 13.5 | 3662.2
Previous Estimate: December 2014

## Table 36
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.9
Revised estimate aligns to Department of the Navy Milestone C SCP. (Estimating) | 7.7 | 8.8
Revised estimate to reflect execution year realignments. (Estimating) | -1.1 | -1.2
Revised estimate for Navy Working Capital Fund (NWCF) rate adjustments. (Estimating) | 1.6 | 1.8
Adjustment for current and prior escalation. (Estimating) | 0.8 | 0.8
RDT&E Subtotal | 9 | 9.3
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A +7.3
Stretch-out of procurement buy profile from FY 2016 thru FY 2024 to align with PB 2017. (Schedule)
Revised estimate to align procurement with Department of the Navy Milestone C SCP and PB 2017 (Ship Construction Navy). (Estimating)
0.0 +14.6
-85.4 -113.7
Revised estimate for NWCF rate adjustments. (Estimating) -27.1 -34.1
Revised estimate to align with Department of the Navy Milestone C SCP (OPN). (Estimating)
-0.5 +0.3
Adjustment for current and prior escalation. (Estimating) -0.8 -1.0
Decrease in Initial Spares to align the procurement with the Department of the Navy Milestone C SCP and the PB 2017. (Support)
-10.2 -12.1
Procurement Subtotal -124.0 -138.7
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.1
Revised estimate to align to Department of the Navy Milestone C SCP. (Estimating) | -4.9 | -5.6
MILCON Subtotal | -4.9 | -5.7

## Table 37
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: SSC Detail Design & Construction
Contractor: Textron, Inc
Contractor Location: 19401 Chef Menteur Hwy
New Orleans, LA 70129-2565
Contract Number: N00024-12-C-2401
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: July 06, 2012
Definitization Date: July 06, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
199.9 226.4 1 332.3 373.4 4 367.3 367.3
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to exercising contract options for the construction of three additional Landing Craft Air Cushions (LCAC) and for engineering changes.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/2/2016) -32.4 -34.9
Previous Cumulative Variances -15.8 -14.5
Net Change -16.6 -20.4
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to increased Textron non-recurring Level of Effort labor due to higher than anticipated manufacturing overhead rates and unanticipated efforts in vendors liaison, Earned Value, and Configuration Management. It is also due to increased discrete Engineering labor as a result of increased design complexity in various areas and to increased Textron Manufacturing and Touch labor associated with rework and Robotic welder issues.
The unfavorable net change in the schedule variance is due to delayed American Bureau of Shipbuilding - Naval Vessel Rules Certification & Full Authority Digital Engine Control environmental testing causing Rolls Royce main engine delivery delays and Integrated Logistics Support baseline activities scheduled unrealistically early.

## Table 38
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 1 | 0%
Production | 0 | 0 | 72 | 0%
Total Program Quantity Delivered | 0 | 0 | 73 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
4561.4
359.9
7.89%
23
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
11
47.83%
859.5
18.84%
The above data is current as of February 09, 2016.

## Table 39
Operating and Support Cost
Cost Estimate Details
Date of Estimate: May 19, 2015
Source of Estimate: SCP
Quantity to Sustain: 73
Unit of Measure: Craft
Service Life per Unit: 30.00 Years
Fiscal Years in Service: FY 2018 - FY 2057
Sustainment Strategy
The SSC product support strategy is based on performance driven sustainment and involves utilizing performance-based objectives with traditional data analysis practices to meet program sustainment goals. This strategy is based on implementing an effective supportability analysis program to develop and deliver the logistics products and processes necessary to execute an efficient, affordable sustainment program. Sustainment goals will be applied to both government and contractor support activities to use supportability analysis practices that delivers required craft availability while enabling best-cost improvement opportunities. Performance of the support activities will be measured by their assigned equipment availability as it relates to overall program operational and material availability measures.
Antecedent Information
LCAC-M is currently used as a financial model and management information tool by the LCAC Program. LCAC-M uses data from the most recent ten years of Operating Target data which funds LCAC Operations, Support, Readiness, Hours of Operation, Sustaining Support, and Continuing System Improvements to predict the O&S cost of a specified level of readiness. The LCAC-M model parameters were adjusted to reflect the specified 150 operating hours per year and manning specified in the CARD for the SSC.
Annual O&S Costs BY2011 $M
Cost Element | SSC Average Annual Cost Per Craft | LCAC (Antecedent) Average Annual Cost Per Craft
Unit-Level Manpower | 1.524 | 1.291
Unit Operations | 0.454 | 0.46
Maintenance | 1.09 | 1.357
Sustaining Support | 0.463 | 0.463
Continuing System Improvements | 0.264 | 0.329
Indirect Support | 0.819 | 0.41
Other | 0 | 0
Total | 4.614 | 4.31

## Table 40
Item | Total O&S Cost $M
| SSC | [5 empty] | LCAC (Antecedent)
| Current Development APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 10171.3 |  | 11188.4 |  |  | 10106 | 94370
Then Year | 18058.9 |  | N/A |  |  | 15657 | N/A
The total program O&S cost estimate is determined to be $15,657 TY$M. This total was de-escalated by the Naval Center for Cost Analysis to arrive at a total O&S Current Estimate of $10,106.0 BY 2011 $M.
Equation to Translate Annual Cost to Total Cost
Total O&S cost is calculated by multiplying the Average Annual Cost per Craft by the total number of craft by total years of service. 4.615 BY 2011 $M X 73 X 30 = $10,106.0 BY 2011 $M.
O&S Cost Variance
Category |  | BY 2011 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
10154
Programmatic/Planning Factors 0.0
Cost Estimating Methodology -48.0 Two factors changes the overall cost estimate at MS C: 1) Systems Engineering and Program Management support at warfare centers funded. 2) MS C estimate included a policy change to include previously non-DoD cost elements, health benefits for retirees under 65 as well as health care for active duty and active duty families.
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes -48.0
Current Estimate 10106.0
Disposal Estimate Details
Date of Estimate: May 19, 2015
Source of Estimate: SCP
Disposal/Demilitarization Total Cost (BY 2011 $M): Total costs for disposal of all Craft are 14.2
The SSC disposal cost estimate is based on the actual disposal costs of the ten LCAC disposed of to date.