## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-197
DDG 1000 Zumwalt Class Destroyer (DDG 1000)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 10
Schedule 11
Performance 13
Track to Budget 15
Cost and Funding 17
Low Rate Initial Production 27
Foreign Military Sales 28
Nuclear Costs 28
Unit Cost 29
Cost Variance 32
Contracts 35
Deliveries and Expenditures 41
Operating and Support Cost 42

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
DDG 1000 Zumwalt Class Destroyer (DDG 1000)
DoD Component
Navy
Responsible Office
RDML(S) James Downey
Program Executive Office Ships (PMS 500) 1333 Isaac Hull Ave. S.E. Stop 2202 Washington, DC 20376-2202
james.downey@navy.mil
Phone: | 202-781-2902
Fax: | 202-781-0021
DSN Phone: | 326-2902
DSN Fax: Date Assigned: | August 6, 2010
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated November 23, 2005
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated March 25, 2011

## Table 6
Mission and Description
DDG 1000 Zumwalt Class Destroyer (DDG 1000) will be an optimally-crewed, multi-mission surface combatant designed to fulfill volume firepower and precision strike requirements. This advanced warship will provide credible forward naval presence while operating independently or as an integral part of Naval, Joint, or Combined Expeditionary Strike Forces.
Armed with an array of weapons, DDG 1000 will provide offensive, distributed, and precision firepower at long ranges in support of forces ashore. To ensure effective operations in the littoral, DDG 1000 will incorporate signature reduction, active and passive self-defense systems, and enhanced survivability features.

## Table 7
Executive Summary
Program Highlights Since Last Report:
General
The Zumwalt program has made significant progress conducting the test, activation, and trials phase of the most challenging and complex class of ships the Navy has ever constructed. The Navy and the shipbuilder, General Dynamics Bath Iron Works (BIW) have evaluated yard-wide workload and scheduling for all construction efforts and contracts to address cost effective ship delivery approaches. The program continues to hold monthly joint BIW and Navy Flag-Level reviews, working closely to prepare for trials and delivery; and to ensure that lessons learned in the course of building and testing the first of class are being fully leveraged to improve performance on the follow ships.
Ship Status
The future USS Zumwalt (DDG 1000), the lead ship of the class is completing construction at BIW in Bath, ME. At approximately 98% complete, the program is heavily focused on the execution of an extensive series of test and trials in preparation for the Hull, Mechanical and Electrical (HM&E) delivery planned for mid-2016. This systematic approach to test and trials of ship systems will help identify and correct issues, mitigate risk and ensure a measured, deliberate approach as the Zumwalt transitions to the fleet. DDG 1000 completed an Alpha Trial December 7-13, 2015.
The stage test program is approximately 84% complete, with Builder’s and Acceptance trials planned to commence in early 2016.
DDG 1001 is approximately 84% complete. Test and activation work is in progress with the Energize High Voltage Power milestone planned for early 2016. The ship is schedule to be christened mid-2016.
DDG 1002 is approximately 43% complete. Keel laying is planned for quarter one FY 2017. BIW completed design of the DDG 1002 steel deckhouse which is 22% complete. On December 31, 2015, Raytheon was awarded a contract for remaining DDG 1002 Mission Systems Equipment (MSE).
There are no significant software-related issues with this program at this time.
History of Significant Developments Since Program Initiation:
January 8, 1995: The program achieved Milestone 0 and started the Cost and Operational Effectiveness Analysis for the surface combatant for the twenty-first century (SC 21), comprised of destroyers (DD 21) and cruisers (CG 21). The DD 21 was intended to replace the DDG 51 by providing advanced land attack and multi-mission capabilities.
January 1998: The program achieved Milestone I for DD 21 and proceeded into the Program Definition and Risk Reduction phase. Primary Milestone I risks identified were a ship with a new hull form, several new combat system elements, significantly reduced manning level, very low signatures, and at lower costs than DDG 51. In order to maintain competitive cost pressure and to maintain technical competition, the Navy awarded Phase I and II concept development contracts to two industry teams.
November 13, 2001: The DD 21 program was restructured into the DD(X) program.

## Table 8
April 2002: Phase II concept development concluded and the Navy competitively selected and awarded a Design and Development contract to Northrop Grumman (NG) Ship systems (now Huntington Ingalls Shipbuilding – HII). The NG team was subsequently expanded to a DD(X) “national” team that also included BIW, Lockheed Martin, and Boeing. The NG concept required RDT&E increases for many of the new technologies including integrated electric drive, radars, software development, optimized manning, the advanced gun, and munitions. To reduce risk, the Navy contracted for Engineering Development Models (EDMs) for 10 subsystems.
2005: The 10 EDMs completed testing and reached sufficient technical maturity to support a Critical Design Review (CDR). At that point, DD(X) was programmed to consist of 10 highly automated, reduced signature, reduced manning electric drive ships. DD(X)’s major new systems included Dual Band Radar (DBR), and Advanced Guns System (AGS) with a Long Range Land Attack Projectile (LRLAP).
November 23, 2005: The program achieved Milestone B. Major outstanding risks at Milestone B were related to the schedule and cost of software development and the integration and test of Mission Systems, as well as the costs of shipbuilder construction, DBR and AGS.
April 7, 2006: The DD(X) program was renamed DDG 1000 and detail design contracts for the dual lead ships were awarded to BIW and Northrop Grumman Shipbuilding (NGSB) (formerly Information Sciences Institute).
December 22, 2007: The ADM was issued authorizing the Navy to enter Production Phase for DDG 1000.
February 13, 2008: The DoD approved LRIP for seven ships, and lead ship construction contracts were awarded to BIW and NGSB.
July 31, 2008: The Navy provided testimony to the House Armed Services Committee Seapower and Expeditionary forces Subcommittee requesting Congressional support to truncate the DDG 1000 program and restart the DDG 51 program.
February 2010: The PB FY 2011 budget submission confirmed the reduction of the DDG 1000 Program to three ships as a result of the Future Surface Combatant Radar Hull Study in which the Navy concluded a modified DDG 51 with an Advanced Missile Defense Radar was the most cost-effective solution to fleet air and missile defense requirements.
February 1, 2010: The Secretary of the Navy notified Congress of a critical DDG 1000 program Nunn-McCurdy breach to the PAUC and APUC. This breach was due to the change in ship procurement quantity, not program performance.
June 1, 2010: The USD (AT&L) certified a restructured three-ship program that included removal of the Volume Search Radar from the ship design, changed the IOC from FY 2015 to FY 2016, and revised test and evaluation requirements
October 8, 2010: Milestone B prime was achieved for the restructured program following the Nunn-McCurdy certification. March 25, 2011: The APB for the restructured DDG 1000 Program was approved.
March 2013: Due to the FY 2013 sequestration impacts commencing during the execution year, the program experienced budget reductions of approximately $70.2M of Shipbuilding and Conversion, Navy (SCN) and $10.3M of RDT&E. The approximate $70.2M FY 2013 SCN sequester prevented the award of a $145M FY 2013 option to Raytheon for remaining MSE efforts for DDG 1000, 1001, and 1002, necessitating restructuring of the FY 2013, FY 2014, and FY 2015 options. A Below Threshold Reprograming for $9.999M of RDT&E was approved to continue LRLAP Guided Flight Tests and combat systems development.
August 2, 2013: The Navy awarded a contract modification for the design and construction of a steel deckhouse, hangar, and Aft Peripheral Vertical Launch System (PVLS) for DDG 1002 to BIW. The award occurred after the DDG 1002 sole source negotiation with HII for the procurement of the DDG 1002 composite deckhouse, composite hangar, and Aft PVLS did not reach an affordable solution and deliveries of these components for DDG 1002 were becoming time critical. The Navy concurrently pursued a steel deckhouse, hangar, and Aft PVLS using limited competition.
April 12, 2014: DDG 1000 was christened at BIW in Bath, ME.

## Table 9
December 31, 2015: Raytheon was awarded a contract for remaining DDG 1002 MSE.

## Table 10
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Schedule Breach is due to technical risk, shipyard production and test challenges, and shipyard workforce constraints. The complexity of activation of the ship's unique Engineering Control System and Integrated Power System has extended the time required for test and activation. Current estimate for First Ship Delivery is mid-2016.
Operational Evaluation, IOC and Milestone C are being assessed in view of Hull, Mechanical and Electrical (HM&E) delivery delays. An updated APB is in process.
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 11
Schedule
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | Nov 2005 | Nov 2005 | May 2006 | Nov 2005
Lead Ship Awards | Jan 2006 | Aug 2006 | Feb 2007 | Aug 2006
Milestone B Re-approval | N/A | Sep 2010 | Mar 2011 | Oct 2010
First Ship Delivery | Sep 2012 | Apr 2014 | Oct 2014 | Apr 20161
OPEVAL | Sep 2013 | Oct 2015 | Apr 2016 | Dec 20171
IOC | Jan 2014 | Apr 2016 | Oct 2016 | Dec 20191
Milestone C | Mar 2015 | Apr 2016 | Oct 2016 | Dec 20191
1 APB Breach
(Ch-1)
(Ch-2)
(Ch-3)
(Ch-4)
Change Explanations
(Ch-1) The current estimate for First Ship Delivery has changed from November 2015 to April 2016 due to delay in shipyard contract completion.
(Ch-2) The current estimate for OPEVAL has changed from August 2017 to December 2017 due to delay in shipyard contract completion.
(Ch-3) The current estimate for IOC has changed from September 2018 to December 2019 due to delay in shipyard contract completion.
(Ch-4) Milestone C is not applicable since all three ships of the class are under contract and thus IOC is used as the Milestone C date.
Notes
First Ship Delivery marks completion of DDG 1000 at point of pre-mission system activation. An initial Inspection and Survey Trial will be performed for HM&E delivery.

## Table 12
The Navy and the shipbuilder, General Dynamics Bath Iron Works (BIW) have evaluated yard-wide workload and scheduling for all construction efforts and contracts to address cost effective ship delivery approaches. The program continues to hold monthly joint BIW and Navy Flag-Level reviews, working closely to prepare for trials and delivery; and to ensure that lessons learned in the course of building and testing the first of class are being fully leveraged to improve performance on the follow ships.
Acronyms and Abbreviations
HM&E - Hull, Mechanical, and Electrical OPEVAL - Operational Evaluation

## Table 13
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Number of Advanced Gun Systems
2 | 2 | 2 | TBD | 2
Number of Advanced Vertical Launch Cells
128 | 128 | 80 | TBD | 80
Total Ship Advanced Gun System Magazine Capacity
1200 rounds (600 rounds per magazine) | 1200 rounds (600 rounds per magazine) | 600 rounds total ship magazine capacity | TBD | 600 rounds (300 rounds per magazine)
Number of ship's company personnel (helicopter detachment included)
125 | 125 | 175 | TBD | 175
Operational Availability (Ao) for mission critical systems:
Ao for 120-day wartime profile
0.95 | 0.95 | 0.9 | TBD | 0.95
Ao for 18 month extended forward deployment
0.95 | 0.95 | 0.9 | TBD | 0.95
Interoperability: All top-level IERs will be satisfied to the standards specified in the Threshold and Objective values.
Achieve 100% of top- level IERs. DD(X) joint tactical battle management and command and control computer programs shall conform to the SIAP System Engineer' s Integrated Architecture and Integrated Architecture Behavior Model now being developed. DD(X) will remain in compliance with CJCSI 6212.01 (Series), Inter- operability and Support- ability of IT and NSS, including future updates. | Achieve 100% of top- level IER. DD(X) joint tactical battle management and command and control computer programs shall conform to the SIAP System Engineer's Integrated Architecture and Integrated Architecture Behavior Model now being developed. DD(X) will remain in compliance with CJCSI 6212.01 (Series), Inter- operability and Support- ability of Information Technology and National Security Systems (IT and NSS), including future updates. | Achieve 100% top-level IER designated as critical. DD(X) joint tactical battle mangage- ment and command and control computer programs shall conform to the SIAP System Engineer's Integrated Architecture and Integrated Archi-techture Behavior Model for Track Management now being developed. DD(X) will remain in compliance with CJCSI 6212.0 (Series), Inter-operability and Support-ability of Information Technology and National Security Systems (IT and NSS), Including future updates. | TBD | Achieve 100% of interfaces; services; policy-enforcement controls; and data correctness, availability and processing requirements designated as enterprise-level or critical in the Joint integrated architecture. This includes the ORD threshold requirements for meeting the IERs which are listed in DDG 1000 ORD Rev 15 (Table B) and the DDG 1000 TEMP Rev D (Table D-3).

## Table 14
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
DDX ORD Change 1 dated January 23, 2006
Change Explanations
None
Acronyms and Abbreviations
CJCSI - Chairman of the Joint Chiefs of Staff Instruction IER - Information Exchange Requirement
IT - Information Technology NSS - National Security System Rev - Revision
SIAP - Single Integrated Air Picture TEMP - Test and Evaluation Master Plan

## Table 15
Track to Budget
RDT&E
Appn BA PE
Navy 1319 05 0204202N
Project Name
2464 DDG 1000 System Design, Development and Integration
4009 Advanced Gun System on DDG 1000 (Sunk) Navy 1319 04 0603513N
Project Name
2465 DC Survivability (Shared) (Sunk)
2467 Advanced Gun System (Shared) (Sunk)
2468 Undersea Warfare (Shared) (Sunk)
2469 Open System Architecture (Shared) (Sunk)
2470 Integrated Topside Design (Shared) (Sunk)
2471 Integrated Power System (Shared) (Sunk)
4019 Radar Upgrades (Shared) (Sunk) Navy 1319 05 0604300N
Project Name
2463 DD(X) Construction (Shared) (Sunk) 2464 DD(X) Sys Design, Dev & Integration (Shared) (Sunk) 2465 DC Survivability (Shared) (Sunk)
2466 MFR Development (Shared) (Sunk)
2735 Volume Search Radar (Shared) (Sunk)
4009 Advanced Gun System (Shared) (Sunk) 4010 Integrated Power System on DD (X) (Shared) (Sunk)
Navy 1319 05 0604366N
Project Name
0439 Standard Missile Improvement: DDG 1000 (Shared) (Sunk) Navy 1319 05 0604755N
Project Name
2735 Volume Search Radar (Sunk)
Procurement
Appn |  |  | BA | PE
Navy 1611 02 0204222N
Line Item | Name
211900 DDG 1000 FY08-FY09 (Sunk)
Navy 1611 02 0702898N
|  | Line Item |  | Name
|  | 211900 |  | Management Headquarters
Navy |  | 1611 | 2 | 0204202N

## Table 16
Line Item | Name
211900 DDG 1000 Construction FY10 and follow
Navy 1611 02 0204228N
Line Item | Name
211900 DDG 1000 FY05-FY07 (Sunk)
Navy 1611 05 0204222N
Line Item | Name
511000 Outfitting/Post Delivery (Shared)
530000 Destroyers - Missile (Sunk)
Navy 1810 01 0204202N
Line Item | Name
094700 DDG 1000 Class Support Equipment

## Table 17
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2005 $M | [6 empty] | BY 2005 $M |  | TY $M
| SAR Baseline Development Estimate |  |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E |  | 8313.2 |  |  | 8994 | 9893.4 |  |  | 8844.4 |  | 8483 |  |  | 9325.5 |  | 9175.8
Procurement |  | 23234.7 |  |  | 10195.3 | 11214.8 |  |  | 10287.3 |  | 27813.3 |  |  | 12497.8 |  | 13225.2
Flyaway |  | -- |  |  | -- | -- |  |  | 10287.3 |  | -- |  |  | -- |  | 13225.2
Recurring |  | -- |  |  | -- | -- |  |  | 9273.9 |  | -- |  |  | -- |  | 12065.2
Non Recurring |  | -- |  |  | -- | -- |  |  | 1013.4 |  | -- |  |  | -- |  | 1160
Support |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Other Support |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Initial Spares |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
MILCON |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 31547.9 |  |  | 19189.3 | N/A |  |  | 19131.7 |  | 36296.3 |  |  | 21823.3 |  | 22401
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The Independent Cost Estimate (ICE) to support DDG 1000 revised Milestone B decision, like all life-cycle cost estimates previously performed by the CAPE, is built upon a product-oriented work breakdown structure, based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for MDAPs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.
Total Quantity
Quantity |  |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  |  | 10 |  |  |  | 3 |  |  |  |  | 3
Total |  |  | 10 |  |  |  | 3 |  |  |  |  | 3

## Table 18
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 8972.4 | 103.2 |  | 45.6 |  | 19.3 | 15.6 |  | 19.7 |  | 0 |  | 0 |  | 9175.8
Procurement | 11916.7 | 479 |  | 343.2 |  | 195.3 | 110.6 |  | 77.7 |  | 41.9 |  | 60.8 |  | 13225.2
MILCON | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 20889.1 | 582.2 |  | 388.8 |  | 214.6 | 126.2 |  | 97.4 |  | 41.9 |  | 60.8 |  | 22401
PB 2016 Total | 20815.1 | 623.7 |  | 272.5 |  | 70 | 37.5 |  | 41.7 |  | 0 |  | 143.6 |  | 22004.1
Delta | 74 | -41.5 |  | 116.3 |  | 144.6 | 88.7 |  | 55.7 |  | 41.9 |  | -82.8 |  | 396.9
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0
Production | 0 |  | 3 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 3
PB 2017 Total | 0 |  | 3 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 3
PB 2016 Total | 0 |  | 3 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 3
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0

## Table 19
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 53.5
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 215.1
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 281.2
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 532.4
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 490.4
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 895.4
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1002.2
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1120.2
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1040.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 755.8
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 516.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 431.2
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 503.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 347.9
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 249.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 120.8
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 189.6
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 197
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 103.2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 45.6
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.3
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.6
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.7
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9175.8

## Table 20
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2005 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.3
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.4
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.1
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 234.8
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 302.6
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 565.1
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 515.3
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 927.3
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1009.8
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1099.7
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 990.7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 702.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 471.4
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 388.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 447.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 301.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 213.1
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 102
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 157.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 161.9
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83.5
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36.2
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.9
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.8
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8844.4

## Table 21
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | -- |  | -- |  | 304 |  | 304 |  | -- |  | 304
2006 |  | -- | -- |  | -- |  | 706.2 |  | 706.2 |  | -- |  | 706.2
2007 |  | 2 | 2587.6 |  | -- |  | -- |  | 2587.6 |  | -- |  | 2587.6
2008 |  | -- | 3009.9 |  | -- |  | 149.8 |  | 3159.7 |  | -- |  | 3159.7
2009 |  | 1 | 1504.3 |  | -- |  | -- |  | 1504.3 |  | -- |  | 1504.3
2010 |  | -- | 1378.5 |  | -- |  | -- |  | 1378.5 |  | -- |  | 1378.5
2011 |  | -- | 247.1 |  | -- |  | -- |  | 247.1 |  | -- |  | 247.1
2012 |  | -- | 512.6 |  | -- |  | -- |  | 512.6 |  | -- |  | 512.6
2013 |  | -- | 682.4 |  | -- |  | -- |  | 682.4 |  | -- |  | 682.4
2014 |  | -- | 312.5 |  | -- |  | -- |  | 312.5 |  | -- |  | 312.5
2015 |  | -- | 521.8 |  | -- |  | -- |  | 521.8 |  | -- |  | 521.8
2016 |  | -- | 479 |  | -- |  | -- |  | 479 |  | -- |  | 479
2017 |  | -- | 309.8 |  | -- |  | -- |  | 309.8 |  | -- |  | 309.8
2018 |  | -- | 162 |  | -- |  | -- |  | 162 |  | -- |  | 162
2019 |  | -- | 108.4 |  | -- |  | -- |  | 108.4 |  | -- |  | 108.4
2020 |  | -- | 75.4 |  | -- |  | -- |  | 75.4 |  | -- |  | 75.4
2021 |  | -- | 39.6 |  | -- |  | -- |  | 39.6 |  | -- |  | 39.6
2022 |  | -- | 60.8 |  | -- |  | -- |  | 60.8 |  | -- |  | 60.8
Subtotal |  | 3 | 11991.7 |  | -- |  | 1160 |  | 13151.7 |  | -- |  | 13151.7

## Table 22
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | BY 2005 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | -- |  | -- |  | 275.1 |  | 275.1 |  | -- |  | 275.1
2006 |  | -- | -- |  | -- |  | 617.3 |  | 617.3 |  | -- |  | 617.3
2007 |  | 2 | 2162.4 |  | -- |  | -- |  | 2162.4 |  | -- |  | 2162.4
2008 |  | -- | 2432.5 |  | -- |  | 121 |  | 2553.5 |  | -- |  | 2553.5
2009 |  | 1 | 1179.4 |  | -- |  | -- |  | 1179.4 |  | -- |  | 1179.4
2010 |  | -- | 1044.2 |  | -- |  | -- |  | 1044.2 |  | -- |  | 1044.2
2011 |  | -- | 181.2 |  | -- |  | -- |  | 181.2 |  | -- |  | 181.2
2012 |  | -- | 367.7 |  | -- |  | -- |  | 367.7 |  | -- |  | 367.7
2013 |  | -- | 479.9 |  | -- |  | -- |  | 479.9 |  | -- |  | 479.9
2014 |  | -- | 215.7 |  | -- |  | -- |  | 215.7 |  | -- |  | 215.7
2015 |  | -- | 354 |  | -- |  | -- |  | 354 |  | -- |  | 354
2016 |  | -- | 319.1 |  | -- |  | -- |  | 319.1 |  | -- |  | 319.1
2017 |  | -- | 202.5 |  | -- |  | -- |  | 202.5 |  | -- |  | 202.5
2018 |  | -- | 103.8 |  | -- |  | -- |  | 103.8 |  | -- |  | 103.8
2019 |  | -- | 68.1 |  | -- |  | -- |  | 68.1 |  | -- |  | 68.1
2020 |  | -- | 46.4 |  | -- |  | -- |  | 46.4 |  | -- |  | 46.4
2021 |  | -- | 23.9 |  | -- |  | -- |  | 23.9 |  | -- |  | 23.9
2022 |  | -- | 36 |  | -- |  | -- |  | 36 |  | -- |  | 36
Subtotal |  | 3 | 9216.8 |  | -- |  | 1013.4 |  | 10230.2 |  | -- |  | 10230.2

## Table 23
Cost Quantity Information 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2005 $M
2005 | -- | --
2006 | -- | --
2007 | 2 | 6474.9
2008 | -- | --
2009 | 1 | 2741.9
2010 | -- | --
2011 | -- | --
2012 | -- | --
2013 | -- | --
2014 | -- | --
2015 | -- | --
2016 | -- | --
2017 | -- | --
2018 | -- | --
2019 | -- | --
2020 | -- | --
2021 | -- | --
2022 | -- | --
Subtotal | 3 | 9216.8

## Table 24
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2017 |  | -- | 33.4 |  | -- |  | -- |  | 33.4 |  | -- |  | 33.4
2018 |  | -- | 33.3 |  | -- |  | -- |  | 33.3 |  | -- |  | 33.3
2019 |  | -- | 2.2 |  | -- |  | -- |  | 2.2 |  | -- |  | 2.2
2020 |  | -- | 2.3 |  | -- |  | -- |  | 2.3 |  | -- |  | 2.3
2021 |  | -- | 2.3 |  | -- |  | -- |  | 2.3 |  | -- |  | 2.3
Subtotal |  | -- | 73.5 |  | -- |  | -- |  | 73.5 |  | -- |  | 73.5

## Table 25
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | BY 2005 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2017 |  | -- | 26.3 |  | -- |  | -- |  | 26.3 |  | -- |  | 26.3
2018 |  | -- | 25.7 |  | -- |  | -- |  | 25.7 |  | -- |  | 25.7
2019 |  | -- | 1.7 |  | -- |  | -- |  | 1.7 |  | -- |  | 1.7
2020 |  | -- | 1.7 |  | -- |  | -- |  | 1.7 |  | -- |  | 1.7
2021 |  | -- | 1.7 |  | -- |  | -- |  | 1.7 |  | -- |  | 1.7
Subtotal |  | -- | 57.1 |  | -- |  | -- |  | 57.1 |  | -- |  | 57.1

## Table 26
Cost Quantity Information 1810 ¦ Procurement ¦ Other Procurement, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2005 $M
2007 | -- | 29.5
2008 | -- | --
2009 | -- | 27.6
2010 | -- | --
2011 | -- | --
2012 | -- | --
2013 | -- | --
2014 | -- | --
2015 | -- | --
2016 | -- | --
2017 | -- | --
2018 | -- | --
2019 | -- | --
2020 | -- | --
2021 | -- | --
Subtotal | -- | 57.1

## Table 27
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2005-11-22 | 2010-10-08
Approved Quantity | 8 | 3
Reference | Milestone B ADM | Milestone B ADM
Start Year | 2007 | 2007
End Year | 2014 | 2009
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the revised Milestone B ADM of October 8, 2010 reducing the LRIP quantity to three ships, which represents the total quantity remaining on the program.

## Table 28
Foreign Military Sales
None
Nuclear Costs
None

## Table 29
Unit Cost
Unit Cost Report
Item |  | BY 2005 $M | BY 2005 $M |  | % Change
|  | Current UCR Baseline (Mar 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 19189.3 |  |  | 19131.7
Quantity | 3 |  |  | 3
Unit Cost | 6396.433 |  |  | 6377.233 |  | -0.3
Average Procurement Unit Cost
Cost | 10195.3 |  |  | 10287.3
Quantity | 3 |  |  | 3
Unit Cost | 3398.433 |  |  | 3429.1 |  | 0.9
Item |  | BY 2005 $M | BY 2005 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Mar 2011 APB)
Program Acquisition Unit Cost
Cost | 19189.3 |  |  | 19131.7
Quantity | 3 |  |  | 3
Unit Cost | 6396.433 |  |  | 6377.233 |  | -0.3
Average Procurement Unit Cost
Cost | 10195.3 |  |  | 10287.3
Quantity | 3 |  |  | 3
Unit Cost | 3398.433 |  |  | 3429.1 |  | 0.9

## Table 30
Unit Cost History
Item |  |  | Date |  |  |  |  | BY 2005 $M | [6 empty] | TY $M
[8 empty] | PAUC |  |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  | Nov 2005 | [5 empty] | 3154.79 |  |  |  | 2323.47 |  |  |  | 3629.62 |  |  | 2781.32
APB as of January 2006 |  | Nov 2005 | [5 empty] | 3154.79 |  |  |  | 2323.47 |  |  |  | 3629.62 |  |  | 2781.32
Revised Original APB |  | Mar 2011 | [5 empty] | 6396.433 |  |  |  | 3398.433 |  |  |  | 7274.433 |  |  | 4165.933
Prior APB |  | Nov 2005 | [5 empty] | 3154.79 |  |  |  | 2323.47 |  |  |  | 3629.62 |  |  | 2781.32
Current APB |  | Mar 2011 | [5 empty] | 6396.433 |  |  |  | 3398.433 |  |  |  | 7274.433 |  |  | 4165.933
Prior Annual SAR |  | Dec 2014 | [5 empty] | 6289.367 |  |  |  | 3357.767 |  |  |  | 7334.7 |  |  | 4296.6
Current Estimate |  | Dec 2015 | [5 empty] | 6377.233 |  |  |  | 3429.1 |  |  |  | 7467 |  |  | 4408.4
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [15 empty] | PAUC Current Estimate
| Econ | Qty |  |  | Sch |  | Eng |  | Est |  | Oth |  | Spt | Total
3629.630 609.833 2104.837 38.100 22.067 1062.533 0.000 0.000 3837.370 7467.000
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [15 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng |  |  |  | Est | Oth |  | Spt | Total
2781.330 606.967 125.469 37.167 -126.500 983.967 0.000 0.000 1627.070 4408.400

## Table 31
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone I | N/A | N/A | N/A | N/A
Milestone B | Nov 2005 | Nov 2005 | N/A | Nov 2005
Milestone C | Mar 2015 | Mar 2015 | N/A | Dec 2019
IOC | Jan 2014 | Jan 2014 | N/A | Dec 2019
Total Cost (TY $M) | 36296.2 | 36296.3 | N/A | 22401
Total Quantity | 10 | 10 | N/A | 3
PAUC | 3629.62 | 3629.63 | N/A | 7467

## Table 32
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 8483 | 27813.3 | -- | 36296.3
Previous Changes
Economic | 11.4 | 1813.3 | -- | 1824.7
Quantity | -- | -19092.9 | -- | -19092.9
Schedule | 2.8 | 57.7 | -- | 60.5
Engineering | 445.7 | -379.5 | -- | 66.2
Estimating | 171.4 | 2677.9 | -- | 2849.3
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | 631.3 | -14923.5 | -- | -14292.2
Current Changes
Economic | -2.8 | 7.6 | -- | 4.8
Quantity | -- | -- | -- | --
Schedule | -- | 53.8 | -- | 53.8
Engineering | -- | -- | -- | --
Estimating | 64.3 | 274 | -- | 338.3
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | 61.5 | 335.4 | -- | 396.9
Total Changes | 692.8 | -14588.1 | -- | -13895.3
CE - Cost Variance | 9175.8 | 13225.2 | -- | 22401
CE - Cost & Funding | 9175.8 | 13225.2 | -- | 22401

## Table 33
Summary BY 2005 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 8313.2 | 23234.7 | -- | 31547.9
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -14646 | -- | -14646
Schedule | 1.7 | 63.8 | -- | 65.5
Engineering | 385.3 | -369.4 | -- | 15.9
Estimating | 94.6 | 1790.2 | -- | 1884.8
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | 481.6 | -13161.4 | -- | -12679.8
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | 37 | -- | 37
Engineering | -- | -- | -- | --
Estimating | 49.6 | 177 | -- | 226.6
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | 49.6 | 214 | -- | 263.6
Total Changes | 531.2 | -12947.4 | -- | -12416.2
CE - Cost Variance | 8844.4 | 10287.3 | -- | 19131.7
CE - Cost & Funding | 8844.4 | 10287.3 | -- | 19131.7
Previous Estimate: December 2014

## Table 34
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -2.8
Revised estimated for Navy-wide funding adjustments. (Estimating) -4.5 -5.5
Revised estimate due to decision to fund DDG 1000 Class Component and Full Ship Shock Trials in the RDT&E Account. (Estimating)
Revised estimate to fund Test and Evaluation effort in accordance with the Test and Evaluation Master Plan. (Estimating)
+31.6 +41.6
+21.8 +27.5
Revised estimate due to Bipartisan Budget Act reductions. (Estimating) Adjustment for current and prior escalation. (Estimating) | -1.5 +2.2 |  |  | -1.9 +2.6
RDT&E Subtotal | 49.6 |  |  | 61.5
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A +7.6
Revised estimate due to cost increases associated with delivery delays. (Schedule) +37.0 +53.8
Revised estimate to reflect shipbuilding completion; and on site support for HM&E test and activation activities. (Estimating)
+234.5 +364.6
Adjustment for current and prior escalation. (Estimating) -5.0 -7.2
Revised estimate due to HM&E Activation. (Estimating) +6.8 +10.0
Revised estimate due budget adjustments (OPN). (Estimating) +0.2 +0.3
Revised estimate due to reduction in Outfitting/Post Delivery; Congressional reductions; FY 2022 Phasing outside the FYDP. (Estimating)
-59.5 -93.7
Procurement Subtotal +214.0 +335.4

## Table 35
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: Phase IV AGS Equipment (DDG 1002)
Contractor: BAE Systems
Contractor Location: 4800 E. River Rd
Minneapolis, MN 55421
Contract Number: N00024-12-C-5311
Contract Type: Fixed Price Incentive(Firm Target) (FPIF), Cost Plus Fixed Fee (CPFF)
Award Date: October 26, 2011
Definitization Date: November 19, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
73.0 N/A 2 190.4 201.6 2 172.1 173.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to initial target was the not-to-exceed price for hardware being procured under a Undefinitized Contract Action (UCA). Current contract price represents the target for the full scope of the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/1/2016) -2.7 -1.4
Previous Cumulative Variances +1.9 -6.3
Net Change -4.6 +4.9
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to subcontractor hardware cost overruns, greater than anticipated engineering support for magazine testing, and costs incurred from Servo Amplifier Unit repair & rework.
The favorable net change in the schedule variance is due to early completion of magazine assembly, early receipt of vendor materials for the fixed shields and upper & lower guns.
General Contract Variance Explanation
The unfavorable cumulative cost variance is minor and schedule variance is recoverable; contractor forecasts on-time contract completion. There is not an impact to in yard need date delivery.

## Table 36
Notes
The Navy awarded the Advanced Gun System (AGS) for DDG 1002 to British Aerospace Engineering (BAE) on October 26, 2011 as an UCA. The UCA was definitized November 19, 2012. The definitization was delayed by changes in contract terms and conditions to better control cost and performance and a change in government contracts negotiator personnel.
BAE established the Performance Measurement Baseline for the DDG 1002 effort, and conducted an Integrated Baseline Review for that effort in April 2013.The contract includes options for FY 2012, FY 2013, and FY 2014 to complete the two AGS for the DDG 1002 and the supporting systems.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 37
Contract Identification
Appropriation: Procurement
Contract Name: Phase IV BIW Construciton (DDG 1002)
Contractor: General Dynamics
Contractor Location: 700 Washington Street
Bath, ME 04530
Contract Number: N00024-11-C-2306/881
Contract Type: Fixed Price Incentive (Successive Targets) (FPIS), Firm Fixed Price (FFP)
Award Date: September 15, 2011
Definitization Date: September 15, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
665.1 N/A 1 673.9 N/A 1 806.6 771.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to this being the first time this contract is reported as a unique effort. Previously, contracts N00024-11-C-2306/880, 881, and 882 were reported as a single contract effort.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/1/2016) -90.2 -15.2
Previous Cumulative Variances -- --
Net Change -90.2 -15.2
Cost and Schedule Variance Explanations
The unfavorable cumulative cost variance is due to overall effects of shipyard production and test challenges. The program is aggressively working to minimize the overall exposure and is addressing the cost variance through Cost Reduction Candidates (CRCs). Through month ending December 2015, the program has processed modifications for $18.6M of scope reductions for the contract. An additional $3.0M of modifications for scope reductions have been proposed and the program will continue to identify CRCs.
The unfavorable cumulative schedule variance is due to yard-wide workforce constraints and scheduling impacts.
The Navy and the shipbuilder, General Dynamics Bath Iron Works (BIW) have evaluated yard-wide workload and scheduling for all construction efforts and contracts to address cost effective ship delivery approaches. The program continues to hold monthly joint BIW and Navy Flag-Level reviews, working closely to prepare for trials and delivery; and to ensure that lessons learned in the course of building and testing the first of class are being fully leveraged to improve performance on the follow ships.
Notes
This is the first time this contract is being reported.

## Table 38
Contract Identification
Appropriation: Procurement
Contract Name: Phase IV BIW Construction (DDG 1001)
Contractor: General Dynamics
Contractor Location: 700 Washington Street
Bath, ME 04530
Contract Number: N00024-11-C-2306/880
Contract Type: Fixed Price Incentive (Successive Targets) (FPIS), Firm Fixed Price (FFP)
Award Date: September 15, 2011
Definitization Date: September 15, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
663.4 N/A 1 762.5 N/A 1 915.7 939.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to this being the first time this contract is reported as a unique effort. Previously, contracts N00024-11-C-2306/880, 881, and 882 were reported as a single contract effort.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/1/2016) -148.0 -66.8
Previous Cumulative Variances -- --
Net Change -148.0 -66.8
Cost and Schedule Variance Explanations
The unfavorable cumulative cost variance is due to overall effects of shipyard production and test challenges in addition to variances related to redetermination areas, including material and engineering support. The program is aggressively working to minimize the overall exposure and is addressing the cost variance through Cost Reduction Candidates (CRCs). Through month ending December 2015, the program has processed modifications for $14.2M of scope reductions for the contract.
An additional $2.4M of modifications for scope reductions have been proposed for the program and will continue to identify CRCs.
Bath Iron Works (BIW) and the Navy have evaluated yard-wide workload and scheduling for all construction efforts and contracts to address cost effective ship delivery approaches. The Program Office will continue reviewing that analysis, including impacts when DDG 1000 starts Post Delivery Availability and Mission Systems Activation, and subsequently adjusting the related Navy Estimated Price at Completion, if necessary.
The unfavorable cumulative schedule variance is due to yard-wide workforce constraints and scheduling impacts being addressed in monthly joint BIW and Navy Flag-Level reviews.
Notes
This is the first time this contract is being reported.

## Table 39
Contract Identification
Appropriation: Procurement
Contract Name: Phase IV BIW Construction (DDG 1002 Steel Superstructure (Deckhouse))
Contractor: General Dynamics
Contractor Location: 700 Washington Street
Bath, ME 04530
Contract Number: N00024-11-C-2306/882
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: August 02, 2013
Definitization Date: August 02, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
212.0 N/A 1 215.9 237.5 1 183.9 212.1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to this being the first time this contract is reported as a unique effort. Previously, contracts N00024-11-C-2306/880, 881, and 882 were reported as a single contract effort.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/1/2016) +5.4 -29.1
Previous Cumulative Variances -- --
Net Change +5.4 -29.1
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to Support and Manufacturing hours at $2.9M and $2.7M respectively with a negative overall rate offset ($0.8M). The at-complete variance is projected to be positive at $0.6M. This is primarily attributable to hours at positive $2.8M with a negative rate offset of ($2.2M), or negative ($1.85) per hour. The Support burden center at positive $2.9M over the life of the project is responsible for the total positive variance due to hours, while the Manufacturing burden center at negative ($2M) over the life of the project is responsible for the total rate variance at completion.
The unfavorable cumulative schedule variance is due to yard-wide workforce constraints and scheduling impacts.
General Contract Variance Explanation
The unfavorable schedule variance is due to overall effects of shipyard production and test challenges.
Bath Iron Works (BIW) and the Navy have evaluated yard-wide workload and scheduling for all construction efforts and contracts to address cost effective ship delivery approaches. The Program Office will continue reviewing that analysis, including impacts when the DDG 1000 starts Post Delivery Availability and Mission Systems Activation, and subsequently adjusting the related Navy Estimated Price at Completion, if necessary.

## Table 40
Notes
This is the first time this contract is being reported.

## Table 41
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 0 | 0 | 3 | 0%
Total Program Quantity Delivered | 0 | 0 | 3 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
22401
19696
87.92%
28
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
22
78.57%
21471.3
95.85%
The above data is current as of February 09, 2016.

## Table 42
Operating and Support Cost
Cost Estimate Details
Date of Estimate: June 02, 2015
Source of Estimate: Service ICE
Quantity to Sustain: 3
Unit of Measure: Ship
Service Life per Unit: 35.00 Years
Fiscal Years in Service: FY 2017 - FY 2055
O&S cost estimates are based on the 2015 Gate 6 Review of DDG 1000 Class. Costs are shown in BY 2005 dollars. The estimate is based on an average unit cost of three ships with an average 35 year service life. The estimate includes separately priced mission system equipment sustainment cost. Mid-life modernization is not included.
The O&S costs are provided in revised cost elements based on the CAPE 2014 O&S Cost-Estimating Guide.
Sustainment Strategy
DDG 1000 maintenance is apportioned to either the ship or a land-based facility. There are two levels of maintenance planned for the DDG 1000 ship class; "on-ship" - accomplished by ship's force and "off-ship" - accomplished through maintenance support contracts in addition to legacy Navy maintenance infrastructure. Maintenance support contracts similar to legacy Multi Ship/Multi Option contracting strategy for repairs and overhauls are planned. The DDG 1000 program provides Integrated Logistics Support oversight and guidance to Participating Acquisition Resource Managers that develop various sustainment approaches for combat systems and Communications, Command, Control, Computers, and Intelligence.
Antecedent Information
The most analogous system to DDG 1000 is DDG 51. The DDG 1000 and DDG 51 ships differ in various aspects that make comparison difficult. Considerations include new technologies, size difference, and an all electric ship design.
The 2014 unit cost of the DDG 51 (Antecedent) is derived using the Naval Visibility and Management of Operating and Support Costs database and is shown in BY 2005 $M. DDG 51 estimates are based on a service life of 35 years for the 28 Flight I and Flight II ships and 40 years for the 54 Flight IIA and Flight III ships. The DDG 51 reports in BY 1987 $M.

## Table 43
Annual O&S Costs BY2005 $M
Cost Element |  | DDG 1000 Average Annual Cost Per Ship | [5 empty] | DDG 51 (Antecedent) Average Annual Cost Per Ship
Unit-Level Manpower |  | 12.776 | [5 empty] | 12.64
Unit Operations |  | 8.603 | [5 empty] | 6.96
Maintenance |  | 22.197 | [5 empty] | 3.44
Sustaining Support |  | 8.131 | [5 empty] | 0.92
Continuing System Improvements |  | 15.368 | [5 empty] | 2.87
Indirect Support |  | 6.623 | [5 empty] | 5.73
Other |  | 0 | [5 empty] | 0
Total |  | 73.698 | [5 empty] | 32.56
Item | Total O&S Cost $M
| DDG 1000 | [7 empty] | DDG 51 (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 7744.4 |  |  | 8518.8 |  |  | 7738.3 |  | 93259.6
Then Year | 15245.3 |  |  | N/A |  |  | 14946 |  | N/A
Disposal Cost is included in the Operating and Support Cost of the current APB objective and threshold for this program.
Equation to Translate Annual Cost to Total Cost
The equation that links the unitized cost to the total cost for DDG 1000 is Total Cost = average annual cost per ship * number of ships * service life = $73.7M per Ship x 3 Ships x 35 year (service life) = $7,738.3M (BY 2005)
O&S Cost Variance
Category |  |  | BY 2005 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
5740.3
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 1998.0 Increased costs in personnel, fuel, and Mission System Equipment Maintenance
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 1998.0
Current Estimate 7738.3
Disposal Estimate Details

## Table 44
Date of Estimate: June 02, 2015
Source of Estimate: Service ICE
Disposal/Demilitarization Total Cost (BY 2005 $M): Total costs for disposal of all Ship are 53.7
O&S Baseline data is from MS B recertification Program Life Cycle Cost Estimates (PLCCE).