## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-364
E-2D Advanced Hawkeye Aircraft (E-2D AHE)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 13
Cost and Funding 14
Low Rate Initial Production 24
Foreign Military Sales 25
Nuclear Costs 25
Unit Cost 26
Cost Variance 29
Contracts 33
Deliveries and Expenditures 39
Operating and Support Cost 40

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
E-2D Advanced Hawkeye Aircraft (E-2D AHE)
DoD Component
Navy
Responsible Office
CAPT John Lemmon
Program Executive Officer Tactical Aircraft Programs Bldg. 2272, Suite 455, Naval Air Systems Command 47123 Buse Road, Unit IPT
Patuxent River, MD 20670-1547
john.s.lemmon@navy.mil
Phone: | 301-757-7363
Fax: | 301-757-7238
DSN Phone: | 757-7363
DSN Fax: | 757-7238
Date Assigned: | May 29, 2012
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated July 31, 2009
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated March 25, 2015

## Table 6
Mission and Description
The E-2D Advanced Hawkeye Aircraft (E-2D AHE) is a carrier based, all weather, multi-mission aircraft. The E-2D AHE mission is to provide premier airborne Battle Management Command and Control and Surveillance as part of the Naval and Joint Integrated Air and Missile Defense architecture including the Naval Integrated Fire Control-Counter Air capability. The centerpiece of the E-2D AHE is the APY-9 radar system. This radar system is designed specifically to provide significantly enhanced surveillance detection and tracking capability against advanced threat aircraft and cruise missile systems in the overland, littoral, and open ocean environments. Maritime surveillance is also maintained in the open ocean scenarios. The E-2D AHE provides early warning of hostile threats and provides the force with the right data to prosecute any engagement. Key capabilities along with the radar include the Identification Friend or Foe system and Electronic Support Measures for surveillance and combat identification, advanced mission processing capability to integrate all on-board sensor data and off- board information into a coherent tactical picture, and communications, data link, and sensor netting systems to share information across the battlespace. These capabilities allow the E-2D AHE to provide a significant contribution to execution of other mission areas such as Strike, Combat Search and Rescue, and Homeland Defense. As a part of the E-2D AHE radar modernization effort, the Navy also invested in integrating a full glass cockpit and full Communication Navigation Surveillance/Air Traffic Management capability. The glass cockpit will also provide the capability for the pilot or co-pilot to perform tactical mission functions.

## Table 7
Executive Summary
All E-2D AHE LRIP and the first two FRP aircraft have been delivered. The total Program of Record is 75 aircraft. The first Fleet Squadron Deployment occurred during March 11, 2015 through November 23, 2015 and the aircraft incorporated the Delta System/Software Configuration Build 1 (DSSC-1) which is the IOC hardware/software configuration. DSSC-1 Follow- On Operational Test and Evaluation was completed on May 29, 2015. DSSC-2, which incorporates prior test deficiency corrections and adds Dual Transmission Satellite Communication capability, commenced Developmental Test and Evaluation on May 28, 2015. The Material Support Date was achieved on October 1, 2015. The Japan Ministry of Defense signed a Letter of Offer and Acceptance (LOA) for one E-2D AHE on August 11, 2015. On November 12, 2015, the Japan E- 2D AHE aircraft was placed on contract as a modification to the E-2D AHE Multi-Year Procurement contract utilizing a variation in quantity clause. The Japan Non Recurring Engineering contract was awarded on December 31, 2015. Japan is expected to procure an additional E-2D AHE via yearly LOAs at a rate of one per year for the next three years.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B | May 2003 | Jun 2003 | Jun 2003 | Jun 2003
Critical Design Review | Nov 2005 | Oct 2005 | Oct 2005 | Oct 2005
First Flight | Aug 2007 | Aug 2007 | Aug 2007 | Aug 2007
Milestone C | Mar 2009 | May 2009 | May 2009 | May 2009
Full Rate Production | Dec 2012 | Mar 2013 | Mar 2013 | Mar 2013
IOC | Oct 2014 | Oct 2014 | Apr 2015 | Oct 2014
Change Explanations

## Table 10
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Radar Ao
=>0.98 | =>0.98 | =>0.85 | 0.89 | >=0.89
Survivability - Safe Egress In Crash
The E-2D AHE shall retain all equipment mounted inside the fuselage in its installed position in inhabited spaces for crash landing inertia load factors applied at the equipment center of gravity of 20g forward, parallel and downward in the cockpit along a single axis. The E- 2D AHE escape hatches and doors shall allow egress subsequent to a 40g crash inertial load. | The E-2D AHE shall retain all equipment mounted inside the fuselage in its installed position in inhabited spaces for crash landing inertia load factors applied at the equipment center of gravity of 20g forward, parallel and downward in the cockpit along a single axis. The E- 2D AHE escape hatches and doors shall allow egress subsequent to a 40g crash inertial load. | The E-2D AHE shall retain all equipment mounted inside the fuselage in its installed position in inhabited spaces for crash landing inertia load factors applied at the equipment center of gravity of 20g forward, parallel and downward in the cockpit along a single axis. The E- 2D AHE escape hatches and doors shall allow egress subsequent to a 40g crash inertial load. | The E-2D AHE shall retain all equipment mounted inside the fuselage in its installed position in inhabited spaces for crash landing inertia load factors applied at the equipment center of gravity of 20g forward, parallel and downward in the cockpit along a single axis. The E-2D AHE escape hatches and doors shall allow egress subsequent to a 40g crash inertial load. | The E-2D AHE shall retain all equipment mounted inside the fuselage in its installed position in inhabited spaces for crash landing inertia load factors applied at the equipment center of gravity of 20g forward, parallel and downward in the cockpit along a single axis. The E-2D AHE escape hatches and doors shall allow egress subsequent to a 40g crash inertial load.
Manpower (Full Operational Capability - FY 2020)
Aircrew Os =< 323 Maintenance Os/Es =< 34 / 1303 Support Os/Es =< 12 / 683 Training Os/Es =< 76 / 60 | Aircrew Os =< 323 Maintenance Os/Es =< 34 / 1303 Support Os/Es =< 12 / 683 Training Os/Es =< 76 / 60 | Aircrew Os =< 323 Maintenance Os/Es =< 34 / 1303 Support Os/Es =< 12 / 683 Training Os/Es =< 76 / 60 | Aircrew Os =< 323 Maintenance Os/Es =< 34 / 1303 Support Os/Es =< 12 / 683 Training Os/Es =< 76 / 60 | Aircrew Os =< 323 Maintenance Os/Es =< 34 / 1303 Support Os/Es =< 12 / 683 Training Os/Es =< 76 / 60
Unrefueled Time On Station
=>2.0 hours at a station distance of 200nm | =>2.0 hours at a station distance of 200nm | =>2.0 hours at a station distance of 200nm | 2.10 hours at a station distance of 200nm | 2.10 hours at a station distance of 200nm
Flat Turn Service Ceiling
=>25,000 feet above MSL at mission profile | =>25,000 feet above MSL at mission profile | =>25,000 feet above MSL at mission profile | 25,600 feet above MSL at mission profile | 25,600 feet above MSL at mission profile
Level Flight Airspeed
=>300 knots true airspeed below | =>300 knots true airspeed below | =>300 knots true airspeed below | 303.5 knots true airspeed below 18,000 | 303.5 knots true airspeed below
(Ch-1)

## Table 11
18,000 feet MSL | 18,000 feet MSL | 18,000 feet MSL | feet MSL | 18,000 feet MSL
Network-Centric Military Operations (Network Readiness)
The system must | The system must | The system must | The system must fully | The system must fully
fully support | fully support | fully support | support execution of | support execution of
execution of all | execution of all | execution of joint | joint critical | joint critical
operational activities | operational activities | critical operational | operational activities | operational activities
identified in the | identified in the | activities identified in | identified in the | identified in the
applicable joint and | applicable joint and | the applicable joint | applicable joint and | applicable joint and
system integrated | system integrated | and system | system integrated | system integrated
architectures and | architectures and | integrated | architectures and the | architectures and the
the system must | the system must | architectures and | system must satisfy | system must satisfy
satisfy the technical | satisfy the technical | the system must | the technical | the technical
requirements for Net | requirements for Net | satisfy the technical | requirements for | requirements for
-Centric military | -Centric military | requirements for | transition to Net- | transition to Net-
operations to | operations to | transition to Net- | Centric military | Centric military
include: (1) The | include: (1) The | Centric military | operations to include: | operations to include:
DISR mandated GIG | DISR mandated GIG | operations to | (1) The DISR | (1) The DISR
IT standards and | IT standards and | include: (1) The | mandated GIG IT | mandated GIG IT
profiles identified in | profiles identified in | DISR mandated GIG | standards and profiles | standards and profiles
the TV-1, (2) DISR | the TV-1, (2) DISR | IT standards and | identified in the TV-1 | identified in the TV-1
mandated GIG KIPs | mandated GIG KIPs | profiles identified in | (2) DISR mandated | (2) DISR mandated
identified in the KIP | identified in the KIP | the TV-1 (2) DISR | GIG KIPs identified in | GIG KIPs identified in
declaration table, (3) | declaration table, (3) | mandated GIG KIPs | the KIP declaration | the KIP declaration
NCOW RM | NCOW RM | identified in the KIP | table (3) NCOW RM | table (3) NCOW RM
Enterprise Services | Enterprise Services | declaration table (3) | Enterprise Services | Enterprise Services
(4) IA requirements | (4) IA requirements | NCOW RM | (4) IA requirements | (4) IA requirements
include availability, | include availability, | Enterprise Services | including availability | including availability
integrity, authenticat | integrity, authenticat | (4) IA requirements | integrity, | integrity,
-ion, confidential-ity, | -ion, confidential-ity, | including availability | authentication, | authentication,
non-repudiation, and | non-repudiation, and | integrity, authenticat | confidentiality, | confidentiality,
issuance of an ATO | issuance of an ATO | -ion, confidential-ity, | nonrepudiation, and | nonrepudiation, and
by the DAA (5) | by the DAA (5) | non-repudiation, and | issuance of an IATO | issuance of an IATO
Operationally | Operationally | issuance of an IATO | by the DAA (5) | by the DAA (5)
effective information | effective information | by the DAA (5) | Operationally effective | Operationally effective
exchanges; and MC | exchanges; and MC | Operationally | information | information
- performance and | - performance and | effective information | exchanges and MC- | exchanges and MC-
IA attributes, data | IA attributes, data | exchanges and MC- | performance and IA | performance and IA
correctness, data | correctness, data | performance and IA | attributes, data | attributes, data
availability, and | availability, and | attributes, data | availability, and | availability, and
consistent data | consistent data | availability, and | consistent data | consistent data
processing | processing | consistent data | processing specified | processing specified
specified in the | specified in the | processing | in the applicable joint | in the applicable joint
applicable joint and | applicable joint and | specified in the | and system integrated | and system integrated
system integrated | system integrated | applicable joint and | architecture views | architecture views
architecture views | architecture views | system integrated
architecture views
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
CDD dated March 3, 2009

## Table 12
Change Explanations
(Ch-1) The current estimate for the Radar Ao KPP has changed from =>0.85 to =>0.89 due to new test results.
Acronyms and Abbreviations
Ao - Operational Availability ATO - Authorization to Operate
DAA - Designated Approval Authority
DISR - DoD Information Technology Standards and Profile Registry Es - Enlisted
g - gravity
GIG - Global Information Grid IA - Information Assurance
IATO - Interim Authorization to Operate IT - Information Technology
KIPs - Key Intelligence Profiles MC - Mission Critical
MSL - Mean Sea Level
NCOW RM - Net-Centric Operations and Warfare Reference Model nm - nautical mile
Os - Officers
TV-1 - Technical View 1

## Table 13
Track to Budget
General Notes
APPN 1506 Line Item 019500 and APPN 1506 Line Item 060510 are shared with the E-2C Reproduction program, which was funded through FY 2007 and no longer requires Acquisition Category reporting as it is over 90% expended. E-2D AHE procurement funding began in FY 2008, as shown in the funding summary.
RDT&E PE 0604234N, Project Unit 9999 not included. FY 2016 Congressional Add is not within scope of approved Program of Record.
RDT&E
Appn |  | BA | PE
Navy 1319 05 0604234N
Project | Name
3051 E-2D Adv Hawkeye
Procurement
Appn |  | BA | PE
Navy 1506 01 0204152N
Line Item Name
0195 E-2D Adv Hawkeye (Shared) Navy 1506 06 0204152N
Line Item Name
0605 Spares and Repair Parts (Shared)
MILCON
Appn |  | BA | PE
Navy 1205 01 0703676N
Project Name
69232565 E-2D Hangar/Apron Modifications at Pt. Mugu (Sunk) Navy 1205 01 0805976N
Project Name
62613603 Facilities Restoration and Mod-Training E-2D Operational Trainer Complex
Navy 1205 01 0815976N
Project Name
60495420 Facilities New Footprint - Trainers NAS Fallon Training Facility, E-2D portion
(Sunk)
(Shared) (Sunk)

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2009 $M |  |  |  | BY 2009 $M |  | TY $M
| SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E | 4140 |  | 5674.4 | 6241.8 |  | 5724.9 |  | 4014.3 |  | 5803.1 |  | 5852.9
Procurement | 13281.9 |  | 12932 | 14225.2 |  | 13741.7 |  | 14968.5 |  | 15045 |  | 15963.2
Flyaway | -- |  | -- | -- |  | 11439.9 |  | -- |  | -- |  | 13277.1
Recurring | -- |  | -- | -- |  | 10686.3 |  | -- |  | -- |  | 12381.9
Non Recurring | -- |  | -- | -- |  | 753.6 |  | -- |  | -- |  | 895.2
Support | -- |  | -- | -- |  | 2301.8 |  | -- |  | -- |  | 2686.1
Other Support | -- |  | -- | -- |  | 2004 |  | -- |  | -- |  | 2357.8
Initial Spares | -- |  | -- | -- |  | 297.8 |  | -- |  | -- |  | 328.3
MILCON | 46.7 |  | 67.2 | 73.9 |  | 67.5 |  | 48.6 |  | 73.6 |  | 73.6
Acq O&M | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 17468.6 |  | 18673.6 | N/A |  | 19534.1 |  | 19031.4 |  | 20921.7 |  | 21889.7
Current APB Cost Estimate Reference
POE dated February 02, 2015
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The ICE to support the E-2D AHE FRP Decision Review, like all previous CAPE estimates, is built upon a product-oriented work breakdown structure; is based on historical actual cost information to the mazimum extent possible; and, most importantly, is based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Department of Defense has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for MDAPs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.

## Table 15
Total Quantity
Quantity | SAR Baseline Production Estimate | Current APB Production | Current Estimate
RDT&E | 5 | 5 | 5
Procurement | 70 | 70 | 70
Total | 75 | 75 | 75

## Table 16
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 4387.3 | 209.1 |  | 363.8 |  | 290.4 |  | 216.9 |  | 185.4 |  | 168.7 |  | 31.3 |  | 5852.9
Procurement | 6776.6 | 1051.8 |  | 1061.6 |  | 832.1 |  | 824.6 |  | 1023.1 |  | 1148.6 |  | 3244.8 |  | 15963.2
MILCON | 45.4 | 28.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 73.6
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 11209.3 | 1289.1 |  | 1425.4 |  | 1122.5 |  | 1041.5 |  | 1208.5 |  | 1317.3 |  | 3276.1 |  | 21889.7
PB 2016 Total | 11212.8 | 1361.1 |  | 1384.4 |  | 1121.5 |  | 1178 |  | 1204.8 |  | 1047.4 |  | 3310.7 |  | 21820.7
Delta | -3.5 | -72 |  | 41 |  | 1 |  | -136.5 |  | 3.7 |  | 269.9 |  | -34.6 |  | 69
Funding Notes
RDT&E PE 0604234N, Project Unit 9999 not included. FY 2016 Congressional Add is not within scope of approved Program of Record.
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 5 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 5
Production | 0 |  | 30 |  | 5 | 6 | 5 |  | 3 |  | 4 |  | 5 |  | 12 |  | 70
PB 2017 Total | 5 |  | 30 |  | 5 | 6 | 5 |  | 3 |  | 4 |  | 5 |  | 12 |  | 75
PB 2016 Total | 5 |  | 30 |  | 5 | 6 | 5 |  | 4 |  | 4 |  | 4 |  | 12 |  | 75
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | -1 |  | 0 |  | 1 |  | 0 |  | 0

## Table 17
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 73.2
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 105.8
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 325.5
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 541.7
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 595.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 480.8
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 784.8
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 467.9
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 345.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 167.8
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 108.5
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 115.7
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 103
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 171.2
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 209.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 363.8
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 290.4
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 216.9
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 185.4
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 168.7
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.3
Subtotal |  | 5 | -- |  | -- |  | -- |  | -- |  | -- |  | 5852.9

## Table 18
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2009 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 84.7
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 120.6
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 360.9
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 585.2
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 624
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 491.7
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 788.2
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 464
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 337.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 160.1
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 101.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 107.5
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 94.3
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 154.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 186.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 318
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 249
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 182.3
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 152.8
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 136.3
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.8
Subtotal |  | 5 | -- |  | -- |  | -- |  | -- |  | -- |  | 5724.9

## Table 19
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | 72.2 |  | -- |  | -- |  | 72.2 |  | -- |  | 72.2
2009 |  | 2 | 404.5 |  | -- |  | -- |  | 404.5 |  | 67.6 |  | 472.1
2010 |  | 3 | 584.6 |  | -- |  | 33.7 |  | 618.3 |  | 161.5 |  | 779.8
2011 |  | 5 | 848.6 |  | -- |  | 73.9 |  | 922.5 |  | 202.9 |  | 1125.4
2012 |  | 5 | 852.8 |  | -- |  | 37.4 |  | 890.2 |  | 131.1 |  | 1021.3
2013 |  | 5 | 772.4 |  | -- |  | 42.5 |  | 814.9 |  | 119.2 |  | 934.1
2014 |  | 5 | 979.4 |  | -- |  | 47.6 |  | 1027 |  | 188.1 |  | 1215.1
2015 |  | 5 | 908.3 |  | -- |  | 64 |  | 972.3 |  | 184.3 |  | 1156.6
2016 |  | 5 | 803.7 |  | -- |  | 51.8 |  | 855.5 |  | 196.3 |  | 1051.8
2017 |  | 6 | 807 |  | -- |  | 52.8 |  | 859.8 |  | 201.8 |  | 1061.6
2018 |  | 5 | 602.7 |  | -- |  | 53.8 |  | 656.5 |  | 175.6 |  | 832.1
2019 |  | 3 | 612.2 |  | -- |  | 54.9 |  | 667.1 |  | 157.5 |  | 824.6
2020 |  | 4 | 800.7 |  | -- |  | 56 |  | 856.7 |  | 166.4 |  | 1023.1
2021 |  | 5 | 941.6 |  | -- |  | 57.1 |  | 998.7 |  | 149.9 |  | 1148.6
2022 |  | 5 | 996.6 |  | -- |  | 58.3 |  | 1054.9 |  | 185.6 |  | 1240.5
2023 |  | 5 | 939 |  | -- |  | 69.5 |  | 1008.5 |  | 121.3 |  | 1129.8
2024 |  | 2 | 455.6 |  | -- |  | 93.8 |  | 549.4 |  | 115.3 |  | 664.7
2025 |  | -- | -- |  | -- |  | 48.1 |  | 48.1 |  | 161.7 |  | 209.8
Subtotal |  | 70 | 12381.9 |  | -- |  | 895.2 |  | 13277.1 |  | 2686.1 |  | 15963.2

## Table 20
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | BY 2009 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | 71.8 |  | -- |  | -- |  | 71.8 |  | -- |  | 71.8
2009 |  | 2 | 396.6 |  | -- |  | -- |  | 396.6 |  | 66.3 |  | 462.9
2010 |  | 3 | 561.4 |  | -- |  | 32.4 |  | 593.8 |  | 155.1 |  | 748.9
2011 |  | 5 | 799.1 |  | -- |  | 69.6 |  | 868.7 |  | 191.1 |  | 1059.8
2012 |  | 5 | 791.7 |  | -- |  | 34.7 |  | 826.4 |  | 121.8 |  | 948.2
2013 |  | 5 | 709.5 |  | -- |  | 39 |  | 748.5 |  | 109.5 |  | 858
2014 |  | 5 | 888 |  | -- |  | 43.2 |  | 931.2 |  | 170.6 |  | 1101.8
2015 |  | 5 | 811.4 |  | -- |  | 57.2 |  | 868.6 |  | 164.6 |  | 1033.2
2016 |  | 5 | 705.7 |  | -- |  | 45.5 |  | 751.2 |  | 172.4 |  | 923.6
2017 |  | 6 | 695.4 |  | -- |  | 45.5 |  | 740.9 |  | 173.9 |  | 914.8
2018 |  | 5 | 509.4 |  | -- |  | 45.5 |  | 554.9 |  | 148.3 |  | 703.2
2019 |  | 3 | 507.2 |  | -- |  | 45.5 |  | 552.7 |  | 130.5 |  | 683.2
2020 |  | 4 | 650.4 |  | -- |  | 45.5 |  | 695.9 |  | 135.2 |  | 831.1
2021 |  | 5 | 749.9 |  | -- |  | 45.5 |  | 795.4 |  | 119.3 |  | 914.7
2022 |  | 5 | 778.1 |  | -- |  | 45.5 |  | 823.6 |  | 144.9 |  | 968.5
2023 |  | 5 | 718.8 |  | -- |  | 53.2 |  | 772 |  | 92.8 |  | 864.8
2024 |  | 2 | 341.9 |  | -- |  | 70.4 |  | 412.3 |  | 86.5 |  | 498.8
2025 |  | -- | -- |  | -- |  | 35.4 |  | 35.4 |  | 119 |  | 154.4
Subtotal |  | 70 | 10686.3 |  | -- |  | 753.6 |  | 11439.9 |  | 2301.8 |  | 13741.7

## Table 21
Cost Quantity Information 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2009 $M
2008 | -- | --
2009 | 2 | 414.9
2010 | 3 | 524
2011 | 5 | 778.9
2012 | 5 | 756.2
2013 | 5 | 743.3
2014 | 5 | 762
2015 | 5 | 848.7
2016 | 5 | 735.9
2017 | 6 | 759.2
2018 | 5 | 549.7
2019 | 3 | 486.5
2020 | 4 | 633.2
2021 | 5 | 764.5
2022 | 5 | 762.1
2023 | 5 | 771.1
2024 | 2 | 396.1
2025 | -- | --
Subtotal | 70 | 10686.3

## Table 22
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
2008 11.5
2009 --
2010 16.8
2011 --
2012 15.4
2013 --
2014 --
2015 1.7
2016 28.2
Subtotal 73.6

## Table 23
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 2009 $M
Total Program
2008 11.4
2009 --
2010 16.0
2011 --
2012 14.2
2013 --
2014 --
2015 1.5
2016 24.4
Subtotal 67.5

## Table 24
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2003-06-13 | 2011-04-03
Approved Quantity | 22 | 15
Reference | Milestone B ADM | LRIP Lots 3 and 4 ADM
Start Year | 2009 | 2009
End Year | 2012 | 2012
The Current Total LRIP Quantity is more than 10% of the total production quantity due to 15 aircraft being the minimum to maintain the industrial base and ensure successful transition to FRP.
The 15 planned LRIP aircraft (including one FY 2011 supplemental) represent 20% of the total quantity. The reduction in LRIP quantities is due to the production quantity ramp changes.

## Table 25
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Japan 8/11/2015 1 540.5 FMS Case JA-P-SCJ, E-2D Advanced Hawkeye, Non-Recurring Engineering to support Japan Unique Wet-Outer Wing Panel Configuration, Spares, Support Equipment and Product Support.
Notes
Nuclear Costs
None

## Table 26
Unit Cost
Unit Cost Report
Item |  | BY 2009 $M |  | BY 2009 $M |  | % Change
|  | Current UCR Baseline (Mar 2015 APB) |  | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 18673.6 |  |  |  | 19534.1
Quantity | 75 |  |  |  | 75
Unit Cost | 248.981 |  |  |  | 260.455 |  |  | 4.61
Average Procurement Unit Cost
Cost | 12932 |  |  |  | 13741.7
Quantity | 70 |  |  |  | 70
Unit Cost | 184.743 |  |  |  | 196.31 |  |  | 6.26
Item |  | BY 2009 $M | BY 2009 $M |  |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Jul 2009 APB)
Program Acquisition Unit Cost
Cost | 17468.6 |  |  |  | 19534.1
Quantity | 75 |  |  |  | 75
Unit Cost | 232.915 |  |  |  | 260.455 |  | 11.82
Average Procurement Unit Cost
Cost | 13281.9 |  |  |  | 13741.7
Quantity | 70 |  |  |  | 70
Unit Cost | 189.741 |  |  |  | 196.31 |  | 3.46

## Table 27
Unit Cost History
Item | [7 empty] | Date |  |  |  | BY 2009 $M | [6 empty] | TY $M
[12 empty] | PAUC |  |  | APUC |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Jun 2003 | [6 empty] | 189.977 |  |  |  | 152.732 |  |  |  | 199.76 |  |  |  | 166.551
APB as of January 2006 |  |  |  |  | Jun 2003 | [6 empty] | 189.977 |  |  |  | 152.732 |  |  |  | 199.76 |  |  |  | 166.551
Revised Original APB |  |  |  |  | Jul 2009 | [6 empty] | 232.915 |  |  |  | 189.741 |  |  |  | 253.752 |  |  |  | 213.836
Prior APB |  |  |  |  | Apr 2013 | [6 empty] | 241.28 |  |  |  | 184.743 |  |  |  | 269.981 |  |  |  | 214.929
Current APB |  |  |  |  | Mar 2015 | [6 empty] | 248.981 |  |  |  | 184.743 |  |  |  | 278.956 |  |  |  | 214.929
Prior Annual SAR |  |  |  |  | Dec 2014 | [6 empty] | 258.515 |  |  |  | 194.957 |  |  |  | 290.943 |  |  |  | 227.771
Current Estimate |  |  |  |  | Dec 2015 | [6 empty] | 260.455 |  |  |  | 196.31 |  |  |  | 291.863 |  |  |  | 228.046
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [20 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth |  |  |  | Spt |  | Total
199.760 5.871 0.000 3.025 8.235 28.608 0.000 8.253 53.992 253.752
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [18 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth |  |  | Spt | Total
253.752 -1.043 0.000 24.459 17.961 -11.595 0.000 8.329 38.111 291.863

## Table 28
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [12 empty] | APUC Production Estimate
| Econ | Qty |  |  | Sch | Eng |  | Est | Oth |  | Spt |  | Total
166.551 4.414 -0.572 3.241 4.910 27.393 0.000 7.899 47.285 213.836
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [12 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng |  | Est |  | Oth |  | Spt | Total
213.836 -0.779 0.000 26.204 2.433 -22.573 0.000 8.924 14.209 228.046
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate |  |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  | N/A |  |  |  | N/A |  |  |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  |  | May 2003 |  |  |  |  | May 2003 |  |  | Jun 2003
Milestone C |  |  | N/A |  |  |  | Mar 2009 |  |  |  |  | Mar 2009 |  |  | May 2009
IOC |  |  | N/A |  |  |  | Apr 2011 |  |  |  |  | Oct 2014 |  |  | Oct 2014
Total Cost (TY $M) |  |  | N/A |  |  |  | 14982 |  |  |  |  | 19031.4 |  |  | 21889.7
Total Quantity |  |  | N/A |  |  |  | 75 |  |  |  |  | 75 |  |  | 75
PAUC |  |  | N/A |  |  |  | 199.76 |  |  |  |  | 253.752 |  |  | 291.863

## Table 29
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
4014.3 14968.5 48.6 19031.4
Economic |  | -14.1 |  | 40.9 |  | 0.5 |  | 27.3
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 1744 |  | -- |  | 1744
Engineering |  | 1146.9 |  | 144.5 |  | 29.9 |  | 1321.3
Estimating |  | 656 |  | -1612.4 |  | -5.4 |  | -961.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 658.5 |  | -- |  | 658.5
Subtotal |  | 1788.8 |  | 975.5 |  | 25 |  | 2789.3
Current Changes Economic |  | -9.8 |  | -95.4 |  | -0.3 |  | -105.5
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 90.3 |  | -- |  | 90.3
Engineering |  | -- |  | 25.8 |  | -- |  | 25.8
Estimating |  | 59.6 |  | 32.3 |  | 0.3 |  | 92.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -33.8 |  | -- |  | -33.8
Subtotal |  | 49.8 |  | 19.2 |  | -- |  | 69
Total Changes |  | 1838.6 |  | 994.7 |  | 25 |  | 2858.3
CE - Cost Variance |  | 5852.9 |  | 15963.2 |  | 73.6 |  | 21889.7
CE - Cost & Funding |  | 5852.9 |  | 15963.2 |  | 73.6 |  | 21889.7

## Table 30
Summary BY 2009 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
4140.0 13281.9 46.7 17468.6
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 1121.7 |  | -- |  | 1121.7
Engineering |  | 984.2 |  | 124.2 |  | 25.7 |  | 1134.1
Estimating |  | 550.2 |  | -1357.9 |  | -5.2 |  | -812.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 477.1 |  | -- |  | 477.1
Subtotal |  | 1534.4 |  | 365.1 |  | 20.5 |  | 1920
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 77.3 |  | -- |  | 77.3
Engineering |  | -- |  | 20.3 |  | -- |  | 20.3
Estimating |  | 50.5 |  | 26.9 |  | 0.3 |  | 77.7
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -29.8 |  | -- |  | -29.8
Subtotal |  | 50.5 |  | 94.7 |  | 0.3 |  | 145.5
Total Changes |  | 1584.9 |  | 459.8 |  | 20.8 |  | 2065.5
CE - Cost Variance |  | 5724.9 |  | 13741.7 |  | 67.5 |  | 19534.1
CE - Cost & Funding |  | 5724.9 |  | 13741.7 |  | 67.5 |  | 19534.1
Previous Estimate: December 2014

## Table 31
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | -9.8
Increase in funding to support Tactical Targeting Network Technology, Multifunctional Information Distribution System Joint Tactical Terminal Radio, Beyond Line of Sight Secret Internet Protocol Router (SIPR) chat, Crypto-Modernization/Frequency Re- Mapping, Integrated Fire Control, Advanced Mid-Term Interoperability Improvement |  | 142.7 | 167.1
Program, and restore Naval Integrated Fire Control-Counter Air wholeness. (Estimating)
Increase in funding for ALQ-217 Electronic Support Measures. (Estimating) +131.9 +156.7
Refinement of estimate to reflect actual funding adjustments of FY 2021 into the FYDP. (Estimating)
+68.2 +84.4
Revised estimate to reflect application of new outyear escalation indices. (Estimating) +7.1 +8.4 Adjustment for current and prior escalation. (Estimating) +2.8 +3.1
Revised Estimate due to decrease in funding for Counter Electronic Attack Increment II and Sensor Netting Phase II. (Estimating)
Revised Estimate due to decrease in funding for Net-Enabled Weapons J11, Stores Performance Assessment Requested Quality, and Navigation Warfare. (Estimating)
Revised Estimate due to Congressional adjustments in FY 2016 delaying new start capabilities to FY 2017. (Estimating)
-133.3 -165.2
-96.7 -113.5
-56.1 -63.0
Revised Estimate to reflect Naval Air Warfare Center rate adjustments. (Estimating) | -15.6 |  |  | -17.9
Revised Estimate to reflect DoD internal adjustments. (Estimating) | -0.5 |  |  | -0.5
RDT&E Subtotal | 50.5 |  |  | 49.8
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -95.4
Schedule variance resulting from re-phasing of aircraft (FY 2015 +1, FY 2019 -2, FY 2020 -
1, FY2024 +2). (Schedule)
Additional schedule variance due to movement of multiple aircraft from FY 2015 - FY 2024. (Schedule)
Increased funding for ALQ-217 Electronic Support Measures Receiver/Processor upgrade. (Engineering)
0.0 -4.0
+77.3 +94.3
+20.3 +25.8
Revised estimate to reflect application of outyear escalation indices. (Estimating) | 25.7 |  |  | 31.7
Revised Estimate for Northrop Grumman Aerospace Sector labor rates. (Estimating) | 19.8 |  |  | 25.5
Adjustment for current and prior escalation. (Estimating) | 20.1 |  |  | 22.5
Revised estimate to reflect actuals. (Estimating) | -38.7 |  |  | -47.4
Adjustment for current and prior escalation. (Support) | 4.2 |  |  | 4.6
Decrease in Other Support due to revised estimate to reflect actuals, reduced Navy | -48.1 |  |  | -53.8
Working Capital Funds labor rates, and congressional reduction to support funding. (Support)
Increase in Initial Spares due to additional spare engine procurements. (Support) | 14.1 |  |  | 15.4
Procurement Subtotal | 94.7 |  |  | 19.2
MILCON | $M

## Table 32
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.3
Adjustment for current and prior escalation. (Estimating) | 0.3 | 0.3
MILCON Subtotal | 0.3 | 0

## Table 33
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: LRIP Lot 4
Contractor: Northrop Grumman Systems Corporation
Contractor Location: 2000 West NASA Boulevard
Melbourne, FL 32904
Contract Number: N00019-10-C-0044/5
Contract Type: Firm Fixed Price (FFP)
Award Date: April 13, 2011
Definitization Date: January 24, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
94.6 N/A 0 787.4 N/A 5 787.4 787.4
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to this contract being awarded on April 13, 2011 as an advanced acquisition contract for the LRIP Lot 4 as a Not to Exceed contract in the amount of $94.6M. The contract was definitized on January 24, 2012 and transitioned to a Firm Fixed Price contract for the procurement of five aircraft with the current contract value of $787.4M.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 34
Contract Identification
Appropriation: Procurement
Contract Name: FRP Lot 1
Contractor: Northrop Grumman Systems Corporation
Contractor Location: 2000 West NASA Boulevard
Melborne, FL 32904
Contract Number: N00019-12-C-0063/5
Contract Type: Firm Fixed Price (FFP)
Award Date: February 01, 2012
Definitization Date: July 24, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
157.9 N/A 0 828.3 N/A 5 828.3 828.3
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to this contract being awarded on February 1, 2012 as an advanced acquisition for the FRP Lot 1 as a Not to Exceed contract in the amount of
$157.9M. The contract was definitized on July 24, 2013 and transitioned to a Firm Fixed Price contract for the procurement of five aircraft with a current contract value of $828.3M.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 35
Contract Identification
Appropriation: RDT&E
Contract Name: E-2D Aerial Refueling
Contractor: Northrop Grumman Systems Corporation
Contractor Location: 2000 West NASA Boulevard
Melbourne, FL 32904
Contract Number: N00019-13-C-0135/1 Contract Type: Cost Plus Incentive Fee (CPIF) Award Date: September 27, 2013
Definitization Date: September 27, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
226.7 N/A 0 226.7 N/A 0 204.2 211.0
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) -0.8 +0.7
Previous Cumulative Variances -2.9 -1.8
Net Change +2.1 +2.5
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to savings associated with a materials account and the offset of labor rate adjustments and the allocation accounts in prior months.
The favorable net change in the schedule variance is due to supplier milestones completing early.

## Table 36
Contract Identification
Appropriation: Procurement
Contract Name: Multi-Year Procurement (FRP Lots 2-6)
Contractor: Northrop Grumman Systems Corporation
Contractor Location: 2000 West NASA Boulevard
Melbourne, FL 32904
Contract Number: N00019-13-C-9999/1
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: May 17, 2013
Definitization Date: June 30, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
113.7 N/A 0 4392.3 4392.3 26 4392.3 4392.3
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to this contract being awarded on May 17, 2013 as an advanced acquisition contract for the FRP Lot 2 as a Not To Exceed contract in the amount of $113.7M. On July 31, 2013, an additional $9.3M contract modification was made. This contract was definitized on June 30, 2014 and transitioned to Fixed Price Incentive Firm Contract for the procurement of 25 aircraft with a current contract value of $3906.7M. On November 12, 2015, a $140.0M modification was awarded for one E-2D aircraft for the government of Japan and on December 30, 2015, a $286.0M modification was awarded for non-recurring engineering and recurring efforts to support the production and delivery of this E-2D AHE aircraft for the government of Japan under a FMS program.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract because an earned value management waiver was granted by the Deputy Assistant Secretary of the Navy for Acquisition and Procurement on May 12, 2014 as delegated by the Assistant Secretary of the Navy for Research, Development, and Acquisition due to the fact that the E-2D AHE airframe is being produced in a mature FRP environment, with a prime contractor displaying a long-term history of consistently meeting delivery schedules, at or below contract targets.

## Table 37
Contract Identification
Appropriation: RDT&E
Contract Name: Full Scale Fatigue Test
Contractor: Northrop Grumman Systems Corporation
Contractor Location: 2000 West NASA Boulevard
Melbourne, FL 32904
Contract Number: N00019-14-C-0036/1
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: July 07, 2014
Definitization Date: July 07, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
52.4 N/A 0 59.5 N/A 0 50.9 54.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the additional scope of Wing Center Section Fatigue Article Testing and the exercise of a repair option.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +0.7 0.0
Previous Cumulative Variances +0.2 0.0
Net Change +0.5 +0.0
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to labor and material efficiencies to review test data.

## Table 38
Contract Identification
Appropriation: RDT&E
Contract Name: Post IOC Capibilities
Contractor: Northrop Grumman systems Corporation
Contractor Location: 2000 West NASA Boulevard
Melbourne, FL 32904
Contract Number: N00019-15-C-0091/1 Contract Type: Cost Plus Incentive Fee (CPIF) Award Date: April 06, 2015
Definitization Date: April 06, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
146.7 N/A N/A 146.7 N/A N/A 121.3 139.2
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +1.5 -0.4
Previous Cumulative Variances -- --
Net Change +1.5 -0.4
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to labor efficiencies within the Program Management accounts.
The unfavorable cumulative schedule variance is due to minor delays in receipt of supplier invoices. This schedule variance is likely to remain in this area until the work scope is complete and all invoices have been received.
Notes
This is the first time this contract is being reported.

## Table 39
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 5 | 5 | 5 | 100%
Production | 17 | 17 | 70 | 24.29%
Total Program Quantity Delivered | 22 | 22 | 75 | 29.33%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
21889.7
9271.1
42.35%
24
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
15
62.5%
12498.4
57.1%
The above data is current as of February 09, 2016.

## Table 40
Operating and Support Cost
Cost Estimate Details
Date of Estimate: February 23, 2016
Source of Estimate: POE
Quantity to Sustain: 71
Unit of Measure: Aircraft
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2011 - FY 2046
Inflation Indices Utilized: FY 2016 OSD rates
Flight Hours per Aircraft per Month: 40 (assumes no change in the Concept of Operations associated with the Aerial Refueling effort)
Number of Aircraft per Carrier AEW Squadron: 5 Total Number of Primary Authorized Aircraft (PAA): 66
- Ten 5 aircraft Carrier Airborne Early Warning squadrons
- One 12 aircraft Fleet Replacement Squadron (FRS)
- 2 aircraft at Air Test and Evaluation Squadron One (VX-1)*
- 2 aircraft at Naval Strike Air Warfare Center (NSAWC)* Aircraft Flight Hours Life Limit: 9,600
Pipeline Rate: 8%
Attrition Rate: 0%
Total Operating Flight Hours: 583,039 Total Operating Aircraft Years: 1,324
*PAA beyond Primary Mission Aircraft Authorized (PMAA) and FRS aircraft are typically not included in Naval Air Systems Command (NAVAIR) AIR 4.2 O&S cost estimates; however, PAA for VX-1 and NSAWC have been included in the E-2D AHE O&S cost estimate. The O&S cost estimate excludes the four PAA for the NAVAIR-owned aircraft, which are not fleet-owned assets.
Sustainment Strategy
The E-2D AHE initial sustainment concept for E-2D AHE unique parts is Interim Contractor Support through Material Support Date (MSD) with common systems supported organically. For the period of MSD (1st Quarter FY 2016) through Navy Support Date (4th Quarter FY 2019), Naval Supply Systems Command Weapons System Support will support E- 2D AHE unique systems through conventional and/or performance-based repair contracts with Original Equipment Manufacturers. With few exceptions, E-2D AHE unique systems have been designated as Core Capabilities and the program is pursuing the establishment of organic capabilities to comply with the U.S. Code Title 10 requirements. As these capabilities are established, business case analyses will be conducted to determine the best value sustainment strategies, whether it is organic or public-private partnership.
The Operating Inventory Utilization per Unit is 40 Flight Hours per Month.

## Table 41
Antecedent Information
The antecedent program is the E-2C. Annual costs for the antecedent program are based upon a three-year average of Naval Visibility and Management of Operating and Support Costs (VAMOSC) data from FY 2010 - FY 2012 where costs for the three years are summed and then divided by the sum of aircraft count for the three years. The average number of aircraft in the three-year VAMOSC dataset is 58.33. Since Naval VAMOSC does not capture Indirect Support costs, the E
-2C Indirect Support cost is calculated by multiplying the E-2C Unit-Level Manpower by the ratio of E-2D AHE Indirect Support to E-2D AHE Unit-Level Manpower.
For comparison purposes, the Total O&S Cost is the product of the Antecedent’s Average Annual Cost per Unit and the Operating Aircraft Years of the E-2D AHE.
Annual O&S Costs BY2009 $M
Cost Element |  |  | E-2D AHE Average Annual Cost Per Aircraft |  |  |  | E-2C (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower |  |  | 2.769 |  |  |  | 2.7
Unit Operations |  |  | 0.509 |  |  |  | 0.415
Maintenance |  |  | 6.322 |  |  |  | 3.535
Sustaining Support |  |  | 0.606 |  |  |  | 0.207
Continuing System Improvements |  |  | 1.502 |  |  |  | 1.034
Indirect Support |  |  | 0.99 |  |  |  | 0.966
Other |  |  | -- |  |  |  | 0
Total |  |  | 12.698 |  |  |  | 8.857
The flight hour utilization rate for E-2C is 30.8 hours per aircraft per month, which contributes to the delta in Unit Operations and Maintenance cost between the E-2D AHE and E-2C.
Item | Total O&S Cost $M
| E-2D AHE | [6 empty] | E-2C (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year |  | 17334.7 |  | 19068.2 |  | 16806.1 |  |  | 11724.6
Then Year |  | 23824.4 |  | N/A |  | 24854.8 |  |  | N/A
.
Equation to Translate Annual Cost to Total Cost
Average Annual Aircraft O&S Cost = Total O&S Cost / Total Operating Aircraft Years
$12.698 (BY 2009 $M) = $16806.1 (BY 2009 $M)/1324

## Table 42
O&S Cost Variance
Category | BY 2009 $M | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
16559.5
Programmatic/Planning Factors 299.8 Update based on FY 2017 PB procurement schedule;
Update to delivery schedule using forecasted aircraft delivery dates; Update to flight hours based on FY 2017 PB hours
Cost Estimating Methodology 0.0
Cost Data Update -181.8 Update to Depot-Level Repairable and Consumable Cost Per Flight Hour based on FY 2016 pricing; Update to engine module repair prices; Update to Depot Planned Maintenance Interval (PMI) cost per event; Incorporated FY 2016 OSD inflation indices
Labor Rate -6.3 Incorporated FY 2016 Military Composite Pay Rates
Energy Rate 14.4 Incorporated FY 2015 fuel price
Technical Input -0.2 Update to Depot PMI schedule
Other 120.7 Corrected cost model to include all applicable costs in FY 2046; Corrected cost model so that only safety improvement modifications occur in last five years
Total Changes 246.6
Current Estimate 16806.1
Disposal Estimate Details
Date of Estimate: February 23, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2009 $M): Total costs for disposal of all Aircraft are 16.9
The estimate will be refined based on future updates to the E-2D Deactivation, Demilitarization & Disposal (3D) Plan.