## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-433
KC-130J Transport Aircraft (KC-130J)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 12
Cost and Funding 14
Low Rate Initial Production 23
Foreign Military Sales 24
Nuclear Costs 24
Unit Cost 25
Cost Variance 28
Contracts 31
Deliveries and Expenditures 36
Operating and Support Cost 37

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
KC-130J Transport Aircraft (KC-130J)
DoD Component
Navy
Responsible Office
Mr. Douglas Dawson
PMA-207, Tactical Airlift Program Office
Program Executive Office - Air, Anti-Submarine Warfare, Assault & Special Mission Programs
Bldg. 419, 46990 Hinkle Circle Patuxent River, MD 20670-1547
douglas.dawson@navy.mil
Phone: 301-757-8574
Fax: 301-342-0962
DSN Phone: 757-8574
DSN Fax:
Date Assigned: April 17, 2014
References
SAR Baseline (Production Estimate)
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated February 7, 2011
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated February 7, 2011

## Table 6
Mission and Description
The KC-130J Transport Aircraft (KC-130J) is a high-wing, long range land based monoplane which is powered by four turboprop engines equipped with six blade variable pitch propellers.
The KC-130J program provides the Marine Corps with air-to-air refueler/tactical transport capability to replace the KC-130 F/R/T aircraft. Specific KC-130J mission capabilities encompass air-to-air refueling, air delivered ground refueling, tactical troop transport, aerial delivery of personnel and cargo, airborne radio relay, tactical aero-medical evacuation, multi-sensor reconnaissance, and close air support. The KC-130J improves readiness, capability and survivability while reducing maintenance and operating costs.

## Table 7
Executive Summary
The current program of record is 104 aircraft - 79 United States Marine Corps (USMC) and 25 United States Navy Reserve. As of January 6, 2016, 48 aircraft have been delivered. All aircraft are being acquired through United States Air Force (USAF) procurement contracts.
The USAF awarded a multi-year procurement (MYP) contract for C-130J aircraft on December 30, 2015. The MYP contract covers FY 2014 - FY 2018 procurements and includes six KC-130Js for the USMC. Additionally, three FY 2013 Congressional adds were definitized on the same date.
The KC-130J has been continuously forward deployed in support of multiple operations since February 2005.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
USAF Program Initiation | Jun 1996 | Jun 1996 | Jan 1997 | Jun 1996
USAF FY 1996 Basic Aircraft Contract | Nov 1996 | Nov 1996 | May 1997 | Nov 1996
USAF First Delivery | Mar 1999 | Mar 1999 | Sep 1999 | Mar 1999
USMC IOC | Feb 2005 | Feb 2005 | Feb 2005 | Feb 2005
Change Explanations
Acronyms and Abbreviations
USAF - United States Air Force USMC - United States Marine Corps

## Table 10
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Net Ready
100% of interfaces; services; policy- enforcement controls; and data correctness, availability and processing in the joint architecture. | 100% of interfaces; services; policy- enforcement controls; and data correctness, availability and processing in the joint architecture. | 100% of interfaces; services; policy-enforcement controls; and data correctness, availability and processing requirements present in the Block 5.4 configuration designated as enterprise-level or critical in the joint integrated architecture. | Objective met with the incorporation of Block 5.4 | 100% of interfaces; services; policy- enforcement controls; and data correctness, availability and processing in the joint architecture.
Range with 25000 lb Cargo Load
2,700 nm | 2,700 nm | The C-130J deployment range, at long-range cruise airspeeds, mean cruise weight fuel flow, a cruise altitude of 27,000 ft or above, 6,700 lbs reserve fuel overhead destination with a 25,000 lb cargo payload, and the conditions stated above, the deployment range must be 2,460 nm | 2,700 nm | 2,700 nm
Maximum Effort Ground Roll
The maximum effort landing ground roll at 135,000 lbs will not exceed 1800 ft | The maximum effort landing ground roll at 135,000 lbs will not exceed 1800 ft | The maximum effort landing ground roll at 135,000 lbs will not exceed 1800 ft | 1800 ft | The maximum effort landing ground roll at 135,000 lbs will not exceed 1800 ft
Maximum Effort Takeoff Run
2700 ft | 2700 ft | The aircraft shall be able to perform a maximum effort take off from a prepared surface at sea level, standard day, no wind, and maximum gross weight of 164,000 lbs in 3,300 ft | 2700 ft | 2700 ft
Requirements Reference
Operational Requirements Letter (ORL) Change 3 dated February 14, 2009

## Table 11
Change Explanations
None
Notes
ORL Change 3 was clarified on November 12, 2013, with no changes to the KC-130J Performance Characteristics.
Acronyms and Abbreviations
ft - Feet
lbs - Pounds
nm - Nautical Miles
ORL - Operational Requirements Letter

## Table 12
Track to Budget
RDT&E
Appn |  | BA | PE
Navy 1319 05 0605430N
Project | Name
3199 C/KC-130 Avionics Modernization Program (Sunk)
Procurement
Appn |  | BA | PE
Navy 1506 04 0206127M
Line Item | Name
0416 KC-130J (Sunk)
Notes: KC-130J Squadrons (Marine Air Wing)
Navy 1506 04 0502504M
Line Item | Name
0416 KC-130J
Notes: KC-130/VMGR Squadrons (Marine Corps Reserves)
Navy 1506 04 0502379N
Line Item | Name
0416 KC-130J (Sunk)
Notes: Direct Support Squadron
Navy 1506 06 0206127M
Line Item | Name
0605 Spares & Repair Parts (Shared) (Sunk)
Notes: KC-130J Squadrons (Marine Air Wing)
Navy 1506 06 0502504M
Line Item | Name
0605 Spares & Repair Parts (Shared)
Notes: KC-130/VMGR Squadrons (Marine Corps Reserves)
Navy 1506 06 0502379N
Line Item | Name
0605 Spares & Repair Parts (Shared) (Sunk)
Notes: Direct Support Squadron
Defense-Wide 0350 00
Line Item | Name
1301 National Guard Reserve Equipment
Notes

## Table 13
PEs 0502379N and 0206127M will be used to procure aircraft beyond FY 2021.
VMGR is a Marine Aerial Refueler Transport Squadron.

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2010 $M | [6 empty] | BY 2010 $M |  | TY $M
| SAR Baseline Production Estimate |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 35.6 |  |  | 35.6 | 39.2 |  |  | 38.1 |  | 35.5 |  |  | 35.5 |  | 37.8
Procurement |  | 9198.3 |  |  | 9198.3 | 10118.1 |  |  | 8644.9 |  | 9846.3 |  |  | 9846.3 |  | 9753.9
Flyaway |  | -- |  |  | -- | -- |  |  | 7390.7 |  | -- |  |  | -- |  | 8379.2
Recurring |  | -- |  |  | -- | -- |  |  | 7223.6 |  | -- |  |  | -- |  | 8181.1
Non Recurring |  | -- |  |  | -- | -- |  |  | 167.1 |  | -- |  |  | -- |  | 198.1
Support |  | -- |  |  | -- | -- |  |  | 1254.2 |  | -- |  |  | -- |  | 1374.7
Other Support |  | -- |  |  | -- | -- |  |  | 826.5 |  | -- |  |  | -- |  | 907.8
Initial Spares |  | -- |  |  | -- | -- |  |  | 427.7 |  | -- |  |  | -- |  | 466.9
MILCON |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 9233.9 |  |  | 9233.9 | N/A |  |  | 8683 |  | 9881.8 |  |  | 9881.8 |  | 9791.7
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The current APB cost estimate provided sufficient resources to execute the program under normal conditions, encountering average levels of technical, schedule and programmatic risk and external interference. It was consistent with average resource expenditures on historical efforts of similar size, scope, and complexity and represents a notional 50% confidence level when established.
Total Quantity
Quantity |  |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  |  | 104 |  |  |  | 104 |  |  |  |  | 104
Total |  |  | 104 |  |  |  | 104 |  |  |  |  | 104

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 37.8 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 37.8
Procurement | 4062.9 | 213.5 |  |  | 155.7 | 164.9 | 213.9 |  | 215 |  | 248.3 |  |  | 4479.7 |  | 9753.9
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 4100.7 | 213.5 |  |  | 155.7 | 164.9 | 213.9 |  | 215 |  | 248.3 |  |  | 4479.7 |  | 9791.7
PB 2016 Total | 4105.8 | 220.7 |  |  | 164.8 | 178.2 | 216.9 |  | 262.1 |  | 634 |  |  | 4117.3 |  | 9899.8
Delta | -5.1 | -7.2 |  |  | -9.1 | -13.3 | -3 |  | -47.1 |  | -385.7 |  |  | 362.4 |  | -108.1
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Production | 0 |  | 53 |  | 2 | 2 | 2 |  | 2 |  | 2 | 2 |  | 39 |  | 104
PB 2017 Total | 0 |  | 53 |  | 2 | 2 | 2 |  | 2 |  | 2 | 2 |  | 39 |  | 104
PB 2016 Total | 0 |  | 53 |  | 2 | 2 | 2 |  | 2 |  | 2 | 5 |  | 36 |  | 104
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | -3 |  | 3 |  | 0

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.4
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.3
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.8

## Table 17
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.3
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.1

## Table 18
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1997 |  | 3 | 162.6 |  | -- |  | -- |  | 162.6 |  | 38.9 |  | 201.5
1998 |  | 2 | 110.1 |  | -- |  | -- |  | 110.1 |  | 7.1 |  | 117.2
1999 |  | 2 | 107 |  | -- |  | -- |  | 107 |  | 4.1 |  | 111.1
2000 |  | 1 | 62.3 |  | -- |  | 1.2 |  | 63.5 |  | 7.7 |  | 71.2
2001 |  | 3 | 195.8 |  | -- |  | -- |  | 195.8 |  | 53.5 |  | 249.3
2002 |  | 2 | 138.2 |  | -- |  | -- |  | 138.2 |  | 30.3 |  | 168.5
2003 |  | 4 | 284.6 |  | -- |  | -- |  | 284.6 |  | 45.1 |  | 329.7
2004 |  | -- | 42.8 |  | -- |  | -- |  | 42.8 |  | 95.9 |  | 138.7
2005 |  | 4 | 289.5 |  | -- |  | -- |  | 289.5 |  | 52.7 |  | 342.2
2006 |  | 8 | 460.7 |  | -- |  | 14.3 |  | 475 |  | 87.5 |  | 562.5
2007 |  | 3 | 176.9 |  | -- |  | 14.3 |  | 191.2 |  | 53.1 |  | 244.3
2008 |  | 13 | 775.9 |  | -- |  | 17.5 |  | 793.4 |  | 40.9 |  | 834.3
2009 |  | 2 | 103.2 |  | -- |  | 3 |  | 106.2 |  | 38.6 |  | 144.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | 1 | 69.6 |  | -- |  | 1.9 |  | 71.5 |  | 14.7 |  | 86.2
2013 |  | 3 | 222.5 |  | -- |  | -- |  | 222.5 |  | 2.7 |  | 225.2
2014 |  | 1 | 87.5 |  | -- |  | 2 |  | 89.5 |  | 19.8 |  | 109.3
2015 |  | 1 | 53.5 |  | -- |  | 2 |  | 55.5 |  | 37.1 |  | 92.6
2016 |  | 2 | 149.8 |  | -- |  | 4 |  | 153.8 |  | 59.7 |  | 213.5
2017 |  | 2 | 134.6 |  | -- |  | 13.9 |  | 148.5 |  | 7.2 |  | 155.7
2018 |  | 2 | 138.2 |  | -- |  | 16.2 |  | 154.4 |  | 10.5 |  | 164.9
2019 |  | 2 | 170 |  | -- |  | 4.3 |  | 174.3 |  | 39.6 |  | 213.9
2020 |  | 2 | 174.4 |  | -- |  | 4.4 |  | 178.8 |  | 36.2 |  | 215
2021 |  | 2 | 179.8 |  | -- |  | 4.5 |  | 184.3 |  | 64 |  | 248.3
2022 |  | 2 | 252.9 |  | -- |  | 4.6 |  | 257.5 |  | 29.8 |  | 287.3
2023 |  | 7 | 665.8 |  | -- |  | 16.3 |  | 682.1 |  | 110.9 |  | 793
2024 |  | 7 | 684.9 |  | -- |  | 16.6 |  | 701.5 |  | 113 |  | 814.5
2025 |  | 7 | 704.5 |  | -- |  | 17 |  | 721.5 |  | 71.9 |  | 793.4
2026 |  | 7 | 724.6 |  | -- |  | 17.3 |  | 741.9 |  | 73.4 |  | 815.3
2027 |  | 7 | 670.4 |  | -- |  | 17.7 |  | 688.1 |  | 68 |  | 756.1
2028 |  | 2 | 188.5 |  | -- |  | 5.1 |  | 193.6 |  | 26.5 |  | 220.1
Subtotal |  | 104 | 8181.1 |  | -- |  | 198.1 |  | 8379.2 |  | 1340.4 |  | 9719.6

## Table 19
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1997 |  | 3 | 199.2 |  | -- |  | -- |  | 199.2 |  | 47.6 |  | 246.8
1998 |  | 2 | 133.3 |  | -- |  | -- |  | 133.3 |  | 8.6 |  | 141.9
1999 |  | 2 | 127.9 |  | -- |  | -- |  | 127.9 |  | 4.9 |  | 132.8
2000 |  | 1 | 73.5 |  | -- |  | 1.4 |  | 74.9 |  | 9.1 |  | 84
2001 |  | 3 | 228.3 |  | -- |  | -- |  | 228.3 |  | 62.4 |  | 290.7
2002 |  | 2 | 159.1 |  | -- |  | -- |  | 159.1 |  | 34.9 |  | 194
2003 |  | 4 | 321.3 |  | -- |  | -- |  | 321.3 |  | 50.9 |  | 372.2
2004 |  | -- | 47.1 |  | -- |  | -- |  | 47.1 |  | 105.4 |  | 152.5
2005 |  | 4 | 309.7 |  | -- |  | -- |  | 309.7 |  | 56.3 |  | 366
2006 |  | 8 | 479.5 |  | -- |  | 14.9 |  | 494.4 |  | 91.1 |  | 585.5
2007 |  | 3 | 179.9 |  | -- |  | 14.5 |  | 194.4 |  | 54.1 |  | 248.5
2008 |  | 13 | 777.5 |  | -- |  | 17.5 |  | 795 |  | 41 |  | 836
2009 |  | 2 | 102 |  | -- |  | 3 |  | 105 |  | 38.1 |  | 143.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | 1 | 65.1 |  | -- |  | 1.8 |  | 66.9 |  | 13.8 |  | 80.7
2013 |  | 3 | 206 |  | -- |  | -- |  | 206 |  | 2.5 |  | 208.5
2014 |  | 1 | 80 |  | -- |  | 1.8 |  | 81.8 |  | 18.1 |  | 99.9
2015 |  | 1 | 48.2 |  | -- |  | 1.8 |  | 50 |  | 33.4 |  | 83.4
2016 |  | 2 | 132.6 |  | -- |  | 3.5 |  | 136.1 |  | 52.9 |  | 189
2017 |  | 2 | 116.9 |  | -- |  | 12.1 |  | 129 |  | 6.2 |  | 135.2
2018 |  | 2 | 117.7 |  | -- |  | 13.8 |  | 131.5 |  | 9 |  | 140.5
2019 |  | 2 | 142 |  | -- |  | 3.6 |  | 145.6 |  | 33 |  | 178.6
2020 |  | 2 | 142.8 |  | -- |  | 3.6 |  | 146.4 |  | 29.6 |  | 176
2021 |  | 2 | 144.3 |  | -- |  | 3.6 |  | 147.9 |  | 51.4 |  | 199.3
2022 |  | 2 | 199 |  | -- |  | 3.6 |  | 202.6 |  | 23.5 |  | 226.1
2023 |  | 7 | 513.7 |  | -- |  | 12.6 |  | 526.3 |  | 85.6 |  | 611.9
2024 |  | 7 | 518.1 |  | -- |  | 12.6 |  | 530.7 |  | 85.4 |  | 616.1
2025 |  | 7 | 522.5 |  | -- |  | 12.6 |  | 535.1 |  | 53.3 |  | 588.4
2026 |  | 7 | 526.8 |  | -- |  | 12.6 |  | 539.4 |  | 53.4 |  | 592.8
2027 |  | 7 | 477.9 |  | -- |  | 12.6 |  | 490.5 |  | 48.5 |  | 539
2028 |  | 2 | 131.7 |  | -- |  | 3.6 |  | 135.3 |  | 18.5 |  | 153.8
Subtotal |  | 104 | 7223.6 |  | -- |  | 167.1 |  | 7390.7 |  | 1222.5 |  | 8613.2

## Table 20
Cost Quantity Information 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2010 $M
1997 | 3 | 199.2
1998 | 2 | 133.3
1999 | 2 | 128
2000 | 1 | 73.5
2001 | 3 | 228.3
2002 | 2 | 159.1
2003 | 4 | 313.9
2004 | -- | --
2005 | 4 | 309.9
2006 | 8 | 483.4
2007 | 3 | 181.6
2008 | 13 | 793.7
2009 | 2 | 132
2010 | -- | --
2011 | -- | --
2012 | 1 | 67.3
2013 | 3 | 186.3
2014 | 1 | 70.2
2015 | 1 | 51.9
2016 | 2 | 125.8
2017 | 2 | 124.3
2018 | 2 | 121.3
2019 | 2 | 141.9
2020 | 2 | 143.1
2021 | 2 | 144.3
2022 | 2 | 145.6
2023 | 7 | 513.7
2024 | 7 | 518.1
2025 | 7 | 522.5
2026 | 7 | 526.9
2027 | 7 | 531.3
2028 | 2 | 153.2
Subtotal | 104 | 7223.6

## Table 21
Annual Funding 0350 ¦ Procurement ¦ National Guard and Reserve Equipment ,Defense
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | 34.3 |  | 34.3
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | 34.3 |  | 34.3

## Table 22
Annual Funding 0350 ¦ Procurement ¦ National Guard and Reserve Equipment ,Defense
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | 31.7 |  | 31.7
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | 31.7 |  | 31.7

## Table 23
Low Rate Initial Production
There is no LRIP for this program.

## Table 24
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Kuwait | 2014-08-11 |  | 49.2 | FMS Case KU-P-GGY, Kuwait KC-130J integrated logistics support and aircraft sustainment (follow-on case to provide support upon depletion of KU-P- SBF funds)
Kuwait | 2014-03-11 |  | 47.9 | FMS Case KU-P-GGU, Kuwait KC-130J and L-100 engine and propeller support
Kuwait | 2010-05-04 | 3 | 569.6 | FMS Case KU-P-SBF, three aircraft were procured through the Air Force production contract and deliveries were completed in FY 2014. This case includes the procurement of the three delivered KC- 130Js, a training facility, one weapons system trainer, and operation and sustainment support.
Notes
Nuclear Costs
None

## Table 25
Unit Cost
Unit Cost Report
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
|  | Current UCR Baseline (Feb 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 9233.9 |  |  | 8683
Quantity | 104 |  |  | 104
Unit Cost | 88.788 |  |  | 83.49 |  | -5.97
Average Procurement Unit Cost
Cost | 9198.3 |  |  | 8644.9
Quantity | 104 |  |  | 104
Unit Cost | 88.445 |  |  | 83.124 |  | -6.02
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
|  | Original UCR Baseline (Feb 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 9233.9 |  |  | 8683
Quantity | 104 |  |  | 104
Unit Cost | 88.788 |  |  | 83.49 |  | -5.97
Average Procurement Unit Cost
Cost | 9198.3 |  |  | 8644.9
Quantity | 104 |  |  | 104
Unit Cost | 88.445 |  |  | 83.124 |  | -6.02

## Table 26
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2010 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Feb 2011 |  |  |  |  | 88.788 |  |  | 88.445 |  |  | 95.017 |  |  | 94.676
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Current APB |  |  | Feb 2011 |  |  |  |  | 88.788 |  |  | 88.445 |  |  | 95.017 |  |  | 94.676
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 84.969 |  |  | 84.603 |  |  | 95.19 |  |  | 94.827
Current Estimate |  |  | Dec 2015 |  |  |  |  | 83.49 |  |  | 83.124 |  |  | 94.151 |  |  | 93.788
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Production Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
95.017 1.167 0.000 8.150 2.337 -12.099 0.000 -0.421 -0.866 94.151
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Production Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
94.676 1.169 0.000 8.150 2.337 -12.123 0.000 -0.421 -0.888 93.788

## Table 27
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | N/A | N/A | N/A
Milestone III | N/A | N/A | Jun 1996 | Jun 1996
IOC | N/A | N/A | Feb 2005 | Feb 2005
Total Cost (TY $M) | N/A | N/A | 9881.8 | 9791.7
Total Quantity | N/A | N/A | 104 | 104
PAUC | N/A | N/A | 95.017 | 94.151

## Table 28
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 35.5 | 9846.3 | -- | 9881.8
Previous Changes
Economic | -0.2 | 172.6 | -- | 172.4
Quantity | -- | -- | -- | --
Schedule | -- | 659.8 | -- | 659.8
Engineering | -- | 233.2 | -- | 233.2
Estimating | 2.5 | -916.1 | -- | -913.6
Other | -- | -- | -- | --
Support | -- | -133.8 | -- | -133.8
Subtotal | 2.3 | 15.7 | -- | 18
Current Changes
Economic | -- | -51 | -- | -51
Quantity | -- | -- | -- | --
Schedule | -- | 187.8 | -- | 187.8
Engineering | -- | 9.8 | -- | 9.8
Estimating | -- | -344.7 | -- | -344.7
Other | -- | -- | -- | --
Support | -- | 90 | -- | 90
Subtotal | -- | -108.1 | -- | -108.1
Total Changes | 2.3 | -92.4 | -- | -90.1
CE - Cost Variance | 37.8 | 9753.9 | -- | 9791.7
CE - Cost & Funding | 37.8 | 9753.9 | -- | 9791.7

## Table 29
Summary BY 2010 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 35.6 | 9198.3 | -- | 9233.9
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | 299.8 | -- | 299.8
Engineering | -- | 168.6 | -- | 168.6
Estimating | 2.5 | -745.5 | -- | -743
Other | -- | -- | -- | --
Support | -- | -122.5 | -- | -122.5
Subtotal | 2.5 | -399.6 | -- | -397.1
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | 39.1 | -- | 39.1
Engineering | -- | 8.5 | -- | 8.5
Estimating | -- | -263.5 | -- | -263.5
Other | -- | -- | -- | --
Support | -- | 62.1 | -- | 62.1
Subtotal | -- | -153.8 | -- | -153.8
Total Changes | 2.5 | -553.4 | -- | -550.9
CE - Cost Variance | 38.1 | 8644.9 | -- | 8683
CE - Cost & Funding | 38.1 | 8644.9 | -- | 8683
Previous Estimate: December 2014

## Table 30
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -51
Adjustment for current and prior escalation. (Estimating) | 2.5 | 3
Revised estimate to reflect the application of new outyear inflation indices. (Estimating) | 36.8 | 47.2
Stretch-out of the procurement buy profile from FY 2026 to FY 2028. (Schedule) | 0 | 119.2
Additional Schedule Variance resulting from a stretch-out of the procurement profile. | 39.1 | 68.6
(Schedule)
Incorporation of Non-Recurring Engineering for production line cut-in of Large Aircraft Infrared Countermeasures. (Engineering)
Re-phasing of Non-Recurring Engineering for production line cut-in of Block Upgrades. (Estimating)
+8.5 +9.8
+0.2 0.0
Revised estimate for prior year actuals. (Estimating) -6.0 -6.5
Reduced Airframe prices to reflect awarded costs for Multi-Year Procurement (MYP) contract. (Estimating)
Reduced projected Airframe prices in future years to reflect known MYP awarded values through FY 2018. (Estimating)
-38.3 -43.8
-258.7 -344.6
Adjustment for current and prior escalation. (Support) +0.8 +0.6
Increase in Other Support due to program stretch-out, additional Peculiar Ground Support Equipment needed for site standup, and updated Trainer estimates. (Support)
Decrease in Initial Spares due to revised cost estimate and an increase due to program stretch-out. (Support)
+64.2 +86.8
-2.9 +2.6
Procurement Subtotal -153.8 -108.1

## Table 31
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: Systems Engineering and Logistics Support Sustainment (SELSS)
Contractor: Lockheed Martin Corporation
Contractor Location: 86 South Cobb Drive
Marietta, GA 30060
Contract Number: N00019-14-D-0006/1
Contract Type: Firm Fixed Price (FFP)
Award Date: December 26, 2013
Definitization Date: December 26, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
49.3 N/A 0 64.0 N/A 0 64.0 64.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract modifications to meet added fleet requirements for engineering services, spare parts, and support equipment.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 32
Contract Identification
Appropriation: Procurement
Contract Name: Multi-Year Procurement (MYP) II Contract
Contractor: Lockheed Martin Corporation
Contractor Location: 86 South Cobb Drive
Marietta, GA 30060
Contract Number: FA8625-14-C-6450/1
Contract Type: Fixed Price Incentive(Firm Target) (FPIF), Firm Fixed Price (FFP)
Award Date: December 09, 2013
Definitization Date: December 30, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
19.0 0.0 0 152.3 155.3 2 399.2 399.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a contract modification for the procurement of two KC-130J aircraft and advance procurement funding for an FY 2016 aircraft.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF/FFP) contract.
General Contract Variance Explanation
The U.S. Navy does not report cost and schedule variance on this contract because the U.S. Air Force (USAF) manages the contract.
Notes
In the December 2014 SAR, the initial contract price target was $408.0M for six aircraft and the current contract price target was $552.6M for eight aircraft. These values were based on the anticipated contract targets and quantities and were entered in error. This SAR corrects those values so that the initial contract target price equals $18.964M, which is the base contract award value awarded on December 9, 2013, for advance procurement funding for two USMC aircraft (one FY 2014 and one FY 2015) only. The current contract price target is now $152.345M, which is based on the value of the contract modification awarded on December 30, 2015, for the FY 2014 and FY 2015 aircraft, as well as advance procurement funding for one FY 2016 USMC aircraft. The CLIN for the contract modification is fixed-price-incentive-fee; therefore, the current contract price ceiling is $155.308M. The estimated price at completion is $399.223M, which is the estimated contract value for six aircraft plus fee.
Aircraft deliveries are scheduled to begin in FY 2016.

## Table 33
Contract Identification
Appropriation: Procurement
Contract Name: C-130J Five-Year Option Contract IV
Contractor: Lockheed Martin Corporation
Contractor Location: 86 South Cobb Drive
Marietta, GA 30060
Contract Number: FA8625-11-C-6597
Contract Type: Firm Fixed Price (FFP)
Award Date: March 16, 2011
Definitization Date: March 16, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
70.0 N/A 1 269.7 N/A 4 269.7 269.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a contract modification for the procurement of the three FY 2013 Congressionally-added aircraft, engineering change proposals, and efforts to mitigate diminishing manufacturing sources.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This report corrects previous administrative errors.
In the December 2012 SAR, the initial contract target price was $121.9M for two aircraft.
In the December 2013 SAR, the initial contract target price was reduced to $71.2M for one aircraft, which was based on the exclusion of the U.S. Coast Guard aircraft that was also procured on this contract.
In the December 2014 SAR, the initial contract target price and current contract target price were $269.3M for four aircraft. These values were based on the anticipated contract targets and quantities.
In this SAR, the initial contract target price equals $69.980M, which is the value of the contract modification awarded on October 23, 2012, for one FY 2012 USMC aircraft only. The current contract price target is now $269.7M, which is based on the contract modification that occurred on December 30, 2015.
The first aircraft acquired on this contract was delivered in March 2015; the remaining aircraft deliveries are scheduled to occur during CY 2016.

## Table 34
Contract Identification
Appropriation: Procurement
Contract Name: Mission Care II
Contractor: Rolls-Royce Corporation
Contractor Location: 2355 South Tibbs Avenue
Indianapolis, IN 46241
Contract Number: N00019-14-D-0028/1
Contract Type: Firm Fixed Price (FFP)
Award Date: March 24, 2014
Definitization Date: March 24, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
52.7 N/A 0 57.7 N/A 0 57.7 57.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to pricing of CLINs that were not priced at original contract award.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 35
Contract Identification
Appropriation: Procurement
Contract Name: Mission Care III
Contractor: Rolls-Royce Corporation
Contractor Location: 2355 South Tibbs Avenue
Indianapolis, IN 46241
Contract Number: N00019-15-D-0009/1
Contract Type: Firm Fixed Price (FFP), Cost Plus Fixed Fee (CPFF), Indefinite Delivery Indefinite Quantity (IDIQ)
Award Date: March 24, 2015
Definitization Date: March 24, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
59.5 N/A 0 59.5 N/A 0 124.0 124.0
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP/CPFF/IDIQ) contract.
Notes
This is the first time this contract is being reported.

## Table 36
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 48 | 48 | 104 | 46.15%
Total Program Quantity Delivered | 48 | 48 | 104 | 46.15%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
9791.7
3780.5
38.61%
32
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
20
62.5%
4314.2
44.06%
The above data is current as of February 09, 2016.

## Table 37
Operating and Support Cost
Cost Estimate Details
Date of Estimate: February 25, 2016
Source of Estimate: POE
Quantity to Sustain: 104
Unit of Measure: Aircraft
Service Life per Unit: 40.00 Years
Fiscal Years in Service: FY 2001 - FY 2069
This is the fifth update for the KC-130J O&S cost estimate since the Navy SCP was established in 2010. Naval Visibility and Management of Operating and Support Costs (VAMOSC) data from FY 2001 through FY 2014 was used to establish the KC-130J baseline. Projections based on the historical costs in VAMOSC provide the majority of the out-year estimates. A phased approach estimate includes the ramp-up of aircraft as they are introduced to the fleet through the retirement of the KC-130J aircraft from service with a total aircraft procurement of 104 (maximum Program Aircraft Authorized (PAA) of 94).
Sustainment Strategy
The KC-130J Sustainment Strategy is based upon four key pillars. The first pillar concerns the KC-130J Depot Source of Repair. The Aviation Logistics Command (ALC) located at Hill Air Force Base (AFB), Ogden, UT, is the primary depot- level maintenance facility for the aircraft. Through a competitively awarded contract, Aircraft Inspection, Repair, and Overhaul Depot, located in Kuala Lumpur, Malaysia, is the depot-level maintenance facility to support aircraft located in Iwakuni, Japan, as well as a back-up facility for Hill AFB, UT. Completed core logistics and level-of-repair analyses favor this approach. Industrial capabilities are sufficient to provide comprehensive support at all levels.
The second pillar is the use of commercial sustainment contracts to help support the KC-130J airframe and propulsion systems. Support of fielded aircraft is currently accomplished through two sole-source Naval Air Systems Command sustainment contracts. The airframe sustainment contract is with Lockheed Martin Aero and the propulsion contract is with Rolls-Royce Corporation, Indianapolis, IN. Both original equipment manufacturers assert restrictions on the government's right to use and release their proprietary technical data due to the commercial origin of their products. PMA
-207 continues to conduct research and exchanges with knowledgeable individuals in the U.S. Government and industry regarding market capabilities to meet KC-130J requirements. If new sources are discovered, appropriate reviews will be conducted as necessary to promote competition to the maximum extent practicable.
The third pillar involves KC-130J peculiar component support for 218 repairable and 505 consumable items maintained under an Interim Spares Support program. This support is currently managed by the Program Office and Naval Supply Systems Command (NAVSUP) Weapon System Support (WSS) and encompasses the management of products, supply chain, inventory, material movement, and warehousing until Material Support Date, scheduled for October
1, 2016, when all management will be transitioned to NAVSUP WSS.
The last pillar involves KC-130J common component support. This support is provided through the normal military supply system that includes NAVSUP WSS, U.S. Air Force (USAF) ALCs, and Defense Logistics Agency.
Antecedent Information
The antecedent systems are the KC-130F, KC-130R, and C/KC-130T aircraft. The KC-130F and KC-130R were used in a blended analysis to compare to the KC-130J. C/KC-130T reserve squadron aircraft data is not included in the Antecedent Average Annual Cost per Aircraft, and it should be noted that the KC-130F/R models were in ramp-down phase during the time that data was available. Additionally, both the KC-130F and KC-130R were ACAT II programs that

## Table 38
relied heavily on USAF program sustainment. KC-130J aircraft will replace the KC-130F, KC-130R, and C/KC-130T aircraft one-for-one.
The capture of O&S data in available reporting systems has changed significantly over time. Antecedent systems began their service life before continuous, reliable recording systems were available. VAMOSC provides costs for FY 1997 to present. The cost data for platforms in existence prior to 1997 is either unavailable or incomplete. In summary, sufficient historical data and resources do not exist to create a credible comparison of Total O&S Costs.
A data pull from the VAMOSC Aircraft Type Model Series Report was made in January 2014 to obtain Maintenance, Sustaining Support, and Continuing System Improvements cost data. The steady state average of this data from 1999 to 2001 was used. The VAMOSC total aircraft number for these years was 47, 48, and 48, respectively. The Unit Level Manpower and Indirect Support costs were assumed to be the same as for the KC-130J. The Unit Operations costs were calculated using December 2012 Cost Adjustment and Visibility Tracking System data from 1995 to 2009 to obtain the fuel consumption ratio of the antecedent aircraft to the KC-130J. The antecedent average annual cost was then multiplied by the KC-130J total operating aircraft years to find the total BY antecedent cost.
For comparison purposes, the BY Antecedent Total O&S Cost is the product of the Antecedent's Average Annual Cost per Aircraft and the Operational Aircraft Years of the KC-130J.
Annual O&S Costs BY2010 $M
Cost Element |  | KC-130J Average Annual Cost Per Aircraft |  |  |  | KC-130 F/R/T (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower |  | 2.108 |  |  |  | 2.108
Unit Operations |  | 1.618 |  |  |  | 1.311
Maintenance |  | 3.637 |  |  |  | 1.869
Sustaining Support |  | 0.284 |  |  |  | 0.124
Continuing System Improvements |  | 0.437 |  |  |  | 0.293
Indirect Support |  | 0.863 |  |  |  | 0.863
Other |  | -- |  |  |  | --
Total |  | 8.947 |  |  |  | 6.568
.
Item | Total O&S Cost $M
| KC-130J | [5 empty] | KC-130 F/R/T (Antecedent)
| Current Production APB Objective/Threshold |  |  | Current Estimate
Base Year | 43344.2 |  | 47678.6 |  | 34974.1 |  | 25676
Then Year | 77520.4 |  | N/A |  | 62411.2 |  | N/A
Equation to Translate Annual Cost to Total Cost
The Average Annual Cost per Aircraft for the KC-130J is calculated by dividing the Total O&S Cost by the Total Operational Aircraft Years for the program. Total Operational Aircraft Years is 3,909 years. $34,974.1M / 3,909 years =
$8.947M/year.
The Total Operational Aircraft Years is calculated by summing the annual total active aircraft constrained by the maximum PAA excluding the test wing aircraft (93 aircraft maximum). The primary input for this is the Aircraft Program Data File produced by Office of the Chief of Naval Operations (N98).

## Table 39
O&S Cost Variance
Category | BY 2010 $M | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
36083.6
Programmatic/Planning Factors -564.1 Updated procurement schedule, reduced flying hours, and
updated aircraft procurement modification costs per FY 2017 PB
Cost Estimating Methodology -1255.8 Updated from a static three-year average to a rolling five-
year average of Aviation Depot-Level Repairable (AVDLR) costs, and updated Reserve service calculations
Cost Data Update 561.1 Updated historical cost information to include FY 2014 actuals, indirect rates, and preventative maintenance interval costs
Labor Rate 19.0 Updated to 2016 military pay rates
Energy Rate 130.3 Updated cost per gallon for fuel Technical Input 0.0
Other 0.0
Total Changes -1109.5
Current Estimate 34974.1
The three primary drivers to the variance are the updates to the methodology in estimating AVDLR and Aviation Fleet Maintenance costs, the programmatic changes resulting from the FY 2017 PB procurement schedule, and the reduction of flying hours in the FYDP. In FY 2021 alone, a reduction of 13,000 budgeted flying hours from the previous estimate is projected.
Disposal Estimate Details
Date of Estimate: January 16, 2015
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2010 $M): Total costs for disposal of all Aircraft are 25.0
This rough order of magnitude estimate will be refined as the System Disposal Plan Annex to the Life Cycle Sustainment Plan is developed.